IRAT Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Improving Rural Access in Tanzania
Programme Value: £25m		Review Date: 7th Feb 2015
Programme Code:	Start Date: 7th Feb ‘14	End Date: 6th Feb 2018

Summary of Programme Performance
Year	2014/15
Programme Score	B
Risk Rating	M

Summary of progress and lessons learnt since last review
The project is making a substantial and direct impact to the intended beneficiaries at a lower cost than alternative intervention methods so it was the opinion of the review team that the project should broadly be scoring an A. The log-frame scoring, however, results in overall output score of B, partly due to the later than expected commencement of the long-term Technical Assistance (TA) in September 2014 and partly due to ambitious targets set in the log-frame which in many cases will be revised.
The primary task of providing all weather access has progressed well in the first phase, (albeit with some delays), and design on the second phase bottlenecks is underway. The secondary elements of work led by the TA such as incorporating road safety and the effects of climate change are still at the inception phase and from the review team’s discussions with PMO-RALG it does not seem that they were well informed of them. There has been good progress on coding the District Road Management System, DROMAS, however considerable more capacity building is required for it to be operational, which is a concern as there is potential for a significant delay leading to reduced outputs. A draft inception report for the evaluating the outcomes and impacts of the project has been submitted but actual data collection in order to set a baseline has not started.
The delivery method through LGA’s is an effective and good value way to deliver local infrastructure which has an immediate impact on beneficiaries. The delivery route promotes local ownership and leverages the skills and local knowledge available in the LGA which would not be possible through a project based approach. The central administration of local government is a key interlocutor providing a degree of oversight and project preparation for the next phase, (roles which both need to be strengthened). See the next section for further information on key lessons learnt.

Summary of recommendations for the next year (see key actions in section B for further points)
- Most of the log-frame milestones and some of the indicators should be review based on the detailed findings of section C below to ensure they are not overly ambitious and reflect the delayed TA start. Indicator 2.4 which covers cost-time-quality should replace indicator 1.2 so that it’s weighting increases from 3% to 20%.
- It is recommended that the method by which the phase II bottlenecks were selected be made clear and the TA team verify each site before the disbursement of phase II funds. As the Phase II projects are likely to be larger than phase I the capacity of the LGA’s to monitor the construction with internal staff is questionable and consideration should be given to requiring the LGA’s to procure local consultants to carry out supervision.
- PMO-RALG and the TA inspections of the construction and contract management need to be more rigorous with a system developed to verify the work carried out against that in the contract and to check the implementation technical recommendations made during site visits
- It is recommended that an ongoing concerted effort is made to ensure the District Road Management System (DROMAS) is effectively operationalised by the districts
- It is recommended that the TA scope of works with respect to procurement support is reviewed and options to support the LGA procurement process are discussed with PMO-RALG
- DFID should consider the proposed changes to the outcome and impact indicators in the evaluation inception report and review the outcome indicators and milestone highlighted in this review. PMO-RALG and RFB should be more engaged with the evaluation to ensure that the evaluation design is finalised and data collection begins in the first half of 2015.
- If the application for additional ICF funding is successful, further result reporting will need to incorporated into the ongoing programmed
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4388107.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4170457.docx

Outline of the programme
 The UK is providing £25 million over 4 years to help improve rural access in Tanzania. £22.2 million will be spent on repairing and improving rural roads and £2.8 million will be spent on helping to improve value for money, manage fiduciary risk and to maximise the impact of rural roads in Tanzania. This includes funding for a full impact evaluation. The project started in February 2014 and is due to end in early 2018. The impact evaluation will continue until 2020.
The programme is delivered through the Tanzania Roads Fund Board, the Prime Minister’s Office for Regional and Local Government (PMO-RALG) and Local Government Authorities. This approach uses existing, functioning delivery mechanisms to help build capacity, deliver value for money and reduce transaction costs. Support to build capacity and manage fiduciary risks is provided by Cardno, an independently contracted technical assistance consultancy.
The first year’s investment is focused on removing 36 of the most economically important bottlenecks on the network. These have been carefully selected as part of a World Bank funded bottleneck study[1]. These 36 bottlenecks will cost approximate £6.5 million and repairing these will improve access in 15 Districts. The population of these wards adds up to just over 1.5 million - an estimated 300,000 households. The first disbursement was made in June 2014 totalling £4.59m. A further £2.05m disbursement is due to be released imminently.
PMO-RALG is proceeding with project selection and design for the second year’s investment which should be rolled out in the second quarter of 2015.
The project aims to incorporate the impact of climate change on rural road planning, engineering, maintenance and funding mechanisms. In Dec 2014 Cardno produced a report titled Guidelines for Regional Climate Change Adaptation that is hoped will culminate in the development of a practicable climate change strategy for PMO-RALG to adapt to the changing climate effects in Tanzania. Additional funding is being sought from the International Climate fund to extend the IRAT programme in recognition of both the impact climate change is having on rural roads and more importantly the additional resilience that a community has to climate change when all weather road access is provided.
A key component of the project is developing and operationalising DROMAS, the District Road Management System, which is a GIS based database of the road network including planning, reporting and cost management between PMO-RALG and the Local authorities.
On rural road safety Cardno is producing a guidance note for local government authorities to use on safe design which is expected to be ready by May 2015 for incorporation into national guidelines.
Summary of expected results:
- The investment will contribute to raising incomes of 125,000 rural households by 2018. The programme will raise the equivalent of 2,100 km of earth roads to all weather, climate resilient standards.
- The expected impact of this intervention is to raise household incomes in rural Tanzania and the main expected outcome is a reduction in transport costs as access to markets is improved.

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The project target outcome is reduced transport costs and increased distances travelled for both passengers and freight. For the phase 1 bottlenecks that have been completed this target is likely to be achieved; particularly in the rainy season as most of the bottleneck roads were impassable before the interventions were completed providing all weather access. The IRAT review team interviewed beneficiaries in both Kondoa and Babati regions, including village residents, village Chairmen, ward councillors and the district administration. The response from all beneficiaries was overwhelmingly positive, with a repeated assertion that the road works will improve access to markets, basic services and participation in local governance. The District Chairman of Babati asserted that the works to date had already halved the cost of travel from the intervention site to the town.

Nevertheless, systematic evidence to prove the reduction of cost across all the bottlenecks has not been captured as the long-term technical assistance was not in place early enough to establish a baseline and have not had the opportunity to re-visit and interview beneficiaries at the sites since they were completed. The programme TA plan to establish a traffic baseline for the phase 2 interventions in April 2015, with the independent evaluation team (led by ITAD) collecting a broader baseline through household survey in May/June 2015. This will enable more robust data to be collected for the next phase of interventions.

However the project evaluators and technical assistance team have expressed concern that the outcome and impact indicator will be difficult to systematically measure and interpret and may not adequately capture the ultimate benefits of the project and have therefore proposed revised outcome and impact indicators for DFID to consider.

PMO-RALG identified the biggest challenges they face as a lack of capacity to monitor the construction works and the need to operationalise the DROMAS system. The review team were broadly in agreement with this whilst also raising a number of other areas of concern described in more detail below and in the report.

Overall output score and description (Italics repeated from summary above)
The project is making a substantial and direct impact to the intended beneficiaries at a lower cost than alternative intervention methods so it was the opinion of the review team that the project should broadly be scoring an A. The log-frame scoring, however, results in overall output score of B, partly due to the later than expected commencement of the long-term Technical Assistance (TA) in September 2014 and partly due to ambitious targets set in the log-frame which in many cases will be revised.

The main output of providing all weather access through bottleneck removal has progressed well in the first phase, (albeit with some delays), and design on the second phase bottlenecks is underway. The secondary elements led by the TA such as incorporating road safety and the effects of climate change are still at the inception phase and from the review team’s discussions with PMO-RALG it does not seem that they were well informed of them. Milestones for the second output of institution and capacity strengthening have generally not been achieved and it is likely that the log-frame will need to be revised to give viable second year milestones. There has been progress on updating the District Road Management System, DROMAS, however considerable more capacity building is required for it to be operational, which is a concern as there is potential for a significant delay leading to reduced outputs.

Little progress has been made by the TA and evaluation team so far on data collection and setting a baseline for the monitoring and evaluation elements required under the third output.

Key lessons (Italics repeated from summary above)
The delivery method through LGA’s is judged to be an effective and good value way to deliver local infrastructure which has an immediate impact on beneficiaries. The delivery route promotes local ownership and leverages the skills and local knowledge available in the LGA which would not be possible through a project based approach. The central administration of local government is a key interlocutor providing a degree of oversight and project preparation for the next phase, (roles which both need to be strengthened).

A key observation is that there are few Log-frame indicators that reflect the time, cost, quality element of implementing the main bottleneck works which count for 90% of the cost whereas there are several quite ambitious indicators covering the value added elements of climate change adaptation and road safety which account for the remaining 10% of the cost. As a result even though the main works have made substantial progress, the delayed start of the long-term TA (see section F on project partners) has been strongly reflected in lower logframe results. It is recommended that the indicators are reviewed based on the recommendation below and in section C to sharpen the focus on value for money.

In general the review team felt there needed to be a stronger oversight of LGA’s financial and technical functions, and where possible also the procurement and contract management functions. Currently oversight is largely the responsibility of the Regional Engineer and PMO-RALG’s Infrastructure Development Unit (IDU) however PMO-RALG identified that systematic construction and procurement monitoring was a weakness which was confirmed by the review team during field visits. (See box under section E).

Key actions
1. Most of the log-frame milestones and some of the indicators should be review based on the detailed findings of section C below. It is recommended that output indicators 1.1 and 1.2 which measure length of improved road be combined as there is currently very little distinction between them. It is recommended that log-frame indicator 2.4 that measures quality of completed work and currently has a 3% weighting replace the merged indicator 1.2 where it would receive a 20% weighting.
2. Indicator 1.1 – It is recommended that the method by which the phase II bottlenecks were selected be made clear and the TA team verify each selected site before the disbursement of phase II funds. As the Phase II projects are likely to be larger than phase I the capacity of the LGA’s to monitor the construction with internal staff is questionable and consideration should be given to requiring the LGA’s to procure local consultants to carry out supervision.
3. It is recommended that DFID and the TA team closely monitor the LGA process of compiling the phase II tender packages which was previously carried out by the World Bank for phase 1, as there is significant potential for delay due to lack of capacity in the LGA’s.
4. PMO-RALG and the TA inspections of the construction and contract management need to be more rigorous with a system developed to verify the work carried out against that in the contract and to check the implementation technical recommendations made during site visits. (See box under section E on Risk)
5. Indicator 2.1: It is recommended that a concerted effort is made to ensure the District Road Management System (DROMAS) implementation is effective and the log-frame is amended to reflect the slower than expected progress to date. While DROMAS is not operational an alternative method needs to be found to capture and analyse cost, quality, and time data.
6. Indicator 2.3. It is recommended that the TA scope of works with respect to procurement support to PMO-RALG and LGA’s is fully implemented and that options to support the LGA procurement process in particular are discussed with PMO-RALG (see section on commercial considerations) The indicator and milestones should also be reviewed. It is suggested that the TA carry out a cost comparison exercise against alternative methods of procurement to help verify value for money.
7. Indicator 2.5: It is recommended TA produce the environmental action plan and carry out the compliance assessment from which a method for monitoring environmental impact is devised accordingly.
8. Indicator 3.1 DFID should consider and respond to the proposed changes to the outcome and impact indicators in the evaluation inception report. It is unclear the extent to which PMO-RALG and RFB are engaged with the evaluation, and it will be vital to ensure that as the design is finalised and data collection begins, both the TA and ITAD engage PMO-RALG and the RFB to ensure both full cooperation and uptake of results at all levels.
9. If the application for additional ICF funding is successful, further result reporting will need to be incorporated into the ongoing programmed.
10. PMO-RALG need to provide an asset register for these items transferred to them.

Has the logframe been updated since the last review? - No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	All weather climate resilient access provided and maintained for two wheel vehicles
Output number per LF		1	Output Score	B
Risk:		Low/Medium/High	Impact weighting (%):	80%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 - Total length (km) of LG roads with bottleneck improvements (cumulative) – condition from poor to fair/good	750	539
1.2 -Total length (km) of priority roads improved or upgraded in addition to bottleneck roads (cumulative) - condition from poor to fair/good	0	0
1.3 - Climate smart design developed and incorporated into planning, engineering and funding mechanism	Agreed with RFB and PMO-RALG	50% towards first milestone
1.4 - Number of districts with road safety programme designed and implemented including road safety features incorporated into rural roads standard designs	15	50% towards first milestone

Key Points: Substantial progress has been made on the bottleneck remedial works which directly achieve the output aim of providing all weather access. However some are in delay, usually blamed on rain holding up progress. The TA team have commenced work on promoting climate smart design and road safety improvements but this will not have an impact on the output aim for some time.
Indicator 1.1: It is likely that this milestone will be achieved by June 2015 (part way through the second year) when most of the first phase bottlenecks have been completed. Approximately 2/3 of the first phase funding has been released by DFID which corresponds closely level of progress on first year/phase 1 road improvements. 75 bottlenecks have been identified for Phase II and design work is underway by PMO-RALG’s consultant Unitec. From discussion with Unitec and PMO-RALG the team ascertained that the methodology for selection was based on the original prioritised list of 400 from which all the small works were removed and some additional bottleneck were added by PMO-RALG. As a result the phase II bottlenecks are all likely to be larger projects consisting of bridges of at least 15m in length and some up to 200m long. The TA has not been involved in the selection process and the criteria by which the small projects were removed and additional projects added was not clear. Selection and prioritisation is critical to philosophy of IRAT project and by selecting only large bottlenecks there is a danger of interventions being inappropriate. PMO-RALG agreed to send a note explaining how the projects were selected and TA and DFID review team agreed that the best way to verify the phase II projects would be for the TA team to visit each selected site, commencing as soon as possible.
Indicator 1.2: This indicator relates to additional roads the LGA’s are able to make operational based on the bottleneck removal approach. There is no milestone for this indicator in the first year and it is not clear that it is relevant in the second year.
Indicator 1.3: Implementation of indicators 1.3 and 1.4 have been delayed as the long-term TA did not start until September 2014. A climate guide has been produced with terms of reference and a strategic plan for implementing this indicator. The guide has been instrumental in enabling DFID to prepare an application for additional ICF funding for rural roads. It indicates that the formal climate adaptation guidelines will be developed over the course of 2015. The milestone of developing and agreeing climate smart design with PMO-RALG and RFB is therefore likely to be achieved at the end of the second year.
Indicator 1.4. Cardno are working to identify road safety issues national and LGA capacity. They are preparing motorcycle road safety guidelines for incorporation into LGA road design, due to be completed by mid-2015. The first milestone is therefore expected to be completed by the end of the second year of the programme.
Recommendations: Indicator 1.1 – It is recommended that the method by which the phase II bottlenecks were selected be made clear and the TA team verify each site before the disbursement of phase II funds. As the Phase II projects are likely to be larger than phase I the capacity of the LGA’s to monitor the construction with internal staff is questionable and consideration should be given to requiring the LGA’s to procure local consultants to carry out supervision.
Indicator 1.2 – It is suggested that indicator 1.2 be merged with indicator 1.1 and indicator 2.4 be moved to replace 1.2 to increase focus on value for money.
Indicator 1.3 and 1.4 – It is recommended that the log-frame is amended to reflect the late start on these elements of the work and the proposed method of implementation.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Institution and capacity strengthened at the central, regional and LGA level
Output number per LF		2	Output Score	C
Risk:		Low/Medium/High	Impact weighting (%):	15%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
2.1 No of districts operating DROMAS (District Road Management System)	15	40% towards first milestone
2.2 % decrease in unit cost of comparable interventions (economy measure indicative of capacity to drive improvements in value for money)	Unit cost structure established and data collection starts	Not started
2.3 % decrease in time to procure works at LGA level(efficiency measure indicative of capacity to drive improvements in value for money)	Time savings identified and plan prepared	Not started
2.4 % of works delivered on time, at cost and to specification (effectiveness measure indicative of ability to administer contracts and quality assure)	60%`	75%
2.5 District Engineers able to enforce national environmental legislation and incorporate environmental design in contracting	15	Not started

Key Points: Progress on institutional strengthen has been limited, partially due to the delayed start of the long-term TA affecting DROMAS implementation, but also due to uncertainty about how improved capacity in procurement and environmental best practice will be achieved.
2.1 Implementation of indicators 2.1-2.13 has been delayed as the long-term TA did not start until September 2014 and LGA’s have been slow to engage with DROMAS. The DROMAS system has been updated by the technical assistance and training was carried out in December 2014 for all engineers and technicians in Morogoro Region. Morogoro DC and Morogoro MC have populated their road data and 5 other districts in Morogoro region are in the process of completing the data upload. It is hoped that these districts will use DROMAS to submit their budget’s in June. PMO-RALG’s IT team did not have a good grasp of DROMAS were concern that it may not be effective; however the TA assured us that with additional discussions this reticence will be overcome. To achieve the first milestone 15 districts must upload their data and then start using the system operationally to submit and exchange information such as budgets and work plans with PMO-RALG. If a concerted effort is made this could achieved by June 2016.
2.2. The unit cost data necessary to measure this output is embedded in the returns the districts submit to PMO-RALG, however this data is not currently being captured although PMO-RALG expressed the intention to start collecting data as they had also received the same request from the Road Fund. For the data to be effectively recorded and analysed the DROMAS system needs to be operational as discussed above, which is likely to delay achieving the first milestone until the third year of the project.
2.3. The TA ToR’s includes a requirement to support PMO-RALG and the LGA’s in their procurement process, but their engagement so far has been exclusively with the technical departments so it is not clear whether the envisaged improvement in this indicator should be expected. The data required to measure this output is not currently being collected, and an action plan needs to be devised if it is to be done. The districts received training on the procurement cycle from PMO-RALG in January 2014, so it should be possible for all districts to start recording the time for procurement and gather previous data relatively easily. The sample check of Babati district council revealed shortcomings in the procurement discussed in under the section on commercial considerations. There is a potential role for additional TA support to try to improve the procurement process if an agreement can be reached with PMO-RALG and the LGA’s
2.4. Only four of the first phase bottlenecks have been fully completed, but from the data available Cardno reported that three of the four were completed on time and to budget. The late completion of the 4th was attributed to a delay in funds transfer. No independent verification or as-built drawings have been received. A number of other bottlenecks are in delay and some over-budget which would be reflected in future scores of this indicator.
2.5. District engineers receive environmental training from PMO-RALG, but as the works are considered to be maintenance there is no need to do an environmental impact assessment. There are environmental protection measures that need to be undertaken such as protecting water courses and re-instating borrow pits but these are not currently being monitored so it is difficult to record any progress against this indicator. The TA are contracted to carry out an action plan and compliance assessment by December 2014 which has not yet been received.

Recommendations
Indicator 2.1: It is recommended that a concerted effort is made to ensure DROMAS implementation is effective and the log-frame is amended to reflect the slower than expected progress to date.
Indicator 2.2: It is recommended that the log-frame is amended to reflect the reliance of DROMAS being functional before the data can be analysed for any fall in prices.
Indicator 2.3. It is recommended that the TA scope of works with respect to procurement support to PMO-RALG and LGA’s is fully implemented and that options to support the LGA procurement process in particular are discussed with PMO-RALG (see section on commercial considerations) The indicator and milestones should also be reviewed.
Indicator 2.4. Verification of completed works through site inspection and as-built drawings needs to be implemented by LGA’s and monitored by the Regional Engineer and TA.
Indicator 2.5. It is recommended TA produce the action plan and carry out the compliance assessment from which a method for monitoring environmental impact is devised and the milestones amended accordingly.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Impact evaluated, including on gender, health, education and poverty reduction
Output number per LF		3	Output Score	B
Risk:		Low/Medium/High	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Evaluation designed and implemented	Designed, agreed with PMO-RALG and RFB and baseline established	40% towards first milestone.

Key Points
The long term TA has submitted a draft monitoring and evaluation plan, which should be approved and begin implementation before the second phase of bottleneck works commenced in June 2015. The independent evaluation for this programme is part of a broader evaluation of a selection of DFID Tanzania’s growth portfolio which has been separately contracted to a consortium led by ITAD.
Delays in contracting and a prolonged inception phase have resulted in this milestone not being met. ITAD have submitted an inception report and are now preparing the detailed design of this evaluation. It is expected that this design will be submitted in the first quarter of 2015, allowing the baseline household survey to be undertaken before June 2015 when the second phase of works is due to begin. Responsibility for baseline collection is split between the long term TA (who will commission and oversee a baseline traffic survey, including fare information) and the evaluators who will conduct a household survey.
In the inception report the project evaluators and technical assistance team have expressed concern that the outcome and impact indicator will be difficult to systematically measure and interpret and may not adequately capture the ultimate benefits of the project and have therefore proposed revised outcome and impact indicators for DFID to consider.
Recommendations
To ensure that the planned impact evaluation will be as robust as possible, it will be important that ongoing monitoring data produced by the programme is properly collected, analysed and stored in a timely manner. There is significant overlap here between the roles of the evaluator, TA and implementers (both PMO-RALG and the district administrations). It will be important as the evaluation design is completed that distinct roles and responsibilities are clear for all.
It is unclear the extent to which PMO-RALG and RFB are engaged with this evaluation, and it will be vital to ensure that as the design is finalised and data collection begins, both the TA and ITAD engage PMO-RALG and the RFB to ensure both full cooperation and uptake of results at all levels.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance
The largest cost is the construction works which are designed by an independent consultant and competitive procured by the LGA with oversight from the region authority, PMO-RALG and the IRAT TA. During the annual review a spot check of the procurement in Babati district was carried out. The LGA was found to have largely followed correct procurement procedure but with some shortcomings that are likely to reduced value for money (see section below on commercial considerations). In most cases that the review team saw the original design appeared to be appropriate given the limited data available to the design engineer and review team, however the district engineers in both Kondoa and Babati had used their local knowledge to make significant changes, which in Kondoa district has not been priced in advance resulting in cost over-runs of approximately 10-15% that PMO-RALG had not agreed to.

VfM performance compared to the original VfM proposition in the business case
Approximately 2/3 of the first phase funding has been released by DFID which corresponds closely to proportion of bottleneck roads completed indicating that VfM performance is broadly in-line with that expected in the business case. Once DROMAS has been operationalised it will be possible to test value for money in more detail by comparison of construction costs between LGA’s. The Road Fund Board annual technical audit for Bababti was issued in August 2014 and mentions the DFID funded structures, highlighting many of the same issue in this report.
The premise of the original VfM proposition in the business case was also that local government is a more effective agent route for rural roads than alternative project based approaches that DFID could have chosen. While not having the evidence to make a direct comparison, this premise seems very likely true from the low cost procurement method and the works in progress observed by the review team. In Babati district for example the total cost of the bottleneck works carried out by the local contractor was approximately £550k and included two 40m sections of box culverts, a 700m long raised embankment, 12km of road regrading, several small box and pipe culvert structures. This was broadly in line with the engineer’s pre-tender estimate and likely to be cheaper than employing a national or international contractor to carry out the work. The local, regional and central authorities receive a total of 7% of the contract value for administration and monitoring costs which again is likely to be cheaper than if DFID were to employ consultants directly for the task. Nevertheless concerns remain that the procurement and construction monitoring need to be improved to be sure that best value for money is being achieved (see key actions 2-4 in section B). Beneficiaries on route were universally pleased with improved road access. It is recommended that the TA be requested to carry out a cost comparison exercise against alternative methods of procurement and construction to help verify these value for money assertions.

Assessment of whether the programme continues to represent value for money
As discussed above it is unlikely that an alternative project based approach could achieve the same value for money as procurement through local government. However, the oversight mechanisms currently in place for procurement and implementation are weak and there is medium risk of poor practice which could undermine future value for money. In the next phase of works the prioritisation and design of the work will be carried out by PMO-RALG and their consultant rather than an independent body. The quality of initial surveys carried out by PMO-RALG’s consultant, Unitec appeared good, however PMO-RALG’s method of selecting the next phase of projects was not always clearly evidence based and at time subjective with the risk the highest value for money bottlenecks may not be always be prioritised – a possibility that was also mentioned by Unitec who recommend that feasibility studies be carried out for the larger bridges, which were likely to cost up to £3m each to ascertain the benefit to local communities would be worth the investment. PMO-RALG said they were aware that some of the projects in design would be beyond the scope of the IRAT programme and they had not yet decided which would be final list for the second phase works.

Quality of financial management Quality of financial management was good; however there is a need to further improve quality particularly of reporting.
Fund disbursal: There was an initial delay in disbursal of funds due to lack of clarity in the fund flow mechanism. Funds are now routed from Ministry of Finance to PMO-RALG and onward to Roads Fund Board, who then send it to the LGAs. Till date, there have been two releases. A total of 11.48 bn Tsh released out of a total approved budget of 16.69 bn Tsh. For LGAs, a total of 10.32 bn Tsh has been released against a budget of 15.58 bn Tsh.
Financial Reporting: LGAs submit quarterly progress reports to PMO-RALG. These reports include financial reports regarding spending on each contract. The PMO-RALG Infrastructure Development Unit (IDU) consolidates the reports sent by various LGAs and submits the same to the Roads Fund Board. (DFID has requested to see the aggregate and LGA-wise expenditure reports), Recommendation: There is need for the IDU to better monitor these financial reports in order to keep track of total commitments and spending across LGAs
Financial Audit: Audit of the Roads Fund is conducted by the CAG on an annual basis. Based on the audit report of 2012-13, the IDU reported that out of the 14 LGAs funded under the programme, 9 LGAs received unqualified opinion, 1 LGA received qualified opinion (We are yet to receive information for 4 LGA – Kilosa, Missenyi, Morogoro DC and Mufundi) Recommendation: There is need for IDU to keep track of audit queries highlighted in the audit reports and ensure compliance. Additionally, there is need to monitor queries on the RFB, if any, that emerge from the quarterly internal audit reports of LGAs.

Date of last narrative financial report	RFB 2012/13 annual report
Date of last audited annual statement	RFB 2012/13 annual report

E: RISK (½ page) Overall risk rating: Medium

Overview of programme risk:
Selected Programme Level Risks and Safeguards identified in FRA:
Fund flow (transparency and accountability): Initial delays in fund flows have been improved so risk is considered low, but they are still linked to GoT transfers although not currently a problem raises the risk of future delays.
Project identification (transparency and accountability): Implementation of the DROMAS system remains a medium risk item. Limited progress is being made (see indicator 2.1) Selection of the second phase projects in not fully transparent - see indicator 1.1 description and recommendations in section C and value for money considerations in section D.
Procurement planning and contract administration (accountability): The FRA identified the need for focused support through provision of carefully designed technical assistance to the Infrastructure Development Unit (IDU) and mentoring of all concerned individuals at district level. The finding of the review team was that there was a need for stronger monitoring of financial expenditure as well as follow-up on external and internal audit findings. The site visits also indicated that procurement and contract administration remain medium risk items:
Procurement risk While procurement procedures were generally followed correctly in the sample district of Babati there were a number of short comings observed which raise the risk of poor value for money. The contract was only advertised in one newspapers for one day (whereas regulations specify two newspapers) Two of the three bidders were excluded from on minor technicalities so only one bid was evaluated. Due to an oversight in the evaluation it was not realised that the turnover of the contractor with the winning bid was only one third of minimum amount required by the tender which called into question their capability to carry out the work. For recommendation see indicator 2.3 above.
Construction Risk The standard of construction observed was adequate although both districts visited were in delay which was generally blamed on seasonal rains. Both LGA’s carried out regular inspections of the work and submit quarterly reports however PMO-RALG and the TA inspections did not appear to be rigorous as they had no system to compare the work carried out with that in the contract – something that should be implemented as a matter of priority. Road Fund Board also carry out a technical audit which highlighted many of the same issues that the review team raised, however the feedback mechanism is too slow to impact projects in progress. The TA is developing a Monitoring Manual in line with Road Fund Board’s strategic plan and an Accounting Manual to be used by LGAs however this is unlikely to impact the current funding through IRAT. Where the TA made technical recommendations from their site visits there is no mechanism for ensuring that they followed up on and are implemented which is a weakness that threatens both quality and value for money. PMO-RALG noted that in two cases where the quality of work had been considerably below expected standards they had written strong letters reprimanding the LGA in question.

Social, Environmental and Climate Change Risks
PMO-RALG collects information on the work force, broken down by sex and wage rate, but this information is not currently being analysed. Once this information is supplied it will be clearer whether additional mitigation measures need to be taken. For instance quota arrangements for women in the work force did not seem to be in place as proposed in the business case.
There was little evidence of programmes to raise awareness and prevent HIV infection. The review team visited 6 intervention sites and only one village appeared to have a signboard stating ‘HIV aware’. There are makeshift settlements to house incoming workers at the sites, and one of these was located very close to a secondary school. TA should ensure that HIV/AIDS procedures are being followed at all sites.
Environmental risks are being actively addressed as a part of the programme – refer to indicators 1.3 and 2.5 – There are environmental protection measures that need to be undertaken such as protecting water courses and re-instating borrow pits but are not currently being monitored. The TA are contracted to carry out an action plan and compliance assessment by December 2014 which remain outstanding actions.

Outstanding actions from risk assessment An updated risk assessment is an annex to this review

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The main element of road procurement and construction by LGA’s started quickly upon project approval in Feb 2014, supported by a short-term TA support. A number of the projects are in delay but they are all expected to finish in the course of the year without affecting the overall aim. The second phase bottlenecks are currently in early stage design and will be ready for procurement in mid-2015 which allows the possibility that the key indicator 1.1 will be achieved in second year.

Performance of partnership (s)
DFID has two key relationships on this programme: with PMO-RALG and with Cardno, the TA provider. There is also liaison with the LGAs, who are the primary delivery agent of the programme, through PMO-RALG.

Short term TA was delivered at the start of the programme, from December 2013 to May 31st through a contract with ITT Cardno (following a procurement procedure run by DFID Tanzania). This was put in place to cover the gap whilst the main TA procurement was underway. The main TA procurement was conducted as a mini-competition from a framework contract by DFID’s Procurement and Commercial Department between March and July 2014. Cardno was judged during the evaluation process to have offered good value for money and was therefore awarded the contract (at a value of £0.97m) and started work in September 2014. The expenses within the contract represent 28% of the costs. It does not appear that sufficient allowance was made by DFID in the log-frame for the time to contract the long-term TA and subsequent delays to implementation which is a significant cause for log-frame milestones not being met.
The contract with Cardno is managed by DFID Tanzania’s Infrastructure Adviser and Programme Manager, who meets them and PMO-RALG quarterly to monitor progress. Cardno provide monthly snapshot progress updates and have a staff member based in Dodoma where the PMO-RALG head office is for regular liason. DFID staff have a positive relationship with both PMO-RALG and Cardno who are critical components of supporting programme delivery. It is suggested that Cardno focus more in the coming year at capacity building at LGA level, where delivery is being carried out, rather than at RFB and PMO-RALG level.

Although DFID does not have a direct relationship with the LGAs, there needs to be oversight at that level as that is where delivery is taking place, either through the TA or local consultants. Significant procurement is carried out at LGA level, in terms of sourcing service providers to carry out the construction activities for the bottlenecks. Based on a review of the procurement of a 1.5 bn Tsh construction tender in Babati, that was started in December 2013, procurement appears generally to be carried out in compliance with PPRA regulations (although a full PPRA style audit was of course not carried out). Particular areas of concern were the hiring of a contractor with lower than the required turnover; and the lack of a contract amendment to reflect the changes in scope or time extension (it appears in fact that the contract has expired, with no extension paperwork in evidence). There are also a number of areas where due consideration should be given to achieving value from procurement, over and above simply following a process. In particular: ensuring tender documents are fit for purpose at the start; understanding the market to check whether sufficient capacity is available to deliver the work (if not the tender can be split into lots); and ensuring a sufficient number of bidders for the competition, by advertising more widely and by considering whether it is appropriate to knock out bidders at an early stage, on what appear to be technicalities. Engineers at regional and PMO-RALG level look at compliance with procurement regulations and report any issues to Council Directors. This is a vital role, but as these are not procurement experts they may struggle to add value to the process without further support and capacity building.

District Engineers and Technicians oversee the construction works being delivered by the service providers on a day to day basis; Regional Engineers and PMO-RALG engineers visit the sites periodically to review the quality of the work. Contract management however is an area of risk, as in both locations reviewed, the management of time and cost overruns was not clear and changes to the work were not reflected in the contract.

Asset monitoring and control
Two vehicles were purchases for use by the PMO-RALG which were observed by the review team. Sixteen Field Gravel Road Test Kits, three computers and a plotter were delivered to PMO-RALG in Dodoma. PMO-RALG must provide an asset register for these items.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The programme has not been affected by the application of partnership principles this year.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The evidence underpinning this intervention as described in the business case has not changed and remains relevant. The long term TA in collaboration with the evaluation consultant have produced a draft review of the impact of rural road interventions on poverty reduction and resilience. This has largely reinforced the Theory of Change particularly in relation to socioeconomic impacts, with strong evidence to show that interventions to improve rural roads increased incomes and reduces poverty. The evidence generated from the review will be used to inform the monitoring and evaluation strategies of the programme.

As discussed at Output 3 above, an independent evaluation of the programme has been commissioned and is currently at the design phase. This will largely rely on household and market surveys to determine if household income rises and/or transport costs reduce.

The long term TA and evaluation consultants have expressed some concern over the logframe indicators, particularly whether they are realistic and whether they capture the full nature of the programme. Throughout the review they have been encouraged to feed these concerns back to DFID Tanzania, and should be engaged in any review of the logframe following the review.

Monitoring progress throughout the review period

Whilst there are both quarterly reports from the districts and periodic spot checks from the TA and PMO-RALG, there is currently no system for collating data and analysing reports to monitor progress of interventions or feed into programme improvements. This review recommends that the TA support PMO-RALG to improve on current reporting systems, fact check data and sufficiently fulfil its monitoring role.

During the course of this review, the team visited Dodoma and two districts (Kondoa and Babati). The team sought feedback from beneficiaries at all levels of the programme, including PMO-RALG Infrastructure Development Unit, the District Executive Directors, District Chairmen, Regional and District Engineers, Contractors, Ward Councillors, Village Councillors and village residents. Their comments and opinions have informed this review, and it was clear that they felt happy with the intervention and had been fully involved in the process to date.

The TA has had initial meetings with Tanzania’s CoST secretariat about implementing CoST (Construction Sector Transparency Scheme) on the bottleneck projects. As there is not a strong civil society sector in Tanzania the intention is to work though district chairpersons to carry out the role of civil society monitoring of the projects. The review team was not convinced that applying CoST scheme was an effective monitor system in this context and consideration should be given to re-directed effort towards ensuring that the TA and PMO-RALGs monitoring of the LGA’s is effective.

The Annual Review team was composed of four DFID advisors: Tim Bushell (chartered civil engineer), Lesley Miller (procurement specialist) Clare McCrum (Social Development Advisor) and Vivek Mistry (Public Financial Management Advisor)