Type of Review: Annual Review
Project Title:regulatory & investment systems for enterprise growth in bangladesh (rise)
Date started: June 2007

Date review undertaken: 12-30 May 2013
## Introduction and Context

What support is the UK providing?
The UK is providing up to £40 million (approximately $62 million current value) over 7 years from 2007 to help improve the investment climate in Bangladesh. This is done through three specific outputs: / (a) Output 1: Through the Bangladesh Investment Climate Fund (BICF), DFID provides £20 million to support Bangladesh to improve the business environment by reducing the time and cost to businesses of engaging with the government. This is done by simplifying, and where relevant automating, the processes that businesses have to deal with. Areas of work include business registration, taxation, and commercial justice/ alternative dispute resolution. The newly started investment generation work will focus on regulatory issues in specific high potential sectors, such as agro-processing and light engineering. BICF is co-funded (40%) by the European Union. DFID has provided an 18 month no-cost extension to BICF meaning that this component will now end in December 2015. / (b) Output 2: Through the South Asia Enterprise Development Facility (SEDF) of IFC, DFID provides £5 million to support improved competitiveness of small and medium enterprises (SMEs). SEDF has two main pillars, the first is Access to Finance which facilitates enhanced credit and savings opportunities for SMEs. The second pillar, Sustainable Business Advisory, improves productivity in an environmentally friendly way in sectors such as textiles, poultry and seeds. SEDF is a regional facility that operates in Bangladesh, Bhutan, Nepal and North East India. DFID provides 37% of SEDF’s funds with the remainder coming from Norway and IFC. / (c) Output 3: Through Private Sector Development Support Programme (PSDSP), DFID is providing £15m in technical assistance to complement the World Bank’s $120m soft loan for developing special economic zones (SEZs) in Bangladesh. These SEZs provide businesses with land that has necessary infrastructure including roads, electricity, gas, connections to major transportation systems and effluent treatment facilities. These zones are important for stimulating private investment for economic growth and job creation, because availability of industrial land, with relevant infrastructural support is limited in Bangladesh.

What are the expected results?
Over 7 years, the RISE programme aims to reduce poverty in Bangladesh through sustained pro-poor economic growth; towards this broader goal, RISE will contribute to 500,000 formal jobs and $1.5 billion of foreign direct investment into Bangladesh. / By the end of the final year of the programme, we expect to see the following outcomes and outputs results under this programme: / The number of formally registered businesses will increase by 90,000. / Net income of 60,000 farmers and businesses will increase by $42 million. / Businesses will save $189 million in reduced compliance costs. / Additional $1.5 billion of private investment in RISE-supported zones.

What is the context in which UK support is provided?
Bangladesh has one of the lowest levels of foreign investment in Asia; this is a direct result of its poor business regulation and business regulatory compliance process making Bangladesh a less attractive place to do business. Without addressing these issues, the country will not see an increase in activity by firms to invest or grow. This investment and growth of businesses is important to Bangladesh and DFID because of its role in creating jobs and income generating opportunities that allow poor people to work themselves out of poverty. Bangladesh has a labour force that is growing by 1.8 million people each year[1], without adequate growth in investment, the economy will not be able to create enough opportunities to absorb these people in a productive way. In addition, without investments, fragility will rise and growth rates will not reach the 8% targeted by the Government of Bangladesh (GoB) necessary to achieve the country’s aspiration to reach middle-income status by 2021. / Improving the ease of doing business is essential in Bangladesh for this growth: a 135 cross-country study conducted by the World Bank in 2006 identified a 2.3% average reduction in annual growth rates due to a poor investment climate[2]. This rationale and the Government of Bangladesh’s emphasis on accelerating growth led to the design and launch of the RISE programme in 2007.
[1] Labour Force Survey 2010, Bangladesh Bureau of Statistics
[2] Bangladesh Investment Climate Assessment, World Bank, 2006

## Section A: Detailed Output Scoring

Output 1: Reduced regulatory compliance cost and improved investment climate.
Output 1 score and performance description: A (Outputs met expectation) / Following the Mid Term Review in 2010, a new strategy was designed for the second phase of BICF (2010-15). After the strategic re-structuring, In 2011-12, BICF focused on re-building relationships with key public and private stakeholders, as the new government (elected in 2009) decided to discontinue some of the reform process and made significant changes in administration. During 2012-13, the year in review, BICF focused more on fostering implementation, delivering results and measuring impacts. / Overall, BICF met its output expectation in this year (details of achievements against indicators are in the following sections). In last 12 months, BICF made notable progress in implementing reforms in business processes, supporting public agencies in drafting key regulations and supporting a mechanism where public agencies can interact with private sector representatives so that policies are developed and reformed based on evidence. Support in drafting of and consultation for a new Companies Act, assistance in enacting a new Value Added Tax (VAT) law and new Competition Act, were key achievements of BICF in2012-13.The Companies Act reform, if successfully enacted, will modernise Bangladesh’s company law and corporate governance arrangements, making it easier to establish, manage and exit from a company. The draft Act also has further potential to broaden the range of businesses that can be incorporated and widen their access to finance. Alongside the new Competition Act, these interventions have helped modernise fundamental pillars of the business framework, and thus improved the enabling environment for investment and business.
Progress against expected results: / Indicator 1: Compliance Cost Savings for private businesses – target for end of programme is $189 million / Achievements met expectation to deliver the end of programme target. / Around $25 million of additional compliance cost savings for private businesses were generated in 2012-13. These cost savings are measured by calculating the costs (both time and direct/ indirect financial outlays) before and after a change is made to a regulation or the way in which private businesses comply with regulation processes[3]. BICF supported regulatory simplification across a broad range of policy areas, particularly through automation of regulatory and tax compliance processes. Total compliance cost savings made by the programme to date is $112 million. With new simplifications and accumulation of previous savings, the programme is on track to reach the cumulative $189 million target by 2015. The most significant savings were achieved through automation of tax and VAT collection processes and automation of business registration process in Board of Investment (BOI) in2012-13. In last 12 months, BICF facilitated simplification of 11 business regulation processes (10 at national level and 1 at sub-national level), which will free up at least 25% of private sector’s time and resource to be used for productive purposes – previously it would have been spent on unnecessarily burdensome compliance. / Indicator 2: Public and private sector contributions allocated/realised to sustain BICF supported interventions – target for end of programme is $21.4 million. / Achievements met expectation to deliver the end of programme target. / In 2012-13, Government of Bangladesh (GoB) allocated $11.09 million worth of direct and indirect contribution to sustain BICF-supported reforms. Public and private sectors’ contribution to support implementation of various reforms initiated by BICF is an indication of ownership of reformed processes and also one of the critical elements of sustainability. In this financial year, GoB provided resources for continuing the Counsellor Programme in Dhaka EPZ, digitisation of direct tax return processing in National Board of Revenue (NBR) and maintenance of automated system in Register of Joint Stock Companies (RJSC). / The private sector is continuing its support for functioning of a body named Business Initiative Leading Development (BUILD). BUILD provides a mechanism for generating and taking forward reforms with private and public sector participation. Dhaka Chamber of Commerce and Industries (DCCI) and Metropolitan Chamber of Commerce and Industries (MCCI) and SME foundation are supporting the operation of BUILD by providing around $62000 worth of in-kind contribution (e.g. free-of-charge office space). Total accumulated contribution of the public and private sectors to sustain BICF’s interventions is approximately $18 million till date. The programme is on track to secure similar contributions to meet end of programme target. / Indicator 3: Value of public and private funds released – target for end of programme is $100 million. / Achievements met expectation to deliver the end of programme target. / $54 million of private and public funds were released by solving commercial and tax disputes through alternative dispute resolution facilities in this financial year. In last 12 months, Bangladesh International Arbitration Centre (BIAC), facilitated arbitration of 2 commercial disputes and helped release $32 million of private funds. With BICF’s support, 39 customs tax disputes, with total value of $22 million, were solved in 3 tax mediation facilities in NBR. / During 2012-13, BICF made significant progress in operationalising and institutionalising Alternative Dispute Resolution (ADR) in Bangladesh. BICF supported BIAC to develop and adopt ‘Commercial Arbitration Rules’ which set out provisions to administer arbitration along with classic clauses that includes arbitrators’ fees, selection of arbitrators, model arbitration clause, administrative fee structure etc. / Amendment of the Code of Civil Procedure (CPC) for making ‘Mediation’ mandatory for all civil cases in Bangladesh has been a major achievement of BICF in last 12 months. The Ministry of Law is now piloting mandatory mediation in 3 districts, which sets a huge potential for success in mainstreaming ADR in Bangladesh. / However, making ADR popular and an effective mechanism for commercial and tax dispute resolution countrywide is a prolonged process. BICF is on track to meet end of programme target for releasing private and public fund. Sustainability of the facilities and institutionalisation of processes will require strategic and careful engagement of BICF with key stakeholders (Detailed recommendations are documented in the following recommendation section). / Indicator 4: Percentage of firms compliant with environment and labour standards in zones – target for end of programme is 90%. / Outputs partially met target. / 92% of the factories in Bangladesh Export Processing Zones (BEPZ) comply with labor standards and 52% of the companies comply with environmental standards[4]. BICF’s support to Bangladesh Export Processing Zone Authoroty (BEPZA) on promoting labour standard ended in this financial year. To sustain environmental compliance in BEPZA, the authority already hired 30 environment counsellors and is training them to support compliance in factories. Furthermore, Central Effluent Treatment Plants (CETPs) have been made operational in the 2 largest EPZs. Since BICF’s engagement in zones concluded and rest of the activities in promoting private economic zones was taken over by the World Bank under Private Sector Development Support Programme (the third component of this programme), this indicator will be revised and taken out of BICF in coming months. / Recommendations: / Overall the review recommends that BICF needs to: / Rationalise the portfolio to consolidate and deepen impact, and prioritise interventions that address binding regulatory constraints : / Following restructuring in 2010, BICF was often opportunistic in selecting interventions that were championed by others; this also balanced risk in the portfolio. The review team raised concerns around relevance and prioritisation of some of the interventions (e.g. Green Building Code, Digital Signature Authority). Review team opined that answer to the question ‘Does this intervention reduce time and resource required for compliance?’-was not necessarily explicit. Given that embedding and sustaining of reforms requires time and the programme has a little more than 2 years left, BICF should focus on prioritising interventions, instead of spreading resources too thinly across the portfolio. BICF needs to conduct a portfolio review exercise using a set of criteria (e.g. match with country needs, institutional and political feasibility, potential for prompt implementation and high impact), that will identify priority interventions for implementation in next two years for improving business and investments in Bangladesh. Priority for the programme in next two years should really be on consolidating (embedding and scaling up) reforms so that key constraints are addressed sustainably. / Based on the portfolio review exercise, BICF needs to develop a clearer Theory of Change for the programme and map prioritised interventions onto that theory of change. BICF needs to have a clear rationale for prioritised interventions and how interventions contribute to outcome/purpose of the programme. Mapping of interventions against the programme outcome will help sharpen focus of the programme and also enable BICF to install a systematic approach for selecting or discarding interventions in future. / Develop plans of action for ensuring sustainability of reforms through proper ownership of public and private counterparts: / BICF has been successful in setting up pilots/initial building blocks for simplifying regulatory processes for ease of doing business in Bangladesh. However, ensuring that changes are sustainable and projects/facilities evolve as effective institutions, will require a strategic and focused engagement from BICF with key stakeholders and institutions. To ensure sustainability of reforms and facilities (e.g. BIAC, Tax ADR, Tax automation, BUILD), BICF needs to develop an action plan (or business plan in some cases) identifying critical tasks and key institutional challenges, pivotal to sustainability of reforms. The plans will have to identify resource need and also a plan for securing resources either through government budgetary allocation or through alternative sources. / Ownership of public and private agencies is at the centre of ensuring sustainability of reform. The sustainability plan for action needs to be developed jointly with relevant public and private agencies and will have to be embedded into the planning process of the institution or other wider reform processes (e.g. World Bank and IMF-led VAT law implementation at NBR). The sustainability plans should be linked with a clear vision for change and exit strategy for BICF, which may include other donors/projects taking on BICF’s initiatives. / Communication will play a vital role in ensuring sustainability of reform. A successful reform in many instances requires change in mind-set and behaviour of public service providers and private sectors as users of service. Bringing in behavioural change and translating awareness into action will require targeted and comprehensive multi-channel (including better use of BUILD to stimulate demand for streamlined/automated services) communication. A communication plan for raising public awareness and stimulating demand for reformed services/facilities should be an integral part of the sustainability plan. BICF needs to support public and private agencies to develop communication plan with a longer term strategic outlook; shifting away from ad-hoc communication. In addition, BICF needs to set up a systematic process for collecting user feedback for continuous improvement of new business processes. / BICF needs to be more cognisant of political economy of reform and develop strategies for mitigating potential risks posed by losers from reforms (e.g. tax lawyers because of Tax ADR). BICF also needs to work with BUILD to ensure its objectivity and to establish it as a credible organisation representing voice of wider private sector, beyond its sponsoring associations. / Develop a comprehensive monitoring and evaluation plan along with a methodology for measuring and reporting BICF-attributable results / BICF operates in a complex regulatory and compliance environment. It is also not the only project, which aims to improve the regulatory environment in Bangladesh. Therefore, BICF needs to develop a more nuanced approach of measuring and reporting attribution of BICF activities to the outputs and outcomes. Otherwise BICF runs the risk of overestimating its impact. Measuring impact of investment climate work is evolving and, therefore, there is limited knowledge available on the methodology of measuring attribution. However, this should not deter BICF from pioneering the methodology and contributing to global knowledge base. Acknowledgement of the fact that not all the regulatory reforms or processes streamlined are fully attributable to BICF will be a good starting point. / Based on a clearer theory of change, BICF needs to map out the indicators against each level of theory of change and develop a monitoring plan for indicators along with gender disaggregation of data. BICF should conduct a diagnostic to identify the evidence gaps and weaknesses in the existing M&E work. Findings of that diagnostic will enable them to adopt a more systematic approach in commissioning detailed study and evaluation, to strengthen evidence base or test assumptions. / BICF needs to publish all of the research work that they commission and ensure that the governance of this work is independent i.e. someone from DFID/a donor is on the management/reference group for the study. / In later part of next financial year, an independent business process evaluation should be commissioned to assess efficiency, rigour and effectiveness of the M&E system (particularly relevant considering the high cost of the research work that has been conducted directly by the IFC) of BICF. / Impact Weighting (%):50% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No
[3] The following formula is used in calculating CCS: Total direct compliance cost savings = Direct compliance cost per transaction ((official fees + other financial costs) + Labor cost (staff time x staff wage)) x No. of transactions of the procedure per year
[4] Results from BEPZA data updated in December 2012

Output 2: Increased access to finance, services and linkages for SMEs.
Output 2 score and performance description: A (Outputs met expectation)
SEDF projects are largely on track to achieve targets for end of programme. Responding to last year’s annual review recommendation, SEDF developed a Theory of Change for all its interventions. The project started tracking and measuring outcome level changes in agri-seed, poultry and textiles along with developing a methodology for measuring project’s attribution of results. Overall, the teams and work plans are in place and in last 12 months the project initiated activities to scale up pilots and strengthen service provisioning for SMEs in selected sectors. These activities will ensure benefits are not limited to one or two lead farms, rather the sector transforms itself. For example, SEDF is now developing a pool of service providers for washing and dyeing companies who can conduct energy audits and help the companies improve energy efficiency of business processes. SEDF also partnered with Bangladesh Garment Manufacturers and Exporters Association (BGMEA) and awarded Environmentally Compliant factories to create wider awareness among industry stakeholders. / However, actual impact of scaling up of pilots in transforming these sectors will be measured and monitored carefully in the next six to eight months. SEDF’s overall success as a transformative facility will depend on its ability to create sector wide impact - which in turn will be crucial for deciding whether there is a need for continuation of this facility beyond its current phase. / Progress against expected results: / Indicator 1: Additional SME portfolio developed and number of SMEs financed by RISE supported programmes. Target for end of programme is $720 million for additional portfolio and 58,000 SMEs financed. / On track, however methodology needs to be further refined. SEDF reports that in 2012, 17,490 new loans were provided to SMEs and total value of the loans were around $300 million from BRAC and Eastern Banks, which is higher than the 2012 milestone of $283 million. SEDF is conducting a detailed assessment of the loan quality and profile of targeted SMEs to identify actual increase in number of new SMEs. / Indicator 2: (i) Additional poultry meat production in SME poultry farms; (ii) Electricity generated (alternative to diesel power) by farms. Target for end of programme (i) 10% additional poultry production in 12,000 farms; (ii) 9 Mwh/year electricity generated; / On track. In the poultry sector, SEDF worked to improve productivity of small poultry farms and in mid-sized farms to convert poultry litter into energy thereby providing the farms with green energy. In 2012, activities in poultry sector generated the following results: (i) 12,700 poultry farms have reported 6.1% productivity increase (ii) 1570 MwH/year electricity is being produced through 35 ‘Waste to Energy’ facilities in poultry farms. To create wider sectoral impact, SEDF is training 12 ‘Waste to Energy’ service providers so that new poultry farms can set up electricity plants and a market for waste to energy is developed. / Indicator 3: Number of Washing, Dyeing and Finishing (WDF) firms that have conducted risk rating and environmental audits; Target for end of programme 50 WDF firms have conducted risk rating and environmental audits;. / On track. In the textiles sector, SEDF has developed a cleaner production programme that has the double benefit of generating savings for the factory while also reducing the amount of pollution generated by the factory. Interventions focused, on a sector level, on regularising audits and, at a factory level, on piloting cleaner production assessments. In last 12 months, 11 factories completed Cleaner Production assessments and in next six months 32 additional companies will complete cleaner production assessment. The project is on track to meet the end of project target. / Indicator 4: Increase in crop yield (rice and vegetable, direct/indirect); Target for end of programme is 30% increase in crop yield by 40,000 farmers (rice and vegetable, direct/indirect) / On track. SEDF’s seed sector programme focuses on increasing production, sales and distribution of quality seed to poor farmers through private sector companies. One component of the programme is geared towards climate change adaptation and focuses on climate resilient seeds in the southwest costal belt. In this reporting year, 11,195 farmers and supply chain members were trained by 3 seed companies. SEDF conducted a quasi-experimental study to determine the productivity of the farmers. The initial findings of the study indicate that around 44,000 farmers on average have experienced 14.4% increase in yield. The study will have to be repeated again in next 6 months to smooth out seasonal variations. / Recommendations: / The review recommends that SEDF, on a priority basis by August 2013, needs to: / Increased focus on implementation for delivering sector wide impact: (is this doable in the last 12 months?) / Based on the Theory of Change of each business line, SEDF needs tofocus on implementation of activities for transformational sector wide benefits. Activities in the last 12 months of the project should aim for change in business practices of different private sector entities as well as outreach of market change. Activities should be implemented to ensure that pilots are scaled up, new businesses are accessing and adapting successful business practices. To achieve these objectives SEDF will have to carefully select and sequence activities in next 12 months. / Plan and implement M&E activities to measure sector level outcomes with credible attribution: / SEDF needs to continue to develop its M&E plan for measuring sector level outcomes and develop evidence, with credible attribution. For agri-business, there is limited understanding on how improved productivity of farmers contributes to better profitability; for Access to Finance (A2F), impact of better access to finance on enterprise performance or job creation is not clear. The planned jobs study needs to be managed carefully because this will be last opportunity to track impact level indicator before the project ends. Evaluations and studies on outcome level results will be important to measure overall success of the project and should be the focus of M&E plan in the last year of implementation. / Improve visibility among sector stakeholders and step up communication effort for sector wide impact: / SEDF needs to be cognisant of the fact that strategic use of communication can help them achieve some sector level changes. The project needs to develop communication materials for documenting qualitative results of SEDF interventions. The communication material will create greater awareness among sector stakeholders about various improvements supported by SEDF. This will stimulate demand for various service e.g. cleaner production mechanisms, ‘waste to energy’ services. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Enterprise Zones (EZ) developed with greater private participation and greater incorporation of environmentally and socially responsible business practices
Output 3 score and performance description: B (Outputs moderately did not meet expectation). / World Bank, the lead on this output, conducted three missions on PSDSP in the last year. World Bank missions rated implementation status as moderately satisfactory as progress on Hi-Tech Park’s tendering and approval of relevant government documents for the two zone authorities (without which actual construction of zones cannot start) have been slower than expected. DFID advisers took part in those missions and agree with the assessment. / Progress was made in capacity building of zone authorities in Bangladesh. PSDSP supported capacity building of newly established zone authority, for developing knowledge and skills relating to best practices in the development and management of economic zones. Bangladesh Economic Zone Authority (BEZA)’s move to an independent functional office and appointment of new Chairman are two major milestones for institutional development of BEZA. The EZ rules and regulations were approved in principle at the first meeting of the Board of Governors in April 2012 and are expected to receive final approval from the cabinet shortly. Approval of EZ rules will be another key milestone for the project, as these rules set the basic regulatory framework of zones’ operation in Bangladesh. However, there are key challenges going forward around contracting, contract management and GoB approval process (please see the key challenges section for detail). These issues will affect progress of construction of zones and its ultimate objective of stimulating private investment in Bangladesh. / World Bank completed a restructuring plan and final internal approval is expected by July 2013. The restructuring will (a) rationalise indicators laying the foundation for the successful implementation of the project, (b) include a Governance and Accountability Action Plan (GAAP) and Operational Risk Assessment Framework (ORAF), (c) establish a more realistic disbursement curve for the project, and (d) reallocate funds and resources to project components that most need them, such as developing new zones through BEZA. The restructuring plan, once approved, will ensure that progress of project is monitored properly, fiduciary risks are better tackled and all components have sufficient budget. / Though some progress was made in last 12 months, there is a moderate to high risk of delays in the months ahead on key issues (e.g. final approval of the EZ Rules and the award of the tender for developing Kaliakor Hi-Tech Park). These are some of the critical activities and failure to accomplish these activities timely will jeopardise success of the programme. / Currently the project is due to end in June 2015. With 2 years left in the current phase, there is high probability that the economic zones’ construction will not be completed and investors will be able to set up factories/businesses in the zones. Slow progress in completing some of the critical steps (tendering, contracting and GoB approval process), absence of strong and dynamic leadership in BEZA, political instability in the context of upcoming election in Bangladesh and WB’s newly introduced additional due diligence process-are the reasons contributing to probable delays in construction of zones.
Progress against expected results: / Indicator 1: Environmental Impact Assessment (EIA), Social Impact Assessment (SIA), financial and economic feasibility, master planning completed for at least two zones and WB board approval of project secured by 2010. / Achievements met expectation / Earlier, DFID funds were used to conduct feasibility studies for 4 zones. 1 of the identified zones, is moving ahead in implementation (Kaliakoir). In 2012, five sites were identified based on BICF-sponsored site assessment exercise, Request for Expressions of Interest for zone development has been issued for 2 of the sites, resulting in a short list of developers, and a contract has been signed for a feasibility study on the remaining three sites. Since the overall project is now moving into implementation phase, in the next annual review, this indicator will be revised to reflect the progression of the project. / Indicator 2: Extent to which assistance for on-site infrastructure, including environmental and social infrastructure, is provided to two PSDSP zones by 2014. No specific milestone or programme-end target. Assistance will be provided from DFID's side to the extent possible given the pace of GoB and WB and the complexities involved in building economic zones. / The progress of this indicator in on track. / The project is on track to provide on-site infrastructure to at least 2 economic zones by the end of 2014 . The tendering process for an alternative road, boundary wall, and bridge to enable the Kaliakor site has been initiated by the High-Tech Park Authority (HTPA). BEZA is now processing a new Development Project Pro-forma ( a mandatory GoB document for project implementation) in order to utilise PSDSP funds to build infrastructure for any sites they are developing as economic zones. BEZA has completed cost estimates for these projects, the relevant government document, is planned to be submitted for approval in June 2013 and tendering and construction for at least one additional zone can begin in early 2014. / Recommendations: / 7. Revise the log frame indicators to be more SMART and set revised milestones for rest of the project period / 8. Following the approval of the World Bank’s structuring plan for the project, DFID adviser, in discussion with the Senior Private Sector Development Specialist of World Bank will prepare a note highlighting any need for revision of project timeline, risk for underspend of DFID funding (till date DFID spend is 40% of the total budget) . / Impact Weighting (%):25% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
Has the log frame been updated since last review? Y/N / Yes, minor revisions have been made in the logframe following last year’s annual review.what are these changes? The revised logframe and rationale for the changes has been attached with the document as Annex 1. / 1.2 Overall Output Score and Description: / A (Outputs met expectation). / In summary, Output 1, or BICF, following the restructuring plan in 2010, made significant progress in implementing various reforms in business registration, alternative dispute resolution, tax streamlining and operationalising the public-private dialogue mechanism BUILD. Various government agencies like National Board of Revenue, Board of Investment, and Ministry of Law are demonstrating ownership of the reforms initiated by BICF. In last 12 months, BICF supported its partner organisations to enact key acts and rules to better operationalise facilities like Bangladesh International Arbitration Centre, supported capacity building of key stakeholders and government staff who will be responsible for managing the new processes or facilities. Private businesses are using various automated services like e-tax payment and BOI registration. BUILD, with BICF’s support, has taken initiatives to improve specific regulations through Private Sector Development Coordination committee in Prime Minister’s Office. The reforms and process improvements are now showing early promising signs of impact. The recommendations listed in Output 1 will help BICF to deepen their work and ensure overall sustainability of reform initiatives in the coming years. / Output 2, or SEDF, followed up on last year’s recommendations and introduced Theory of Change for all the interventions. This process helped the project to better articulate how achievements of outputs are leading to broader outcome level results. Some progress have been made in better tracking of results. Output targets are being met and cumulative results show that the project is likely to meet end of phase target for most of the indicators. In last 12 months, SEDF made efforts to strengthen off-site supervision, through regional heads. However, on a number of occasions (e.g. consistent results reporting, steering projects based on theory of change), need for stronger management at the top was evident. / Output 3, or PSDSP, moderately did not meet expectations because of reasons already explained; however, as the impact weighting of this output is 25%, it did not affect the overall output score. More attention will be focused on this area over the coming six months to address barriers and management issues in more detail. / Direct feedback from beneficiaries / The review processes for Outputs 1 and 2 involved discussions and interviews with a large number of BICF and SEDF partners, including small, medium and large businesses in the private sector. / Overall feedback for BICF was complimentary; partners largely appreciated the helpful attitude and the technical support that was provided by BICF staff and external consultants. GoB counterparts appreciated BICF’s ability to share global best practice on regulatory reform, tax streamlining and public-private dialogue framework. / The review team met the Managing Director (MD) of Kohinoor Chemical Company and his team. They used automated services of RJSC. He reported that name check now can be done on-line and the verification happens within 5 minutes compared to 7 to 10 days in the past. In this context, he referred to his experience with the registration process of Mid-Land Bank. The MD reported that online registration of the Bank was completed within few hours. He also reported that different templates of the Articles of Association and Memorandum of Association are available on-line. This is a major improvement as it allows new businesses to use these documents for registration without resorting to intermediaries. / The review team also met the Executive Director of an insurance company who used alternative dispute resolution process for settling a tax dispute with NBR. He expressed satisfaction with the overall process. He highlighted that the company saved significant amount of money for lawyers’ fees as the dispute was resolved quickly. The company required only two sessions to resolve the dispute, as opposed to 10-15 hearings in tax tribunal. / To assess user experience of e-tax payment process, review team met CEO of an IT company. The CEO was impressed with the facility for ease of paying VAT and his staffs now do not need to spend hours in the queue for paying VAT. However, he viewed lack of a systematic process for collecting feedback, as a major flaw in the process. / Concerns were expressed by some government counterparts that often BICF tend to offer off-the shelf solution without customising to local context. BICF also needs to strengthen its post implementation follow up at service provider end, as well as, at user end. During discussions, BICF’s lack of post-implementation follow-up appeared as a weakness, which can seriously affect quality of reforms. / The private partners appreciated SEDF’s support in piloting various initiatives. Private partners were appreciative of SEDF’s responsiveness to the need of the client and also its ability to provide global standard technical assistance. / DBL-one of the companies supported by SEDF for Cleaner Production technique, was interviewed by review team. The company was positive about SEDF’s engagement in the overall process. The company appreciated the project’s technical assistance in improving production technique. The company was surprised with level of savings they could make with only basic modification in production process. DBL particularly appreciated SEDF’s understanding of commercial incentives and business processes. DBL suggested that SEDF should continue its engagement with the sector as they see huge scope of generating private sector savings through cleaner production mechanism.
Summary of overall progress / Overall programme outputs met expectations in last 12 months. Annual milestones for both output 1 and output 2 show progress and the external (and internal) review team confirms that progress in both Outputs 1 and 2 are on track to achieve end of programme targets. Using simplified procedures, private sector is already saving money and time. Annual milestones, for the remaining duration, will be monitored closely and once the recommendations made for Output 1 and 2 are implemented, the results will be much more robust, adjusted for attribution and triangulated across multiple sources. Though Output 3 suffered from initial delay, progress has been made in setting up key regulatory frameworks and institutions in last 12 months. However, DFID will work closely with World Bank for preparing a strategy note and an action plan, following the restructuring exercise, for monitoring progress. Progress in next 12 months are pivotal to the success of the project , as the critical tasks (e.g. managing the contract with private zone developers, finalise tender of two new zones) for successful completion of the project, will have to be completed by end of 2013
1.4 Key challenges / For BICF, key challenges going forward are: / Sustaining achievements through change in the political cycle: Success of reforms to a great extent depends on the political ownership for reforms. There is always a possibility of change in administration, following election in coming months. The change in administration poses risk of slowing down progress, if not reversing, made so far by BICF. For BICF, challenge will be to develop understanding and support of new administration for specific process reforms, as well as for wider business environment reform. / Ensuring business continuity and maintaining the network and social capital built over time: From the review, it was evident that BICF team has developed a strong relationship (especially senior manager in country) with key stakeholders. Part of BICF’s success in rapid recovery following restructuring was due to network and social capital of key staff. In coming days, BICF’s ability to implement quality reform will depend on its ability to attract and retain quality staff. Therefore, maintaining business continuity, retaining key staffs and minimising gaps in senior management position through succession plan will be a major challenge for IFC management. / Balancing need for consolidation and responding to client needs: BICF has been appreciated for its responsiveness to clients’ needs. BICF continuously receives requests for support from wide range of stakeholders. However, at this stage of project cycle, BICF needs to strike a balance between being strategic and being opportunistic. As BICF needs to prioritise its engagements in coming years, the project may not be able to respond to all the clients’ needs. Therefore prioritising BICF’s support, while maintaining high level of client engagement will be a major challenge for BICF. / For SEDF, key challenges in the near term are to: / Ensure successful pilots are scaled up and changes are transformative for the sectors as a whole. / Ensure technical supervision and oversight from the senior managers (from regional base) are sufficient and coherence between country team and senior regional managers is further developed. Lack of such coordination in previous years contributed to lack of strategic vision and weaker portfolio coherence in some cases. / Retain key staff of the project, in the last year of the project / For PSDSP, key challenges for the coming years are: / Increase the pace of GoB approval of regulatory framework for economic zones and project documents: The final draft of EZ Rules is currently in the Ministry of Law awaiting final approval and approval process has been delayed by almost 10 months. Efforts to promote the new EZs among private sector developers have often been hampered by delays with the final approval for the EZ Rules. Overall progress of the PSDSP and the tendering of one of the economic zone (KHTP) were delayed. Padma bridge difficulty, unforeseen changes in the design and lack of coordination between different agencies within GoB caused this delay. In next 12 months, increasing momentum of GoB approval process for regulation and GoB documents remain as a major challenge. Inability to overcome this challenge will cause further delay in construction of zones and will risk jeopardising overall purpose of attracting foreign direct investment in Bangladesh. / Minimise rotation of key GoB staff and develop BEZA as an effective institution: A steady rotation of all key personnel in BEZA, including the exit of the Chairman in November 2012, hampered proper impetus for Project activities in that institution. Minimising rotation of key staffs will be a major challenge, especially for a new institution like BEZA. In addition, developing BEZA as an effective institution with capacity to manage procurement, contracts and projects, is central to the success of economic zones in Bangladesh. The project in next 12 months needs to ensure that BEZA’s capacity building continues in strategic and effective manner.
1.5 Annual Outcome Assessment / Indicator 1: Number of formally registered businesses. Target for end of programme is increase of 90,000. / On track. In 2012, 7450 new businesses registered with the Registrar of Joint Stock companies in last 12 months. There has been 5% increase in number of businesses registered from 2010 to 2012. Further, 1,373 new trade licenses have been issued from the 3 pilot municipalities using the reformed and streamlined processes for trade license issuance. So far 49,000 new businesses have registered in the period that BICF has been working with the Registrar of Joint Stock Companies. / Indicator 2: Private sector savings through energy efficiency and GHG emissions avoided. Target for end of programme is (i) $25million savings/year (ii) 59,000 Tons GHG emission avoided. / On track. Through introduction of cleaner production process in Washing Dyeing factories and installation of waste to electricity facilities in poultry farms, SEDF contributed to energy efficiency and savings in costs for private sector. In 2012, SEDF-supported companies avoided 13,665 Tons of GHG emission and also contributed to $968,000 savings. In total, the project till date has contributed to $1.9million savings for private sector. Savings are expected to be accumulated faster in next 12 months, as SEDF is working to scale up cleaner production initiatives across the industry. / Indicator 3: Net income of farmers and businesses. Target for end of programme is increased income of $42 million for 60,000 farmers and small businesses. / Too early to judge. SEDF conducted a quasi-experimental study to determine the effect of SEDF supported activities on productivity of farmers. In 2012, 44,000 farmers have total additional revenue of $64 million. A repeat survey has been planned to validate the data and determine the impact of revenue increase on profitability of farmers. The findings of that study will be adjusted for SEDF attribution and revalidated as part of the project completion review later in 2013. / Indicator 4: Private investment in RISE supported sectors and economic zones. Target for end of programme is $1.5billion as result of various sector initiatives and the work done in existing Export Processing Zones (EPZ) and new Economic Zones (EZ). / Too early to judge. In 2012, BICF facilitated $120million private investment in zones. However, BICF’s activities in investment generation in key sectors are at early stage and the PSDSP supported zone construction is yet to start. The success of delivering end of programme target for this indicator depends largely on the success of PSDSP in setting up economic zones and attracting investment.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / The project is on-track against revised financial forecasts except Output 3. Output 1 has gained momentum in implementation and following the last year’s annual review the project duration has been extended till 2015. Though political uncertainties around upcoming election may slow down the progress of reforms, the project however is likely to meet the financial forecast. Output 2/SEDF is entering its final year and is on track to meet the financial forecast. Output 3, or PSDSP, went through a difficult phase, especially in the context of the issues around Padma Bridge project at the ends of both GoB and WB. However, recent progress in activities suggests that DFID’s support in strengthening the capacity of BEZA and other aspects of the zone development will be utilised within the project period. / 2.2 Key cost drivers / For BICF, total expense in last 10 months of the financial year (July 2012 – April 2013) was $6 million, which includes the contractual IFC administration fee of 3.5% ($175,443). Of the net amount of $4.8 million, major cost drivers were cost of consultants (58%). Consultant’s costs along with costs of various event form bulk of direct programme cost (total 78%). Travel expense has reduced significantly this year, which also matches with projects focus in last 12 months. During 2011-12, the project supported number of study tours for GoB stakeholders to learn and experience global best practices of business process reform, tax streamlining and ADR. In 2012-13, focus was on implementing those reforms and this explains rise in programme delivery cost and a drop in travel budget. / For SEDF, total expense in last 10 months of the financial year (July 2012-April 2013) was $1.9 million. 86% of the budget was programme expenditure, which is slightly lower than last year’s expenditure. Cost of consultants and various events remain same, while the cost of staff declined. / For PSDSP, technical assistance to BEZA has been the major cost driver in this financial year. The technical assistance includes cost of training and capacity building of GoB staff, various consultancy services as well as cost of participating in international road shows. / 2.3 Is the project on-track against original timescale: Y / Following the last year’s annual review, Output 1/BICF has been extended till 2015, without any increase in budget. Output 2/SEDF is on track and will end in 2014. Output 3 has suffered from implementation delays. WB and DFID will discuss and reach an agreement on the need for extending the project duration in next three months.

3. Evidence and Evaluation
Assess any changes in evidence and implications for the project / For BICF, the evidence base for the need for less burdensome regulatory reform, tax streamlining and ease of setting up and closing down business is strong. A recent thematic review of DFID’s investment and business enabling support programmes, conducted by the policy division, concluded that multiple sources show that easier business registration increases the number of firms in the market, increasing innovation and driving productivity growth. The report also documented that there is growing evidence that successful reform in improving ease of investment and doing business reduces the time and monetary costs of business operation. However, there is limited evidence on whether compliance cost savings lead to increased investment and better enterprise performance. Therefore, BICF needs to continue to invest in creating evidence base to support that :a) better investment climate reform leads to ease of business operation, b) compliance cost savings contributes to better enterprise performance and increased investment, and c) better investment climate reform leads to growth and job creation. / SEDF following the last review recommendation has developed a theory of change for each intervention. The independent impact assessment of seed intervention suggests that farmers’ productivity has improved after the training and quality seed promotion by the project. However, there is limited evidence on how better access to finance for Small and Medium Enterprises lead to better enterprise performance. To strengthen the evidence base on access to finance and enterprise performance, SEDF will conduct surveys and evaluations within next financial year. For both outputs, growing evidence suggests that basic theory of change is still valid. / For PSDSP, it’s too early to assess any change in the evidence base. / 3.2 Where an evaluation is planned what progress has been made? / In last 12 months, BICF conducted 2 major evaluations of their interventions. Both the evaluations followed rigorous statistical techniques and findings of the evaluations were published by BICF. SEDF also conducted a quasi-experimental study on the effect of training and promotion and on the productivity of the farmers. Findings of the study have been used to report progress at output level.

4. Risk
4.1 Output Risk Rating / Medium / 4.2 Assessment of the risk level / Key Risks: Output(s) that will be most affected: Mitigating Plan: / Change in government’s buy-in for the programme’s work at both policy level and at ministry/agency-level. BICF & PSDSP BICF: To mitigate the risk, BICF has aligned a bulk of its reform initiatives as part of the government’s ‘Digital Bangladesh’ agenda, as well as focused on the reforms led by different public agencies. However, this remains an inherent risk for any reform focused project like BICF, for the political economy of reform. Institutionalising the client relationship and proactive efforts to build strong ownership for different components within different departments will be at the heart of tackling this risk further. / PSDSP: The Project will take a proactive approach for building relationships both between the Bank and the GoB as well as among the implementing and other agencies. This will primarily be accomplished through the Project Advisory Committee (or “PAC”), in order to create an effective working group that will have a vision what economic zones can accomplish in Bangladesh. / Political instability especially in the period leading up to the national election in the form of slowdown in implementation during hartals (strikes) etc. All three This is a major risk for all the projects and the projects are exploring alternative ways of working (e.g. remote access to system for all key staffs, possibility of organising events on weekends) to maintain momentum of implementation. However, projects have limited ability to cope with the risk. / The Government changes and a new administration must be acquainted with the need for reform. BICF & PSDSP BICF: BICF will approach this proactively by focusing on a bipartisan approach to reform even before the elections. In addition, BICF will step up its communication and advocacy initiatives through BUILD, to stimulate demand for reform from private sector and raise awareness of bureaucrats on the need for better investment climate. Such multipronged approach is likely to minimise the lead time for regenerating political support for reform, if there is change in leadership following the election. / PSDSP: Economic zones have been a key feature of both major parties’ manifestos. Only specific issues within the topic of zones may need to be addressed. / Change in key programme personnel Mostly SEDF and partially BICF SEDF: SEDF will develop a HR strategy, identify key staffs and develop a plan for staff retention. SEDF will also prepare a succession plan to avoid longer gaps in filling key positions. To minimise uncertainty, SEDF will work with Donors to reach a decision on the future of SEDF. / BICF: As recommended, BICF will prepare a succession plan and try to identify key staff risks, especially at programme manager level.
Risk of funds not being used as intended / Low. Funding for RISE is managed by International Finance Corporation (IFC) and World Bank. Programme partners are not responsible for procuring goods or services. IFC and World Bank have multiple checks and balances in the procurement and financial management systems. There is clear separation of responsibilities between procurement and programme; as a result there is a strong quality assurance process in place. In addition, there are regional and central procurement and financial management teams for enhanced internal control. IFC and World Bank regional teams conduct regular financial audits. Therefore, risk of funds not being used as intended is low. / 4.4 Climate and Environment Risk / Both BICF and SEDF are conscious of environmental effect in the selection of their interventions. All IFC projects have to comply with the Performance Standards outlined in IFC’s Environmental and Social Sustainability guideline – which is a detailed approach to managing environmental and social risks and impacts in a structured way on an on-going basis. / Several of SEDF projects directly address avoiding CO2 emissions (e.g. Sustainable Energy Finance projects, poultry waste to energy project, textile project, etc.); A2F work developed environmental risk management guidelines for all financial institutions to apply in Bangladesh, thereby contributing to positive impact on carbon emissions. / For PSDSP, climate and environment risk assessment was a critical part of the initial assessment done. To address possible negative consequences of construction of zones on environment, an environmental management framework has been developed to integrate environmental aspects in EZ planning, design, construction and operation phases. The framework sets out procedures to (i) identify, predict, and evaluate environmental impacts of project activities; and (ii) set up suitable institutional arrangements to implement the environmental management measures. This framework is currently being updated in sync with the project’s restructuring.

5. Value for Money
5.1 Performance on VfM measures / VfM measures for Investment Climate reform programmes is still an evolving process and it is particularly difficult for the programmes which were developed prior to the Business Case format. Recently completed systematic review of DFID-supported investment climate programmes, concluded that ‘The structure of programmes (multi-donor, broad outcome objectives, complex channels of impact, long pay-off times) means that assessments of efficiency and effectiveness are difficult’. VFM assessments were made based on the documents and results reported by the projects. The cost effectiveness analysis was done based on the direct programme cost (without including the indirect costs as there are overlaps of staff time and other resources across different projects). / Economy & Efficiency: / Cost of consultants is the major cost driver for different components of the RISE programme. For example, in last 10 months, BICF spent 58% of total expenditure on consultancy costs- consultants are core to the technical assistance provided to different partners. Anecdotal evidence suggests that IFC is improving its economy in operation. In last financial year, BICF prioritised hiring of local experts over international experts. Total number of consultant days for local consultants were almost 3 times of the consultant days of international consultants / BICF also reported around 30% savings in cost of training for different partners and stakeholders, arising mainly from rationalisation of cost of venue and using partners’ facility. In next 3 months, DFID programme management team will work with IFC in developing a process for identifying ways for further efficiency savings and recording efficiency savings in a more systematic way. However, developing unit cost of reform will remain elusive and will be of little benefit for lack of comparability, as the reform process is country context specific. / Following the last annual review recommendation, IFC reports some breakdown of direct programme costs and the overhead expenses (including General and Admin costs, IFC admin fees and staff costs). All projects implemented by multilateral organisations like IFC or World Bank are governed by global Framework Arrangements (FAs) agreed centrally between DFID and multilateral organisations. The FAs set out limited performance, reporting and financial requirements for a project period. While there is some scope to include additional requirements in project specific Administration Arrangements under the FAs, the terms of the overarching FAs are non-negotiable. So, there is limited reporting of detail costs and breakdown of overhead expenses. As a result, costs could not be benchmarked against programmes implemented by other multilateral organisations like UN or other DFID supported programmes, which are implemented by the World Bank. / Effectiveness: / Because of multiplicity of outcome of the programme, it is difficult to develop a single indicator for measuring effectiveness of the programme. Two specific examples can be used to assess the effectiveness of the programme in saving private sector resources: / The automated registration services at BoI resulted in an aggregated cost savings of $16.3m in a year. The online platform enables investors to complete the entire registration process that includes submitting an application, attaching supporting documents, tracking status, obtaining interactive feedback and seeking approval without having to make multiple visits to BoI offices. Beneficiary survey data shows that the automation has led to $16 million in aggregated compliance cost savings ($0.2 million direct compliance cost savings & $15.8 million in indirect compliance cost savings) in one year. Approximate direct programme expenditure of BICF to establish the automated system was US$ 464,000. In basic terms of effectiveness, $ 35.13 was saved for every dollar spent. / Bangladesh International Arbitration Centre’s (BIAC)’s logistical facility, helped resolve 2 commercial disputes in 2012 and released about $32.3million private funds. Till date, the total expense which includes the establishment of BIAC, training of arbitrators and the drafting of ADR rules cost $683,000. This means that for every dollar spent, approximately $47.3 of private funds have been released. / As BICF improves its attribution strategy and takes other indirect costs into consideration, a more nuanced analysis of cost-effectiveness of BICF’s intervention will be developed. In next 12 months, DFID adviser will work with BICF in analysing cost-effectiveness of all the key interventions of BICF. / 5.2 Commercial Improvement and Value for Money / IFC uses formal World Bank procurement guidelines that are designed to deliver transparent processes for ensuring better VFM. Where appropriate, the IFC uses competitive procurement process according to the World Bank’s procurement guidelines, thereby obtaining best-valued goods and services in the local, regional and global markets. Procurements are initiated and managed by programme staff, with overall supervision and quality control from a central procurement team within the IFC. All staffs are thus trained in procurement and update their knowledge through regular refresher sessions. / BICF / To ensure greater local ownership and sustainability, BICF should have a plan for internalising the projects into GoB process from very onset. Contributions from private sector or public sector should be significant enough to avoid risk of moral hazard. / SEDF / IFC's pricing policy requires 50% of the total project costs (less IFC staff costs) to be shared by the client with some exceptional cases (e.g. global public goods, innovative approaches where risks are perceived to be very high). Given that pilots have been successful in demonstrating commercial success to private companies, SEDF should aim to further leverage private sector contribution and negotiate for greater contribution from private companies. Greater contribution from private sector will ensure greater ownership and sustainability. In addition, it will free up resources for supporting activities like M&E. / Role of project partners / BICF and SEDF are managed by IFC and both of these projects work with range of different partners including government agencies, business association and private companies. PSDSP is managed by World Bank and the project mainly works through BEZA. / BICF forms partnership with government agencies to implement reforms in compliance processes, regulations and tax streamlining. BICF also partners with private sector associations to promote public-private dialogue and continue the momentum of demand for reform. The sustainability of reform depends on the ownership of the process by key stakeholders and the capacity of public agencies in maintaining new services beyond BICF support. Though the interventions are implemented in partnership with different public, private agencies, IFC is responsible for financial and procurement management of this project and no funding is channelled through GoB system. / SEDF works with private companies and associations to improve access to finance for SMEs as well as to improve productivity and efficiencies of SMEs in different sectors. SEDF works with lead companies on a cost-sharing basis to pilot innovative business process. SEDF provides technical assistances to companies and business associations and IFC is responsible for procurement and financial management. / 5.4 Does the project still represent Value for Money : Y/N / Yes. / RISE represents VfM in terms of effectiveness because of the returns of the programme against the investment that DFID and other donors have made. The compliance cost savings and the value of public and private funds released from disputes are significantly higher than the investments made so far. Most importantly, RISE has the potential to generate huge amount of benefits to the private sector in terms of savings as well additional investment in the economy, which will outweigh the cost of the projects by manifold. With greater attention to efficiencies and cost saving opportunities, value for money would be demonstrated further still by the project management staff. An action item has been suggested for both DFID and project staffs, to be implemented in next 12 months. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
This review indicates that the next 12 months will be critical for all three Outputs. Priorities are: / For output 1, developing comprehensive plans for ensuring sustainability of reforms and ensure quality implementation; / For output 2, implement activities to ensure transformational impacts at key sectors and monitor and report results in much more coherent and nuanced manner; / For output 3, identify key delivery risks following the World Bank restructuring plan and develop a mitigation plan for ensuring effective utilisation of DFID support to PSDSP / The following is a list of the major action points: / For Output 1 / BICF: / BICF will reflect on the review recommendations and submit a management response to DFID by 31st of July 2013. DFID and BICF will agree an action matrix based on the review recommendations by 30th of August 2013. / To better manage the looming political risk, BICF will present a detailed assessment of the interventions highlighting the likely impact of political uncertainty and proposed mitigation plan. / DFID programme manager and BICF will agree on future scope of efficiency saving and develop a process for systematically recording efficiency saving by 31st of July. DFID adviser and BICF will work together to develop better indicator for capturing VfM. / For Output 2 / SEDF: / SEDF will reflect on the review recommendations and submit a management response to DFID by 31st of July 2013. DFID and SEDF will agree an action matrix based on the review recommendations by 30th of August 2013. / A decision on the future phase of SEDF should be made by August 2013 to minimise uncertainty among staff, as well as to provide clearer direction to the project. / For Output 3 / PSDSP: / The Joint DFID/ World Bank Infrastructure Adviser in PSDSP, Martin Norman, will keep the DFID lead adviser will inform DFID on the progress of the project on monthly basis for next 12 months / Lead adviser will keep DFID’s senior management informed on this issue and will produce a short note in August 2013 to highlight risks and mitigation plan at that point. / Following the approval of the restructuring plan, DFID programme management team will develop a revised fund disbursement schedule to the PSDSP. The revised disbursement schedule will ensure that DFID payments to the trust fund are not made in advance of need, but are available when needed.

8. Review Process
This document is developed based on three separate review processes for the three different components. Output 1, or BICF, was reviewed by an independent team. The review team interviewed key government representative at various institutions, user and beneficiary of various reforms and also reviewed documents. Output 2, SEDF, was reviewed by Private Sector Adviser, DFID. The review was conducted in discussion with project partners, IFC staffs and documents produced by SEDF. Output 3, or the economic zones where DFID is a silent partner, is based on the last World Bank mission report of May 2013 and discussions with the joint World Bank Senior Private Sector Development Specialist and DFID Infrastructure specialist.