Project Completion Review

ASIA REGIONAL ANTI-TRAFFICKING PROGRAMME - PILOT PROGRAMME

Date started: November 2011	Date review undertaken: July 2013

Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The UK provided £544,780 to pilot different approaches and develop evidence and lessons on how best to help women and girls protect themselves from being trafficked in South Asia. The purpose was to inform the design of DFID’s new programme to prevent trafficking of women and girls from South Asia in the garment and domestic work sectors, which will run from 2012/13 – 2016/17.

What were the expected results?
This Project Completion Review assesses the first stage of the Asia Regional Human Trafficking Programme and focuses on Design & Inception, with the aim of conducting pilot projects and generating an improved evidence base. / The expected outputs were: / 5 pilot projects, delivered by the International Labour Organisation (ILO), Global Alliance Against Traffic in Women (GAATW), Nimbus Social Enterprise Consulting Ltd and Anti-Slavery International; / 3 literature reviews, delivered by the London School of Hygiene and Tropical Medicine, the Governance and Social Development Resource Centre and a partnership between DFID and the John F. Kennedy School of Government at Harvard University; / A workshop in the region to share latest evidence and lessons; and / A robust measurement and evaluation framework, undertaken by the London School of Hygiene and Tropical Medicine (LSHTM). / Across these outputs, the expected results were: / Robust insights and evidence of trafficking interventions that work, specifically within the garment and domestic sectors; / Evidence of approaches and interventions that use technology and communication systems to tackle trafficking and that give voice to trafficked women so that their experience can inform more effective strategies to preventing forced labour; / Demonstration of practices, approaches and results that show an integrated approach with potential for scalability, partnership and innovation. / A deeper understanding of the legal, policy, institutional and implementation issues of trafficking women and girls in the labour sector in South Asia. / Engagement with over 60 experts in the field, including government, donor, private sector and civil society actors, to share latest evidence and lessons; / Deeper insights into how to design an effective measurement and evaluation framework for DFID’s Asia Regional Human Trafficking Programme. / These results were intended to inform the design of the second phase of the Asia Regional Human Trafficking Programme. This programme is now underway, and is supporting results and interventions such as providing pre-departure training for vulnerable women, working with private sector recruitment agents and helping domestic workers secure legal contracts and a decent wage by providing skills training.

What was the context in which UK support was provided?
Millions of people in South Asia attempt to escape grinding poverty by migrating to richer countries in search of work. There is increasingly strong evidence to show that this has a major role to play in tackling poverty, by improving migrants’ wages, standards of living and employability but also by assisting family members and their communities back home through sending remittances. Remittances to Nepal, for example, were estimated to account for 21% of its GDP in 2009, and 12% for Bangladesh in 2010. / However, many migrants - particularly women and children – are at risk of being trafficked, exploited and abused. This is especially the case for women and girls from South Asia, where gender inequality indicators are amongst the worst globally and women and girls face discrimination and exclusion from economic, political and social opportunities. / Asia has the highest number of trafficking victims. According to the ILO, there are 21 million men, women and children trafficked and in forced labour worldwide, the majority of whom are in Asia (11.7 million). Approximately four million victims of forced labour are from Bangladesh, India and Nepal. / Human trafficking is a crime and a human rights violation. It restricts the ability of people to lift themselves and their families and communities out of poverty. The economic costs of trafficking are considerable. It is estimated that the opportunity costs of forced labour amount to $21 billion annually. / The UN definition of trafficking includes the recruitment, transportation or harbouring of human beings by threat, use of force, coercion, abduction, fraud, deception and/or abuse of power for the purpose of exploitation. Most of the international effort on human trafficking has focused on sexual exploitation. However labour trafficking, which is far more prevalent, has been relatively neglected. / However, preventing trafficking and forced labour of women and girls is complex and challenging. There is little robust research and evidence on trafficking in the garment or domestic work sectors in South Asia. And there is little available data as it is a criminal act that takes place under the radar and is fuelled by corruption. What evidence does exist has not been coordinated or adequately captured and as such remains weak. There are also different approaches to tackling trafficking and it requires careful coordination across different government ministries, agencies, international organisations and civil society groups. That’s why the purpose of this first stage of DFID’s Human Trafficking programme has been to support the development of an improved evidence base so that we can understand the nature of the problem, review the evidence and identify DFID’s comparative advantage. / The programme to tackle trafficking will help deliver DFID’s Strategic Vision for Girls and Women in two priority areas - Preventing Violence against Women and Girls; and increasing Direct Assets for Girls and Women through better wages, working conditions and remittances from safe labour migration. It will also help deliver DFID’s public commitments as part of the UK Government Strategy on Human Trafficking.

## Section A: Detailed Output Scoring

Output 1: To demonstrate practices, approaches and results that can prevent trafficking of girls and women into domestic and garment sectors in South Asia and that show an integrated approach with potential for scalability, partnership and innovation.
Output 1: final score and performance description: A+ (Outputs moderately exceeded expectation) / Under this output, a number of external partners were contracted to deliver five pilot projects that: ‘demonstrated practices, approaches and results that can prevent trafficking of girls and women into the domestic and garment sectors in South Asia and that show an integrated approach with potential for scalability, partnership and innovation’. / All five pilots have been successfully delivered, and all met and in some cases exceeded the expectations set out in their respective Terms of Reference. The pilot projects were (with the contracted organisation shown in brackets): / Vivhaan: Using Innovative Technologies to Prevent Human Trafficking (Nimbus) / Voice and Participation of Trafficked Women and Girls (GAATW) / Preventing Trafficking of Women and Girls into the Garment Industry (ILO) / Preventing Trafficking of Women and Girls for Domestic Work (ILO) / Personal Costs: An analysis of the policies and practices affecting Nepalese migrant domestic workers travelling to Lebanon (Anti-Slavery International) / Taken together, the pilots delivered an impressive set of results, including: / Over 4,000 vulnerable women and girls were engaged in face to face dialogue on human trafficking, for example through community workers who conducted local visits; / Over 650 police were trained to better respond to labour trafficking; / 82 community workers were trained to either travel to local, vulnerable communities and help women and girls avoid being trafficked or work with victims of trafficking. / A new web and mobile platform was built to empower women and girls to find decent jobs and migrate safely; / A wide range of capacity building initiatives were supported to help governments, police and local officials, trade unions and civil society groups better respond to human trafficking in the textile and domestic work sectors; / And while not explicitly the role of these pilots, 14 instances of trafficking were identified leading to the rescue of 4 victims, re-uniting them with their families. / Across these activities, the pilots generated a wealth of insights and findings that together contributed to achieving Output 1. These are set out in detail in the five ‘end of pilot’ reports but, to demonstrate delivery against expected output for the purposes of this Review, these include: / Why women migrate – Research conducted as part of the pilots found that two of the key drivers of women migrating for work are low family income (women who migrate are often the sole provider of income for their family) and a lack of local opportunities. / Victims of trafficking? - Talking to returned migrant women, one of the pilots learnt that many don’t view themselves as having been trafficked, despite the fact that the suffered terrible abuse and exploitation. This is largely because they decided freely to move to another country to seek work. / Recognising labour trafficking - One of the key challenges has been getting the conversation on human trafficking to recognise the issue of labour trafficking, as much as sex trafficking. There are few trafficking programmes specifically addressing labour trafficking. And many victims are not identified as ‘trafficked’ by legislation - in either their destination or country of origin – so few ‘anti-trafficking interventions’ are able to reach them. / Face to face outreach works - Surveys showed that women who participated in such sessions within their local communities achieved significant increases in knowledge (e.g. awareness of the availability of pre departure training increased from 50% to 96%). / Use of innovative technologies such as tablet computers by Community Knowledge Workers (CKWs) worked well. The tablets generated interest and awareness with women in local meetings (e.g. via video, women’s stories and visual tips for safe travel). They not only helped to establish CKWs’ status on arriving in a community, but also provided an opening to discuss the issues, helped avoid ‘loss of message’ and worked especially well for people with low literacy. / Pre-departure /skills training – Focus groups demonstrated that women for the most part did receive pre-departure training on the risks they could face, but that it didn’t provide what would have been most useful to them – information and advice on what to do if they find themselves exploited, trafficked or abused (e.g. where they can go to seek help – organisations, embassies, the authorities), and what they were entitled to (e.g. Government insurance schemes in Nepal before departing). Follow up reports from Anti-Slavery International highlighted that, in the case of Nepal, many women were effectively discouraged from attending pre-departure or skills training because 1) they are all held in the capital Kathmandu; 2) the length of training can be up to 21 days and 3) while the cost of the courses are subsidised, few costs are paid for food or accommodation. / Big brands working with trade unions - Working with the private sector within the global supply chain to join them in dialogue with trade unions meant they were able to understand that a) they had a responsibility to help ensure they didn’t employ trafficked workers and b) that trade unions weren’t just a force that advocated against employers but could work closely with employers and help them to overcome some of these issues. / Multi-dimension interventions are needed - Donor funding for purely project/activity based interventions needs to be matched by allocations for building research, analysis or advocacy capacity of NGOs, the authorities and others to ensure sustainability. / Multi- partner approach - The model of involving a number of partners in delivering anti-trafficking projects proved highly successful – it enriched available expertise and improved project implementation, and should be built on in future programmes. / All of these insights (and significantly more within the fuller pilot findings) have been able to inform the design of DFID’s new anti-trafficking programme in the region to ensure it delivers effective outcomes and achieves the desired impact.
Final results: / This review concludes that the pilot programmes achieved and moderately exceeded the expected performance against targets for Output 1, as set out in the logframe. This is because: / A greater quantity of outputs was generated than expected, and within existing resources – for example Anti-Slavery International were – with prior agreement from DFID - able to produce additional, related pilot projects; and / The quality of the outputs was higher than expected for such a modest investment and the pilots in some cases exceeded the expectations set out in their respective Terms of Reference. For example, while the purpose of this phase of the programme was to generate evidence, some projects were able to prevent actual cases of trafficking. / Impact Weighting (%):50% / Revised since last Annual Review? No / Risk: Low/Medium/High / Revised since last Annual Review? Medium

Output 2: To develop evidence and lessons of what works on labour trafficking prevention in South Asia.
Output 2: final score and performance description: A+ (Outputs moderately exceeded expectation) / Work towards this output has performed well, exceeding expected results targets as described below. / This Output exploited the expertise of LSHTM, ILO, academics, donors, private foundations, NGOs, global and regional trafficking experts, practitioners and policy makers. It enabled a wide-ranging review of the evidence and experience in this field and lessons to inform the design of the future DFID programme. Through this process, DFID was seen as a catalyst for transparent and collaborative knowledge-sharing in the field of trafficking and praised by global experts as modelling good practice on evidence-based policy and programming. This was also achieved in a cost-effective way, delivering good value for money. / Output Indicator 2.1: Number of literature review papers that examine legal, policy, institutional and implementation issues of trafficking women and girls in the labour sector in South Asia. [Target: 3] / A total of four literature review papers were delivered. / The Governance and Social Development Resource Centre was commissioned to undertake a rapid literature review that assessed the evidence of impact from trafficking programmes globally and in South Asia. Their work outlined promising examples of success and lesson-learning. The GSDRC also delivered an additional literature review paper (at no additional cost) identifying the key actors with an established track record of programming and credibility on trafficking, particularly in South Asia. / A non-funding partnership with the Harvard Kennedy School of Government provided a legal expert for six weeks to conduct a literature review that analysed each target country separately (Bangladesh, Nepal and India). It delineated the laws and policies relating to trafficking, labour and migration, and analysed the evidence of government measures successfully implemented and gaps that remain. It reviewed programmes in Asia aimed at influencing legal and policy change, and the support provided by donors, international, regional and non-governmental organisations, and the private sector. The paper also made recommendations for potential approaches, priorities and gaps requiring further work. / The London School of Hygiene and Tropical Medicine (LSHTM) were identified as the implementing partner leading on this component for the pilot project phase. The LSHTM has over ten years of experience of research and evaluation work on trafficking and violence against women, and is regarded as a global leader in this field of research. / The LSHTM conducted two systematic reviews of interventions (presented in one paper) looking at bibliographic databases for relevant articles published in English between 2005 and 2012. Additional documents were located through consultation with experts, search of relevant websites and using reference snowballing techniques. The study was additionally guided by two key questions: / Which are priority components that are either essential to or most likely to have the greatest impact on reducing trafficking of women and girls for domestic or garment labour? / Which are the most complementary or synergistic activities that, when conducted in parallel or together, are most likely to achieve ‘more than the sum of their parts’? / Results found no peer-reviewed articles on evaluation of anti-trafficking programmes for forced labour or labour exploitation in the garment or domestic work sectors. Documents most commonly located were process evaluations, operational studies and dissemination reports, primarily based on qualitative data and desk reviews. In the absence of rigorous evaluation data it was difficult to gauge the effectiveness of interventions. Aims of the most common intervention activities were to: strengthen legislation and law enforcement; reduce higher risk labour migration; and detect and interrupt trafficking situations at destination or offer assistance to leave trafficking situations. / Output Indicator 2.2: Number of workshops supported that bring key donors and stakeholders together to share latest evidence and lessons on preventing labour-related trafficking in the garment and domestic work sectors in South Asia. [Target: 1] / DFID held a South Asia Regional Anti-Trafficking Workshop in Bangkok over 26-28 June 2012 in conjunction with the ILO. This expert group meeting aimed to build a platform for knowledge, programming and coordination to identify and implement the most promising intervention approaches. It shared evidence and lessons on trafficking interventions in the garment and domestic work sectors in South Asia, including findings achieved through the DFID sponsored pilot projects. / The workshop benefitted from excellent attendance with over 60 experts participating, including representatives from international and non-governmental organisations, and government and private donors focussing on trafficking and forced labour. Groups included organisations providing direct services, conducting advocacy, forming coalitions and providing funding, technical and other support for activities to prevent or interrupt human trafficking, specifically programming that included women and girls in forced labour in the garment and domestic work sectors. / Evidence from the final report of the workshop shows that it achieved its objectives, and that the dialogue was “constructive” and helped to establish where DFID could “add value to existing anti-trafficking efforts” and “what works, what’s replicable or scale-able in other sectors or countries”. / In particular, it met its objectives: / To network and build partnerships; / To learn lessons from our pilot programmes – including discussing lessons around “building coalitions, trying more integrated and ‘whole trafficking chain’ approaches”; / To build the evidence – helping to understand “the data and evidence there is on what works and why, and identifying gaps”; and / To help DFID think through the design of its programme – “building and complementing what’s there already, identifying key gaps and specific indicators and outcomes we want to support and help partner countries deliver”. / It exceeded its objectives in a number of areas that were unforeseen: / It fostered new partnerships and collaboration by bringing together key actors in the field of trafficking that were previously highly polarised and hostile towards one another – particularly on approaches to sex trafficking. Participants reflected that “it was the first time this set of actors had all been in the same room at the same time – learning from one another and developing new insights”. This happened because DFID’s approach was to encourage lesson-learning in an open, transparent way, and invited a wide range of stakeholders with experience and expertise on labour trafficking and labour migration – including victims of trafficking, trade unions, policy makers and international agencies. / DFID was praised for modelling good practice in evidence-based programming: it subjected pilot programmes to open and transparent peer review and scrutiny (unheard of previously, according to those present). It also broke new ground by inviting a wide range of actors to help design a theory of change for DFID’s new programme based on lessons and experience of what has failed, and what works. It was clear that most donors did not share their evaluations of anti-trafficking programmes, and continued to design new programmes despite evaluations showing poor results, and demonstrated little attempt to learn lessons. DFID’s focus on building an evidence base is regarded as one of the most valuable contributions it could make to the global knowledge public goods because a rigorous evidence base does not exist. / Output Indicator 2.3: Number of logframes designed that provide a robust measurement and evaluation framework for delivery of DFID’s Asia Regional Human Trafficking Programme. [Target: 1] / As part of work to design the programme for full implementation, a logframe was developed jointly between DFID, LSHTM, and the ILO, to provide a robust framework to support the monitoring and evaluation of DFID’s Asia Regional Human Trafficking Programme. This drew extensively on the theory of change for the project developed with the LSHTM, which in turn considered in full the existing evidence as outlined in the literature reviewed discussed above. The result is a logframe complete, in general, with indicators, baselines, milestones, targets and assumptions. / In addition to the monitoring framework set out in the logframe, great consideration has been given to the evaluation of the ARHTP, in consultation with the LSHTM, ILO and DFID. This is likely to include two Impact Evaluations to build the evidence base for what works to prevent labour-trafficking in the garment and domestic sectors of South Asia. It is notable that the considerations are continuing apace at this early stage of the project, in order to inform an appropriate and rigorous Ex-Ante Impact Evaluation design. The inclusion of monitoring and evaluation partners at the early stages of design of a programme is not usual, but is regarded as best practice in evaluation. It ensures that indicators set in the logframe are evaluable and will enable wider conclusions to be drawn for the benefit of others.
Final results: / This review concludes that the activities undertaken achieved expected performance against targets for Output 2, as set out in the logframe. / Impact Weighting (%):50% / Revised since last Annual Review? N / Risk: Low/Medium/High / Revised since last Annual Review? Medium

## Section B: Results and Value for Money.

1. Achievement and Results
Has the logframe been changed since the last review? No. / 1.2 Final Output score and description: A+ (Outputs moderately exceeded expectation) / All key activities fully and successfully achieved their objectives. Some exceeded the objectives.
Direct feedback from beneficiaries / All of the pilots engaged with target groups of vulnerable women and children in focus groups, community village meetings, through trade union or migrant worker associations to inform their interventions and to ensure they were relevant to the needs of migrant women. There was positive feedback from beneficiaries who said they felt pleased to be engaged as key stakeholders and not just recipients of project interventions. For example, beneficiaries of the ILO-led pilot project on domestic work said they “felt empowered after the completion of pilot training activities”. / The pilot projects also engaged in a range of training and capacity building initiatives, which received positive direct feedback from beneficiaries and participants. For example 94% of government and other key stakeholders who participated in the ILO-led training/workshops felt their workplace would benefit from their newly acquired knowledge. And the Nimbus-led work to train police officers in garment sector related trafficking was very well received – to the extent that it secured the commitment to include a bonded labour curriculum in standard police training in Chennai, which will reach over 12,000 new police recruits this year alone. / One of the pilots (delivered by the Global Alliance Against Traffic in Women) specifically focused on voice and participation of the beneficiaries of anti-trafficking programmes. In-depth interviews were carried out with 420 women in 8 locations across India, Bangladesh and Nepal. These provided rich information and analysis that will ensure better design and delivery of the DFID programme so that they meet the needs and priorities of those who experience the direct impacts of trafficking. After participating, women also had a visible increase in confidence, an ability to better articulate and analyse their own experience and a feeling of being part of a group.
1.4 Overall Outcome score and description: A(Outcome met expectation) / The desired outcome of this pilot programme (as stated in the logframe) was to design a new programme to help women and girls protect themselves from being trafficked is based on evidence of effectiveness and impact. / The projects and other activities conducted through this pilot programme have enabled the outcome to be achieved by contributing to an evidence base on what activities would work. DFID ministers approved the new programme in early 2013. The Business Case for this new programme drew extensively on the lessons and evidence generated through the pilot programme. / The pilot programme contributed by achieving and moderately exceeding the key outputs (as below) in a way that exceeded expectations on quality. / Expected outputs: Actual outputs / 5 pilot projects, 5 pilot projects (plus 2 additional / sub-pilot projects) / 3 literature reviews 4 literature reviews / 1 lesson sharing workshop 1 lesson sharing workshop / 1 M&E framework 1 M&E framework / In addition, the pilot programme achieved a set of beneficial results in how they were conducted that was not originally stipulated in their respective Terms of Reference. This included reaching a significant number of beneficiaries (including some 4,000 vulnerable women and girls and 650 police officers) . / The overall Output score is therefore A+ (outputs moderately exceeded expectation). / 1.5 Impact and Sustainability / The desired ultimate impact of the programme (as stated in the logframe) is to reduce the incidence of trafficking for garment and domestic work among adolescent girls and women from Bangladesh, India and Nepal. / This programme has been able to contribute directly towards this objective by laying the foundations for DFID’s new programme, which seeks to help 100,000 women and girls in this respect by 2018. The pilot programme is also able to demonstrate strong principles of sustainability because its work is being continued through the new DFID programme and because the lessons, insights and evidence generated are being shared extensively with wider partners and actors in the field of trafficking, so that their work may benefit in the longer term.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / £500,000 was approved for the Inception and Pilot Phase of the programme, and a further, £50,000 was requested to cover additional costs for a multi-stakeholder planning workshop and costs for monitoring and evaluating the inception phase. Total costs for the pilot phase have been just under £550,000 with the bulk of those costs being used to finance the five pilot programmes. / 2.2 Key cost drivers / The key cost drivers in this pilot were to ensure that the bulk of the costs were spent on delivering direct benefits for women and girls, rather than on institutional costs or legal and policy work. To achieve this, there was a reliance on partners’ existing institutional arrangements and partnerships to ensure an enabling environment for these interventions. This was viable only because it was a short-term pilot, and was delivered at the cost of partners’ own resources. / 2.3 Was the project completed within the expected timescale: No / There were some delays due to unforeseen circumstances including to contracting, localised flooding etc. This meant that some of the projects were not able to follow the original timetable. However all have now been delivered and have been able to contribute to the design of the full anti-trafficking programme, which was the intended purpose of their work.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / As a direct result of the piloting and evidence work carried out as part of this project, there has been a notable improvement in evidence in relation to the specific field of the trafficking of women and children into garment and domestic work in South Asia. This will have benefits and implications for the detailed design of future programmes run by DFID and other partners. / 3.2 Set out what plans are in place for an evaluation. / N/A. A robust Measurement and Evaluation programme is in place for the main implementation phase of this programme, which – at the time of writing - is just in the process of being operationalised.

4. Risk
4.1 Risk Rating (overall project risk): Medium / The risks for this phase of the project have been defined as medium. Detailed risk assessments will be carried out in later stages as the programme enters its implementation phase. / Did the Risk Rating change over the life of the project? No / 4.2 Risk funds not used for purposes intended / All results have been achieved exceeding expectation in some areas, and there is no risk of funds not being used for their intended purpose. / 4.3 Climate and Environment Impact / Environmental degradation and climate change can have an impact on human trafficking. There are indications that growing numbers of migrants today are those who've experienced economic and livelihood shocks as a result of natural disasters or environmental degradation. When poor families are desperate to migrate abroad for jobs quickly, they are more vulnerable and at risk of using traffickers as intermediaries. The UN’s recent report (‘Human Security, Climate Change and Environmentally Induced Migration’) for example identified that 125 million people are likely to migrate in the Indian sub-continent in the coming century due to environmentally induced factors. / The work to tackle human trafficking can therefore have a potentially positive effect on people impacted by climate change. It is also able to help improve the financial literacy of vulnerable families and their working conditions when migrating for jobs. / If migration continues to increase there is likely to be an increased burden on natural resources (energy for transport, impact in urban areas on water, food etc) in the long term. However, since this programme is not promoting migration per se, but merely seeking to ensure it is safe and free of trafficking, this impact risk cannot be attributed to this programme. However, travel undertaken for programme activities contributed to increased carbon emissions. The requirement to travel was considered carefully and minimised wherever possible. Virtual meetings and email communication were used as much as possible.

5. Value for Money
5.1 Performance on VfM measures / This programme represented strong value for money across a number of areas. First, by involving a significant number of other multilateral and NGO partners, this programme used their stakeholders and existing resources to generate additional value for money. (A result that achieves ‘economies of scale’ and that is greater than the sum of its parts). / DFID was able to exploit the expertise and institutional infrastructure of each of the pilot partners to ensure that only new, innovative and catalytic interventions were funded. Whilst the larger institutions could absorb these costs, it was more challenging for smaller organisations. However each pilot partner was keen to be part of this initiative, and as such, found ways to draw down other resources. / Two of the contributions to Output 2 to build the evidence were cost-free: the GSDRC Helpline service, and a non-funding partnership with Harvard Kennedy School for a six-week graduate internship using a legal expert on trafficking. / The work also dovetailed with wider activities and initiatives, such as DFID’s Responsible and Accountable Garment Sector (RAGS) Challenge Fund and its Retail Business Innovative Facility (RBIF) and together helped to improve working conditions and responsible labour practices, especially for women and girls, in a more efficient manner. / 5.2 Commercial Improvement and Value for Money / The Monitoring and Evaluation Manager was selected through a competitive tendering process managed by Procurement Department, meeting requirements of OJEU. The Board comprised representatives from Procurement Department, Evaluations Department, a DFID country office, the Lead Adviser and Programme Manager in the Asia Regional Team and an external trafficking expert from Newcastle University. The Board agreed the Terms of Reference, and scrutinised two stages of bids over a period of four months before deciding on the London School of Hygiene and Tropical Medicine. The LSHTM is a trusted and credible evaluation partner for DFID on a number of global programmes. / A competitive bidding process was used for the pilot partners. Terms of Reference were shared widely through DFID’s own resource centre networks as well as key trafficking delivery and policy institutions operating globally and in Asia. There was a high level of interest and wide range of bids received from stakeholders that reviewed by a Board of DFID staff from different departments and country offices before selecting the five projects. / Value for Money, track record of results, credibility of delivery partners and individuals were amongst the factors considered, meeting best practice in DFID’s procurement procedures. / Costs for the regional workshop were carefully considered with high attention to value for money and limiting budget expenditure. The decision to hold the workshop in Bangkok was made because many of the Asia regional institutions tackling trafficking are based there. Hotel and flight costs were also far cheaper for people travelling from Bangladesh, India and Nepal, and visa restrictions in some countries also made this a good choice to secure participation from all key stakeholders. A modest hotel and conference centre were selected from a range of options. Relative costs and feasibility were investigated for hosting this event in Bangladesh, India and Nepal – including in DFID offices - but were found to be not as cost-effective or reliable as Bangkok (there were a number of other factors such as political instability and flooding taken into consideration). Where possible, attendees paid for their own flight and accommodation costs; and none of the invited experts were paid a consultancy rate to attend and share their expertise. Other costs such as note-taking and translation that are normal for such an event were not incurred because attendees were asked to volunteer their time for these tasks. / 5.3 Role of project partners / This project intentionally took an approach that involves multiple project partners. All partners performed well and met or exceeded their objectives, either in quantity of results achieved and/or quality. Feedback has been that the model of involving a number of partners in delivering anti-trafficking measures has proven highly successful. It enriched available expertise and improved project implementation, and should be built on in future programmes. / 5.4 Did the project represent Value for Money : Yes / The projects have delivered a wide-ranging and impressive set of activities and results for an extremely modest investment. / For example, for an investment of less than £100,000, Nimbus worked with six other partners to deliver an impressive set of results in just 3 months, and help make a tangible difference to people’s lives. The project reached 3,500 people; trained 30 Community Knowledge Workers to travel to local communities and work with them on the issue of trafficking; trained 650 police officers to improve how they identify and respond to victims of trafficking, and identified 14 instances of trafficking, so far leading to the rescue of 4 victims, re-uniting them with their families.

6. Conditionality
6.1 Update on specific conditions / N/A. This project does not provide Financial Aid given directly to a partner government so this section on UK conditionality does not apply.

7. Conclusions
The pilot phase of DFID’s Asia Regional Human Trafficking programme has been ambitious but our partners and contractors have delivered a set of impressive results commensurate to the challenge, which have either met or exceeded expectations and that have demonstrated excellent value for money. This has directly helped DFID to design a cutting-edge new Human Trafficking programme that draws on the evidence, lessons and findings of the pilot project work. This is – at the time of writing – beginning the first of its five years of operations.

8. Review Process
DFID requested all project partners to complete final reports detailing activity completed against the Terms of Reference, findings and results, financial data and where relevant providing ratings against delivery. / In addition to reviewing the five project completion reports, the Review incorporated an appraisal of following documents: / Theorising and measuring change: Prevention of trafficking of women and girls for domestic and garment work, LSHTM, June 2012 / Review of the literature on interventions to prevent trafficking for labour exploitation, LSHTM, June 2012 / Human Trafficking in South Asia: Piloting new approaches and improving the evidence base - A summary of results from DFID’s five pilot projects, DFID internal document, April 2013 / Asia Regional Trafficking Programme (ARTP): Report from the expert group meeting (26-28 June 2012) to inform DFID’s trafficking prevention programming 2012-2015 (July 2012) / The Business Case for the Asia Regional Anti-Trafficking Programme – Pilot Programme (DFID 2011) / The Logframe for the Asia Regional Anti-Trafficking Programme – Pilot Programme (DFID 2011) / The four Terms of Reference for each of the primary pilot project contractors (2011-12) / The detailed guidance (How to Note) - Reviewing and Scoring Projects (Nov 2011) / Key data from ARIES, including the risk rating / The separate project scoring calculation sheet / In line with DFID guidance, the relatively small-scale budget for this programme has dictated an appropriate and proportionate investment of staff administrative and management time in this review. However a rigorous approach was none-the-less taken to assessing this inception phase. / This Review was conducted over July 2013 by the Policy and Partnerships Manager within the Asia Regional Team at DFID, with oversight by the Senior Social Development Adviser for Asia, and sign off from the Deputy Director of Asia, Caribbean and Overseas Territories Department. / This Project Completion Review draws heavily on the recently completed Annual Review for the pilot programme. This is because the vast majority (an estimated 95%) of the pilot programme’s activities had been completed and assessed by the time of that review. It was not possible to conduct a full Project Completion Review at the time of the Annual Review because all project documents and payments had not yet been received and finalised.