Type of Review: Annual Review

Project Title: Trade Transparency Project

Date started: July 2012	Date review undertaken: June 2013

## Introduction and Context

What support is the UK providing?
The UK is supporting work to analyse trade and consumer price data and develop mobile phone applications and other online tools (such as interactive websites, games or infographics) to make this data more accessible to ordinary people. This will help people in the developing world to understand how trade policy affects them. / Hack days were held in Lagos, London and Cape Town, bringing together a mix of IT coders and developers, graphic designers and community activists to come up with locally relevant solutions for presenting the data. The process was filmed in all three locations to enable the team to share lesson-learning with DFID colleagues given that hack days had never been tried before. / Building on this early work, a second phase has been launched which takes some of the best apps or tools and provides support to partner organisations to develop them further and disseminate them more widely to reach larger numbers of users. / The total approved budget is £300,000 up to April 2014.

What are the expected results?
The project was designed to produce mobile phone applications or online tools that communicate the impact of trade barriers on consumer prices to a large audience. The original logic for the results chain was as follows: / Large number of consumers become more informed about the impact of trade barriers on their shopping baskets; / Increased public debate and advocacy on free trade; / Increased number of formal and informal consumer and other citizen groups formed and lobby government on free trade. / Governments’ trade policy decisions become less protectionist as a result of citizen-led lobbying and advocacy; / Trade increases in countries that lower trade barriers as a result of advocacy; / Increased trade leads to more jobs, increased income and poverty reduction / Other results are also to be expected from an innovative project such as this. Breaking down data and making it more accessible, as well as encouraging the release of new data where possible, helps to increase transparency around trade issues. Ordinary people are informed and empowered by access to the information and may choose to use this information in a variety of different ways.

What is the context in which UK support is provided?
Trade and growth / This support is in line with the broader DFID wealth creation agenda as identified in the Structural Reform Plan (2011-2015). This plan draws on a body of evidence that shows that growth is the most effective means of raising incomes, creating jobs and reducing poverty in the developing world. Trade drives long term economic growth and the key to achieving increased trade is policies that promote trade openness. According to the World Bank, in the 1990s per capita income grew more than three times faster for those developing countries that lowered trade barriers (5% per year) than for other developing countries (1.4% per year)[1]. / The Trade Transparency Project is one of an ambitious portfolio of DFID programmes designed to improve trade openness and thus the ability of developing countries to grow through trade. Many governments in developing countries (and some NGOs in developed countries) believe that protectionist measures such as tariffs are necessary to protect domestic production and jobs. The negative impact of these measures on consumer prices in the short term and the potential to disrupt lasting growth and development is rarely highlighted. / Transparency and accountability / In part, this is because trade data is quite widely available but is complex and largely inaccessible to non-economists. This means that many people do not understand the implications of the decisions on trade policy being made by their own governments. Furthermore, there are few consumer advocacy groups in Africa and the developing world; this is not an issue that is debated outside of specialist spheres and it is not something that ordinary citizens have any say over. / Thus it is clear that the Trade Transparency Project, with its focus on improving transparency and accountability for trade policy decisions, also fits well with the open societies and open economies agenda. Transparency is an essential characteristic of good governance and the free availability of information is an indicator of a functioning democracy. Promoting advocacy and citizen engagement more widely might empower citizens to influence government policies. / New technologies / The use of hack days to produce applications and online tools is a new process for DFID (although it is increasingly being used by the private sector and other government departments). It is particularly relevant for a transparency project such as this. There has been an exponential increase in the use of new technologies in the developing world, including mobile phones, internet and other media. This enables projects to reach potentially huge numbers of people around the world: the number of mobile phone subscriptions in South Asia and Sub-Saharan Africa was well over 1 billion in 2010 (World Development Indicators, 2010). Many of these mobile phones are feature phones or ‘dumb phones’ with only SMS capability, but some applications can be tailored to work on basic handsets. / In South Africa, DFID has partnered with Mxit – the biggest social media network in Africa – to host the Trade Transparency Project applications in a suitable format. Mxit has 50 million registered users across Africa and can operate on 3000 mobile phone handsets. The potential reach of an application hosted on the MXit platform is huge.
[1] OECD, ILO, WORLD BANK, WTO (11-12 November 2010) “Seizing the benefits of trade for employment and growth”, final report, Prepared for submission to the G-20 Summit meeting Seoul (Korea), http://www.oecd.org/dataoecd/61/57/46353240.pdf

## Section A: Detailed Output Scoring

Output 1: Online tool is launched to illustrate the impact of trade barriers on consumer prices
Output 1 score and performance description: / A++ Outputs substantially exceeded expectations
Progress against expected results: / Indicator 1: Online tool launched / Several online tools and mobile phone applications have been launched, thus substantially exceeding the single tool expected in the programme logframe. 25 tools were launched in prototype format and hosted on the Rewired State site. Three of the most developed prototypes were demonstrated by representatives from RLabs and Rewired State at the Omidyar Open Up! Conference and by CCHub at the DFID Digital Development Day in November 2012. / Five tools have been selected for further development to include incorporating more data and increased functionality – three of these are being hosted on the Mxit social media platform and two are stand-alone websites. Of these five tools, three focus on illustrating the impact of trade barriers on consumer prices or on making trade data more understandable while the other two adopt a slightly different approach – crowdsourcing consumer price information and enabling informal traders to market their products respectively. / Indicator 2: Number of people reached through HMG communication channels / The number of people reached through HMG communication channels has not been significant. This is because the apps and tools were not suitable for hosting on the DFID website but instead have been hosted on Mxit and standalone platforms. In fact this has meant that the apps should be able to reach many more people than was originally anticipated, although it is still early days for drawing any conclusions. Early versions of the apps on Mxit have attracted 190,634 users in 101 countries with new users being reached on a daily basis. Monitoring information is not yet available for the other online tools. / Recommendations: / This output has been achieved and in fact substantially exceeded. But it is not enough. The Rewired State website, where information and links to the apps are currently displayed, does not attract traffic from as wide an audience as the project hopes to reach. It is not clear that the early hacking work has made much of a difference. Further support is needed to host the applications in an accessible and prominent location, to continually develop and modify them in line with user needs and to reflect new data, and to disseminate them as widely as possible. It is recommended that at least one other Output be added to the logframe to cover this process. It is also recommended that the milestones be adjusted up to be more ambitious and reflect the greater than expected popularity of the apps. / Impact Weighting (%): 100 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? / No. However it is recommended that the logframe be updated following this review to include another Output and adjust the success indicators. / 1.2 Overall Output Score and Description: / A++ Outputs substantially exceeded expectations / 1.3 Direct feedback from beneficiaries / The idea of hacking trade data was well received in all three locations. Working with multiple partners and making use of in-country talent was seen as a very positive approach. / In Cape Town the event was credited with “bringing together diverse people with diverse sets of skills putting their resources and their efforts into using those talents for good” (Marlon Parker, RLabs). In Lagos, a hackathon participant praised the concept of giving data to the people “to see what they think about it, what they can do with it, rather than making assumptions” (Chuka Ofili). These participants are direct beneficiaries of the programme in that their understanding of and engagement with trade data has been increased, but they will also play a crucial role in sharing this understanding with other people through the apps and tools that they create. They “used the data not just to empower themselves but also to add value for other community members” (Marlon Parker, RLabs). Their engagement and enthusiasm is thus essential for the long-term success of the project. / Those people who use the apps and tools will be able to use feedback features to record their thoughts and comments. However, because the apps are in the early stages of development, these features are not yet operational. Nevertheless, the act of downloading an app or spending time on a website suggests an interest in the work of the project and the potential for future engagement.
1.4 Summary of overall progress / Progress has been strong both in terms of output delivery and laying the groundwork for the project in the longer term. Highlights include: / Successful hack days in three locations: the hack days ran smoothly and teams engaged with both data sets to generate a large number of varied tools and applications in prototype format. / Promising early usage statistics: despite most of the apps being at an early stage of development, the level of engagement through the Mxit platform has been very encouraging and the potential reach is much larger than had originally been envisaged. / Decision to take five tools forward: the best tools and applications are being taken forward for further development and dissemination over the coming months to reach a wider audience and ensure the apps reach their full potential / Enthusiasm and excitement generated: the hack days encouraged teams (and local media outlets) to engage with trade issues that they had little prior knowledge of. In DFID, the potential of hack days for improving transparency and accountability is also beginning to be realised. / In fact during the course of the project, the focus of the work and the expected results have shifted slightly. Engagement with stakeholders and hack day participants in the three locations led to an identification of much broader and locally relevant needs. For example, in Cape Town, efforts to improve economic literacy or to enable local traders to boost business were seen as more relevant than the free trade debate. Teams took very different directions that could not have been foreseen, which is perhaps unsurprising because the project team deliberately did not specify any preferred solutions or outcomes in order to encourage the development of locally relevant solutions. As a result, raising awareness or educating people or enabling small businesses to benefit from sharing data became ends in themselves.
1.5 Key challenges / A number of challenges have arisen during the course of both the inception and implementation stages of this project. / Inception / One of the main challenges faced in the early stages was the difficulty of obtaining consumer price data for a sufficiently diverse range of countries and products. In fact one of the main advantages of hiring the Economist Intelligence Unit was that they compile a Cost of Living Survey database for a wide range of countries, although this data is not publicly available. Interestingly, one of the applications developed and being taken forward in the second phase of the project has a crowd-sourcing feature to obtain price data, which overcomes the limitations of being confined to a proprietary database. / The analysis of the impact of trade barriers on consumer prices also did not present clear results: the effects identified varied a great deal by country and were in many cases statistically insignificant. It is important to note that this is consistent with the evidence available on the relationship between prices and trade barriers as identified in the scoping phase. In order to address this challenge, the scope of the project was widened beyond the original question of how trade barriers affect consumer prices. In addition to the EIU data, other economic and trade related data such as data on trade costs, time taken to trade, business environment etc. were provided for the hack days from the World Development Indicators database. It was hoped that the developers would be able to use these data to build applications that could be still be used to inform everyday people about the importance of trade and how it affects them and the countries they live in. Feedback from one technology hub justified this choice: the usability of the data was rated as “8/10”. / Implementation / During the hack days, it quickly became apparent that there was a much lower than expected capacity amongst participants to understand trade data and economic concepts. Grasping the meaning of complicated data was essential to be able to create useful tools and a lot of support from the DFID team was needed to help explain it. The technology hubs also sought external assistance: RLabs partnered with UCT Business School and CcHub consulted a trade expert to deliver a presentation on trade economics at the hack day. / It also became clear, as outlined above, that teams would most likely produce locally relevant solutions that might diverge slightly from the original idea. Because of the innovative and creative nature of the project and the need to make tools as useful and meaningful as possible, this ‘challenge’ was embraced as an opportunity and a positive outcome from using the hack day methodology. However it does mean that the impact of the project might differ from what was originally intended – there is a risk that people becoming more informed about trade will not necessarily lead to the advocacy and lobbying activities that might encourage governments to make their trade policies less protectionist. / Original plans to host tools or apps on DFID IT systems proved to be unrealistic. DFID systems were not suitable and they do not engage with the target audience of citizens in developing countries. More suitable alternatives were discovered that could disseminate these apps to many more people (namely Mxit and standalone sites) although DFID lost some oversight of the content as a result. / Finally it became apparent during the course of this project that hack days are not an end in themselves – further support is needed to facilitate long-term hosting, on-going development and wider dissemination. Following an evaluation report in March 2013 – the TTP Pilot Evaluation - it was decided that several tools should be supported in order to enable this.
1.6 Annual Outcome Assessment / At Outcome level, informing and engaging with citizens about trade issues cannot yet be clearly measured. Nevertheless the interest and enthusiasm around the applications can be reported. The hack days succeeded in informing and engaging a variety of different people about trade issues, many of whom had very little knowledge to begin with. The number of users and comments on the Mxit apps also indicates some level of educating or informing users. The hack days generated a buzz in the local area and on social media sites: hack day participants tweeted about their work, one wrote a blog about the experience and in Cape Town the event was covered by a local radio station and newspaper. It was suggested that increased visibility from senior DFID staff or Ministers at the UK hack day might have increased this visibility yet further and reached more people as a result. / Nevertheless the process of raising awareness and engaging citizens takes time. Further Outcome level information should be available at the time of the next review.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / No. The project seems likely to significantly underspend. This is because the cost of hack days and application development has been much cheaper than was originally estimated. Because hack days are a new process for DFID, it was very difficult to forecast how much they might cost. In fact they have proved to be an extremely cost-effective way of manipulating data and creating apps and tools for use by ordinary people. This is because they rely on local people, many of whom have volunteered their time and expertise, and non-profit technology hubs. The costs of hosting applications or websites were also significantly overestimated. This is perhaps because the outputs are not being hosted in the UK but instead on more locally suitable sites or media servers. / 2.2 Key cost drivers / This has proved to be a relatively low cost intervention. The main cost drivers are outlined below: / Data analysis and modelling: this encompassed work by the Economist Intelligence Unit to analyse price data on consumer products in five countries which went on to form the basis of several tools and applications. / Hack day costs: running the three hack days in Lagos, London and Cape Town included costs to the technology hubs for fees, overheads and materials. / Development costs: there are costs involved in further developing five of the prototype apps, mainly around fees, web hosting, marketing etc. / Monitoring and evaluation: the hack days were filmed to enable monitoring of the process, there will be on-going monitoring of online metrics such as usage statistics, downloads, page views likes etc. to judge the output results / 2.3 Is the project on-track against original timescale: / The original timeframe for support was August 2012 to August 2013. However, the project has been extended to April 2014 to support the development and dissemination of five of the best tools and applications. This extra work falls within the original budget.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / In an innovative project such as the Trade Transparency Initiative, the evidence base is very limited as was discovered during the scoping phase, which is why a small pilot project was recommended. . / Several assumptions were acknowledged when designing the project. For example, there was a strong assumption that informing a large number of people would lead to advocacy and lobbying: because the apps remain in prototype format, it is too soon to judge whether or not this will come about. Moreover, given the nature of hack days and the widening of the scope of the project, it is possible that people would be more interested in other trade-related topics that they consider to be more relevant and would therefore not choose to lobby. At the next level up, it was assumed that lobbying would prompt governments to reduce trade barriers which would in turn increase trade and jobs: again, it is too early to judge this impact level response. Many of these assumptions should be revisited at a later review. / Output level monitoring has to date been disaggregated by sex, age and geographical location where applicable and where information allows it. This gives an indication of who is interested in these issues and has access to the technology required to engage with them. This will help not only to judge the impact of this particular programme but also to judge the possible target audience and expected results of the second phase of the project and indeed future programmes. / One of the main risks identified was that the target population would be limited to the young, urban and middle class. In terms of age at least, this has so far proved to be the case. Around half of the users of the two most established Mxit applications have been in the 18-25 age group and only around 10% were aged 36 or over. Further analysis would be required to determine the class and location of these users, but it would not be surprising if a project that relies on technology (and particularly mobile phones) would appeal more and be more accessible to wealthier, urban populations in developing countries. It is unclear how far this is a risk to the ultimate outcomes of the project because young, middle class urban dwellers are more likely to take up lobbying or advocacy activities than other segments of the population, but this is something that should be monitored going forward. In Phase II, perhaps an older demographic could be targeted as part of the dissemination strategy. / Nevertheless the target for phase I of the project was approximately 530,000 users (500,000 via Mxit and 30,000 through DFID channels). In phase II, this was expected to rise to 2 million people (based on the size of the potential target population in South Asia and Sub-Saharan Africa). Early indications suggest that this might be attainable: nearly 200,000 users have already engaged with the Mxit apps in their early prototype status despite there being no serious dissemination strategy. / Having said that, some elements of the project design would merit modification at this point. The level of understanding about trade policy amongst hack day participants and ordinary citizens was vastly overestimated at the beginning of the project. In fact, an earlier logic step of ‘large numbers of people understand and are informed about trade economics and policy’ is required in the results chain before looking at trade barriers specifically. / The creative process of hack days also resulted in a number of different takes on the original project proposal. For example, the ‘What’s Your Price’ app on Mxit started with the narrow data set on consumer prices for a limited number of products and countries, before moving on to crowd-source information for any product in any country. This will create a continually updated living database that will be far more useful for the average consumer. / This project contributes to understanding about transparency and accountability projects, specifically those relying on hack days to break down data. There has been a high level of interest in the project from other DFID teams. The project managers were requested to brief the Heads of African country offices, the extractives team, and a climate change project officer in China. A seminar to share experience of hack days with other DFID teams generated further interest from the Private Sector lead on land and property rights and the Civil Society Department. The Trade Transparency project might go on to inform the project designs of these teams in the coming months. It is also expected that this project might provide greater evidence on the link between increased transparency and outcomes such as lower trade barriers: there has been little discovered to date on the impact of such programmes. / 3.2 Where an evaluation is planned what progress has been made? / This is a relatively small programme and proportionality was an important consideration when planning its monitoring and evaluation. / Monitoring activity was built into the original plans for the hack days: a short film was produced to cover the process which has been shared widely in DFID. Plans are in place to monitor quantitative (e.g. usage statistics) and qualitative (e.g. comments and media coverage) indicators for the five developed applications up to April 2014. / In terms of formal reviews, an interim evaluation report was compiled by the DFID project team six months into the programme to check progress and guide the decision to scale up to Phase II. This Annual Review forms the next progress report and a Project Completion Report will be completed after the end of the programme.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / The Output risk rating was originally declared to be medium. However, this review helps to make the case for a reduction of this risk rating as the early results have exceeded expectations and the costs have been much lower than anticipated. / Previously identified risks include: / Timing of delivery (medium): this has been managed by close monitoring of progress against initial delivery plans and the inclusion of time-bound output milestones in all contracts with delivery partners. The project launched 25 prototype online tools ahead of schedule in October 2012 and contracts for the further development of five applications are based on tightly time bound payments, thus directly addressing this risk. / Financial risk (low): payments have been made on demonstration of output delivery and all partners have complied with the requirement for robust financial reporting. / New risks to consider: / Unintended consequences (medium): the online tools will be used and modified in ways that are relevant to people in developing countries, which may mean that they are not used to lobby governments for change and the expected impact of reduced protectionism may not come about. / Lower than expected usage (low): there are no guarantees to how many people will use the apps and tools. Early indicators give cause for optimism but a strong dissemination strategy will need to be in place to ensure that the maximum number and range of people are reached. / Interest and usage of applications sustained over time (medium) – there is a risk that many of the tools and applications developed may attract traffic when first launched and then interest drops off. Ways to keep people engaged will need to be considered.
Risk of funds not being used as intended / Funds are paid directly to partners in arrears upon demonstration of output delivery as detailed in milestone based contracts. Payments would be withheld if outputs were not delivered to a satisfactory standard. There is therefore very little risk of funds not being used as intended. / 4.4 Climate and Environment Risk / This programme was assessed as being low risk in terms of potential negative impact on climate change and the environment. This remains the case. Steps have been taken to minimise operational impacts, for example ensuring that DFID staff members travelled in economy class when attending hack days. In the Business Case it was suggested that a scale-up of the project might include opportunities to incorporate information on the environmental impacts of traded goods and how these bring additional costs to the consumer. This is not yet feasible as teams continue to work to build apps from the existing data, but it is something that might be considered were this project to be extended further.

5. Value for Money
5.1 Performance on VfM measures / This project was designed as a relatively low-cost option that might reach a potentially extremely large audience. The unit-cost measure was initially estimated to be in the region of £0.28 (£150,000 spent on reaching 530,000 people). / In fact, the cost of Phase I of the Trade Transparency Initiative came to £130,606 and reached at least 143,219 users, thus at a unit cost of £0.91 per user. However this figure is based on the usage statistics for just the two applications hosted on Mxit for which there is any data at this early stage of the project. There have been many more page views of tools and apps in their prototype state: for example, one application had received more than 7 million page views by July 2013, although it is unclear how many of these were repeat views. Clearly this unit cost ratio is set to reduce when more usage metrics are available and this is something that should be picked up on in later reviews. / Although unit cost measurement is an imperfect way of assessing VfM, the main benefits of transparency and greater consumer awareness are difficult to quantify and a benefits-to-cost ratio is therefore impossible to calculate. / 5.2 Commercial Improvement and Value for Money / Due to the small size of the contracts with service providers (well within the OJEU limits) single source procurement was used in all cases. In such a ground-breaking project, it was also inevitable that only a very small number of suppliers would have the requisite skills and capacity to undertake this work. This is particularly true when working in developing country contexts where technology hubs with hack day experience are not common. It was also important to tap into the local networks and knowledge of these institutions. Nevertheless, contract negotiations ensured that the costs were reasonable and it was possible to benchmark proposals in the three locations against each other. / All contracts are based on milestone payments and delivery of satisfactory outputs which ensures on-going VfM through delivery of the contract. / Going forward, two suppliers have been engaged to further develop five of the online tools and applications. The two supplies had already run the hack days and established effective working relationships with the teams behind the best applications. As this was an extension of earlier work, single source procurement was used. DFID Procurement Group were involved in negotiating one of these contracts, and advice was sought from Business Solutions Department and the Digital Team to help ensure the best VfM. / 5.3 Role of project partners / Implementing partners have been required to i) collect and analyse data, ii) develop, host and disseminate online tools, and iii) assist with monitoring and evaluation. DFID does not have the specialist expertise (and in the case of EIU, access to their commercial databases) necessary to undertake these tasks. / Performance of EIU – The EIU services were relatively costly compared to the other service providers involved in this project but their costs were partly driven by the cost of accessing their database and making some of this proprietary data public. Apart from the data costs, the fees for the analytical work were in line with the fees charged in most research and analytical projects. The EIU provided the data and presented a thorough analysis of the possible relationships between consumer prices and trade barriers. While their analysis did not provide conclusive results, this is a reflection of the complex nature of the problem rather than lack of rigour on their part. / Three technology hubs – one in each location - were engaged to manage the process of developing, hosting and disseminating the apps and online tools. All three had experience of running hack days either for the private sector or other government departments. They organised teams of IT developers, graphic designers, statisticians and community activists to come together to tackle the data challenge. This was a creative, interactive and low-cost methodology of producing online tools and apps and all three partners brought local knowledge and technical expertise to the table. The hubs in South Africa and Nigeria were able to offer further development, hosting and monitoring services for Phase II of the project at very low cost (significantly less than had been anticipated in the project design). / A small film company produced a monitoring film covering activities at all three hack days and interviewing the main participants. This film was shown at the DFID Digital Development Day and at a lunchtime seminar in DFID. The cost of the monitoring film was equivalent to 3% of the total programme budget and this initial expenditure has been worthwhile because the film has been invaluable for sharing lessons with other DFID teams involved in hack days and also for showcasing the process of developing the applications. / 5.4 Does the project still represent Value for Money : Yes. / This is a low cost and low risk project with potentially far-reaching impacts. Output level results have been substantially exceeded for a lower cost than was originally envisaged. Evidence of strong interest and uptake in the early prototype tools lies behind a decision to take them forward for further development and dissemination. / Even if the main outcome of the project is increased transparency and citizen engagement with trade and economic policy, this project will have added significant value. Through the process of doing the hack days, it was clear that these issues are not well understood in developing countries and governments are not held accountable as a result. What people do with the information that the Trade Transparency Project provides is up to them, but providing that information is a gain in itself. / Not only has it been an efficient and innovative way to make complex trade data more accessible to ordinary people, it has implications for DFID’s work to make data more transparent in any number of different fields. As a result, the impact for each pound spent is twofold: this project both informs citizens about trade policy and increases transparency, and builds evidence of what works for future DFID programmes. The Trade Transparency Project was used as a case study in the reformulated DFID Digital Strategy and has strong support from the Digital Team: “This project is exactly the sort of exemplar we need” (Julia Chandler, Digital Strategy Implementation Lead). / 5.5 If not, what action will you take? / Not applicable.

6. Conditionality
6.1 Update on specific conditions / None.

7. Conclusions and actions
The project has made a strong start and delivered some positive early results. The hack days were successful and generated a large number of innovative data solutions. Several of these have reached a large number of users around the world already. / Challenges were overcome by innovating or adapting the project in both the inception and implementation phases. For example, working with the Economist Intelligence Unit and broadening the scope of the project solved the data availability problem, and further innovation at the hack days (to crowd source data) turned this challenge into an opportunity. Similarly the inability to host the apps on DFID IT systems pushed the project to consider alternative options – Mxit and standalone platforms – which turned out to be far more suitable and have a much larger potential user base. / These are lessons that should be taken forward. Managing a project such as this requires flexibility and an open mind. Hack days are in essence creative processes that show the myriad possibilities of manipulating data sets, rather than producing solutions to order. They are also just the start of a process – further support is needed to develop prototype applications to their full potential and market them to an appropriate target audience. The emphasis should now be on continual development and dissemination of the apps to hit more ambitious usage targets. / As a result, it is recommended that the logframe is adjusted to incorporate another output, namely the hosting, continual development and monitoring of the online tools and apps until April 2014. The indicators might also be adjusted to be more ambitious to reflect the greater number of expected users. / Results in terms of usage have been lower than initially anticipated as the hack days only produced prototype applications and hosting on UK servers did not make sense. Phase II has been designed to remedy this problem. In fact, the end results are expected to be much more impressive than originally envisioned, although they will occur somewhat later than expected. It is recommended that usage statistics be monitored closely and apps continually developed in line with user feedback. / The costs of the project have been significantly less than what was planned for. Phase II will spend more but will still come well under budget. This is because hack days proved to be very economical and hosting and developing these tools in developing countries is cheaper than in the UK. Pending evaluation of final results, this project could be a good example of using technology and local solutions to achieve impact in a very cost-effective manner. / The output has been judged to be significantly exceeding expectations. Several online tools were produced and they were varied and locally relevant. Five of these have been deemed fit for further development. This is not something that could have been predicted before the hack days due to their creative nature. / It seems possible that many more people will be reached than were originally predicted, and these will be predominantly from the developing world. However the project will need more time to reach these users – the hosting and dissemination effort required was underestimated. / There have been a number of lessons that have come out of this project. In terms of trade, it was found that knowledge and understanding of international trade and economics was much lower than had been anticipated. This is an important lesson for the design of trade projects going forward – ordinary people will not engage unless their understanding is increased. There does however appear to be an appetite for this sort of information. In part this is a symptom of a wider concern for increased transparency around government spending policy (as evidenced by the other tools launched by the technology hubs in recent months) and an interest in trade itself and how trade policy affects people’s livelihoods. / The project is also useful for guiding the future design of technology based hack day projects. The need for flexibility, support to understand the datasets and an eye to future hosting and dissemination from the outset are all lessons that have been shared with other DFID teams.

8. Review Process
This review was conducted during June 2013. The process was led by the Trade Policy Unit Aid for Trade Policy Adviser with assistance from the Trade Policy Unit Economic Adviser. / Interviews were held with representatives from two of the three hack day implementing partners: RLabs (Marlon Parker) and Rewired State (Adam McGreggor). It was inappropriate to interview CcHub because they were undergoing contract negotiations for Phase II of the project at the time. / A number of documents and sources were consulted including: / TTP Business Case (June 2012) / TTP Log frame (August 2012) / TTP Pilot evaluation (March 2013) / M&E 10 minute film / Implementing partner contracts and ToRs / Where available, the mobile phone apps and online tools were also investigated.