Annual Review

Title: Support to Displaced People and Migrants
Programme Value £ (full life): £36,000,000		Review Date: 26 April 2018
Programme Code: 300404	Start Date: 1 June 2017	End Date: 31 May 2020

Summary of Programme Performance
Year	2018
Programme Score	B
Risk Rating	Major

DevTracker Link to Business Case:	Business Case and Summary 300404
DevTracker Link to Log frame:

A. Summary and Overview (1-2 pages)
Description of programme
This programme is strengthening protection of civilians in Yemen by supporting refugees, asylum seekers, internally displaced people (IDPs), migrants, as well as the host communities that they live among.
Yemen marked a tragic anniversary in March 2018, when the humanitarian crisis entered its fourth year. There are now at least 2.9m displaced people in need of support. The UK supports the United Nations High Commissioner for Refugees (UNHCR) and International Organisation for Migration (IOM) to respond to urgent humanitarian ‘protection’[1] needs to secure the safety, dignity and basic rights of people. With DFID support IDPs, migrants and refugees receive life-saving assistance including essential core relief items, emergency shelter kits[2] and financial assistance for people with serious medical conditions, vulnerable women-headed households, and those at risk of eviction and homelessness. Other programme activities include monitoring and referral of people for specialised mental health and psychosocial support; provision of health, counselling and legal assistance; sexual violence support; support to children separated from their families; as well as a country-wide displacement tracking mechanism (DTM). IOM works in consortium the Danish Refugee Council, Norwegian Refugee Council, Intersos and Humanity and Inclusion[3] to deliver services to IDPs, migrants and host communities. UNHCR delivers services through downstream partners to IDPs, host communities, refugees and asylum seekers.
[1] Protection encompasses all activities aimed at full respect for the rights of the individual in accordance with the relevant bodies of law (i.e. human rights law, international humanitarian law and refugee law). Its emphasis is on safety, dignity, integrity and empowerment.
[2] Core relief items include things like mattresses, blankets, sleeping mats, wash buckets and kitchen sets. Emergency shelter kits include items like a saw, hammer, rope, pickaxe, wooden poles, wooden planks, nails, metal pegs, utility knife and tarpaulin.
[3] Previously known as Handicap International
In August 2017 there was a six month cost extension of £2,000,000 to IOM to support the cholera response, later extended to twelve months but with no further increase in costs. UNHCR also received a cost extension of £2,000,000 in March 2018 for the procurement of non-food items (NFIs) and emergency shelter kits (ESKs) to respond to a new wave of displacement.
Summary supporting narrative for the overall score in this review
This programme has scored a B in its first annual review. Overall, the outputs moderately did not meet expectations. The outputs under the UNHCR component mostly met expectations, despite initial delays due to lengthy Memorandum of Understanding and reporting negotiations. However, IOM and its partners have experienced significant delays due to problems obtaining the necessary permissions to operate in northern Yemen. A key delay in both programme expenditure and outputs has been in displacement tracking activities, where access has been denied in northern governorates since May 2017.
The UNHCR cost extension was added into the logframe in output 3, and the IOM cost extension added as output 7. For this year the IOM component 7 has been zero weighted as activities are ongoing. Performance under these new activities has been consistent with delivery seen under the original activities and is discussed in Section F. The risk rating remains within DFID Yemen’s risk appetite at major. There has been deterioration in the operating environment this year and at times implementation has almost been paralysed by access constraints. However, new mitigation measures have been put in place and overall partners have delivered, albeit at a reduced scale on some activities, and improvements are being seen.
Recommendations for the year ahead
Following a slow start to programme delivery, UNHCR has overachieved on a number of targets and IOM is improving. Whilst delays from a slow inception are not expected to continue into year 2, access is going to continue to be a challenge and must remain a focus of the leadership of both organisations.
DFID, UNHCR and IOM programme should strive to be more flexible, quickly adapting to changes to the operating environment. Specifically but not exclusively:
1. DFID should focus on strengthening relationships with IOM and UNCHR, ensuring that partner information sharing is substantive and proactive. At times, these relationships should be extended to downstream partners, to ensure comprehensive feedback on implementation and its challenges
2. With ongoing delays to programme delivery DFID Yemen will strengthen oversight of the programme including regular updates on access constraints and actions taken; progress reports on delivery; and enhanced scrutiny of report quality including finances. If access constraints for the Displacement Tracking Mechanism continue beyond May, this programme component should be redesigned or funding should be reassigned.
3. Significant revisions are required to the logframe in order to clarify, simplify and ensure it is accurately reflecting progress in the intended areas. There are indicators from the original logframe that the IOM consortium is currently not reporting against. UNHCR have significantly overachieved against a number of indicators. DFID should review targets going in to year two to ensure appropriate levels of ambition and ensure overachievement is not at the expense of other indicators. All partners should disaggregate results by gender, age and disability. Partners should also collect and act on data on the percentage of beneficiaries satisfied with services Any proposed changes to the logframe are to be discussed and agreed with DFID, with sufficient consideration of potential impacts on VfM, theory of change and risk. DFID will consider agreeing individual weightings for output indicators.
4. Given significant new funding from Saudi Arabia (KSA) and the United Arab Emirates (UAE) for IDP programming, DFID should consider focussing support towards refugees and migrants. Host communities are often as vulnerable and resource starved as the displaced communities they host. Expanded programming for the host community should also be considered, particularly on building/rebuilding community infrastructure. This “humanitarian+” programming would improve sustainability of the response, ease community tension, and support vulnerable displaced and host communities.
5. The system for referring migrants to response points needs to focus on building the capacity of service providers for beneficiaries and establishing clear responsibilities in referral pathways for complex cases. IOM should consider more direct service delivery if referral services are non-functional.
6. In line with humanitarian best practice, partners should be encouraged to reduce in-kind distributions and instead deliver cash, as appropriate. This will enable to most vulnerable to prioritise their needs, whether that be food, shelter, or medical care. We recognised there are certain circumstances where cash distribution is not feasible or appropriate.
7. The Civilian Impact Monitoring Project (CIMP) should be reviewed to understand if it is achieving its goals. If not, the CIMP should be adapted to be more effective or funds re-aligned and spent on more effective programming.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)
Output Title	Conflict affected migrants benefit from protection screening, determination of immediate needs, and referral to tailored assistance including; shelter, psychosocial support, medical services, food, NFI, dignity kits and referral to other agencies for services not offered by the consortium. ( Delivered by IOM Consortium)
Output number per LF		1	Output Score	B
Impact weighting (%):		25	Impact weighting % revised since last AR?	N/A

	Indicators[4]	Quarter 3 Milestones[5]	Progress
1	# of encountered migrants registered and/or screened, identifying vulnerabilities and human rights abuses suffered.	22,149	31,399 - exceeded
2	# of migrants whose vulnerabilities are addressed by receiving WASH, food, NFIs , ICLA, and temporary shelter; prioritising the most vulnerable including women, children, Persons with disability and elderly.	12,375	28,998 – exceeded
3	# of host community members who receive WASH, health care and benefit from sensitisation on migrant rights. / And % of beneficiaries receiving two or more services.	12,000 and 70% (70% men, 3% women, 25% boys, 2% girls)	0 – not met
4	# of migrants benefiting from life-saving health care. And % of migrant health care beneficiaries reporting satisfaction with medical service received.	5,850	21,342 - exceeded (satisfaction indicator not yet reported)
5	# of migrants benefiting from Mental Health and Psychosocial support (MHPSS).And / % of this beneficiaries reporting satisfaction with medical service received.	2,994	6,909 - exceeded (satisfaction indicator not yet reported)
6	# of beneficiaries with improved access to clean water because of installation of five (5) water storage tanks with a 2,000-liter capacity, 5 water storage tanks and 475 basic hygiene kits and 100 emergency water kits.	500 for year one.	0 – not met
7	# of community members receiving awareness sessions on migrants' rights and / % of local community members reporting improved knowledge on migrant rights and issues.	2,700	77 – not met (improved knowledge indicator not yet reported)
8	# of partner staff receiving training in protection mainstreaming and inclusion. / And % demonstrating gain in knowledge on mainstreaming and inclusion. [Suggested this should be for migrants and IDPs, as a cross-cutting indicator or combined with 1.10]	140 and 80% for year one.	0 – not met
9	% of surveyed beneficiaries reported that they have received the project services through safety, dignity and relevant to their needs as result of inclusive humanitarian response - cross cutting indicator.	80%	89.5% - met
10	# of individuals receiving training in cross-cutting issues mainstreaming, inclusion, Psychosocial Support, Mine Risk Education. / And % demonstrating gain in Knowledge on mainstreaming, inclusion, PSS, Safety / And, % of trainees demonstrating increased knowledge on PSS service provision	219	100 – not met
11	# of consortium partner staff trained as trainers in MRE safety (completion of initial and refresher training sessions) / AND Translation, design and production of ToT curriculum for consortium partners for awareness raising and safety information related to the risk of mines, UXO, ERW and IED [Suggested to combine with 1.10]	0 / Year 2 only	N/A
12	# of beneficiaries who receive and have access to information necessary to make informed decision on humanitarian assistance and protection services: info on services available at NRC and other INGOs. / And % of these beneficiaries satisfied with the information received.	22,251	1,213 – not met (satisfaction indicator not yet reported)
13	# of migrants who receive legal counselling, to address critical humanitarian and protection needs. / % of legal counselling beneficiaries who are satisfied with the assistance provided.	3,630	3,357- not met (satisfaction indicator not yet reported)
14	# of migrants receiving awareness sessions on migrants' rights and humanitarian assistance and % of beneficiaries satisfied with the information received.	29,668	1,213 – not met (satisfaction indicator not yet reported)
15	# of beneficiaries supported through protection referrals including victims of trafficking and GBV	1,629	1,192 – not met
16	# of awareness sessions on the existence and use of the feedback mechanism - Cross cutting indicator.	12	21 - exceeded
[4] Grey boxes identify indicators to be further reviewed as a result of this assessment; italics show indicators not reported on by IOM.
[5] For this review quarter three milestones and results have been used representing the latest data available. The Annual Review due date on DFID’s Aid Management Platform (AMP) is 26 April (date funds approved), however the first year of the programme’s implementation ends on 31 May 2018. This misalignment reflects funds approved on AMP before implementation began.

Provide supporting narrative for the score
Migrants and asylum seekers, particularly from the Horn of Africa, continued coming to Yemen despite the conflict and humanitarian situation as it remains a major transit route to the Gulf. Overall the output scores a B with some over and under-performance, but some information relevant to targets was not collected.
Overall, the partners performed well on identifying and recording the challenges of migrants, reaching over 140% of the target set for screening and/or registering. They also excelled on meeting basic needs of this group, including health, WASH, food, NFIs shelter and legal support. Achievement across these indicators highlights that IOM and partners are doing a good job with tasks of identifying and addressing of migrant’s basic needs. This shows that they are operating in the right areas and engaging with the right population.
Although the majority of response indicators are being overachieved, there is some shortfall in WASH and mental health. The major underachievement, however, was on training and awareness sessions for both migrants and the host community, including on mine risk education. On quality, the programme also scores less well. Beneficiary satisfaction was not monitored as outlined in the results framework, and this needs to be done going forward.

IOM and partners are already reaching the right target population and so are well placed to diversify their support for migrants (in line with the logframe) so that needs can be more comprehensively met. From talking with the implementing agencies, we have confidence that indicators will be achieved going forward, however this output is currently being scored B due to underachievement across certain key indicators.
There are some ongoing challenges with the logframe, particularly on this output, including issues with duplication across indicators. A detailed revision is urgently needed in coming quarter.
Lessons identified this year, and recommendations for the year ahead linked to this output
The original IOM programme proposal had a very complex logframe. DFID encouraged IOM to refine it and a still extensive logframe was then agreed. Following this direction IOM continued to streamline the logframe and removed a number of indicators prior to submitting the results to DFID (shown in italic in the table). However, this was done without further consultation or agreement. All changes to the logframe must be clearly communicated and agreed formally in writing, with consideration of any impact on value for money and the theory of change.
IOM’s logframe still has indicators that potentially duplicate one another and could be combined. Conversely, UNHCR’s indicators, particularly for refugees and asylum seekers, are too high-level, referring to ‘response activities’, and obscuring details on cash assistance and other. DFID and partners should work to create a revised, streamlined logframe. The indicators in grey have been included in this annual review and the scoring process but have been identified as requiring immediate consideration for revision, pending discussion and agreement between DFID and partners. Reporting on support to host communities will also have to be further developed in the logframe. The weighting of individual indicators is also to be considered to ensure adequate assessment of harder deliverables.
IOM needs to ensure sufficient awareness raising activities are carried out for migrants on migrants' rights and humanitarian assistance and for the host community as a conflict sensitivity measure to reduce the risk of creating community tensions.
Partners need to be collecting and using data on beneficiary feedback for all groups, including migrants. This is an important measure of the quality of services provided and it is currently not being consistently reported.

Output Title		Refugees and asylum-seekers have improved access to protection services (delivered by UNHCR)
Output number per LF			2		Output Score		A
Impact weighting (%):			25		Impact weighting % revised since last AR?		N/A
	Indicators / Grey boxes indicates suggested revision			Quarter 3 milestone		Progress
1	# of individuals supported with sexual and gender-based violence (SGBV) prevention and response activities (SGBV survivors receive medical support, legal services, psychosocial counselling).			413		521- met
2	% of assisted refugees (disaggregated by age, gender and nationality), reporting that some of their immediate protection needs were fulfilled			80%		Nothing to report - not met. / (UNHCR will not report on this until the next quarter)
3	# of community-based committees/ groups working on SGBV prevention and response.			12		12 - met
4	# of children supported with child protection activities in Sana'a, Aden, Kharaz, camp and Lahj (includes # of unaccompanied and separated children identified).			244		891 - exceeded
5	# of Best Interest Determination conducted.			191		87 – not met

Briefly describe the output and provide supporting narrative for the score
Ongoing conflict, shrinking asylum space and grinding poverty has placed women, girls, boys and men at heightened risk of harm, including sexual and gender based violence (SGBV). Refugees and asylum-seekers suffer disproportionally from SGBV, which is both a cause and a result of forced displacement, often due to a breakdown in family and community structures. UNHCR is the lead on works with refugee and asylum-seekers in Yemen to address SGBV. UNHCR is also working to reduce risks for displaced people, and to provide support to survivors, including comprehensive care management such as medical services, psychosocial interventions, legal support, home visits, and emergency financial assistance along with the provision of core relief items.
UNHCR has met or exceeded most of its targets. 12 community-based committees worked on SGBV prevention and response. This is sufficient in number to address needs because refugees are generally less mobile and reside in more concentrated areas than IDPs .This allowed 2.1 to be exceeded supporting 521 people with SGBV prevention and response activities. The breakdown of cases referred for individual management and what kind of support within that number is as follows: physical assault response (health, psychological and legal) 42%; psychological abuse (health, psychological) 34%; and rape cases (health, psychological and cash) 14%.
UNHCR is currently not reporting against output indicator 2.2 and has therefore not met the target. This indicator is designed to measure the quality of services provided through the percentage of assisted refugees (disaggregated by age, gender and disability), reporting that some of their immediate protection needs were fulfilled. In the previous programme of support to UNHCR, this information was not captured as UNHCR did not consider it had the appropriate mechanisms in place to do so. It was agreed that it would be measured for the current programme. UNHCR is measuring it for IDPs (output 3) but has not yet been able to report on the indicator of refugees.
Under output indicator 2.4, UNHCR exceeded the target on child protection activities by over three times, to meet increasing needs. This has included conducting interviews and counselling, regular home visits, follow-up and referrals to other service providers in Sana’a, Aden, Kharaz camp and Lahj for unaccompanied and separated children.
Multi-purpose cash assistance to address basic needs is used as a means of averting negative coping mechanisms for extremely vulnerable individuals. Resorting to negative coping strategies can place vulnerable individuals at increased risk of exploitation and abuse. Cash assistance is evidence-based and best practice in humanitarian assistance. Needs assessments are conducted to identify beneficiaries with extreme vulnerability after applying vulnerability criteria. Multi-purpose cash grants are distributed by protection partners (or directly by the money transfer agent if a particularly remote area), to respond to a range of humanitarian needs, including health, shelter/NFI, food assistance and protection related needs. There is coordination with other implementing partners but this is something we will continue to monitor.
Under output 2.5, Best Interest Assessments / Determinations are UNHCR assessments as part of case management for children at risk, whereby UNHCR caseworkers monitor service provision and ensure that child protection cases under UNHCR assistance receive the necessary care and support. This can include education, psycho-social counselling, legal counselling and family tracing. The target has not been met as UNHCR has continued to face challenges with regard to carrying out the assessments / determinations due to the suspension of registration imposed by authorities.
There are also some results relevant to this output reported under output 4 on community based protection networks (CBPN), which is performing better than expected, as some of these operate as the drop-in centres for refugees to access services (12 offer the SGBV services for refugees).

Lessons identified this year, and recommendations for the year ahead linked to this output

We persevere with UNHCR to capture, share and act on data relating to the quality of services provided under output 2.2. The DFID team should work with IOM and UNHCR to standardise the language in (IOM and UNHCR) indicators that seek to measure the satisfaction of beneficiaries with services, or beneficiaries reporting that some of their immediate protection needs were fulfilled (as above with 2.2). This would enable clearer comparisons and ensure that there is a workable measurement mechanism for UNHCR.
Update indicator 2.3 in the logframe, as issues would be evident from measuring the number of beneficiaries (2.1); more usefully it could identify geographical spread, to assess whether services are appropriately located to reach those most in need.
UNHCR’s disaggregation of results could be strengthened, as we currently only receive information on the gender of beneficiaries.

Output Title	Internally Displaced People (IDPs) have improved access to humanitarian and protection services / (UNHCR and IOM)
Output number per LF		3	Output Score	B
Impact weighting (%):		25	Impact weighting % revised since last AR?	N/A

	Indicators / Grey boxes indicates suggested revision	Quarter 3 milestone	Progress
1	# of people of concern receiving unconditional cash grants (those with special personal needs (SPN)). Targeting is done at household level. (UNHCR)	1,200	2,865 - exceeded
2	% of assisted IDPs (disaggregated by age, gender, geography, disability), reporting that some of their immediate protection needs were fulfilled (UNHCR)	70%	99% - met
3	# of people of concern with psychosocial needs receiving psychosocial support (UNHCR)	12,750	17,125 - met
4	# of people of concern receiving legal assistance (UNHCR)	2,250	2,549 - met
5	Procurement of emergency shelter kits (ESK) and non-food item (NFI) kits (UNHCR).	10,000 NFI kits and1,600 ESK	10,000 NFI kits and1,600 ESK - met
6	# of IDPs and % of Host communities benefiting from life-saving health care. And % of health care beneficiaries reporting satisfaction with medical service received. (IOM)	14,625	11,159 – not met
7	# of IDPs benefiting from life-saving MHPSS and PSS. And % of health care beneficiaries reporting satisfaction with medical service received. (IOM)	3,000	10,618 - exceeded
8	# of cases (child victims of trafficking, GBV, or otherwise particularly vulnerable children) identified and assisted with reintegration support in Yemen. (IOM)	75	0 – not met
9	# of IDPs and returnees benefitting from psychosocial support assistance provided during the conduct of DTM activities and / # of cases referred for specialised MHPSS services (IOM)	1,000	0 – not met
10	Government Health consultants trained (IOM).	120	0 – not met
11	Health centres provided with operational support (IOM).	2	0 – not met
12	Cases referred for specialised services (IOM, NRC)	956	11 – not met
13	# of beneficiaries receiving legal counselling, assistance and awareness raising activities (NRC).	Counselling - 631 / Assistance – 325 / Awareness - 1,251	Counselling - 371 Assistance – 283 / Awareness – 451 / Not met

Provide supporting narrative for the score
As the crisis in Yemen becomes more protracted, people are being displaced for longer periods but new displacement is still happening. According to UNHCR, the total number of families displaced to southern governorates since 1 December 2017 (when violence along the Red Sea coast began increasing) has reached 8,702 households (61,000 people). Both UNHCR and the IOM consortium deliver activities under this output to support IDPs, including those recently displaced.
Whilst UNHCR has met its targets, IOM, although generally covering a smaller portion of the output, have been unable to meet most of their targets. As is the case with output 1, there are indicators that IOM reported on in quarter one but subsequently removed. These have been included as nil results and revisions to be agreed after this review. Due to the wide intended reach of displacement tracking activities, indicator 3.9 was intended to utilise the DTM as an opportunity to go beyond recording displacement information and actually assist those in need of mental health and psychosocial support (MHPSS) or refer them for support. Without local authority permission to operate, IOM was unable to carry out population tracking activities in ten northern governorates for the duration of the programme (see output 6). As DTM has not been functioned effectively, the delay has meant no results were reported under output indicator 3.9 whilst IOM focussed their efforts on operationalising the DTM before using if for referrals. The second element of 3.9 (referrals for specialised services) has results reported upon in indicator 3.12 – also not met.
However, IOM has assisted many more people than expected with mental health and psychosocial support (as has UNHCR – 3.7 and 3.3 respectively). Results under 3.6 are made up of medical consultations, reproductive healthcare, vaccinations and health awareness. The majority of results are concentrated under medical consultations, with much lower results in vaccinations, reproductive health and health awareness. Results under 3.7 are all made up of IOM MHPSS services. Results under 3.12 were all adults referred by NRC. Results under 3.13 were quite evenly balanced with 50% of beneficiaries being female (40% for awareness-raising).
UNHCR’s one-time cash grants (3.1) are relatively large at $300 per beneficiary and continue to be a critical assistance tool for those in need. Assistance is provided on a one-time basis and can be extended based on the needs in exceptional cases. UNHCR ramped up cash support during the past quarter, more than doubling the expected reach, with 2,865 vulnerable households receiving assistance. The increase is attributable to a more favourable exchange rate between the Yemeni Riyal (YER) and US Dollar, and the shift to disburse all cash in YER directly through a financial service provider (Al Amal Bank) which resulted in additional savings allowing more people to benefit from UNHCR Protection assistance. UNHCR produced an analysis of post-distribution monitoring on its overall cash assistance support in 2017 that shows good results in general but areas that could be improved.
Occasionally, Al Amal Bank (UNHCR’s money transfer contractor) delivers cash to hard-to-reach beneficiaries that live in remote areas. Cash assistance beneficiaries are particularly vulnerable, and remote beneficiaries in particular. UNHCR has identified protection risks relating to the cash transfers under this output and output 2 and has therefore put in place mitigation measures by providing protection training to Al Amal money transfer staff. Cash transfers will also be delivered in three separate payments of $100 to improve the ability of beneficiaries to plan their spending and protect their safety.
UNHCR has observed increasing psychological stress on the Yemeni population, in particular among the displaced population. Prolonged conflict, exacerbated by limited medical facilities, has placed further urgency on the broader protection response, with 17,125 individuals receiving psychosocial support during the December to February period, exceeding the target by over 4,300. This figure reflects both growing capacity by UNHCR partners to respond and refer cases to the appropriate services, but also the increasing numbers of IDPs approaching mental health providers of their own accord, reflecting a worrying trend in the needs of a community traumatised.
Legal assistance provided through UNHCR’s partners also exceeded the target of 2,250, reaching 2,549 IDPs. The assistance covers legal counselling mainly in relation to essential documentation such as civil status documentation and birth registration documents, including for children born out of wedlock.
Lessons identified this year, and recommendations for the year ahead linked to this output
As with output 1, a key recommendation is that changes are made to logframe for the greyed boxes in the table above. DFID and partners should work together proactively to ensure the logframe appropriately reflects the programme’s theory of change, value for money, risk appetite and changing reality on the ground. The logframe should be regularly reviewed with partner and if changes are needed they should be justified and agreed in writing.
A recommendation relating to output indicator 3.2 is that DFID should seek to better understand both the disaggregation (age, gender, geography, disability) of IDPs reporting that that some of their immediate protection needs were fulfilled and how it was measured. UNHCR has been able to report against this for IDPs but not been able to yet measure the same for refugees, so there could be lessons to share.
UNHCR should report a more granular level of disaggregation of targets and results, supporting IOM’s reporting. For example, where IOM is carrying out a range of activities, DFID should be able to understand how many of beneficiaries there are of each activity making up the results reported, how that compares to what was planned and have the ability to interrogate any delivery issues.
Only 29% of cash recipients were female and 17% of surveyed beneficiaries experienced problems in receiving cash. We will continue to work with UNHCR to ensure that women, as a vulnerable group, are targeted for cash assistance and to reduce the frequency of all beneficiaries experiencing problems in receiving cash.
Section C notes that the ability of IOM and partners to address the protection challenges is limited due to the collapse of basic services throughout the country. A recommendation is that in the coming year, IOM and partners should continue to support better service delivery at referral points. Given the scale of devastation of basic service infrastructure and staffing, IOM should also consider supplementing referral with more direct service delivery, where possible and appropriate.

Output Title		Strengthened Protection monitoring and support to Community Based Protection Networks (CBPN) / (UNHCR)
Output number per LF			4		Output Score		A+
Impact weighting (%):			10		Impact weighting % revised since last AR?		N/A
	Indicators / Grey boxes indicates suggested revision			Quarter 3 milestone		Progress
1	# of community based protection networks supported/maintained			90		116 - exceeded
2	# of people of concern reached through protection monitoring			60,000		98,930 - exceeded

Provide supporting narrative for the score
Protection monitoring is a core activity for UNHCR and constitutes the backbone of the IDP protection response for 2018. It is the first step in addressing people’s protection needs as it enables those individuals in need to be identified and appropriate referrals made. The indicators for this output have both exceeded expectations as a greater number of people (predominantly IDPs but also refugees, host community members and migrants) have been reached through a greater number of Community Based Protection Networks (CBPN) than was planned. Under output indicator 4.2 UNHCR has exceeded the target by reaching 98,930 individuals through protection monitoring. A number of initiatives aimed at strengthening the protection response were launched in 2017 and continued during the reporting period. These have included harmonisation of household-level assessments and focus group discussions to ensure consistent assessments of protection risks and vulnerabilities.
Under output 4.1, Community Based Protection Networks (CBPNs), have increased community participation and engagement to identify protection risks and strengthen IDPs’ own capacity to address these risks. A common protection service directory has been developed to facilitate referrals. Between December and February, UNHCR continued to expand assistance to partners, supporting 116 CBPNs, a higher number than the 90 planned, through partners Adventist Development and Relief Agency (ADRA), Al Bena and Yemen Red Crescent Society. Due to changes in the operating environment, UNHCR has stopped working with Al Bena and has instead partnered with the Yemen Development Foundation.
Lessons identified this year, and recommendations for the year ahead linked to this output
It is difficult to measure the quality of service provided by CBPNs and the logframe does not currently measure this. Greater benefit is derived from focusing on quality over quantity and by building the capacity of existing CBPNs rather than increasing the number of networks themselves.
DFID will continue, as far as practical, to monitor the quality of CBPNs, overseeing a combination of sufficient training, using and refining standard operating procedures (SOPs) and promoting a more systematised way of ensuring capacity and performance.

Output Title		Strengthened coordination through Protection Cluster Support / (UNHCR)
Output number per LF			5		Output Score		A+
Impact weighting (%):			5		Impact weighting % revised since last AR?		N/A
	Indicators / Grey boxes indicates suggested revision			Quarter 3 milestone		Progress
1	# of Protection Cluster partner staff members and government authority staff members trained.			188		549 - exceeded
2	# of information products produced and disseminated by the Protection Cluster.			23		31 - exceeded
3	# of Protection Cluster meetings held each quarter.			3 per quarter		3 each quarter - met

Provide supporting narrative for the score
UNHCR has met and exceeded the target for output 5.1 the number of partner staff and government partners trained by almost three times, with 549 individuals benefiting from capacity building efforts, following challenges in the previous quarter. Training covered protection programming; protection mainstreaming; guiding principles, Protection Cluster coordination[6], cluster approach[7], International Human Rights and Humanitarian Law; civil documentation; housing, land and property rights.
[6] Clusters are groups of humanitarian organizations, both UN and non-UN, in each of the main sectors of humanitarian action, including protection. The Protection Cluster’s responsibilities include coordinating the overall response, eliminating duplication and gaps, identifying priorities, providing technical standards for members and leading coordination with other clusters and the Humanitarian Coordinator.
[7] The Cluster Approach is a part of the 2005 Humanitarian Reform Agenda, a major reform of humanitarian coordination that introduced a number of new elements to the international humanitarian coordination system to enhance predictability, accountability and partnership.
Output indicator 5.2 has been met and exceeded as 31 information products were produced by the Protection Cluster and disseminated to members. These include 3Ws (Who does What, Where?), maps, Protection Cluster monthly updates, assessment reports and infographics.
Output indicator 5.3 measures whether Protection Cluster meetings are held and at regular intervals. There are an increasing number of national participants. In February, over 42 organisations, the majority of whom are national, attended a two-day Protection Cluster strategy meeting, looking at activity planning for 2018 and beyond. The Protection Cluster Coordinator further held a Protection Roundtable attended by protection actors (UN, INGOs, and donors).
Lessons identified this year, and recommendations for the year ahead linked to this output
DFID funding for the cluster ensures our close connection to emerging protection issues and should be continued. With DFID support the cluster has been proactively pushing the protection agenda.

Output Title	Yemeni populations displacement monitoring (IOM)
Output number per LF		6	Output Score	C
Impact weighting (%):		10	Impact weighting % revised since last AR?	N/A

	Indicators / Grey boxes indicates suggested revision	Quarter 3 milestone	Progress
1	# of displacement tracking matrix (DTM) Reports on internally displaced and returnee populations developed, / # of DTM Governorate Monitoring reports developed on internally displaced and returnee population, and / # of end of assessment In-Depth Task Force on Population Movement (TFPM) Reports developed from data captured from geographically comprehensive in-depth multi-cluster needs and/or intentions assessments on internally displaced and returnee populations, shared with humanitarian actors in Yemen.	5 / 5 / 2	2 DTM reports / 5 Emergency Tracking reports / 0 end of assessment TFPM reports / Not met
2	# of migrant flow monitoring reports on migrant trends shared with humanitarian actors in Yemen (IOM). / # of monthly reports developed and disseminated on migrant trends (emanating from DRCs database).	9 / 9	5 / 0 / not met
3	# of trainings conducted on new/enhanced DTM tools, methodologies, and quality control procedures to ensure the accurate and comprehensive data collection.	2	2 - met

Provide supporting narrative for the score
IOM’s Displacement Tracking Matrix (DTM), overseen by the multi-agency Task Force on Population Movement (TFPM), was launched in Yemen in April, 2015 in an effort to better inform the humanitarian community about the location and needs of the displaced populations in Yemen. IOM undertook population tracking in the south of the country and UNHCR (through partners) in the north. At the end of the last DFID Yemen programme of support (31 May 2017) we suggested that one partner undertook displacement tracking for the entire country, and IOM with more direct implementation took this forward. The operating environment deteriorated, making access to the 10 northern governorates impossible. IOM was unable to secure agreement from authorities to collect DTM data. Negotiations have been protracted, but progress is slowly being seen. This output has therefore not been met as IOM has been unable to collect new data in the ten northern governorates since it fully took over the DTM in July 2017. Needs identification and response for IDP populations is therefore affected and is currently the weakest component of this programme.
Since the beginning of this programme, IOM has produced two DTM reports, one in July 2017 and the October 2017 (6.1). Reports used to be received monthly. The 16th report (October) identified, 2,014,026 IDPs who have been displaced due to conflict since March 2015, dispersed across 21 governorates. For the same period, the DTM identified 956,076 returnees, across 20 governorates. The DTM produced 5 Emergency Tracking reports covering January and February 2018 but these have been light-touch and reports have been shared with OCHA but IOM has not been proactive in sharing reports with DFID.
Under output 6.2, the DTM has produced 5 Migrant Flow Monitoring reports covering: May – June; July 2017; a dashboard for June 2017; a Regional Migration Flow Report covering June – August 2017; and a report for the year of 2017. DRC has not produced any reports.
Under output 6.3, IOM met the target as it carried out two coordination meetings with OCHA, UNFPA and the Yemen’s civil society organisation department to present the DTM tools, the nature of the data collected and the methodologies used.
IOM has continued DTM operations in the south of the country and done what it can in the north, meaning that IOM has not been able to produce or share comprehensive reports as planned this year. IOM is hopeful that we will be able to soon announce that DTM has started in the northern governorates.
Lessons identified this year, and recommendations for the year ahead linked to this output
Changes to the logframe to better measure performance are proposed. These are intended to measure success on whether the reports are shared with humanitarian actors, including DFID, and cover all governorates.
For the year ahead, DFID will closely monitor IOM’s progress in re-establishing the DTM in the north of the country. If blockages continue DFID will need to consider other options, including stopping support to this component; this would be as a last resort as the data produced and shared is vital to the planning and implementation of the humanitarian response in Yemen.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)
Summarise the programme’s theory of change and any major changes in the past year

The theory of change diagram above highlights elements needed to improve the protection of refugees, asylum seekers, migrants and IDPs in Yemen. It looks at the major elements supported under the programme as well as factors that are outside of the influence of this programme.
Underlying the theory of change is the identification of needs and strengthening of partners to respond to protection needs. The next levels look at specific program components that contribute to protection and the links between them. An example of how this has worked in practice: Needs of displaced families were identified by UNHCR through assessments at the household level. That information was then used to make cash transfers to 2,865 families with specific vulnerabilities. Families then spend cash grants on necessary rent, food, health care, debt repayment and non-food items (in that order), reducing their need to borrow, limit food intake, or resort to risky behaviour, like theft, that would increase their protection risks. A post-distribution monitoring report from March 2017 indicated that 99.7% of beneficiaries said that the cash support from UNHCR “addressed some of their immediate needs”.
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
Due to ongoing conflict, the ability of a government to provide a protective environment to refugees, migrants and internally displaced has been severely compromised. In this much restricted environment, DFID’s partners have been doing well to improve protection of these vulnerable groups although there remains significant room for improvement.
UNHCR’s refugee response component of this programme has had the strongest performance. The one exception to this is the delayed resettlement of refugees, due to a stoppage of status determination. Programming targeting migrant populations has been performing well in some aspects although continues to struggle due to a poorly resourced referral network. In practice this means that despite IOM’s ability to determine protection challenges, the ability to address these issues is limited by poor service availability (e.g. health care, legal support) throughout the country. In the coming year, IOM and partners should continue to support better service delivery at referral points. Given the scale of devastation of basic service infrastructure and staffing, IOM should also consider supplementing referral with more direct service delivery.
The weakest component of the program is needs identification for IDP populations due to access issues. This has hampered IOM’s ability to comprehensively roll out their Displacement Tracking Matrix (DTM), creating a countrywide lack of data on the scale of displacement and the severity of needs. A slow start to the IDP components of the programme has also impacted achievements. IOM has addressed many of these issues and we will monitor progress against targets over the next months.
Explain major changes to the logframe in the past year
DFID encouraged IOM to refine the extensive logframe originally proposed; the agreed logframe still contained some complex, compound indicators, so further revisions were recommended. Following this feedback, IOM submitted to DFID an abridged logframe, removing indicators italicised in the tables used in this report. Suggested changes to the logframe must be clearly communicated and agreed formally in writing between partners, with consideration of any impact on VfM and the theory of change. DFID should also track the performance of partners contributing to output indicators and encourage IOM as consortium lead to support partners that are under-achieving.
Describe any planned changes to the logframe as a result of this review (1/2 page)
Consistent with the first recommendation made in Section A of this report, the logframe, requires revisiting. Proposed changes are intended to simplify, clarify and ensure that results in the logframe accurately reflect real performance and will be discussed and agreed with partners in quarter two of year two. This includes ensuring that the indicators relevant to producing reports (such as the DTM) stipulate that reports are also shared and cover all governorates that they plan to. There will be an additional output included for the cholera response project that IOM is carrying out (see section F).

## D: VALUE FOR MONEY (1-2 pages)
Assess VfM compared to the proposition in the Business Case, based on the past year
Economy
Large procurement including NFIs and emergency shelter kits procured by UNHCR were bought on the international market, through UNHCR’s global procurement framework, following best practice. For smaller, day to day procurement partners will frequently use the local market. UNHCR has a long-term agreement for the procurement of fuel and IOM (and partners) are supplied through WFP, which supplies fuel to the majority of humanitarian agencies. The average cost of the NFI kits and 1,600 emergency shelter kits procured by UNHCR was £147 per kit, which is within the normal cost range identified in a DFID NFI cost review. Both organisations operate at scale, creating economies of scale.
Efficiency
The UNHCR component represents good VfM as greater results than planned at the outset of the programme were achieved with the same level of funding. To better illustrate UNHCR’s achievements, the logframe will be reviewed in year two of the programme, further disaggregating indicators. UNHCR has also responded with speed, appropriateness and cost (the three components of humanitarian VfM) in procuring NFIs and emergency shelter kits with DFID funding following stringent UN procurement rules as discussed in section F.
UNHCR had a transportation contract that did not offer good VfM as there were conditions whereby detention fees would be paid by UNHCR when trucks were detained. UNHCR therefore reviewed the terms of the contract at the beginning of 2018 and changed it so that these costs are covered by the contractors. It continues to look for new contracts to diversify risk.
At the beginning of the programme there was some duplication of services between DRC and Intersos under the IOM consortium but this was recognised and resolved in November. To try to avoid duplication in the future, the consortium is making an effort to better communicate between partners and other organisations the work they are doing with migrants. IOM has started to produce a service map showing who is working where with migrants.
Given the variety of activities undertaken and variations in operational environment, overall cost per beneficiary is an unreliable measure of humanitarian VfM, especially for protection activities which help contribute to a wider protective environment. For these reasons, cost per beneficiary has not been included as a measure of VfM in this programme; Instead, we will continue to monitor the results delivered for the funding provided and the proportion of management costs in the delivery chain.
Effectiveness
Some indicators include a measure of satisfaction with services provide, which would give an indication of the effectiveness of protection activities. Unfortunately, partners have not yet been consistently measuring this. UNHCR has done so for IDPs and the results are very positive, with 99% of assisted IDPs reporting that some of their immediate protection needs were fulfilled. Further assessment will be made on receipt of quarter four reports.
Equity
Displaced people and migrants remain among the most vulnerable in Yemen, with women, children and the disabled facing even greater vulnerability. Breakdown of government systems and legal mechanisms to protect asylum seekers and migrants mean that these groups are almost entirely reliant on host community, which is becoming increasingly strained, and aid agencies support. As a segment of the wider population in need, these groups are particularly vulnerable and are thus a good target for DFID programming. As noted under section F there is more work to be done on ensuring that equity exists within results. While this is being measured on some outputs, in year two of this programme we will need to work with partners to ensure consistent gender (and age) disaggregation in data. Inclusion of people with disabilities is addressed through an IOM consortium partner, Humanity and Inclusion, which conducts training on disability inclusion for partners and the host community. HI is increasing its implementation in year 2 of this programme.
Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
Despite some areas of slow progress, the programme should continue from a VfM perspective because it has helped to identify and support some of the most vulnerable groups of people in Yemen, and it has helped to ensure that the rest of our portfolio is targeting those most in need.
- From an economy perspective, despite inflation in Yemen, costs in the programme have remained fairly constant. Staffing costs constitute a cost driver and will need to be monitored should new staff be brought on-board.
- Despite slow initial progress, results are picking up and there are examples of opportunities being taken to maximise efficiency. More can be done on ensuring the DTM is an efficient use of resources, bearing in mind the opportunity cost; and where possible, encouraging the reduction of management costs of partners. The success of displacement tracking will remain under review and if no progress is seen by September the continuation of this component will be reconsidered.
- From an effectiveness perspective it is saving and improving the lives of some of the most vulnerable people in Yemen. More is needed on monitoring the effect of activities over a longer period, and the planned mid-term evaluation could help to address this challenge.
- This programme helps to deliver equity and ‘leave no one behind’ by ensuring that those with nothing, who are most vulnerable due to displacement, language barriers, lack of social networks and (at risk of) falling victim to extortion, violence and abuse, are protected. DFID’s continued support to these particularly vulnerable groups remains vital in an underfunded sector. There are improvements to be made on ensuring equity among beneficiary groups; improved disaggregation of data will allow DFID to better understand the equity of results. IOM disaggregates results by age and gender

E: RISK (½ to 1 page)
Overview of programme risk (noting the rating from p.1) and mitigation
Yemen is widely considered one of the most challenging working environments for humanitarian workers. As well as the risks directly related to the conflict such as airstrikes, crossfire and other violence - there have also been instances of kidnapping, which calls for extreme precaution around the movement of international humanitarian workers across the country. As a result international staff movements are often confined to offices and guesthouses, mostly in Sana’a and Aden cities, resulting in limited direct interaction with key stakeholders across the governorates. The 2016 Operational Peer Review recommendation to develop humanitarian hubs in Aden, Mukalla, Sada’a, Hudaydah and Ibb/Taiz was broadly implemented and the year 2017 has seen the development of area Humanitarian Country Teams, area Humanitarian Access Working Groups and area security management teams. This did not translate in the deployment of international staff to hubs to the extent we had expected. This posture reduces security-related issues, but limits local first-hand capacity to assess, plan, negotiate and monitor and therefore higher reliance on national staff to implement those key functions.
The period under review was marked by a series of offensives, which have rapidly stalled, affecting large urban centres including Aden, Taiz and Sana’a. Overall, humanitarian agencies were not targeted and very little indirect damage (airstrikes, looting, crossfire) was reported. Displacement from the Red Sea coast has taken place in December 2017 and early 2018, generating a risk of there is an increased and increasingly complex caseload of vulnerable people with this displacement and the return of Yemenis from Saudi Arabia to Yemen. Ironically, given this context of protracted conflict with unpredictable spikes of violence, partners’ biggest obstruction has been from bureaucratic impediments, including political pressure exerted by authorities to assist certain groups, constraining their access to districts and sub-districts for the conduct of needs assessments, the provision of assistance and the conduct of standard monitoring activities. Corruption in the form of nepotism or favouritism in beneficiary selection is an increased risk considering that 80% of Yemen’s population in is in need of assistance. Partners resist these pressures which results in delays and obstructions to delivery. There has also been insufficient collection of data relating to satisfaction with services and a gap in terms of delivering services to the host communities. This may create a risk of tensions within or between communities that could go unchecked. The period under review saw a very worrying trend in where bureaucratic impediments have increased from programme inception.
Partners have to provide an update on their understanding of risk, its management and mitigation measures in their narrative reports. Updated partners’ risk matrixes are systematically reviewed during quarterly meetings in Amman. Some of the key risks regularly monitored included: fiduciary risks, such as the risk of aid diversion, fraud and corruption; operational risks, such as partner capacity to deliver effectively; delivery risks including safeguarding, high levels of staff turnover and consortium coordination ensuring effective delivery in targeted locations. Due diligence assessments were undertaken on both partners; IOM’s 2017 findings included: audit, fraud reporting, risk management and partner due diligence assessments. There has been some progress, for example, IOM has carried out an audit of its Yemen office in 2017. There will be a DFID Yemen independent monitoring study in 2018 and IOM plans to contract third party monitoring to help address the due diligence findings regarding a lack of verification and spot checks due to the conflict. DFID will continue to work with all partners to strengthen the control environment and maintain a manageable level of risk. In particular we will put in place enhanced oversight arrangements to minimise the risk of further delivery delays.
The overall risk of this project remains major, as it involves operations in an active conflict where access remains uncertain. Over the reporting period bureaucratic obstructions increased, as well as constrained access related to increased conflict in some part of the country. At the time of writing access negotiations have improved and operations are anticipated to pick up in pace going into year 2.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)
Performance of partners and DFID, notably on commercial and financial issues
IOM
IOM has experienced staffing issues in the period under review. The protection specialist and DTM programme manager left at the end of their contracts and the DFID focal point was transferred, all within the same three months that the Chief of Mission his deputy were transferred. Staffing shortages and repositioning staff to provide cover positions has had an effect on reporting and financial forecasting quality and timeliness. We have taken measures to improve the quality of reporting by developing a reporting template, which IOM has used for the third quarterly report but improvements could still be made in terms of relevance and accuracy.
Funding for the DTM makes up the largest proportion of IOM’s budget; as activities in northern governorates have blocked by authorities since the beginning of the programme DFID has not been getting the best commercially. Negotiations are ongoing to restart the DTM but this is yet to produce significant results. Relationships with the authorities are problematic for all delivery partners in Yemen and IOM has experienced difficulties in getting the political buy-in for its work as there is resistance to allowing migrants to enter the country and pressure to return people against their will.
A large cholera outbreak, directly attributable to the conflict, took hold in Yemen in 2017 as critical infrastructure and vital public services were in a state of collapse. IOM was one of the humanitarian actors that contributed to the response. In August 2017 we supported IOM Yemen with a six month cost extension for an additional £2,000,000 to respond to the cholera outbreak. As with other activities, initial progress was slow due to access constraints. The interim report submitted in January showed that IOM engaged in coordination, followed the health and WASH cluster guidance and adjusted some activities to adapt to the changing situation e.g. adaptation of the referral component and capacity to re-allocate funds internally to begin training activities before DFID support was received. Some issues were reported on awareness raising and the WASH components, weakening the initial objective of an integrated approach. Due to delays experienced a time extension to 31 August 2018 was granted. The extension included addressing cholera prevention activities to prepare for a new caseload in spring 2018.
Although IOM shares detailed budgets, the accuracy of IOM’s financial forecasts has been disappointing with variances seen of up to 70% underspend at the end of 2017. Spending has been much slower than anticipated due to access constraints and slow start up of the consortium as detailed above – however timely communication and accurate presentation of budgets would permit more effective use of tax payers’ resources and give DFID the confidence to allow for additional flexibility within budgets. It is imperative that all partners factor in more realistic timeframes for delivery at project inception as well as factor in optimism bias for the remainder of the programme.
We are hopeful that the performance of IOM will be improved as the new Chief of Mission began working in April and recruitment for other vacant positions is being expedited. Notwithstanding changes in staff, there has generally been proactive engagement from IOM in terms of discussing risks, issues and updating the programme delivery chain map.
UNHCR
UNHCR underwent considerable contract negotiations with DFID at the start of this programme. Although reporting requirements and format were clearly set out in DFID’s call for proposal guidelines, UNHCR was reluctant to stick to these reporting expectations – which include quarterly financial reports. There were further lengthy negotiations agreeing DFID’s new Memorandum of Understanding (MoU) wording as required for the programme. Agreement on the new format was suspended for 6 months whilst the central MoU for core DFID funding to UNHCR was agreed. The previous MoU wording was used in the interim before incorporating relevant terms from the new DFID-UNHCR central agreement.
Whilst agreements were prolonged, UNHCR has forecast accurately, spent and reported on time. UNHCR has improved the quality of its narrative and financial reporting to DFID and budgeting but further improvement is needed in terms of the formal sharing of information on risks, finances, VfM and the detail underpinning logframe results, including disaggregation of data. The level of detail provided by UNHCR is less substantive than other partners. UNHCR has demonstrated the flexibility to deliver at pace with a concept note and £2,000,000 budget for a cost extension for DFID support to purchase NFIs and ESKs to replenish the pipeline and enable immediate distribution of assistance in response to a new wave of displacement from the Red Sea coast.

Date of last narrative financial report(s)	IOM received April 2018 (9 months) / UNHCR received February 2018 (6 months)
Date of last audited annual statement (s)	Calendar year 2017: / IOM 17 May 2017 / UNHCR 30 June 2017

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

UNHCR
UNHCR has carried out post-distribution monitoring to follow-up after delivery; detention monitoring of the situation of migrants and refugees being detained; and field visits to check the delivery of partners. Multi-discipline teams monitor the project through:
- Announced and unannounced spot-checks and site visits;
- Age, gender and diversity assessments;
- Focus group discussions;
- Informal interviews with beneficiaries; and
- The tracking of programmatic and financial data through programme files, databases, and records.
The findings feed into programme evaluation, as well as planning and project design.
Adjustments to refugee focus groups were made following beneficiary consultations. For example, selection criteria were refined and there is now a crèche for children whilst mothers get support from UNHCR. Community centres (through the CBPN) are used as an opportunity to collect feedback and complaints through a questionnaire. Protection monitoring is a core activity for UNHCR, as reported under output 4. We will continue to encourage UNHCR to coordinate with other partners to ensure that the results are used effectively. For instance, it is not clear what standardisation there is between agencies, so there could be an opportunity for the Protection Cluster to improve this function to get more useful data. An example of UNHCR collecting and acting upon beneficiary feedback to ensure conflict-sensitive programming is when UNHCR obtained feedback that displaced people in Hajjah wanted different contents in shelter kits: they preferred grass to tarpaulin. IDPs were therefore cutting grass and using it to build shelters. This was creating tension with the armed forces as cutting the grass uncovered their weapons store so UNHCR intervened to find alternative supplies of grass.
UNHCR was subject to independent monitoring through DFID Yemen’s Independent Monitoring Programme in 2016, before this programme started, though the findings remain relevant. The study focused on cash transfers. Although the report rated the quality of cash transfer work as good, there was a lack of clarity over: vulnerability criteria, partner adherence to beneficiary selection protocols, poor beneficiary satisfaction in relation to one downstream partner and questions over the reliability of information on beneficiary numbers with one partner. It was also found that multi-sector cash payments did not necessarily lead to improved protection outcomes. As a consequence, DFID decided not to go ahead with a cash element for the short-term intervention that followed the programme in 2016-17. Cash Standard Operating Procedures (SOPs) were subsequently developed by UNHCR and others through a cluster-wide approach (with support from DFID). UNHCR’s proposal for the Support to Displaced People and Migrants 2017-20 programme included cash transfers, which are expected to be improved following the findings of the independent monitoring and subsequent development of SOPs.

DFID supports the Civilian Impact Monitoring Project (CIMP), a service under the Protection Cluster (led by UNHCR), which is contracting the company Safer Yemen. This pilot monitoring mechanism targets 5 governorates; Al-Hudaydah, Sa’ada, Sana’a Governorate, Sana’a Capital and Marib. It involves real-time collection, analysis and dissemination of data on the civilian impact from armed violence in Yemen, including protection forecast and information on victim assistance needs with the purpose of informing and complementing protection programming. The CIMP is reported to be useful for some partners but there are clear limitations – the CIMP is only a pilot covering a select number of governorates but the Protection Cluster has plans to gather feedback and expand to the rest of the country. Some partners in the IOM consortium do not operate in the areas covered and therefore do not find the CIMP to be relevant and another area to improve is follow up action on the data shared. Something that we have suggested it that actors working on data gathering and sharing do a stocktake of what work is being done and where there are opportunities to improve, such as Safer Yemen working more closely with OHCHR to make better use of CIMP data.

IOM
IOM has had difficulty monitoring this year. The DTM has not been fully functional and it has had to reduce the number of monitoring visits in the cholera project due to the challenges posed by movement restrictions. Planned water chlorination and trucking activities were delayed due to the security developments as well as bureaucratic hurdles. There is an inherent difficulty in doing post-distribution monitoring with migrants as they are sometimes only encountered once but efforts are made to track migrants with patrolling teams and there is a beneficiary feedback hotline distributed. For example, an Intersos patrolling team met a group of migrants 15km from where they had initially provided support and received feedback that the shoes provided by Intersos were of poor quality and uncomfortable in the heat. Intersos took on board this feedback and refined the type of shoes provided. There are opportunities to better monitor the routes that migrants take into, through and out of Yemen and use the findings to enhance programming. DRC (in the IOM consortium) has initiated communication with counterparts in Djibouti with a view of strengthening the information sharing between the mixed migration teams in Djibouti and Yemen to enhance the monitoring process. The DTM has worked on the regional migrant flow monitoring report that is pending publication this month. Half of the migrants recently identified by DRC departed Djibouti (Obock) at night and arrived in the morning. DRC has initiated communication with the team in Djibouti with a view of strengthening the information sharing between the mixed migration teams in Djibouti and Yemen to enhance the monitoring process.
Towards the end of 2017, the political and security context was problematic: there was an uptick in ground fighting in Sana’a following the assassination of Saleh and partners therefore scaled back the number of international staff in the country and working patterns of national staff were disrupted. This resulted in a coordination and communication gap, which impacted implementation and monitoring of activities.
IOM is currently going through DFID’s independent monitoring process. Design for the study is underway and the study is expected to take place in quarter two.

Evidence
The business case for this programme includes budget for a mid-term evaluation study. The design of this study would be informed by the recommendations of this review. There is not yet a plan but possible topics for evaluation could include CBPN or regional migration flows. It is anticipated that a plan will be agreed with partners before quarter three
Overall in Yemen, there has been a lack of humanitarian data in relation to population tracking due to the DTM not fully functioning. Scenario planning by different humanitarian actors relies on DTM figures, which are being produced despite the DTM not being fully functional, and the Inter-Cluster Coordination Mechanism (ICCM) uses DTM data. OCHA is coordinating a survey on how clusters are using DTM data, and there should be results in 2-3 months. We will receive these results and work with IOM to use them to drive improvements.
To better serve the ‘Leave no one behind’ agenda, this programme could generate more data on the disaggregation of results. There is some good disaggregation reported to DFID of IOM’s results by age and sex. This shows that there is generally a high proportion of male migrant beneficiaries, for example, 89%, of beneficiaries of legal counselling are male (79% men and 10% boys), which is consistent with assumptions but for IOM protection referrals 41% of beneficiaries are female. Gender disaggregation of results relating to IDPs and refugees is more balanced between males and females.

Learning
Quarterly reports and meetings as well as meetings between consortium partners have been opportunities capture and share lessons. Key lessons identified are:
- Involvement of local authorities at the outset of programme design is key in securing quick endorsement by authorities. Involvement of these actors at project design phase may have helped to minimise resistance to activities, although the turnover of staff within the authorities can mean renegotiation is necessary regardless.
- Approaching the authorities as a united consortium that is implementing one programme may have contributed to obtaining the approval of activities sooner, particularly for the migrant component, which has been met with resistance as more than one agency is struggling to secure approval in the north.
- Stronger coordination between consortium partners from the start would have: removed the duplication of activities; provided an improved referral system; allowed for more effective negotiation with authorities; and better data and quality of services. Consortium partners have been discussing the design and development of one screening form and one database with disaggregated figures on men, women, girls, boys, elderly, disabled, GBV cases and unaccompanied and separated children. The consortium met in March 2018 to discuss and agree on the timing of meetings, reporting, service mapping, a migrant database, referral pathway and activation of the consortium technical working groups. Lessons from this session will be taken forward and regular coordination meetings between consortium partners, DFID and UNHCR to be maintained.

Progress on recommendations from previous reviews
The programme completion report (PCR) of this programme’s predecessor and the programme of support to UNHCR before that recommended ensuring that targets are realistic given the highly dynamic political and conflict context in Yemen. For the design of this programme, realism was factored into the targets set for UNHCR and these targets have mostly been surpassed. We will assess, jointly with UNHCR, whether the targets could be revised to make them more ambitious for the next review.
Another lesson was that all project indicators are measurable by partners. In spite of a focus on this in the design of the programme, there are some (elements of) indicators that partners don’t report on. Specifically, the beneficiary feedback element that proved unmeasurable for UNHCR under the previous programme. UNHCR is recording this information for IDPs and is working on doing the same for refugees. IOM has been prioritising delivery of services before capturing feedback on those services but we will push for this information to be collected when possible.
One lesson that has not been taken forward but will be from now is that partners should report in the first instance using the overarching log frame to maximise efficiency and avoid confusion when it comes to reporting. The overarching logframe will therefore be the format that partners use when reporting to DFID.
There has been progress in encouraging UNHCR to respond on the basis of needs alone, in terms of assistance to IDPs, for instance, as UNHCR, using UK funds, were able to quickly respond to a wave of displacement at the beginning of 2018 by procuring shelter kits and core relief items for IDPs. There is still progress to be made, however, especially with regard to responding to the needs of migrants with clear protection and medical needs in the vicinity of the Kharaz refugee camp.
There has been progress against the recommendation to disseminate factual information to potential migrants in their country of origin regarding the on-going conflict and security and economic situation in Yemen – including security risks and protection threats. In 2017 UNHCR carried out an information campaign entitled ‘Dangerous Crossings’ involving TV, radio, social media and billboards.