Type of Review: Annual Review

Project Title: Support to Ministry of Gender and Child Development - Programme for the Promotion and Protection of Women and Children’s Rights in Zambia

Date started:	13/03/12	Date review undertaken: February 2014

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is investing £2,337,500 over 3 years (2013-2016) to support the empowerment of women and girls in Zambia through the Ministry of Gender and Child Development (MGCD). The funding is supporting the Ministry’s “Programme for the Promotion and Protection of Women and Children’s Rights” (PPPWCR) and includes a flexible Technical Assistance Fund for Gender Equality. This programme is allowing the Ministry to provide technical support to priority line ministries (lands, agriculture, health and education) which will then enable them to implement gender-responsive policy, planning and budgeting including increased collection of sex-disaggregated data. The programme is providing training to key staff at district, provincial and national level as well as to Zambia’s traditional leadership. The Technical Assistance Fund will provide the Ministry and key partners with high level and specialist training including strategic planning, advanced gender analysis and training of trainers. / The Ministry of Gender and Child Development is one of the most underfunded and under-resourced ministries in Zambia[1]. With its expanded role which now includes child development, the Ministry needs even more dedicated resources to ensure that it can fully meet its challenging gender mandate. The funding is aimed at enabling MGCD to access a reliable and predictable funding source which willl in turn enable it to deliver results that will allow it to make the case for sustained funding from the Government of the Republic of Zambia (GRZ). / The funding is channelled through the UNDP who act as the management agent. Currently DFID is the only bilateral supporting the programme and UNDP has a variable contribution between £500,000 and £600,000 dependent on project need. To date, UNDP have contributed USD$101,000.
[1] The mid-term review of the JGSP noted GIDD’s key weaknesses as limited staff and limited resources.

What are the expected results?
The intended impact of the intervention is reduced gender inequality in Zambia. / The intended outcome is an enabling environment for the legal, political, economic and social empowerment of women in Zambia. / With DFID support, the MGCD will deliver the following outputs: / Effective leadership, coordination and monitoring of action to improve gender equality. / Support to priority ministries to implement gender-responsive policy, planning and budgeting. / Coordinated action to domesticate[2] the Convention on Elimination of all forms of Discrimination Against Women (CEDAW) and to implement the Anti-GBV Act. / A national communication strategy to promote positive gender norms and increase awareness of laws and policies. / A national strategy to increase women’s representation in decision-making positions. / The intervention will contribute to achievement of the following results: / Revision of at least 4 laws to conform to CEDAW provisions. / 30% of newly allocated state land allocated to women. / 40% of decision-making positions in the civil service held by women. / 55% of adults attaching equal importance to men and women.
[2] Government commitments are reflected in legislative frameworks i.e. in the Constitution and relevant laws.

What is the context in which UK support is provided?
Gender inequality is high in Zambia and women and girls face discrimination in every aspect of life. The legal framework provides inadequate protection against discrimination for women and girls. Zambia has yet to incorporate the provisions of international and regional conventions on gender equality into the Constitution and related laws. Women are under-represented in politics and decision-making positions at all levels of society. Female representation in Parliament is among the lowest in the region; only 12% of MPs are women. Representation falls to 6% at local government level. Women are also poorly represented in the upper echelons of the civil service. / Women face significant economic disadvantage. They have less access than men to productive resources such as land, credit, agricultural inputs and markets to sell products, and are also less likely to be in employment particularly in the formal sector. Social norms support widespread discrimination. Women are regarded as subordinate to men and have less voice and autonomy and fewer opportunities than men. Gender discrimination limits the educational opportunities of girls, who are more likely to drop out of school than boys and are less likely to have access to vocational training. / Progress in the empowerment of women and girls has been slow. Much of the 2000 National Gender Policy has yet to be implemented. The Gender in Development Division (GIDD), which pre-dated the Ministry of Gender and Child Development (MGCD) and which was mandated to lead the national response, suffered from weak capacity. / However, recent changes offer the prospect of taking forward the gender equality agenda. The enactment of the Anti-Gender Based Violence (GBV) Act in 2011 demonstrated what can be achieved when key actors in government and civil society collaborate. Since the election of a new government in 2011, there have been signs of greater political commitment to gender equality, including the upgrading of the GIDD to a full ministry – the Ministry of Gender and Child Development (MGCD) – with both the Minister and Permanent Secretary having a strong track record in gender and increased funding from the Government of Zambia (GRZ). The MGCD has developed a restructuring plan, which is expected to be approved and which will increase its capacity and its ability to push through positive gender measures at provincial and district levels. Following wide consultation, the MGCD has developed a Programme for the Promotion and Protection of Women and Children’s Rights (PPPWCR), which will focus on legislative reform, political representation, economic empowerment and social empowerment. Donor investment is required to complement GRZ investment, to ensure that the PPPWCR is fully funded. A recent cross-programme evaluation of DFID Zambia programmes also concluded that a stronger support to the MGCD will be critical if DFID Zambia is to achieve its goals on the empowerment of women and girls. / DFID Zambia commissioned an evidence review in 2012 to inform the development of the programme, which identified examples of where gender ministries have made a difference but also highlighted some of the challenges. The evidence review showed that supporting gender ministries can have a positive impact on legal and policy frameworks and on the political representation of women. But it also noted that gender ministries are often weak, marginalised, under-resourced and ineffective, as well as being prone to changes in leadership and structure. / Although DFID funding commenced in March 2013, the Ministry officially commenced the PPPWCR in June 2013 mainly due to protracted government approval processes. DFID is currently the only bilateral agency supporting this programme. This is the first Annual Review.

## Section A: Detailed Output Scoring
Output 1: MGCD delivers effective leadership, coordination and monitoring of action to improve gender equality
Output 1 score and performance description: A
Progress against expected results: / Output 1.1: Number of functional working groups for coordinating gender programmes and strategies that include all relevant stakeholders including civil society, other line ministries, traditional leaders: Milestone indicator: 5 working groups - Steering Committee of Permanent Secretaries. 2, Gender Statistics Committee at Central Statistics Office 3. Gender Sub Committees in 3 Line Ministries ( PITC) / Milestone met – Following a recommendation from the MGCD to the Secretary to Cabinet in November 2013, the Steering Committee of 13 Permanent Secretaries met in February 2014. The Gender Statistics Committee of the CSO met in Nov 2013. Working groups with the Ministry of Finance, Ministry of Lands and Ministry of Agriculture have also been formed and met. It is expected that all groups will meet at least three times each year. / Output 1.2: National gender M&E plan and system established and implemented: Milestone indicator - 25% (5) of line ministries and provinces submit data on core indicators in the national gender M&E plan. / Milestone met: In December 2013, 7 line ministries and 3 provincial offices met in December 2013 to submit and update the data in National M and E Plan which will feed into the forthcoming Gender Status Report / Output 1.3: Annual publication and dissemination of National Gender Status report: Milestone Indicator - 2011 report produced and disseminated to key political, traditional, religious, media and civil society stakeholders / Milestone met: 2011 National Gender Status Report published and disseminated. Breakfast meeting held in September 2013 with between 40 and 50 stakeholders from other line ministries, academia, the private sector, co-operating partners and civil society organisations in which findings presented and discussed. / Output 1.4: Gender Equality fund used for strategic training and capacity building of MGCD and gender focal points. Milestone indicator - Strategic Training and Capacity Building Analysis Plan completed and approved by MGCD. / Milestone met: After consultation with the MGCD, the then Permanent Secretary (PS) agreed for the Ministry to undergo a strategic training and capacity building analysis. MGCD drew up a concept note and Terms of References were agreed in which direct reporting was to the Permanent Secretary. Consultants were engaged in November 2013 and completed their report of the Strategic Training and Capacity Building Plan Analysis. The consultancy involved wide-ranging consultations at all levels of the Ministry, priority line ministries, gender focal points and gender sub-committees. In December 2013, a meeting of the MGCD team was called to discuss the draft report and despite a change of PS in January 2014, the report was finalised and positively received. In order to keep up the momentum, a follow-up consultancy is underway to agree to a 2 year national Strategic Gender Training Plan. / Key Issues: / Leadership within the Ministry has been uneven due to 3 changes of Permanent Secretaries in the past six months. Co-ordination and monitoring within the Ministry are weak. There is currently no dedicated M&E officer which is a key function for the Ministry and the systems in place to monitor other ministries performance against gender targets, is antiquated. MGCD’s Restructuring Plan, which would have seen it expand and strengthen its national, provincial and district outreach, has not as yet been approved by the Treasury (although it has received Cabinet approval). Gender focal points and Gender sub-committees in both line ministries and provincial offices are generally not performing their gender responsibilities to the standard required. Strategic planning has also been weak in the Ministry and internal systems need to be strengthened in order for MGCD to deliver on its commitments with the existing resource-base. It is clear from the Strategic Training and Capacity Needs Assessment and from talking to Ministry staff, that a few small strategic changes could go a long way in improving its effectiveness. / Recommendations: / (1) That gender focal points and gender sub-committees need to be better motivated, utilised and co-ordinated to assist the Ministry in delivering its commitments on gender. / (2) That an electronic data capture system needs to be installed as soon a possible so that line ministries can update the system remotely. The data management system of the current M&E system is outmoded. / (2) That an M&E officer needs to be appointed and deployed in the Ministry as soon as possible to fill this critical function. Currently there is no dedicated officer dealing with M&E. / (3) That a further assumption should be added to the logframe indicating that M&E capacity is adequate to ensure effective monitoring. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 2: Priority Line Ministries implement gender responsive policies, planning and budgeting
Output 2 score and performance description: A / Progress against expected results: / Output 2.1: No of Priority ministries demonstrating increased gender planning - 1. guidelines for gender responsive budgeting developed. / Milestone met: With some technical support from GIZ (Germany), guidelines were developed in September. 2013 and ‘validated’ (officially approved) in Dec 2013. These guidelines were based on the SADC protocol guidelines and represent a more robust and systematic tool for gender planning and budgeting than that used previously by the Ministry. / Output 2.2: % (No of Line Ministries) that have adopted gender responsive budgeting tools. Milestone: 47% (9) line Ministries (Education, Health, Lands, Agriculture, Chiefs, Home Affairs, Energy, Community, Mines) have gender responsive budgets / Milestone met: These line ministries have all included a component of gender responsive budgeting in their budgets. The challenge now will be to ensure they are all trained using the new guidelines and that they further increase the percentage of their budgets dedicated to strategic gender activities. / Output 2.3: %( No of line Ministries) reflecting expenditures on gender programmes. Milestone -- 5 (25%) line Ministries (Education, Lands, Chiefs, Home Affairs, Community)
Milestone met: GRZ’s 2013 National Financial Report demonstrate that these line ministries have actually expended the budgets on gender activities / Key Issues: Despite attainment of these targets, the Ministry still has a way to go before it has the capacity to really influence line ministries to adopt a more substantive adoption of strategic gender planning and budgeting. The Ministry will need to increase its own skills set as well as the number of officers available to undertake this strategic influencing role. / Recommendations: / MGCD need to have a more robust system to record percentage of budgets allocated against percentage of budget actually expended. This needs to be made easily available. / MGCD to develop a stronger collaboration with GIZ to ensure it is fully equipped to train and influence other line ministries to adopt gender responsive budgeting and planning. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 3: Coordinated action to domesticate CEDAW and implement the Anti-GBV Act
Output 3 score and performance description: A
Progress against expected results: / Output 3.1: Strategy to review and revise laws to conform to CEDAW[3] provisions developed: Milestone: Gender Equality Bill developed and submitted to Cabinet. / Milestone on track: Draft Gender Equality Bill completed in December 2013 and on track to be submitted to Cabinet in March 2014. / Output 3.2: % (number) of traditional leaders trained in CEDAW provisions and the Anti-GBV Act - Training plan developed. / Milestone exceeded: Training Plan developed and 30 traditional leaders already trained. / Output 3.3 Fast track courts for cases of GBV piloted: Milestone - Draft framework for the creation of fast track courts developed. / Milestone met - The framework has been developed in collaboration with Zambia Law Development Commission (ZLDC) and will be shared by end March 2014. / Output 3.4 Strategy implemented to to increase women's land ownership: Milestone - gendered assessment of land ownership conducted. / Milestone met. MGCD has been collaborating with the Zambia Land Alliance to ensure that the a gendered assessment of statutory land allocation was conducted in November 2013. The draft report has been produced and will be published by April 2014. / Recommendations: / That MGCD needs to develop a closer working relationship with the Ministry of Justice (as well as other relevant stakeholder ministries) to ensure that the process of domesticating is not stalled, using the Steering Committee of PSs to lobby for acceleration of the domestication process. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? Yes – given that MGCD is dependent of Ministry of Justice for overall progress on this output, we recommend that risk rating in increased from low to medium
[3] Convention for the Elimination of Discrimination Against Women

Output 4: Communication strategy promotes positive gender norms and increased awareness of laws and policies
Output 4 score and performance description: A
Progress against expected results: / Output 4.1: No of radio Programmes produced on community and commercial radio stations. (cumulative): Milestone - 200 / Milestone met - 218 programmes have been produced. / Output 4 2: No of TV Programmes on gender equality issues produced and aired. (cumulative): Milestone - 50 / Milestone met – 50 TV programmes on gender equality were budgeted for and aired. / Output 4.3: No of Journalists trained in Gender/ Child responsive reporting (per annum): Milestone – 20 / Milestone exceeded – 50 journalists have been trained / Output 4.4 - Film dealing with gender equality issues produced: Milestone - Gender film (Malliposa) launched and aired / Milestone met: Film has been launched and aired nationally on Muvi TV and ZNBC. Social media (Facebook) has captured public reactions to the film which are generally positive. An accompanying series has been developed and will be aired on TV with live discussions straight after each viewing. A mini review of the film was undertaken as a result of which plans are already afoot to take film to the rural areas and to the compounds. / Output 4. 5: National Gender Perception surveys conducted and disseminated and feed into gender strategy: Milestone - 2012 NGPS validated and fully disseminated to stakeholders / Milestone met: 2012 NGPS validated and disseminated in the second half of 2013. / Recommendations: / That MGCD maintain and boost its efforts on changing social norms through a sustained media and communications strategy. There are lots of competing demands on the Ministry’s time and resources and communications is all too easily dropped in favour of other more ‘pressing’ demands. / That MGCD systematically captures and records social media commenting so to compile ‘lessons learned’ which can feed into similar ventures in the future. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

Output 5: Strategy to increase women's representation in decision-making positions implemented
Output 5 score and performance description: A
Progress against expected results: / Output 5.1 - Consultation processes take place to ensure adoption of engendering public service strategy: Milestone: PSMD consulted and have agreed to start implementing the Strategy / Milestone met: In Nov 2013, MGCD initiated a communication to the Secretary to Cabinet recommending the appointment of a Steering Conmmittee of permanent secretaries to enforce gender mainstreaming in key line ministries. A committee of 13 PSs was formed including the PS of the Public Services Management Division (PSMD). The Secretary to Cabinet (SC) has urged the Ministry to draw clear targets for the line ministries to meet in 2014. A strategic gender training session is being planned for April 2014 with the Committee of Permanent Secretaries. The SC has inputted into the design of this training. Moving forwards, it will be important for the Ministry to ensure it does not lose the momentum which has been gained within the Cabinet Office. / Output 5. 2: Number of Parliamentarians sensitised on 50/50 SADC Protocol – This milestone will be measured in 2015 / Output 5.3: Campaign to increase votes for women takes place: Milestone - Analysis of major Political Party manifestos for affirmative action has been conducted. / Milestone on track: MGCD has commenced work with the Women’s Lobby on this analysis which will feed into the 2016 Vote for Women Campaign. The analysis will be finalised in March and disseminated short thereafter. / Recommendations: / MGCD should increase its efforts to engage the Women’s movement in the 50:50 campaign to regain lost momentum since this will lay the groundwork for the 2016 Vote for Women campaign. / MGCD should include women’s representation in its Communication Strategy and engage with media on this as early as possible. / MGCD will need to think strategically about how it engages line ministries to be more gender responsive. Clear and measurable targets will need to developed if line ministries are to have greater buy-in. / Impact Weighting (%): 20% / Revised since last Annual Review? Y/N / Risk: Medium / Revised since last Annual Review? Y/N

## Section B: Results and Value for Money.
1. Progress and results

1.1 Has the logframe been updated since last review? Yes. Some changes have been made to some of the milestone indicators after consultation with MGCD. These changes were agreed with DFID Results Adviser. The agreed changes have improved the measurability of the milestones. / Two output indicators have been introduced: / Output Indicator 1.4: Gender Equality fund used for strategic training and capacity building of MGCD and gender focal points. / This was added to reflect the level of internal effort expended in ensuring that this component underpins the capacity building of MGCD / And / Output Indicator 4.4: Film dealing with gender equality issues produced and aired / This indicator was added to reflect the increased emphasis (as a result of DFID influencing) being put on changing social norms and negative cultural practices. / 1.2 Overall Output Score and Description: / Overall output score is A – outputs met expectation / 1.3 Direct feedback from beneficiaries / As part of the Strategic Training and Capacity Building Analysis, extensive consultations were held with A broad range of governmental and non-governmental stakeholders. Roundtable Conversations were convened with Gender Focal Persons Civil Society organisations. Tailored, confidential questionnaires were distributed to GFPs and the Chairs of Gender Sub-committees (GSC) within priority Line Ministries; and to middle ranking MGCD personnel at national level. / The feedback from the gender focal points was particularly noteworthy. It suggested that although the GFPs potentially represent an important resource, they are currently not being effectively utilised for the promotion of gender equality, largely because the role is insufficiently supported, recognised and valued by the line Ministries which employ them and by the MGCD. This serves as a serious brake on individual GFP motivation and limits their potential for innovation. Consultations with Ministry staff revealed that even within the Ministry, there is no up-to date record of GFPs and that they rarely meet with GFPs, suggesting poor co-ordination. Few national level GFPs have received either the GFP Terms of References or an orientation or induction and some complained that they do not feel motivated or confident to carry out a gender role. They often perceive the GFP role as being an “add-on” which they must juggle with their substantive job responsibilities and there is little accountability. The strategic gender training session is being planned for April 2014 with the Committee of Permanent Secretaries noted above should help. / Recommendation: / That the Ministry establish an up-to-date database of GFPs. MGCD should identify an officer (possibly located in the Directorate of Information and Planning) to take on he role of maintaining and updating GFP records
1.4 Summary of overall progress / After a slow start to the programme due to a protracted internal approval process, the PPPWCR was finally approved by MGCD in June 2013. Progress has been steady and in some instances impressive such as in the implementation of their communications strategy. It is important to note that despite achievement of outputs, sustainable change will only happen if underlying institutional change accompanies programme delivery. The undertaking of the Strategic Training and Capacity Building Analysis was a key component for the overall strengthening of the Ministry and it was important to get agreement for this so early on in the programme. Despite 3 PSs since the inception of the programme, buy-in at the senior level has been important for developing a forward looking plan which will see the Ministry strengthened in a number of critical areas identified in the assessment.
1.5 Key challenges / 1. Senior management turnover - the Ministry has had 3 Permanent Secretaries since the start of the programme. Despite this, the new PS has demonstrated leadership and commitment to the programme. / 2. The constraints on capacity and resources are a key challenge for Government budget. The Ministry is underfunded – out of the 35 million Kwacha assigned to MGCD in the 2013 Yellow Book, only 14 was disbursed and it was unclear at the time of this Annual Review, what government contribution has been to the PPPWCR. / 3. The Strategic Training and Capacity Building Analysis outlined a number of challenges including poor coordination and utilisation of gender focal points and gender sub-committees at provincial level; weak monitoring and planning capacity. However, more fundamental than this is the low gender analytical capacity within the Ministry itself and strategic planning. / 4. Financial capacity within the Ministry needs to be strengthened in order for the Ministry to demonstrate its ability to manage external resources. UNDP have agreed to assist the Ministry with a short-term Finance Officer. UNDP will also undertake a HACT (Harmonised Approach to Cash Transfers) which assesses the capacity development needs of public financial management systems. It is expected that once the HACT has been conducted and the Finance Officer in place, the programme could trial some ring-fenced direct transfers to the Ministry.
1.6 Annual Outcome Assessment A / Outcome Indicator Milestone Planned - 2014 Progress / Outcome 1 / Number of laws revised to conform with CEDAW One The Gender Equality Bill has been drafted and will be submitted to Cabinet by April 2014. It is expected to be passed during the course of 2014 / Outcome 2 / % of Newly Allocated State Lands allocated to women 20% According to the 2014 draft Gendered Assessment of Lands carried out by MGCD and Min of Lands 27% of newly state lands have been allocated to women / Outcome 3 / % women in decision-making positions in the civil service PS: 22%; Director: 25%; Deputy Director: 45% Still awaiting data - Information has been requested from PSMD / Outcome 4 / % of Zambians aged 18 and above that attach equal importance to both women and men N/A This will be measured in 2016 (using the 2015 National Gender Perception Survey) / The outcome of the programme of support to MGCD is to create an enabling environment for the empowerment of women. The theory of change assumes that action in a number of areas (social, legal, economic and political) will result in a more enabling environment for the empowerment of women and girls. For this to occur, building sustainable institutional capacity is critical since only government can bring about the policy, legislative change to address structural barriers to gender equality and ensure that sector ministries deliver gender responsive programmes. / Although there are a number of both external and internal challenges to the achievement of the outcome, it is expected that the programme will strengthen the enabling environment for the empowerment of women and girls, thus achieving its outcome. The Strategic training and capacity building of the Ministry will be a key underlying factor for this overall outcome achievement and it is encouraging that the Ministry has accepted the findings of the Strategic Training and Capacity Building Analysis and that moves are afoot to implement a corresponding plan.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The project has five financial components as per table below: / Financial Performance: Budget Vs. Actuals Disbursed / Component Budget Expenditure % utilised / 101 £24,111 £24,111 100% / 102 £343,750 £316,854 92% / 103 £151,404 £97,322 65% / 104 £150,000 £58,226 39% / Component 1- this was spent on the Appraisal and Design phase in which a consultant was contracted to design the programme. There was no spend on this line in 2014. / Component 2 - this component represents the contribution to the MGCD channelled through UNDP. DFID’s total disbursement was £316,854 against a forecasted £343,750. This 8% underspend was mainly due to a two months delay for UNDP local office to receive the funds on the first disbursement. This was caused by UNDP’s own internal processes which require that funds are first channelled through their headquarters in New York. / Component 3 - this funding represents the TA Fund for Gender Equality which is principally for support to the MGCD (and key stakeholders) to build capacity for gender. The total budget for 2013 was £151,404 and £55,139 was spent in the year under review while £42,183 is already committed to running contracts leaving 35% as unspent. The 35% will be spent in April 2014 – the Strategic Planning training which was envisaged for end of March 2014 has now shifted to April. / Component 4 – This component is Front Line Delivery and has a yearly budget of £150,000. A total of £58,566 was spent in 2013 leaving a balance of £91,773. This and outer year budgets will not be spent because the advisor is now being funded from the administration budget. It is being recommended that the remaining funds be moved to component 102, to programme delivery. / 2.2 Key cost drivers / The major cost drivers in the Programme were media costs (22%). The Ministry of Gender and Child Development has prioritised information dissemination in order to increase public awareness on gender and child issues. This is aimed at changing entrenched negative perceptions on gender equality. The engagement of community radio stations from various and remote parts of the country has proved to be an effective channel to disseminate key information to the remotest parts of the country. Use of media is important because MGCD has no structures at the district level. / This is followed by consultative meetings and training programmes that the Ministry of Gender and Child development, undertakes in its coordination role (19%). In order to achieve maximum participation and attendance at these events, MGCD often undertakes workshops which entail costs related to conferencing and accommodation. The third cost driver is that of technical/consultancy services (14%). / 2.3 Is the project on-track against original timescale: Yes / The project is on-track on most of the planned activities under two of the programme components although the UNDP component had a slow start due to the two months delays in the local country office receiving funds from its head-office.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There have been no substantive changes in evidence. / 3.2 Where an evaluation is planned what progress has been made? / A mid-term evaluation is planned for October 2014. Terms of Reference for this evaluation will be drawn up in April 2014.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / This programme has been risk-rated ‘Medium’ given the overall underfunding of the Ministry, the low level of resources assigned to it by GRZ as well as its weak gender analytical capacity. In addition, MGCD is reliant on the collaboration with and cooperation of other ministries in order to successfully fulfil its mandate. It is expected that the Strategic Training and Capacity Building Plan will directly mitigate some of the internal risks for programme delivery such as weak strategic planning skills and inadequate gender analytical capacity as well as better utilisation of gender focal points. However there is still a risk that the Ministry will remain under-resourced and that turnover at senior level (in particular at PS level) will remain high.
4.3 Risk of funds not being used as intended – Low. All funding is channelled through UNDP which has financial guidelines and stringent financial management controls with various approval levels which guide the implementation of the programme. It has a fully dedicated Finance office which is supervised by the Deputy Country Director for Operations. In addition, audits are undertaken annually – these are supervised by the Office of the Auditor General. UNDP will carry out an audit of the programme in April to May 2014. / 4.4 Climate and Environment Risk – Low

5. Value for Money
5.1 Performance on VfM measures / The indicative VFM measures used in the Business Case to assess programme performance included consultancy fees, transport costs, subsistence allowances and transport costs. Despite some savings and efficiencies (noted below) against some of these measures, namely training and consultancies, since the start of the programme, it is noted that a more robust VFM framework is needed and we have agreed to put these in place by May 2014. / Trainings: In the 2014 work plan, the cost for meetings & trainings has dropped from 27.58% of the budget to 19%, this is a result of continuous dialogue with the Ministry in the management of the project that resulted in behaviour change of the Ministry, where they have reduced the number of days for most meetings & training workshops from 5 days to 2 days. This has contributed to significantly reducing the costs associated with these activities. / Consultancy fees - UNDP has urged MGCD to negotiate competitive consultancy fees based on results/end product as opposed to negotiating daily rates. This has led to significant cost savings. For example, MGCD forecasted a budget of USD 211,000 in its 2013 annual workplan for consultancies against an actual expenditure of USD 122,000. / 5.2 Commercial Improvement and Value for Money / The Programme has demonstrated VFM in a few areas. For example, when procuring goods, UNDP requires competitive bidding and as such, all procurement requests must be accompanied by 3 quotations as proof. / In addition, given the high costs associated with printing material, UNDP has recently entered into a long term agreement for printing services which is expected to significantly reduce the Ministry’s printing costs associated with this programme. / Recommendation: / It is recommended that a meeting is set up with UNDP and DFID programme team and DFID Economist to develop a robust VFM framework with agreed upon VFM measures and indicators by May 2014. It is further recommended that a VFM component is included in the ToRs for the independent evaluation which will take place in October 2014. / 5.3 Role of project partners / Working relationship between DFID and MGCD is deemed good. Besides MGCD, the main project partner is UNDP. There is a strong working relationship with UNDP with fluid communication with DFID. Communication between UNDP and MGCD has at times been strained due to the stringent financial controls exercised by UNDP over all aspects of the budget. While this ensures financial rigour and ensures DFID funding is well spent, it does not allow MGCD to demonstrate its ability to spend effectively and efficiently. The undertaking of the HACT and the putting in place of a Finance Officer should allow MGCD the opportunity at a later stage to demonstrate capacity in this area. / 5.4 Does the project still represent Value for Money: Yes – given the above savings noted above, we believe that it does still represent value for money. However, in line with the above recommendation, we plan to be able to robustly test the extent of VFM through putting in place a robust and agreed set of VFM measures and as part of an independent review of the programme in October 2014. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / There are no specific conditions attached to this programme.

7. Conclusions and actions
Despite some significant challenges in terms of underfunding, high turnover of permanent secretaries and inadequate staffing levels, the Ministry has worked hard to deliver concrete results, in particular in the area of communications. However, improvement in the overall organisational planning, co-ordination role and analytical capacity of the Ministry will be fundamental not only for the success of this programme but for the longer term ability of the MGCD to make a sustainable difference to gender equality in Zambia. It is encouraging to note that the MGCD have accepted the findings of the Strategic Training and Capacity Building Analysis so positively and that they are actively engaged in the development of a plan to implement the key recommendation. DFID will need to oversee this process closely. In addition, MGCD will need to adopt a more strategic and co-ordinated approach vis a vis the utilisation of GFPs. Given that it is unlikely in the near future that there will be a significant increase in MGCD’s staff resources, GFPs should be used as the foot-soldiers of the Ministry to assist in the delivery of line ministries’ gender commitments.. / List of Recommendations summarised below: / MGCD / That gender focal points and gender sub-committees need to be better motivated, utilised and co-ordinated to assist the Ministry in delivering its commitments on gender. / That an electronic data capture system needs to be installed as soon a possible so that line ministries can update the system remotely. The data management system of the current M&E system is outmoded. / That an M&E officer needs to be appointed and deployed in the Ministry as soon as possible to fill this critical function. Currently there is no dedicated officer dealing with M&E. / That a more robust system to record percentage of budgets allocated against percentage of budget actually expended. This needs to be made easily available. / That working relationships with the Ministry of Justice need to be strengthened to ensure that the process of domesticating is not stalled, using the Steering Committee of PSs to lobby for acceleration of the domestication process / To maintain and boost its efforts on changing social norms through a sustained media and communications strategy. There are lots of competing demands on the Ministry’s time and resources and communications is all too easily dropped in favour of other more ‘pressing’ demands. / To systematically capture and record social media commenting so to compile ‘lessons learned’ which can feed into similar ventures in the future. / To increase its efforts to engage the Women’s movement in the 50:50 campaign to regain lost momentum since this will lay the groundwork for the 2016 Vote for Women campaign. / To include women’s representation in its Communication Strategy and engage with media on this as early as possible. / To think strategically about how it engages line ministries to be more gender responsive. Clear and measurable targets will need to developed if line ministries are to have greater buy-in. / To develop a stronger collaboration with GIZ to ensure it is fully equipped to train and influence other line ministries to adopt gender responsive budgeting and planning / To establish an up-to-date database of GFPs. MGCD should identify an officer (possibly located in the Directorate of Information and Planning) to take on he role of maintaining and updating GFP records / DFID / That a further assumption should be added to the logframe indicating that M&E capacity is adequate to ensure effective monitoring / That all funds be removed from the component budget which were meant for the advisor who is now being paid through Admin budget and allocate them to programme. / DFID/UNDP / That DFID inform UNDP when funds have been disbursed and for UNDP thereafter to track the transfer and confirm receipt of funding. / That a meeting is set up with UNDP and DFID programme team and DFID Economist to develop a robust VFM framework with agreed upon VFM measures and indicators by May 2014. It is further recommended that a VFM component is included in the ToRs for the independent evaluation which will take place in October 2014.

8. Review Process
The review was undertaken by the Social Development Adviser and the Programme Officer for this programme in the Governance Team. Joint meetings were held with the Programme Implementation Technical Committee of the PPPWCR, the Ministry and separately with the with UNDP. The DFID Economist was also consulted with regards to the VFM aspects of the programme. The recently 2014 DFID-commissioned Strategic Training and Capacity Building Analysis of MGCD was also consulted.