Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attach ed to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Programme for the Promotion and Protection of Women and Children’s rights in Zambia
Programme Value: £2.3m		Review Date: 6th March 2015
Programme Code: 203428	Start Date: 12th March 2013	End Date: 30th June 2017

Summary of Programme Performance
Year	2013	2014
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

Over the past year, the Ministry of Gender and Child Development (MGCD) has demonstrated good progress in its leadership, coordination and monitoring of actions to improve gender equality, particularly in the revision of the National Gender Policy and production of the National Gender Status Report. The Ministry has made good progress on its coordinated action to domesticate CEDAW[1], to implement the Anti-GBV Act, and establish the foundations for piloting fast track courts. The development of the Gender Equality Bill is a particularly significant achievement which entailed intensive consultation with a wide range of government and civil society stakeholders.
[1] Convention on the Elimination of All forms of Discrimination of Against Women.

MGCD has increased and improved a number of its coordination structures albeit to different degrees of regularity and has made good progress on its national communication strategy which is broadly on track. Moving forwards, it will need to adopt a more strategic approach to communication and use of media to promote positive gender norms and increase awareness of new and existing laws and policies.

The Committee of Permanent Secretaries - established in 2014 by the Secretary to Cabinet to mainstream gender - has now expanded to encompass 13 line ministries and continues to meet under the strong leadership of the SC.

There has been goodfprogress with the national strategy to increase women’s representation in decision-making positions, The Ministry has developed the ‘Count Her In’ strategy aimed at increasing women’s political reperesentation. They will now also need to increase the focus on increasing women’s representation within the public service.

DFID-funded training and capacity development has been well received with positive feedback although it is too early to assess impact. The Ministry needs to ensure that it improves the speed at which it issues contracts to key service providers.

The Ministry has made attempts to increase its ownership of the PPPWCR by directors and ensure the latter are assigned responsibility for the different outputs of the programme.

A consultant was contracted to undertake an independent evaluation of the programme. This was done in September/October 2014 and the findings of that review have fed into this Annual Review. During the Annual Review process, we have requested evidence where the evaluation noted evidence gaps.

The Ministry continues to bes underfunded by central government. In 2014 only 26% , of the total budget allocation was disbursed to MGCD. The 2015 budget saw an increase in the allocation to the Ministry but only on one budget line: the Women’s Economic Empowerment Programme

Summary of recommendations for the next year

Outcome Indicator
Outcome Indicator 1.4 to now become an impact indicator

Output 1
- MGCD to establish electronic database of Gender Focal Points by August 2015
- MGCD to meet with GFPs at least once a year and update GFP database (ongoing)
Output 2
- MGCD and MoF need to work together to develop clear, practical guidelines for line ministries on how to do gender-responsive planning and budgeting, and to ensure that gender is addressed in MOF guidelines for output-based budgeting and the draft bill (May 2015)
- MGCD should develop a longer term plan of engagement with MoF: This should included a gender audit of the MoF; targeted orientation in gender analysis and gender mainstreaming for Directors of the 14 departments in MoF and plans for joint analysis of the 2015 budget. The Bank of Zambia has conducted its own internal gender audit and it could be helpfut to engage with them (June 2015)
- MGCD needs a clear plan for influencing and training line ministries in gender-responsive planning and budgeting. This should include a meeting or workshop to sensitise PSs, capacity development for line ministry Directors of Planning and GFPs, and capacity development for the MGCD;s own staff in gender-responsive planning and budgeting. The budget process begins in April, so training should be conducte
Output 3
- MGCD needs to ensure that the design for evaluating the fast track courts is robust and assesses the effectiveness and costs of this approach. (May 2015)
- MGCD should work with the MOCTA to clarify respective roles and responsibilities and ensure that training for traditional chiefs is well planned and coordinated (Sept 2015)
- MGCD should work with their Communications department to ensure increased public awareness on women’s land ownership issues (Dec 2015)
- MGCD to incorporate into their strategy some actions aimed at increasing women’s acquisition of land titles. (Dec 2015)
Ourtput 4
- MGCD needs to take a more strategic approach to communication and use of media to promote positive gender norms and increase awareness of laws and policies. This should be reflected in a revised strategy (October 2015). The findings of the evaluation should feed into the development of this strategy.
- MGCD needs a communication strategy that goes beyond use of media to include community approaches. Partnerships with district gender sub-committees and CSOs would enable the MGCD to reinforce media activities. MGCD should take forward plans for more road shows, but ensure that these are monitored and evaluated.(October 2015)
- MGCD communication strategy in 2015 should include evaluation of the audience, reach and impact of media activities and include a follow up National Gender Perception Survey. (Nov 2015)
- The planned evaluation of the Communications Strategy should focus on how social norm change can be effectively achieved through media. (April 2015)
Ourput 5
- MGCD needs to finalise the Count Her In campaign strategy, including identifying clear timeframes and roles and responsibilities for different partners in delivering the strategy, and ensure that there are regular meetings of all partners to coordinate activities and review progress (April 2015)
- MGCD needs to continue to raise the issue of women’s representation in the public services so as to give greater weight to the Engendering the Public Strategy and PSMD’s role therein. (ongoing)

Value for Money
- As the programme is in the 2nd year of implementation, MGCD reduce on conference services and focus more on programme implementation (ongoing)
- MGCD and UNDP to adhere to paying all DSAs from the GRZ funds. (March 2015)
- VFM framework should be updated and establish the main unit costs and ensure they are reasonable and represent VFM.(June 2015)
- The training and capacity development programme we have embarked on with the Ministry in both planning and gender analysis should address some of these internal risks, including weak performance, capacity and skills. MGCD and UNDP need to monitor risks and develop a plan for risk management and mitigation.(October 2015)
- DFID should ensure strong and early engagement with the new Minister of Gender as well as with any other key personnel that may have been changed as a result of the change in government (ongoing)
- There is need to conduct a more rigorous assessment of the impact of trainings, including training and capacity building activities implemented through the DFID-funded Gender Equality Fund. (October 2015)
- communications activities in particular radio and TV shows needs further assessment, using listenership surveys and other tools to ascertain coverage and a better estimate of unit costs (Nov 2015)
- UNDP and MCGD need to identify how the expenditure approval process can be made more efficient (April 2015)

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

DFID is providing £2,337,500 over 3 years (2013-2016) to strengthen the capacity of MGCD through funding for the Ministry’s Programme for Promotion and Protection of Women and Children’s Rights (PPPWCR) and flexible technical assistance. DFID funding is managed by UNDP, which also provides technical and advisory support. MGCD is expected to deliver: effective leadership, coordination and monitoring of action on gender equality; support to priority ministries to implement gender-responsive planning and budgeting; coordinated action to domesticate the Convention on Elimination of all forms of Discrimination Against Women (CEDAW) and implement the Anti-Gender Based Violence (GBV) Act; a national communication strategy to promote positive gender norms and increase awareness of laws and policies; and a national strategy to increase women’s representation in decision-making positions. The main objectives of the mid-term evaluation of the PPPWCR, which was conducted in October-November 2014, were to evaluate progress towards these results, identify potential adjustments to PPPWCR design and implementation, and make recommendations to improve execution and achievement of results.
The two main programme components are:
the direct support for the implementation of the PPPWCR
Gender Equality Fund(technical assistance) for training and capacity building of MGCD staff, Committee of Permanent Secretaries and gender focal points (GFP) from the line ministries.

The main programme assumption is that if the laws which provide equal rights for women and men are implemented and enforced, and the social norms are changed, this will increase women’s voice and influence . In turn, it will reduce gender inequality by providing an enabling environment for the legal, political, economic and social empowerment of women in Zambia.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Outcome: Enabling environment for legal, political, economic and social empowerment of women

Indicators	Milestone 2014 (March)	Milestone 2015 (March)	Progress
1.1 Number of laws revised to conform to CEDAW provisions	1	2	On track. The Gender Equality Bill will shortly be tabled to Cabinet and is expected to be passed by Parliament in early 2015. The Child Code Bill has been drafted.
1.2. % newly allocated state land allocated to women	20%	25%	Exceeded. Based on data from Ministry of Lands, CSO reports that 28.3% of newly allocated state land was allocated to women in 2013.
1.3.% women in decision-making positions in the civil service	PS: 22%; Director: 25%; Deputy Director: 45%	No milestone	No data in draft National Gender Status Report 2014; progress report not provided by PSMD. Available data, from CSO Gender Statistics Report 2013 and ZNWL Gender Audit 2014, suggests little overall improvement.
1.4.% of Zambians aged 18 and above that attach equal importance to both women and men	N/A	N/A	To be measured in 2016 using the 2015 National Gender Perception Survey. This indicator will now become an impact indicator – see explanation at the end of this section

The theory of change assumes that action in a number of areas (social, legal, economic and political) will result in a more enabling environment for the empowerment of women and girls. For this to occur, building sustainable institutional capacity is critical since only government can bring about the policy, legislative change to address structural barriers to gender equality and ensure that sector ministries deliver gender responsive programmes.

Although there are a number of both external and internal challenges to the achievement of the outcome, it is expected that the programme will strengthen the enabling environment for the empowerment of women and girls, thus achieving its outcome. The Strategic training and capacity building of the Ministry is a key underlying factor for this overall outcome achievement and it is encouraging that the Ministry has embraced the training under the Gender Equality Fund. The work of the Committee of Permanents Secetaries is also a good indicator that government is taking the necessary steps to improve the enabling environment for women and girls.

There are four outcome indicators, two of which are on track, one is slightly off track and one will be measured next year.

Outcome indicator 1.1 is on track.: There has been good progress with efforts to ensure that legal frameworks are in place that conform to CEDAW and Convention on the Rights of the Child (CRC) provisions. The draft Gender Equality Bill, which encapsulates key issues from CEDAW and the SADC Protocol on Gender and Development, will shortly be tabled to Cabinet MGCD expects the bill to be passed by parliament in early 2015. MGCD has also developed a draft Child Code Bill, which aims to domesticate the CRC provisions in their entirety.

Outcome 1.2 This has been exceeded. However, there still needs to be greater awareness of the Ministry of Lands 2000 directive that land agencies, particularly local councils, should allocate 30% of newly allocated land to women, is limited. Encouragingly, the Minister of Lnads has recently declared increased this to 40%. The revised draft National Gender Policy includes a commitment to ensuring that women own at least 50% of land allocated, although no timeframe is included for achieving this.

Outcome 1.3 There has been little change in the proportion of women represented in decision-making positions in the civil service. According to the CSO 2013 Gender Statistics Report, the proportion of female PSs increased from 26% (11/43) in 2010 to 40% (16/40) in 2012. However, the ZNML 2014 gender audit of the public and private sectors reports that this had subsequently declined to 17% (7/42). The picture is similar for Directors and Deputy Directors. The CSO 2013 report shows that the proportion of female Directors increased slightly from 25% (37/150) in 2010 to 28% (38/136) in 2012, while the proportion of female Deputy Directors decreased from 36% (28/76) in 2010 to 34% in 2012 (30/87); MGCD will be working with PSMD (Public Services Management Division) in the coming year to increase women’s representation within the Public Service.

Outcome 1.4: Yet to be measured. During the Annual Review discussions, it was recommended that this outcome indicator should become an impact indicator because its achievement is dependent on a large range of factors mostly outside MGCD’s control.

Overall output score and description

Key lessons

Ownership of the programme by MGCD directors is key for the longer term sustainability of PPPWCR’s programme objectives. MGCD has taken active measures to ensure greater ownership of PPPWCR by individual directors.
The Secretary to Cabinet has shown high level political will to mainstreaming of gender in the public service by establishing and chairing the Permanent Secretaries Committee on Gender Equality. MGCD should take full advantage of this development to ensure implementation of gender equality commitments.

Key actions

- MGCD to prepare for the development of the National Perception Survey
- MGCD to conduct an evaluation of its Communication Strategy and revise it to ensure it has a more strategic focus on changing social norms
- Travel costs still remain one of thethe major cost drivers for this programme. One of the components of this is related to international travel. Therefore DFID and UNDP to advise MGCD that travel to attend international meetings are part of the core business of government and therefore should be catered from MGCD government resources.

Has the logframe been updated since the last review? Some slight amendments were made to the logframe. Yes – following consultation with MGCD, the following minor amendments have been made to the logframe:
Output indicator 1.1- change of SAG working group to “Social Protection working group” since the SAG has been superceded by the SPWG
Output indicator 1.2 – Change ‘ ministries and provinces to MPSAs’ – Ministries, Priovinces and Spending Agencies (MPSAs) to be in line with GRZ terminology
Output indicator 3.1 –Change of advocacy meetings to Consultative meetings
Output 5.1: The milestone has been swapped with the output indicator to ensure a logical flow i.e consultations need to take place before full implementation of the strategy. Output indicator now is: Committee of Permanent Secretaries implementing the strategy and Milestone now reads Consultation processes take place to ensure adoption of engendering public service strategy

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	MGCD delivers effective leadership, coordination and monitoring of action to improve gender equality
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones / March 2015	Progress

1.1 Number of functional working groups for coordinating gender programmes and strategies that include all relevant stakeholders including civil society other line ministries, traditional leaders	7 (two additional including Group; Gender Status Forum.	Exceeded: four additional groups all of which have met at least 3 times in the past year. / Gender Status Forum / Social Protection Group / Ministry of Lands Taskforce / Anti GBV Committee / This brings total number of functional working groups to 9
1.2 National gender M&E plan and system established and implemented	9 (47%) MPSA – ministries, provices, and spending agencies submit data on core indicators in the national M&E plan	Slightly exceeded: 10 / Ministries Agriculture.; Lands; / Education; Health; Community DevelopmentMother and Child Health; Justice; Commerce; Labour (8) and Victim Support Unit; Bank of Zambia (2)
1.3 Annual publication and dissemination of National Gender Status Report	2013 report produced and disseminated to key stakeholders	Achieved. 2013 report has been combined with 2014 data and finalised. This will be published by the beginning of March and a dissemination meeting is planned on Women’s Day – 8th March 2015.
1.4 Gender Equality Fund used for training and capacity building of MGCD and gender focal points[2]	Gender Equality Fund used to develop capacity of 50% of gender analysts and Directors in MGCD	Exceeded: All 5 directors and 10 assistant directors have attended 2 of the training provided under the GEF. In addition, 10 provincial child development coordinators also received training.
[2] Output Indicator 1.4 was added following the DFID Annual Review in February 2014.

Key Points

Achievements
- Overall, there has been good progress on this output, particularly with respect to production of the National Gender Status Report and planning and implementation of training and capacity development; however, coordination and monitoring and evaluation (M&E) need to be improved.
- MGCD has provided effective leadership in the legal and policy arena, in particular they have demonstrated strong leadership and coordinated action in developing the Gender Equality Bill and in advocating for Cabinet approval. The latter underwent intensive stakeholder consultation.
- MGCD successfully revised the National Gender Policy including active participation of line ministries and other stakeholders. The revised policy was adopted in October 2014 and is expected to be ratified in parliament in early 2015. Unlike the last NGP, this one sets out the roles and responsibilities of line ministries in relation to gender.
- Coordination has improved and this is reflected in the number and breadth of meetings on key thematic areas as well as the streamlining of certain groups. An example of the latter was the streamlining of four anti GBV fora to two.
- The Committee of Permanent Secretaries has now expanded to include 13 line ministries and continues to be driven by the strong leadership of the Secretary to Cabinet. The PSs and the Secretary to Cabinet have undergone strategic planning training from the Gender Equality TA Fund to positive feedback.

Challenges
- Although coordination structures have been established, the Ministry now needs to consolidate and focus on building on the success and ensuring meetings are consistent and regular.,
- National gender focal points do not meet regularly and receive limited support. There has been little change since the 2010 Auditor General’s report. MGCD used to have quarterly meetings with GFPs in line ministries and at provincial levels. Although GFPs are invited to participate in meetings and workshops, there is no forum that provides them with the opportunity to meet together, or with MGCD, on a regular basis. MGCD does not have an up to date database of GFPs. There is no systematic approach to ensure that the knowledge and skills of GFPs are kept up to date or to build their capacity for influencing.
- Provincial staff lack capacity and support. MGCD has Provincial Child Development Coordinators (PCDCs) at provincial level and plans to recruit additional provincial staff in 2015. However, their job descriptions do not reflect their gender-related responsibilities and training is often lacking. The TA Fund will address some of the training issues.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. Gender focal points and gender sub-committees need to be better motivated, utilised and coordinated to assist the Ministry in delivering its commitments on gender. Status: The training and capacity development plan incorporates support for institutional strengthening of gender focal points through action learning sets and peer support.

2. An electronic data capture system needs to be installed as soon as possible so that line ministries can update the system remotely. The data management system of the current M&E system is outmoded. Status: Limited progress. However, VSO is proposing to provide additional advisory support to MGCD, which would include support for the introduction of management information systems.

3. An M&E officer needs to be appointed and deployed in the Ministry as soon as possible to fill this critical function. Currently there is no dedicated officer dealing with M&E. Status: MGCD should be able to address this when new staff are recruited in 2015. The proposed VSO officer is likely to be assigned to the Ministry to help build M&E capacity.

4. A further assumption should be added to the logical framework indicating that M&E capacity is adequate to ensure effective monitoring. Status: This has been added.

Recommendations
- MGCD to establish electronic database of GFPs by August 2015
- MGCD to meet with GFPs at least once a year and update GFP database (ongoing)

Output Title	Priority line ministries implement gender-responsive policies, planning and budgeting
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones / March 2015	Progress

2.1 Priority ministries demonstrating increased gender planning	Guidelines for gender-responsive budgeting implemented in all priority ministries	Achieved: There are 5 priority line ministries: Lands; Agriculture; Community Development; Health and Education. / All of these ministries have budgeted for gender equality programming.
2.2 % (number of line ministries) that have operationalised gender-responsive budgeting tools	60% (11) line ministries have adopted gender-responsive budgeting tools	Slightly off track- 10 / 9 line ministries were reported in the 2014 Annual Review. A further ministry – PSMD – has been trained since that period.
2.3 % (number of line ministries) reflecting expenditures on gender programmes	45% (8) line ministries	Achieved:8. Ministries of Agriculture; Works and Supply; Commerce; Lands; Labour’ Heath’ Education and Community Development

Key Points
.
Achievements
In addition to the gender responsive guidelines, meetings have been held with the Secretary to the Cabinet and the Committee of Permanent Secretaries to orient them on gender-responsive budgeting. ;
Challenges
- Engagement with the Ministry of Finance has been challenging. Despite MGCD efforts, the Ministry of Finance (MOF) has not been fully engaged in development of the guidelines. MOF is currently revising guidance on planning and budgeting, to shift from activity-based to output-based budgeting. This will be piloted initially in a few ministries, including Education, Health and Agriculture. MOF is also reported to be drafting a bill to ensure that cross-cutting issues such as gender are integrated in planning and budgeting process.
- Even though ministries may budget for gender equality programming., often ministries may not receive more than 50% of what they have budgeted for, some as little as 30% (according to discussions with MGCD) thus this indicator is unlikely to be achieved.

Summary of responses to issues raised in previous annual reviews (where relevant)

1. MGCD needs to have a more robust system to record percentage of budgets allocated against percentage of budget actually expended. This needs to be made easily available. Status: Work in progress. MGCD uses the GRZ National Financial Report. The Ministry intends to put this system in place in the following months.

2. MGCD needs to develop a stronger collaboration with GIZ to ensure it is fully equipped to train and influence other line ministries to adopt gender responsive budgeting and planning. Status: Planned for 2015,
Recommendations
- MGCD and MoF need to work together to develop clear, practical guidelines for line ministries on how to do gender-responsive planning and budgeting, and to ensure that gender is addressed in MOF guidelines for output-based budgeting and the draft bill (May 2015)
- MGCD should develop a longer term plan of engagement with MoF: This should included a gender audit of the MoF; targeted orientation in gender analysis and gender mainstreaming for Directors of the 14 departments in MoF and plans for joint analysis of the 2015 budget. The Bank of Zambia has conducted its own internal gender audit and it could be helpfut to engage with them (June 2015)
- MGCD needs a clear plan for influencing and training line ministries in gender-responsive planning and budgeting. This should include a meeting or workshop to sensitise PSs, capacity development for line ministry Directors of Planning and GFPs, and capacity development for the MGCD;s own staff in gender-responsive planning and budgeting. The budget process begins in April, so training should be conducted as early as possible in 2015, if MGCD is to influence the 2016 budget (June 2015)

Output Title	Co-ordinated action to domensticate CEDAW and implement the Anti-GBV Act
Output number per LF		3	Output Score	A+
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones / March 2015	Progress

3.1 Strategy to review and revise constitution and laws to confirm to CEDAW provisions developed	Consultative meetings for the adoption of the Gender Equality Bill held	Achieved. The Gender Equality Bill will shortly be tabled to Cabinet and is expected to be passed into law in the next session of Parliament. Parliamentarians and civil society have been consulted extensively.
3.2 % (number) of traditional leaders trained in CEDAW provisions and the Anti-GBV Act	20% (46) traditional leaders trained	Exceded: 62 traditional leaders trained of which 32 were gazetted chiefs.
3.3 Fast track courts for cases of GBV pilot implemented	Fast track courts piloted	Achieved – Piloting has commenced. Fast track courts in Kabwe and Lusaka have been identified and are being equipped. The’ rules of court ‘ have been developed and are just awaiting quality assurance by the Ministry of Justice
3.4 Strategy implemented to increase women’s land ownership	Results from gender assessment feed into development of the land and gender strategy	On track to be achieved – the strategy document will be finalised by end February. Recommendations from the the Gendered Lands Assessment are already being implemented and this has resulted in Ministry of Lands issuing a policy statement that 40% of newly allocated statutory land will be issued to women.

Key Points
Overall, there has been good progress with this output, particularly with respect to the Gender Equality Bill and establishing the foundations for action on training of traditional leaders, piloting fast track courts and improving women’s access to land. Further efforts are required to take forward these priority areas.

Achievements
- The draft Gender Equality Bill is a significant achievement. MGCD has played an important role in the process of drafting the bill and in coordinating consultation, including organising two meetings to obtain inputs from parliamentarians.
- The Minister of Land has issued a policy statement declaring that 40% of newly allocated state land will be issued to women.

Challenges

- There is a need for a coordinated approach to working with traditional leaders. The Ministry of Chiefs and Traditional Affairs (MOCTA) is conducting sensitisation for traditional leaders, and the Joint GRZ UN Programme is also targeting this group. Greater efforts are needed to ensure that those responsible for administering customary law are aware of CEDAW and changes in statutory law.
- Despite the declaration by the Minister of Lands, a lot of work will need to happen to ensure that this actually happens. There is still a huge challenge in Zambia of low levels of women actually accessing title deeds to land even though they may have been allocated land.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. The MGCD needs to develop a closer working relationship with the Ministry of Justice to ensure that the process of domesticating is not stalled, using the Steering Committee of Permanent Secretaries to lobby for acceleration of the domestication process. Status: There is still scope to strengthen the working relationship with the Ministry of Justice and to better use the Steering Committee to ensure that the Gender Equality Bill is reflected in other relevant laws.

Recommendations
- MGCD needs to ensure that the design for evaluating the fast track courts is robust and assesses the effectiveness and costs of this approach. (May 2015)
- MGCD should work with the MOCTA to clarify respective roles and responsibilities and ensure that training for traditional chiefs is well planned and coordinated (Sept 2015)
- MGCD should work with their Communications department to ensure increased public awareness on women’s land ownership issues (Dec 2015)
- MGCD to incorporate into their strategy some actions aimed at increasing women’s acquisition of land titles. (Dec 2015)

Output Title	Communication Strategy promotes positive gender norms and increased awareness of laws
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones / March 2015	Progress

4.1 Number of radio programmes produced on community and commercial radio stations (cumulative)	50 (cumulative 250 )	Exceeded – 259. 225 have been programmed and a further 34 will be planned in and around International Women’s Day in March on Hot FM and Pan African radio stations.
4.2 Number of TV programmes on gender equality produced and aired (cumulative)	25 (cumulative 75)	Achieved. Exactly 25 programmes have been aired including a documentary on women’s economic empowerment,
4.3 Number of journalists trained in gender/child responsive reporting (per annum)	20	On track to be achieved.. Training was delayed but MGCD are contracting Zamcom with training 20 national and provincial journalists on gender equality by end March 2015. The contracts will be issued by 2nd March and training will take place by mid March.
4.4 Film dealing with gender equality issues produced and aired[3]	TV series for gender film aired and related radio programmes aired	On track. Film aired nationally on ZNBC and Muvi TV. An accompanying series of 13 episodes has aired on national TV and a commercial channel with live discussion. MGCD has recently started community road shows in rural areas where the film is followed by facilitated discussion.
4.5 National Gender Perception Surveys conducted and disseminated and feed into gender strategy	National Gender Communication strategy implemented	Achieved: The Strategy is being implemented and the above results reflect some of the action areas in the strategy.
[3] Output Indicator 4.4 was added following the DFID Annual Review in February 2014.

Key Points
This output is on broadly on track, in terms of specific activities, although there have been delays in implementation in 2014. Media reporting of gender issues has increased and improved – although much of this focuses on GBV and child marriage

Achieved
- MGCD has developed a good relationship with the Zambia National Broadcasting Corporation (ZNBC) and Zambia News and Information Services (ZANIS), works closely with newspapers such as the Times of Zambia and Daily Mail and with one third of community radio stations nationwide in nine of ten provinces
- MGCD has played an important role in increasing the visibility of gender and has put a lot of effort into increasing its profile in the media..
- Three daily newspapers – the Times, the Daily Mail and New Vision – now have a dedicated gender section

Challenges
There is considerable emphasis on commemoration of specific days and events. This takes up significant time and resources, and limits capacity for communication on wider gender equality issues, policies and laws and women’s and girls’ rights. MGCD needs a communication strategy that underpins a sustained campaign on priority issues – for example, to promote awareness of the Gender Equality Bill, the directive on women’s access to land, and participation of women in politics. Messages also need to move beyond the general to be more informative and action-oriented.

Communications is under-staffed. All media work – including liaison with radio, TV and print media campaigns and coordination of training – is done by the Communications Specialist funded by UNDP. MGCD currently has no staff with communication and media skills and expertise. Consequently, the Communications Specialist has little time to devote to other tasks in her terms of reference, including support for communications and advocacy at a more strategic level.

Communications activities need to be better monitored and evaluated. Currently monitoring is limited to asking community radio station presenters to provide feedback through self-assessment forms; forms for 2014 have not yet been analysed. Plans to evaluate MGCD communication strategy in 2015 should include evaluation of the audience, reach and impact of media activities and include a follow up National Gender Perception Survey.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. MGCD should maintain and boost its efforts on changing social norms through a sustained media and communications strategy. There are lots of competing demands on the Ministry’s time and resources and communications is all too easily dropped in favour of other more ‘pressing’ demands. : Status: Progress has been made on this as reflected in the overachievement of some of the indicators, However the current communications strategy will need to look at how to achieve a sustained media and communications strategy focusing on changing social norms.

2. MGCD should systematically capture and record social media commenting so as to compile ‘lessons learned’ which can feed into similar ventures in the future. Status: This has been done to some extent , Example: following the airing of the Mariposa series, viewer feedback was sought and a decision taken to assign longer discussion time for more indepth post programme discussions.

Recommendations
- MGCD needs to take a more strategic approach to communication and use of media to promote positive gender norms and increase awareness of laws and policies. This should be reflected in a revised strategy (October 2015). The findings of the evaluation should feed into the development of this strategy.
- MGCD needs a communication strategy that goes beyond use of media to include community approaches. Partnerships with district gender sub-committees and CSOs would enable the MGCD to reinforce media activities. MGCD should take forward plans for more road shows, but ensure that these are monitored and evaluated.(October 2015)
- MGCD communication strategy in 2015 should include evaluation of the audience, reach and impact of media activities and include a follow up National Gender Perception Survey. (Nov 2015)
- The planned evaluation of the Communications Strategy should focus on how social norm change can be effectively achieved through media. (April 2015)

Output Title	Strategy to increase women’s representation in decision making positions implemented
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress

5.1 Committee of Permanent Secretaries implementing the strategy	Consultation processes take place to ensure adoption of engendering public service strategy	Achieved: The accountability for this is now with the Committee of Permanent Secretaries. Some consultation has already taken place and PSMD will be responsible for spearheading activities under the strategy regarding recruitment, promotions, appraisals etc to ensure gender equality.
5.2 Number of parliamentarians sensitised on the 50/50 SADC Protocol (cumulative)	100 (baseline 50)	Achieved - As part of the Gender Equality Bill 50 MPs were sensitised on issues of SADC50:50 – (28 at the Protea Hotel meeting and 22 at Radisson Blu in facilitated discussions) However MGCD is conscious that they will need to undertake more engaged discussions as part of the Count Her In Strategy. These will be done upon the passing of the Gender Equality Bill
5.3 Campaign to increase votes for women takes place	No milestone	On track. Although the next measurable milestone is in 2016, MGCD have already commenced the vote for women campaign including the launch of strategy for the Count Her In campaign to increase women’s political representation and participation.

Key Points
Achievements
MGCD convened a meeting with political parties and civil society organisations in September 2014 to develop the Count Her In campaign strategy. This strategy document,was the result of stakeholder consulation and sets out proposed campaign activities,

Challenges
Recent data on female representation in management positions in the civil service show little change (see discussion of Outcome indicators below). PSMD has not developed targets for line ministries, as requested by the Cabinet Secretary. MGCD has not been able to obtain a progress report on strategy implementation from PSMD. Concerted action is required to ensure that PSMD meets its commitments and takes forward the strategy for engendering the public service.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. MGCD should increase its efforts to engage the Women’s movement in the 50:50 campaign to regain lost momentum since this will lay the groundwork for the 2016 Vote for Women campaign. Status: meeting held in September 2014 and the Count Her In Strategy launched.

2. MGCD should include women’s representation in its Communication Strategy and engage with media on this as early as possible. Status: No action as yet, but media activities are included in the Count her In strategic framework.

3. MGCD will need to think strategically about how it engages line ministries to be more gender responsive. Clear and measurable targets will need to developed, if line ministries are to have greater buy-in. Status: The MGCD is engaging through the Cabinet Secretary Committee of Permanent Secretaries. No PSMD targets set for line ministries.

Recommendations
- MGCD needs to finalise the Count Her In campaign strategy, including identifying clear timeframes and roles and responsibilities for different partners in delivering the strategy, and ensure that there are regular meetings of all partners to coordinate activities and review progress (April 2015)
- MGCD needs to continue to raise the issue of women’s representation in the public services so as to give greater weight to the Engendering the Public Strategy and PSMD’s role therein. (ongoing)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Key Costs	Percentage of the total budget	Cost analysis and drivers
Admin	17.8%	Admin costs were quite high due to procurement of equipment (vehicle, computers, printers, photocopiers. Admin costs will reduce in subsequent years as no large procurement is envisaged on this programme.
Consultancy /technical services	17.6%	This component of the budget consultancy /technical services costs buys technical knowledge and services where they are lacking in MGCD . The 2013 AR recommended for steps to be taken to reduce consultancy and technical costs by support for quality techincal assitance to be provided through the equality fund. The initial TA interventions appear to be effective, we anticipate to see inhouse expertise. We are expecting the cost on this to increase because DFID is also likely to support VSO proposal for in-house capacity building staff to place four advisors with the Ministry as this will improve the Ministry’s capacity to provide support to other line ministries for gender mainstreaming. Even if the cost will increase, we expect the returns to be high. DFID support will be conditional on MGCD commitment to ensuring that advisors have direct counterpart staff.
Media	15.6%	Media is another significant component within the overall budget. MGCD has priotised information dissemination in order to increase public awareness on gender and child issues with the view to change negative perceptions on gender. Media costs are likely to increase during the programme lifetime as gender equality publicity is vital to the programme. As noted above on Output 4, this output has acheived well.

Recommedation:
- As the programme is in the 2nd year of implementation, MGCD reduce on conference services and focus more on programme implementation.
- MGCD and UNDP to adhere to paying all DSAs from the GRZ funds.
VfM performance compared to the original VfM proposition in the Business Case

The Business Case noted that evidence was incomplete over which interventions addressing the gender-specific dimensions of poverty deliver the best VfM. However, the indicative VFM measures used in the Business Case to assess programme performance included consultancy fees, transport costs and subsistence allowances with performance against these being measured at annual reviews. The 3Es of economy, Efficiency and Effictiveness are useful dimesions for VFM analysis and are relevant at all stages of the programme lifecycle.

Economy – There has been good progress, steps have been taken to reduce consultancy costs. DFID is no longer paying DSA; this together with measures taken by MGCD to reduce the length of trainings and consultative meetings will contribute to reduced costs. Further, the annual review has recommended assessment of the reach of communications activities, in particular radio and TV shows. Plans to evaluate MGCD communication strategy in 2015 should include assessment of the audience, reach and impact of media activities; consideration should also be given to inclusion of these issues in a follow up National Gender Perception Survey.

Efficiency – Results are satisfactory relative to overall costs to DFID. TA costs for training and capacity development are relatively high but the quality of outputs is also high and is beginning to demonstrate results.Although might be too early to say, improvements in the work of MGCD are showing. Media costs are relatively high but some high quality programmes have been produced and are likely to contribute to desired results. The disbursements against work plans in this year has been good with planned most activities completed. To some extent, the project is meeting or exceeding some of its targets. However, more assessment is required to provide data on unit costs of training using different training methods and unit costs of support provided per beneficiary.

Effectiveness – Current performance indicates that the goal and specific objectives should be achieved. The factors contributing to success include strong support from the Secretary to Cabinet and PS’s Committee. As noted in the risk assessment , government funding to MGCD for this year was low which meant DFID is the major contributor to the progress made. However, further assessment is required to measure the percentage achievement of results in relation to funding provided per result area and in comparison with alternative approaches although it is recognized that comparison with programmes elsewhere is difficult. Similarly, it is also difficult to measure the total number of direct and indirect beneficiaries reached through replicated results and project multiplier effects.

The last annual review recommended that a robust VfM matrix and a framework be developed within which to assess these needs and this was done. However an update to this is required for the programme to establish and monitor the main unit costs and ensure they are reasonable and represent good value for money.

Recommendation
- VFM framework should be updated and establish the main unit costs and ensure they are reasonable and represent VFM.
- There is need to conduct a more rigorous assessment of the impact of trainings, including training and capacity building activities implemented through the DFID-funded Gender Equality Fund.
- communications activities in particular radio and TV shows needs further assessment, using listenership surveys and other tools to ascertain coverage and a better estimate of unit costs.

Assessment of whether the Programme continues to represent value for money
The enormous gender inequalities in Zambia continue to justify the value of the programme. Programme management lessons learnt during the course of the programme have progressively improved value for money. The Mid-term Review conducted in December 2014 highlighted a number of areas where we can strengthen the value for money of this programme and we will be discussing/discussed these with the partner.
With respect to commercial improvement, the programme has demonstrated VfM in a few areas including through competitive tendering for procurement and entering a long-term agreement for printing services. This is expected to significantly reduce MGCD’s printing costs. Which areas are remaining?

Quality of financial management
For the financial year 2014/15, £662,430 was forecast and disbursed of which 44%has been spent leaving a balance of 56% which is already committed for capacity building and other programme activites taking place in February 2015.

Annual funding to UNDP is split in two tranches (March and September) to avoid payment in advance of need. To date £1.029m (65%) of the total programme budget has been disbursed by DFID Zambia. The risk of funds not being used as intended is considered to be low as UNDP have sound financial management systems. In addition, DFID scrutinises project’s progress and financial reports, work plans and budgets. Narrative and financial reporting requirements have been met.

Date of last narrative financial report	30 Jan 2015
Date of last audited annual statement	Not reqired, only annual certified report which is due in June 2015. However the UNPD audit was obtained quest No. 4867276

E: RISK

Overall risk rating: Low

Overview of programme risk
Following Annual Review discussions, the risk rating has been downgraded to ‘low’ to reflect the low risk of this programme not achieving its output targets The original rating reflected risks identified in the Business Case which included GRZ commitment to deliver on gender equality, under-funding and under-staffing of the MGCD, limited gender analytical capacity and skills and limited leverage to ensure action is taken by other line ministries.

Gender has received high-level political commitment including from the new President, President Lungu. The Vice President is also a strong gender advocate and a former Mnister of Gender who is likely to provide greater leadership on gender.
The Secretary to Cabinent and the PS-MGCD are highly supportive and have established a Committee of Permanent Secretaries which has provided an opportunity to increase the Ministry’sinfluence on other line ministries. However, with a change in the presidency there is a risk that the new minister may be less committed and engaged on gender equality. There is also risk that the both the Secretary to Cabinent and the PS MGCD are moved and that their successors are less supportive of our work. The current PS has been in post for more than one year, the risk of turnover at this and director level has been high from the past.The Ministry is underfunded by central government. Risk of underfunding is still a real issue. In 2014 only 26% , of the total budget allocation was disbursed to MGCD. The 2015 budget saw an increase in the allocation to the Ministry but only on one budget line: the Women’s Economic Empowerment Programme.

Recommedation:
The training and capacity development programme we have embarked on with the Ministry in both planning and gender analysis should address some of these internal risks, including weak performance, capacity and skills. The MGCD and UNDP need to monitor risks and develop a plan for risk management and mitigation.

DFID should ensure strong and early engagement with the new Minister of Gender as well as with any other key personnel that may have been changed as a result of the change in government.

Outstanding actions from risk assessment:

A due diligence was conducted in December 2014 and the following are the outstanding actions for UNDP.
Finding	Recommendation
1.Clarity on responsibility of Steering Committee members in providing oversight	UNDP should develop clear / TORs for the Steering Committee
2. Despite fraud and whistleblowing policies and frameworks, previous agreements which UNDP signed with both Government and NGOs contain inadequate provisions on fraud reporting, investigation or recovery. There is potential scope to further strengthen fraud reporting provisions in the agreements UNDP signs with other partners.	UNDP to ensure all agreements with downstream partners contain robust anti-fraud provisions, including a clear statement of zero tolerance on fraud, a requirement upon the partner to immediately report any credible suspicions of fraud, and effective investigation and recovery provisions.
6. Based on the review of the recent internal audit report (September 2014) from UNDP Office of Audit and Investigations (OAI), some budgets were not adequately set up in ATLAS system. As a result, budgets did not correspond with outputs in project documents and could not be clearly assessed on the accuracy of expenditure in line with budgeted outputs.	Although, management has confirmed its plan to take action on this, there is need to improve effective checking and monitoring of project budget set up in ATLAS system.
7. On procurement process, the OAI also observed few cases of procurement undertaken without evidence of competitive selection. Further, it noted unnecessary delays in the procurement lead-time.	It has been recommended that UNDP need to enhance its compliance with procurement policies and procedures and identify and address possible delays in processing time.

Recommedation:
DFID to agree with UNDP on the timeline for implementation of these recommedations.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Yes. The programme has made progress against the approved timescales in the Business Case and is largely on track against the delivery of most outputs.

Performance of partnership (s)
The programme is implemented by MGCD and managed by UNDP which also provides expertise to strengthen the capacity of MGCD. Partnerships with DFID are good, but the relationship between UNDP and MGCD at times is less positive. According to the Mid Term Evaluation, DFID is viewed by MGCD and UNDP as a constructive, collaborative and supportive partner. DFID and UNDP have a good working relationship and hold regular meetings to review progress in addition to participating in quarterly PITC meetings. The relationship between UNDP and MGCD has been strained at times. This is mainly due to the financial controls exercised by UNDP that MGCD perceives UNDP to be bureaucratic and slow to approve expenditure requests.

Recommedation:
UNDP and MCGD need to identify how the expenditure approval process can be made more efficient.

Asset monitoring and control
Since the inception of this programme, there have been a few assets - mainly office equipment for MGCD - were procured in November 2014 by UNDP with DFID’s approval. The assests procured were in line with the budget and procurement plan. The programme does not envisageany future large procurements. The asset register will be updated quarterly and verification spot checks will take place during the next quarter.

G: CONDITIONALITY (½ page)

Update on partnership principles
Not applicable

H: MONITORING & EVALUATION

Evidence and evaluation
An independent Mid-Term Review was conducted in December 2014 to inform DFID Zambia, as well as MGCD and UNDP on the coverage and effectiveness of PPPWCR implementation, provide evidence to assess the likelihood of achieving the expected results and make recommendations for improving performance. The review assessed the progress of the PPPWCR against stated outputs and identified issues and challenges affecting the efficient implementation of outputs, their contribution to project outcomes. Recommendations from this review have been considered and discussed with MGCD and will help to improve project delivery for the remaining project

The Evaluation consultant conducted a field visit to Kabwe and also conducted individual and group interviews with a range of stakeholders, including government representatives.

Recommedation:
DFID should monitor the recommdations from the mid-term review with the partners on a quarterly basis.

Monitoring progress throughout the review period
A Steering Committee, chaired by the Permanent Secretary is responsible for oversight of the PPPWCR. The Steering Committee comprises DFID, UNDP, PS and Directors in MGCD, representatives from priority line ministries and also includes CSOs and NGOs.

The Steering Committee meets on a quarterly basis to review progress, determine the strategic direction of the programme, and ensure a focus on results.

MGCD submits quarterly progress reports to UNDP, reporting against the PPPWCR annual work plan, including progress towards milestones in the DFID logical framework. In addition, DFID meets with UNDP quarterly in advance of the Steering Commette meeting to monitor progress towards expected results. These meeting are based on the quarterly narrative financial reports.

This Annual Review has drawn heavily on the findings of the mid-term review. In addition, a meeting was held on 30th January 2015 with UNDP and MGCD staff to discuss the progress against outputs and financial management.

The Annual Review was conducted by the Social Development Adviser and the Programme Officer with support from the DFID Economist.