PROJECT COMPLETION REVIEW OF THE
STRENGTHENING EDUCATION PROGRAMME

INTRODUCTION AND CONTEXT

In 2007/08, the Secretary of State approved the ‘Strengthening Education in Pakistan’ (SEP) project. This allocated £2 million for appraisal and design work to develop an education portfolio of up to £150 million over a five year period (2007/08 – 2011/12). In 2011, given the substantial increase in DFID Pakistan’s ambition in education, as articulated in the Operational Plan (2011-2015), the budget of SEP was increased by £0.5 million to £2.5 million.

  1. Expected results

The impact or purpose statement (as stated in the concept note) of SEP is:

“DFID support will strengthen capacities to deliver improved education access, quality and equity of opportunity.”

The programme had three main outputs:

Output 1 - Design and appraisal activities to support the development and implementation of the DFID Pakistan bilateral education programme.

Output 2 - Research, strategy and policy to support the development and implementation of the DFID Pakistan bilateral education programme.

Output 3 - Programme support activities to support the development and implementation of the DFID Pakistan bilateral education programme.

SEP was designed and implemented before the new Business Case process. Therefore, this Aide-Memoire acts as the project completion report.

  1. Context in which UK support was provided

In 2007/08 half the adult population and two thirds of women could not read or write; more than a third of primary school aged children were not in school; and 40% of children had never attended school. 6.8 million children aged 5-9, 60% of which were girls, did not go to primary school representing 10% of the world’s out of primary school children. Pakistan faced, and still does, an education emergency.

Education is the one area with the potential to really transform Pakistan. There is a critical window of opportunity. Pakistan’s growing population is getting younger. This means more its people are under thirty years old, at an age where they can contribute to the country’s economic growth. Never before has it been more important that this generation is healthy, well-nourished and educated, able to work and set up business and play their part in the transformation of Pakistan. This represents a ‘demographic dividend’.

As a result of the Bilateral Aid Review (BAR) in 2010, the size of the education portfolio was further increased to £650 million over the Operational Plan period (2011-2015).

DETAILED OUTPUTS, ACTIVITIES AND RESULTS

Activities have ranged from programme design to strategic level interventions and can be divided into three categories:
- Design and appraisal activities;
- Research, strategy and policy; and
- Programme support activities.

2.1.	Design and appraisal activities

SEP played a key role in design and appraisal activities for DFID Pakistan’s education portfolio, allowing DFID Pakistan to respond quickly and rapidly to changing needs. This now represents DFID’s largest bilateral investment in education to date.

Project	Value	Start Date
Punjab Education Sector Programme (PESP I)	£80 million	Dec 09
Punjab Education Sector Programme II (PESP II)	£350 million	April 12
KP Education Sector Programme	£203.5 million	Sept 11
Punjab Education Roadmap	£2.1 million	Dec 09
Pakistan Education Task Force (PETF)	£2.8 million	Mar 12
Scoping study in Baluchistan	£77,000	Sep 12

2.2.	Research, strategy and policy activities

SEP supported a number of research, strategy and policy activities as outlined below.

Effective Education Budgets Initiative (EEBI)

SEP supported the “Effective Education Budget Initiative’ (EEBI). This was carried out by the Institute for Policy and Social Sciences (I-SAPS) as an innovative approach to monitoring how much the Government of Pakistan was spending on education as well as advocacy for an increased education budget. EEBI increased public knowledge of Government expenditure on education which allowed donors and civil society to engage with policy makers and advocate for a more efficient use of the existing budget and for increased allocations.

The Annual Review of EEBI in 2011 scored a ‘2’ i.e. largely met its objectives. I-SAPS published 2 federal budget analysis reports covering FY 09/10 and 10/11 and engaged with politicians and the media on public policy issues, including the implications of not providing financing. I-SAPS also successfully positioned themselves as a credible policy institute with key decision makers; offering technical assistance to political parties and parliamentary committees on education as well as advocacy.

ISAPS has also been able to leverage the networks developed under EEBI to assist delivery of the current DFID ‘Transforming Education in Pakistan’ (TEP) programme.

Annual Status of Education Report (ASER)

SEP supported the development and production of the ‘Annual Status of Education Report’ (ASER). ASER has been a big success and is widely recognised as a reliable source for education statistics in Pakistan including access, retention, quality and basic learning.

ASER has been endorsed by a range of decision makers and has become a standard reference point for Government, other donors and the wider public sector and private sector.

Support to the Education Sector Reform Unit (ESRU) in Khyber Pakhtunkhwa

SEP helped strengthen the Education Sector Reform Unit (ESRU) in the Department of Elementary and Secondary Education (E&SE), Government of Khyber Pakhtunkhwa (KP). Support from SEP bridged the gap until the DFID funded Khyber Pakhtunkhwa Education Support Programme (KESP) started.

ESRU has acted as the co-ordinating body for education in Khyber Pakhtunkhwa with development partners, NGOs and Government Departments. ESRU has also been involved in the implementation and monitoring process of stipends to the girl students and free textbooks.

2.3.	Programme support activities

In addition to the previous two strands of work, SEP has supported on-going programme implementation activities for DFID Pakistan’s education portfolio including fiduciary risk assessments/audits as well as annual reviews and project completion reports.

VALUE FOR MONEY (VFM)

SEP has expedited the design and appraisal of DFID Pakistan’s £360 million education portfolio of support, allowing much larger and ambitious investments to move to implementation.

All procurement is carried out through an open tendering process to ensure competition and procure the most effective resource possible.

COSTS AND TIMESCALE

SEP was approved in 2007/08 and £2 million allocated for preparation and design work to develop an education portfolio of up to £150 million over a five year period (2007/08 – 2011/12). In 2011, given the substantial increase in DFID Pakistan’s ambition in education, as articulated in the BAR and Operational Plan (2011-2015), the budget of SEP was increased by £0.5 million to £2.5 million.

RISKS

Given the nature of SEP, the risk rating of the programme was ‘low’. Education has remained a policy priority for DFID Pakistan as confirmed through the BAR and Operational Plan (2011 -2015) process.

Challenges have included maintaining sustained oversight of the diverse portfolio of activities supported through SEP.

CONCLUSIONS AND RECOMMENDATIONS

Over all, SEP has achieved its objectives. It has funded design and appraisal activities which have expedited the scale up of DFID Pakistan’s education programme making it DFID’s largest bilateral portfolio of support anywhere in the world. Niche research, strategy and policy activities have been funded; some of which in the case of ASER have become a wider public good through the provision of reliable education statistics and data.

Continued management oversight and ownership is critical to run programmes of this nature to avoid the programme moving in un-intended directions. In the future, a small governance board or committee should be considered to help with management and scrutinise activities.

7.	PROJECT SCORING

The impact or purpose statement (as stated in the concept note) of SEP is:

“DFID support will strengthen capacities to deliver improved education access, quality and equity of opportunity.”

The three outputs have been scored:

Output 1 - Design and appraisal activities

This output has been marked A++. The impact weightage for this output is 60%. Design activities carried out under this programme have substantially exceeded expectations. SEP was originally conceived to support the design of the £150 million programme but, after the 2011-2015 Operational Plan, supported design activities for DFID Pakistan’s £360 million education portfolio.

Output 2 - Research, strategy and policy

This output was scored as A+ with an impact weightage of 20%. Activities performed under this output have moderately exceeded expectations. The programme has designed and funded strategic interventions such as EBBI, ASER and ESRU.

Output 3 - Programme support activities

This output was scored as A with an impact weightage of 20%. The activities performed under this output have met expectations. With support from SEP, critical activities like fiduciary risk assessments, annual reviews and project completion reports have been completed.

Given the above, the Review Team recommend that the impact level score should be A+.

The SEP Project Completion Report Review Team
April 2013