Annual Review – post April 2018

Title: Programme for Improving Mental Health Care (PRIME) – Research Programme Consortium (RPC)
Programme Value £ (full life): £7,977,172		Review Date: September 2018 (reporting period 1st April – March 31st)
Programme Code: 201446-104	Start Date: 1 May 2011	End Date: 30th April 2019

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017	2018
Programme Score	A	A+	A+	A+	A+	A	A +
Risk Rating	High	High	High	High	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201446/

A. Summary and Overview

Description of programme
It is estimated that 10.4 % of the global burden of disease is due to mental, neurological and substance use disorders with a significant proportion in low and middle income countries (LMICs). This equated to 258 million disability adjusted life years (DALYs) in 2010. Despite this burden, is it estimated that almost four out of five persons with severe mental disorders in LMICs did not receive any treatment in the previous year[1][2].
[1] Kohn R, Saxena S, Levav I, Saraceno B. The treatment gap in mental health car. Bull World Health Organ 2004; 82 (11): 858-66.
[2] WHO. Mentlah health gap action programme (mhGAP): Scaling up care for mental, neurological and substance use disorders. Geneva. World Health Organization; 2008

In order to address this, there have been numerous calls for the implementation and scale up of evidence based treatment in LMICs but there remains little evidence on how to practically develop and implement this within the significant financial, human resource and system constraints.

The Programme for Improving Mental Health Care (PRIME) is an eight-year DFID-funded Research Programme Consortium (RPC) working in 5 countries; India, Uganda, Ethiopia, Nepal and South Africa. The programme aims to generate high quality research evidence on the implementation and scaling up of treatment programmes for priority mental disorders (depression, alcohol use and psychosis, with the addition of epilepsy in Nepal, Uganda and Ethiopia) in primary and maternal healthcare contexts in low resource settings. It seeks to achieve this through the following overlapping phases and activities:
- Inception (2011-12) - develop district specific integrated mental healthcare plans (MHCPs) comprising packages of mental healthcare for delivery in primary and maternal healthcare.
- Implementation (2012-16) - implement the MHCPs in partnership with Ministries of Health in PRIME countries (Uganda, Ethiopia, South Africa, India and Nepal), and evaluate the feasibility, acceptability and impact of these plans in primary healthcare and maternal healthcare.
- Scaling Up (2016-17) - evaluate the scaling up of these packages of care at district or sub-district levels.
- Extension (2017-19) – use data and evidence gathered during the implementation and scale up phase to refine the PRIME MHCPs, publish findings and ensure PRIME research is understood, effectively shared, and used to inform policy and practice.

Summary supporting narrative for the overall score in this review
The programme has scored an A+. PRIME has continued to function effectively as a consortium, achieving or exceeding all our logframe targets. Research activities have included the data cleaning and analysis of the implementation phase of PRIME, the completion of scale up in Ethiopia, Nepal and South Africa (n=59 facilities), quality improvement work in all five countries and a specific focus on developing and implementing maternal mental health interventions. 23 peer reviewed publications and 13 presentations at scientific conferences in the last grant year. Research uptake activities have included ongoing engagement with the media and 82 meetings with policy makers and planners at district, national and international levels have been produced. Different audiences are engaging in PRIME`s work, including academics (cited 2223 times in Google Scholar), media (206 media citations) and policy makers; PRIME research has been cited in 13 international documents which are likely to affect policy and practice, including the draft WHO mhGAP operations manual, and various national and sub-national policy documents in PRIME countries.

Recommendations for the year ahead
- PRIME has identified the challenge of balancing time and resources to both maximise dissemination of outputs versus publication writing. The PRIME leadership team and country teams should continue to maintain oversight of time and resource management to ensure that opportunities to disseminate results are maximised without impacting on the writing and publication of PRIME research, particularly the key outcomes papers. The PRIME publication list should be reviewed monthly to ensure work remains on track. (ongoing)
- PRIME are in an intense final phase of writing up their findings, including revising the district mental healthcare plan model. It will be important to ensure that this updated version is disseminated and shared effectively, particularly to those currently using and rolling out the old plan (ongoing).
- A key challenge during the reporting year has been for PRIME PhD students (many of whom are also key members of PRIME staff, e.g. PIs and project coordinators) to balance their scientific work with other broader needs of the programme. Now that field work is winding down, this challenge has reduced but with the demands of key dissemination events and activities over the final year, and with potential increase in focus on new grants and projects that are starting, PRIME should closely monitor progress, including setting clear deadlines and protecting time for publication writing (ongoing).
- Amendments to the logframe should be made as outlined in section C (by December 2018).
- Learning objectives for PRIME during the final year of the programme include: identifying the barriers to success of implementing and scaling up integrated district metal healthcare plans, and strategies that can be used to overcome them.
- PRIME should upload research outputs and outcomes into ResearchFish after March 2019.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Establish and maintain an efficient and well managed RPC which draws on the strengths of each partner to deliver a high quality research programme that achieves the RPC’s goal and purpose.
Output number per LF		1	Output Score	A
Impact weighting (%):		10	Impact weighting % revised since last AR?	N

Indicator(s)		Milestone(s) for this review	Progress
1.1 Proportion of the following key RPC deliverables completed in consultation with all consortium partners	Key programme documents have been reviewed and revised as needed during years 7 and 8 to improve progress towards achieving outputs, purpose and goal of RPC.		Met: key documents (logframe, risk register, and the PRIME publication and expression of interest policy) and processes (meeting structures and lines of accountability) have been reviewed and revised as needed.
1.2 meetings held between key governance groups (PMG; CAG; CMG)	All groups have continued to meet as planned during the life of the consortium ( 4 meetings annually of the PMG, 2 meetings annually of the CAG and monthly CMG meetings)		Met: all groups have continued to meet as planned.
1.3 Draft mental health care plans for priority disorders in primary care and maternal care available.	Data analysis of outcome data from implementation phase completed for use to revise integrated mental healthcare plan		Met: Data analysis of evaluation data is complete and being written up for publication.

Output moderately exceeded expectations. PRIME continue to be a well-managed consortium with robust systems and processes to ensure effective oversight and financial management, whilst maintaining open communication channels and facilitating collaboration across the consortium partners. All meetings have been conducted as scheduled, including: an annual face-to-face meeting, quarterly teleconferences, which include all PRIME partners, and monthly teleconferences between the core PRIME Management Group (PMG). The consortium management group, in each country has been meeting more than monthly to ensure that activities remain on track and staff feel supported, given the timelines during the final phase of the programme,. The Community Advisory boards (CABs) in Ethiopia, India and Uganda continue to meet twice a year. As previously reported, a CAB was never formed in South Africa at the request of the district and in Nepal, changes in staffing at district level meant that the CAB was not functioning as planned; PRIME now conduct regular meetings with district stakeholders to inform them of progress.

A key achievement in the reporting period was final approval of PRIME`s data sharing and publication policy. Over the life of PRIME, the approach to open access of data has changed rapidly across the health and development sectors. Consent forms for most of PRIME studies did not explicitly ask participants to consent to data being made available open access. PRIME have now received approval from all PRIME country institutional review boards to make PRIME data available on request, and with a data sharing agreement in place prior to sharing the data, from August 2019. In the interim, PRIME will accept requests that don’t duplicate existing PRIME publications or for the verification of findings.

Following the annual meeting held in Durban (February 2018), the final data analysis of the outcome data from the implementation phase was completed and is being written up for publication. The findings from these studies, together with those from the case study publications, will be used to revise the integrated mental healthcare plans in the PRIME countries.
Lessons identified this year, and recommendations for the year ahead linked to this output
- PRIME has identified the challenge of balancing time and resources to both maximise dissemination of outputs versus publication writing. The PRIME leadership team and country teams should each continue to maintain oversight of this delicate balance and implement mitigations (such as a regularly monitoring publication list), alerting DFID of any potential slippages in a timely manner.
- PRIME are in an intense final phase of writing up their findings, including revising the district mental healthcare plan model. It will be important to ensure that this updated version is disseminated and shared effectively, particularly currently using this plan; many of whom will have already embedded the design of the old plan into their health system.
Output Title	A coherent body of high quality, peer-reviewed and policy relevant research that makes a significant contribution to understanding the implementation and scaling up of packages of care for mental disorders
Output number per LF		2	Output Score	A +
Impact weighting (%):		50	Impact weighting % revised since last AR?	N

Indicator(s)		Milestone(s) for this review	Progress
2.1 Research project is implemented in countries (d1)	Contributions to the WHO mhGAP Operations manual, including use PRIME tools, examples, contributions to content and structure of manual. Scale up data collection completed in 3 countries. Data analysis completed for main outcomes of PRIME implementation phase. (Target: 84% of projects in analysis phase or completed)		Moderately exceeded: PRIME findings informed WHO mhGAP Operations manual. Scale up data collection completed in 3 countries and data analysis completed. 92% (95/103) of projects in analysis phase or completed.
2.2 # of high quality policy relevant primary research papers by RPC partners published in peer reviewed publications (A3).# of conference presentations by RPC partners.	75 papers published (80% with a LMIC home institution lead or co-author; 80% with a Female lead or co-author; 70% with a Female LMIC home institution lead or co-author, 70% open access) (A3), 65 conference presentations		Exceeded: 85 papers published (cumulative), 98% with lead/co-author from LMIC home institution, 85% with female lead/co-author (39% lead authors), 71% female or co-lead author with home institution in LMIC; 95% of publications open access. 72 conference presentations conducted (cumulative)
2.3 No of partner institutions who collaborate and publish with each other. (E7)	No target for reporting period		NA

Output moderately exceeded expectations. PRIME has built a strong coherent body of mental health evidence and literature that is relevant to policy and practice. During the reporting period, PRIME expertise, tools and evidence were used to inform the WHO mhGAP Operations manual. Once finalised, the manual will be used in more than 100 countries where mhGAP is being rolled out.

23 research articles were published during the reporting period, bringing the cumulative total to 85. These include a large systematic review on the links between the social determinants of mental health and the Sustainable Development Goals, publications describing the experiences and/or mental health care access in specific populations such as women in the perinatal period, people with severe mental disorders, and epilepsy. PRIME also investigated the distribution of mental illness in the general population in several PRIME districts, and barriers to care and recognition of mental illness by primary healthcare workers. PRIME continue to share lessons learned from the programme.
PRIME has continued to contribute to the increased research leadership from female and LMIC authors. In the reporting period, 98% of papers had an author with an LMIC home institution, 85% had a female author, 39% a female first author, and 71% had a female author with a LMIC home institution. 95% of papers in the last year are in an open access format.

Lessons identified this year, and recommendations for the year ahead linked to this output
- An ongoing challenge is the competing commitments of PRIME partners which may impact on the analysis and timely dissemination of the PRIME research findings. The PRIME publication list with deadlines for each publication is currently reviewed quarterly to check on progress. PRIME should increase this review period to monthly.
- DFID SRO and PRIME to update the target for the end of the programme (85), which has now been achieved. (November 2018)
- Amend the wording in the final milestone target of indicator 2.1 to 5 rather 4 PRIME countries (November 2018)

Output Title	Effective communication of relevant research findings and their uptake by national and international stakeholders to influence policy and practice in the study countries and other low and middle-income countries.
Output number per LF		3	Output Score	A +
Impact weighting (%):		20	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 # of PRIME products disseminated to policy makers and donors across relevant sectors via multiple channels (conferences, high level briefings, workshops etc.) at the following levels: Local, National, International (A4, D2, D3)	At least 95 PRIME products disseminated to policy makers and donors; At least 18,500 page view (disaggregated by UK based, LMIC based or other) since the start of the RPC; reflection (through qualitative narrative) on the top 5 most effective research uptake activities carried out in the reporting period.	Met: 99 PRIME products disseminated. (Since PRIME website migrated in October 2017: 4513 unique page views (50% from LMICs, 21% from UK; 28% from other). PRIME have reported their top 5 research uptake activities (detailed below)
3.2 Participation of mental health service users and community groups in mental health care	MH service users taking an active role in service planning or delivery of mental health care in all PRIME countries.	Met: Service user representatives and caregivers of People living with mental Illness (PLMI) attend CAB meetings; involved in training, supervision and/or anti-stigma work; represented on clinical committees in district steering committees.
3.3 # of PRIME citations in the media	At least 200 media citations of PRIME or PRIME outputs	Met: PRIME cited 206 times in local and international media
3.4 # of citations of PRIME outputs in research articles or other academic publications, curricula or training materials	950 citations of PRIME outputs	Substantially exceeded: 2223 times in google scholar and 1264 in Scopus

Output moderately exceeded expectation. Since the PRIME website was migrated to its new platform (October 2017), there have been 4513 unique page views and 661 downloads. The majority (over 50%) from LMICS, 20-25% from UK. PRIME partners completed the evaluation of research uptake strategy, which provided evidence to demonstrate the significant contribution that the research has had in a range of changing in policies and practises across PRIME countries. It also generated new learning about the effectiveness of their research uptake activities (see section C for more information).

PRIME identified the following 5 engagement activities to be the most effective in the reporting period:
1. The participation in Government of India’s task force on the integration of primary healthcare by the PRIME research director and PRIME India Principal Investigator, which led to the inclusion of the PRIME model in the operational guidelines for the new Health and Wellness Centres in India.
2. The contribution of PRIME to the WHO mhGAP Operations manual, in the form of technical material, tools and case studies.
3. The participation of PRIME Nepal project co-ordinator in development committee of Community Mental Health Care Package, that substantially draws on PRIME’s work.
4. PRIME CEO presentation to over 200 people at WHO mhGAP forum in Geneva, increased awareness of PRIME`s work, and tools and resources available for others to use.
5. The publication of an invited article in African Policy Review, reworked for ‘The Conversation’ website, resulted in international online and print media coverage, including in: Independent Media Group newspapers in South Africa, the Herald in Zimbabwe, The Wire, The Huffington Post and IOL online. This contributed to PRIME`s total coverage of 206 citations in local and international media.

PLMI continue to be involved in the planning and delivery of services in all PRIME countries. In Uganda, Ethiopia and India, service user representatives and caregivers of PLMI attend CAB meetings. In Ethiopia and Nepal, service users have been involved in training, supervision and/or anti-stigma work in the PRIME districts. In South Africa, PLMI are represented on the clinic committees in the PRIME district and by the South African Federation for Mental Health on the PRIME Steering Committee.
Lessons identified this year, and recommendations for the year ahead linked to this output – n/a
Output Title	Capacity exists in study countries to conduct and effectively disseminate research to improve access to mental health care
Output number per LF		4	Output Score	A +
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of externally funded policy-relevant research grants successfully applied for; and level of funding achieved. (E2)	At least 1 externally funded research grants successfully applied for or received from 2017 onwards.	Exceeded: Three grants received (£7,294,000)
4.2 Number of researchers who complete higher training and/or successfully apply for fellowships (E7 & E7.1)	2:5 (M:F) PRIME researchers successfully graduate with PhD*	Met: 2:5 (M:F) PRIME researchers / successfully graduated with PhD; 1 Female Student submitted
4.3 Number of research publications and other research outputs by PRIME partner groups (E7)	Research publications by partner groups increase by 10% since end year 6	Exceeded: 16% increase in research publications from 2016 to 2017

Output exceeded expectations. This output aims to measure the progress towards increasing resources available and mental health research capacity in lower and middle-income countries.
PRIME continues to build institutional and individual capacity for the increased and improved quality of research on mental health in low and middle income countries. During the reporting period 7 (two males and five females) of the 21 PhD students supported through PRIME, completed their PhDs. These students have significantly contributed to PRIME publication outputs, writing 11/23 PRIME publications produced during the reporting year. PRIME also supports junior and mid-level researchers to analyse and write up papers for publication.
At the institutional level, DFID funding has enabled PRIME to secure three grants during the reporting period (£7,92m), contributing to a cumulative total of £33.5m of funding leveraged (28 grants), in line with PRIME objectives, since programme inception. PRIME`s continued success against this indicator reflects their growing reputation and recognition as a well-managed, high performing research consortium, with strong partnerships and leading expertise in conducting mental health research in low and middle income countries.

From 2016 to 2017 the average increase in the cumulative number of publications across partner groups was 16% with a range of 9-18% across countries. The groups which had the most established researchers prior to PRIME’s establishment have tended to be those with the smallest percentage increase because their initial number of publications was much higher. These results show clearly the growth in institutional capacity over time in terms of writing and publishing papers.

Lessons identified this year, and recommendations for the year ahead linked to this output

A key challenge during the reporting year has been for PRIME PhD students (many of whom are also key members of PRIME staff, e.g. PIs and project coordinators) to balance their scientific work with other broader needs of the programme. Now that field work is winding down, this challenge has reduced but with the demands of key dissemination events and activities over the final year, and with potential increase in focus on new grants and projects that are starting, PRIME need to continue to closely monitor and manage workloads, including setting clear deadlines and protecting time for publication writing.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The PRIME theory of change assumed that achieving outputs would enable PRIME`s world class research, on implementation and scaling up of treatment programmes for mental disorders, to be adopted by policy makers & practitioners for the benefit of the poor including mothers. That this would contribute to the impact of widespread implementation of mental health programmes that improve the health and socio-economic status of individuals, particularly women and those living in poverty.
No evidence has emerged to challenge the theory of change causal chain, and assumptions continued to be monitored and updated, at least twice a year. The assumption that ‘countries and their health systems remain stable and enable PRIME to implement and evaluate the programme’ has not held true in all PRIME countries. For example, unrest in Ethiopia created challenges for final stages of data collection, and in India, the challenges of transferring funds to local partner (Public Health Foundation India), delayed the transfer of funds from the University of Cape Town. These challenges have been managed well, causing only minor delays to activities.

There is a high risk that the assumption of ‘political buy-in is obtained despite competing priorities’ does not hold true in Nepal, where the decentralisation of the government system poses risks to sustainability of programme achievements. PRIME continue to prioritise engagement with policy makers and are working to navigate the government changes in order to maintain momentum gained and buy-in from key stakeholders.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The programme is on track to contribute to the expected programme outcomes and impact. All impact and outcome indicators for the reporting period have been met. PRIME tools and evidence have been used by between 4-51 districts in PRIME countries, and in 7 additional countries (exceeding the target of more than 4 districts in each country, and more than 7 programmes in other countries). The target for international policy citations has also been exceeded with 13 documents citing PRIME research.
At outcome level, PRIME has already met its end of programme outcome target of influencing at least one policy, guideline, plan or strategy at subnational or national level. Examples of this influence include in Nepal, where PRIME evidence has been used to revise the Nepal national Community Mental Health Care Package (2018), and in South Africa, where PRIME tools are being used by district mental health teams in 6 of the 9 provinces.

During the reporting period PRIME evaluated its research impact strategy against pre-defined research uptake impact indicators. Impacts identified ranged from the impact on policy and practice at national level, to the influence of PRIME work on international guidelines and strategies. PRIME collected qualitative data that demonstrated that policy makers agreed that PRIME research had contributed to the changes in policy and practise reported.

Explain major changes to the logframe in the past year
As recommended in the last annual review, logframe milestones were added for the current reporting period. Changes at impact, outcome and output level were made to incorporate DFID results framework indicators, and to increase the milestones targets (where they had already been achieved during the 2016/17 period). One impact milestone was amended due to poor availability of data on national health budget allocation to mental health in PRIME countries (indicator 1.1).

Describe any planned changes to the logframe as a result of this review
The following changes to the PRIME Logframe Indicators should be made:
1. Impact Indicator 3 from PRIME evidence cited in ≥12 key documents (policies, guidelines, practise, plans, strategies, roadmaps and/or leadership initiatives, and products included in treatment guidelines) to ≥ 14 as target already exceeded.
2. The wording of output 2.1: milestone target for the end of the programme should be amended to 5 prime countries.
3. Output indicator 2.2: from 85 papers published and 70 conference presentations to 95 papers published and 80 conference presentations, including outcome papers that share national, and cross –country findings.
4. Output 3.2: change target to ‘MH service users taking an active role in service planning or delivery of mental health care in all PRIME countries and PRIME have shared findings with the CAB (India, Uganda and Ethiopia) and other where PLMI are represented.’
5. Output indicator 4.2: from 3:6 (M: F) PRIME researchers successfully graduate with PhD to 3:7 (M:F) PRIME researchers successfully graduate with PhD.

DFID and PRIME should agree increases to end-of programme targets for outcome indicator 1.1, output indicator 3.1 (including an decrease to the target for page views) and output indicator 3.4. Output indicator 1.1 milestone targets should be defined further with the DFID SRO. Targets for this output 1 should also be set so it is possible for PRIME to exceed expectations (score above an A).

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year
PRIME continues to spend efficiently to meet the agreed logframe targets. Personnel costs remain the primary cost-driver taking up around 50% of the annual budget. The funding supports local partner expertise and costs associated with implementation and evaluation of PRIME field work. In the final year field work and training costs are reducing and in the final year will be replaced by an increased cost associated with dissemination events (national/district) and open access fees.

PRIME continues to provide good value for money in relation to the 4 E’s Economy; Efficiency; Effectiveness and Equity:
- Economy: In line with institutional policies, PRIME ensures that the best price for goods purchased for the programme is attained, through obtaining quotes from several suppliers for equipment and travel. Where possible field visits and conference attendance is combined with other activities to minimise costs.
- Efficiency: PRIME met or has exceeded its logframe targets with respect to outputs. E.G. produced 85 peer reviewed articles during the programme to date, more than 4 times the target proposed in the original logframe. Indicator targets have increased throughout the programme to keep them relevant and stretching. PRIME conducted more research studies than initially planned through efficient management of funding, and through obtaining multiplier-funding from elsewhere. PRIME has received over £30m to continue work related to their objectives, this will increase the use of research infrastructure built and the sustainability of achievements to date.
PRIME have worked with the Ministries of Health to ensure that health systems are operating efficiently and using the resources as intended. PRIME SA has actively supported (with training) the upskilling of facility based HIV counsellors who have a limited and under-utilised role within health care, to deliver mental health counselling services to patients suffering with depression. PRIME SA has negotiated with the Department of Health to train people with Bachelors in Psychology (Counselling) in the depression intervention. Currently many university graduates with counselling skills in SA cannot work within the public sector. Utilising these counsellors within the public sector is an important innovation in scarce resource contexts such as public sector health services in SA.
- Effectiveness: PRIME has used research findings to effectively influence policy. They work closely with policy makers to ensure that policy impact is attained in all five focal countries. Close collaboration with WHO and a growing reputation as an effective consortium have allowed PRIME to contribute and influence global policy discussions and documents. During the reporting year PRIME made a significant contribution to the WHO mhGAP Operations Manual which will be used in more than 100 countries in which mhGAP is currently recognised.
- Equity: The starting point of PRIME, the integration of mental healthcare into routine primary care is the provision of accessible, evidence-based care for people with mental health problems within primary care facilities and communities. The development of PRIME interventions was based on thorough formative work which included addressing the potential impact of the intervention on mental health stigma. PRIME has continued to involve service users and care givers in the design and implementation of their work, to ensure they remain responsive to need.
  A key focus for PRIME is to ensure fairness and transparency in the distribution of resources across partners in low and high income countries. All partners hold their own budgets which were allocated based on an assessment of need. PRIME continues to build female and southern research leadership both in terms of recipients of training, graduate studies supported and publication authorship.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
PRIME is a high performing programme, scoring an A or A+ since inception. PRIME has produced a significant amount of evidence relating to mental health. The consortium has worked closely with local Ministries of Health and been effective in influencing policy, particularly through having mental health care plans adopted at district level. The continued support to these stakeholders throughout the last year of the programme will be crucial for maximising the sustainability of achievements made to date. In the final phase of the programme there is a high emphasis on dissemination of results to ensure that evidence generated is used to improve the situation of people living with mental illness. PRIME has put together a challenging calendar of events for the final year that will increase the reach of PRIME evidence to key stakeholders.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation
The programme risk rating remains minor. PRIME risk management includes monthly calls with representatives from partner organisations. The partners review monthly activity logs and challenges and risks to the project are highlighted and acted upon where necessary. A formal review of the risk register is conducted bi-annually with partners updating and sending new risks as relevant. PRIME also discuss key risks, and any changes to risk ratings with DFID on a quarterly basis.

There have been a number of staff changes during the reporting period, including the change of research director from Prof. Mark Tomlinson to Dr. Charlotte Hanlon. This change was perceived as low risk as Dr. Hanlon has been involved in PRIME from the outset and attending PRIME management meetings. The transition appears to have been managed very well without delays or detriment to the programme.

The environment in which PRIME is implemented has continued to present some challenges to delivery, these include:
- two significant states of emergency in Ethiopia, combined with other periods of unrest, caused delays to data collection.
- several months of strikes in the PRIME India scale-up sites effected data collection and evaluation
- Elections in Nepal and a shift to a new federal system has required flexibility and amendments to PRIME`s approach. PRIME has conducted a series of meetings with Municipal officials who have now committed to ensuring regular supply of psychotropic medicines and continuation of community level health activities including community psychosocial workers.
- Political upheaval in South Africa North West province where PRIME implementation and scale-up sites are situated. This has led to public service strikes and the closure of health facilities. Although implementation and scale up have been completed, PRIME will need to continue to closely monitor and identify mitigation strategies to minimise the impact of this on programme sustainability when the clinics re-open.
- In Uganda there has been some difficulty gaining buy-in at district level in one of the scale up districts. PRIME has deployed the mental health co-ordinator to assist with this process.
- Due to competing priorities from partners (such as effective engagement and presenting of PRIME`s work at key dissemination events) there is a risk that the publication of the main outcomes papers are delayed. To mitigate this, PRIME has placed clear deadlines for completing these activities and is providing mentorship to ensure that resulting papers are of high quality.
- Findings from the implementation phase have been mixed and reflect challenging contexts within which the work has taken place, and the difficulties in evaluating such complex programmes. PRIME are committed to ensuring that the results are presented in a nuanced way using both quantitative and qualitative data to ensure key lessons from the implementation phase are communicated effectively.
- as the programme moves towards completion there are additional challenges in holding the core team together. It is important that PRIME continue to find ways to mitigate this and ensure key lessons, publications and activities are concluded satisfactorily.
F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues
PRIME continue to provide accurate and timely financial reports, invoices, and narrative summaries within 6 to 8 weeks after the end of the quarter. Part of the quarterly progress meetings are used to discuss financial issues including difficulties that may impact on ability to meet forecasting targets. Regular communication ensures that DFID is aware of the current position and can address any issues quickly and before they become more serious.

PRIME is on track to hit the programme’s overall financial forecast and has to date spent approximately £6.9m out of a budget of £7.95m. PRIME provides regular forecasting information and this has enabled figures to be adapted when underspends/overspends are identified. In 2017/18 PRIME spent approximately 94% of the annual budget available. There were 3 main reasons for underspend:

- the cancellation of the Public Health Foundation of India (PHFI) Foreign Contributions Regulation Act certification, Sangath (another Indian NGO) took over as the main PRIME India partner. PHFI incurred costs during the transition period which could not be reimbursed. Although PHFI has now attained provisional re-certification, it was not possible to reimburse these costs during 17/18 and this will now become an additional 18/19 liability.
- Delays in scheduling an African dissemination event with WHO Afro office.
- Un-used budget for open access fees. Papers earmarked for publication not yet accepted.

Although the University of Cape Town annual audited statement does not provide details of the DFID award separately, the Auditors provide a letter of comfort to confirm that funds have been appropriately managed. The most recent audited statement for the period to 31 December 2017 has no qualifying remarks.

Asset registers are collected annually by the PRIME Secretariat from country partners. Although no spot-checks have been conducted recently, UCT conducted a financial management audit in years 2 and 3, which involved spot-checks on partners where the audit highlighted issues in financial management practices. As the programme is now in the closing stages of the programme it is recommended that random spot-checks are introduced where feasible to ensure assets are properly accounted for.

DFID often requires ad-hoc information quickly to allow response to senior management or ministerial enquiries. All requests to PRIME are always responded to within acceptable timescales which is highly appreciated by the DFID programme team and the source of the enquiry.

Date of last narrative financial report(s)	22 August 2018
Date of last audited annual statement (s)	31 December 2017

G: MONITORING, EVIDENCE & LEARNING

Monitoring
This review was carried out by members of the Health Team in DFID’s Research. During the reporting period the DFID Senior Responsible Owner (SRO) and programme manager: attended the biannual Consortium Advisory Groups; had face to face meetings with members of the PRIME consortium on 3 occasions in London, and had frequent telephone and email engagement with the Senior Management Team. There were quarterly catch-up calls throughout the year, on progress, challenges and highlights, risks and any financial management. The SRO also undertook a monitoring visit to a PRIME South Africa scale up site, and met with the PRIME SA team, and saw a continuous quality improvement intervention. The SRO also met with the PRIME Uganda team in Kampala to learn more about their work and progress made in the last year. In addition to the information collected during these visits and meetings, the team used supporting materials such as the PRIME annual report, the PRIME website, data from the online platform ResearchFish, and key articles PRIME outputs to complete this review.

Evidence
There have been no significant changes in the evidence base during the reporting period. PRIME continue to generate high quality research that builds upon the limited evidence available on mental healthcare integration in low and middle income countries.

PRIME`s own analysis has highlighted the importance of demand for services at grassroots level, and strengthening health systems in order to integrate mental health services adequately. PRIME included demand side activities in the Nepal mental healthcare plan; a community key informant detection tool, and in the Ethiopia mental health care plan, where they trained community informants for case finding of severe mental illness. In all countries, PRIME`s work has included health systems interventions; this has ranged from improving the psychotropic medication supply chain, to strengthening health management information systems.

The separation of maternal health systems from standard primary care systems in PRIME countries, led to maternal care being excluded from MHCPs. The extension phase of PRIME included research that will contribute to learning on how to integrate maternal mental healthcare services.

During the reporting period PRIME evaluated their research uptake strategy. This generated evidence to support the contribution of PRIME outputs to intended outcomes, and that engagement and research uptake activities had been successful, and facilitated the use of PRIME research by policy makers and practitioners working in LMICs.

Learning
95% of PRIME`s research articles were published in open article journals, allowing for lessons and learning to be shared internationally. PRIME also developed a new publication and data policy to allow researchers to access and analyse the wealth of data collected over the last 7 years. Key learning for PRIME has been from the results of the evaluation of the implementation phase, which highlighted the importance of health system strengthening and demand generation at the grass roots level, in increasing the access and provision of treatment. PRIME are still analysing and distilling key learning and messages (national and international) that will be shared and disseminated during the final year of the programme.

Key learning objectives for PRIME during the final year of the programme include: identifying the barriers to success of implementing and scaling up integrated district metal healthcare plans, and strategies that can be used to overcome them.

Progress on recommendations from previous reviews
PRIME have responded to all recommendations made in the previous annual review. This includes amending their logframe, revising their research uptake strategy and informing DFID of any potential setbacks created by changes in the context, outside of the programmes control. PRIME also put in place strategies to support staff in writing publications on time, for example they have developed a publication list with clear deadlines and have more than monthly meetings at country-level to review progress.