## 1.1 Logframe
Tab 1.1 Logframe
Provision of emergency food, voucher and nutrition assistance in Yemen through the World Food Programme (WFP), 300434
Milestone | Duration (From - To) | Months | Report Submission
Q1 | July - September 2018 | 3 | Report submitted by 31 October 2018
Q2 | October - December 2018 | 6 | Report submitted by 31 Jan 2019 (with financial report)
Q3 | January - March 2019 | 9 | Report submitted by 30 April 2019
Q4 | April - June 2019 | 12 | Report submitted by 31 July 2019 (with financial report)
Q5 | July - September 2019 | 15 | Report submitted by 31 October 2019
PROGRAMME TITLE | Provision of emergency food, voucher and nutrition assistance in Yemen through the World Food Programme (WFP), 300434
IMPACT | Impact Indicator 1 |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
|  | Planned | 60 | 60 | 60 | 0 | 0 | 0
Critical humanitarian need is alleviated amongst the targeted population, ensuring more people are food secure and a reduction in acute malnutrition. | Number of districts out of the 120 convergence districts assessed as in Phase 4. | Actual |  | 0 | TBC. |  |  | 0
Source
Famine Monitoring System (FMS) reports; Integrated Food Security Phase Classification (IPC); Fewsnet
| Impact Indicator 2 |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
| Number of districts with a GAM rate over 20% amongst the 120 convergence districts | Planned | 58 | 58 | 58 |  |  | 174
|  | Actual |  | 0 | TBD |  |  | 0
Source
Polio Screening Campaign; Smart Survey; Nutrition Cluster Reports
OUTCOME | Outcome Indicator 1 | [7 empty] | Assumption
|  |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
Critical humanitarian need is alleviated amongst conflict-affected people, ensuring more people are food secure and a reduction in acute malnutrition | Average Food Consumption Score by beneficiary household. (in 'Acceptable" category). | Planned | Stablized or higher than baseline GF =47% CV=56% | [5 empty] | Required funding is made available
|  | Actual | [6 empty] | Humanitarian access remains unconstrained
|  | Source | [6 empty] | Targetting of beneficarise not obstructed
| Outcome Indicator 2 | EMOP, WFP Post-Distribution Monitoring Surveys, WFP quarterly reports | [6 empty] | Commerical and humantiarian imports into Yemen are unconstrained
| Average Consumption-based Coping Strategy (index). |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
|  | Planned | Stable or lower than baseline CF=22.5 CV=23.5 | Stable or lower than baseline CF=22.5 CV=23.5 | Stable or lower than baseline CF=22.5 CV=23.5 | Stable or lower than baseline CF=22.5 CV=23.5 | Stable or lower than baseline CF=22.5 CV=23.5 | Stable or lower than baseline CF=22.5 CV=23.5
Actual
g
| Outcome Indicator 3 | EMOP, WFP Post-Distribution Monitoring Surveys
| Average Dietary Diversity Score by beneficiary household (Average number of different food types consumed/week) |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
|  | Planned | > 3.0 | > 3.0 | > 3.0 | > 3.0 | > 3.0 | > 3.0
|  | Actual | GF=4.8 CV=5.0 | GF=4.8 CV=4.9 | Sep (Aug Ben) GF=4.9 CV=5.2 |  |  | 0 | RISK RATING (Minor, Moderate, Major, Severe)
| Outcome Indicator 4 | EMOP, WFP Post-Distribution Monitoring Surveys,
| Average GAM rate |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
|  | Planned | < 10.0% | < 10.0% | < 10.0% |  |  | 0
|  | Actual | [5 empty] | 0
Source
DFID (£) |  | WFP Post-Distribution Monitoring Surveys, WFP quarterly reports, Smart Surveys, Polio Campaign
DFID (£) | 0
OUTPUT 1 | Output Indicator 1.1 | [7 empty] | Assumption
|  |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
Number of beneficaries reached with in-kind food (cumulative). Disaggregated by sex, age (and disability, when available) Ration size (e.g. P1 and P2) must be indicated in results.
In-kind food assistance and commodity vouchers delivered to vulnerable Yemenis on a monthly basis, using the targeted criteria and prioritisation approach outlined in WFP's Emergency Operations in Yemen. Not DFID specific funding or results. |  | Planned | [6 empty] | Required funding is made available
|  | Actual | [5 empty] | 0 | Humanitarian access remains unconstrained
Source
|  | WFP Post-Distribution Monitoring Surveys, WFP-DFID fortnightly calls, WFP exteranl monthly and quarterly reports | [6 empty] | Targetting of beneficaries is not obstructed
| Output Indicator 1.2 | [7 empty] | Commerical and humantiarian imports into Yemen are unconstrained
| Number of beneficaries reached with full food rations provided to through commodity vouchers (cumulative). Disaggregated by sex, age (and disability when available) Ration size (e.g. P1 and P2) must be indicated in planned and actual results. |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
Planned
Actual
Source
WFP Post-Distribution Monitoring Surveys, WFP-DFID fortnightly calls, WFP exteranl monthly and quarterly reports
Output Indicator 1.3
| Number of beneficaries reached with full food rations provided to through cash transfers (cumulative). Disaggregated by sex, age (and disability when available) Ration size (e.g. P1 and P2) must be indicated in results. |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
Planned
Actual
Source
WFP Post-Distribution Monitoring Surveys, WFP-DFID fortnightly calls, WFP exteranl monthly and quarterly reports
Output Indicator 1.4
| Amount in metric tonnes (MT) of food delivered to final distribution points. |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
Planned
Actual
Source
WFP Post-Distribution Monitoring Surveys, WFP-DFID fortnightly calls, WFP external monthly and quarterly reports
Output Indicator 1.5
| Percent of beneficiaries in post-distribution monitoring: 1) reported no safety issues going to/at distribution 2) Satisfied with quality and type of food assistance they received for in-kind and vouchers). Disaggregated by gender. |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
IMPACT WEIGHTING (%) |  | Planned |  | Safe experience GF= >90% CV=90% Quality/type (Ave) Stable or above baseline GF= 90% CV= 91% | Safe experience GF= <90% CV=90% Quality/type (Ave) Stable or above baseline GF= 90% CV= 91% | Safe experience GF= <90% CV=90% Quality/type (Ave) Stable or above baseline GF= 90% CV= 91% | Safe experience GF= <90% CV=90% Quality/type (Ave) Stable or above baseline GF= 90% CV= 91% | Safe experience GF= <90% CV=90% Quality/type (Ave) Stable or above baseline GF= 90% CV= 91%
70% |  | Actual
|  | Source | [6 empty] | RISK RATING (Minor, Moderate, Major, Severe)
DFID (£) | Output Indicator 1.5 | WFP Post-Distribution Monitoring Surveys | [6 empty] | Severe
£17 million | Cost per beneficiary (for in-kind and voucher) |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) |  | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
|  | Planned |  | $11.37 (in-kind);$14.21 (CV-TN)
|  | Actual | [5 empty] | 0
Source
WFP Post-Distribution Monitoring Surveys, EMOP
0
OUTPUT 2 | Output Indicator 2.1 | [7 empty] | Assumption
| Number of child beneficiaries (6-23 months) reached with nutritional assistance |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
Provision of supplemented food to prevent acute malnutrition among children and pregnant and lactating women Not DFID specific funding or results. |  | Planned | 197078 | 197078 | 197078 | 197078 |  |  | Required funding is made available
|  | Actual | [5 empty] | 0 | Humanitarian access remains unconstrained
|  | Source | [6 empty] | Targetting of beneficarise not obstructed
| Output Indicator 2.2 | EMOP, WFP Post-Distribution Monitoring Surveys, WFP quarterly reports | [6 empty] | Commerical and humantiarian imports into Yemen are unconstrained
| Number of PLWs reached with nutritional assistance |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
|  | Planned | 57500 | 57500 | 57500 | 57500 | 57500
|  | Actual | 0 | 0 | 0 | 0 |  | 0
Source
Output Indicator 2.3
| Cost per beneficiary for the BSFP for U2s and PLWs |  | Baseline (April-June 2018) | Milestone Q1 (July - Sept 2018) | Milestone Q2 (Oct - Dec 2018) | Milestone Q3 (Jan-Mar 2019) | Milestone Q4 (Apr -Jun 2019) | Milestone Q5 (July - Sept 2019)
|  | Planned |  | $ 5.10 (U2); $6.22 (PLW) | $ 5.10 (U2); $6.22 (PLW) | $ 5.10 (U2); $6.22 (PLW)
|  | Actual | [5 empty] | 0
IMPACT WEIGHTING (%) |  | Source
30%
DFID (£) | 0 | WFP Post-Distribution Monitoring Surveys, Quarterly reports

## WFP Risk Matrix
Risk Category | Risk Description | Gross Risk | Mitigation | Net Risk after mitigation | Updates Q1
External Context | Humanitarian Access: The ability of WFP to access affected populations remained one of the most fundamental risks to programme delivery. This risk is broad and includes the risk that insecurity or the actions of parties to the conflict will impede humanitarian access into the country (by sea or air) and within the country, preventing WFP from reaching targeted beneficiaries. In areas where there is no active fighting, obstruction by local authorities (including denial of visas, refusal to allow WFP to carry out food security assessments and levying taxes on humanitarian vehicles) has also prevented WFP reaching beneficiaries. For post distribution monitoring, WFP stated that around 15-18 districts were too volatile to enable access for verification. | Severe | Mitigations include: WFP negotiating access with local authorities, recognising that decisions agreed in Sana’a are not necessarily implemented; and coordination with Office for the Coordination of Humanitarian Affairs and other partners on access negotiations. De-conflict field missions, convoys and fixed assets with the EHOC (Saudi-led Coalition) notification system. WFP hold regular meetings with district authorities, local council members and religious leaders to improve access and acceptance at the local level. WFP work through local staff whenever possible, employing female workers as appropriate. Engage in community mobilisation and local participation in planning and implementation of activities to increase local acceptance. DFID works to support the humanitarian response by engaging with parties to the conflict directly or indirectly to ease access restrictions. | Major
External Context | Conflict restricts beneficiaries to programme locations. WFP have a different prioritisation approach in North and South Yemen. Difficulty implementing it in the North means some intended beneficaries in the North are still not receving their intended rations. | Major | Ensure WFP have strong contingency plans, including the ability to bring the delivery of assistance closer to beneficiaries, and the investment in local capacity building – to do localised delivery where needed. Ensure that strong gender and conflict sensitive approaches are implemented, to increase equal accessibility for men, boys, women and girls, whilst ensuring the ‘do least harm’ principle is upheld. WFP have robust beneficiary complaint feedback mechanisms including regular focus groups and call centres. WFP respond to all complaints to strengthen accessibility for beneficiaries. | Major
Delivery | Supply Chain: Given that Yemen relies mainly on sea deliveries as the first entry point of humanitarian cargo both in the North and South, any prolonged block on imports has the potential to have a cataclysmic impact. Indeed, the severe import restrictions imposed by the Coalition at the end of 2017 resulted in no commercial food or fuel entering Northern Yemeni ports for over 6 weeks. | Severe | WFP have worked over the reporting period to put in place a contingency plan to address the potential closure of Red Sea Ports. They have tested out different entry points, and alternative regional corridors for food procurement and dispatch. WFP have also worked to augment their warehouse capacity and prepositioning of food stocks. Continued advocacy vis-à-vis restrictions on assessments and internal movements over the next year, with key consideration given to the evolving conflict dynamics | Major
Delivery/ Operational | Capacity of Cooperating Partners (CPs) and Targeting: WFP implements its programme through over 26 Cooperating Partners, who are responsible for ensuring that the assistance reaches those beneficiaries who fit WFP’s targeting criteria. Despite WFP having worked to train both the CPs and authorities on the targeting criteria, ensuring the assistance reaches the intended beneficiaries remains a significant risk. | Severe | WFP have committed to increase field presence to support the CPs and also to engage in further training of the CPs and authorities on the targeting criteria. CPs have explicitly requested that WFP cascades dialogue on targeting with national level down to local authority level. WFP has also recently introduced an enhanced due diligence of all CPs. All CPs are now required to submit monthly narrative reports to allow WFP to pick up any discrepancies. WFP engages in regular informal conflict analyses, together with Cluster partners to monitor changing dynamics with a view to seeing how it can affect delivery – though there is scope to work more with CPs on this. DFID should also work with WFP to ensure it is considering the impact that its activities (including those interrupted by authorities) could have on conflict dynamics, and whether its programme needs to be adjusted. Finally, implementation of biometrics in the second half of 2018 should ensure that only those on the beneficiary list will be targeted – though there is a significant risk that this will be delayed in northern governorates. | Severe
Fidiucary/reputational | Collateral damage and diversion of supplies during storage or transportation, | Severe | Where possible WFP supplies are held in variety of locations to minimise risk. Keep up to date with security updates and sit reps to make early decisions on relocating people and assets. Have appropriate precautions and controls such as security guards, bars, CCTV, stock logs etc are in place WFP always investigate opportunities for asset recovery of losses and assess any lessons learnt on controls. WFP project locations and transport plans submitted to deconfliction cell in Riyadh and the Ministry of Interior in Sana’a. WFP required to report any cases or suspicions of aid diversion of DFID funds. WFP have put in place effective beneficiary complaint feedback mechanisms. WFP have confirmed their compliance with UK counter-terrorism legislation. | Major
Fidiucary/reputational | Corruption, Fraud and Aid Diversion: The availability of resources and food commodities in an insecure context increases the potential for fraud and corruption by WFP staff members, vendors and CPs. There is also a risk that incidences of aid diversion are undetected as WFP have a limited field presence. Diversion is also a conflict sensitive risk as it benefits particular conflict actors. This has had a notable impact on programming this year with key private suppliers with close links to parties to the conflict attempting to coerce WFP to award them contracts. | Severe | To mitigate such risks, WFP has in place multiple monitoring mechanisms (e.g. a call centre to report incidences of aid diversion and post distribution monitors to highlight diversions of resources). WFP is piloting a Commodity Tracking Database to follow-up on the movement of commodities from the moment of dispatch to the moment of distribution. The introduction of biometric registration in the end of 2018 will also reduce the risk of diversion. In addition, DFID should consider bringing together an analysis of the key suppliers used by WFP in Yemen, assessing their political affiliations and the key risks – and sharing with WFP as appropriate. There is an ongoing risk that CPs are not confident in reporting corruption, fraud and aid diversion to WFP, in part because of fears about their personal security. DFID work closely with WFP to instil confidence in WFP and CPs’ approach to mitigating aid diversion and encouraging reporting of incidences. | Major
Fidiucary/reputational | Cash going to terrorist organisations | Severe | Delivery chain mapping undertaken identifying all stakeholders before reaching the beneficiary. DFID Yemen approach followed on working alongside (de facto) government institutions. WFP conduct robust risk assessment on their partners and suppliers and transactions are made through legitimate financial institutions/intermediaries. Annual audited statements provide assurance funds are all accounted for. | Major
Programme | Lack of coordination with other agencies/actors. There is a strong risk that lack of cooperation within the UN structure risks duplication or inefficient of aid. | Major | DFID to enourage WFP to work with various working groups include CMWG, FSAC to ensure coordination and no duplcation | Moderate