Annual Review

Project Title: HIV Prevention Programme - DFID Uganda

Date started:	15 October 2012

Date review undertaken: 15 - 23 October 2012

## Introduction and Context

What support is the UK providing?
DFID is providing £16.3m over four years (2011 - 2014) through a variety of channels to improve the effectiveness of Uganda’s HIV/AIDS prevention response. Planned funding channels are the Joint UN Programme of Support on AIDS in Uganda - JUPSA (£3.5m), the Civil Society Fund (£11m) and the Knowledge Management Communication Centre (KMCC - £0.8m). The World Bank is planning an evaluation of the programme (£0.5m). / The programme is delivered through: JUPSA to deliver combination prevention services in 6 focus districts (Rakai, Gulu. Arua, Kasese, Mayuge and Kabale); Support to the Civil Society Fund to address behavioural and structural drivers of the epidemic; and support to the Knowledge Management Communication Centre for improved policy and practice.

What are the expected results?
The expected impact of the programme is “a reduction in the number of new HIV infections occurring annually in Uganda from 120,000 in 2009 to 72,000 by 2014.” / The programme purpose is “improved effectiveness of the prevention response.” / DFID attributable planned outputs by 2014 are: / Completion, implementation and monitoring of a national HIV prevention strategy and action plan / The National HIV Prevention Strategy (NPS) and Action Plan effectively implemented and updated in light of evidence emerging from M&E / HIV intervention packages implemented & delivering results / Effective routine monitoring and impact evaluation of NPS carried out / Improved delivery of HIV prevention services / 80% of babies born to positive mothers receiving anti-retrovirals to protect them from Mother to Child Transmission of HIV (MTCT) / 215,000 males circumcised in 6 pilot districts bringing the total to 50% of males circumcised in those districts / 680,000 – 80% of adults in 6 pilot districts with access to integrated sexual and reproductive health (SRH) and HIV prevention services / More effective prevention response through community mobilisation and engagement in addressing structural drivers of the epidemic / 1,000,000 people reached through new social change communications programmes focusing on HIV prevention / 50% more women and men reporting safer sex practices in pilot districts / Reduced stigma – measured by 50% women and 50% men with accepting attitudes towards people living with HIV/AIDS (PLHA) in the pilot districts / Improved policy and practice through effective dissemination and uptake of HIV-related research, evidence and lessons learned from experience / National policy reflects research and analysis disseminated by KMCC

What is the context in which UK support is provided?
The Programme was designed in 2010 against the following evidence at that time: / Uganda was one of the first countries in the world to report a contracting HIV epidemic, with an impressive decline in the HIV infection rate from 18% in 1992 to 6.1% in 2002. This early success was characterised by strong political leadership and social mobilisation across all levels in Ugandan society. / These achievements were difficult to sustain. HIV prevalence levels started to increase whilst annual new infections were rising to outstrip the number of people annually enrolled in Anti-Retroviral Treatment (ART) programs. In 2009, an estimated 1.2 million people were infected with HIV[1], more than during the peak of the early epidemic in 1994 (1.1 million). AIDS remained the leading cause of Disability Adjusted Life Years (DALYs) lost in Uganda and without appropriate attention to prevention; progress toward Millennium Development Goal 6[2] would be reversed. / Prevention of new infections was the only sustainable option for mitigating the socio-economic impact of HIV. For cost reasons alone, Uganda could treat itself out of the epidemic. The response needed to be geared towards the prevailing characteristics of heterogeneous epidemic in Uganda and the factors that drove them, including social and structural factors (mobility, levels of violence, stigma, urbanisation, culture, income distribution, gender inequality) acting in different combinations across different regions to drive and influence the character of risk and vulnerability. There were wide geographic and social differences, with northern Uganda having an HIV prevalence of 8.2% versus the national average of 6.4% and women more likely to be infected (7.5%) than men (5%). / In Uganda HIV is primarily spread heterosexually. Having multiple, concurrent sexual partners was and continues to be the key driver of the HIV epidemic in Uganda. Yet, little was known about the extent, motivating factors, underlying socio-cultural and behavioural determinants and the impact of multiple and concurrent partnerships (MCP). / Mother to child transmission (MTCT) of HIV was the second most important means of HIV transmission in Uganda, accounting for 15-25% of new infections. However MTCT prevention remained low and by June 2009 only half of HIV infected pregnant women received ART to reduce the risk. The World Health Organisation recommended Safe Male Circumcision (SMC) as a cost effective intervention for HIV prevention but there had been limited uptake in Uganda. There was little information as to what had worked and what hadn’t in terms of social change communication for HIV prevention and safer sex. / Although Uganda is one of the most heavily researched countries on HIV/AIDS, findings had been poorly disseminated, monitoring and evaluation was weak and lessons learned were poorly reflected in policy and programmes. There was limited understanding of structural factors that drive vulnerability to HIV/AIDS or how best to address them. This prompted the need to develop more robust monitoring and impact evaluation, and support lesson learning and evidence-based policy-making and programming on HIV/AIDS in Uganda. / At the time of this annual review, most of the above conditions still existed. In addition, Uganda’s recent AIDS Indicator survey revealed a worrying phenomenon - that Uganda was one of just three countries (the others are Angola and Mozambique) where HIV prevalence is increasing[3]. And Uganda is the only heavily resourced US President's Emergency Plan for AIDS Relief (PEPFAR) country where this is happening. After Uganda set for the world the best example on how to reduce HIV in the late 1990s (Uganda hosted the first studies on maternal to child transmission and sero-discordant couples and was the first country in Africa to put significant numbers of people on ART), the country is making a reversal. / Prevalence has started rising again and is currently at 7.3%. Current political messaging does not seem to match the new prevalence as well as the advent of new HIV prevention interventions. For example, the President has blamed the increasing HIV/AIDS prevalence on the NGOs that are promoting condom use and circumcision.[4]. Similar uncertainty reigns across national communications on HIV/AIDS and the public receive mixed messages from the health services and the NGOs across the board. Arguably this has led to a slower uptake of AIDS prevention services such as safe male circumcision and condom use. / The mandate of the Uganda AIDS Commission (UAC) is to coordinate the AIDS response across ministries including the Ministry of Health, the Ministry of Finance, Planning and Economic Development, and the Ministry of Local Government among others. The Ministry of Health (MOH) is responsible for the biomedical response to the AIDS epidemic, playing a large role in coordinating the majority of resources for the AIDS response. / Despite considerable development partner support (by DFID, DANIDA, Irish Aid, SIDA, and the US Government), there has been relative under-resourcing to prevention interventions, with a heavy concentration on treatment and care.
[1] UNAIDS Global Report 2010
[2] MDG 6 aims to halt and reverse the spread of HIV.
[3] WHO (2011) Global HIV/AIDS Response, Epidemic Update and Health Sector Progress towards Universal Access
[4] The Daily Monitor, 2 October 2012.

## Section A: Detailed Output Scoring

Output 1: Completion, implementation and monitoring of a national HIV prevention strategy and action plan
Output score: C: Output substantially did not meet expectation / Progress against expected results

Indicator Baseline Milestone 2012 Achievement of 2012 milestones / 1.1 National HIV Prevention Strategy & Action Plan addressing socio-cultural and structural drivers of the epidemic NPS under development Institutional developments recommended by NPS being implemented Functional institutional arrangements in place, but not fully attributable to this Programme / 1.2 Effective intervention packages identified through the NPS NPS under development No 2012 milestone The planned 2011 milestone was “Effective intervention packages designed, costed and guidelines produced.” This milestone was not achieved and was carried forward to 2012, and was still not achieved. / 1.3 NPS monitoring and impact evaluation including evaluation of complex combination prevention No M&E framework for the new NPS No 2012 milestone No planned milestones for 2012 - However, the Milestone for 2011 (Tender awarded for NPS monitoring and impact evaluation to the World Bank was not undertaken) / The other milestone for 2011 was a programmatic baseline to be carried out by UNFPA. The baseline was not conducted in 2011 and was still underway at the time of the annual review. / Indicator 1.1: National HIV Prevention Strategy & Action Plan addressing socio-cultural and structural drivers of the epidemic: The Programme supported the development of a national HIV prevention strategy and an action plan to operationalise it. It was also planned that through the Programme, existing and new institutional arrangements would be supported to implement the action plan. At the time of annual review, the UAC and MoH each had functional departments to implement the NPS. The existence of functional structures to implement the NPS cannot however be entirely attributed to DFID’s support. / Indicator 1.2: Effective intervention packages identified through the NPS: The NPS which was finalised and launched in 2011 recommended broad intervention packages. It was however planned that intervention packages for specific population groups (e.g. commercial sex workers, fishing communities, etc) would be identified and costed and guidelines for delivering these interventions would be produced. This 2011 milestone was not achieved and was carried forward to 2012, and was still not achieved. / Indicator 1.3: NPS monitoring and impact evaluation - including evaluation of complex combination prevention: To operationalise the monitoring and evaluation of the NPS, baseline studies and subsequent evaluations were planned. The baseline studies were scheduled to be conducted in 2011, but were carried over 2012 had still not yet been concluded at the time of the annual review. A programmatic baseline was supposed to be conducted by UNFP, while a separate bio-behavioural baseline was to be conducted by the World Bank as part of the impact evaluation of combination HIV prevention. Both baselines were delayed by a myriad of factors – including the lack of technical agreement on the scope/content of the baselines, as well as lack of agreement between UAC and MoH regarding the technical oversight of the programme and the programmatic baseline. At the time of the annual review, UAC had relinquished responsibility for coordinating the implementation of this programme to MoH – which went ahead to set up a technical review panel to provide technical oversight for the programmatic baseline. / Recommendations: / The governance component of this programme needs to be considerably strengthened as many of the programme’s problems reside here. Clear demarcation of responsibilities between UAC, MoH and other institutions in this partnership needs to be agreed. / There is need to set critical milestones for results expected from MoH during a programme “redesign phase” (recommended - Dec 2012-Mar 2013) in order to mitigate any further delays in implementation. If these milestones are not met, it could be an indication that the programme will continue to face delays and may not achieve its targets – in which case it may be necessary to halt the programme altogether. / Impact Weighting (%):15% / Revised since last Annual Review? No / Risk: High / The review recommends moving the risk from Medium to High

Output 2: Improved delivery of HIV prevention services
Output score: C: Output substantially did not meet expectation / Progress against expected results / This output was planned to be delivered through JUPSA in six focus districts – Rakai, Mayuge, Arua, Kabale, Kasese and Gulu. Progress against the expected milestones is elaborated below: / Indicator Baseline Milestone 2012 Achievement of 2012 milestones / 2.1 Number of babies born to positive mothers receiving anti-retrovirals to protect them from MTCT 28,040 – 30% at national level (July 2009) No 2012 milestone - However, progress was required towards meeting the overall target of 4,500 receiving anti-retrovirals to protect them from MTCT by 2014. No services provided pertinent to this project in the six districts. / 2.2 Number of men safely circumcised and counselled 25% males circumcised (national level) No 2012 milestone - However, progress was required towards meeting the overall target of 215,000 men circumcised by 2014. 1485 men circumcised (616 attributable to DFID support through JUPSA and 869 through the Civil Society Fund) / This pace however does not demonstrate that the target of 215,000 men circumcised by 2014 will be achieved / 2.3 Number of women and men with access to integrated SRH and HIV prevention services To be established by baseline study for pilot districts No 2012 milestone No services provided pertinent to this project in the six districts. / Indicator 2.1: Number of babies born to positive mothers receiving anti-retrovirals to protect them from MTCT: This result was expected to b delivered through the catalytic role of the JUPSA working with the public sector to scale up service delivery in the focus districts. The JUPSA 2012 midyear report indicates that upstream policy and advocacy work has been undertaken to promote uptake of PMTCT. Notably, leadership has been mobilized for an effective and efficient prevention response for the sector, with specific advocacy efforts targeting MoH, Ministry of Gender, Labour and Social Development (MoGLSD), Uganda People’s Defence Forces (UPDF), cultural and religious leadership for eMTCT and SMC. In addition, district advocacy meetings have been conducted for Rakai, Arua, and Mayuge, with councillors, heads of departments, sub-county chairpersons, and selected opinion leaders to secure political commitments on PMTCT. / Despite the processes which have been undertaken and may indeed be useful to set the ground for delivery of PMTCT, there is no record of number of babies receiving ARVs attributable to this programme. / Indicator 2.2: Number of men safely circumcised and counselled: The JUPSA 2012 midyear report indicates that training of SMC trainers of trainers (ToT)/surgical teams has been initiated. Through Alliance of Mayors and Municipal Leaders Initiative for Community Action on AIDS at the Local Level (AMMICAL), JUPSA mobilised and provided circumcision to 616 men. The Civil Society Fund through various grantees also mobilised and provided circumcision to 869 men. Although some men have benefited from this service, to-date less than 1% of the programme target has been achieved and it is unlikely that the full target of 215,000 circumcisions will be met by 2014. / Indicator 2.3: Number of women and men with access to integrated SRH and HIV prevention services: There is no evidence of numbers of people reached with these services. However, policy and advocacy work was done by JUPSA – notably, a National RH/HIV Integration strategy was approved by Health Policy and Advisory Committee (HPAC)/MoH in April 2012; Consultations around the eMTCT Plan, Condom Strategy and Sex Work Action Plan are on-going; and National standards and tools to support delivery of integrated SRH/HIV prevention services were finalised. / JUPSA (Phase II) was an existing initiative of the UN and DFID proposed to fund a specific component of the work under HIV Prevention with UNAIDS providing the coordination function. The project design erroneously assumed that UN assistance to the public sector, particularly to the local authorities, would result in strengthened service delivery. Ultimately, these combination prevention services would be delivered with a mixture of public and private sector services, with the majority being delivered by the public sector. / Overall, DFID programme milestones have not been achieved mainly because there was a mismatch between the results reported by JUPSA and the results DFID expected from funding to JUPSA. This could be due to the focus of the JUPSA more on policy, advocacy and institutional development – and less on service delivery. In addition, the JUPSA 2012 midyear report blamed delays in government (MoH/UAC) consensus on the DFID funding programme for hindering their progress.
Recommendations: / Consider ceasing cooperation with JUPSA as a group and determining the UN partners with whom DFID needs to continue to work. This could include UNFPA (to complete the district baseline and to partner on HIV prevention). / If a decision is taken to continue service delivery in the 6 focus districts, DFID needs to work with MoH to convene a Technical Working Group for the six districts to determine HIV biomedical prevention needs and gaps in the six districts, and accelerate service delivery. / Since biomedical service delivery targets are not likely to be achieved through JUPSA, consider delivering these services using a third party contractor on an output-based basis (to deliver a specified number of services). Also consider how a third party contract can build public sector capacity (in consultation with the MOH). / Impact Weighting (%):30% / The review found no reason to change the impact weighting. / Revised since last Annual Review? No / Risk: The review recommends changing the risk rating from medium to high.

Output 3: More effective prevention response through community mobilisation and engagement in addressing structural drivers of the epidemic
Output score: C: Output substantially did not meet expectation / Progress against expected results / Results for this output were expected from activities implemented by projects under the Civil Society Fund (CSF). DFID had allocated funds in late 2011 through the CSF to 23 successful grantees. However, lack of consensus between the UAC and MoH led to delays in disbursement of the grants to the 23 grantees. Instead of releasing the funds in January 2012, the funds were only released in October 2012. The lack of agreement by MoH was mainly because they did not approve of the heavier investment of DFID funds in behavioural and structural interventions (over 65%) and less on biomedical interventions. Discussions between UAC and MoH over the management of the CSF also took up a lot of project time and delayed the release of project funds to the grantees for implementation. / Progress against the expected milestones is presented below: / Indicator Baseline Milestone 2012 Achievement of 2012 milestones / 3.1 No. of people reached through new social change communications programmes focusing on HIV prevention 0 No milestone for 2012, but working towards reaching 1,000,000 by 2014 392,447 reached with behaviour change communication (BCC) messages attributable to DFID through the Civil Society Fund to National NGOs / 3.2 Number of women and of men reporting safer sex practices in pilot districts To be established through baseline No milestone for 2012, No activities took place pertinent to this project in the six districts / 3.3 Stigma, measured by proportion of people with accepting attitudes towards PLHA in pilot districts 19% women and 28% men express acceptance on all four measures in Uganda HIV/AIDS at national level (2005) 25% Women / 35% Men No stigma reduction activities took place. / Summary of activities
Indicator 3.1: No. of people reached through new social change communications programmes focusing on HIV prevention: About 39% of the overall programme target of 1,000,000 people were reached with HIV prevention communications. These results were achieved through a spill over of programme funds from the previous year which DFID had put into the CSF to support the work of National HIV NGOs (NNGOs). / Indicator 3.2: Number of women and of men reporting safer sex practices in pilot districts: Since the 23 successful grantees who were supposed to implement the behavioural and structural interventions in the 6 districts (Gulu, Arua, Rakai, Mayuge, Kabale and Kasese) only received funds a few weeks to the annual review, no interventions and results had been achieved yet, / Indicator 3.3: Stigma, measured by proportion of people with accepting attitudes towards PLHA in pilot districts: This did not happen, for the same reasons explained in indicator 3.2. / Overall, the Civil Society Fund was not responsible for the delay in fund disbursement as projects had been chosen and notified early in 2012. The CSF had only disbursed funds for the 23 chosen projects two weeks before the Annual Review. This means that no projects had begun to produce results. The reason for poor performance on this output was not technical but political. / This notwithstanding the other potential challenges of this output are: / Will all behavioural and structural HIV prevention challenges in the districts be covered by these projects? In interviews with CSF staff, the World Bank, and civil society organisations, it is clear that the CSF systematically tried to reach all key target high-risk audiences and to choose a good cross section of behavioural and structural interventions. The problem, however, is that the interventions may not be implemented at a scale high enough to generate the required impact in a combination prevention approach. / Institutional and Management arrangements for the CSF: The CSF is a shared mechanism which nearly all Aids Development Partners (ADPs) are using to fund the civil society HIV response. That the CSF is going through some changes is nothing to do with this particular DFID programme but will have some implications for it. The CSF has been administered by the USG, ensuring that the administration was strong but also very expensive. At the time of the Annual Review, USAID had decided to cease this support so all the ADPs have been working hard to come up with a new CSF plan. The new plan involved setting up the fund under the auspices of the UAC. A working board made up of UAC, ADPs, and civil society is being determined now along with business plans on how best to fund and what proportion of fund costs will be taken up in its administration. (These plans were work in progress at the time of this report.) Meanwhile, DFID has contracted Deloitte to bridge the financial management gap in the time between USAID’s exit and when the new fund mechanisms emerge. DFID has undertaken to contract Deloitte until 30 March 2013. / Recommendations: / The Review recommends discussion of the merit of technically continuing to support the 23 CSOs – based on whether their interventions will be transformative in the six districts. If the decision is made to continue funding the CSOs, the review recommends an extension of the programme by one year to allow these projects (planned for three years) to be completed. / Impact Weighting (%):30% / The review found no reason to change the impact weighting. / Revised since last Annual Review? No / Risk: Not specified in logframe, the Review would suggest High

Output 4: Improved policy and practice through effective dissemination and uptake of HIV-related research, evidence and lessons learned from experience.
Output score: A: Output met expectation / Progress against expected results / Indicator Baseline Milestone 2012 Achievement of 2012 milestones / 4.1: Effectively functioning KMCC No centre No milestones stated for 2012 KMCC was set up and is effectively functioning and implementing its work plan / 4.2: No of dissemination events and quality reports from HIV related bio-medical and social science research & analysis produced by KMCC 0 No milestones stated for 2012 Draft PMTCT synthesis report in place / 1 PMTCT dissemination event / On-going behavioural change synthesis / 4.3 HIV policy and programmes informed by quality operational and academic research including social science. No baseline No milestones stated for 2012 Draft PMTCT synthesis report in place to inform eMTCT policy dialogue / Summary of activities
Indicator 4.1: Effectively functioning KMCC: KMCC completed its set up phase, recruited all necessary staff and had started to deliver against its planned results by the time of the annual review. The KMCC completed the following: / Knowledge collation & synthesis: Designed EMTCT project including building team and quality assurance group and begun data collection. / Communication & influence: Work with media and government is on-going. / Capacity building: Designed KMCC training modules but awaiting the National HIV/Aids Documentation and Information Centre (NADIC) capacity assessment. / Indicator 4.2: No of dissemination events and quality reports from HIV related bio-medical and social science research & analysis produced by KMCC: At the time of the annual review, KMCC had completed the PMTCT synthesis and was undertaking discussions with MoH for uptake and wider dissemination of the PMTCT communications briefs. Work had also begun on behavioural change communications (BCC) synthesis. / 4.3: HIV policy and programmes informed by quality operational and academic research including social science: Both the PMTCT and BCC synthesis work was done drawing from expertise from Uganda Virus Research Institute, Medical Research Council, Aids Alliance and other experts both in Uganda and the UK.. / The KMCC has faced some challenges in working with UAC. The UAC notes that NADIC should be carrying out all the functions planned for KMCC. While the UAC recognises that NADIC currently has weak capacity, the UAC has committed to strengthening NADIC. In working within the government system and being responsive to government needs, the KMCC plans to a) change KMCC’s role from a Knowledge Management and Communication Centre to Knowledge Management, Communication and Capacity Initiative; b) have the KMCC Initiative act as a model for managing information and communication and build the capacity of NADIC to perform these functions themselves; and c) see KMCC as a temporary organisation that will cease to exist when sufficient NADIC capacity exists in Uganda (although no length of time is set for how long this will take). / The UAC is currently assessing NADIC’s capacity and this will reveal NADIC’s gaps and set suggestions for next steps. The KMCC Initiative will work with UAC and NADIC as the results of this assessment are completed in early 2013 / Recommendations: / A National Communication Framework is needed. It would be pertinent for KMCC to work with UAC/NADIC and other stakeholders to develop one – which will inform KMCC and NADIC contributions. / DFID should consider support to UAC once the results of the NADIC capacity needs assessment are clear. / Impact Weighting (%):25% / The review found no reason to change the impact weighting. / Revised since last Annual Review? No / Risk: Medium

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: C / Outputs substantially did not meet expectation / Direct feedback from beneficiaries / No beneficiary feedback was sought since most of the planned activities were not implemented.
Summary of overall progress / Nearly all the delays and problems with this programme have been political, rather than technical. The project has been stalled for nearly two years because of lack of consensus between UAC and MOH. The decision to put all funding through the UN or the Civil Society Fund meant poor MOH ownership. In addition, the UN did not broker a good relationship with MoH for this programme to achieve its service delivery targets. The assumption that the joint UN activities in support of MOH would add up to accelerate service delivery was also a limitation. / While the CSF delivered on their promise to fund civil society’s community response by supporting and choosing 23 projects in the six districts, the CSF also ran into delays due to political disagreement between MoH and UAC which went on for over one year. / The KMCC was also stymied politically but has recovered with a good strategy for moving forward and supporting Uganda in its knowledge management and communications needs by building capacity in the UAC’s NADIC. / Finally, the impact evaluation planned by World Bank could not proceed without effective service delivery and results anticipated by the programme. / The programme needs to start afresh but only if there is full GOU backing, a four-month period for operation planning for Phase 2 (Dec 2012-Mar 2013) and a proposed project extension of one year.
Key challenges / Government ownership was not guaranteed with the original programme design: While the Government was consulted during the programme design phase, the design did not elaborate the roles of UAC vis-a-vis MOH. / The programme design meant working with JUPSA to accelerate delivery of key biomedical interventions. As the UN organisations are not implementing organisations, this proved to be a flaw. What each UN organisation contributed was difficult to ascertain from the progress reports. / Some Civil Society Fund administrative challenges persist: The CSF is moving from a fund administered by a USAID-funded cooperating agency (Chemonics) and a fund management agency (Deloitte) to a stand-alone fund under the Uganda AIDS Commission. The transition is planned to take place over the next year (with DFID-funded bridging arrangements temporarily in place for the financial management agent). A new governance structure is being worked out over the next several months in consultation with the UAC, DPs, and civil society. However, realisation of a new functional structure in 2013 is not yet fully guaranteed. / An Impact Evaluation was not possible amid delayed programme implementation: An impact evaluation in the absence of programme results was not possible. It will be important for the team to determine if an impact evaluation is still feasible. Whether or not the impact evaluation takes place, the programme needs to reorient the focus of the evaluation and offer the chance to implement combination prevention in six ‘learning’ districts in the interest of learning lessons on the way to a full Uganda scale up in all districts. This work will compliment the development of implementation guidelines and M&E guidelines for combination prevention.
Annual Outcome Assessment / The overall programme purpose is “improved effectiveness of the prevention response,” measured by the indicators below: / Indicator Baseline Target (2014) / Proportion of adults aged 15 - 49 reporting more than one on-going sexual partnership 3.8% F; 29.3% M (2006) 2% F; 15% M / Number of new child infections due to MTCT 24 600 (2009) 7000 / % of adults aged 15 - 49 reporting the use of a condom the last time they had sex with a casual partner 9.1% F; 16.1% M (2006) Increased to 60% F; 80% M / Since the DFID HIV prevention programme has hardly yielded results at output level, any national-level changes cannot be attributed to DFID’s support. / The above notwithstanding, Uganda looks likely to meet the targets for Indicator 1 (Proportion of adults aged 15-29 reporting more than one on-going sexual partnership in the past year) as the Aids Indicator Survey (2011) shows that the proportion is decreasing for both males (2006: 29.3%; 2011: 17.8%; 2014 target; 15%) and females (2006: 3.8%; 2011: 2.9%; 2014 target: 2%) engaging in multiple concurrent partnerships. / However, the targets to reduce the number of babies born positive (MTCT) have only come down very slightly. With 23,478 babies born positive in 2012 (down only slightly from 24,600 in 2009), the target of reducing this number to 7000 by 2014 is very unlikely to be met. / Finally, the third indicator measures the percentage of adults aged 15 to 49 reporting the use of a condom the last time they had sex with a casual partner. This number is increasing for females (15.7% from 9.1 in 2006) but decreasing for males (13.3% from 16.1% in 2006) and the 2014 target of 60% for women and 80% for men looks currently unattainable.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / Table 1 below shows the forecast budget that was presented in the programme memorandum (PM). By April 2012 it was forecast that £12.1m would be spent. Table 2 shows the committed and actual spend so far. By the end of 2012, £6.7m will have been spent. Thus spending is off track relative to the original budget and Table 3 indicates the revised budget. According to this, by the end of 2012, £8.4m should have been spent. So, relative to the revised budget there is still an under spend. / Table 1: Forecast spend for each output from PM / Output Budget in £ M / 2010/11 2011/12 2012/13 2013/14 Total / 1. Finalisation and implementation of National Prevention Strategy and M&E framework 0.3 0.1 0.1 0.5 / 2. Improved delivery of HIV prevention services 1.5 1 1 3.5 / 3. Community mobilisation and engagement 3 7 1 11 / 4. Knowledge management and communications 0.3 0.25 0.25 0.8 / Impact evaluation 0.5 / Total 3 9.1 2.35 1.35 16.3 / Table 2: Disbursements up to October 2012 (in £) / 2010 2011 2012 Total / Finalisation and implementation of National Prevention Strategy and M&E framework 0 187,543 110,075 297,618 / Improved delivery of HIV prevention services 1,000,000 0 6,574 1,006,574 / Community mobilisation and engagement 3,000,000 3,000,000 176,999 6,176,999 / Knowledge management and communications 0 0 278,061 278,061 / Impact evaluation 0 417,300 0 417,300 / DFID consultancy costs 2,834 796 3,219 6,849 / Total 4,002,834 3,605,639 574,928 8,183,401 / Table 3: Budget summary / Original budget Disbursed to date (October 2012) Balance available up to 2014 / 16,300,IV prevention indicators below:o minimise the risk of mis-use of funds. dation responsibilities. ursement of the funds planned000 8,183,401 8,116,599 / The under spend in 2012 has occurred due to political barriers, inefficiencies and delays. There have been budget adjustments to try and mitigate this under spend including contracting a Senior Implementation Adviser at Ministry of Health and the bridge funding contract for the financial management services of the Civil Society Fund following the end of the USAID funding for the same services in June 2012. / The reason why the spend in previous years has deviated so much from the original budget as at Project Memorandum is because these were estimations as actual budgets had not been received from all partners and when these were eventually approved and MOUs finalised, there were some variations that were accommodated within the project budget. / 2.2 Key cost drivers / HIV prevention service delivery (through JUPSA) and CSF are the key cost drivers. The spend by both components has however been low. Despite the disbursement of funds to JUPSA in 2011, the funds had not been fully utilised and precluded the disbursement of funds planned for 2012. CSF on the other hand received a disbursement for 2012, but had only spent funds equivalent to one quarter by the time of the annual review. In terms of administrative costs, UNDP which is the administrative agent for JUPSA charges an administrative fee of 7%; while the CSF management contract cost is £850,000 for nine months (up to March 2013). / Is the project on track against original timescale: No / There have been significant delays on all the programme outcomes – mainly attributed to political challenges.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There have been no significant changes in the HIV prevention evidence base with implications for the project except the worrying trend of increasing HIV prevalence in Uganda. Until the Theory of Change has been developed, it is not yet clear how to re-design and measure the success of this programme. It will be important to assess each output and how it will contribute to HIV impact. / 3.2 Where an evaluation is planned what progress has been made? / The original project envisaged an impact evaluation in the six districts and the World Bank was contracted to carry this out. However, the evaluation has met the following challenges: / As implementation of the programme has been held up, the plans for the evaluation have moved forward without the benefit of any programme progress to evaluate, causing frustration for all concerned; / The emphasis on an Impact Evaluation has meant the GOU and the ADPs have perceived this programme as research more than as demonstration work in six districts on how the National Prevention Strategy might be implemented; and / The time left in this programme is now too short to demonstrate impact in terms of HIV incidence. / In addition, there have been problems with completing the baseline survey (by UNFPA) - now due to start in November 2012 and be completed at the end of January 2013. This gives some time to reconsider the evaluation plan. / Recommendation / Consider deeming the Rakai district a ‘Super learning district’ as it has the highest biomedical coverage and is one of the most studied/intervened upon districts in Uganda.

4. Risk
4.1 Output Risk Rating: High / The review recommends changing the risk from medium to high because within the remaining time, it is unlikely that the programme will meet its targets by 2014. / 4.2 Assessment of the risk level / This programme was always assessed as medium risk and, given the political obstacles the programme has encountered; the review would move the risks to be higher. While the political obstacles have now been overcome to a great extent and it looks likely that the MOH will deliver on its commitment, this is not guaranteed. / Of the risks listed in the 2010 Project Memorandum, two risks have been realised resulting in the present stalled programme circumstance. A major risk (lack of agreement by MOH delaying the programme) was not anticipated. / Project Memorandum Risks Probability Impact What happened / The UAC fails to achieve consensus and stakeholder buy-in or fails to win political support for the NPS Low High The NPS generally had stakeholder buy-in; however, there was no agreement between MoH and UAC on responsibility for its coordination. / GOU will fail to deliver responsive prevention services leaving communities frustrated and disempowered Medium High The GOU’s fragmented prevention response has not been delivered to an adequate scale. / AIDS DPs fail to maintain current CSF management arrangements Medium High The ADPs have not yet been able to establish a sustainable CSF management structure / UN agencies do not provide high level strategic support Medium Medium The UN agencies overall failed to coordinate and provide the required strategic support to the prevention programme (with the exception of some agencies) / Contextual changes such as increased mobility due to regional economic integration or to instability in neighbouring countries may facilitate the spread of HIV, working against achievement of programme interventions Low Medium No major contextual changes occurred.
Risk of funds not being used as intended / Measures have been put in place to minimise the risk of miss-use of funds. Funds to JUPSA are managed and accounted using UN financial management regulations, and DFID receives annual financial reports. For the CSF, DFID receives monthly expense reports upon which payment of management fees is based, and quarterly technical reports that tally expenditure against activities. Delta partnership/KMCC is also paid monthly based on specific deliverables. / 4.4 Climate and Environment Risk / There are few potential climate and environmental direct risks from this project. Indirect risks would include the complex multi-factoral pathways which would include food insecurity, natural resource use, agriculture, land tenure and gender issues. When the main wage earner is infected, the loss of agricultural labour can lead to more environmentally damaging farming techniques. Women are disproportionately affected by HIV/AIDS as the natural resources that they traditionally manage such as firewood and medicinal plants face increased demand. Other links include women’s rights to land which may be compromised or lost as the result of the death of a male relative. These risks have not changed from the Project Memorandum.

5. Value for Money
5.1 Performance on VfM measures / The ‘3E’ framework is used to understand performance of the programme within a VFM framework. / Economy: For outputs 1 to 3, there have been virtually no activities, and limited disbursements, hence there is no basis to make any comments on cost economy. For output 4, the following measures have taken place by the implementing agent to achieve economy: / Sharing costs of office rent, office equipment and services with Delta Partnership(Uganda) Ltd; / Using seconded staff as part of the capacity building programme to provide excellent value for money technical inputs; / Making use of the established network of AIDS Alliance key correspondents to document stories from the field, rather than hiring independent journalists; and / Using internal facilities to host training events, instead of using external venue hire. / Efficiency: Due to the political barriers and delays, this programme on the whole has suffered from inefficiency, in terms of converting inputs into outputs. For Output 1, however, the National Prevention Strategy was prepared within time. For Output 2, there has been no efficiency because there has been no service delivery. For Output 3, efficiency has also not been achieved because MOH and UAC failed agree on expedited fund disbursement for the chosen CSF projects. For Output 4, there has been some efficiency due to planning, setting out of a methodology, work plan and a robust business process that responds to requirements and context (including identified risks. / Effectiveness: For outputs 1-3 effectiveness has been non-existent, as no or few activities have been turned into outputs. / 5.2 Commercial Improvement and Value for Money / The KMCC was competitively tendered, while the civil society proposals were assessed on the basis of a challenge fund (therefore competitive). In addition, the evaluation component was competitively tendered. While these components being competitively tendered would imply value for money, the political hold-ups in all aspects of this programme have hampered any programme efficiency. / 5.3 Role of project partners / The UN: Was to accelerate service delivery and improve coordination of HIV combination prevention in the pilot districts. (Output 2) / The World Bank was supposed to undertake costing of the NPS as well as develop operational guidelines – in addition to conducting an impact evaluation of combination prevention. The World Bank made progress in ensuring a country understanding of combination prevention. However, the World Bank’s momentum to conduct an impact evaluation has been greatly undermined by the lack of programme results. / The Civil Society Fund through a competitive process identified 23 CSOs to deliver behavioural and structural interventions in the 6 pilot districts. / The KMCC was to deliver on knowledge and communications for policy influencing on HIV prevention / 5.4 Does the project still represent Value for Money : No / The project performs badly on economy, efficiency and effectiveness, thus shows no representation of good VFM. / 5.5 If not, what action will you take? / DFID will review options and risks for the future of this programme and discuss with project partners the way forward. The following recommendations pertain: / Interrogate further the pros and cons of terminating or redesigning the programme / If the decision is made to redesign the programme; / Revisit and revise the logframe and ensure that the indicators are at the correct levels / Clarify management arrangements; / Address VFM issues; / Ensure the evaluation design is appropriate to a DFID country programme and can be completed in the timeframe; / Programme Timing: The review recommends that this programme has a four-month period for operational planning where the following takes place: / The baseline survey is completed in the six districts; / The feasibility of the impact evaluation in the reduced timeframe is ascertained. Or, consider having the World Bank focus on supporting the programme with a good Process Evaluation; / Decisions are made on the UN role and the UN is alerted of the final decisions; and / Extend programme for an additional year (to 2015) so that combination prevention in the six districts has the full implementation period of three years.

6. Conditionality
Not applicable

7. Conclusions and actions
The programme has aimed all along to support development and implementation of the NPS particularly the combination HIV prevention (CHP) approach. Actual gains from the programme have been: / Increased understanding of combination prevention and what this means as a concept including within UAC and MoH; and / Completion and dissemination of the NPS. / To be gained by continuing could be: / Actually putting the combination prevention strategy into practice in six districts; / Leading on development of comprehensive prevention interventions; / Learning lessons from application in the 6 focus districts; and / A coordinated GOU response. / The following issues however undermined programme success and will need to be addressed if the programme is to continue: / Government (UAC and MoH) never fully agreed and owned this programme and this delayed progress; / The UAC and MOH did not work together in a coordinated way; / The UN could not be held accountable for service delivery; / A planned impact evaluation in the absence of programme results is not feasible / The programme has taken up a lot of DFID staff time than it should have taken. The management arrangements of the revised programme must take this into account and be simplified so that DFID has to relate to fewer entities. The MoH has already hired a Senior Technical Assistant to coordinate work on operationalizing the NPS in the 6 districts and this position is paid for by DFID. It is imperative for DFID to devote continued staff time at all levels to see this programme carefully embedded within the MOH. / This programme has suffered from being perceived by other stakeholders as research at a time when prevention scale up was more of a GOU priority. This reputation needs to be shed with a new emphasis on what can be learned from the scale up of combination prevention in six districts and what programmatic and monitoring lessons can be replicated. / Going forward therefore, DFID needs to: / Interrogate the pros and cons of continuing with the programme or terminating it / Determine the merit of redesigning the programme to retain strategic components if the decision is made to continue with the programme

8. Review Process
The annual review was informed by the findings of a review undertaken by an independent evaluation team which included Carol Bradford (Team Leader and an expert in sexual and reproductive health and HIV prevention), Max Anyuru (Political economy and institutional specialist) and Valsa Shah (economist). Two members of the team spent eight days in Kampala interviewing a range of stakeholders including the Ministry of Health, the Uganda AIDS Commission, Development Partners (Irish Aid, DANIDA and USG), UNAIDS and UNFPA, the World Bank, the Civil Society Fund, a variety of civil society partners, the Knowledge Management Communication and Capacity, the Infectious Diseases Institute, and a public health expert who helped in the original project design.

## ACRONYMS

## ADPs Aids Development Partners
## ACP Aids Control Programme
## CSF Civil Society Fund
## DANIDA Danish AID Agency
eMTCT	Elimination of mother to child transmission
GOU	Government of Uganda
JAR	Joint AIDS Review
## JUPSA Joint UN Programme of Support on AIDS in Uganda
## KMCC Knowledge Management and Community & Capacity Initiative
MARPS	Most at risk populations
MDG	Millennium Development Goals
MOH	Ministry of Health
MOU	Memorandum of Understanding
NADIC	National AIDS Documentation and Information Centre
NGO	Non-governmental organisation
NPS	National Prevention Strategy
PEPFAR	President's Emergency Plan for AIDS Relief (USG)
PMTCT	Prevention of mother to child transmission
RFA	Request for Applications
## SIDA Swedish Aid Agency
SMC	Safe male circumcision
SRH	Sexual and Reproductive Health
TASO	The AIDS Support Organisation
TOC	Theory of Change
## UAC Uganda AIDS Commission
## USG United States Government