Type of Review: Project Completion Review

Project Title: DFID Support to the National AIDS Council - HIV Common Fund 2009 -2013

ARIES Code: 200605

Date started:	August 2009	Date review undertaken: July 2013
## Introduction and Contex

What support did the UK provide?
DFID contributed £ 1.44m in financial aid from 2009-2012 for the Mozambique National AIDS Council (CNCS acronym in Portuguese) to coordinate the national response to HIV & AIDS in Mozambique. In March 2012, decision was made to have a no cost extension for another year, in order to monitor the results of the last disbursement that had just been made. DFID funds to the Common Fund were distributed as follows: / CY 2009 2010 2011 2012 Total / Amount in £ 0,36m 0,36m 0,36m 0,36m 1,44m / This funding was provided through a common fund with four other donors, namely, Germany, Canada, Denmark and Irish Aid.

What were the expected results?
The results expected from this support on its approval in 2009 were as follows; / The expected impact of the programme was “to improve the quality of life of people infected and affected by HIV and AIDS and reduce the incidence of HIV in Mozambique”. / The expected outcome of the programme was “to support the effective implementation of the Government of Mozambique’s (GoM) HIV and AIDS multisectoral plan (PEN III)”. / The following outputs were set out: / New multisectoral strategic plan in 2009 (PEN III), informed by good quality policy work and evidence based priority [as evidenced by an inclusive process for elaborating the strategic plan and the implementation of different components of the strategic plan by different sectors]. / Strengthened coordination of the multi-sectoral response with the public sector, private sector and civil society [through the strengthening of coordination and accountability structures between CNCS and other stakeholders and the phasing out of HIV grant management function by CNCS] / Improved results based monitoring and accountability of CNCS [ agreement on how HIV is reported across government and the implementation of one overarching monitoring and evaluation (M&E) framework for HIV] / Better planning, allocation and tracking of HIV resources in order to achieve improved outcomes [by having a prioritised costed annual plan and an annual review process that is aligned with the GoM cycle].

What was the context in which UK support was provided?
HIV&AIDS continues to be one of the greatest threats to Mozambique’s development. It is estimated that 1.4 million people in Mozambique have HIV & AIDS.[1] According to a national survey (INSIDA) the HIV prevalence levelled off at 11.5% in (2009). However these national statistics mask large regional variations – from 25% in Gaza Province to 4% in Niassa Province. Furthermore, urban areas had a higher prevalence (15%) than rural areas (9%). Prevention efforts in HIV in Mozambique lag behind many other countries in the region because they were slow to start and Government commitment to prevention has not been inconsistent over the years. However, as table below shows, there has been significant progress in HIV prevention awareness and treatment between 2003 and 2009. / Table 1: Comparison about HIV knowledge and treatment between 2003 & 2011 / Indicator 2003 (Demographic Health Survey) 2011 DHS / % of women aged 15-49 who have knowledge of two HIV/AIDS prevention methods 45.2 51.7 / % of women aged 15-49 who received information about HIV in pre-natal visits 3 49 / Number of health units offering treatment for HIV 24[2] 316 / Coverage of treatment for adults needing it (%) 3 48 / Knowledge about two methods of HIV prevention increased by 6.5% between 2003 and 2011. There has also been more integration of HIV services into other programmes such maternal health as evidenced by the proportion of women who get information about HIV in ante-natal visits. Access to treatment has also improved with coverage increasing significantly from 3% to 48%. However, the 316 health units that offer treatment for HIV are equivalent to 22% of all health facilities in Mozambique (1414), which is still a small proportion. Their uneven distribution implies that poor and remote areas have less access to treatment. / Background on the support to CNCS / CNCS was established in 2000 with the mandate to supervise, evaluate and provide orientation in relation to the multi-sectoral AIDS response. In 2006-2009, another function was added, that of manager and grantor of HIV funds to implementing agencies. The majority of resources to the institution were external, coming from multilaterals particularly the World Bank’s Multi-Country HIV& AIDS Programme for Africa (MAP) and the Global Fund to fight AIDS, TB and Malaria (GFATM). MAP funding alone was $55 million between 2006- 2008. HIV & AIDS in Mozambique was therefore divided into the biomedical approach (treatment and prevention of HIV transmission from mother to child) which was addressed by the Ministry of Health and the social side consisting of prevention, awareness raising and behaviour change under CNCS. These were supposed to be complimentary requiring coordination between the two government agencies. / However, there were a few challenges. One of these was that CNCS was not adequately equipped with the financial systems and management capacity to perform its on-granting mandate. As a result CNCS focused more on resource mobilization and fund management than performing their coordination role. Another challenge was that due to the institution’s dependence on external funds, it was not fully integrated into the Government. For example, salaries were much higher relative to those of other Government institutions. A third challenge is that the division of labour between CNCS and the Ministry of Health was never clearly defined making coordination between the institutions ad-hoc rather than systematic. / Due to CNCS weak internal capacity to manage funds, and the low absorptive capacity civil society who could not meet the pre-requisites for disbursements the expenditure of MAP funds in 2008 declined. Consequently, the MAP project was rated as “unsatisfactory” by the World Bank. In response to this poor performance Partners and Government decided that CNCS should focus on its core mandate of coordinating the HIV response and withdraw from the function of providing grants to civil society, the private and public sectors. This new mandate comprised of a three pronged approach of (i) coordinating the national response, (ii) monitoring and evaluation of the national response, and (iii) communication. In light of this change, both international partners and the Government of Mozambique (GoM) significantly reduced their funding to CNCS. In addition, CNCS went through a process of restructuring to become more effective and more closely aligned to the government structure and payroll. In order to support these changes, Government agreed to provide CNCS with a mandate to hold all stakeholders implementing HIV prevention activities accountable. This never happened and consequently CNCS’ role as coordinator of the national response was undermined. / The Common Fund (Canadian CIDA, Germany, Danida, Ireland and DFID) ended in 2012 as initially planned when set up in 2007. Partners are keeping to this decision given the shift in international policy to address HIV through the health sector and promote a continuum of care from prevention to treatment. Government have decided that CNCS will continue to coordinate the national response. To ensure a responsible exit from the Common Fund, partners followed a dual strategy: to encourage GoM to fund most of CNCS core functions; and to encourage the US Government and UN agencies, as key players in HIV, to take more of a leading role in policy dialogue. Both have been successful. Government increased their funding to CNCS in 2013 by 223 % , that is from 76,521,927.31 Mts in 2012 to 170,714,540 Mts in 2013. This has allowed the institution to continue functioning as well as to re-start their on-granting function. / The United States Government through the Presidential Emergency Programme for AIDS Relief (PEPFAR) is a key supporter of the national response, mainly through the Ministry of Health and civil society organizations. The total amount of funding the United States provides to the national response is over 200 million USD annually, mostly off-budget. Another key player is UNAIDS who do not have much funding, but are respected for their leadership in this area. They also led the sector in 2009 and 2010 on behalf of partners. / Reflecting CNCS’ mandate to coordinate the national response, this PCR reports not only on how well the institution performs this function, but also the role and contribution of other stakeholders (public sector, private sector and civil society) to the national HIV response with oversight from CNCS.
[1] Source: WHO Summary Country Profile for HIV/AIDS Treatment Scale Up. Mozambique, 2005
[2] Source: Report on the Millennium Development Goals , Republic Mozambique 2010

## Section A: Detailed Output Scoring

Output 1: New multisectoral strategic plan 2010-2014 (National HIV Plan), informed by good quality policy work and evidence based priority setting
Output 1 score and performance description: B – [Output moderately did not meet expectation]
Indicator 1: Inclusive participatory process used for elaborating the national HIV plan. MET / The national HIV plan was elaborated through an inclusive process. However, it is not being implemented in all provinces and prevention activities are not yet at scale. / The new National HIV Plan (PEN III) was developed through a well managed inclusive and participatory process which took place during the second half of 2009. DFID was a member of the steering committee overseeing the development of the Strategic Plan and also made significant inputs through the work of technical assistance to offer coordination support for all stakeholders. The process of developing the new plan was well managed, and incorporated inputs from all stakeholders, including civil society organizations, the private and public sector as well as donors. This was accompanied by a consultation process in all provinces. The new strategy was completed and presented to the CNCS Board and key national level stakeholders at the end of December 2009. It was officially approved in March 2010 by the Government of Mozambique. / As a result of the consultation the national HIV plan was technically strong and included evidence of lessons studies of the previous years including the 2007 sentinel surveillance data, the 2008 modes of transmission study and the National AIDS Spending Assessments. UNAIDS in Geneva reviewed the new HIV plan positively. / Indicator 2: National Prevention Policy/Priorities approved and implemented: NOT MET / The new plan approved in March 2010, took over 18 months to operationalize. Line Ministries at subnational levels (provincial) incorporated activities from the plan using different approaches. Some developed stand-alone HIV operational plans while others incorporated their HIV activities into their annual plans as part of the planning and budgeting cycles. By 2012, all three provinces visited as part of the Annual Joint Review reported that the number of private and public sectors institutions integrating policies from the HIV strategic plan into their annual operational plans was growing rapidly. For example, the central province of Manica had HIV prevention activities integrated into the annual plans of the Agriculture, commerce, tourism and defence sectors for the first time. In Maputo province the provincial AIDS Nuclei collaborates with at least seven sectors including Education, Customs and Youth and Sports. / However, the extent to which these HIV prevention activities were implemented by the sectors once approved in the annual plan continues to be an issue. In part, this is because there is currently very little funding targeted specifically at HIV prevention and awareness raising activities in Mozambique. Each sector had to allocate its own funding to implement these activities. Furthermore, each institution or line Ministry tended to select activities they could easily implement given their particular remit, rather than those defined as being effective in the national HIV plan. To address this, in 2012 CNCS appointed HIV focal points assist the different sectors in each district to integrate HIV prevention activities in their annual plans and implement these. Nevertheless, budget shortages restrained the ability of these focal points to participate fully in the different sector planning and reporting meetings. / Impact Weighting (%): 25 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Strengthened coordination of the multi-sectoral response with the public sector, private sector and civil society and donors
Output 2 score and performance description: [C- Output substantially did not meet expectations.] / CNCS have not been able to coordinate the multi-sectoral response effectively because their mandate was never formalised and also because they are not accountable to the GoM for their performance. In addition, the initial cessation of the on-granting function as agreed with partners and GoM in 2009, was re-instated it in 2012.
Progress against expected results: / Indicator 1: Coordination and Accountability structures between CNCS and other stakeholders strengthened: NOT MET / At central level there is a lack of clarity about how to operationalize CNCS coordination role. Monthly Partners Forums are designed to bring together all national stakeholders in the response: CNCS, multilateral and bilateral partners, private sector and Civil society organizations, as well as key line ministries to make decisions about the national response. It is also in this forum that stakeholders and CNCS can hold each other to account for their contribution towards the national response. The Partners Forum has not succeeded in fulfilling its objectives. The main reason for this is that from the CNCS side there has been little engagement. Meetings are often cancelled at the last minute and very few decisions are made by the CNCS Secretariat. As a result, the Partners Forum has become more for information sharing rather than a decision making and accountability forum. / Furthermore, since 2009 the Management Board which is chaired by the Prime Minister as CNCS President and the Minister of Health as vice- President has not met. In the Common Fund structure the Management Board is where partners could discuss the performance of the sector and raise concerns about the lack of leadership from CNCS. It is also where Government could hold partners accountable to their commitments and actions. This has meant the CNCS has not been able to respond to changing contextual needs. A review of the coordination structure in 2011 only looked at partners and did not address the lack of accountability of the CNCS Secretariat to the Board nor the weak leadership by CNCS. For example, in November 2011, Common Fund partners wrote a letter to the Prime Minister raising concerns about the sustainability of funding to the national HIV response with the phasing out of the Common Fund in 2012. The letter also expressed willingness by partners to dialogue with the Prime Minister about the national response. In response, the Prime Minister acknowledged partner concerns but gave no indication of how these would be addressed or willingness to dialogue with partners about the sustainability of the institution. An outcome of this lack of leadership and accountability has been the development and implementation of HIV activities without always involving CNCS. / There is also a wider framework of coordination involving other areas in the response which are not necessarily covered by CNCS as a coordinating body (Health Partner Group, the Global Fund to combat AIDS, TB and Malaria’s Country Coordination Mechanism, and the Civil Society Platform) which can be considered as entry points for improved collaboration between sectors. Participation to the Partners Forum by different stakeholders has decreased significantly since 2007. / Despite the challenges at central level, there were improvements at provincial level. These include regular meetings and joint planning with line Ministries. Visits to three provinces as part of the joint annual review process in 2012 showed that several sectors do joint planning of HIV activities with CNCS. Nevertheless the Provincial AIDS Nuclei complained that this coordination is not systematic as sectors feel they ought to be accountable only to their line Ministries for any HIV activities they implemented. The reason for this is that Government have not formalised CNCS’ mandate as coordinator of the national HIV response implying that implementers of HIV activities do not feel they need to report to CNCS or ensure that their activities align with the national HIV plan. For example, since 2011 the Ministry of Public Services has led the HIV response in the public sector. They have not systematically reported their activities to CNCS. Consequently, HIV prevention and care activities in Mozambique tend to be small scale and uncoordinated rather than strategic as set out in the national HIV prevention plan. / Indicator 2: Phasing out of on-granting work by CNCS: NOT MET / As agreed between partners and the GoM, CNCS was to transition from their function of grant manager to the coordinator of the national HIV response by the end of 2010. The reason for this decision was the high fiduciary risk of this on granting function due to CNCS weak capacity to ensure that funds were used for their intended purposes. In addition by managing grants CNCS did not have time to coordinate the national HIV response. This transition took longer than expected. In part this was because CNCS resisted it, feeling that it would undermine their legitimacy with civil society and other public sector institutions. As a result CNCS suggested in October 2010 that Common Fund financing be ring fenced allowing them to perform this on-granting function with other funding in the future. An addendum to the Common Fund MoU including a clause that it would not be used for on-granting was approved at the end of 2010. By December 2011 partners had evidence that CNCS had phased out of all their on-granting work. / Several changes in 2012 led to the reinstatement of this on-granting function. One of them was that no alternative on-granting mechanism for HIV related activities was set up by partners and Government between 2009 and 2011. As a result, there was a significant reduction in the number of civil society organizations as well as HIV prevention and awareness raising activities at all levels. Another change was that with the end of the Common Fund in 2012, Government decided to increase CNCS budget by over 200% between 2012 and 2013. This was accompanied by a decision by Government that 30% of the CNCSbudget in 2013 is for on-granting to community based organisations. / What is not clear is what has been done at all levels of CNCS to reduce the fiduciary risk associated with this on-granting function. Funds therefore risk being badly managed or at best slowly absorbed as civil society organizations struggle to have all their systems in place to meet disbursement prerequisites. / Impact Weighting (%): 25 / Revised since last Annual Review? Y- / Risk: Medium / Revised since last Annual Review? N

Output 3: Improved accountability within CNCS
Output 3 score and performance description: A- [Output met expectation] / There is an HIV indicator in the General Budget Support performance assessment framework (PAF). In addition, for the first time the CNCS 2012 annual plan had several indicators for each programme (coordination, monitoring and evaluation, capacity building and communication), which will allow the level of implementation to be assessed at the end of the year .
Indicator 1: Agreement reached on how HIV is reported across government: MET / The milestone set for 2011 was to have consistent reporting on HIV indicators in government plans. The indicator for prevention of HIV transmission from mother to child was reported in the PAF of the of the General Budget support donors for two consecutive years (2011 and 2012). It is also reported in the health PAF. Although this does not cover all sectors, it shows progress, as the Budget Support PAF represents the performance of Government, in their dialogue with partners at the highest level in the country. The targets for this indicator in the Budget Support PAF were not met in 2011 and met in 2012. / At lower levesl, this work needs to be expanded to ensure that the indicators used by CNCS are the same as those used by other line Ministries and civil society. CNCS agreed with sectors what indicators they should be reporting. For instance, in Health the main indicators are focused on treatment of HIV and opportunistic infections, prevention of mother to child infection and HIV counselling and testing. In the Education sector the main indicator is to disseminate communication and advocacy programmes targeting youth in schools. In the Social Welfare Sector the indicator is to increase the provision of services for orphan and vulnerable children and people living with HIV and AIDS. / Indicator 2: One agreed overarching HIV performance assessment framework (PAF) with supporting M&E framework: PARTIALLY MET / The HIV performance assessment framework was established in 2010. It had 61 indicators and this made annual reporting difficult and time consuming. In 2011 it was improved and the number of indicators for each of the four components of CNCS mandate (communication, M&E, coordination and capacity building) was brought down to four. In addition to the PAF, CNCS has other tools to assist them to monitor the national response. These include the Global AIDS Response Programme Report (GARPR) (previously known as the UNGASS) and the National AIDS Spending Assessments. A GARPR was produced for the years 2008-2009 and 2010-2011. / CNCS has struggled to perform their M&E function seeing it more as information gathering rather than to assess the quality and effectiveness of HIV activities. The tools to gather data at the district level are perceived to be complex thereby not motivating stakeholders to report on their work. CNCS also often lack funds to perform supervisory visits or visit remote stakeholders in order to teach them how the M&E tools function. In addition, the M&E tools do not allow for a qualitative assessment of interventions to be made. In conclusion, although the PAF and M&E framework exist, their implementation has met with a few challenges. / Impact Weighting (%): 25 / Risk: Medium / Revised since last Annual Review? N

Output 4: Better planning, allocation and tracking of HIV resources in order to achieve improved outcomes
Output 4 score and performance description: B [Outputs moderately did not meet expectation] / CNCS have improved the quality of their annual plans ensuring that they are more strategic and have an M&E framework to assess performance. However, they still haven’t managed to fit the joint annual review into the GoM cycle.
Indicator 1: Annual operational plan, prioritised, costed and with clear M&E framework to review performance: MET / CNCS has improved this area. Annual operational plans used to be activity based with little strategic thinking or prioritization. Activities were also not costed, implying that some were not achieved within the year due to insufficient funding for the activities. Furthermore, plans were often submitted late, not allowing Common Fund partners any time to comment before the final report had to be submitted to the Ministry of Planning and Development. CNCS has slowly improved over the years, taking into consideration partner comments. They also received technical assistance from GIZ at provincial level to improve their planning and costing processes. / The annual operations plan for 2012 was submitted to partners on time. However, a slow response from CNCS to partner comments delayed approval of the final plan. This, in turn, delayed partner disbursements. The quality of the plan for 2012 was much improved compared to the annual plan for 2011, which consisted mostly of activities. It was more strategic; more clearly set out and included costing of the individual activities. It also set four annual indicators against which to assess progress in each area of coordination, monitoring and evaluation, communication and institutional development. For example communication had a budget of 480,000 USD while M&E had slightly smaller budget of390,000 USD. / One outstanding issue in the plan is that they are costed in USD instead of the local currency, the Mozambican meticais. They are therefore still suited for donors rather than for internal use by CNCS or wider GoM. Another problem with the plans is that they were often not submitted on time. The Common Fund MoU links disbursements to the reception of several reports including the annual plan and audit report. As these were submitted late partners often disbursed late resulting in a balance at the end of the year (see the Value for money section for more on this). / Indicator 2: CNCS joint planning and review processes adhere to GoM cycle: NOT MET / The planning process for joint annual review processes should be improved. The joint annual review includes a joint field visit to at least three provinces to see CNCS work, a report assessing the performance of the sector against the indicators set for each component, and then a meeting where partners and Government discuss the main findings of the report. All these processes should feed into the political dialogue between Government and Budget Support partners in May. Government performance should take into consideration the performance of CNCS. / CNCS struggled to start a joint annual review with partners. As a result, in 2010 the joint annual review took place only in September implying that the main findings of the review did not feed into the higher level political dialogue between Budget Support partners and Government. In 2011 the joint annual review took place on the same day as the political dialogue. For 2012 the field visits did not happen in January and February due to floods. The field visits only took place in April and the final report was delivered in June. In 2011 and 2012, the main findings from the joint annual review did not contribute to the political dialogue. / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No. The original logframe was amended in March 2012 by including milestones for the year. / 1.2 Overall Output Score and Description: B – [Moderately did not meet expectations] / 1.3 Direct feedback from beneficiaries / This report is based on the HIV joint annual review process. This involved partners and other stakeholders including beneficiaries (in this case civil society organizations); other public sector institutions and the private sector. Beneficiaries’ comments were collated during the field visits to 3 provinces included in the review. / Civil Society Organizations were pleased that CNCS re-started their on-granting function in 2013. This would allow them to scale up HIV prevention and care work at subnational level. Many civil society organizations had closed or scaled down their HIV prevention work since the end of 2008, when the role of CNCS changed. However, there are also concerns that in re-starting their on-granting function CNCS will be very slow to disburse funds, as happened with the World Bank’s MAP funding.
1.4 Overall Outcome Score and Description / The expected outcome was to support the effective implementation of the GoM’s HIV and AIDS multisectoral plan (PEN III). The four indicators to assess this were: / Coordination: Functional coordinating mechanism ( CNCS Board, partners forum and management committee meetings) – NOT MET / Communication: Community authorities (traditional healers and other key members) targeted by interactive dialogue – MET / Capacity building: Internal re-structuring plan elaborated and approved- NOT MET / Monitoring & Evaluation: Number of progress reports produced and published- NOT MET / Overall progress is unsatisfactory. Three out of the four indicators were not met. CNCS changed their mandate during the implementation of the project, making their function largely that of coordinators of the national response, with very little funding or political support for this oversight role. Their coordination function was therefore not met. The Management Board stopped meeting in 2009, and the Partners Forum meets on an ad-hoc basis. The partners’ forum also became largely for information sharing rather than for decision making. / Communication improved. Community authorities were involved in various HIV activities leading to tailored messages for communities. As the Minister of Health commented in the 2012 GARPR report: “It can now be noted that the prevention messages have been given a Mozambican flavour, with slogans such as: Andar fora é maningue arriscado (having affairs is just too risky) or Amores a mais é demais” (too many lovers is just too much).” / In capacity building, although the CNCS restructuring plan was submitted to Government in 2011, it is still awaiting approval. Without this plan CNCS cannot be fully integrated into Government, making its sustainability difficult in particular because salaries are quite high. For monitoring and evaluation, only half of partners at sub-national level regularly reported their activities to CNCS. In addition CNCS only published 60% of progress reports they received from partners, due to insufficient funds. / By the end of 2012, CNCS ceased have such an important and relevant role in the national HIV response in Mozambique. Many stakeholders are continuing with their HIV activities without involving CNCS. The re-instatement of CNCS’ on-granting role at the end of 2012 may change this. However, it will bring with it new issues such as the risk that funds are mismanaged by weak civil society organizations and CNCS with their weak management capacity will not be able to adequately monitor this.
1.Impact and Sustainability / The expected impact of this project was to improve the quality of life of people infected and affected by HIV & AIDS and reduce the incidence of HIV in Mozambique. The implementation of this programme has not contributed significantly to achieving the impact. CNCS were not effective in coordinating partners to prevent duplication of efforts and resources, share learning and scale up on-going initiatives. They were also not able to restructure their mandate and staff to make them more effective. In addition, they struggled to be accountable by producing reports on progress at the country level. / After the Common Fund ends, CNCS will continue with funding from the GoM and the re-instatement of their on-granting function. The Common Fund assisted the institution to produce more strategic and prioritised annual plans that will be useful for CNCS and other stakeholders. However, the institution also stopped having a relevant role becoming one of several stakeholders in the national response rather than the main coordinator of it. The challenge for CNCS in the coming future will be to prove that they still have a role in the increasingly bio-medical response to HIV &AIDS. / Several lessons could be learned from this programme: / Set a deadline for when changes should all be made. If these are not met within this time frame, DFID should consider ending the programme or achieving the results through an alternative means. CNCS mandate was changed in early 2009. However, it took more than two years for many changes to be finalized, some of which were resisted by the organization. The on-granting function is being re-instated without addressing some of the fiduciary risk issues partners raised about this function involved. CNCS mandate has still not been formalised undermining their ability to coordinate the national response. DFID should have set a deadline after which the project should have either been closed or initial objectives achieved through other means. / If there is no political will to make the governance structures of the institution effective, then DFID should consider leaving. CNCS has not been accountable to its Board since 2009. Partners including kept trying to engage members of the Board through various means including a letter. DFID should have considered whether to leave the programme due to this lack of accountability which implied that there were no incentives to improve the institution’s performance.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: YES / DFID disbursed £1,440,000 (£360,000 per year from 2009) worth of financial aid for the CNCS as initially planned. / DFID’s contribution was to a common fund in support of the broader CNCS programme and so the extent to which the project as a whole is on track must be considered in that context. / In the last two years the budget execution for the common fund improved. A total of 4.2 million USD was disbursed into the common-fund in 2012 and overall common-fund execution has been at about 74% of available resources. This is largely explained by delays in donor disbursements. Around US$ 1.1 million or about 26% of total disbursements for 2012 only took place in the fourth quarter of the year. The reason for this was that some Common Fund partners (Canada) needed to have a procurement audit complete before disbursing. The audit started late and the partner disbursed late. / This contributed to a large positive common-fund balance of 1.7 million USD at the end of the year, which is accounted for in the 2013 opening balance. This corresponds to more than 4 times the outstanding positive balance registered at the end of 2010, which was 304,800 USD. / As shown in the table below, overall budget execution for the sub-sector stands at 85%. This is is due to the lower execution of the common-fund. Execution from other sources of CNCS funding (funds from the State Budget and from other partners to the provinces) was according to plan. With the removal of CNCS on-granting function their budget execution improved considerably. / Currency: Meticais / Source of Fund 2012 Final Budget 2012 Budget Execution % Execution / External Funds / Common Fund 94,315,640.00 69,809,488.27 74% / Earmarked Funds / DANIDA 640,850.95 463,580.70 72% / German Development Agency (GIZ) 1,454,155.00 1,333,271.62 92% / UNDP* 1,715,314.40 1,680,339.87 98% / Sub-total of Earmarked Funds 3,810,320.35 3,477,192.19 91% / Total External Funds 98,125,960.35 73,286,680.46 75% / Internal Funds / Recurrent 7,179,276.00 6,954,958.19 97% / Investment (Salaries) 70,128,090.00 69,566,969.12 99% / Total Internal Funds 77,307,366.00 76,521,927.31 99% / Total External Funds + Internal Funds from State Budget 175,433,326.35 149,808,607.77 85% / Key cost drivers / By the end of 2012, CNCS was no longer a manager and grantor of HIV funds to implementing agencies. Accordingly, the cost drivers are now mainly goods and services, (such as equipment and consultancies accounts), salaries and per-diems, and small proportion for investment in capital goods. / The CNCS initial budget proposal (contained in its Annual Operational Plan for 2012) includes a general planned budget allocation per type of expenditure and per activity; However, these are not reported against in end-of-year performance and financial reports. / This means that a detailed analysis of key cost drivers in 2012, and of how execution performed against plan at a detailed level, is not possible with the information currently available. / As in 2011, the budget execution report for 2012 suggests that, the key cost driver is recurrent expenditure of CNCS operations. These include, planned expenditure on goods and services, such as equipment and consultancies (58% of total planned expenditure) salaries and per-diems (40%); and just 4% for investment in capital goods. Part of the reason for this is that CNCS staff are not hired as civil servants, as the institution is not yet fully integrated in government. Staff salaries are higher than those of civil servants. The transition to integrate the institution into the public sector has taken 3 years, with the approval of the proposed organizational statutes still awaiting approval by Government. / 2.3 Was the project completed within the Expected Timescales: Yes / This project was expected to end in March 2013 as originally planned. The Common Fund partners have all phased out their funding. Due to late disbursements by Canada and Denmark, they will continue to monitor activities throughout 2013.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / When DFID started their funding through the common fund there was little evidence about the effectiveness of different HIV prevention activities including behaviour change communication, school based prevention and prevention among people living with HIV & AIDS. These were the main activities that CNCS funded for implementing agencies. There is now strong evidence that these activities are not cost effective in preventing HIV. [3] / There was no evaluation carried out in 2011 and an independent evaluation is not planned for this project. An overview by Denmark of the HIV/AIDS Response in Mozambique in 2010 highlighted the main issue in CNCS as (i) limited technical capacity (ii) limited authority to exercise its coordination mandate and (iii) limited financial resources. / 3.2 Where an evaluation is planned what progress has been made? / Does not apply
[3] DFID analysis of systematic reviews on value for money in HIV Prevention (taken from HIV value for money teamsite).

4. Risk
4.1 Output Risk Rating: The risk did not change over the course of the project / Political Economy risk: High / The target for 2012 was to ensure that DFID along with other Common Fund partners exited the sector responsibly. This required strengthened efforts to: / Secure allocations from Government to the HIV sector; / Ensure that CNCS is accorded a clear mandate by Government to coordinate the HIV response, and; / Ensure that key stakeholders such as GIZ; UNAIDS, UNICEF and the United tates Government continue policy dialogue with government. / The first point was achieved; Government allocations to the sector increased by over 200% between 2012 and 2013. The end of the Common Fund therefore did not have a negative effect on the role of CNCS. On the second and third points partners are in the process of preparing a brief for strategic dialogue with CNCS that focuses on clarifying its focus and mandate. / Fiduciary Risk Rating: Medium to High / Fiduciary risk reduced during the implementation of the project as CNCS on-granting function was phased out. The fiduciary risk assessment commissioned by DFID in 2011 showed that not all the funds disbursed to CNCS were used for the purposes intended, adequately reported or accounted for. Note must be taken that for most of the weaknesses identified in the assessment, the risks were associated with CNCS’ on-granting function that ended by December 2011, and the financial management weaknesses of implementing agencies. The report states that, “most of these risks become marginal with the change in role that is taking place in CNCS that will only be a coordinating institution.”[4] Furthermore, since 2009, DFID funds had been ring-fenced to ensure that they were no longer used for on-granting. / The decision by Government to reinstate the CNCS on-granting function needs to address the fiduciary risks brought about by this role. The remaining partners in the sector are in dialogue with CNCS to see if the institution will be given sufficient financial management capacity to perform this role. / Institutional risk: Medium / Limited M&E capacity undermined the ability of CNCS to supervise and effectively report on HIV prevention, treatment and care activities. This risk has been reduced now that Government has committed sufficient resources for CNCS to implement their plan in 2013. However, their mandate is still not strong enough to secure cooperation of other government bodies.
Climate and Environment Risk : Medium / Flooding in early 2012 undermined some HIV prevention activities and caused a delay in the field visits for the joint annual review process.
[4] Umarji, M.; Paulo, A. (2011) Avaliacao do risco fiduciario: Relatorio Preliminar. Relatorio para o CNCS com o apoio do DFID.MB Consulting. Maputo, Mocambique. p.4

5. Value for Money (VfM)
5.1 Performance on VfM measures / The programme did not benefit from a formal economic appraisal, as it was approved prior to the introduction of the new Business Case format. / As a result, no explicit value for money (VfM) metrics that can capture the level of economy, efficiency and cost-effectiveness of CNCS’s activities, were developed and monitored throughout the life of the programme. / VfM aspects of CNCS operations are currently not reported on in financial and physical performance reports, and the information available is not sufficiently detailed to enable ex-post VfM analysis. / Many of the indicators specified in the logframe are not amenable to VfM analysis. Targets relate more to processes (such as producing plans and reports or strengthening capacity) and coordination activities, rather than to directly quantifiable outputs and outcomes. / In any case, measuring VfM in the context of CNCS operations is extremely difficult, given that CNCS is not an implementing institution but manages the national HIV response by coordinating the planning, coordination and monitoring of programmes implemented by third parties. / CNCS used to transfer funds to implementers to in the private and public sectors and to civil society organizations, for prevention activities. Many of the activities funded for prevention are now not considered to be cost effective based on recently available evidence. For example, small scale activities targeting high risk groups such as sex workers or behaviour change interventions / Although CNCS budget attempts to cost activities at a general level, the annual activity reports do not provide details on actual expenditure by activities. Only a very aggregate economic classification of expenditure is provided in GoM’s financial execution reports. / 5.2 Commercial Improvement and Value for Money / A procurement audit was undertaken in the sector. This highlighted no major weaknesses in procurement and made recommendations for how to strengthen identified weaknesses. All procurement undertaken by CNCS, including with Common Fund resources, was carried out in accordance with the government’s rules and procedures. / Low budget execution during the implementation of the project was due to limited capacity to write and submit narrative and financial reports on time. This contributed to delays in disbursements by donors but had improved slightly by the end of the project. A fiduciary risk assessment commissioned by DFID in 2011 also raised concerns about financial management and internal controls (the overall risk was rated as substantial), although by the end of 2012 most of these weaknesses had been reduced with CNCS ending their on-granting function. / 5.3 Role of project partners / CNCS is responsible for coordinating the national response to HIV&AIDS through programmes implemented by third parties such as Government entities (eg. Ministries), national and international NGOs, line ministries, the private sector and Civil Society Organisations (CSOs). Execution of this role was challenging due to the lack of formal endorsement of CNCS as coordinators of the national response by Government. / DFID and other donor Agencies (Canadian CIDA and Danida) are responsible for the provision of financial aid into a common-fund, and joint monitoring with the government. The Common Fund ended in 2012. The Government is now responsible for providing all the funding for CNCS’ core functions. Other players such as the United States Government and UN took on more of a prominent role as the Common Fund phased out in 2012. GIZ will continue to provide funding and technical assistance for institutional development at the subnational level until the end of 2013. / 5.4 Did the project still represent Value for Money : We don’t know but unlikely / As mentioned earlier, no hard evidence is currently available to assess the VFM of the programme against ex-ante agreed benchmarks. However, due to the low performance of CNCS since 2009 and the fact that most funds contributed not towards coordination or monitoring and evaluation but towards salaries, this project was not good VfM. / Global evidence shows that investing in HIV&AIDS prevention and awareness-raising represents good value for money, and offers excellent rates of return given the huge economic costs of HIV&AIDS to society. According to WHO estimates, in 2004 HIV&AIDS accounted for 22% and 25% of total Mozambican DALYs[5] and deaths respectively. However, we do not have any firm evidence as to the VfM of this particular intervention in Mozambique. As manager of funds for HIV until 2008, and coordinator of the national response, CNCS played a positive role in enabling the incidence and prevalence curves to finally plateau after 9 years of steady increase. In recent years, the new infection rate and HIV prevalence has somewhat stabilised in Mozambique at 11.5% (INSIDA 2009). However note must be taken of the fact that despite the large resources channelled through CNCS, the global evidence suggests that behaviour change communication and focusing on most at risk groups at a small scale are not effective HIV interventions. Only some of CNCS’ interventions such as peer to peer support are cost effective.[6] / The majority of cost effective interventions for HIV prevention and treatment (such as the provision of anti-retrovirals for people living with HIV; prevention of transmission from mother to child; voluntary counselling and testing and the treatment of STIs) are being undertaken by the Ministry of Health.[7] There is a lack of evidence that coordinating the national HIV response is effective in preventing HIV. The savings in terms of new infections averted are to be attributed not to CNCS but to the Ministry of Health. DFID’s decision to phase out of HIV and continue to address it through our support to the Ministry of Health is therefore expected to offer better value for money. / 5.5 If not, what action will you take? / DFID phased out of HIV in 2012 and decided to address HIV through the health sector. The Ministry of Health is responsible for implementing cost effective HIV prevention, treatment and care activities at a national level. They will also continue to collaborate with CNCS.
[5] DALY – Daily adjusted life years – the health gap in terms of potential years of life lost due to ill health or death
[6] DFID analysis of systematic reviews on value for money in HIV Prevention (taken from HIV value for money teamsite).
[7] DFID analysis of systematic reviews on value for money in HIV Prevention (taken from HIV value for money teamsite).

6. Conditionality
6.1 Update on specific conditions / The only concern regarding the commitment to Partnership Principles during the reporting period was addressed when CNCS phased out their on-granting function in December 2011. In addition, CNCS showed greater commitment to strengthening their financial management systems by addressing almost all the audit annual recommendations by the end of 2011. Although CNCS resumed their on-granting function in 2013. This was not with DFID funds, which were ring-fenced. The Common Fund was subsequently closed by partners.

7. Conclusions
As evidenced by this project completion report, performance of this programme can be rated as unsatisfactory. CNCS changed their mandate in early 2009. However, their new mandate was never properly defined or established by GoM making it difficult to implement. Consequently the instituiton was unable to coordinate the sector. In addition, the Management Board to which CNCS was accountable never met implying that the instituon never had any incentive to improve its performance. The lack of constructive dialogue between stakeholders and CNCS has meant that CNCS’ function as coordinator of the national response has been undermined. Many stakeholders now plan,implement and assess their HIV activities without any CNCS involvement. / Furthermore, with the end of CNCS on-granting function, no alternative source of funding was available for HIV activities in Mozambique. Stakeholders therefore had little funding for their HIV activities and CNCS was not able to support the sectors to include strategic HIV activities in their annual plans at the provincial and district level. Consequently, HIV prevention activities in Mozambique have become uncoordinated, not strategic and of small scale. / The Common Fund, to which DFID contributed phased out in 2012. Government has taken on all the activities funded by the Common Fund, including salaries. This addresses DFID concerns about CNCS’s sustainability. Government also decided to re-instate CNCS on-granting function in 2013. This was in reponse to requests by civil society organizations for a mechanism to fund their HIV prevention and care work. It is not yet clear how the high level of fiduciary risk brought about by this function will be minimized. / Although the programme score was unsatisfactory some progress was seen. CNCS improved its coordination with other line Ministries and civil society. They also signficiantly improved the quality of their annual reports, which are now more strategic, costed and have a clear M&E framework against which to assess progress. In addition, although they are still not aligned with Government’s planning cycle, they do have an annual review process. All these factors will have made the institution much stronger internally. Government has yet to define exactly how relevant CNCS role in the national response will be in the future .

8. Review Process
This review was conducted by Etelvina Mahanjane (Health Adviser) Marcos Levi (DPM) with inputs from inside DFID Mozambique (Senior Health Adviser - Saul Walker, Economic Adviser -Kobi Bentley and Evaluation and Results Adviser Cormac Quinn). The key sources of information were the: / CNCS 2012 Joint Annual Review report; / CNCS Activity Plan for 2012. / Aide Memoire of Workshop between CNCS and Health Sector for more complementarity and optimization of resources at provincial and district levels (June 2012). / CNCS Fiduciary Risk Assessment Report (2011) / Mozambique report on the MDGs (2010) / Overview of the HIV/AIDS Response in Mozambique (2010) Austral Cowi / DFID analysis of systematic reviews on value for money in HIV Prevention.