Annual Review

Creation of the National Fund for Climate and Environment (FONERWA) - Rwanda
(Aries project number: 203431)

Project start date:	11 May 2012
Review undertaken: 10 July 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Log frame / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
UK support will enable the creation of a National Fund for Climate and the Environment in Rwanda. / The creation of the Fund is an integral part of the recently approved Government of Rwanda’s National strategy for Climate Change and Low Carbon Development.[1] The Fund is identified in the strategy as a vital enabling pillar for implementation. / The UK will support the operation of the Fund for an initial period of 2 years at an estimated cost of £1.5 million. These funds have already been identified and approved in the DFID Rwanda Operational Plan and the concept note was approved by the International Climate Fund (ICF) Board in July 2011. This is an innovative intervention and evidence of impact is currently limited. Therefore £200k will be earmarked for in-depth impact evaluation.
[1] Republic of Rwanda: Green Growth and Climate Resilience, National Strategy for Climate Change and Low Carbon Development, October 2011

What are the expected results?
The expected outcome is that Rwanda is able to finance and further develop national programmes and private sector initiatives which contribute to low carbon and climate resilient development in line with the National Strategy for Climate Change and Low Carbon Development. / The programme will contribute to the outcome through supporting the operation of the Climate and Environment Fund for the first two years. Specific outputs will be: (1) securing capitalisation of the Fund from government of Rwanda, development partners and other sources; (2) building national capacity for managing the Fund, through technical assistance; (3) facilitating Steering Committee decisions on early proposals approaching the Fund for support through day-to-day administration and quality assurance; (4) monitoring and evaluation of Fund results. / Expected results are: / A minimum of £4m resources mobilised for Rwanda’s climate and environment objectives by August 2014 / Strengthened national capacity for managing the Fund: at least 70% of the Secretariat comprised of trained national staff by August 2014 / Decisions reached on a minimum of 15 proposals by August 2014 / Evaluation of early Fund results carried out by early 2015 / The initial 2-year operation management of the Fund will be attributable to DFID. The longer term impact of the fund will be attributable to contributors and the Government of Rwanda.

What is the context in which UK support is provided?
Rwanda is highly vulnerable to climate change as it is strongly reliant on rain-fed agriculture both for rural livelihoods and its significant exports of tea and coffee. The country has experienced a temperature increase of 1.4°C since 1970, higher than the global average, and can expect an increase in temperature of up to 2.5°C by the 2050s from 1970. Average annual rainfall may increase by up to 20% by the 2050s from 1970, increasing the risk of landslides, crop losses and damage to infrastructure.[2] / Rwanda also imports all of its oil-based products so any increase in oil price has a significant negative effect on GDP and economic growth.[3] Rwanda is fortunate in that it has large, untapped clean energy resources, in the form of geothermal, hydro and solar, which have the potential to meet Rwanda’s electricity needs and replace oil-fuelled power plants. This could offer domestic energy security and support socio-economic development whilst significantly reducing greenhouse gas (GHG) emissions that contribute to global climate change. / The Government of Rwanda is determined to set the economy on a low carbon and climate resilient development trajectory. DFID have been working with the Government in support of its climate and environment objectives since 2009, most recently in the development of a National Strategy for Climate Change and Low Carbon Development which was approved by the Rwandan Cabinet in October 2011. The challenge Rwanda now faces is in implementation of the Strategy. / The initial implementation phase needs to focus on creating and building institutions that will enable Rwanda to access international and bilateral climate finance, mainstream climate resilience and low carbon development into the national development plans and achieve its vision of being a low carbon and climate resilient middle income economy by 2050. A key recommendation from the Strategy was the creation and operation of a National Fund for Climate and the Environment. / The rationale for the Fund stems from growing recognition amongst both donors and recipients that a coordinated, streamlined approach to climate financing is needed to respond to developing countries’ adaptation and low carbon needs, and that such coordination would best be achieved through a ‘devolution’ of management to developing country governments.[4] The purpose of the Fund is therefore to facilitate and coordinate access to domestic, bilateral, multilateral and international climate funding streams and align them with national development programmes that contribute to low carbon development and climate resilient growth in Rwanda. The Fund, recently enabled in Law[5], will be an integral part of the Rwandan government and financial institutional architecture and could also promote new and innovative ‘green’ private sector initiatives. / DFID Rwanda support will be used to establish and run the Fund for an initial two year period. We will do this by direct procurement of a team of international and national experts. The team will be tasked with securing long term financing for the Fund’s operation after the initial two year start-up period, as well as capitalisation of the Fund. We hope to be in a position to capitalise the Fund from the ICF within 1 year of its operation. This will be the subject of a separate Business Case to be submitted by the end of this financial year. / The opportunity to support this intervention exists due to the strong commitment by the Government of Rwanda to address the effects of climate change and drive low carbon growth.
[2] Ibid.
[3] Econometric modelling conducted as part of the Baseline Report to inform the National Strategy, (unpublished) suggests that a 10% increase in the price of oil will lead to a reduction in GDP by 1.5%
[4] Capacity Development for Development Effectiveness Facility (2010) op cit; Agulhas (2011) Realising the Potential: Making the most out of climate finance - A synthesis report from six country studies: Cameroon, Ghana, Kenya, Morocco, South Africa and Tanzania, Draft report to OECD, http://www.oecd.org/dataoecd/27/38/48597031.pdf . Similar funds to that proposed by Rwanda have recently been, or are in the process of being, established in Indonesia, Bangladesh, Brazil and Ethiopia
[5] FONERWA Law

## Section A: Detailed Output Scoring

Output 1: Process of screening projects and disbursing finance is effectively managed
Output 1 score and performance description: / C: Substantially did not meet expectations / Targets could not be scored as the Fund was only capitalised in June 2013. Milestones for this output are based on the Fund requesting project proposals which did not occur during this reporting period. These outputs do not reflect inception phase activities undertaken to date with respect to management of the fund. The Fund Management Team was appointed in October 2012, so progress reported covers a period of nine months only. / 1.1 Percentage of a)Project Profile documents and b) Project documents reviewed within 10 working days, and in accordance with agreed screening procedures: Milestone = a) 50 b) 40 / 1.2 Percentage of available fund resources executed per year (disaggregated by recipient- private sector/government/CSOs): Milestone = 80%
Progress against expected results: / A key assumption that sufficient resources would be available for a call for project proposals was not realised until June 2013. This was largely beyond the Fund Management Team’s (FMT’s) control. The Fund Management Committee (FMC), responsible for final screening of projects, did not meet for the same reason and members were only confirmed following government approval of a Prime Ministers Order in June 2013. / Progress has been made on building blocks for this output e.g. elaborating the fund operational manual and project screening procedures with respect to value for money; refining the monitoring and evaluation framework (refer output 4); securing and transferring government finance contributions from the Forestry Fund and environmental fees/fines into the FONERWA account; mobilising additional external finance through applications to the Adaptation Fund (USD 10m) and African Development Bank - Low Carbon Development Fund (USD 8.8m) and concept proposals have been approved for further development; as well as training and outreach to sectors and potential project partners to develop a pipeline of potential projects. / Recommendations: / These targets are deferred as FONERWA was only capitalised in June 2013. / The project expects to catch up on the log frame targets outlined for June 2014 next year. / Impact Weighting (%):35% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Capacity for managing the Fund built and transferred to Government of Rwanda
Output 2 score and performance description: / A+ –Moderately exceeded expectation
All milestones were fully met for this output and one exceeded. / Progress against expected results: / As of June 2013, 6 member team positions have been filled locally. This exceeds target of 10% in the first year. Team members employed have received training and mentoring. / 2.1 Number of initial local technical staff recruited who are retained at the end of the project period: Milestone: no target for this reporting period. / Not applicable / 2.2 Percentage of the Fund Secretariat made up of locally trained technical staff: Milestone 10% / Milestone exceeded: 100% of secretariat team is local. / The Fund Co-ordinator was in place from October 1st, 2012. An additional three member team started work from November 4th, 2012. They included the Financial Management, Accounting and Procurement Specialist, Monitoring and Evaluation Specialist and Executive Secretary. An Internal Tax Adviser was in post from the 14th of January, 2013, while the Fund Management Specialist (FMS) only took up the position in June 2013. / The absence of the Fund Management Specialist (FMS) did not have any implications on the day-to-day management of FONERWA, given the capitalisation delay. While it did provide some cost savings, some capacity development initiatives targeting skill building for fund management were deferred. / 2.3 Number of government of Rwanda staff participating in mentor meetings or workshops with FONERWA mentors at least one a month: Milestone 5 / Milestone met: Local FMT team members confirmed they meet at least monthly (weekly with team leader) to receive on the job training and guidance from CIDT specialists with regard to day to day management of the fund. This has included effective procedures for collection of government fees and resources, financial reporting; project value for money criteria and monitoring and evaluation. Point persons have been identified for each of the team members. A few focal points (from Ministry of Commerce and Industry, Finance and Economic Planning; Environment; Agriculture and Infrastructure) as well as ministry interns have been identified through training workshops to receive additional support and coach stakeholders (be trainers) in their respective sectors on project proposal development. A capacity needs assessment was completed and capacity development plan updated in December 2012. / Recommendations: / Deferred activities identified under the capacity development plan for the first six months of 2013 need to be delivered. A revised delivery plan schedule is required now that the FMS is in post and call for proposals next month. While the FMT has addressed some capacity building needs at ‘Strategic Level 1’: Efficient fund management and ‘Strategic Level 2’: Proposal development and project cycle management, very little progress has been made on ‘Strategic level 3’: Capacity to develop and effectively roll out and manage financial instruments of the private sector. This needs to be urgently addressed given the challenging in-country private sector landscape. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Awareness raising and technical assistance support submission of good proposals
Output 3 score and performance description: / A: Outputs met expectations. / Out of four milestones for this output, one was exceeded, one met, and two not met (assumed fund application round initiated) for this reporting period. / Despite the delay in initiating the fund proposal rounds, substantial time and effort has gone into the capacity building programme (training, e-documents) for project proposal preparation. A broad group of almost 300 persons has been reached to date. A range of pipeline project ideas (over 85 to date) and potential project documents has been generated by stakeholders and across sectors (summarised below). On-going coaching and mentoring support is being provided to ensure strong project profile and project document preparation.
Progress against expected results: / Number of people trained in developing proposals (disaggregated by private sector/district level government/central government/CSO): Milestone 100 / Milestone exceeded: / In March 2013, fund orientation training was delivered through 4 workshops as well as through training sessions in partnership with Rwanda Environmental Management Agency (REMA) to 291 participants. / . / Workshop no. Private sector District level government Central government CSO Number of participants / 1 22 23 / 7 5 4 16 / 4 12 2 18 / 34 34 / REMA sessions 165 35 200 / Total 177 35 73 6 291 / Staff from a range of central government departments (primarily sectoral staff with monitoring and evaluation / project management roles) some NGOS, private sector organisations including banks (Business Development Services for four provinces) as well as interns for the district level whose role it is to mainstream climate and environment planning into district development plans attended. These workshops explained the FONERWA fund, provided guidance on selection criteria as well as project proposal requirements. Participant feedback illustrated a need for further guidance on how to structure, format and budget project proposals. / The next round of training, undertaken from May-June, took a more mentoring and hand on practice approach, building on initial ideas submitted from various sectors as well as targeting more civil society and private sector organisations. The 4 workshops were organised in collaboration with the following sector working groups (refer below) and hosted in the various ministries. No participant evaluation was carried out for this second round of training, but more detailed log frame training and baseline setting, targeting chosen project profile documents, has been identified as a need. Most of the participants had not attended the initial workshops. / Workshop no. Number of participants / MINIRENA (Environment and Natural Resources Sector) 20 / MININFRA (Energy Sector) 13 / MINICOM (Private Sector) 19 / MINAGRI (Agriculture Sector) 19 / Total 71 / Workshop no. Private sector Central government CSO Number of participants / MINRENEA 0 13 7 20 / MININFRA 0 13 13 / MINICOM 9 10 19 / MINAGRI 4 13 3 19 / Total 13 49 10 72 / District and provincial workshops are being planned with the ministry of local government for July with Climate Development Knowledge Network (not captured above). An orientation meeting chaired by the Vice mayor of Kayonza district was held in June to discuss potential project submissions. / Currently there is reportedly a good range of ideas for Fund windows 1 (Conservation and natural resources management) and 3 (Environmental and climate change mainstreaming) but less so for Window 2 (R&D and technology transfer). Details are summarised below. / Lead organisation Main proposal sector / Private Sector Government CSO Natural resources Energy Urban / infrastructure Other / 36 39 10 46 16 4 7 / 3.2 Number of requests to the FMT for a) information relating to the Fund and b) Technical assistance in proposal development: Milestone = a) 50 b)15. / Milestone met: a) 7 per week b) 63 (requests indicated in pipeline proposals) / The FMT has received significant number of requests for further information through phone calls, email and drop in visits by potential beneficiaries. They estimate they have been receiving around 7 requests per week over the past several months. Out of the 85 project pipeline proposals received, 63 have requested technical assistance. If successful in their application this will be provided during the project development stage. / 3.3: Percentage of projects that receive technical assistance in proposal development from the FMT and which are subsequently approved by the Fund Management Committee: Milestone 80 / Not scored given the FMC is only just constituted and call for proposals not initiated. No project proposals shortlisted for development. / Some early assistance has been provided to project developers by FMT and CIDT through the fund orientation training workshops which targeted potential pipeline projects on funding requirements and selection criteria. Specific sectoral or activity related technical assistance will be available through a call down arrangement once projects are shortlisted. / 3.4: Number of financial instruments targeting the private sector developed and piloted by the FMT: Milestone = 1 instrument developed / Milestone not met. / Instruments could not be piloted until the Fund was capitalised. A draft Standard Operating Procedure (SOP) document for private sector performance-based grants was produced in June 2013. / In March 2013, a roundtable dialogue session was organised with representation of Private Sector Federation (PSF); Rwanda Renewable Energy Association (RREA), local entrepreneurs and the Business Development Fund (BDF) to discuss challenges in accessing various funds and their understanding of ‘green’ projects. A draft targeting strategy was then prepared identifying a range of possible instruments but further elaboration and analysis is needed in terms of FONERWA unique approach, situational analysis and market failures, instrument use and linkages etc. In the short term, private sector performance grants will be made available. Progress with BDF, as a local partner support role on private sector, has not materialised given their limited capacity and experience. / Recommendations: / Capacity building: Demands for project development capacity building will intensify. Given delays experienced, timelines for the capacity development plan will need to be revisited and measures to facilitate execution at a faster pace identified. Strong coordination is also needed for the over 40 technical specialist on call for support and training. GoR counterparts (viz. trainers) have been identified and are shadowing international consultants conducting the training, to then in turn facilitate future sessions (applying the training modules they helped develop), Their competence levels will also need to be boosted. The learning by doing approach should be more effective, but the risk of falling behind demand or not meeting quality required needs to be constantly monitored and addressed where needed. / Private sector targeting: Refinement of financial instrument design and a revised Private Sector Targeting Strategy are urgently needed as well as identification of suitable partner for the private sector implementation component of the Fund. / Impact Weighting (%): 25 % / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Results from the Fund are effectively and transparently monitored and lessons disseminated
Output 4 score and performance description: / C: Substantially did not meet expectations / Fund only capitalised in June 2013. Milestones for this output could not be scored as they are based on approved projects by the Fund. Applications have not yet been initiated.
Progress against expected results: / 4.1 Percentage of active projects collecting data of sufficient quality and timeliness to satisfy the FONERWA Monitoring and evaluation system: Milestone 90 / Not scored / 4.2 Percentage project documents affecting households that demonstrate transparent community participation and gender equality in a) proposal development b) implementation: Milestone a)80 b) 80 / Not scored / 4.3 Percentage of projects whose emerging lessons (both positive and negative) have been collated and disseminated by the FMT / Not scored / A comprehensive FONERWA M&E framework is in place and a FONERWA Metadata Handbook produced. Several FONERWA indicators were incorporated into Rwanda’s Economic and Development Poverty Reduction Strategy 2 (EDPRS 2: 2013-18), as well as the Environment and Natural Resources Sector Strategy monitoring framework for the next five years. The National Institute for Statistics and Research (NISR) is expected to support the data collection. Indicators tracking FONERWA’s contribution at sectoral level include the vulnerability change index and creation of green jobs. / Recommendations: / None / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the log-frame been updated since last review? No / The business case log frame was refined during the inception phase of the FMT support contract in November 2012. / Updates to reflect the slower than expected capitalisation of the fund should have been made in 2013. / 1.2 Overall Output Score and Description: / B – Moderately did not meet expectations. / Out of four outputs, two outputs (total 50% weighting) assumed there would be sufficient funds in the fund to initiate an application call in this reporting period. Their targets could not be assessed and scored a C (substantially did not meet expectations). The other two outputs scored A and A+, but being evenly weighted against the others, a score of B was the overall result. / 1.3 Direct feedback from beneficiaries / There are no beneficiaries of fund support yet, but some feedback from local FMT recruits and training participants was collected. All indicated that the sessions on value for money were useful and new for them. Training modules working with concrete examples or concepts was constructive. Identifying good indicators and targets, cost benefit analysis and setting baselines will be a challenge for many applicants.
1.4 Summary of overall progress / The FMT has been in place for nine months. The fund has now received sufficient support to initiate an application call. There is strong political interest in the Fund and incorporation into Rwanda’s Economic and Development Poverty Reduction Strategy 2 (2013-18) policy and results matrix. We expect progress to continue and accelerate now that initial partner and government funding has been mobilised. A first call for proposals is expected to occur in July 2013 as well as the inaugural meeting of the Fund Management Committee (FMC). / The first application round is expected to draw a strong response given current indications. Quality of proposals will still need to be determined however. Project pipeline ideas are being developed through training and mentoring approach. Call down technical expertise has been arranged to provide assistance at short notice. District and provincial capacity building is being boosted through joint programming support provided by the Climate and Development Knowledge Network (CDKN). / The Prime Ministers Order on FMC’s composition and its powers, responsibilities and functioning was approved by cabinet in June 2013. The FMC will be chaired by Director General (DG) of Rwanda Natural Resources Authority (RNRA) with vice chair, DG of Rwanda Environment Management Authority (REMA). Head of DFID Rwanda will co-chair on behalf of the contributing development partners. It also includes members from Ministry of Finance, Agriculture, Energy; Industry, Urban Planning, Civil Society chairman and the Private Sector Federation. Membership on the FMC was lowered from permanent secretary level and includes those originally envisioned for the Fund Technical Committee (FMC). Identifying suitable alternate FTC members will need to be addressed urgently to ensure effective oversight or governance of the fund and review of proposals. / The Fund Management Team / Secretariat is now fully staffed and has the capacity to manage a total fund up to around $40m. Key achievements and activities in the first year have included / Staffing and setting up the FONERWA offices, financial systems and grant application processes as well as call down consultants to provide technical assistance for project development / Preparing decree for establishment of governance structure / Opening of the fund account and collection of local government finance resources (fines/fees) / Preparing a communication strategy, brochure and initiating outreach services / Refining the monitoring and evaluation framework / Integration in EDPRS2 / External fund raising, including providing support on proposals submitted to the Adaptation Fund and African Development Bank-Low Carbon Development Facility / Designing and implementing a capacity building programme based on a needs assessment which to date has included basic orientation on environment and climate change; project formulation and value for money; and on job training for FONERWA Secretariat local staff members.
1.5 Key challenges / The key challenges faced by the project include: / delays in securing fund finance which has led to many related outputs not being realised that will now need to be caught up over the next year; / delays in recruitment of fund management specialist but is now in place; / private sector targeting strategy development and finalising local implementing partnerships / the sheer amount of time it takes to begin such a wide variety of work across several different sectors, with a range of partners and respond to their varying needs.
1.6 Annual Outcome Assessment / The project outcome is Rwanda is able to finance and further develop national programmes and private sector initiatives which contribute to low carbon and climate resilient development in line with the National Strategy for Climate Change and Low Carbon Development and the Economic Development and Poverty Reduction Strategy. / There are three outcome indicator milestones: / Cumulative volume of finance mobilised for climate and environmental purposes with a target / A) contribution in government finance of US$1.3m by June 2013: Milestone met / B) co-financing from private sector $1m by June 013 : Milestone not met (fund only capitalised in June 2013) / C) Contribution /co-financing from MDB’s /other development partners: Milestone 0: US$640,000 is provided by Climate Development Knowledge network (CDKN) / 115 project profile documents (PPDs??) a)received by the FMT , 8 meeting the standard required to proceed to project document stage and 5 approved by the FMC - Milestone not met (fund only capitalised in June 2013) / 80% selected projects successfully implemented (i.e. project being on track to deliver at least 80% of the results set out in its project document) - Milestone not met (fund only capitalised in June 2013) / The UK approved its finance for the Fund, of up to £22.5m till March 2015, in June 2013. The FONERWA account was opened in March 2013 and £1,350,787 has been collected so far from the Rwanda Forestry Fund and collection of environmental fees and fines from district level. / Overall, the project had a slower than anticipated start with set-backs primarily due to delay in fund capitalisation levels as well as recruitment of the fund management specialist. Private sector targeting and implementing partners’ needs to be addressed urgently. It is expected that work in all areas will be back on track in the coming year.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / The project had a slower than expected start, which is reflected in slower than anticipated spend. We expect this spend to be made up in the coming year, and have agreed adjustments where appropriate. / A delay of 6 months in agreeing UK finance for the Fund and initiating an application round means that this project support may need to be extended post September 2014. The period of extension and whether or not it is on a ‘no additional cost’ basis will depend on available resources. This will be affected by the performance of the fund and number of project proposals selected that need technical assistance, so this will need to be monitored and assessed in the coming months. / 2.2 Key cost drivers / In the first year, as expected, key cost drivers have been salaries for FMT staff (project management and development, as well as travel and training. The delays in recruiting the Fund management specialist post (now started in June 2013) as well as changes in work plan were major reasons for underspend. / 2.3 Is the project on-track against original timescale: N / It had a slower than expected start, and there were delays in recruitment of key posts. By quarter 2 (end March 2013), 40 out of 59 identified activities across 11 work streams or 12 out of 14 deliverables were fully or partially implemented The remainder were not undertaken largely due to delay in initiating proposal rounds. They have been reprogrammed into a revised work plan.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Assumptions used in the project design and theory of change are still valid based on latest evidence reviewed. This project will also contribute to building the evidence base for climate ‘smart’ (safe and green) development in practice as well as evidence of impact related to the creation of national level institutions and basket funds to enable access to climate resources and meet cross cutting needs. / 3.2 Where an evaluation is planned what progress has been made? / An evaluation is expected to be completed by March 2015 to cover the first two years of Fund operation (including FMT support). Later this year, the evaluation team will be procured to establish a baseline and put in place measures to ensure adequate information is available to facilitate an effective impact evaluation.

4. Risk
4.1 Output Risk Rating: Medium / The log-frame rates the risk of each output (1-4) as medium. / This has not changed. / 4.2 Assessment of the risk level / The risk level remains medium. Major risks, their probability and impact ratings identified during project design have not changed and are still valid. A risk register and risk management matrix was produced as part of FMT technical proposal Key risks and triggers identified are : / Fund resources: / GoR unwilling to provide additional funds given other priorities / Donors are not willing/able to provide additional support / GoR reduces support to the Fund as donor/other contributions increase / Results: / Sectors lack capacity, project proposals are weak and do not respond to FONERWA requirements for funding / Call down consultants schedules conflict with FMT planning. / Inappropriate timing of capacity building training sessions. / Pressure to spend DFID resources in order to secure future disbursements; / Political pressure to support particular projects / Project screening processes not followed / Resources spread too thinly across funding windows to have a meaningful transformational effect (Donors earmark funding for particular ‘windows’; Challenge of harmonising monitoring and evaluation systems as well as streamlining funding conditionality) / Fund supports proposals with negative Climate &Environment (C&E) impacts / Insufficient interest from private sector (Enabling environment is discouraging to investors; Insufficient investment opportunities) / Fund management / Design of fund rules out certain approaches / Lack/low levels of the in country technical capacities to develop financing mechanism to support private sector access to funds / Once trained, local staff move on or Losing critical staff at crucial point of the project / Pressures on implementation capacity are expected to intensify. The impact of not having sufficient funds was realised during this first year, causing significant delays in operationalization of the fund. This remains an active risk. While provision of financing (£22.5m) from the UK and revenue transferred from Rwanda environmental funds, fees & fines has enabled application initiation, ensuring Fund has sufficient resources to meet demand but also delivers transformational and effective action on the ground will be crucial to success.
Risk of funds not being used as intended / Low risk with respect to fraud and corruption. Payment to CIDT/FMT is made quarterly against achievement of verified progress deliverables (i.e. in arrears). / CIDT/FMT has robust procurement and reporting processes as well as dedicated staff in place to ensure best value for money. Audited annual statements are awaited, but there is no reason to suspect any problems. Separate records and accounts are maintained for the project and a financial report is produced every three months. / For the Fund as a whole, monitoring, reporting and accounting for spend will be the responsibility of the Fund manager, following Government of Rwanda rules and procedures. The Secretariat will produce the accounts and financial reports which will be reviewed by the Steering Committee and audited by the Office of the Auditor General on an annual basis. / 4.4 Climate and Environment Risk / This is a climate change and environment project, focussed on reducing the risks of climate change, helping countries adapt and improve local, national and regional planning as well as move towards low carbon development options. / The largest risk around project management is on travel (air miles), which is relatively low as all key staff is based in Rwanda. Options for carbon-offsetting can be explored.

5. Value for Money
5.1 Performance on VfM measures / The secretariat and all outreach activities have included a value for money training segment. A fund VFM reporting template has been generated and while generic at this stage, will be refined as funded projects generate their own VfM indicators. / In the business case the following VfM measures were agreed: / VfM measures / Economy Operational cost per proposal considered by the Steering Committee / Effectiveness Additional donor finance mobilised / Government of Rwanda finance mobilised / Private sector finance leveraged / Number of poor people made more resilient to future climate impacts / Number of additional households with energy access / Efficiency Net Present Value / Benefit Cost Ratio / VfM gains from one co-ordinating mechanism, the balance in the portfolio and economies of scale should become more obvious as project are approved and implemented picks up pace. Other outputs of the programme, particularly those related to capacity building will be appraised though the results based monitoring and evaluation framework. / Due diligence, good practice procurement procedures and frequent monitoring remain crucial to ensuring VfM for our inputs. To date, Fund Management and Technical committee meetings have not been held, but DFID will be represented on both committees to help ensure meet our impact requirements. / 5.2 Commercial Improvement and Value for Money / Procurement of the CIDT led Fonerwa fund management team support services was through competitive open tendering according to DFID and Official Journal of the European Union (OJEU) procedures. Selection was based on commercial criteria (e.g. competitiveness of fee rates, a clear financial plan and consideration of financial risks etc.) as well as quality and past performance in order to ensure that optimum value for money was obtained. / 5.3 Role of project partners / CDKN are currently the only other development partner and we have a joint support programme for the capacity development elements of the Fund. CDKN resources provide additional coaching and mentoring support to district and provincial stakeholders for proposal and project development. / 5.4 Does the project still represent Value for Money : Yes

6. Conditionality
6.1 Update on specific conditions: None

7. Conclusions and actions
The project has recently begun to scale up its activities with respect to project proposal identification and support ahead of the first application round next month. Despite the significant delay in securing expected fund finances, it has shown results so far with integration of FONERWA in EDPRS2, a strong project pipeline interest, a fund secretariat fully made up of locally trained technical staff and securing and setting up procedures for local revenue collection from environmental related fines. There is strong interest in building climate change resilience at national level and we expect progress to continue and accelerate. It is also likely that other donors will join in following demonstration of effectiveness and need and funding proposals submitted to global adaptation and low carbon funds are looking optimistic. / Whilst no changes are recommended to the substance of the programme, some adjustments may be needed to the milestones to reflect a slower than expected start. This should be assessed following results of the first call. An overall no cost extension may also be needed if there is an underspend in allocated support for the fund management team. Future annual reviews should be harmonised with those conducted for the Provision of UK Finance to the National Fund (Aries project #: 203582) in August, as they are closely interconnected and share results. / Project management by CIDT has been good, although revision of the private sector targeting strategy is urgently needed as well as resolution of identification of implementing partner/s for the private sector components. Governance arrangements through the Fund Management and Technical Committees will be critical and ensuring they conduct their roles effectively and ensure value for money is essential for success. / Boosting and accelerating the capacity development plan where it has been delayed is now urgent to ensure proper targeting and development of strong proposals across the windows of the fund. Additional sector trainers and their development is needed to meet expected demand. Local secretariat members would also benefit from an individually tailored on the job training/mentoring and competence development plan. Training and technical support evaluation mechanisms are also important to ensure effectively addressing demands and needs. / Activities will move now from fund ‘establishment’ to ‘operationalization’ activities and bulk of the FMT support services provided in this project. This includes strengthening fund management, initiating quarterly application rounds; outreach in the form of communication and awareness raising; capacity building; additional resource mobilisation and reviews to ensure delivery of results. / Recommendations from this review are to be tracked in an action plan and included in the quarterly progress reports.

8. Review Process
The review was conducted by the DFID Rwanda Climate Change Adviser and the DFID Rwanda programme officer over the period 4-10 July, 2013. It was informed by quarterly reports from CIDT, discussion with FMT and secretariat members as well as some beneficiaries of the fund orientation workshops.