Type of Review: Annual Review

Project Title:	State Partnership for Accountability, Responsiveness	and Capability (SPARC)

Date started: August 2008
Review undertaken: January 2013
ARIES Report submitted: February 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Acronyms and Abbreviations

BC & CoA	Budget Classification and Chart of Accounts
BEMST	Bureau of Establishments, Management Services and Training
CBA	Cost Benefit Analysis
CBO	Community Based Organisation
CGS	Conditional Grants Scheme
CMS	Content Management System (of the NGF)
CSO	Civil Society Organisations
CSP	Civil Service Performance
DSA	Daily Subsistence Allowance
DFID	Department for International Development
EnSG	Enugu State Government
ESEPC	Enugu State Economic Planning Commission
ESSPIN	Education Sector Support Programme
ExCo	Executive Committee (of State Government)
FCT	Federal Capital Territory
FGN	Federal Government of Nigeria
G&SI	Gender and Social Inclusion
GEMS	Growth and Employment in States Programme
GSDRC	Governance & Social Development Resource Centre (DFID)
HMG	Her Majesty’s Government (UK)
HoS	Head of Service
HR	Human Resources
HRM	Human Resource Management
IMEP	Independent Monitoring and Evaluation Programme
LASG	Lagos State Government
LG	Local Government
LGA	Local Government Area
MDAs	Ministries, Departments and Agencies
MDG	Millennium Development Goal
MDGs CGS	Millennium Development Goals Conditional Grant Scheme
M&E	Monitoring and Evaluation
MoBP	Ministry of Budget and Planning
MoH	Ministry of Health
MTSS	Medium-Term Sector Strategy
NGF	Nigeria Governors Forum
NGO	Non-Governmental Organisation
OoT	Office of Transformation (Lagos State)
OSSAP	Office of the Senior Special Assistant to the President
P&S	Policy and Strategy
PATHS2	Partnership for Transforming Health Systems Phase 2 Programme
PDG & STL	Programme Development Group & State Team Leaders (SPARC)
PE	Political Economy
PEA	Political Economy Analysis
PEFA	Public Expenditure and Financial Accountability
PFM	Public Finance Management
PSM	Public Service Management
PSR	Public Sector Reform
SAVI	State Accountability and Voice Initiative Programme
SDP	State Development Plan
SEAT	State Evaluation and Assessment Tool
SG	State Government
SHoA	State House of Assembly
SLP	State Level Programme
SPARC	State Partnership for Accountability, Responsiveness and Capability Programme
SPoA	State Plan of Action
SPRM	State Peer Review Mechanism
SSAR	State Self Assessment Report
TA	Technical Assistance
ToC	Theory of Change
ToR	Terms of Reference
UNDP	United Nations Development Programme
UNECA	United Nations Economic Commission for Africa
VFM	Value for Money
WB	World Bank

## Introduction and Context

What support is the UK providing?
How much funding does the UK expect to provide? / Ministers originally approved the State Partnership for Accountability, Responsiveness and Capability (SPARC) in 2007 as a £45.9m programme, as part of the joint approval of a suite of State Level Programmes (SLPs) for Nigeria’s federal system of governance. This was increased in November 2012 by an additional amount of £14.5 million to total funding of £60.4m by the Secretary of State following a Business Case presented by DFID Nigeria (DFID N) in November 2012 to scale up SPARC’s focus from the original five to 10 focal states, with four additional states in the North (Katsina, Niger, Yobe & Zamfara) and one in the South East (Anambra). / Period of funding / Four years (2012-2015). This constitutes a year’s extension to a programme that began in 2008. / What’s the broader context for this support? / SPARC is integral to DFID’s Operational Plan for Nigeria, which has an over-arching aim of assisting Nigerian governments (National and State Public Administrations) to improve the way they use their own resources for the benefit of citizens. With its ‘good governance’ focus on improved Public Service Management (PSM) and Public Finance Management (PFM), SPARC sits at the hub of a suite of SLPs designed to collectively increase the efficiency and effectiveness of utilisation of Nigeria’s resources to achieve the Millennium Development Goals (MDGs) through leveraging improved pro-poor service delivery. The other SLPs are: / State Accountability and Voice Initiative (SAVI) / Education Sector Support Programme in Nigeria (ESSPIN) / Partnership for Transforming Health Systems Phase 2 (PATHS 2) / Growth and Employment in States (GEMS). / Within this framework, SPARC’s objective is to help improve state-level planning, policy and strategy formulation; M&E; PFM and civil service performance (CSP) by providing technical assistance (TA) to selected focal state governments.

What are the expected results?
The impact (goal) of the intervention is expected to be “Nigeria’s own resources used efficiently and effectively to achieve the MDGs”. / The programmes outcome (purpose) is “the efficiency and effectiveness of selected state governments’ use of public resources is enhanced”. / The programme logframe specifies four outputs: / Output 1: Policy and Strategy (P&S) development, monitoring and evaluation (M&E) improved. / Output 2: State PFM improved. / Output 3: State CSP improved. / Output 4: Federal support to state governance improved. / Detailed milestones for the impact, outcome and outputs are defined in State specific SPARC logframes (dated 17th July 2012) and synthesised in the overall Programme logframe (dated 25th July 2012).

What is the context in which UK support is provided?
What need are we trying to address? / Nigeria is a large and diverse Federation. Of Nigeria’s 158 million people, 64% live in poverty[1]. The federation consists of 36 states plus the Federal Capital Territory (FCT) of Abuja, an arrangement often referred to as 36+1. The 36 states are regionally organised into 6 geo-political zones: / South East Enugu, Anambra, Abia, Ebonyi and Imo / South-South Akwa-Ibom, Bayelsa, Cross-River, Delta, Edo and Rivers / South -West Lagos, Ekiti, Ogun, Ondo, Osun and Oyo / North Central Niger, Benue, Kogi, Kwara, Nassarawa, Plateau and F.C.T / North East Yobe, Adamawa, Bauchi, Borno, Gombe and Taraba / North West Jigawa, Kaduna, Kano, Katsina, Zamfara, Kebbi and Sokoto / Key Bold letters – original 5 SPARC focal states since 2008 / Bold italics – new SPARC states from 2012 / Despite oil revenues, Nigeria’s human development indicators are worse than in comparable lower middle-income countries[2]. The World Bank’s (WB) World Wide Governance Indicators place Nigeria below the 25th percentile on political stability, government effectiveness, regulatory quality, rule of law and control of corruption, and in the second lowest quartile for voice and accountability[3]. These symptoms point to a range of conditions – political history & political economy, patronage politics, weak institutional systems, unequal wealth and income distribution, ineffective use of government revenues - which are seen as underlying reasons for the instability and violent conflict that Nigeria is currently experiencing, particularly in the North of the country.[4] / In Nigeria’s federal system, effective public management at state level is essential for improved service delivery and poverty reduction. State and local government spending comprises around 50% of total government spending, with Ministries, Departments and Agencies (MDAs) of state governments responsible for delivery of core public services such as basic healthcare and primary education. However, state government is often ineffective with the situation in many - if not most - states characterised by: / Absent or poor evidence-based policy and planning, and rudimentary (if at all) M&E systems. / Weak PFM systems for planning and budgeting, cash management, internal and external audit, and procurement. / A poor, unresponsive public service culture, with weak Human Resource Management (HRM) and Performance Management (PM) systems. / Limited oversight or accountability, internally and externally by the Federal Government, State Houses of Assembly (SHoA), civil society and media. / How will SPARC address these problems? / SPARC partners with state governments institutions to tackle the problems identified above, by focusing on improving: P&S, PFM, CSP and Federal support to state governance[5]. It’s approach is defined by: / A public policy premise that posits a link between stronger institutions, in particular with good budget management, and improvements in service delivery outcomes. This is supported by empirical research from developing countries published by the WB and DFID’s GSDRC[6]. / TA rather that grants or budget support. Given the fiduciary risks, SPARC is implemented through TA rather than provision of money to state governments. / State specific approach; partnership & decentralisation: SPARC TA works closely with partner institutions through the project cycle, from problem-identification to systems-reform, to identify conditions conducive for reform and VFM taking into account: the political economy of the state, current institutional environment and receptivity to reform, leadership commitment to reform. / Evidence from the first 3 years of SPARC’s operation (2008-2011) appears to confirm, that together with other DFID interventions, it has made progress in helping partner State ministries better analyse and plan the use of State resources, leading to improved service delivery, notably in health and education.[7] SPARC was originally intended to work in 5 states, Enugu, Jigawa, Kaduna, Kano and Lagos, and then expand into a further 2 to-be-determined states. Instead, in 2011, the project was expanded by a further 3 states: Katsina, Yobe and Zamfara, in line with DFID's Vision for Nigeria 2011-2015, which saw an expansion of DFID’s programme in northern Nigeria. SPARC was asked to respond to this vision by expanding its programme to cover a total of 10 states from its fifth year onwards (2012/13), incorporating a further 2 states, Anambra and Niger. This expansion was based on the following assumptions: / The thrust of DFID N’s Operational Plan is to expand DFID work in northern Nigeria where poverty rates are the highest. Given SPARC’s pivotal institutional position in facilitating state-wide governance reforms, it was felt that the project could usefully complement other DFID sectoral investments, particularly in health (PATHS 2) and education (ESSPIN) aimed at improving MDGs in the North. / The possibility of expanding SPARC influence nationally by consolidating the relationships with the Nigeria Governors Forum (NGF) and MDG office, thereby transmitting useful governance reform lessons, and affecting positive change by diffusion across the country. / Extending the programme for an additional year to 2015 to enable reforms to be more fully embedded, particularly in the new states. / The possibility of replicating SPARC’s success in delivering governance reforms with good VFM. In the mid-term review in 2012 SPARC achieved an A+, with the reviewers suggesting that on one component alone (PFM), it helped states to save £68m. / SPARC produced a Consolidation and Expansion Strategy in 2012. This strategy is based on a technical and institutional capacity assessment of 10 states, divided into three categories based on the 'readiness for reform’: / Approach Type A (Jigawa & Lagos): 'Going with the Grain'. Appropriate for states that have a track record of delivering governance reforms and require targeted TA to supplement and enhance their own plans. / Approach Type B (Enugu, Kaduna, Kano, Yobe): 'Consolidation Approach’. This is the original SPARC incremental change model, with TA provided in steps on the evidence of achieving previously planned institutional reforms. This approach has been found useful for states where there is already some reform experience, and an understanding of the need for systematic cross-government reforms. / Approach Type C (Anambra, Katsina, Niger, Zamfara): 'Building Foundations' - States in which, although there may be limited experience of undertaking governance reform, there are some instances of reform initiatives and opportunities on which to build, which can be enshrined in a negotiated intervention plan.
[1] The poverty rate is higher in Northern Nigeria at 77%, one of the main reasons for DFID’s increased emphasis on that part of the country.
[2] UNDP (2011) Human Development Index 2011. http://hdrstats.undp.org/en/countries/profiles/NGA.html
[3] World Bank Nigeria Governance Approach FY12-FY16
[4] Aigbokhan, Ben. E (2008) Growth, Inequality and Poverty in Nigeria, Prepared for the United Nations Economic Commission for Africa (UNECA), Addis Ababa, Ethiopia.
[5] The original design of SPARC envisaged strengthening state level civil society and SHoAs, but this was subsequently hived off to constitute a distinct programme: State Accountability and Voice Initiative (SAVI) within the broad portfolio of SLPs.
[6] See for example: World Bank (2003). “Making services work for poor people”, World Bank Development Report 2003. World Bank, Washington DC & World Bank (2007) Strengthening World Bank Group Engagement on Governance and Anticorruption, World Bank, Washington DC. D. Kaufmann, A. Kraay, and P. Zoido-Lobaton, “Governance Matters”, Policy Research Working Paper No 2195. Washington D.C.: The World Bank, October 1999; Peter Evans and J. E. Rauch, “Bureaucracy and Growth: A Cross-National Analysis of the Effects of ‘Weberian’ State Structures on Economic Growth” American Sociological Review, Vol. 64, No 5 (October 1999), pp 748-765; and, Peter Evans and J.E. Rauch, “Bureaucratic Structure and Bureaucratic Performance in Less Developed Countries”, Journal of Public Economics, vol. 75 (January 2000), pp. 49-71. Earle, L. et al., (2010), Assessing the Evidence of the Impact of Governance on Development Outcomes and Poverty Reduction, Emerging Issues Research Service, GSDRC.
[7] We note that there is also an argument that improvements could be due to the ‘Hawthorne Effect’, which holds that there is a tendency of some people to work harder and perform better due to the attention they are receiving from researchers / observers / trainers rather than because of any other factor or the manipulation of independent variables.

## Section A: Detailed Output Scoring

The scoring below is based on guidance provided by DFID to assess SPARC’s performance on the basis of:

- A desk review of reports from SPARC.
- Two state visits (to Lagos and Enugu, in that order) and discussions with stakeholders, in these states and at the federal level.
Notwithstanding the methodological weaknesses inherent in this weakly-triangulated, ‘light touch’ approach prescribed by the ToR – with a heavy reliance on material provided by the subject of the appraisal – the reports provided by SPARC that we examined, and validated with external stakeholders, were invariably accurate and reliable. This provides us with the necessary degree of confidence to score ARIES in line with the requirements of the ToR.

Output 1: Appropriate state policies and strategies adopted, monitored and evaluated
Output 1 Score and Performance Description: Score: A++ (outputs substantially exceeded expectation) / As specified in the TORs, only output indicators 1.2 and 1.4 have been considered. / Development of Plans, Policies and Strategies: Progress has been made in preparing State Development Plans (SDP), particularly in Jigawa, Enugu and Lagos. Out of 8 good quality policy content standards, the Jigawa Comprehensive Development Framework (CDF), Enugu Vision 2020 Medium-Term Implementation Plan (ENVMTIP) and Lagos SDP meet 7, 6 and 5 respectively. / Across the 5 original SPARC states the number of sectors with an MTSS has expanded in recent years to 2 in Kano, 3 in Kaduna, 4 in Jigawa, 7 in Enugu and 25 in Lagos. We found no evidence of ‘organic diffusion’ of the MTSS process. Only in Lagos has the MTSS process been wholly internalised by the State government, with the rollout across MDAs not dependent on SPARC support (or at the least prompting). / The quality of the MTSSs done by states and facilitated by SPARC is gradually improving. With the key sectors of education and health sectors as indicators (which also provide an indication of SLP coordination), on average the MTSSs produced in 2012-15 in these sectors met 60% of good quality strategy content standards, compared to 50% for first generation MTSSs. / Findings from field visit of potential general application / Stakeholders interviewed spoke of no inconsistency in the approaches to MTSS taken by SPARC and the other relevant DFID programme (whether ESSPIN or PATHS 2). This is a welcome and positive change on the issue of SLP coordination and harmonization (cf. findings of the SLP inception review in 2009). / SPARC’s approach to MTSS and planning processes emphasized ownership by State’s own institutions: the Ministry for Economic Planning and Budget (MEPB) in Lagos; and ESEPC and MOBP in Enugu. Stakeholders confirmed that SPARC had worked with and strengthened state planning instruments & schedules, and policy guidelines. / Where there were internal tensions in the MTSS processes e.g. as reported by the Ministry of Health (MOH) in Enugu, this arose from the need for state plans to align with national health sector plans as laid out by the Federal MOH. However, this structural tension between horizontal state level planning and vertical sector planning was accepted as being within the margins of tolerance of the MDAs concerned. / Strengthening the Monitoring and Evaluation of Plans: Good progress in supporting sector partners to conduct performance reviews of MTSS implementation. Annual sector performance review guidelines have been provided to all MTSS sectors (and in some cases others) alongside training in their use in Enugu, Lagos, Jigawa and Kaduna. Some states have made earlier than anticipated progress in institutionalising responsibilities for leading this process, including Lagos and Enugu. However, strengthening of the M&E functions of state governments and individual ministries, and fully integrating this function into the development planning and budget execution process is not without challenges. We note two challenges endemic across government: / The link between the political executive and the technical planning & budgeting function, so as to decide on resource utilization on the basis of dynamic, substantive information, remains weak across all focal states. Essentially, development priorities – especially expenditure on capital projects - are a prerogative of the Political Executive. We saw no evidence of these Executive decisions being informed by systematic and comparative use of detailed M&E data. Even intra-sectoral policy prioritization is generally weak, with rare examples of M&E shaping policy[8]. / Effective M&E requires electronic data storage and data processing equipment. The MDAs we visited spoke of the need not just for training but also for computer equipment. The impression we formed was of M&E functions that were perfunctory appendages to MDA structures, rather than a critical knowledge-management resource in shaping policy and resource allocation. As such these units were unlikely to be early recipients of computer equipment from within government.
PROGRESS AGAINST EXPECTED RESULTS / Indicator 1.2: Quality and comprehensiveness of policies and strategies. / Type 2013 Milestones Actual Progress / A / Jigawa, Lagos In all states: / The SDP meets 30% of good quality content standards. / MTSSs in priority sectors (depending on the State) meet 30% of content quality standards. The approved SDP in Jigawa meets 86% of content quality standards whilst the draft SDP in Lagos meets 71%. / In both Jigawa and Lagos, all priority sectors have MTSSs and a sample analysis shows that all current MTSSs meet at least 30% of content quality standards. / B / Enugu, Kaduna, Kano, Yobe In at least one state: / The SDP meets 30% of good quality content standards. / MTSSs in priority sectors (depending on the State) meet 30% of content quality standards. The approved SDP in Enugu meets 75% of content quality standards. / In both Enugu and Kaduna, all priority sectors have MTSSs and a sample analysis shows that all current MTSSs meet at least 30% of content quality standards. / C / Anambra, Katsina, Niger, Zamfara In at least two states: The strategy/plan in at least one sector is consistent with at least 30% of Strategy content standards. The Health Sector Plan in Katsina meets 40% of strategy content standards. / Indicator 1.4: Extent to which performance management processes are being used. / Type 2013 Milestones Actual Progress / A / Jigawa & Lagos In all states: The central planning agency has the capacity to support sectors in implementing annual sector performance reviews that incorporate a Gender & Social Inclusion (G&SI) focus. In both Jigawa and Lagos, the central planning body has provided support to sectors in implementing sector performance reviews. Capacity for supporting sectors is more institutionalized in Lagos where MEPB has provided training to all sectors (including a focus on G&SI) and has established a technical working group to provide sustained support to sectors. / B / Enugu, Kaduna, Kano, Yobe In at least one state: The central planning agency has the capacity to support sectors in implementing annual sector performance reviews, which incorporate a G&SI focus. In Enugu and Kaduna, the central planning body has provided support to sectors in implementing sector performance reviews. Capacity for supporting sectors is more institutionalized in Enugu where ESEPC has provided recent training to all priority sectors (including a focus on G&SI). / C / Anambra, Katsina, Niger, Zamfara No milestones planned. N/A / Summary and Scoring[9] / On the basis of data in the SPARC progress reports (validated in part by our field visit) the results are as follows: For Type A and a Type C states, results have substantially exceeded expectations. For Type B states, the results have moderately exceeded expectations. / Type A (81%) Type B (75%) Type C (100%) / Jigawa Lagos Enugu Kaduna Kano Yobe Katsina Zamfara / 63% 100% 75% 25% 25% 50% 100% 0% / Notes: / 1. Average milestone achievement figures for each Type of Approach are calculated based on the target number of states for each approach (e.g. two for Type A, one for Type B and two for Type C). / 2. Anambra and Niger (Type C approach) are not included since inception work is being completed and they do not yet have logframes. Therefore, the milestone target of two out of four states with a Type C approach is being interpreted as 50% and is being applied to Katsina and Zamfara only at this stage. / Recommendations: / Training is a key and much-valued element of SPARC’s approach to capacity building and institutionalising PSM and PFM systems and processes (MTSS contains aspects of both). Our interviews with stakeholders suggested that there would be value in SPARC taking a closer look at training methodologies to identify which training approaches (action learning, workshops, on the job support, longer term embedded trainers / consultants etc.) contribute best to sustainable institutional learning. / Wholly government-led planning appears to have occurred only in Lagos. Thus ‘organic diffusion’ of policy planning and M&E processes is unlikely across MDAs in the other 9 focal states, and in other non-focal States. This assumption needs to be reviewed, so that P&S and M&E are not only successfully institutionalised in the DFID-SLP supported parts of government. Consideration should be given to deepening and broadening the capacity building partnership with more MDAs over a longer term, so that a critical mass of government routinely does business in this way, thus demanding the same from non-compliant MDAs. / Use SDP and MTSS development or annual adjustment exercises to explicitly review against quality standards (including those related to financial feasibility and alignment) and use the results to identify areas of improvement required. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N
[8] A notable exception was the case from Enugu where the MOE’s M&E system had generated data revealing that secondary school drop out rates are higher for boys than girls. As a result of this finding the Ministry is tackling the growing problem of male youth unemployment through increased provision for vocational training.
[9] We assume that this assessment is made at the midway point between the 2011 baseline and 2013 milestones in the logframe. Thus a performance of 50% of 2013 milestones achieved is used as the benchmark for expectations.

Output 2: State Public Financial Management Improved
Output 2 score and performance description: Score: A+ (outputs moderately exceeded expectation) / SPARC report progress in strengthening the budget preparation process, particularly in Lagos and Kaduna, including the use of medium-term revenue forecasts to develop ceilings, breaking these down by sectors and communicating them through the budget call circular in a timely fashion according to a fixed budget calendar. (Confirmed directly in Lagos.) In addition to this technical support, SPARC state teams are increasingly engaging at the political level, including in collaboration with SAVI, to minimise the tendency for politicians in some states to increase budget allocations without reference to revenue forecasts. (See page 8, pt. 1 under ‘Challenges’). The result is a mixed picture with more positive elements than negative, which says more about the internal political conditions in focal states, and the readiness to embrace governance reforms, than it does about the TA. / Budget realism has been entrenched in Jigawa, and to a degree in Lagos. / Significant improvement in realism is reported in Zamfara and Niger, and marginal improvement in Katsina. / Enugu and Yobe remain in a similar position as before with a reasonable level of credibility. / There has been disappointing deterioration in Kano and Kaduna, and particularly Anambra. / The lack of traction in Kano and Kaduna can justifiably be attributed to external political conditions: in Kano a new administration has sought to do things its own way with particular disregard for reforms embraced by the previous administration. In Kaduna – on the frontline between the North and the South – an inflated budget probably reflects the need to camouflage and contain structural ethno-religious-political conflicts. / Type 2013 Milestones Actual Progress / A / Jigawa & Lagos In all states: Approved 2014-2016 budget has been developed using medium-term revenue forecasts. The Lagos State Government 2013-2015 Medium-Term Budget Framework (MTBF) was developed using medium-term revenue forecasts and the draft 2013 budget is broadly consistent with this framework with a variance of around 15% against forecasts. / B / Enugu, Kaduna, Kano, Yobe In at least one state: Annual call circulars prepared which include aggregate and sector ceilings derived from a realistic Revenue Model. An annual call circular for the 2013 budget process has been prepared in all Type B states. Apart from Kano, these call circulars are prepared on a multi-year basis using a revenue forecasting model and include aggregate and sector ceilings. / C / Anambra, Katsina, Niger, Zamfara In at least two states: / A fixed budget calendar is used to guide the 2014-2016 budget process / The Budget Call Circular includes sector ceilings based on realistic revenue forecasts. In both Katsina and Zamfara a fixed budget calendar is being used for the 2013 budget process and whilst 2013 budget call circulars have been prepared, these have not been based on revenue forecasts and do not include sector ceilings. / SPARC has not been engaged in Anambra long enough to be held accountable for the milestones, but it should be fair to judge its contribution to PFM from 2013. The engagement on budget realism will present an unusual and new challenge. Anambra has a politically turbulent history, and as is typically the case in such conditions expenditure decisions rest with the Governor, with the civil service generally bypassed. Curiously, the pre-SPARC profile of the state reveals an interesting picture with a budget actually ‘realistic’ (by Nigerian standards) from a revenue perspective: performance in 2010 and 2011 was 107% and 129% respectively. Ironically, the state has struggled with budget execution, with SPARC background data reflecting execution at 57% and 65% for 2010 and 2011. In theory this would suggest that the state has built up large reserves / surpluses. If confirmed through closer examination by SPARC, this would present a fresh challenge to the programme: budget realism that requires faster and increased expenditure, alongside strengthened expenditure control.
Progress against expected results / Indicator 2.1: Extent to which the budget is credible and policy based. / Indicator 2.4: Quality of accounting, recording and reporting. / Type 2013 Milestones Actual Progress / A / Jigawa & Lagos In all states: Improvements for budget performance reporting formats prepared (actual + commitments against budget). In Lagos, improvements to reporting formats have been proposed and documented, but not yet accepted. SPARC has assisted the MEPB in developing a more robust Quarterly Budget Performance Reporting template, which captures actual performances along sectoral and programme basis. / B / Enugu, Kaduna, Kano, Yobe In at least one state: A Final Accounts Procedures Manual prepared and accounts staff trained. In Kano, an updated Bank Reconciliation model has been implemented, alongside documented procedures and staff training, and has resulted in significant reductions in the time and difficulty of synchronizing MDA returns into the IFMIS. / C / Anambra, Katsina, Niger, Zamfara In at least two states: Proposed formats for budget monitoring and reporting are presented to State Government. In Katsina, budget monitoring and report formats and processes have been prepared and presented to State Government. / Findings from field visit of potential general application / The validation visits to Lagos and Enugu raised a number of issues which are worth noting as a reflection of SPARC’s performance and implications across the programme: / Building PFM systems and a culture of professionalism. When asked for examples of SPARC’s contribution to improved governance systems for their state, both Lagos and Enugu stressed the value of SPARC support in producing the following instruments: / Lagos Enugu / PFM Act / Procurement Act / Audit Act / Chart of Accounts / Budget Calendar Internal Audit Manual / Budget Codes & Chart of Accounts / Internal Control Manual / Procurement Manual / Debt Management Policy & Manual / Draft Audit Law / While the full, tangible, downstream benefits of these instruments remains to be seen they have solidified a culture of professionalization, substantively grounded in laws and technical standards, offering a compelling template for systematising good governance in all 10 focal states. / Indirect benefits: inclusion of Local Government Audit Staff. In Enugu training of State Audit Department staff undertaken by SPARC, was broadened to include Local Government (LG) audit staff. This was done at the initiative of the State government. Reportedly, this has resulted in an improvement in the financial management systems of local governments overseen by these LG Auditors. In which case at a marginal cost SPARC’s contribution has gone beyond the state level and positively impacted on local government. / Training and capacity building through sequenced inputs by embedded consultants. When asked to critique the modality of training that has proved most effective in building institutional capacity, respondents invariably pointed to training provided through sequenced inputs by consultants in a long-term relationship with the host MDA. This has implications for work in the northern states where security is a matter of concern. / Prioritization within PFM components. One of the inevitable consequences of drilled-down state level log-frames is that these have reduced to some extent the room for flexibility and responsiveness. This is ironic given that these qualities are among the key internationally acknowledged strengths of DFID’s work. Stakeholders in Lagos spoke of the need for greater flexibility to re-order the interventions within the PFM work-stream so that the project could ‘ride the waves’ better. In the case of Lagos this might have involved going further with the work on procurement, where there was an appetite and urgent need for the training of the full cadre of procurement officers (located across MDAs). No provision exists in the budget for such an opportunity. Yet the downstream benefits of such an initiative could be significant. / Summary and Scoring / Against a 2011 baseline and 2013 milestones, this assessment is made at the halfway point and, on an arithmetical basis a performance of 50% of 2013 milestones achieved is used as the benchmark for expectations. As required by the TORs, only output indicators 2.1 and 2.4 have been considered in this analysis. / For states with a Type B approach, results have substantially exceeded expectations, for states with a Type C approach, results have moderately exceeded expectations and for states with a Type A approach, results moderately did not meet expectations. / Type A (31%) Type B (100%) Type C (63%) / Jigawa Lagos Enugu Kaduna Kano Yobe Katsina Zamfara / 0% 63% 35% 100% 50% 75% 63% 0% / Notes / 1. Average milestone achievement figures for each Type of Approach are calculated based on the target number of states for each approach (e.g. two for Type A, one for Type B and two for Type C). / 2. Anambra and Niger (Type C approach) are not included since inception work is being completed and they do not yet have logframes. Therefore, the milestone target of two out of four states with a Type C approach is being interpreted as 50% and is being applied to Katsina and Zamfara only at this stage. / Recommendations: / Use Joint review meetings with the State to re-prioritise PFM work / Where the additional costs are marginal, consider replicating the model of drawing in relevant local government PFM staff (such as LG audit staff) into training provided to state PFM cadres. / SPARC should facilitate broader political engagement around 2014 budget preparation in order to help ensure 2014 budgets are as credible as possible, in addition to its core technical work, including through: a) advocacy and sensitization through the NGF, b) advocacy and accountability by Civil Society, in partnership with SAVI, and c) sustained dialogue on budget credibility issues by DFID representatives. / Impact Weighting (%): 40% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: State Civil Service Performance Improved
Output 3 score and performance description: Score: A (outputs met expectations) / This is the component with the weakest results, illustrating the fact that improvements in civil service performance that require structural Public Sector Reforms (PSR) are immensely contentious, given their direct impact on employees across the entire public service. Nonetheless, in both the states we visited (Lagos and Enugu), and reportedly in all other states (according to SPARC reports), State Government has demonstrated a clear interest in drawing in SPARC assistance to improve public service performance in two areas: / Mandates / functional reviews & corporate planning: Good progress has been made in clarifying MDA mandates and implementing Corporate Planning approaches in priority central MDAs. All five original states have reached the point where MDAs are beginning to realign structures, functions and objectives. However, the extent to which this is completed and the civil service restructured to align with clarified functions will depend on the level of commitment by the Political Executive. / Service charters: Progress has been made in the introduction of service charters (particularly in Enugu and Lagos) and performance management approaches (particularly in Lagos and Kaduna). The stage of implementation of these processes varies between states, reflecting the fact that initiatives were developed in one state and then adopted in others. / Progress against expected results / Indicator 3.1: Clarity and appropriateness of public service organisation and operational management. / Type 2013 Milestones Actual Progress / A / Jigawa, Lagos In all states: / A process for rationalising mandates is in place / Selected central MDAs (depending on the state) have completed the first phase of corporate plan implementation. In Lagos, SPARC has supported the Office of Transformation to develop plans for the review and update of mandates every 3-5 years and these have been submitted in ExCo for approval. In Jigawa, guidelines for the review of mandates have been prepared and submitted to the PSM Core Group for review. / In Jigawa, 2 of the 4 targeted central MDAs have realigned 50% of functions and departmental objectives. In Lagos, work has just commenced on realigning functions and departmental objectives in 2 of the 6 targeted central MDAs. / B / Enugu, Kaduna, Kano, Yobe In at least one state: / A system and guidelines to support the publication and review of mandates has been developed / A system and guidelines to support the roll out of Corporate Planning to other MDAs is being used. Kaduna has commenced work on developing guidelines for the publication and review of mandates and the Bureau of Establishments, Management Services and Training (BEMST) has been identified as the responsible unit. / Also in Kaduna, the Corporate Planning committee has developed plans for the roll out of Corporate Planning across government using updated Corporate Planning guidelines. / C / Anambra, Katsina, Niger, Zamfara In at least two states: Corporate improvement plan developed for the Central Planning Agency. In Katsina, the Steering Committee and Technical Committee on Corporate Planning has been inaugurated and the first stage of corporate planning (review of mandates, vision, mission, objectives) has been concluded. In Zamfara, goals and strategies of MoBEP have been reviewed and an action plan for developing a corporate improvement plan has been prepared. / Indicator 3.4: Extent to which MDA performance management policies and procedures are in place. / Type 2013 Milestones Actual Progress / A / Jigawa & Lagos In all states: / A relevant unit has been identified and has the capacity to support MDAs to prepare service charters / Selected MDAs (depending on the State) have developed G&SI-sensitive service charters with performance statements / Performance Management model agreed. In Jigawa, a service charter committee has been established and placed under the supervision of a Service Charter Unit within Office of the Secretary to the State Government and a draft service charter has been prepared for the Office of the Head of Service (HoS). / In Lagos, the Office of Transformation (OoT) is the unit responsible for supporting MDAs to develop service charters. / All 12 pilot MDAs have now published service charters that contain performance statements. The OoT is currently conducting an assessment to review the impact of these charters on service delivery improvement. The performance management model being adopted in Lagos consists of performance agreements between the Governor and Commissioners. Draft agreements have been prepared for the first phase of Commissioners (within 5 MDAs) and are awaiting formal submission to the Governor. / B / Enugu, Kaduna, Kano, Yobe In at least one state: / A relevant unit has been identified and has the capacity to support MDAs to prepare service charters / Selected central and priority MTSS sector MDAs (depending on the State) have developed service charters with performance statements. In Kaduna, a service charter concept paper for has been developed, consulted and agreed upon. It has been generally adopted by the HoS and other PSs as the format/standard for MDA service charter preparation for the State and will be used in two pilot MDAs. / In Enugu, the SERVICOM office has the responsibility for supporting MDAs with the preparation of service charters and has Ministerial Service Charter Units across the MDAs with permanent staff. Service charter exists for six of the seven pilot MDAs. / C / Anambra, Katsina, Niger, Zamfara No milestones planned. / Findings from field visit of potential general application / Corporate planning. When asked to describe the practical benefits from the production of MDA corporate plans the responses of MDA representatives were lukewarm. As yet the plans appear to be just that – plans, with the serious business of reorganization yet to occur. No estimates had been done on the financial cost of managing internal change suggested by the corporate plans. Further there were mixed views on the quality of consultants who had facilitated the corporate planning exercises: a rare moment of qualified comment on the quality of SPARC consultants. / Service Charters. As with corporate plans, the impact of Service Charters remains unclear. Lagos is undertaking an impact assessment, without SPARC support. We found no examples of organizational restructuring precipitated by the Service Charters, which suggests that the structural implications of the focus on customer service has yet to be manifest. In one case (MOH, Enugu) we found the Service Charter was for the Ministry HQ, and not front line service units such as hospitals and clinics. / Convergence. Ultimately, the three strands of PSM work being pursued by SPARC – mandate clarification, corporate planning and service charters - need to converge into a coherent PSR programme purposefully driven by state government. In Lagos the OoT is headed by an officer capable providing such leadership, but he will still require support HoS and beyond that from the political Executive. On balance few states are likely to offer fertile conditions for sustainable gains in this area. / Recommendations: / Roll out Service Charters to frontline service providers of key service delivery MDAs / If corporate planning is continued, SPARC should review the performance of consultants used. Some fresh talent is probably necessary, and subject MDAs should be assisted with drawing up financial estimates for the cost of managing organisational change. / If PSM gains are to be sustainable it is vital that State Governments are able to converge and expand reforms developed with SPARC support (e.g. Corporate Planning, Service Charters) across government. A strategy of engagement with the political executive and the HoS will probably be necessary, and will need to involve DFID. / Summary and Scoring / With a 2011 baseline and 2013 milestones, this assessment is made at the halfway point and, on an arithmetical basis, a performance of 50% of 2013 milestones achieved is used as the benchmark for expectations. As required by the TORs, only output indicators 3.1 and 3.4 have been considered. / For states with a Type B approach, results have moderately exceeded expectations and states with either a Type A or C approach, results have met expectations. / Type A (54%) Type B (67%) Type C (50%) / Jigawa Lagos Enugu Kaduna Kano Yobe Katsina Zamfara / 33% 75% 50% 67% 13% 0% 50% 0% / Notes / 1. Average milestone achievement figures for each Type of Approach are calculated based on the target number of states for each approach (e.g. two for Type A, one for Type B and two for Type C). / 2. Anambra and Niger (Type C approach) are not included since inception work is being completed and they do not yet have logframes. Therefore, the milestone target of two out of four states with a Type C approach is being interpreted as 50% and is being applied to Katsina and Zamfara only at this stage. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 4: Federal Support To State Governance Improved
Output 4 score and performance description: Score: A (outputs met expectation) / SPARC’s main interlocutors at the federal level are the Nigeria Governors Forum (NGF), a voluntary and non-statutory association of state governors, and the Office of the Senior Special Assistant to the President (OSSAP), a dedicated unit in the Presidency which manages the MDG Conditional Grants Scheme (CGS). The first offers an unstructured, unique but potentially potent medium for soft policy influence across states. The second uses cash incentives to induce better governance and improved M&E in local government areas (LGAs) and related state governments. Progress has been made in work with both these partners: / NGF: Rolling out the State Peer Review Mechanism (SPRM), knowledge management (archiving good practice examples of governance reforms) and budget analysis through an induction course for new governors / OSSAP: expanding and strengthening the MDG Conditional Grants Scheme (CGS). Support to the OSSAP MDGs CGS unit has helped to scale up the CGS LG track from 113 LGA to 261 by adding another 148 LGA i.e. a third of the 774 LGAs. SPARC reports suggest that this is the first time a scale up of this magnitude has been attempted anywhere in the world.
Progress against expected results: / Indicator 4.1: Effectiveness of National mechanisms for improving state governance. / 2013 Milestones Actual Progress / The SPRM mechanism has been piloted and reviewed / State level CGS is reviewed and adjusted / LG-CGS is fully operational / The NGFS strategic plan has been updated and implementation started. The SPRM mechanism is currently being piloted in four states. / The state level CGS implementation manual was reviewed and adjusted in June 2012, including incorporating the LG-CGS track and updated evaluation criteria. / The LG-CGS is fully operational with 100% of selected LGAs having been awarded CGS funds. / A draft of the new NGF strategic plan has been produced and is awaiting final approval before implementation can commence. / Indicator 4.2: Responsiveness and success of State Governments to National initiatives to improve state performance. / 2013 Milestones Actual Progress / At least 10 states have submitted SPRM State Self Assessment Report (SSAR) and State Plan of Action (SPoA), / All states continue to access State level CGS and maintain a 90% completion rate. Three states have submitted their SSAR and SPoA and two further states are expected to submit in early 2013. / State CGS grants were disbursed only in 2009 and 2011 but not in 2010. In 2011, all 36 states (100%) accessed the CGS. In 2012, all states had access to state-CGS funds except Benue state (which did not apply). For states where data is available, the CGS completion rate was 86.41% for 2009 and 74.1% for 2011. / Indicator 4.3: State governments have a mechanism for accessing and sharing lessons through appropriate Federal organisations / 2013 Milestones Actual Progress / SPARC state level lessons have been collated and made available to all non-SPARC states. Five key SPARC State lessons have been collated from states and are currently being produced into SPARC lesson leaflets. These include: / Bank Reconciliation Model (Kano) / Corporate Planning (Lagos) / Service Charters (Lagos) / Establishment of Bureau of Public Service Reforms (Kaduna) / Medium Term Planning (Enugu). / The NGF Content Management System (CMS) currently houses SPARC results and will be used to disseminate the SPARC lessons leaflets. All states have access to the CMS. / In addition to this more formal knowledge management mechanism, SPARC has facilitated lesson sharing through helping organize governance 'share fairs' during 2012 for both Northern and Southern states (including non-SPARC supported). Another means of dissemination used by SPARC is to distribute result flyers to Governor's during their monthly meetings. In the case of Ebonyi State, this has resulted in the state writing to ask for the programme's technical support in reforming its Civil/Public service. / Findings from field visit of potential general application / NGF remains an interesting mechanism for dissemination of policies, despite the danger that the Forum could on occasion pursue policy positions that are primarily in the self-interest of Executive Governors. (Note the current debate on the redrafting of the Constitution with a proposal to finance LGAS directly through a national budgetary vote; a move that the NGF opposes since it will diminish the powers of governors to determine levels of funding for the LGAs in their state). Given these tendencies, SPARC will need to be watchful for the political dimensions to what may seem purely technical reforms. Centralizing power in state administrations at the expense of LGAs would mean compromising the deepening of democratic governance. There is no evidence of this occurring but it is an issue worth being alert to. / The geo-political, zonal sub groups of the NGF offer another avenue for policy dissemination that SPARC has used profitably in the South West. Given the trend towards regionalization in the country, these informal groupings may become useful media for promoting ideas on reform in the particularly in North West (where 5 out of 7 are SPARC states) and South East (2 out of 5) / The development and expansion of the MDG-CGS is a significant achievement, reinforcing PFM reforms at state level i.e. through the use of PFM-focused conditions. The CGS tries to achieve the MDGs in Nigeria through Transparent and Results-based Public Expenditure Management. As part of the evaluation criteria, CGS looks at the Evidence of Institutional Capacity to account for CGS fund. For instance the criteria ask for: / Evidence of a Budgetary classification system capable of tracking poverty / Evidence of 2011 and first quarter 2012 budget monitoring reports / Evidence of 2009, 2010 and 2011 state audited financial statement / Evidence of enactment of State Fiscal Responsibility law (either in Bill or Law form) / Evidence of due process or public procurement manual (either commencement, completion or produced) / Evidence of submitting regular projects and financial reports / Recommendations: / Expand initiatives through regional sub groups of NGF / Ensure that the NGF CMS is not the only mechanism for disseminating SPARC lessons learned and supporting the replication of SPARC governance reform initiatives. Monitor use of the NGF CMS by states and support the NGF in developing strategies for helping states become pro-active users of the system. / Review CGS completion rate baseline and target figures and adjust logframe milestones accordingly. / Summary and Scoring / With a 2011 baseline and 2013 milestones, this assessment is made at the halfway point and, on an arithmetical basis a performance of 50% of 2013 milestones achieved is used as the benchmark for expectations. Inline with the TORs, output indicators 4.1 - 4.3 have been considered. / It is estimated that 54% of Output 4 2013 milestones have been achieved and that expectations have therefore been met. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

## Section B: Results and Value for Money.
1. Progress and Results / 1.1 Has the logframe been updated since last review? Yes / The SPARC Consolidation and Expansion Strategy (CES, 2012) stipulated state specific logframes. This was also a recommendation of the 2011 SPARC Mid-Term Review. Consequently, using its previous programme logframe (dated 1st February 2011) as a guide, state specific logframes have been prepared by SPARC using the earlier agreed results and with the same indicators but with milestones tailored to the specific context and needs of each state. This exercise was undertaken in the period May-July 2012. Subsequent to the preparation of individual state level logframes SPARC prepared an overall programme logframe which synthesised state milestones within the three categories of approach detailed in the CES (Type, A, B and C), and which integrated Output 4. / 1.2 Overall Output Score and Description: / A+ (outputs moderately exceeded expectation) / 1.3 Direct feedback from beneficiaries / Not applicable. / 1.4 Summary of overall progress[10] on delivering the end-2013 milestones for four outputs specified in the ToR: / Output 1: Appropriate state policies and strategies adopted, monitored and evaluated A++ / Output 2: State Public Financial Management Improved A+ / Output 3: State Civil Service Performance Improved A / Output 4: Federal Support To State Governance Improved A / Particular progress has been made in the preparation of SDPs that include medium-term financing frameworks, with SPARC having supported these in all five original states and beginning to support development, to varying degrees, in the additional five states. There has also been good progress in the introduction of sector strategies linked to policies and medium-term financing frameworks. Across the five original states 41 sectors now have an MTSS. SPARC has helped to institutionalise capacity within the central planning agency for increasing the number of sectors with an MTSS. The combination of the effects of SPARC and ESSPIN and PATHS2 has resulted in greater progress in strategic planning processes in the health and education sectors. / In reviewing the draft 2013 budgets, it would appear that SPARC, together with DFID and other DFID programmes, has had a positive impact on budget realism in a number of states. Progress on budget realism has been entrenched in Jigawa, and to a degree in Lagos. Significant improvement in realism has been introduced in Zamfara and Niger, and marginal improvement in Katsina. SPARC recognises that in addition to technical support for budget preparation processes, there is a continued need for political engagement during the budget approval stage. SPARC stepped up efforts in this area during 2012 and is developing plans to strengthen this engagement (including through the NGF) during 2013. / There has been good progress towards the rationalization and restructuring of selected state government MDAs; SPARCs support for mandates work and Corporate Planning has resulted in realignment plans which State Governments are now beginning to implement in core central MDAs. SPARC support for service charters and performance management processes has contributed to increased public accountability and transparency of results. / There is evidence that SPARC, working together with the other SLPs, is helping to create greater awareness of the problems, detailed characteristics and causes of poor public administration and possible approaches to addressing these within the state governments, and is helping to promote pressures to improve the quality of public administration management both from within the civil service and from outside of the state governments. / 1.5 Key challenges / The key challenges to the programme are the following: / State Government Performance / Continued overall lack of realism in medium-term State Government’s (SG) budgeting processes. / Lack of discipline within SGs to ensuring that medium-term and annual budgets are aligned with overall and sectoral development plans. / Lack of commitment of several SG’s to implement difficult reforms (the technical work for which has been completed) such as institutional restructuring or the implementation of legislation. / SHoA / Lack of commitment by some SHoA to budget realism and discipline (indeed some SHoAs continue to inflate budgets), and their lack of willingness or ability to impose appropriate levels of discipline on the Executive. / Insecurity / The security situation constitutes a difficult, and increasingly dangerous, operating environment in which to deliver programme activities. Given the increased risk of terrorist attacks in the north and criminal activities in the south, SPARC has had to undertake a number of security improvements in order to remain functional. / The escalation of the Boko Haram insurgency in the north has forced a suspension of all short-term technical inputs in the northern states since mid 2012. Jigawa State, which has the largest SPARC programme, has been hit the hardest. Inputs have not been possible and outputs have therefore suffered. (Generally staff from decentralised northern state offices visit Abuja, with virtually no visits to the North by Abuja based senior staff) / In January 2012, protests at the removal of fuel subsidies stopped activities in all states for a two-week period. Lagos was the epicentre of the protests, and programme activities in that state (the second largest SPARC state programme) was severely affected. / Limitations to Air Travel / Recent aviation incidents have also adversely impacted on SPARC operations. On advice, SPARC only uses the Arik and Aero airlines. As Aero does not fly into Kano from Abuja and Arik suspended its Abuja-Kano flight for nearly a year, travel to all parts of northern Nigeria is now by road only. / 1.6 Annual Outcome Assessment / Against a 2011 baseline and 2013 milestones, this assessment is made at the halfway point and, on an arithmetical basis a performance of 50% of 2013 milestones achieved is used as the benchmark for expectations. Across all Types of approach, results have met expectations for those milestones against which performance can currently be measured (see Table below). / Some milestones refer to 2014 budgets or 2013 expenditure and since it is too early to measure these, they have been excluded from the analysis below. However, as recent analysis[11] shows, between 2009 and 2011, the total expenditure budget variance has fallen significantly in all five original SPARC states apart from in Kano (largely due the policies of a new administration) and Lagos (where variance fell in 2010 but returned to 2009 levels in 2011). / Type A (45%) Type B (60%) Type C (42%) / Jigawa Lagos Enugu Kaduna Kano Yobe Katsina Zamfara / 30% 70% 44% 60% 20% 18% 43% Too early to measure / Notes: / 1. Average milestone achievement figures for each Type of Approach are calculated based on the target number of states for each approach (e.g. two for Type A, one for Type B and two for Type C). / 2. Anambra and Niger (Type C approach) are not included since inception work is being completed and they do not yet have logframes. Therefore, the milestone target of two out of four states with a Type C approach is being interpreted as 50% and is being applied to Katsina and Zamfara only at this stage. / Whilst the previous (February 2011) and current (July 2012) programme logframes both include Outcome Indicator 4 (% of PEFA/SEAT Dimensions improving by at least one rating), the former includes a milestone for end 2012 whilst the latter includes a milestone for end 2015. / Comparing between the results of the baseline and 2012 PEFA/SEAT assessments in the five original states, Table 1 below shows (for SPARC supported indicators) the % of PEFA/SEAT indicators improving by at least one rating. Against the milestone of 25% (in at least three states), Enugu, Jigawa and Kaduna have achieved the target. / LF Output Enugu Jigawa Kaduna Kano Lagos All / Output 1: P&S 32% 55% 29% 20% 22% 35% / Output 2: PFM 33% 21% 53% 9% 22% 25% / Output 3: PSM 63% 13% 16% 7% 16% 21% / All 42% 26% 30% 10% 19% 26% / Note that this table shows only SPARC-supported indicators. The review team did not validate these results and has not had a chance to comment on the selection criteria. In the VFM section, when all indicators are taken into account the picture is more mixed. Nonetheless, taking account of the differences, the overall assessment of programme indicators suggests that progress has been made and assuming this continues then achievement of the programmes purpose still looks to be feasible within the programme time frame.
[10] As required by the TORs, only output indicators 1.2, 1.4, 2.1, 2.4, 3.1, 3.4 and 4.1-4.3 have been considered.
[11] SPARC Working Paper: State Budgets for 2013

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / Given that SPARC is a technical assistance programme the largest cost driver is consultancy fees combined with related daily subsistence and accommodation costs. As detailed in part 5 of this section, SPARC has actively sought to achieve greater value for money associated with these costs. / 2.3 Is the project on-track against original timescale: Yes / The original Project Memorandum envisaged that SPARC would run for six years from April 2008. During 2012 a Business Case was prepared, and subsequently approved, for the scale up of SPARC, including extending the programme until August 2015. / Progress to date is on track and it is likely that all four outputs are likely to be achieved by mid 2015. If current progress is maintained, then the project purpose is likely to be achieved. / However, the current deterioration in the security situation may mean that progress is delayed as implementation becomes more difficult, despite mitigating measures and new ways of working being implemented by SPARC to overcome this.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There is a sufficient evidence to suggest that SPARC will meet the programme outputs and outcomes. (The recent approval by Ministers of the Business Case for Consolidation and Expansion would have taken this issue into account). Two pieces of evidence are relevant in this respect: / The Mid-Term Review in November 2011 awarded SPARC a score of A+ (performance has moderately exceeded expectation). / An internal research study commissioned by SPARC at the end of 2011 concluded that SPARC had achieved all 2010 logframe outcome milestones. / SPARC’s ability to contribute to programme impact, together with other DFID programmes, is based mainly on research evidence that argues that there is a link between stronger institutions, in particular good budget management, and pro-poor service delivery outcomes. Nevertheless, the causal link between the two is somewhat contested, and success is dependent on political will and incentives. Lack of political will or other political uncertainties could compromise delivery of SPARC results. / SPARC has sought to address this risk by undertaking political economy analyses (PEA) of the states it works in, and on the basis of this drawing up Measures of Political Commitment. The PEA are updated regularly, and used to adapt programming. SPARC – with DFID support – has also paid more attention to managing these risks through its political advocacy work. / Timely, good quality data to monitor state level results in Nigeria is generally weak. To fill this gap, SPARC has sharpened its focus on ensuring robust data collection and M&E systems, with the help of independent service providers. / However, though diagnostic analyses have been undertaken in the proposed new states (including the North States Inception Report, SPRM study & PEA), expansion to new states will bring an element of uncertainty to the delivery of results. This will be compounded if the security situation deteriorates further in the North. / 3.2 Where an evaluation is planned what progress has been made? / The DFID programme team monitors progress against the logframe. SPARC’s performance is also assessed by internal monitoring; by independent monitoring through annual and mid-term reviews; and by an independent end-of-programme evaluation. / Internal Programme Research / SPARC implemented an annual Research Study in late 2011 and is currently preparing the 2012 Research Study report having completed analytical work in late 2012. The primary objective of this research is to systematically review performance and provide lessons to decision-makers at both state and programme levels, as part of internal reprioritisation and adjustment of strategies, implementation plans and budgets. The 2012 Research Study is expected to be completed by mid February 2013 and will inform programme adjustment and work planning discussions scheduled for March-May 2013. Specific objectives of the study will include: / Document where SPARC supported work has resulted, or is starting to result, in improvements in the efficiency and effectiveness with which supported state governments’ use public resources. / As part of this, to provide a more evaluative basis for SPARC’s reported performance against the programme logframe. / To selectively assess the efficiency and effectiveness with which SPARC has used resources to deliver outputs and achieve results. / Independent Evaluation / As with all the state level programmes (SLPs), SPARC is subject to annual Independent reviews, conducted by a separate shared service provider; the Independent Monitoring and Evaluation Programme (IMEP). IMEP also provided an independent mid-term review evaluation and will provide an independent evaluation of the suite of SLPs at the end of the programmes.

Risk / This Risk Assessment has been done primarily on the basis of documentary research, drawing on material provided by SPARC. No field visits or face-to-face interviews were scheduled for the review mission to interrogate the issue of the deteriorating security situation in the North, and significantly the mission itinerary was revised on the basis of security warnings. Given the dangers to human life we recommend a detailed, independent assessment.
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / Given the challenging reform and security environment in Nigeria, particularly in the North, the overall risk rating for the programme is high. The main risks, and the plans to manage and mitigate them, are set out below. / The deteriorating security conditions make it very difficult to work in most parts of Northern Nigeria. / To mitigate the risk that security constrains programme delivery, SPARC has engaged a specialist Security Adviser and set up a security management system and business continuity plan. It has also engaged a full time Security and Logistics Manager to ensure that procedures are complied with at all times. / In addition to managing security risks for programme staff and partners, the programme also adapts conflict sensitivity in its approach. This means for example, that SPARC continues to ensure that the programme has a level of acceptance among local partners and populations; it works to maintain a strong credibility as an independent provider of high-quality TA. But these measures may not be sufficient to ensure programme effectiveness. Note for example a finding from our field research that suggests that ‘embedded’ trainers / consultants have been seen as the most effective form of TA in Lagos and Enugu. Such an arrangement is unlikely in most of the north-western states. / When we raised this issue in broad terms with SPARC consultants from the South, without exception all said that they would be unwilling to risk working in the affected parts of the North. One of the consequences has been that SPARC staff based in these states make frequent visits to Abuja to re-tool themselves and ‘carry skills’ to their home states. This modality does not inspire confidence, though clearly one would need to check the results on the ground. Which of course is currently not possible. / We conducted telephone interviews with the two DFID representatives covering two northern states each: Kano and Jigawa; and Kaduna and Yobe. Both emphasised the importance of sourcing local consultants, while acknowledging the intense competition among donor programmes (including within DFID) for the same small pool of talent. / The trend towards localisation / indigenisation / An emerging risk in Nigeria is the trend towards ‘localisation’ at the state level. At one level, this is a natural and legitimate extension of the principle of ‘Federal Character’ enshrined in the constitution. A commonly traded phrase illustrating this trend was that ‘only Northerners can effectively work in the North. They have the cultural capital and political connectivity’. Variations of this line of argument were discernable in Enugu and to an extent in the SW of the country too. / This issue raises difficult questions for a reform-minded, essentially meritocratic, performance orientated programme such as SPARC, which now has to balance progressive, normative principles of inclusivity with a pragmatic accent on effectiveness, impact and VFM. / Vested interests and weak political commitment impede reforms. Elections lead to a loss of momentum. / SPARC has developed an array of scenario mapping and planning tools to deal with these issues. / To manage the risk of insufficient political will SPARC has developed a system to assess political commitment to reform. The system called ‘Understanding Political Commitment’ entails an analysis of various sources of information to inform SPARC about the likelihood of success of various initiatives. (SPARC suggests that there could be insufficient political will in Zamfara, Katsina and Yobe, for the reforms envisaged by the programme to take hold). / The 2015 General Elections in Nigeria could lead to a loss of focus or momentum in the last year of the programme – and there are only three Governors who are in their first term out of the ten states – Kaduna, Zamfara and Yobe. 2014 elections in Anambra could lead to a loss of focus or momentum in that state. To mitigate the risk of loss of focus or momentum as a result of elections, SPARC intends to do its most substantive reform work between mid-2012 and mid-2014. This means that the most strategic interventions can take place while the environment for reform is still conducive. The last year of SPARC will then focus on completing already initiated reforms; learning and documenting lessons; policy engagement and preparing the ground for any possible follow-on programme. / Additionally, SPARC is making arrangements to agree its reform programmes with various states. This will set out mutual expectations and responsibilities. Lastly, DFID has appointed State Representatives that will help to improve political engagement with state governments. / The risks and assumptions concerning specific programme activities are set out in state level logical frameworks, as well as in the programme-level log frame.
Risk of funds not being used as intended / SPARC’s expenditure mostly consists of the delivery of TA, the provision of support to other forms of capacity-building activities, and the conduct of studies. Funds are not provided directly to the state governments for the implementation of project activities. SPARC’s accounts are audited annually, and there are no reports of improper utilization of funds. / 4.4 Climate and Environment Risk / The likely relevance of this type of project to climate and environment risk and risk mitigation is only in terms of the potential positive impact of the project on the relevance and effectiveness of state government development strategies in terms of climate risk management (through improved state government effectiveness in anticipating and planning for responses to local climate and environmental risks).

5. Value for Money
5.1 Performance on VFM measures / This assessment is made on the basis of financial information provided by SPARC, on information from annual reports and the SEAT and PEFA assessments. The assessment takes account of both the DFID ‘how to’ note on VFM and the ITAD document ‘Better Assessing VFM in DFID Nigeria Governance and Conflict Programming’ produced in late 2012. Further detailed analysis and commentary is contained in the comprehensive Annex 2 attached to this form, including comparative tables and figures. Economy, efficiency and effectiveness are individually assessed against for all four stages (as outlined in the DFID guidance). / SPARC, in common with all SLP’s and all DFID programmes underway in Nigeria, have to adapt to the rapid evolution of the DFID VFM agenda. Looking back over the past performance is valid in terms of analysis of figures for the period 2009 - 2012, and this is presented below and in the attached Annex. The utility of historic analysis, as a tool to inform learning and guide future decisions, is perhaps greatest in a stable delivery environment where year-on-year changes are relatively infrequent. This is not the case in the SPARC delivery environment; the national context is rapidly changing, the VFM agenda is still evolving and SPARC itself is embarking on an ambitious expansion (into some of the most challenging states). In these fluid circumstances, the potential for learning and adapting future practice (to enhance VFM measures) from historic analysis is diminished. / Notwithstanding the limitations mentioned above, SPARC has taken the initiative in relation to the evolving VFM agenda. SPARC shows clear commitment to engage in the debate, to learn and to share, and a number of activities are worth highlighting as positive attributes in the evolving context. SPARC are proactive participants in SLP discussion and knowledge exchange initiatives. SPARC have been active in contributing to the development of and responding to the recommendations from the 2012 paper on VFM prepared by ITAD. A re-examination of VFM, as part of the 2012 development in the ‘business case’ format, has helped focus concepts as SPARC expands into new states. / 5.2 The results achieved, with matching costs (at overall program level) / Economy: Unsurprisingly professional fees (consultancy fees) are the main cost driver, followed by costs of housing and DSA for experts. Other cost drivers are the office costs, program initiatives such as training, study trips and workshops. The tables in Annex 2 show historical data and the allocations (to date). / Efficiency: Each of the four work-streams has received around a quarter of the budget to date. Over time, the Federal work stream has expanded (in relative terms) at the expense of the SP&ME work stream. The tables in the Annex show the detail of work stream allocation by year from the start of the programme (2009) / Effectiveness: To assess the effectiveness at overall program level, the resource allocation is related to the outcomes. The impact of the work streams SP&ME, PFM and PMS can only be identified at the State level, so the relation between all outcomes and overall costs (at overall program level) are problematic. / 5.3 Comparing VfM of different parts of the programme / The tables below show the cost structure across States per work stream for efficiency and effectiveness. A number of observations are presented in the attached Annex 2 to supplement these tables. / State policies and strategies efficiency across states: / State Enugu Lagos Jigawa Kaduna Kano / Output MTSS costed / budgeted in 7 key sectors MTSS costed / budgeted in 25 key sectors MTSS costed/budgeted in 5 key sectors MTSS costed/budgeted in 3 key sectors No costed / budgeted MTSS in any sector / Input £459,253 £779,654 £667,431 £169,633 £861,660 / Output/input £65,000 per MTSS £31,186 per MTSS £133,486 per MTSS £56,544 per MTSS / PFM efficiency across states: / State Enugu Lagos Jigawa Kaduna Kano / Output No increase in budget credibility (PEFA indicators 1, 2 3 and 4 remained ‘D’) No increase in budget credibility (PEFA indicators 1, 2 3 and 4 remained ‘D’) No increase in budget credibility (PEFA indicators 1, 2 3 and 4 remained ‘D’) Increase in budget credibility for indicator 4 payment arrears (other indicators no change) Decrease in budget credibility (PEFA indicators 3 and 4 deterioration) / Input £1,032,762 £1,862,693 £1,219,474 £674,649 £1,064,082 / Output/input See discussion section 5.3 / State Civil Service efficiency across states: / State Enugu Lagos Jigawa Kaduna Kano / Output Service Charters in 7 pilot MDAs Service Charters in 12 pilot MDAS Pilot Service Charter in preparation Primary Education Benchmarks published No service charters adopted / Input £352,883 £765,091 £1,084,087 £881,454 £819,617 / Output/input £65,000 per Charter £64,000 per Charter See discussion section 5.3 / Strategic Planning effectiveness across states: / State Enugu Lagos Jigawa Kaduna Kano / Outcome Net increase SEAT SP-indicators: +3 out of 9 Net increase SEAT SP-indicators: +2 out of 9 Net increase SEAT SP-indicators: no data Net increase SEAT SP-indicators: 0 out of 9 Net increase SEAT SP-indicators: -2 out of 9 / Input £479,842 £795,867 £710,828 £169,989 £861,725 / Outcome/input £159,947 for each indicator net increase £397,933 per indicator increase unknown No outcome improvement deterioration / Monitoring and Evaluation effectiveness across states: / State Enugu Lagos Jigawa Kaduna Kano / Outcome Net decrease SEAT PSM indicators: -4 / 6 Net increase SEAT PSM indicators: -2 / 6 Net increase SEAT PSM indicators: no data Net increase SEAT PSM indicators: 6 / 6 Net increase SEAT PSM indicators: -5 / 6 / Input £230,420 £410,114 £530,092 £600,562 £466,663 / Outcome/input deterioration deterioration unknown £100,093 / indicator increase deterioration / PFM effectiveness across states: / State Enugu Lagos Jigawa Kaduna Kano / Outcome Net increase PEFA dimensions: 12 of 70 Net increase PEFA dimensions: 1 of 70 Net increase PEFA dimensions: 0 of 61 Net increase PEFA indicators: 3 out of 28 Net decrease of PEFA dimensions: -25 of 62 / Input £1,173,792 £2,083,307 £1,299,047 £722,046 £1,718,765 / Outcome/input £97,816 per net increase of a dimension scores £2,083,307 per net increase of 1 dimension £1,299,047 for no net increase of dimension scores 240,682 for every net increase of a dimension Deterioration / 5.4 Can things be done differently to enhance VFM? / Economy: possible areas for consideration for improved economy: / Professional fees: The daily fee rates (per class of professional) are fixed in the contract. As the contract was negotiated following a competitive tender, it can be assumed that economy on consultancy fees (at the point of contract signature in 2009) was optimized. Within the current contract, fee rates are affected by i) the balance of international to national professionals and ii) the balance of short and long term input days. Unit rates (and associated costs) can be influenced by adjusting the balance of short and long term, national and international advisers. Observation from the field mission to Lagos and Enugu confirms that a higher use of national experts does not necessarily compromise on the quality of the experts. However quality needs to be assessed on a case by case basis and preference, in case of similar quality, should be given to full utilization of long-term resources (as opposed to short term inputs) and to national experts (as opposed to international experts. The evidence provided by SPARC demonstrates that project management has actively manipulated the balance of experts with the following outcomes: / Across the entire programme, the average fee rate has reduced by 9%. This represents a saving of £317,500 in 2011/12. / With the exception of Lagos, across the five original states, the average fee rate has reduced by between around 12%-16%. This represents a saving of £195,000 in 2011/12. / Capital costs: At this stage of the programme, most capital costs have already been incurred. There is limited room for improvement; the system is already established. SPARC’s internal procurement rules are that three independent quotes must be obtained for purchases between Naira 100,000 and Naira 1 million. Anything above this level, including vehicles, must be procured through Crown Agents, in accordance with DFID rules. / Training costs: Training facilities are commonly procured from hotels that offer catering and conference facilities. Alternative facility hire could be considered, especially if sustainability (beyond project funding for venue hire) is factored in / Office rent: In the original 5 states only Kaduna offices are located in government facilities. In the ‘new’ states all SPARC project teams are all located in accommodation at the premises of the beneficiary. This will translate into improved VFM in relation to office costs going forward. / Balance of Abuja and State operations expenditure: On face value the costs of the Abuja operations appear high at 43% of the total expenditure. This masks a number of central management, financial administrative, M&E, knowledge management and security functions that are carried out on behalf of the whole programme. It also contains allocations to federal spending. SPARC indicates that once these costs are accounted for, the Abuja expenditure is closer to 10% for 2011/12. In order to continue to monitor the balance of Abuja to state operational expenditure going forward, SPARC could consider more systematic recording of expenditure in this area. / Efficiency: In all SP&ME activities, the VFM evidence shows tangible outputs in all states save for Kano. MTSS delivery costs vary between £31,186 in Lagos and £133,486 in Jigawa. Future reviews could be tasked with a more in-depth analysis on the causes of the large variance. / The VFM evidence for PFM shows a clear negative using PEFA indicators only. In two states, more than £1m have been spent without an increase of the indicator. SPARC argue that the use of SPARC-supported indicators only would be a more valid measure. In future reviews, close attention should be paid to the selection of indicators. A critical reflection on the reform sequencing and theory of change is suggested. Issues that could be considered are: / The ability to forecast revenues in circumstances where federal grants account for a significant share of total revenues, but predictability is limited; / The disconnect between approved budget estimates and actual budget releases; / The systems that control and monitor expenditures in line with the votes; / Political commitment with respect to budget credibility. / The VFM evidence for PMS shows clear outputs in the form of Service Charters have been delivered in Lagos and Enugu. The VFM analysis shows that the amount per Service Charter is about £ 65,000. In the other states it was not possible to provide a comparative VFM analysis. / Effectiveness: For Strategic Planning, the VFM evidence shows mixed results. While positive results for the effectiveness in both Lagos and Enugu are observed, the evidence is negative on Kaduna and Kano. / For M&E, the VFM evidence is largely negative based on the SEAT measurement tool. To address the effectiveness of SPARC´s effort going forward, the root causes of the apparent deterioration need to be identified. The validity of the SEAT measurement tool is questioned.[12] In any case, SPARC may want to reconsider its implementation strategy for M&E to enhance the possibility that VFM can be demonstrated in this work stream. / In the PFM work stream, the VFM evidence shows mixed results. On the one hand, a substantial improvement is observed in Enugu, while results are strongly negative in Kano.[13] Improvements in Lagos, Kaduna and Jigawa are modest. On balance, effectiveness in PFM are assessed as slightly positive. / 5.5 Does the programme represent good VFM, what improvements could be made? / Economy: On balance, the review team concludes that SPARC represents good Value for Money within the parameters set. No significant opportunities (for factors that are in the control of SPARC) are identified as having potential to increase the value at lower costs. SPARC are already pursuing more economy by increasing the balance international/national experts in the favour of the latter. The balance of short vs long term professional resources may also be considered. More economy in the project could be considered if different configurations of SLP may be considered (especially at State level). SPARC already is enhancing VFM related to the location of office premises in their five ‘new’ states. Some opportunity to consider economy and sustainability for training facilities could be considered. / Efficiency: SPARC delivery of VFM is rated as positive on balance. For the SP&ME and PMS work streams, improvements may be possible following more thorough analysis of the quality of the MTSS, mandate maps and service charters. Though small teams of experts would probably be capable in drafting sectoral MTSS and Service Charters with less resources, this would probably be counterproductive in sustainability, buy-in and ownership terms. More robust metrics, which aim to measure the added value of the current approach, will enrich the analysis in future years. / For PFM and budget credibility, the activities carried out by the SPARC team focus primarily on revenue forecasting and medium term budget preparation. It is not likely that these activities could have carried out more efficiently. An argument can be made for considering whether better results (in terms of budget credibility) may be achieved by shifting efforts from medium term budget preparation towards control in budget execution including cash management. SPARC and DFID need to continue to tackle the difficult area of mobilisation of political commitment in relation to budget credibility. / Effectiveness: Given the evidence seen by the review team, SPARC’s intervention in the Strategic Planning work stream is judged positively in terms of its effectiveness. For the M&E work stream, the effectiveness of SPARC’s intervention is considered to be poor on the basis of the indicators assessed. It is likely that this conclusion is explained because of inappropriate indicators; going forward the issue of appropriate indicators needs to be discussed and agreed. / For PFM, the effectiveness of SPARC’s support is judged to be mixed but overall moderately positive. Recommendations on the way forward are specific for each State. For Lagos, it is suggested to reconsider the prioritisation of the intervention (from support to budget preparation to elements in the downstream aspects of public finance management). A clear commitment from State government by means of a formally approved government PFM reform strategy would certainly facilitate the effectiveness of SPARC’s intervention. / For the PMS work stream, the effectiveness of SPARC’s intervention cannot be judged yet as the main outputs (mandate maps, service charters and corporate plans) are only recently finalised and approved and have not yet resulted in concrete results in both states. Looking forward, it is suggested that SPARC continues to focus on making sure that the preparatory work (laid down in the mandate maps and service charters) can be translated into measurable results to underpin VFM analysis. These may include rationalised organisational structures and case studies as examples of improved service delivery.
[12] Based on the reasoning that the SPARC intervention has raised the expectations on M&E which has resulted in lower scorer in the SEAT
[13] Negative results are partly caused by a too positive baseline assessment in 2009 which makes a comparison over time on the basis of PEFA scores partly invalid.

6. Conditionality
6.1 Update on specific conditions / Not applicable.

7. Conclusions and actions
SPARC continues to make substantial progress in embedding governance reforms in selected states and strengthening the foundations for governance reforms in others. Despite undergoing significant changes over the last 12 months as the result of consolidation and expansion into 10 states, SPARC has maintained its strategic coherence and level of performance as evidenced by an overall score of A+ (the same as awarded during the 2011 Mid-Term Review). / However, the worsening security situation in the North could impact negatively on SPARC's ability to deliver results, despite the mitigating strategies put in place. In this respect we recommend a more detailed assessment of the security situation and the risks this poses to working in Northern states.

8. Review Process
This form has been completed by drawing on the following information sources: / Interviews with SPARC consultants in Abuja, Enugu and Lagos / Interviews with SPARC government stakeholders at the Federal level and in two states: Enugu and Lagos / Meetings with DFID staff in Abuja and selected DFID state representatives / SPARC 2012 Annual Report, September 2012 QPR and December 2012 QPR. / 2012 Research Study field visit reports and state logframe assessments. / 2012 VFM Working Paper. / 2012 SPARC Scale up business case. / SPARC ARIES self-assessment

# Annex 1 FINDINGS FROM FIELD VISIT TO LAGOS AND ENUGU

Re: OUTPUT 1 Appropriate state policies and strategies adopted, monitored and evaluated
Development of Plans, Policies and Strategies
In Enugu there was role conflict between two organs of government both of whom see it as their role to play a central role in the state development planning process: the Enugu State Economic Planning Commission (ESEPC) vs. the Ministry of Budget and Planning (MOBP). The first is a statutory body particular to Enugu State; the second could be seen as a typical state level planning and budgeting ministry or department of a Ministry of Finance. SPARC is caught in the unenviable position of having to deal with both parties: working with the ESEPC to help define a more realistic SDP aligned to the government’s longer term Vision 2020, and train ESEPC staff to produce MTSSs for ministries, while at the same time strengthening MOBP to help them monitor MTSS’s better.

While SPARC has alerted the State government of this issue, the problem has yet to be resolved, inhibiting optimal returns for engagement in this area.

The role conflict in Enugu between ESEPC and MOBP reflects the tension between working in a similar way across all focal states e.g. by partnering with and strengthening MOBPs, and contextualising assistance in a state-specific way (supporting ESEPC). We acknowledge that the resolution of this role conflict is beyond SPARC’s scope. Nonetheless we recommend the engagement of a functional review consultant, with sufficient gravitas and experience in mediating such conflicts over organisational mandates, to suggest possible changes to the Governor’s office. Resolution of this matter will has the potential to significantly increase the impact of SPARC’s work in this state, with the inculcation of MTSS capacity within MDAs. (Currently centralised in ESEPC).

# Annex 2 VALUE FOR MONEY

The following Value for Money (VFM) analysis is based and consistent with the report “Better Assessing VFM in DFID Nigeria Governance and Conflict Programming” draft prepared by ITAD (October 2012) and the DFID Nigeria Guideline “How we judge the VFM better for our programmes”. It makes use of SPARC financial information, the annual reports and the SEAT and PEFA assessments.

Based on the DFID Guideline, the analysis distinguishes between economy, efficiency and (cost) effectiveness, and applies the following structure:

- Stage 1 Show the results achieved and match these to the costs at overall program level;
- Stage 2 Comparing the value for money of different parts of the programmes;
- Stage 3 Asking if there are different things that we can do;
- Stage 4 Judging the extent the programme already represents good Value for Money and recommending improvements.

5.1 Economy
The criterion ‘economy’ is concerned with the costs of the inputs. However, as the ITAD paper points out, ‘value’ is equally important in this criterion to avoid “a race to the bottom” in the name of economy (through the procurement of key inputs based on price and not value).

Economy - Stage 1: show the results achieved and match these to the costs at overall program level

The following table shows the shares of the key cost drivers of the project:
Cost drivers	Amount	%
Consultancy fees	21,251,258	64%
DSA + housing	4,577,723	14%
Air travel	1,231,192	4%
Office/Misc	2,540,867	8%
Program initiatives	3,432,298	10%
Vehicles	393,267	1%
Total	33,426,605	100 %

Consultancy fees appears as by far the main cost driver followed by costs of housing and DSA for experts. Other cost drivers are the office costs, program initiative such as training, study trips and workshops. The importance of transport (vehicle and air travel) relatively.

Economy - Stage 2: Comparing the value for money of different parts of the programmes;

The following diagram provides a breakdown of the main cost drivers over the states.
Cost drivers	Abuja		Enugu		Jigawa		Kaduna		Kano		Lagos
	Amount	%	Amount	%	Amount	%	Amount	%	Amount	%	Amount	%
Consultancy fees	8,705,502	61	1,864,003	65	2,452,207	67	1,793,894	68	2,531,384	69	2,915,931	63
DSA + housing	2,168,586	15	30,3960	11	234,162	6	382,468	15	404,784	11	786,426	17
Air travel	723,501	5	54,039	2	90,128	2	72,392	3	138,780	4	134,482	3
Office/Misc	1,364,556	10	23,1581	8	406,405	11	83,221	3	153,935	4	249,484	5
Progam initiatives	1,197,382	8	390,982	14	403,302	11	267,673	10	394,466	11	504,078	11
Vehicles	165,490	1	34,818	1	53,841	1	25,495	1	34,788	1	57,220	1
Total	14,325,019		2,879,385		3,640,047		2,625,145		3,658,139		4,647,622

The table makes clear that some differences in the cost structure across the States can be observed but they are not that significant to warrant a more detailed analysis of the underlying causes.

Economy - Stage 3: Asking if there are different things that we can do;
The following analysis of the various cost drivers provides detail on SPARC’s room for manoeuvre in improving the economy of the project:

- Consultancy fees: The consultancy fees are fixed by the contract. As the contract is negotiated following a competitive tender, it can be assumed that economy on consultancy fees has been maximized. In the current contract, the only way to increase economy is by making more use of national experts instead of international experts. This will save on fee rates and per diems. Our observation from the field mission to Lagos and Enugu confirms that a higher use of national experts does not necessarily compromise on the quality of the experts but that expert quality needs to be assessed on a case by case basis and that preference, in case of similar quality, should be given to national experts.
- The evidence provided by SPARC demonstrates that project management has been conscious of the economy that can be gained by shifting towards a higher proportion of national experts. It reports that:
  - Across the entire programme, the average fee rate has reduced by 9%. This represents a saving of £317,500 in 2011/12.
  - With the exception of Lagos, across the five original states, the average fee rate has reduced by between around 12%-16%. This represents a saving of £195,000 in 2011/12.
- Vehicles: There is limited room for improvement. SPARC’s internal procurement rules are that three independent quotes must be obtained for purchases between Naira 100,000 and Naira 1 million. Anything above this level, including vehicles, must be procured through Crown Agents, in accordance with DFID rules.
- Training facilities: Training facilities are commonly procured from hotels that offer catering and conference facilities. Following the often expressed need of the SPARC beneficiaries, it is suggested to DFID to consider the possibility to support setting up a training center within the State administration. This will certainly not reflect a saving of money in absolute terms. However, in relation to the (sustainable) value created, it could improve VFM.
- Office rent and security arrangements: Except for Kaduna, the SPARC project teams are located in private accommodation at significant rental cost. A cheaper option in terms of rental costs and security arrangements would be to request accommodation at the premises of the beneficiary. In some aspects, this would also increase SPARC’s value as the SPARC team could interrelate more effectively with the beneficiary. The decision to locate in private office accommodation is a consequence of DFID’s requirements that SLP programmes should collocate. Once DFID loosens this requirement, it can be investigated whether a more economical beneficial accommodation arrangements can be negotiated with the beneficiary.
- Shift from Abuja to States expenditures: the costs of the Abuja operations are 43 per cent of the total expenditures. This includes the costs for the Federal workstream. The review team understands that the expenditures by the national team has not increased after the extension with 5 more States which strengthens the efficiency of the project. However, given that, except for the Federal Support workstream, SPARC’s results have to be achieved at State level the share of the Abuja operations in total costs seems to be too high.

Economy - Stage 4: Judging the extent the programme already represents good Value for Money and recommending improvements.

Judgement on the VFM/economy is based on the question whether the inputs could have purchased (1) with less resources and equal value; (2) equal resources and higher value.

In sum, on the criterion ‘economy’, it is concluded that SPARC is representing good Value for Money given the boundaries set by DFID. No obvious opportunities that are in the control of SPARC to increase the value at lower costs are identified. It is already pursuing more economy by increasing the balance international/national experts in the favour of the latter. More economy in the project could be considered in case DFID revises its policy on collocate the different SLP programmes and its policy not to provide any assistance ‘in kind’. In that circumstance, SPARC could consider to increase VFM by locating in accommodation at the premises of the beneficiary and by providing support to setting up a training facility at the beneficiary’s premises.

5.2 Efficiency

The criterion ‘efficiency’ is concerned with the costs in relation to the value of the outputs.

Stage 1 Show the results achieved and match these to the costs at overall program level

The outputs of the SPARC program are divided in four different work streams: SP&ME, PFM, PMS, federal support. The following table shows the total resource allocation over the four workstreams in the period 2009-2012 (first 6 months).

Work-stream	2009		2010		2011		2012		Total
	amount	%	Amount	%	amount	%	Amount	%	amount	%
SP&ME	1,369,632	28%	695,595	21%	921,516	18%	452,832	23%	2,986,743	22%
PFM	1,234,878	25%	822,984	24%	1,466,526	29%	440,080	22%	3,524,388	26%
PMS	1,253,317	25%	769,357	23%	997,356	20%	389,962	20%	3,020,030	23%
Federal	793,006	16%	842,319	25%	1,439,822	29%	581,143	29%	3,075,147	23%
Other	286,150	6%	245,025	7%	183,209	4%	138,944	7%	714,384	5%
Total	4,936,983	100%	3,375,281	100%	5,008,430	100%	1,975,961	100%	13,320,694	100%

The table shows that each workstream has received around a quarter of the budget with the PFM workstream. Over time, there is a trend to increase the allocation to the Federal workstream at the cost of the allocation to the SP&ME workstream. To assess the efficiency of the allocation, the inputs need to be related to the outputs. The outputs of the workstreams SP&ME, PFM and PMS are delivered at state-level and will be examined in the next section.

Efficiency - Stage 2 Comparing the value for money of different parts of the programmes

To assess the efficiency, we distinguish the following main outputs for the workstreams SP&ME, PFM and PMS.
Workstream	Output	Indicator	Comment
SP&ME	Evidence-based and costed MTSS	Number of sectors for which a MTSS is prepared in 2012	Quality of MTSS and costing is not included in the indicator
PFM	Increase of budget credibility	Increase of score on indicator 1, 2, 3 and 4 in PEFA 2009 versus PEFA 2012	The output could be considered to be an outcome. However, in the SPARC logframe this is explicitly presented as output / The indicator does not include improvements in the fiscal year 2012 as the PEFA scores are updated up to the fiscal year 2011; / The SPARC team questions the validity of the indicator as the score to pass the minimum PEFA scores are considered to be too high for the Nigerian context.
PMS	Mandate maps and service charters	Number of MDAs with final mandate maps and service charters	Quality of mandate maps and charters is not included in the indicator

SPARC’s financial management system allows to identify the resources that have been spend to deliver these outputs.[14] The following table relates the outputs to the costs for the five states.
[14] The following codes from SPARC’s financial system have been used for this calculation: 1.2 for MTSS, 2.1 for budget credibility and 3.1 for mandate mapping.

In the domain of SP&ME, the following table compares efficiency across the states:
State	Enugu	Lagos	Jigawa	Kaduna	Kano
Output	MTSS costed and budgeted in 7 key sectors	MTSS costed and budgeted in 25 key sectors	MTSS costed and budgeted in 5 key sectors	MTSS costed and budgeted in 3 key sectors	No costed and budgeted MTSS in any sector
Input	£459,253	£779,654	£667,431	£169,633	£861,660
Output/input	£65,000 per MTSS	£31,186 per MTSS	£133,486 per MTSS	£56,544 per MTSS

In the domain of PFM, the following table compares efficiency across the states:
State	Enugu	Lagos	Jigawa	Kaduna	Kano
Output	No increase in budget credibility (PEFA indicators 1, 2 3 and 4 remained ‘D’)	No increase in budget credibility (PEFA indicators 1, 2 3 and 4 remained ‘D’)	No increase in budget credibility (PEFA indicators 1, 2 3 and 4 remained ‘D’)	Increase in budget credibility for indicator 4 on payment arrears (other indicators no change)	Decrease in budget credibility (PEFA indicators 3 and 4 showed a deterioration)
Input	£1,032,762	£1,862,693	£1,219,474	£674,649	£1,064,082
Output/input	See discussion below

In the domain of PMS, the following table compares efficiency across the states:
State	Enugu	Lagos	Jigawa	Kaduna	Kano
Output	Service Charters in 7 pilot MDAs	Service Charters in 12 pilot MDAS	A pilot of Service Charters is in preparation	Primary Education Benchmarks published	No service charters adopted
Input	£352,883	£765,091	£1,084,087	£881,454	£819,617
Output/input	£65,000 per Charter	£64,000 per Charter	See discussion below

Stage 3: Asking if there are different things that we can do

In the domain of SP&ME, the VFM evidence shows that only in Kano the investments have not resulted in tangible outputs. In the other States, SPARC has delivered MTSS for an amount that varies between £31,186 in Lagos and £133,486 in Jigawa. A more in-depth analysis on the causes of the large variance in the average amount is recommended. One reason may be that in Lagos, the beneficiary has taken more ownership for the MTSS process.

In the domain of PFM, the VFM evidence above is negative. In two states, more than a million UK pound has been put in without an increase of any of the four budget credibility indicators. It cannot be concluded that no value for money has been delivered.[15] For such a conclusion, the results should be analysed more carefully. However, the indicator shows that increased attention is required on this deliverable to prevent in 2015 that more resources will be invested in this workstream without tangible results.[16] Increased attention should not be confused with increased resource allocation. Rather a critical reflection on the reform sequencing and theory of change is required. Issues that need to be considered are:
[15] To the defence of the SPARC programme, it can be argued that it is too early to use the PEFA indicators as a valid indicator in early 2013 as the PEFA indicator is not only based on the performance in the last fiscal year but includes the last three years in its rating methodology. Budget credibility seems to have increased in the fiscal year 2012 and this improvement will only be reflected in a follow up PEFA to be carried out at the end of the program in 2015.
[16] A tangible result refers to an increase of any of the four PEFA indicators on budget credibility. The argument that the PEFA framework is not applicable to Nigerian states because the benchmarks are too high should be rejected. No Value for Money has been created if the credibility of the Nigerian state budgets have improved from 50% deviation to 30% deviation. A budget with 30% deviation should still be considered to be ‘not credible’.

- The ability to forecast revenues in circumstances that the federal grant accounts for a significant share in total revenues and is limited predictable;
- The disconnect between approved budget estimates and actual budget releases;
- The lack of commitment control system to control and monitor expenditures in line with the votes;
- The political commitment to regard budget credibility as an objective.

In the domain of PMS, the VFM evidence shows that clear outputs in the form of Service Charters have been delivered in Lagos and Enugu. The VFM analysis shows that the amount per Service Charter is about £ 65,000. In the other states, no Service Charters were prepared to allow for a comparative VFM analysis.

Efficiency - Stage 4: Judging the extent the programme already represents good Value for Money and recommending improvements.

Judgement on the VFM/efficiency is based on the question whether the outputs could have been delivered (1) with less resources and equal value; (2) equal resources and higher value.

In the domain of SP&ME and PMS, answering the 2 questions requires more in-depth analysis of the quality of the MTSS, mandate maps and service charters. We suspect that the answer is most likely to be affirmative. A small team of experts would in most cases be capable in drafting sectoral MTSS and Service Charters with significant less resources. However, in line with the partnership approach of SPARC, the MTSS and Service Charters have been produced in cooperation and partnership with the beneficiaries. A lot of effort has been invested in this partnership. The value of this approach is that the outputs can rely on significant support and ownership of the beneficiaries which should increase the sustainability of the MTSS and Service Charters. It is too early to assess whether SPARC’s approach has indeed increased the sustainability of the outputs.

In the domain of PFM and budget credibility, the activities carried out by the SPARC team focused primarily on revenue forecasting and medium term budget preparation. It is not likely that these activities could have carried out more efficient. However, it can be postulated that better results in terms of budget credibility could have been achieved by shifting efforts from medium term budget preparation towards control in budget execution including cash management. Also, it would have been beneficial to the results in case SPARC (in collaboration with DFID) had given more attention to the mobilisation of political commitment for the objective of budget credibility.

5.3 (Cost) Effectiveness

The criterion ‘cost effectiveness’ is concerned with the costs in relation to the value of the outcomes.

Effectiveness - Stage 1: Show the results achieved and match these to the costs at overall program level

To assess the effectiveness at overall program level, the resource allocation needs to be related to the outcomes. As discussed in 5.2, the impact of the workstreams SP&ME, PFM and PMS can only be identified at the State level. A relation between the outcomes and overall costs at overall program level would therefore not be appropriate. The balance between costs and outcomes for the various workstreams will be provided at State level in the next section.

Efficiency - Stage 2: Comparing the value for money of different parts of the programmes

For the workstreams SP&ME, PFM and PMS, the following indicators to capture the main outcomes are distinguished:
Workstream	Outcome	Indicator	Comment
SP&ME	Policy and strategy development improved	Net increase SEAT indicators for S.P. domain	The indicator is calculated by comparing the scores of all SEAT indicators in 2009 to the scores of the SEAT carried out in 2012. All instances of indicator that have increased are scored as +1 and added and subtracted by all instances of indicators that have deteriorated scored as -1.
	Monitoring and evaluation improved.	Net increase SEAT indicators for M&E domain
PFM	State public financial management improved	Net increase PEFA scores[17]	The indicator is calculated by comparing the scores of all dimensions of PEFA carried out in 2009 to the score of the PEFA carried out in 2012. All instances of dimensions that have increased are scored as +1 and added and subtracted by all instances of dimensions that have deteriorated scored as -1.
PMS	State civil service performance improved.	reduction of the number of staff	This would be an appropriate indicator for the impact of ‘mandate maps’ and the rationalising of the public sector. However, as the mandate maps have only recently been finalised there are no outcome results yet available.
		change in client satisfaction	This would be an appropriate indicator for the impact of ‘Service Charters’. However, as the Service Charters have only recently been finalised there are no outcome results yet available.
[17] The indicator should better be confined to the PEFA scores on dimensions on which SPARC has directed its activities/outputs. However, given that the outputs in SPARC’s logframe are related to all PFM domains, the improvement across the entire PEFA assessment is taken as a valid indicator.

SPARC’s financial management system allows to identify the resources that have been spend to deliver the outcomes at State level. The following table relates the realised outcomes to the costs for Enugu and Lagos.

In the domain of Strategic Planning, the following table compares effectiveness across the states:
State	Enugu	Lagos	Jigawa	Kaduna	Kano
Outcome	Net increase SEAT SP-indicators: +3 out of 9	Net increase SEAT SP-indicators: +2 out of 9	Net increase SEAT SP-indicators: no data	Net increase SEAT SP-indicators: 0 out of 9	Net increase SEAT SP-indicators: -2 out of 9
Input	£479,842	£795,867	£710,828	£169,989	£861,725
Outcome/input	£159,947 for each indicator net increase	£397,933 per indicator increase	Unknown	No outcome improvement	deterioration

In the domain of Monitoring and Evaluation, the following table compares effectiveness across the states:
State	Enugu	Lagos	Jigawa	Kaduna	Kano
Outcome	Net decrease SEAT PSM indicators: -4 out of 6	Net increase SEAT PSM indicators: -2 out of 6	Net increase SEAT PSM indicators: no data	Net increase SEAT PSM indicators: 6 out of 6	Net increase SEAT PSM indicators: -5 out of 6
Input	£230,420	£410,114	£530,092	£600,562	£466,663
Outcome/input	deterioration	deterioration	Unknown	£100,093 per indicator increase	deterioration

In the domain of PFM, the following table compares effectiveness across the states:
State	Enugu	Lagos	Jigawa	Kaduna	Kano
Outcome	Net increase PEFA dimensions: 12 out of 70	Net increase PEFA dimensions: 1 out of 70	Net increase PEFA dimensions: 0 out of 61	Net increase PEFA indicators: 3 out of 28	Net decrease of PEFA dimensions: -25 out of 62
Input	£1,173,792	£2,083,307	£1,299,047	£722,046	£1,718,765
Outcome/input	£97,816 for every net increase of a dimension scores	£2,083,307 for a net increase of 1 dimension	£1,299,047 for no net increase of dimension scores	240,682 for every net increase of a dimension	Deterioration

Stage 3 Asking if there are different things that we can do

In the domain of Strategic Planning, the VFM evidence shows mixed results. While positive results for the effectiveness in both Lagos and Enugu are observed, the evidence is negative on Kaduna and Kano.
In the domain of Monitoring and Evaluation, the VFM evidence is largely negative. With the exception of Kaduna, we observe significant negative results in Lagos, Enugu and Kano. To address the effectiveness of SPARC´s effort, the root causes of the observed deterioration needs to be identified. It may be argued that the deterioration is caused by problems in the validity of the SEAT measurement tool.[18] However, such a claim needs still to be proven. In case the validity of the SEAT tool is not disputed, SPARC need to reconsider its implementation strategy in the M&E workstream to ensure that, by the end of the project, value for money has been realised.
[18] Based on the reasoning that the SPARC intervention has raised the expectations on M&E which has resulted in lower scorer in the SEAT

In the PFM workstream, the VFM evidence shows mixed results. On the one hand, a substantial improvement is observed in Enugu, while results are strongly negative in Kano.[19] Improvements in Lagos, Kaduna and Jigawa are modest. In sum, effectiveness in PFM are assessed as slightly positive.
[19] Negative results are partly caused by a too positive baseline assessment in 2009 which makes a comparison over time on the basis of PEFA scores partly invalid.

In the PSM workstream, the lack of data has inhibited the VFM analysis at outcome level.

Stage 4 Judging the extent the programme already represents good Value for Money and recommending improvements.

Judgement on the VFM/cost effectiveness is based on the question whether the outcomes could have been delivered (1) with less resources and equal value; (2) equal resources and higher value.
Given the evidence presented above, SPARC’s intervention in the domain of S.P. is judged positively in terms of its effectiveness. In the domain of M&E, the effectiveness of SPARC’s intervention is poor. It needs to analysed whether this conclusion can be explained by reference to non-validity of the indicator or whether the intervention itself needs to be reconsidered.

In the domain of PFM, the effectiveness of SPARC’s support is mixed and overall moderately positive. Recommendation for the way forward are specific for each State. For Lagos, it is suggested to reconsider the prioritisation of the intervention from support to budget preparation to elements in the downstream aspects of public finance management. A clear commitment from State government by means of a formally approved government PFM reform strategy would certainly facilitate the effectiveness of SPARC’s intervention.

In the domain of PMS, the effectiveness of SPARC’s intervention cannot be judged as the main outputs, being mandate maps, service charter and corporate plans are only recently finalised and approved and have not yet resulted in concrete results in both states. In the coming year(s), it is recommended that SPARC puts its efforts in making sure that the preparatory work laid down in the mandate maps and service charters are translated in concrete results to underpin the value for money analysis, such as rationalised organisational structures and concrete examples of increased service delivery.

# Annex 3 PEOPLE INTERVIEWED

Meetings in Lagos - 15th - 16th of January, 2013
	Name	Designation	Ministry/Agency		Phone Number
1	Adesegun O. Ogunlewe	Head of Service	Office of the Head of Service		8033074360	aogunlewe@lagosstate.gov.ng
2	David O.A. Sunmoni	P/S - Accountant General	Ministry of Finance		8033215538	dsunmoni@lagosstate.gov.ng
3	Ige Olujimi	Director	Office of the State Accountant General		8023014812	igejimi@yahoo.co.uk
4	O.A. Balogun	Permanent Secretary	Office of the State Accountant General		8023845237	oabprospers2@yahoo.com
5	Onibon W.A.	Permanent Secretary	Office of the State Accountant General		8033089590	wonibon@yahoo.co.uk
6	Keshinro K.O.	Director	Office of the State Accountant General		8029293253	okkesh2003@yahoo.co.uk
7	Dada A.	Director	Office of the State Accountant General		8023199990	bimsoldad@yahoo.com
8	Mrs Arinola Odulama	Director	Office of the State Accountant General		8033254944	armodu@yahoo.com
9	Azeez G.T.	Director	Office of the State Accountant General		8027266317	gafarazeez@yahoo.co.uk
10	Liadi A.A.	Director	Office of the State Accountant General		8054584393	biolaliadi@yahoo.com
11	Mrs Akibayo T.A.	Director	Office of the State Accountant General		8029293264	tanta00@yahoo.co.uk
12	Olusanya A.T.	Deputy Director	Office of the State Accountant General		8022930820	olutaofik2002@yahoo.com
13	Mahmud T.A.	Chief Accountant	Office of the State Accountant General		8056168256	mahmudtas@yahoo.com
14	Akinola C.O.	Deputy Director	Office of the State Accountant General		8023417986	calebolaolu@yahoo.com
15	Femi Ogunlana	Deputy Director	Office of the State Auditor General		8037278530	femiogunlana@yahoo.com
16	Anifiwose M.J.A.	Deputy Director	Office of the State Accountant General		8034028390	oluomoalade2015@gmail.com
17	Odubote T.K.	Chief Accountant	Office of the State Accountant General		8023260460	taofeekaz@yahoo.com
18	Mrs Deile H.M.	Director	Office of the State Auditor General		8033582351	helendeile@yahoo.com
19	Odusote A.A.	Senior Accountant	Office of the State Accountant General		8023065060	sirgbengo@yahoo.com
20	Mrs O.A. Adegbuji Onikoyi	Director (Central Internal Audit)	Ministry of Finance		8023012800	tonikoyi2000@yahoo.com
21	Toba Otusanya	Director General	Office of Transformation		7032689630	ootransformation@hotmail.com
22	F.A.O. Akodu	Permanent Secretary	Office of the Head Service Lagos State		8023190312
23	S.O. Ogunyemi	Deputy Director	Office of the Head Service Lagos State		8023317401
24	Bayo Sodade	Permanent Secretary	Ministry of Economic Planning & Budget		8034735859	bsodade@lagosstate.gov.ng
25	Dr. Femi Olugbile	Permanent Secretary	Minstry of Health		8037707546	olufemi54@hotmail.com
25	Akinkunmi Onimole	General Manager/CEO	Lagos State Public Procurement Agency		8023139059	akinonimole@lagosstate.gov.ng
26	Dr. Adesina Fagbenro-Byron	Regional Coordinator	DFID		8065724207	a-fagbenro@dfid.gov.uk
27	Austin Ndiokwelu	Technical Coordination Manager	SPARC		8050897311	austin.ndiokwelu@sparc-nigeria.com
Meetings in Abuja - 14th, 21st &22nd January, 2013
28	Asishana Okauru	Director General		Nigeria Governors' Forum	8035981617		aokauru@nggovernorsforum.org
29	Dr. Afeikhena Jerome	National Coordinator, State Peer Review Mechanism		Nigeria Governors' Forum	8154545432		ajerome@ngovernorsforum.org
30	Nafisa Usman	Head, ICT		Nigeria Governors' Forum	7038173555		nafisausman@nggovernorsforum.org
31	Ben Fisher	State Representative Northern Nigeria		DFID	8103702510		b-fisher@dfid.gov.ng
32	Kayode Sanni	National Programme Manager		ESSPIN	8065976747		kayod.sanni@esspin.org
33	Mike Egboh	National Programme Manager		PATHS2 Project	8055024969		m.egboh@paths2.org
34	Benson Obonyo	Deputy National Programme Manager-Technical		PATHS2 Project	8135385045		b.obonyo@paths2.org
35	Tim Donaldson	Senior Knowledge Management Advisor		SPARC	7055777169		tim.donaldson@sparc-nigeria.com
36	Mike Walker	Deputy National Programme Manager		SPARC	8068954496		mark.walker@sparc-nigeria.com
37	Hadiza Elayo	Senior Technical Coordination Manager (Federal)		SPARC	8035964527		hadiza.elayo@sparc-nigeria.com
38	Dr. Joe Abah	National Programme Manager		SPARC	8036680414		joe.abah@sparc-nigeria.com
39	Chris Perry	Monitoring & Evaluation Adviser		SPARC	7055292492		chris.perry@sparc-nigeria.com
Meetings in Enugu - 17th & 18th January, 2013
40	Sylvanus C. Onoyima	Special Adviser to the Governor of Enugu State		Office of the Governor of Enugu State	7039682449
41	Chidi B.S. Ezema	Head of Service		Office of the Head of Service	7066006789		chizemas@yahoo.com
42	Sir P.I.P. Okolie	Director (Revenue Monitoring and Inspection)		Office of the Accountant General of Enugu State	8035528500		p_okolie@yahoo.com
43	Godson S. Nnadi	Honourable Commissioner		Ministry of Finance & Economic Development	8033434374		gsnnadi@yahoo.com
44	Mrs Eunice Nwanneka Ugwu	Accountant General		Office of the Accountant General of Enugu State	8033195657
45	K.O.K. Agbowo	Honourable Commissioner		Ministry of Budget & Planning	8066738933		agbowokok@yahoo.com
46	Mrs. Roseline I.A. Egbo	Permanent Secretary		Office of the Head of Service	8051022910		princessegboo@yahoo.com
47	K.C. Ugwu	Permanent Secretary		Ministry of Budget & Planning	8033351211		casugwu@yahoo.com
48	V.O. Amadi	State Auditor General		Office of the State Auditor General	8058059119		amadivin@yahoo.com
49	Nnanyelugo Dan Onyishi	Executive Secretary		Enugu State Economic Planning Commission	8037406979		bukyonyishi@yahoo.com
50	Sam Onov Onyia	State Programme Manager		SPARC	8036664807		sam.onovonyia@sparc-nigeria.com