Type of Review: Annual Review

Project Title: Guyana Agricultural Sector Diversification Programme

Date started:	2/5/2012	Date review undertaken: 15-31/7/2013

## Introduction and Context

What support is the UK providing?
DFID Caribbean is providing £1,475,000 to support agricultural diversification and increased exports of fresh fish and agricultural produce in Guyana, through technical advice to farmers and policymakers and making financing available to these sectors, to enable growth as a share of total export volumes.. The programme is being implemented by CARANA Corporation, and builds on successful work that organisation started with USAID. CARANA is a private sector company with almost 30 years of experience in designing and implementing innovative technical assistance programs for international donor agencies as well as governments and private businesses. Their specific focus has been on more efficient, coherent and innovative approaches to implementation of development assistance programs, increasing aid effectiveness and value for money. / GADP works at three levels: directly with farmers to introduce new technologies and raise productivity; streamlining the paperwork and red tape for investors and exporters; and helping build relationships with new markets and buyers for the sector. / DFID Caribbean is supporting agricultural diversification in Guyana through a limited high impact intervention addressing the following constraints: / Internal and International Logistics / International Market Standards / Skills Development and Training / It is helping to establish aquaculture and non-traditional agriculture as viable export sectors, able to attract new foreign and local investment, generate substantial revenues and generate employment, particularly in rural areas where poverty rates are among the highest in the country.

What are the expected results?
Impact level results: / Diversification of agricultural sector increased as shown by: / An 8% increase in the percentage of non-traditional agricultural exports of total exports by 2015 / An approximate £9million increase in the level of new investment in non-traditional agricultural export industries by 2015 / Outcome level results: / Increase aquaculture and (non-traditional) agricultural exports (into Caribbean, Europe and USA) as demonstrated by: / Creation of at least 1000 new jobs; 50% for women; by 2015 / Increase the volume of Tilapia exports from a baseline of around 1000 kg per week currently to 12,000kg per week by 2015 / Increase the volume of non-traditional agricultural exports from a baseline of around 1000 kg per week currently to 16,000kg per week by 2015

What is the context in which UK support is provided?
Guyana, one of the poorest countries in the Western hemisphere, has vast tracts of productive land which present enormous opportunities for agricultural growth. As the only net food exporter in the region, it is often cited as the (potential) ‘breadbasket of the Caribbean’. DFID support will help to establish aquaculture and non-traditional agriculture as viable export sectors, able to attract new foreign and local investment, generate substantial revenues and generate employment in rural areas where poverty rates are highest. / The Guyana Poverty Reduction Strategy [May 23,2002 updated every three years] identified growth in the agricultural sector as “particularly important for reducing poverty because of the heavy concentration of the poor working in the sector. The Survey of Living Conditions [August 2007] indicated that 41% of households under the poverty line were employed in agriculture and that poverty rates in the rural coastal and rural interior zones were 38.7% and 52.5% respectively as compared to 16% in urban areas. By virtue of its impact on the modernisation of agriculture and aquaculture, the up skilling of labourers in the sector and the generation of employment the project is likely to contribute to poverty reduction in the rural areas. / Market Constraints in Guyana: Although the value and share of processed goods and fresh fruit and vegetable exports have experienced a positive growth trend in recent years, a series of market constraints exist which impede the transition to a modern, export based agriculture and aquaculture sector. / Internal and international logistics: The cost of harvesting vegetables or fish in Guyana and getting them to the airport is more costly then shipping them to international markets by airfreight. This is in spite of the comparatively high cost of airfreight at around US$ 1.60 per pound - a direct result of low export volumes – which creates a vicious circle that makes exports uncompetitive. At the domestic end, the Government is slowly beginning to understand the costs associated with overlapping bureaucracies and the non-systematic processes. / In addition, farmers often do not understand the need to change how they harvest crops by using techniques to better preserve the shelf life of crops. Due to a lack of up-to-date market information, their ability to match specific products to specific markets is also hindered, leading to an inadequate allocation of resources and increased waste. The challenge going forward is to improve the ability of exporters to move into new markets in the Caribbean, US or Europe via more direct air-links. / International Market Standards: Guyanese entry into new markets in Europe, the US or the Caribbean is constrained by a limited understanding of market requirements in three distinct areas. First, exporters need to recognise that international market requirements not local preferences dictate what crops to plant. Agricultural exporters have traditionally believed that local seed varieties and crops would easily be accepted in the Caribbean or US markets. This is simply not the case. International buyers often dictate down to the seed variety what type of crop needs to be grown. Second, local farmers are unaware of the importance of traceability in the export chain. The key to international acceptance and higher prices is keeping records of inputs and pesticide usage and being able to verify this through credible mechanisms. Finally, exporters have limited experience of how to deliver a product to market. Guyanese products often flow into the Caribbean in used onion bags, reused boxes or in the case of fish frozen solid. These products inevitably spoil or receive minimal prices. / Skills Development and Training: Farming techniques in aquaculture and agriculture are at best 10 to 20 years behind modern practices. Modern agribusiness is premised on precision and limiting the costs of inputs to improve margins. Guyanese farmers do not adhere to these principles. Soil and water tests are not common practices, record keeping is non-existent and pesticide usage is based upon what is available versus what is actually needed. / DFID Caribbean is supporting agricultural diversification in Guyana through a limited high impact intervention addressing the constraints detailed above.

## Section A: Detailed Output Scoring

Output 1: Modern aquaculture and agricultural practices adopted
Output 1 score and performance description:
Progress against expected results: / The indicators and relevant milestones for this Output were: / Output Indicator 1.1 / Number of acres under production using modern seed varieties, drip irrigation, greenhouse cultivation and appropriate pesticide usage techniques (producing export quality) = Ten (10) acres / Milestone substantially exceeded. At the time of this review, there are now Memorandums Of Understanding (MOUs) covering twenty five (25) acres of land. These include farms at all stages of the production process; i.e. clearing of land in preparation for ploughing, resting of land after harvest and before planting of the next crop and having crops planted, growing and with crops ready for harvest. It should be noted that there has been a great interest since the official project launch and there are currently a number of MOUs under negotiation. Each MOU requires the farmers to follow the expert technical advice, and use the specific inputs provided by CARANA. / Output Indicator 1.2 / Number of acres under production utilizing modern water quality testing, pond stocking, feeding regimes and fish safety techniques (producing export quality) =Ten (10) acres / Milestone substantially exceeded There are MOUs covering thirty six (36) acres of fish ponds. These are all growing Tilapia, or a mixture of Tilapia and Tambaqui. As with agriculture, the farms under MOU are receiving expert technical advice and specific inputs from CARANA. / Output Indicator 1.3 / Number of labourers/ managers trained in modern agricultural and aquaculture practices = Thirty (30) / Milestone moderately did not reach expectation. Across both the agricultural and aquacultural farms, eighteen (18) farm managers/labourers have so far been trained to follow the Global Good Agricultural Practice (Global GAP) policies and procedures. It is anticipated that the number will increase fairly rapidly as those farms move through the various stages of the production process. The level of achievement against this milestone has also been affected by delays in contracting at the start of the project. / Scoring Summary: / Overall, this output should be scored as A+. / Recommendations: / The logframe should be revised to include output indicators that specifically refer to acres under cultivation, fertilizer conversion rates based on Global GAP standards and other such measures which are used by the farmers and CARANA to show the financial viability of the programme. This is especially important as the results based payment structure will require proper validation of results being reported. / Impact Weighting (%): 35 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Global GAP requirements/ standards adopted
Output 2 score and performance description:
Progress against expected results: / The indicators and relevant milestones for this output were: / Output Indicator 2.1 / Number of acres under production compliant with Global GAP standards = Ten (10) acres / Milestone substantially exceeded. A total of sixty one (61) acres of land require the farmers to follow the expert technical advice, and use the specific inputs provided by CARANA; This ensures that the Global GAP standards are met and the quality and quantity of the produce is sufficient to meet the requirements of the international buyer for all areas under production. / Output Indicator 2.2 / Percentage of agricultural/aquacultural produce adhering to appropriate packing standards (from field to export point that improve shelf life and price) = 5% / Compliance with this indicator is difficult to accurately measure because all (100%) agricultural/aquacultural produce under this programme, will adhere to appropriate packing standards before being exported. It is likely however, that the 5% refers to the percentage of all Guyanese agricultural/aquacultural produce that is exported to standard and it is not possible to obtain data to verify this. / There has been some export of Tilapia, although it was only to show potential buyers that the fish met the required standards and that the Global GAP policies and standards were being followed. Production levels have not reached a stage where there is enough volume to export, and the sequential production required to sustain such exports has also not been implemented. / For the purposes of scoring if the milestone is strictly interpreted then progress against the milestone substantially did not meet expectation. / Output Indicator 2.3 / Number of labourers & managers trained in Global GAP certification processes/ standards/ practices = 30 / Milestone moderately did not reach expectation. As for the third indicator in ouput 1, across both the agricultural and aquacultural farms, there are eighteen (18) farm managers/labourers being trained to follow the Global GAP policies and procedures. / Scoring Summary / The overall score for this output as the indicators are currently written mean that it would sit somewhere between B and C. Given the progress that has been made, particularly in ensuring that global GAP standards are followed in the past six months, the most appropriate score for this output is a ‘B’. / Recommendations: / Rewrite Output Indicators 2.1 and 2.3 are essentially the same as Output Indicators 1.1 and 1.3 respectively, while Output Indicator 2.2 needs to be rewritten to reflect a different aspect of compliance with global GAP standards – perhaps total volume of exports. The GADP is predicated on the use and adoption of appropriate Global GAP standards at all stages of production. Therefore, as a project measure they would always score 100%. / Impact Weighting (%):35 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Regulations governing aquaculture and agriculture export practices streamlined
Output 3 score and performance description:
Progress against expected results: / The indicators and relevant milestones for this output were: / Output Indicator 3.1 / Number of forms required to export (i.e. complete export process) = no progress expected on baseline. / Output Indicator 3.2 / Number of working days to export (i.e complete export process) = no progress expected on baseline. / Output Indicator 3.3 / Number of regulatory changes approved = no progress expected on baseline. / It was agreed with CARANA at an early stage of project implementation that the milestones for the first Annual Review would show no reduction in the number of forms, days to export or in the number of regulatory changes approved. These will all follow in the second year of the programme. The Minister of Agriculture was in attendance at the formal project launch on 25 June, and this allowed CARANA to begin the process of negotiation and interaction with the staff of the Ministry of Agriculture. Staff meetings are held weekly, and CARANA’s work on GADP is a standing item on the agenda. The Minister is leading this work in his Ministry and at the Cabinet level, seeking to have the regulations altered and to reduce the number of forms required. / Scoring Summary / As no quantitative progress was expected against the indicators of this output, this scores an ‘A’, noting the ongoing process of consultation with and engagement of the Ministry of Agriculture and other agencies of the Government of Guyana to the changes. / Recommendations: / Based on conversations with the implementing partner, it is to be noted that these Output indicators will all be met in 2014. This is important because the financial viability of the farms in GADP is based on a model which allows for the harvesting, packing and shipping of fresh produce from the field/pond to the buyer which meets required international standards, and which therefore is aided by a streamlined set of regulations, forms and overall processes. We will regularly engage in a series of follow-up discussions with the Ministry, to track progress on modifications or amendments. / Impact Weighting (%): 30 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? This is the first Annual Review for this programme. However, as the implementation phase was effectively six months, rather than a full year, it was agreed with the implementing partners to revise the milestone targets for year one. The remaining milestones were then adjusted accordingly. Additionally, the AR has revealed that the original indicators need revisiting to more accurately reflect progress towards project outputs and outcome. / Overall Output Score and Description: The overall output score comes out at ‘A’ – Outputs met expectation. / Direct feedback from beneficiaries: During the site visits on the 23rd and 24th July; the opportunity for informal conversations with farmers and labourers presented itself. In every instance the farmers were complimentary of CARANA and very excited by the prospect of utilising Global GAP standards while following the expert technical advice provided.
Summary of overall progress: The GADP became active on 1 February 2013, despite the project being approved in DFID on 2 May 2012. The delay was mainly caused by the process to be followed before entering into a contract between DFID and CARANA. This means that rather than a full year of implementation elapsing before this Annual Review, only six months of work has actually been completed. / CARANA has provided technical and extension support to partner farms in agriculture and aquaculture. Under agriculture, the aim is to sequence production on these farms so as to reach and maintain the ‘critical mass’ volume required to fulfil the export orders negotiated with buyers. For aquaculture, CARANA has been working to ensure the Global GAP Standards are being rolled out to managers and labourers; in preparation for the certification process to be completed. / However, since that date, and as a result of the excellent press coverage on tv and in the newspapers, CARANA has become involved in a number of negotiations with new farmers. That press launch has also been the catalyst for a number of conversations with the Minister and the staff in the Ministry of Agriculture; which have revealed the Minister as the “champion” for export process reform, as well as a desire to work with CARANA on the volume purchase of inputs for onward sale to farmers across Guyana.
1.5 Key challenges / In agriculture, the ordering of inputs (drip irrigation equipment, fertiliser, seeds) has to be consistent and well managed, since it impacts on the sequence of production for farms. This means that lands that have been taken out of production are brought back online as soon as the requisite rest period is complete, or that new areas being cleared and prepared for cultivation are not left idle after banks are prepared, resulting in rapid regrowth of indigenous weeds and loss of downstream revenue. / The introduction of new farms under MOU also needs to be carefully managed. There will need to be a comprehensive and rapid learning program for new persons capable of being sent to farmers on a daily/weekly basis to assist and monitor in activities in order to ensure consistency and momentum are maintained. / In aquaculture, the challenges appear more to surface at the end of the production chain, both in terms of the National Aquaculture Association of Guyana (NAAG), buyers of the fish, and the disparity between local and international prices for the products. / The ‘tambaqui’ currently have one buyer identified in the US, and while it is noted that this buyer has twenty-five years of experience in this industry and approached CARANA regarding this fish, there is still the need to identify further potential markets. / The market for tilapia has not been completely exploited as yet, and with high demand comes high prices. There is a danger in farmers seeking to maximise short term profits by focusing on supplying their local markets, while neglecting to build up the volumes and sequence of production required to meet the large export market. / The exposure of agricultural and aquacultural capital investment to natural or man made disasters is quite high, and the ability to mitigate against those risks is limited. / Government of Guyana (GoG) participation in this programme is critical to achieving the stated outcome and impact. Additionally, there is a risk of corruption at the individual level, especially as it relates to removal of barriers to export. There needs to be regular consultation with and monitoring of activities within the various Government agencies and officials who are integral to the GADP activities.
1.6 Annual Outcome Assessment / Against the annual outcome level milestones, the project is currently off-track. However, this is completely due to delay in starting the implementation phase. Given the excellent progress made in the project in this short (six month) period, overall the project is on-track to deliver both the outputs and the final outcome by 2015. Indeed, if the level of interest that has been generated in the project is realised through new farmers, then the targets for the outcome indicators may well be exceeded.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: YES / 2.2 Key cost drivers / The key cost drivers have not changed: / Technical and managerial expertise coming from outside Guyana / Specialist nature of key inputs – fish feed, drip irrigation equipment. Highly technical specifications have to be met, and there are limited suppliers, therefore, the programme will be a price taker. / Volumes – volumes of inputs initially will not be large enough to get direct supply from the manufacturer or discounts from wholesale/retail distributors. However, as the number of acres under production increases, that situation is expected to change. Additionally, volumes of product meeting Global GAP standards and ready for export to buyers need to be built up and over the duration of the programme it is expected that these will increase as well. / 2.3 Is the project on-track against original timescale: No / It was anticipated that the Implementation phase would have begun in September/October 2012. Therefore, the project can be said to be five/six months delayed. There are no cost implications to this delay and all the logframe indicators still appear to be valid and achievable.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Evidence that market-led approaches to value chain development can be very successful in supporting growth, job creation and investment (if correctly applied) is borne out through numerous studies and evaluations. The expectation remains that once a critical mass of lead firms or anchor firms establish themselves as reliable suppliers to international markets, the demonstration effect will be sufficient to drive further adoption of best practice amongst domestic producers in the agriculture sector. The degree to which this expectation will be realised is yet to be determined and necessitates no change in the evidence ranking of Medium. / 3.2 Where an evaluation is planned what progress has been made? / The design phase of an evaluation is being discussed with CARANA Corporation.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / The risk rating for all three outputs remains at Medium. / 4.2 Assessment of the risk level / Whilst the excellent start to the project and the controls put in place by CARANA have meant that risks of delivering the outcome are minimised, a lot will depend on the Ministry of Agriculture delivering on its promises around regulations and red tape. For this reason, the overall risk rating should remain as MEDIUM.
Risk of funds not being used as intended / There is minimal risk of funds not being used as intended. DFID is actively investigating CARANA’s operating financial model, especially the administrative and programme costs. The process of invoicing internal to CARANA will show that the disbursements by DFID based on results achieved, will never see payment given in advance of need, since CARANA’s spend rate for the production of the outputs will always be larger than the disbursement. / The business plan for the Agricultural Investment Partnership has been submitted to DFID, and the review of this document to ensure the long term sustainability of GADP impact, as well as the assurance that UK funds are not being misappropriated is ongoing. / The procurement of inputs by CARANA was also reviewed by the team, to ensure that it was fair, competitive and free of fraud and corruption. / 4.4 Climate and Environment Risk: / There are continued generic environmental risks and climate change. The expansion of agriculture will involve land use changes or forest clearance in the intermediate savannah (for example, along the Linden Highway), with possible carbon emissions (though forest clearance and also ground transport and airfreight of produce) as well as related to project management (site visits). Several of the crops (vegetables and tilapia) to be cultivated are not native to Guyana and so measures are being be taken to keep them contained (for example, all tilapia farms to have enclosed circulation systems and empty to the ocean, no tilapia to be introduced inland from the coastal belt). Controls so far have been effective – tilapia have not overwhelmed their new habitat as the pH of the water is too acidic for reproduction beyond the coastal belt and predator fish keep the population in check.

5. Value for Money
5.1 Performance on VfM measures / The team has identified specific measures for CARANA to report on, that will (i) ensure value for money; (ii) monitor/report on value for money throughout the course of implementation. These measures include evidence of how the programme ensures that inputs are economically procured (economy) and how streamlining the exporting process will reduce time and cost to the government and private sector while raising export volumes and revenues (effectiveness). For example, measures that have been identified include proportion of administrative cost to programme costs, costs of international expertise vs local experts, price per job created, and the amount of investment required to generate a unit of export. As the project implantation is still at an early stage quantitative data are not yet available, though CARANA have agreed to provide this within six months of this AR. / 5.2 Commercial Improvement and Value for Money / DFID successfully negotiated a reduction in fees for technical personnel, travel and accommodation rates, saving around £300,000. The contract has also been designed with an output based payment structure with payments being based on actual deliverables (such as number of acres under cultivation). / In addition to saving thousands of pounds/dollars in rent by finding cheaper office space in Georgetown, CARANA utilised all the office equipment that was put in storage after the closure of Guyana Trade and Investment Support (GTIS), the predecessor USAID funded project. These along with other assets were transferred from GTIS to GADP. This reduced the initial setup costs for the CARANA office. There is an emphasis on the transference of knowledge and information, as the CARANA international expert staff are all working with and training local staff to provide field extension services. It should be noted that all the expert and technical staff listed by CARANA in their commercial tender have actually been secured and are currently working. Ultimately, as GADP progresses and then closes, the field extension services will be provided by trained local staff, both in the public and private sector. / The highly specialised and technical inputs required for the fertilizer and drip irrigation systems are supplied by very few firms worldwide. Additionally, the cost and logistics of importation to Guyana from locations in Europe, South America and parts of North America, reduces the practical options even further. Therefore, the options for supply of inputs to the project are limited, but the costs are being managed by consolidation of orders for all farms into one large order, and ensuring that only necessary inputs for a specified timeframe are included in that order. / 5.3 Role of project partners / The key project partners are CARANA, the farmers and the Ministry of Agriculture. Relationships appear very good between CARANA and the MoA and between CARANA and the farmers. Regular meetings will ensure that relationships remain strong. CARANA have also been asked by the MoA to purchase inputs on their behalf in an attempt to drive down input costs. This should will also ensure that relationships are underpinned by good commercial practise. / 5.4 Does the project still represent Value for Money : Yes

6. Conditionality
6.1 Update on specific conditions: none

7. Conclusions and actions
Overall, the project is on-track to deliver if not exceed the outcome targets by December 2015. However, the logframe requires revision to more accurately reflect progress towards the project outputs. The first draft of the revised logframe has already been completed, and it is expected that by the end of August 2013, the logframe will be updated to include the VFM measures identified earlier, and the milestones will be revised to more accurately reflect the current implementation timeline. / There are several areas where the implementing partner has been asked to deliver short updates on aspects of project progress. / Performance on VFM measures / One page summaries on gender, environmental impact and the number of jobs / Data to supports the ‘spotcheck’ on financial flows and results. / It is expected that the ‘one page summaries’ will be received with the second Quarterly report due by the end of August 2013; and these will be updated; along with the VFM measure performance and supporting farm, export and process data; at each Quarterly reporting milestone. / It was agreed that the review team will follow-up on progress in October 2013 through a field visit to coincide with the Caribbean week of Agriculture. This CARICOM led initiative will also provide an opportunity to speak with the GoG representatives, as well as to pursue donor coordination activities with Canada; EU; etc.

8. Review Process
The review was conducted by Results Adviser and Senior Programme Officer from DFID Caribbean. Input was sought from CARANA Corporation along with a representative from the Haurarooni Community and other farmers. / Site visits were undertaken on the 23rd and 24th June 2013.