Business Case and Intervention Summary

Intervention Summary

## Title: Improving UK Private Sector Engagement in Humanitarian Response

What support will the UK provide?
The UK will provide up to £755,000 over a 5 year period to Business in the Community to help improve the coordination and effectiveness of the UK private sector when they respond to humanitarian emergencies.

Why is UK support required?
The UK Government’s humanitarian policy ‘Saving lives, preventing suffering and building resilience’ recognised that humanitarian need is likely to continue to grow.[1] The systematic use of the private sector in partnership with humanitarian actors will go a long way to help meet these challenges. / One of the seven goals the UK Government set itself for improving the effectiveness of UK humanitarian support was making themselves a network enabler that supports greater partnerships within the humanitarian sector, including with businesses. In so doing, it recognised the invaluable role that the private sector has to play as a donor of both resources and expertise, and how it can operate in partnership with humanitarian actors to save lives. / There has however been a growing sense within the humanitarian sector that, beyond monetary donations, there is insufficient guidance, support, and regulation to guarantee quality humanitarian support from businesses. Moreover, a lack of mutual understanding and communication between humanitarian and commercial actors means that access to the opportunities which humanitarian-business partnerships represent has been severely inhibited. The commercial sector therefore remains, for the most past, an ad hoc responder to major emergencies. / To address this problem work needs to be undertaken to build and disseminate guidance and best practice to businesses on how to respond, and to generate the mutual respect and trust between the private sector and humanitarians necessary to establish collaborative partnerships that can be activated during emergencies. / Business in the Community (BITC) has approached DFID seeking to address this problem. Their proposal entails: / Producing and disseminating guidance for business on developing their approach to disaster relief. / Building a matching tool to identify and link businesses’ actual, and potential, contributions and engagement on this agenda with non-government organisations (NGOs). / Support to BITC in the development of a Disaster Award Category in their Annual Responsible Business Awards.
[1] http://www.dfid.gov.uk/Documents/publications1/The%20UK%20Government's%20Humanitarian%20Policy%20-%20September%202011%20-%20Final.pdf

What are the expected results?
The results of this investment will be that UK businesses are better prepared to respond to humanitarian emergencies quickly, effectively and appropriately. The increased awareness that this support will provide of the case for greater corporate engagement in humanitarian response, as well as practical advice and brokering, will see a more routine application of their skills, expertise, products and services. / This investment offers value for money by capitalising on BITC’s strategic position as a central source of advice and guidance for the private sector and their existing experience of partnering with the public sector to leverage business to address social challenges. Given its wide network of members and experience of working with a number of other UK Government departments, partnering with BITC offers DFID the opportunity to influence sector wide change in humanitarian response.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Over the coming decades it is expected that both the frequency and intensity of disasters will continue to increase as a result of climate change, urban migration, population growth and increased scarcity of natural resources. With the international system struggling to respond to current demands, there is an urgent need to unlock the potential of the private sector if future challenges are going to be met. / The UK Government Response to the Humanitarian Emergency Response Review (HERR) committed it to give full consideration to the use of private sector expertise where it can enhance humanitarian response effectiveness.[2] The response recognises that, where appropriate, the private sector can significantly complement and enhance UK emergency responses through the additional goods, services and skills that they can provide. / The private sector has a long history of being a generous donor to humanitarian appeals. Alongside committing large financial donations, it mobilises its customers and the wider public to contribute to humanitarian appeals, and it provides much of the logistics, transport and other services needed to move supplies during an emergency. Private sector contributions also appear to be on the increase. ALNAP’s ‘State of the Humanitarian System Report 2012’ points to global private sector contributions (counting both corporate and foundation entities) accounting for 1% of humanitarian aid flows in 2007-08 and rising to 6% in 2009-10.[3] / In addition to this monetary support, the private sector may have direct involvement during humanitarian responses through: / In-kind donations of goods. / Partnerships with humanitarian organisations and the provision of advice and expertise. / Direct commercial agreements with humanitarian organisations. / Direct commercial engagement in humanitarian contexts separate to the activities of humanitarian actors. / A number of international agencies have also recognised the potential increased role of the private sector, and the positive impact that this could create. For example, the US Office of Foreign Disaster Assistance (OFDA) has recently been promoting strategic partnerships between the private sector and NGO community to build disaster resilience and humanitarian response. / There are also a number of well-known examples of businesses that have embraced the role of corporate-NGO partnerships in humanitarian relief. This includes companies such as UPS and its role in the Logistics Emergency Team facilitated by the World Food Programme, and IBM, which has a longstanding programme incorporating expertise from its consultants, volunteer efforts and monetary donations. / However, because of the often ad hoc nature of business engagement, focused principally on large scale natural disasters, it is difficult to find consistent evidence which accurately reflects overall levels of business support in disaster relief. Some quantitative data does exist to measure levels of private sector support, with the Active Learning Network for Accountability and Performance in Humanitarian Action’s (ALNAP) ‘State of the Humanitarian System Report’ and the Office for the Coordination of Humanitarian Affairs’ (OCHA) Financial Tracking Service being notable examples. However, the drawback with these sources is that while they can measure to a certain extent the levels of donations received, they do not highlight other modes of support such as products and services or staff secondments. This information tends to be gleaned to a much greater extent from either anecdotal evidence or very specific, individual examples of giving. / Looking at the existing levels of private sector engagement, the motivations for providing this type of support are varied. Obviously, well publicised philanthropic activities will help to bolster a company’s public reputation and fulfill obligations related to corporate social responsibility. However, businesses are also beginning to recognise the wider opportunities that exist when engaging in humanitarian action: business development; professional development of employees; acquiring new knowledge, and, possibly, gaining information and access to new market opportunities. / For humanitarian actors, the benefits of engagement with the private sector can go beyond the monetary or material assistance that they are able to provide as a donor. These may include the insights they can provide in terms of value for money, beneficiary feedback, and supply change management. All of these may contribute to improvements in the effectiveness of assistance. / A number of NGOs have also undertaken to ensure that any companies they work with have to abide by specific guidelines. Oxfam, for example, states that it will only enter into humanitarian partnerships with private sector firms on the basis that they abide by the Principles of Conduct for the International Red Cross and Red Crescent Movement and NGOs in Disaster Response Programmes.[4] Similarly, the UN has developed its own guidance to determine how these partnerships should operate, ‘Guiding Principles for Public-Private Collaboration for Humanitarian Action’. The beginning of any partnership between humanitarian organisations and businesses must therefore be underpinned by each partner understanding the motives and interests of the other, and where each has a clearly defined role within the context of an emergency response. / However, the current nature of corporate-NGO relationships is clearly prohibitive to such successful partnerships being established. As the Humanitarian Futures Programme notes, “The reality of commercial and humanitarian engagement in crisis contexts now and in the immediate future will most likely remain a mix of last-minute engagements, memoranda of understanding, isolated interventions and long-term commitments.” Their study points to a lack of common frameworks to guide collaboration[5] alongside a lack of clear communication and mutual understanding between the two sectors. / Despite these problems however, the appetite for increased corporate-NGO partnerships remains strong, for the reasons outlined previously. There also exists some evidence in terms of what NGOs and the private sector would like to see to improve the nature of their collaborations. Examples include the Humanitarian Futures Programme workshop on Private Sector Innovation and Humanitarian Action held on 12 September 2012 [6] and Business in the Community’s ‘Business and Disaster Relief Conference’ held on 11 September 2012[7]. In discussions with both NGO s and the private sector a number of key themes were identified to help overcome the underlying problems of corporate-NGO collaborations. These include: / Donors lending reputational support to private sector initiatives. / Promoting collaboration through platforms. / Building the evidence base on the private sector’s contribution and impact. / Development of an online information centre and resource portal for private sector engagement in humanitarian action. / Development of sector networks to maximise leverage. / Better communication of needs and requirements. / Central repository of product standards and specifications. / A system of match making between NGOs and companies which adopts a thematic approach to link them. / Instigating these changes would be significantly aided by the establishment of an easily accessible, centralised source from which information can be drawn and partnerships established. This underpins BITC’s proposal to DFID: that they can increase the awareness amongst NGOs and businesses of the case for action and how to do it, as well as practical support and brokering, to scale up the level of private sector engagement and the quality of their responses. / Evidence does exist for the efficacy of using one umbrella organisation to assist in disseminating guidance to private sector organisations and promoting partnerships between NGOs and companies. In operation since 2004, International Health Partners (IHP) coordinates donations from pharmaceutical companies for use in emergencies. IHP works with the World Health Organisation and international medical NGOs to establish what is needed in responses. These ‘platform organisations’ can then form a vital function in helping coordinate the private sector during emergency responses. The Humanitarian Futures Programme conducted a study on how platforms can support the private sector’s further engagement in humanitarian action, ‘Platforms for Private Sector-Humanitarian Collaboration’. This makes a compelling case for the efficacy of their use, “They have proved successful at tapping the expertise of the private sector in ways that enhance the effectiveness and efficiency of humanitarian action and ultimately improve humanitarian outcomes”[8]. Moreover, this study points to the appetite expressed in the private sector for the expansion of such platforms and the means by which their functions can be enhanced. / In partnership with Business in the Community the UK Government is then in a strong position to help address this need by providing a readily available source of information on humanitarian and business partnerships in terms of how and where funding and donations can be injected, as well as the modes of engagement and positive outcomes. Delivering a programme of support will help to generate a series of new ideas and partnerships that are able to provide improved humanitarian responses. / BITC will undertake the following activities to support this proposal: / Producing and disseminating guidance for business on developing their approach to disaster relief. / Building a matching tool to identify and link businesses’ actual, and potential, contributions and engagement on this agenda with non-government organisations (NGOs). / Support to BITC in the development of a Disaster Award Category in their Annual Responsible Business Awards. / These activities are expected to achieve the following results: / The UK private sector is better prepared to respond quickly, effectively and appropriately to humanitarian crises. / Increased insight and understanding for business on how they can best assist during humanitarian emergencies. / Formal partnerships between NGOs and businesses are created. / Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response.
B. Impact and Outcome that we expect to achieve / Impact: The UK private sector is harnessed to reduce human suffering in humanitarian disasters. / Outcome: The UK private sector is better prepared to respond quickly, effectively and appropriately to humanitarian crises. / DFID will require a review point after 2 years to take stock of outcomes and plans for the remainder of the programme. / Inputs / Activities / Outputs / Outcome / Impact / Inputs / Process / Outputs / Outcome / Impact / Support to BITC in the development of a Disaster Award Category in their Annual Responsible Business Awards. / Assumption: That increased awareness amongst NGOs and businesses of the case for action and how to do it, as well as practical support and brokering, will scale up the level of private sector engagement. / Creation of a matching tool to identify and link business’ actual, and potential, contributions and engagement on this agenda with NGOs. / Up to £755,000 over 5 years. / Production and dissemination of guidance for business on developing their approach to disaster relief. / Increased insight and understanding for business on how they can best assist during humanitarian emergencies. / The private sector is better prepared to respond quickly, effectively and appropriately to humanitarian crises. / The private sector is harnessed to reduce human suffering in humanitarian disasters. / Formal partnerships between NGOs and businesses are created. / Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response.
[2] https://www.gov.uk/government/policies/helping-developing-countries-deal-with-humanitarian-emergencies
[3] www.alnap.org/pool/files/alnap-sohs-2012-lo-res.pdf
[4] http://policy-practice.oxfam.org.uk/publications/the-private-sector-and-humanitarian-relief-215649
[5] http://www.humanitarianfutures.org/futures-issues/commercialhuman
[6] http://www.humanitarianfutures.org/content/private-sector-innovation-and-humanitarian-action
[7] Business in the Community Business and Disaster Relief – NGOs Session – Meeting Notes – 11 September 2012
[8] http://www.humanitarianfutures.org/content/platforms-private-sector-humanitarian-collaboration

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / There are two feasible options: / Option 1: “Do nothing” – DFID does not support the development of a programme to improve the coordination of private sector responses during humanitarian emergencies. / Option 2: DFID supports Business in the Community (BITC) to develop a programme to enable companies to better understand how they can assist during humanitarian emergencies, and establish partnerships with NGOs.
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence for each option is rated as either Strong, Medium or Limited / Option Evidence rating / 1 “Do nothing” – DFID does not support the development of a programme to improve the coordination of private sector responses during humanitarian emergencies. Medium / 2 DFID supports Business in the Community (BITC) to develop a programme to enable companies to better understand how they can assist during humanitarian emergencies, and establish partnerships with NGOs. Medium / Add rows as necessary / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C B / In summary: / Option 1 “Do Nothing” is rated as “no impact” (C) as no coordination programme is established. / Option 2 “DFID support to BITC to develop a programme to enable companies to better understand how they can assist during humanitarian emergencies, and establish partnerships with NGOs” is rated as: / “C” – low risk” given the desk based nature of the programme. These can be minimised through the effective implementation of BITCs environmental commitments (see Tables 4 and 5 at Annex A). / “B” - “medium opportunity” given the potential to raise awareness, provide guidance, create complementary partnerships and support best practice in terms of mainstreaming the environment into humanitarian response. / As a result of the category B rating of the programme for opportunities, a Risk Assessment to scope and appraise the climate and environment issues identified through the Sensitivity Analysis was carried out using climate and environment checklists (see Tables 4 and 5 at Annex A). The tables further identifies measures to mitigate/manage these risks and maximise opportunities that once agreed, will need to be built into the programme (design through to monitoring, evaluation and reporting).
C. What are the costs and benefits of each feasible option? / Option 1: “Do nothing” – DFID does not support the development of a programme to improve the coordination of the private sector responses during humanitarian emergencies. / Benefits: Rather than proposing additional UK funding, this option acknowledges the work already being done in this field between businesses and NGOs. There are a number of examples of businesses that already have longstanding programmes linked to this agenda, and guidance is available to aid their interventions (e.g. the UN’s ‘Guiding Principles for Public-Private Collaboration for Humanitarian Action’). / This option also recognises that the private sector is already placed to offer assistance during emergencies through mechanisms such as the Disaster Emergency Committee’s Rapid Response Network. / Costs: The Government’s humanitarian policy commitment to increasingly use the private sector to find new solutions to humanitarian emergencies is not properly acted upon. / The private sector continues to respond to humanitarian emergencies in an ad hoc and largely uncoordinated manner. / Partnerships between NGOs and the private sector for humanitarian response remain few and far between. / The evidence base to support greater private sector engagement in humanitarian response remains limited. / Conclusion: The principal weakness in using this option is that it fails to address the continuing uneven quality and scale of private sector responses to humanitarian emergencies. / Option 2: DFID supports Business in the Community (BITC) to develop a programme to enable companies to better understand how they can assist during humanitarian emergencies, and establish partnerships with NGOs. / Benefits: The support proposed will assist in enabling the UK Government to meet its commitment in its response to the HERR to work to find new ways to engage with the private sector and to bring their skills and expertise into humanitarian action. / Their proposed programme will aim to: / build the private sector’s understanding and commitment to address the challenges of how to respond during humanitarian emergencies; / identify best practice models; / and, build the mutual respect and trust between the private sector and NGOs developing effective collaborative partnerships to be activated on the ground. / In terms of direct responses, this will help to: / improve the speed of response; / and, improve the quality and appropriateness of the response due to the greater breadth of resources and skills NGOs are able to access. / BITC are already well placed to deliver this package of support given the breadth of their membership, and their track record of partnering with the public sector to leverage business to address social challenges. They also have some experience of developing guidelines to enable companies to better coordinate their emergency responses, having done this for DEC in 2003. / As the strategic case mentioned, there also exists a lack of robust evidence to account for the effectiveness or otherwise of NGO-business partnerships in response. This programme will seek to increase that knowledge base through a mixture of both desk based research and interviews, and with the disaster relief award, find companies and examples that are less well known and business areas less associated with humanitarian action. / Opportunities also exist to leverage the impact of this programme of work. The two main opportunities for leverage are BITC’s CSR360 Global Partner Network and business supply chains. The CSR360 GPN offers a powerful infrastructure of local expertise, insight and support through which companies and partners can better work together to mobilise business on this agenda. BITC will actively promote this work to the CSR360 GPN and put in feedback mechanisms to capture interest, engagement, take up and endorsement. / Many of the businesses that BITC will engage with through the project will also have global supply chains and suppliers present in countries in which DFID has country offices. BITC will ask companies to promote action on disasters to their suppliers, and incorporate feedback mechanisms as part of the monitoring and evaluation process to capture this. / BITC will effectively act as an access point for businesses to respond to emergencies by helping to address the commonly perceived themes which prevent successful NGO-corporate partnerships: standard operating procedures, timelines, terminology, guidelines, decision making processes.
D. What measures can be used to assess Value for Money for the intervention? / DFID and BITC will hold quarterly review meetings throughout the life of the project. A monitoring framework will also be established, with the submission of 6 monthly monitoring reports. A mid-term review will be conducted after 2 years, agreeing the terms of reference 6 months in advance. This will be used to assess progress made and decide if funding will continue for the remaining 3 years of the programme. The proposed investment would no longer be considered to offer value for money if the review at the end of 2 years determined that there was insufficient buy-in and interest from the private sector and NGOs around the proposals to develop guidance and best practice, the matching tool, and the disaster relief award for business. / Key measures for assessment of value for money will be determined by the establishment of a baseline in the initial stages of the programme to identify the current level of UK business support for humanitarian emergency response. The indicator for this could be the total annual investment of all activities in financial terms, or the numbers of businesses engaged in disaster relief with data on how they are engaged (corporate donations of cash, products and services, leveraging employee donations etc). This may also entail working with a number of NGOs to measure the level of business investment they receive, including in kind support and staff skills. BITC’s proposal suggests a 15-20% increase on this baseline over the 5 years of the programme. A select measure to monitor progress includes the numbers of new partnerships established between NGOs and businesses attributable to this programme.
E. Summary Value for Money Statement for the preferred option / The preferred option offers value for money, as it capitalises on BITC’s strategic position as a central source of advice and guidance for the private sector and their existing experience of partnering with the public sector to leverage business to address social challenges. BITC has a broad range of experience in: / Identifying, articulating and driving the business case responsible and sustainable business action. / Providing fora to share expertise, information, research and best practice / Capacity building and partnership brokering, whether in the UK or internationally. / Given its wide network of members and experience of working with a number of other UK Government departments, partnering with BITC offers DFID the opportunity to effect sector wide change in humanitarian response. Though difficult to quantify in absolute terms improving the private sector’s coordination during humanitarian emergencies offers the potential to improve the quality and effectiveness of their responses by ensuring that it is only those resources which are both appropriate and needed which are used. It should also help make both funding agencies and NGO more aware of the sorts of resources at their disposal, enabling smarter funding decisions.

Commercial Case

Direct procurement

A. Clearly state the procurement/commercial requirements for intervention / Accountable Grant to BITC.
B. How does the intervention design use competition to drive commercial advantage for DFID? N/A
C. How do we expect the market place will respond to this opportunity? N/A
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? N/A
E. What is the intended Procurement Process to support contract award? / The standard practice for DFID arrangements with “not for profit” (NfP) organisations, is through an Accountable Grant. / DFID will require a review point at the end of phase 1 (2 years) to take stock of outcomes and plans for the next phase before agreeing funds for phase 2 (remaining 3 years).
F. How will contract & supplier performance be managed through the life of the intervention? / No formal contract will be established given the funding route of accountable grant. However, CHASE staff will closely monitor the performance of the project with reference to the log frame, on a regular basis.

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / An Accountable Grant is the standard DFID approach to funding to non-governmental organisations and this responds to a direct approach by an NGO to fund its proposal. / BITC has a long and established history of working in partnership across the UK Government including with the Department for Business, Innovation and Skills, the Department for Education, the Department for Work and Pensions, and the Department for Environment, Food and Rural Affairs. It has also worked in partnership with DFID before, having received funding as one of three organisations for a Pilot Business Outreach Programme in 2010. Its core membership of over 800 companies offers DFID a good opportunity to influence a broad range of businesses with a diverse set of expertise, and to utilise those competencies in humanitarian response.
B. Value for money through procurement / All “not for profit” humanitarian organisations seeking funding from DFID are required to comply with internationally accepted standards and good practice. All NGOs must satisfy DFID that they have sound, effective and efficient financial and other processes in place. / BITC has been assessed on the quality of its proposal submitted for this response. BITC has worked with DFID in other contexts and their past performance noted accordingly.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / Inclusive of VAT Year 1 Year 2 Year 3 Year 4 Year 5 Total / Development of guidance including research £27,000 £27,000 / Support to BITC in the development of a Disaster Award Category in their Annual Responsible Business Awards. £42,000 £42,000 £42,000 £42,000 £42,000 £210,000 / On-going Awareness raising through meetings events and online £25,000 £25,000 £25,000 £25,000 £25,000 £125,000 / Relationship management £24,000 £24,000 £24,000 £24,000 £24,000 £120,000 / Development of Matching Tool concept £35,000 £35,000 / Matching Tool tender, build and testing £100,000 £100,000 / Matching Tool maintenance £12,000 £12,000 £12,000 £12,000 £48,000 / Monitoring and Evaluation £6,000 £6,000 £6,000 £6,000 £6,000 £30,000 / (Contingency) £24,000 £12,000 £12,000 £12,000 £60,000 / Total £159,000 £233,000 £121,000 £121,000 £121,000 £755,000 / Note, depending on where the Matching Tool is on the spectrum from a database to active brokering will have implications on how much of the budget lines for this will be database build in Year 2 and maintenance thereafter or staff time Year 2-5. / Charge Out Rates / International Director International Manager Admin and Events support / Charge out rates/day £900 £600 £400 / Development of guidance including research (Year 1 only) Estimated % of Budget Line / The budget is based on the following tasks: / Background research 15% / Interviews 20% / Writing draft report 20% / Confirming case studies 10% / Reviewing 15% / Design Layout 15% / Posting on BITC website 3% / Production of postcard flyers on guidance 2% / Support to BITC in the development of a Disaster Award Category in their Annual Responsible Business Awards. Estimated % for budget line / The budget is based on the following tasks: / Developing category 3% / Targeting entries 15% / Running Assessment and Judging panels 25% / Writing case studies and feedback 15% / Communicating winners 5% / Developing case studies on winners 10% / Dissemination through BITC website 2% / Disaster Relief workshops for business on best practice. 15% / Guidance for businesses on how to improve their programmes. 10% / On-going awareness raising of NGOs and business through meetings, events or online (per Year, Year 1-5) Estimated % for budget line / The budget is based on the following tasks: / Managing online awareness raising on websites, social media etc 30% / Article writing 5% / Meetings/calls with NGOs, CSR360 GPN members and others 20% / Either an event or a series of smaller meetings 30% / Focus groups or surveys to establish level of awareness 15% / Relationship Management, per year, Year 1-5 Estimated % for budget line / The budget is based on the following tasks: / BITC in-house seminar for national account managers 8% / Writing discussion guide and guidance on data capture and reporting system 4% / Cross referencing and identifying the core group of targets 8% / Targeting businesses with account managers 80% / Development of Matching Tool concept, Year 1 only Estimated % for budget line / The budget is based on the following tasks: / Scoping 5% / Concept Development 10% / Testing of concept at workshop or via feedback from CHASE 20% / Further refinement and creation of brief for database build 20% / Follow up workshop or via feedback from CHASE 20% / Finalising concept 10% / Establish baselines and Monitoring and Evaluation methods, with input from CHASE 15% / Matching Tool tender, build and testing and Matching Tool maintenance / Depending on where the Matching Tool is on the spectrum from a database to active brokering will have implications on how much of the budget lines for this will be database build in Year 2 and maintenance thereafter or staff time Year 2-5. / Monitoring and Evaluation / Estimate per quarter, one day of International Manager and Admin and Events Support and 1/2 day of International Director. This also includes regular meetings with CHASE.
B. How will it be funded: capital/programme/admin? / CHASE programme fund.
C. How will funds be paid out? / As is standard for Accountable Grant arrangements, DFID contribution funds quarterly in arrears, unless there are overriding reasons to justify advance funding and this is agreed at the outset of the project. The AG will be amended if costs or other details alter.
D. What is the assessment of financial risk and fraud? / Minimal. BITC is a trusted partner which has worked with DFID and other UK Government departments on a regular basis. BITC has also undergone a due diligence assessment by CHASE HRG.
E. How will expenditure be monitored, reported, and accounted for? / CHASE Humanitarian Response Group (HRG) will monitor expenditure. Audit, accounting and reporting / monitoring arrangements will be clearly specified in the AG. Final reports are requested within three months of the project completion. DFID requires partners to provide a copy of their certified Annual Audited Accounts (AAA) and that they clearly show DFID funding as a distinct line of income.

Management Case
A. What are the Management Arrangements for implementing the intervention? / CHASE HRG will provide oversight for the 2 year programme. Two programme staff will act as the focal points for monitoring progress and as the principal contact points. / DFID and BITC will hold quarterly meetings throughout the lifetime of the programme to monitor progress. BITC will provide 6 monthly update reports. DFID will require a review point at the end of phase 1 (2 years) to take stock of outcomes and plans for the next phase before agreeing funds for phase 2 (remaining 3 years). / To establish the outcome baseline DFID will work closely with BITC to measure current levels of UK business support in disasters and resilience. DFID will also attend select events funded by the programme and provide a member of staff as part of the panel assessing applications for the proposed disaster relief award.
B. What are the risks and how these will be managed? / Risk Likelihood Potential Impact Mitigation / That the evidence to support further engagement with the UK private sector in this agenda is weak. Low High Initial evidence shows that there is a strong desire amongst business and NGOs to pursue this agenda. / Buy in from key stakeholders not achieved Low Medium DFID engagement in key events including Ministerial or senior participation in disaster relief award. / Humanitarian Response Group humanitarian response leads to resource shift. Medium Low HRG to ensure this is factored into prioritisation of other work streams during response and that contingency is in place. / Matching Tool fails to encourage corporate-NGO partner development. Low High Testing of this concept will be conducted in year 1 of the programme with a shift from active brokering to maintenance of a database with lower costs entailed.
C. What conditions apply (for financial aid only)? N/A
D. How will progress and results be monitored, measured and evaluated? / Results to be assessed against objectives in this Business Case and log frame. / DFID and BITC will hold quarterly meetings throughout the lifetime of the programme to monitor progress and BITC will submit 6 monthly update reports. DFID will require a review point at the end of phase 1 (2 years) to take stock of outcomes and plans for the next phase before agreeing funds for phase 2 (remaining 3 years). Terms of reference for this will be established 6 months in advance.
Lograme / Quest No of logframe for this intervention: