Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Strengthening Tanzania’s Anti-Corruption Action (STACA)
Programme Value: £10.1m from 2012 to 2016		Review Date: February 2016
Programme Code: 202770	Start Date: 21/2/2012	End Date: 31/10/2016

Summary of Programme Performance
Year	2012/13	2013/14	2014/15	2015/16
Programme Score	B	A	A	B
Risk Rating	MD	S	S	S

Summary of progress and lessons learnt since last review

Government of Tanzania partners continue to recognise the value of the STACA programme, and in the light of a new government showing strong commitment to anti-corruption, this programme is strategically well-placed to deliver a key priority both for Tanzania and the UK. This programme is now in its final year, and good progress has been made in implementing some key activities – particularly in outputs 1, 3 and 4. However output 2, involving the police and judiciary, has significantly not met expectations. There are strong lessons in this for the design of any future programme.

Good outcomes have been achieved by the programme in terms of case flow in the criminal justice chain and relations between different agencies. This should be celebrated given the central role of case flow in the theory of change and the challenges presented by working across several institutions. However outcomes related to public trust in institutions and investigation of money laundering have not yet been achieved. The latter continues to have potential but the former is likely not to be achieved by the end of this programme.

There are lessons both for policy and management that should inform remaining work under this programme and also the design and implementation of any future programme in anti-corruption in Tanzania, many of which come out of the recently completed evaluation. Some of these lessons will be applicable in other contexts, as STACA was one of the first of a generation of DFID programmes aiming to improve end-to-end criminal justice responses to corruption.

Summary of recommendations for the next year

Recommendations are as follows:
1. SRO and programme officer to continue to seek detailed information on delivery of activities, both to monitor the programme and to extract learning to inform future support.
2. PCO to ensure any future training courses under the programme establish a baseline and are evaluated afterwards so that the impact can be measured.
3. SRO to decide on whether further disbursements to the police and judiciary will be made, in consideration of the issues identified and the time remaining to implement programme activities.
4. Programme officer to establish a routine procedure for receiving reports on training conducted by the NCA and meeting any financial requirements relating to training.
5. AcT to finalise the ‘telling stories’ document and the externally-written report to ensure that learning from the Integrity Fund is published and available to a wide and relevant audience in a timely fashion.

In addition to these the SRO and DFID programme officer will need to begin preparations for completion activities, including a proposal for asset disposal.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717452.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4779689.xls

Context of corruption in Tanzania
The term ‘corruption’ covers a multitude of behaviours ranging from extortion, bribery, and embezzlement to fraud, collusion and organised crime. It is helpful to distinguish harmful from less harmful manifestations of corruption to describe Tanzania’s recent experience of the issue. Specific forms of corruption in Tanzania include high-level scandals involving million-dollar collusion – such as the IPTL affair – as well as daily extortion by officials, rent extraction for services, and many variations of malpractice in between.

Outline of the STACA programme
STACA was originally conceived as a comprehensive programme supporting both the supply and demand side of anti-corruption work. On the supply side this included working across the criminal justice chain with a focus on case flow and bottlenecks and hence an emphasis on inter-agency working. On the demand side it envisaged an Integrity Fund to support civil society through a grant mechanism coupled with technical assistance. In 2014 a decision was made to implement the Integrity Fund and hence the demand side of the programme through ‘Accountability in Tanzania’ (AcT) – an existing KPMG-managed grant-making programme for civil society. The components of STACA are therefore:
1. Support to Government of Tanzania (GoT) institutions (£9.3m). This support is intended to improve the performance of the institutions most directly involved in tackling corruption. It is also intended to increase public trust and lower expectations of corruption, especially in the Tanzanian Police and Judiciary.
2. Support for a financial investigator from the UK’s National Crime Agency (£0.35m) to assist law enforcement agencies to process complex international aspects of corruption cases. The Financial Liaison Officer is intended to (a) build capacity of Tanzanian agencies to investigate and prosecute financial crime (especially money laundering related to corruption), and to recover stolen assets; (b) assist Tanzanian agencies with direct support in investigations of financial crime, where requested, especially where this crime is related to corruption.
3. Consultancy support to Monitoring and Evaluation (£0.45m) to provide international expertise on anti-corruption and evaluation methods to ensure the programme adapts to changing circumstances and lessons can be captured and recorded.
4. Integrity Fund (£1.2m – transferred to AcT programme budget) to support citizens to demand Government response to exposed instances of corruption, and/or work collaboratively with Government at local level to address problems with a corruption dimension

STACA has been implemented from 2012-2016. The government component is due to end this Tanzanian financial year (June 2016) and the NCA component at the end of October 2016. AcT is scheduled to finish in March 2016.

Theory of change
STACA’s theory of change was revised in 2013 following expert advice. The previous theory had seen corruption in Tanzania as largely a ‘principal-agent’ problem in which corruption is an isolated form of wrongdoing in a largely non-corrupt system. The 2013 revision introduced the concept of the ‘collective action problem’ in which the system provides incentives against integrity, and corruption is not an isolated issue or act by one person.

The current theory of change posits that if capacity building activities are delivered, then an increased number of better quality corruption cases will be developed for prosecution in court, the conviction rate will increase, and therefore a deterrence effect will reduce the incidence of corruption. It also posits that if increased enforcement of anti-corruption measures takes place, and agencies signal the change through public communication, then trust in the police and judiciary will increase, citizens will not expect to pay a bribe, and therefore the incidence of corruption will decrease.

Results
STACA has seen a continued improvement in some of its outcome indicators this year, notably the number of cases in court and the conviction rate. However there is little evidence that this translates into a deterrent effect that might reduce the incidence of corruption.

Tanzania’s high-level indicators of corruption are variable and difficult to interpret.	The following table shows data rendered comparable by the World Bank, comparing relevant international surveys in Tanzania:

Specific Data Sources (0-1)	2006	2007	2008	2009	2010	2011	2012	2013	2014
Bertelsmann Transf. Index - BTI	0.45	0.45	0.45	0.45	0.45	0.45	0.4	0.4	0.4
Global Corruption Barometer - TI					0.43	0.43	0.37	0.37	0.37
Global Compet. Survey - WEF	0.43	0.41	0.32	0.36	0.33	0.41	0.33	0.28	0.32
CPIA - AfDB	0.5	0.5	0.5	0.5	0.5	0.5	0.6	0.53	0.53
AfroBarometer - REPOA	0.76	0.76	0.76	0.76	0.76	0.71	0.71	0.71	0.72

When graphed these sources show variation, suggesting that survey technique has an impact on the results. However a general downwards trend emerged up to 2013, with a possible uptick from 2013-2014:

In light of this, it is worth re-examining the assumptions underpinning the theory of change, though as the independent evaluation noted, “the World Development Report 2011 shows that the twenty fastest-moving countries needed an average of 27 years to bring corruption under reasonable control”. With an effective implementation period of less than 4 years, it would be highly ambitious to expect a change in international survey indicators so soon as a result of STACA activities.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

STACA’s stated outcome is “More effective enforcement of anti-corruption laws and systems”. This is measured through 5 indicators.

Outcome indicator	Performance against Milestone
1. Increased conviction rate in corruption cases / (% of total corruption cases in court in a given year which end in convictions; % of total decisions which end in convictions)	Performance met expectations. / 19% of all corruption cases in court ended in conviction – a 5% increase / 47% of decisions ended in conviction – a 2% decrease / A large number of cases were not decided and rolled over to 2016 – hence the difference between these figures.
2. Increased number of cases presented by PCCB to DPP; Decreased number of cases returned for further Investigation; Increased number of new cases in Court.	Performance met expectations. / 366 cases were presented to DPP – an increase on 2014 but below a programme high of 423 in 2013 / 133 cases were returned to the PCCB for further investigation – an increase from 91 in 2014 / 361 new cases were filed in court – an increase on 238 in 2014 / These figures are a best estimate, as administrative data received vary depending on the source. For example PCCB published statistics do not correspond exactly with figures received from DPP in 2015 (though the difference is slight). No figures were received from DPP in 2016.
3. Increased public trust in police and judiciary / (Afrobarometer survey)	No new Afrobarometer results were released this year. Previous results are from the Round 6 survey in 2014, which shows: / 60% of Tanzanians said they trust the police ‘somewhat’ or ‘a lot’ in 2014, and 60% in 2012 / 68% of Tanzanians said they trust the judiciary ‘somewhat’ or ‘a lot’ in 2014, and 74% in 2012
4. Increased number of detected, investigated, prosecuted, decided and adjudicated cases of money laundering and asset recovery (AR)	Performance moderately did not meet expectations. / No figures were received from the police in 2016. Previous results show: / 45 anti-money laundering (AML)/AR cases were investigated in 2014, an increase on 23 in 2011. / 1 case was prosecuted in court in 2014, 0 in 2013 / 0 decisions were reached in 2014.
5. Selected civil society partners demonstrate credible anti-corruption results, and learn lessons about effective ways of engaging with anti-corruption	Performance met expectations. / AcT provided a vehicle for support to civil society from 2014-16 / 4 NGO partners selected to receive additional funding, leading to increased direct results attributable to the programme (see output 4) / Effective analysis of approaches led to concrete lessons for future work applicable in Tanzania and contributing to a global evidence base

The lack of data available to assess indicator 3 and 4 compromises the evaluability of the programme, so overall assessments are tempered with qualitative information wherever possible.

Overall output score and description

The overall output score is B. STACA has maintained modest but worthwhile achievements throughout the life of the programme, with a strong final year in terms of the National Crime Agency component and the Integrity Fund, both of which made significant progress after a long period of delay. Progress on inter-agency working within the criminal justice system has also been made, though less dramatically.

One powerful example is that the time taken for the DPP to return cases to the PCCB with consent or a request for further action. In 2014, this was on average well over 100 days and in some outlying cases could take over a year. In the latter part of 2015 the average time reduced to well under the statutory limit of 60 days, with no such outliers. This suggests a significant improvement in inter-agency cooperation.

3 out of 4 of STACA’s outputs scored an A, but efforts to strengthen public trust in the police and judiciary have substantially not met expectations. Serious procurement and other concerns arising this year and continuing from last year mean that this component brings down the overall score for the programme.

Key lessons

The following lessons are selected from the independent evaluation of STACA completed just prior to this review, and from a debrief with the former STACA Senior Responsible Owner, Justin Williams:

Policy lessons
1. Lack of robust and high quality data undermines the evaluability of the programme. The Project Coordination Office is not able to produce such data, as it is held internally by government agencies with no cross-agency verification.
2. The theory of change and purpose of the programme as it was envisaged did not translate into relevant government-led workplans. Workplans tended to build general institutional capacity rather than emphasise inter-agency cooperation (e.g. photocopiers for primary courts, model police stations).
3. Following significant delays to implementation, caused by various factors, the actual implementation period for STACA has been relatively short (a little over 2 years). This makes it unrealistic to expect the kind of systemic impact the programme design envisaged.
4. There appears to be more political will in government when corruption is small-scale and/or non-threatening to entrenched interests. This has implications for civil society tactics to address corruption (using inside track or outside track advocacy) and for realistic criminal justice outcomes.

It should be noted that the election of President Magufuli in October 2015 may significantly change the political landscape on corruption and open doors that were previously closed.

Management lessons
1. STACA placed an unusual management burden on DFID due to its high risk and lack of management assistance. The Project Coordination Office has struggled to provide the standard of oversight and management control expected of the programme.
2. The process for approving workplans after grant amounts were agreed meant that DFID in practice had only moderate leverage over what activities agencies chose to use STACA funds for. This process contributed a disjoint between the theory of change and the actual activities.

There are also a series of lessons and learning points arising from the Integrity Fund component which are valuable for future work with civil society on accountability and anti-corruption. These are referenced in the relevant output discussion and will be published once the relevant documents are finalised.

Key actions

SRO and DFID programme officer to begin preparations for completion activities including a proposal for asset disposal.

Has the logframe been updated since the last review?

Yes, an updated logframe was saved to Quest on 14/05/2015 #4979189.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Oversight agencies' performance and cooperation enhanced in the fight against corruption
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 NAO auditors trained in detecting fraud and corruption	2015 - 500 (cumulative inc 120 new auditors trained)	480 auditors were trained to detect fraud and corruption, of which 130 trained in 2014/15. / 130 also trained in giving court testimony, and 40 in fraud and corruption in extractive industries.
1.2 Effective compliance regime used by FIU for increasing numbers of STRs received	2015 - regular inspection of money laundering reporting persons in place	465 people attended 9 FIU workshops from 2012-2015. / 144 STRs were received by the FIU in 2014/15, a significant increase on 84 in 2013/14.
1.3 Case review system in place to improve PCCB investigation of corruption red flags in NAO reports	2014/15 - 90 files investigated annually	125 NAO files were investigated by the PCCB in 2014/15.
1.4 Nationwide telecommunications network established to facilitate information management within PCCB	2015 - 40 out of 96 district offices connected	90% of 96 district offices connected. / Connections allow real-time updates to the Statistical Database. / Connections were observed and functional in Shinyanga and Singida regional offices.
1.5 New Case Docket Management System in DPP established and effectively used	2015 - Case Docket Management System fully functional in 12 regions	Procurement and training ongoing in 7 regions and HQ.
1.6 Effective monitoring system established to track quality of PCCB/ DPP prosecutions	2015 - Joint DPP/ PCCB inspection of 100 corruption cases, which tracks the progress of cases in the courts, develops statistics, monitors quality of prosecutions and adherence to procedures	20 joint district visits took place from 2013-2015 / 700 case files were reviewed. / Qualitative progress is not clear, with a number of issues raised during the evaluation.

Key Points
The log-frame indicators are a selection taken from larger workplans. Not every activity has been covered in this annual review, but a representative sample is used to form a judgement. Also, 40% of funds were not disbursed by DFID until December 2015, meaning that agencies chose either to partially implement activities up to then or to postpone activities until funds were received.

The specific activities under this output have, on the whole, proceeded reasonably well and in some cases well exceeded the expected targets. To some extent this has contributed to the outcomes of a higher conviction rate and higher number of corruption cases in the courts. However there are many missed opportunities, meaning that the activities do not yet add up to more than the sum of their parts. Persistent issues remain across the criminal justice chain, including:
- Delay – at every stage in a case there are unexplained delays that reduce effectiveness. Delays in implementing STACA itself (as highlighted in previous annual reviews) are symptomatic of this.
- Communication – the independent evaluation of STACA highlighted poor communication between PCCB and DPP, but inter-agency communication is recognised as an issue across the chain. This was a key aim in STACA’s original design but few of the activities made progress to improve inter-agency communication (basic case statistics, for example, are still not agreed between the DPP and PCCB).
- Independent and transparent decision-making – in many instances it is not clear why a decision regarding a case has been made, and even management decisions such as who is selected for a training course are opaque.
- Bottlenecks – the requirement for DPP consent to prosecute public officials is a well-known bottleneck, with cases sometimes bouncing between the two agencies 3 or more times. One case remained with the DPP for 1239 days before being returned with consent. On average this delay has reduced over the course of 2015, but continues to slow down the system. Other bottlenecks exist in the courts while cases are assigned and transferred between judges.

The activities under this output were broadly relevant to the theory of change and, despite the ongoing issues, did meet expectations considering the added complication of delays to funding disbursement outside of the agencies’ control. The NAO continues to be a welcome source of leads to the PCCB and good feedback on the identification of red flags was received during a regional visit. Training on identifying corruption during an audit was welcomed by the Controller and Auditor General, but there was no monitoring and evaluation during the training courses. This means that it’s not possible to properly assess the impact of the training. Progress in the FIU looks strong due to the increase in the number of STRs received. However when compared to STRs received by FIUs in comparable countries (e.g. Botswana) the number is still very low, and shows a high degree of non-compliance with reporting obligations by the financial sector and other reporting entities. Due to the sensitive nature of STRs, it is not possible to systematically link STR reporting to the progress cases.

It should be noted that since the election of the 5th phase government in October 2015, significantly more energy and drive has been observed in these agencies. The DPP, for example, has made public press statements about ongoing cases and the PCCB has taken on several new cases exposed by executive action at the Ports, Revenue and Railway authorities.

Summary of responses to issues raised in previous annual reviews (where relevant)

Issue: Lack of progress in AML/AR cases in the courts despite training, reducing the deterrent effect of prosecution.

Response: Complementing training with an embedded PCCB mentor, and promoting use of AML legislation at a high level on specific cases.

Issue: Weak reporting of results.

Response: This continues to be an issue, though this annual review is able to draw on results from the independent evaluation as well as from routine reporting.

Issue: Weak understanding of the logic of STACA activities outside of HQ.

Response: Regional visits during this annual review showed a relatively good understanding of the activities by PCCB and NAO representatives. However the disjoint between the activities and STACA’s overall theory of change was picked up by the independent evaluation.

Issue: External communications activities were not in accordance with workplans or the strategic plan.

Response: This continues to be an issue. Although communications outreach has been done, this has emphasised public awareness of agencies’ work rather than a step-change in performance.

Issue: Some activities were over-ambitious relative to implementation capacity e.g. Case Docket Management system.

Response: This Case Docket system is still not implemented, but other activities are mostly within implementation capacity of the institutions,

Recommendations

1. SRO and programme officer to continue seeking detailed information on delivery of activities, both to monitor the programme and the extract data and learning to inform future support.
2. PCO to ensure any future training courses under the programme establish a baseline and are evaluated afterwards so that the impact can be measured.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Efforts made to strengthen public trust in the Police and Judiciary
Output number per LF			Output Score	C
Risk:		High	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Sting operations in the Police arrest and sanction those involved in petty bribery	2014/15 - 140 officers arrested (cumulative). Follow through (e.g. dismissal, legal action) remains strong	160 officers arrested 2011-2015. / c. 10-20% of arrests lead to a charge. / Remainder transferred, dismissed or reprimanded.
2.2 Model Police Stations established and working effectively	2015 - 15 model police stations in operation where all police forms available and in good supply, special officers available in station during working hours; police standards clearly communicated	3 new police stations constructed and operational. (Katavi + 2 others) / 6 new police stations under construction, not operational. (Simiyu, Manyoni, Ikungi, Lushoto + 2 others) / 6 existing stations under renovation (Geita, Songea, Kigoma, Mtwara + 1 other) / n.b. construction is outside the the remit of approved workplans
2.3 Community policing partnership to fight corruption established	2015 - new community policing initiatives operational in 12 districts	Anecdotal information suggests existing community links reinforced, not newly set up.
2.4 Model Courts established and working effectively	None (funding for Judiciary ended in financial year 2013/14)	Equipment purchased in previous years verified as in place and working. / Re-assignment of 2013-14 funds approved. / Additional funding withheld pending financial review.

Key Points
This annual review discussed only the sample of activities represented in the log-frame. Other activities are recorded in the PCO results matrix and progress report.

Rather than focussing on case flow and the criminal justice chain for corruption, this output built general capacity within the police and judiciary. As noted in the independent evaluation report, this added to STACA being seen as a traditional capacity-building programme rather than a programme to improve case flow thorugh the system. Only police sting operations had a specific focus on corruption, and that was to improve integrity within the police rather than to improve the processing of corruption cases.

Implementation has been particularly challenging for this output. Only the sting operations have been successfully implemented without serious concerns being raised by DFID. Outstanding issues are:
- The model police station activity has been interpreted as an opportunity to build new police stations in 9 districts. Only 3 of these have been completed, and there is no budget available to complete work on the remaining 6. The review team received verbal assurance that a future police budget would cover the costs, but have not received evidence of this to date. Site visits in Singida showed that new stations were ambitious in scale, up to 4 times the actual available budget.
- For the Lushoto station construction, an audit revealed that TZS 375,000,000/- had been paid without a contract being in place. DFID raised concerns about this with the PCO and the Inspector General of Police, and has continued to do so. Because of this DFID is withholding a final payment to the police of £320,000. At the time of writing a contract has been signed and two clarification meetings held, one with the police accountancy section and the other with the PCO.
- Equipment purchased for the judiciary was initially subject to procurement concerns, leading to a procurement review that completed in September 2015. All equipment has now been verified as delivered, and site visits to primary courts in Shinyanga and Singida in January 2016 confirmed this. Because of the issues, DFID insisted on a light-touch review of judiciary financial systems before any further payment can be made. This review has been ongoing since November 2015, largely due to delays accessing information and arranging meetings. DFID is withholding a final payment of £300,000 until it is complete.

Summary of responses to issues raised in previous annual reviews (where relevant)

Issue: A need to communicate the purpose and strategy of STACA more clearly from HQ to regional and district level.

Response: There remains confusion at the local level about what STACA is about. For example in Shinyanga and Singida, the emphasis was on improving customer service and construction of new stations.

Issue: The concept of ‘model courts’ was not implemented, with resources not linked to changes in standards and no public communication around a conscious change. A recommendation was made that no further support should be provided to the judiciary under STACA.

Response: With resources stretched thinly among many courts it is unlikely that the ‘model court’ concept will regain traction. DFID continues to withhold £300,000 allocated to the judiciary in 2014/15, pending the review of judicial financial systems. It remains possible for DFID to pay this in 2015/16, subject to a credible workplan.

Recommendations

SRO to decide on whether further disbursements to the police and judiciary will be made, in consideration of the issues identified and the time remaining to implement programme activities.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	NCA financial investigator assists law enforcement agencies to process complex international aspects of corruption cases
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1. Establishment of effective NCA financial investigator role which meets agreed output targets	2015 - agreed output targets met	Inception report received Feb 2015. / AML/AR training delivered Jul 2015. / Relationship established with all relevant institutions. / Narrative report received Sep 2015. / Close and effective mentoring apparent on high-level cases. / Positive feedback received from heads of agencies.

Key Points
After a slow start, this mentoring role is now delivering effective outputs at pace. Despite initial resistance to having an international mentor embedded, the relationship with the PCCB is now strong, with positive feedback received from the Director-General to DFID in mid-February. A less close but still productive relationship is also in place with the FIU, and positive feedback has been received from the FIU Commissioner.

A development programme for regional PCCB officers on AML/AR has taken place in Arusha, though it is too early to assess whether this will lead to an increase in the number and quality of cases charged under money laundering legislation. There are also several other initiatives to train PCCB staff in AML/AR, including from the International Centre on Asset Recovery and the Stolen Asset Recovery Initiative.

Summary of responses to issues raised in previous annual reviews (where relevant)

Issue: Use of the financial investigator’s time on NCA work unrelated to corruption or capacity-building should be minimised.

Response: It is important in the DFID-NCA relationship to recognise shared objectives where they exist, and also to recognise the added value of using UK-related casework as an entry point for mentoring and capacity building. However unrelated work should not prevent the financial investigator from engaging in the core work of supporting Tanzanian corruption investigations. This is no longer a cause for concern, but DFID should lightly monitor the situation in future.

Recommendations

Programme officer to establish a routine procedure for receiving reports on training conducted by the NCA and meeting any financial requirements relating to training.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Citizens supported to demand Government response to exposed instances of corruption, and/or work collaboratively with Government at local level to address problems with a corruption dimension
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Individual case studies of each of the partner organisations funded through STACA, plus an overview comparing and contrasting their strategies, to elicit lessons learned	Identification and documentation of case studies / Strategic workshop with AcT partners to compare and contrast	4 partners selected to receive additional grants for deepening results in integrity and anti-corruption / Joint field visits and a learning event held to compare strategies / Case studies documented by partners
Documentation of how this pilot year has been approached, particularly in terms of learning opportunities for partners and how they have responded	‘Telling Stories’ document summarising the approach, and key learning	High-quality draft received in March 2016, including analysis of strategies and learning opportunities
Implications of the above two for donor support to anti-corruption work going forward	Externally-written academic report summarising implications for donors supporting civil society anti-corruption activities	First draft received, awaiting further amendments and proof-reading

Key Points
Earlier years of the programme were challenging for this indicator, facing considerable delays because a credible implementing partner could not be found through the competitive procurement process. In 2014 a decision was taken to implement this component through the existing AcT programme, making use of existing partners and relationships. The Integrity Fund is able to demonstrate worthwhile results in the communities it has supported even with a very short implementation period (1 year). But its main result is the learning generated by documenting different partners’ strategies and approaches to related integrity and corruption issues. Four of AcT’s 29 existing partners were selected to receive additional funding: Norwegian Church Aid, Tanzania Forest Conservation Group, HakiKazi Catalyst, and Tandabui Health Access Tanzania.

In terms of direct results for communities, the Fund supported the identification of c.TZS 26m/- (£8000) misused funds, and led to the return of TZS 1.3m/- (£400) plus TZS 12m/- (3,700) p.a. going forward. It also led to an additional TZS 19m/- (£5850) made available to communities through compensation. Non-quantifiable results include 300 land plots that were at risk of expropriation secured for villagers, and reduced ecosystem damage from illegal mining, forestry and charcoal burning.

The main learning points coming out of the analysis of Fund activities are as follows:
1. Effective partner strategies are based on supporting groups of active citizens
2. For Citizen Action to be effective it has to be flexible and able to work through formal channels as well as informally
3. Most ‘corruption’ cases are highly complex and time-consuming.
4. Complexity and culture also influences what constitutes resolution of a corruption issue

The final learning point has significance for wider anti-corruption programming, in that fixating on prosecution outcomes isn’t necessarily the best solution to grievances arising from corrupt behaviour. The final product (externally written academic study) links the learning arising out of the Integrity Fund to existing themes in anti-corruption and accountability literature, and will identify the contribution to the evidence base that this component has made. The conclusions of this will be available publicly and add to the global store of knowledge on these issues.

Summary of responses to issues raised in previous annual reviews (where relevant)

Issue:
This component should be moved to the AcT programme and the logframe and ARIES updated accordingly.

Response:
The STACA log-frame has been updated and the civil society component removed. However it is still appropriate to reflect the results of the activity in this Annual Review for the following reasons:
- The funding for this activity was originally approved as part of the STACA business case and is consistent with the aim of STACA being a broad anti-corruption programme rather than one narrowly focussed on the justice sector.
- AcT will not have another Annual Review, being in its final year. A Project Completion Review will take place for the entire programme (£36m since 2009) which is unlikely to cover the Integrity Fund in as much depth given the breadth of its remit. It is important to capture the results and learning from the Integrity Fund in formal review documentation.

Care will be taken to ensure that the results are not double-counted under both programmes.

Recommendations
AcT to finalise the ‘telling stories’ document and the externally-written report to ensure that learning from the Integrity Fund is published and available to a wide and relevant audience in a timely fashion.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Key costs in the STACA programme are personnel (salaries and per diems), training costs such as conference packages, and equipment (motorcycles etc). These costs are largely determined by the Government of Tanzania through the workplans prepared each year.

The cost drivers are largely as expected, but the decision not to use a managing agent for STACA means that management costs are 2% lower than planned. While this may seem positive, it is important to note the concerns around programme management that have been raised in successive annual reviews.

Costs relating the NCA component have been significantly reduced following negotiations with the NCA – 30% below the originally quoted figure.

VfM performance compared to the original VfM proposition in the business case

The following indicators were cited in relation to VfM in the business case, with a comment on this year’s performance:

Indicator	Performance to date/ Comment
Effectiveness (how well our outputs will achieve our desired outcome)
% of low income households paying bribes and the % of the public that encounter police, judiciary or magistrates and pay a bribe. (both measures expected to decrease)		Previous reporting on this indicator used Global Corruption Barometer (GCB) data from 2011 and 2013. The report 2015 shows: / 25% of Tanzanians paid a bribe in the past year, down from 56% in 2013. / 35% of those in contact with the police or judiciary paid a bribe, down from 62% for the police in 2013 and 52% in the judiciary. / However further investigation with the data producers (REPOA) suggests that time series may not be comparable in this dataset, so to compare across years is misleading.
% of targeted citizens who believe that Government is committed to tackling corruption in the public sector and/or % that are willing to complain about corruption. (both measures expected to increase)		GCB data was also used previously, but the latest data does not specifically cover this indicator. The closest result is that 37% of Tanzanians surveyed say ‘the government is doing well in the fight against corruption’. Data was collected in 2014.
Number of corruption cases reported and/or % of reported cases investigated by PCCB and/or % of investigated cases that are accepted for prosecution. (all measures expected to increase)		5000 leads received by PCCB, broadly consistent with previous years. / 802 files opened (16% of leads) – broadly consistent / 361 new cases filed in court – an increase
Number of complaints concerning the police and judiciary that are received and acted on (expected to increase in the short term as confidence grows in reporting mechanism, then decrease in long term as complaints reduce)		Data not available.
Efficiency (how our inputs are converted into outputs)
Increase in the number of fraud cases detected by NAO as a result of staff trained on fraud detection, new fraud detection system being installed and forensic/special audits conducted		Data not available.
Increase in number of complex corruption cases detected and prosecuted as a result of PCCB, FIU and DPP staff being trained		Data not available. Anecdotally, the number of grand corruption cases is driven by scandal arising from journalism or executive action, therefore a poor indicator of skills development in PCCB, DPP and FIU.
Decrease in perceptions of corruption in traffic police in pilot areas as a result of measures introduced by programme		Data not available.
Economy (inputs being purchased at the appropriate quality and right price)
Overhead costs of the managing agent will be monitored. These should not exceed 10% of the cost of the programme, as benchmarked against programmes with similar management structures		Managing agent not recruited. / PCO costs (replacing managing agent) are c.8% of programme total, but deliver less management functions.
Unit costs for the provision of technical assistance and training will be monitored to ensure high quality assistance at a reasonable price. The managing agent will be asked to benchmark this against the equivalent provided in Tanzania and internationally.		No private TA is provided. Government to government mentoring such as NCA is not directly comparable to private TA. Costs to DFID of the NCA MOU are c.30% lower than originally quoted.

Assessment of whether the programme continues to represent value for money

STACA has been moderately effective but lacks sufficient data to demonstrate this conclusively. Prior to release of the GCB data for 2015, indicators for effectiveness appeared to be declining. There is some positive movement also in the outcome indicators – suggesting better flow of cases in the system – and as the most comprehensive development programme in this area STACA should receive due credit. A more accurate assessment of STACA’s effectiveness at each level would require more granular data from the institutions, which is not currently available (though the PCCB Statistical Framework and Judicial Dashboard may make it partially available in future). The evaluation report on STACA came to a similar conclusion that “there are mixed signs for STACA’s effectiveness, and the programme needs to improve its evaluability to answer these questions with certainty.”

Some activities have been inefficient, but this also needs more data e.g. number of staff trained to a specific level. This financial reporting is not yet available, though budgets do give some indication of expected costs. In retrospect the indicators suggested in the business case do not, even if they could be measured, accurately indicate efficiency e.g. traffic police was not a major focus of the programme. The evaluation report, in discussing efficiency, said: “the poor efficiency of the activities concerning provision of equipment to primary courts, the FIU awareness workshops and construction of Police Posts are powerful examples. These examples are manifestations of a larger systemic problem with the management structure of the programme.”

It is worth quoting in full the evaluation report conclusion on the management structure of STACA:

“The budget for the PCO constituted 10% of the total funds of Component A. Yet, this setup did not deliver a good supervision of activities. The PCO was hampered by the lack of clear targets, indicators and M&E capacity from the outset, and continued to struggle with monitoring throughout the programme. It is hard to manage a complex programme effectively without basic records and data of the activities performed, and the PCO did not possess this information.”

Issues in PCO management were raised in previous reviews, particularly where VfM is concerned, but it should be recognised that the PCO is only 3 people coordinating all the work of 6 government institutions. The PCO has met basic standards of reporting and has also conducting some field monitoring of activities. However its place within the Steering Committee and Technical Committee set-up of STACA has meant that it is unable to critically challenge institutions and extract management information of a quality expected by DFID.

Some economy savings were achieved, but as in other areas the lack of high quality data makes a proper assessment difficult. Economy measures show reasonable unit costs where data is available and significant savings in the NCA contract and the managing agent. This latter is not a straightforward saving, as the service received is quite different to that of a managing agent. Some management functions are not provided by the PCO, but it does enhance Government buy-in to the programme.

In spite of the concerns above, it should be noted that the PCO continued operations through the extension of STACA into 2015/16 without additional funding. This is a worthwhile economy and has meant other activities could be implemented, meaning that the programme has had an additional year to be effective. PCO familiarity with government procurement systems also meant that in some cases better economy could be achieved. For example in the construction of new police stations (an issue discussed elsewhere) the ‘Force Account’ procurement regulation was used to lower construction costs of some stations. This involved using pre-existing government staff, in this case police officers, to implement the activity, rather than prepare a contract with a private provider. A further advantage of the PCO structure is that government buy-in at technical level was maintained in a challenging political environment.

STACA on balance represents value for money, especially considering alternatives in a context of low political will to drive reform. Financial aid to the PCCB, FIU, NAO and DPP was used to deliver improvements in inter-agency working and strengthen capacity, and following significant delays the NCA and Integrity Fund components were able to deliver strongly in the final year. Weaker value was achieved in work with the police and judiciary, particularly around model police stations and model courts. While individual economies were achieved (e.g. through the use of Force Account procurement) the activities did not appear to increase public trust in a measurable way, and issues with contracts and equipment delivery undermined efficiency.

Quality of financial management

As a financial aid programme that includes a component grant to another UK agency and a flexible consulting component, STACA’s financial management is relatively complex. This means there are multiple budgets associated with the programme alongside the main ARIES budget, including:
- The original MOU, which is extended by letter into 2015/16, with the 2014/15 budget being split between both years. This does not include additional PCO costs that arose in the early years of the programme and were budgeted separately;
- Budget from each government institution alongside its annual workplan, by Tanzanian financial year (Jul-Jun);
- Expenditure report from the PCO covering each year, periodised by Tanzanian financial year plus 6 months (i.e. 18 months from July to the following December);
- Budget and expense report from the National Crime Agency covering costs of the mentor plus any training and equipment expenses;
- Ad-hoc budgets and expense reports related to consultancy contracts e.g. the evaluation.

The programme is likely to underspend significantly in its final year due to withholding of final payments to the police and judiciary, NCA component coming in under budget and less consultancy activity than expected. This underspend is likely to be over £600k at current estimates.

Within the government component, there are some outstanding concerns regarding financial management that have been noted elsewhere but are worth laying out as part of this review:
1. Receipts from the Ministry of Finance are not available for every disbursement, despite repeated follow-up. This makes it challenging to reconcile expenditure reports with the amount actually received in TZS by the institutions;
2. Disbursements typically reach the implementing institutions late in the financial year, limiting the amount of time available for implementation, reducing their ability to plan, and complicating subsequent financial reporting (see below);
3. Inconsistency in use of financial years between the PCO (Jul-Dec) and MoF (Jul-Jun) mean that budget and expenditure figures do not reconcile during the year or with the published budget figures;
4. Unauthorised use of funds for activities not specified in the workplans e.g. construction of new police stations;
5. Asset registers were received very late following repeated requests for follow-up;
6. A light-touch review of judiciary financial systems has been ongoing since November 2015. Delays have been largely due to lack of responsiveness from the judiciary e.g. to requests for meetings and documents.

For the NCA component, previous issues with invoicing are now on track, with the last invoice paid in February 2016. Financial management has also improved, allowing more accurate forecasting. There is however a need for an improved per diem payment process for training courses with government institutions to avoid delays.

Date of last narrative financial report	January 2016
Date of last audited annual statement	May 2015

E: RISK (½ page)

Overall risk rating: Minor/Moderate/Major/Severe

Severe (formerly High – mapped to Severe under new risk categories)

Overview of programme risk

Programme risk continues to be high, but there has been a significant change in the operating environment since the election of the 5th Phase Government in October 2015. There now appears to be significantly higher political will to tackle corruption, which has an impact on a number of risks previously identified.

The other significant change to risk management is the requirement to consider the Overseas Security and Justice Assistance (OSJA) guidelines in relation to this programme. This has not been done previously due to the programme’s focus on anti-corruption rather than security and justice, but close working with institutions in the security and justice sector – particularly the police – warrant a closer scrutiny of human rights risk.

An updated risk table is below:

Risk Description		Proba-bility (L,M,H)	Impact on Success / (L,M,H)	Mitigating Actions / (in Business Case)	Update March 2016
Risk 1	Programme relationships negatively impacted by wider pressures building in GBS/SBS relationship around underlying principles etc.	M	H	- Strong communication of results / - Strong relationship with the heads of implementing institutions	GBS is no longer provided. / There have been tensions related to the Zanzibar elections, but not so far impacting the programme. / IPTL remains an outstanding issue between donors and the government.
Risk 2	Low political will means that capacity built through STACA cannot be used	M	H	- GBS dialogue intended as a test political will, focusing on the willingness of the Government to pursue the active fight against corruption. / - Progress against outcome indicators will give an objective sense of whether the fight against corruption is progressing / - Non-government component of the programme will help to some extent but will not deliver political will on its own	Significant improvement to political will following the Oct 2015 elections. / However new government still in early days and too soon to reduce the risk level. / Legal action against high level suspects remains ineffective, but with potential improvements underway with new PCCB leadership. / Risk remains otherwise very difficult to mitigate.
Risk 3	The UK seen as not being the right bilateral donor to lead on an anti-corruption programme because of its own recent corruption record in relation to Tanzania	L	M	- Provide world class expertise – if the product is useful, this will overcome concerns / - The recent introduction of the UK Bribery Act may help to counter the negative impressions of the UK on corruption	No impact so far on the programme. / Growing closeness of cooperation with UK since CJA and NCA mentor relationships have grown. / President directly referenced close UK cooperation on corruption and organised crime in recent statement.
Risk 4	The Judiciary is not fully committed to working with the UK on tackling corruption and may therefore block work in this area	H	M	- programme of support to the judiciary will only take place under strict conditions including clear commitments from the judiciary themselves (to be initiated through early high-level engagement with the Chief Justice) / - the programme’s focus on the primary courts may offer a less contentious entry point than seeking to tackle higher level corruption	CJA engagement may lead to closer working with judiciary at senior level. / Focus on the primary courts has in fact reduced entry points for talking with judiciary about corruption case flow, as most cases are heard in magistrate or high courts. / Administrative issues with procurement have meant a challenging relationship with the judiciary – funds are currently withheld pending resolution of issues.
Risk 5	Programmes supporting police reforms or working across the security and justice sectors are normally categorised as high-risk. The possibility of high level political/public criticism is present especially in the event of allegations of a human rights breach	H	M	- Capitalise on the Inspector General of Police’s commitment to act. Ensure that interventions supported have a clear benefit to the police and judiciary / - Closely monitor progress and be prepared to alter the programme or cease support if there is no traction / - monitor closely (through CGA and other mechanisms) HR record of police	This risk remains pertinent due to low management oversight of day-to-day activities. / An OSJA assessment will be conducted to provide further detail for assessment. / No human rights allegations have so far been made in relation to this programme.
Risk / 6	Consultancies do not deliver the high quality work needed	M	M	- clear specification of consultancy requirements and outputs will help mitigate this risk / - use of results based management, checking that milestones have been achieved before disbursing next payment.	Only 1 consultancy has been procured so far, with clear ToRs and objectives. / Final payment is pending until final report is received and published. / Strong QA has been needed on the final report, but following that it is now of sufficient quality and provides useful lessons to inform this and future programmes.
Risk / 7	Corruption is uncovered in the programme, undermining its credibility and forcing DFID to suspend funding	H	M	- due diligence of NCJF and project partners before disbursing funding / - development of clear workplans with measurable results, and payment by results / - annual audits with in-depth checks on high risk spend such as procurement and workshops / - DFID will authorise any procurement over £100,000 / - annual reviews to look at corruption prevalence and risk, and whether managing risk adequately / - publish information on support given to each institution, and establish complaints mechanism to facilitate reporting of any abuses.	This risk remains high probability given weak management. / Issues around procurement have repeatedly arisen, leading to a procurement review and to withholding of payments to the police and judiciary. / Issues so far do not amount to corruption within the programme. / CFWU is kept informed of all concerns as they are raised.
Risk 8	Risk that capacity building initiatives are not effective in improving capacity. For example risk that training is low value or does not lead to improvements in knowledge and skills; that equipment is the wrong specification, is delivered to the wrong location or that people are not trained to use it, etc.	M	H	- close scrutiny and discussion of workplans before approval / - keep requests for equipment and study tours to a minimum except where there is a very strong case / - suggest other changes to improve effectiveness (e.g. publication of research and studies) / - PCO to step up work on monitoring and delivery of workplans / - request for DFID to attend a higher number of STACA-sponsored events / - use NCA advisor to provide support to institutions in designing activities / - increase frequency of field visits	There is limited capacity within DFID to mitigate this risk entirely through direct monitoring. / However programme controls such as procurement reviews, field visits and audits provide mitigation against improper purchases of equipment and delivery to the wrong recipient. These mitigations have worked to identify and correct issues as they arise e.g. delivery of equipment to primary courts. / Baseline data is not collected for most training events, making evaluation challenging. / NCA involvement in training provides significantly more assurance of effectiveness.

Outstanding actions from risk assessment

An OSJA assessment needs to be conducted and recorded with the appropriate level of approval.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Government component: delivery of planned activities has been delayed for a number of reasons since the start of the programme. In 2015/16 this has been less of an issue, due to the same work plans rolling over from the previous year allowing a longer lead-in and implementation time for activities. However activities under the police and judiciary have continued to be delayed due to DFID withholding funds.

NCA component: in previous years this component has suffered significant delays around the recruitment of the mentor. However, the mentor has been in place for the whole of 2015 and during that time has built strong relationships enabling effective delivery. Examples include training courses for PCCB investigators on money laundering and asset recovery.

Consultancy: the one consultancy contract entered into has been extended due to delays delivering the final product. These were in part due to release of information to the evaluation team and in part due to HR issues within the supplier and the timing of the delivery date over the Christmas period. This delay has not significantly undermined the activity, as the lessons are still available in time to inform this annual review and the design of a future programme.

Performance of partnership (s)

Partnerships are functioning reasonably well, and the UK is recognised as a trusted partner on anti-corruption issues. The presence of mentors able to assist in direct and operational way with UK-related casework makes a difference to these partnerships and adds value to the funding relationship held by DFID.

Government representation at meetings has been relatively consistent, and the SRO has been able to hold constructive 1-1s with each of the heads of institutions in a relatively short time. The relationship with the PCO has remained constructive, despite a number of challenging issues to resolve – including delivery of results and financial reporting and follow-up of procurement concerns. It is recognised that some of these challenges stem from the fact that the PCO need to chase government institutions for the requested information. The Project Coordinator has been replaced this year following the untimely death of the previous coordinator, and the vacancy period reduced the capacity of the PCO for several months.

The partnership with the NCA has improved thanks to progress on financial reporting and closer working with the PCCB, and a closer link between the programme and other HMG initiatives including the Criminal Justice Advisor has been made in recent months.

Asset monitoring and control

Asset monitoring has been a challenge throughout this programme, though some progress has been made in 2015-16. The main areas of progress have been:
- Resolution of the judiciary procurement issues: equipment intended for the primary courts was procured by the judiciary but not delivered to the intended recipients. This has now been delivered and the review team saw evidence of this in Shinyanga and Singida during a field visit.
- Completion of asset registers: these are now received and include relevant and detailed information on assets purchased by the programme. However there is still some information missing, and further improvements are possible.

Over the coming months it will be necessary to establish a strategy for asset disposal for each component of the programme. This should include updating information from the asset registers and a clear position on what happens to the assets after the programme closes and any residual responsibility owed by any of the stakeholders.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Corruption remains an important part of the Underlying Principles (UPs) – which were jointly refreshed by donors in January 2016. The directly relevant principle for this programme is UP5, which covers “Good Governance, accountability of the government to the citizenry and integrity of public life, including the active fight against corruption in accordance with the laws of the United Republic of Tanzania”.

This programme does not give financial aid to the government of Zanzibar, for which a separate assessment of partnership principles is under consideration.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The most significant update on evidence and evaluation in 2015-16 was the evaluation study commissioned by DFID for the programme. The successful bidder for this study was the U4 Anti-Corruption Centre/Chr. Michelsen Institute in partnership with Research on Poverty Alleviation (REPOA), a well-respected Tanzanian think-tank who also conduct the annual Afro-barometer surveys. The in-country work for this evaluation concluded in November 2015 and a final report is due to be received in March 2016 following in-depth consultation with government stakeholders. This evaluation used a case study methodology to look deeply at 6 activities supported by the programme under the government component, and draw conclusions about effectiveness, and lessons for the future based on these.

Several of the findings of the evaluation have been used to inform this annual review, in particular the conclusion that “STACA has already proven its relevance and has been effective in reaching a number of pre-defined performance indicators”. One of the notable findings, however, was that DFID and the government representatives of the programme appeared to have different ideas about the theory of change and the relevance of some of the activities, which undermined effectiveness in some areas. This is an important point for the design of any future programme, which must consider government uptake of ideas and ambitions. The final report of the evaluation made 9 recommendations based on its findings, which are presented in the executive summary.

Other relevant developments in the evidence base include the publication of the following studies:
Hazel Gray, 'The Political Economy of Grand Corruption in Tanzania' African Affairs, 114, 456, (July 2015) 382 – 403
This provides critical analysis of grand corruption, including commentary on four recent high-level cases. It brings out the political drivers of corruption in Tanzania with implications for donor programming.
Heather Marquette and Caryn Peiffer, ‘Corruption and Collective Action’ U4/DLP, Research Paper 32 (January 2015)
This paper was recently cited in a submission to the International Development Committee and provides information on evolving best practice to inform any future donor programming.
AfriMAP, ‘Effectiveness of Anti-Corruption Agencies in East Africa’, Open Society Foundations (December 2015)
This article covers the performance of the PCCB including detailed institutional information of relevance to the STACA programme.

Monitoring progress throughout the review period

This annual review was carried out by a review team led by the SRO, including the DFID programme officer and the PCO. A field visit was conducted in Shinyanga and Singida regions and one-to-one meetings held at head of agency and technical level to discuss progress over the last 12 months. Key documents were reviewed, including the business case and previous annual reviews, the delivery plan, and a range of reporting documentation provided by the PCO. In between annual reviews the programme is monitored by the PCO and overseen where possible by the SRO and DFID programme officer.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process