Business Case and Intervention Summary

Intervention Summary

Title: Neglected Tropical Diseases Implementation Research Programme (NIRP)

What support will the UK provide?
DFID will provide up to £15 million over a 5-year period (2013-2018) for 1-3 substantive programmes of Integrated Neglected Tropical Disease (NTD) Control Implementation Research. The research will be conducted alongside, and inform, the implementation of disease control initiatives on the ground.

Why is UK support required?
At any moment in time over 1 billion people globally, 400 million in Africa, are infected with or at risk of one or more Neglected Tropical Diseases (NTDs). This group of infections represent the most common diseases for the 2.7 billion people living on less than US$2 a day and cause loss of livelihood, disfigurement, stigma, disability and poverty. As a signatory to the 2012 London Declaration, the UK has publically committed to leading the fight against these diseases. / Seven diseases – blinding trachoma, schistosomiasis, elephantiasis, river blindness and three soil-transmitted helminths – are responsible for 90% of the total global burden of NTDs. These same 7 diseases can be treated and controlled by a simple oral package of 4 drugs administered to high risk populations once or twice a year. Studies have suggested that integrated NTD control initiatives are highly cost effective and that the integrated delivery of mass drug administration (MDA) activities could be implemented for as little as US$0.40-0.79 per person/year in sub-Saharan Africa. Cost savings associated with integrated MDA to address multiple NTDs concurrently have been estimated at 26-47% compared to non-integrated programmes, offering the potential for increased efficiency and intervention coverage. / However, delivery of integrated NTD programmes at-scale is at a relatively early stage and much remains unclear. Implementation research is needed to inform the optimal delivery and monitoring of integrated NTD programmes, to ensure we have the right tools and the right knowledge to cost-effectively, equitably and sustainably control NTDs across a range of settings and contexts, and thus maximise the likelihood of achieving the 2020 NTD control, elimination and eradication targets. Getting the best combinations of drugs and measures to deliver them includes biological questions (do drugs combine safely and effectively) and operational questions to maximise delivery effectiveness and cost-effectiveness.

What are the expected results?
This programme is intended to contribute towards the ultimate impact goal of achieving the WHO 2020 NTD control, elimination and eradication targets[1] through informing improved Integrated NTD Control Programmes on the ground (outcome). / It will do this through the commissioning of high quality implementation research conducted alongside integrated NTD Control initiatives on the ground. / The main output areas will be: / Increased knowledge and evidence for safe, effective, cost-effective and sustainable integrated NTD control in disease endemic countries. / New, generalisable knowledge communicated within and beyond disease control programmes alongside which research is conducted.

Business Case
1 Strategic Case

Context and need for a DFID intervention / Neglected Tropical Disease Burden and Control / At any moment in time over 1 billion people globally (500million in Africa) are infected with or at risk of one or more Neglected Tropical Diseases (NTDs). This group of infections represent the most common diseases for the 2.7billion people living on less than US$2 a day and cause loss of livelihood, disfigurement, stigma, disability and poverty[2]. These diseases can lead to irreversible blindness, chronic illness, physical deformities and death. The term NTDs is used by the WHO for 17 parasitic and bacterial infections[3] with different distribution, transmission, vector involvement, zoonotic aspects, pathology, and requirements for prevention and control. This business case focuses on implementation research to enhance efforts to control 7 of these NTDS which are together responsible for 90% of the total global NTD burden[4]: / Blinding trachoma / Schistosomiasis (Bilharzia) / Elephantiasis (Lymphatic filariasis) / River blindness (Onchocerciasis) / Soil-transmitted helminths – hookworm, roundworm and whipworm / While a lack of appropriate diagnostics and/or drugs are major barriers in the battle against certain other NTDs such as sleeping sickness and leishmaniasis[5], the 7 NTDs addressed in this business case are preventable by a simple oral 4-drug[6] treatment package administered once or twice a year. These drugs are currently donated in whole or in part by the pharmaceutical industry. / Since 2006 there has been a growing movement towards greater integration of NTD mass drug administration (MDA) programmes due to geographic overlap of endemic areas and a common requirement for preventive chemotherapy (PC). Studies indicate that integrated NTD programmes are highly cost effective and that integrated delivery of MDA could be achieved for as little as US$0.40-0.79 per person per year in sub-Saharan Africa[7]. Cost savings associated with integrated MDA (as opposed to vertical, single disease focussed programmes) have been estimated at 26-47% compared to non-integrated programmes[8], and offer the potential for increased efficiency and coverage. Despite calls for integrated programmes and some similarities in the prevention and/or management of multiple NTDs, there are also significant differences and in-country implementation of integrated activities by government agencies remains at an early stage. Figure 1 demonstrates the current rate of scaling up of integrated MDA against the required trajectory if the WHO 2020 NTD control and elimination targets are to be achieved. / Substantial challenges and significant questions remain when initiating, scaling-up and/or replicating the practical integration of activities that have different epidemiological goals, different control methods, different funders and different programme delivery partners on the ground[9]. For example, it remains unclear how best to integrate preventative chemotherapy for schistosomiais and/or trachoma within mass drug administration (MDA) programmes for onchocerciasis, lymphatic filariasis and the soil-transmitted helminths; or how best to ensure and measure drug adherence or to track adverse drug reactions and/or the development of drug resistance; knowledge is limited regarding the best delivery mechanisms for effective and sustainable MDA or what the preventive chemotherapy frequency should be under different conditions; and countries are lacking simple surveillance and monitoring and evaluation systems that allow them to track their own progress towards NTD control targets. / However, as figure 1 demonstrates, these challenges and questions need addressing if we are to stand any hope of reaching the 2020 targets. / Figure 1: Current versus required rates of NTD preventive chemotherapy coverage rates for reaching the 2020 NTD control and elimination targets. / Implementation research[10] is clearly needed to inform the optimal delivery and monitoring of integrated NTD programmes delivered at scale, and to ensure we have the right tools and the right knowledge to cost-effectively and sustainably control NTDs across a range of settings and contexts[11]. / Stronger evidence relating to the effects of NTD control campaigns to health systems and service delivery and, conversely, on the impact of the state of the wider health system on the effectiveness of NTD control efforts is also required[12]. Integrated NTD control programmes have the potential to enhance elements of the general health service (e.g. surveillance systems, health workforce and health service reach) but may also introduce negative distorting effects. However, policy makers and donors need guidance on how best NTD control programmes can leverage the wider health system and vice versa to allow for not just stronger NTD control but more robust, efficient healthcare delivery in general[13]. / Fit with DFID Priorities and International Development Frameworks / The Coalition Government has significant commitments relating to the prevention and control of infectious diseases of poverty. This is demonstrated through the DFID Business Plan 2011-15 which honours international commitments to support the achievement of the Millennium Development Goals (MDGs) and restrict the spread of major diseases. The plan states that the generation of evidence and the translation of this new knowledge in to policy and practice has the potential to significantly improve rates of return on DFID’s investments in these areas by informing funders, policy makers and implementation programme managers on the most cost-effective and sustainable tools and strategies to treat and control infectious diseases. / Neglected Tropical Diseases / The UK is a key player in the control and prevention of NTDs, alongside the WHO, USAID and the Bill and Melinda Gates Foundation (BMGF). In 2011, Minsters approved DFID’s greater involvement in NTD control with an additional funding of £195 million between 2011 and 2015 (with £20 million of this committed specifically to research). This commitment was formally announced at the January 2012 event marking the launch of the London Declaration on NTDs and associated WHO NTD Roadmap for Implementation which lays out ambitious NTD elimination and eradication targets by the year 2020. These targets include the eradication of Guinea worm and yaws; the global elimination of trachoma, leprosy, elephantiasis and sleeping sickness; the regional elimination of rabies, Chagas disease, visceral leishmaniasis and schistosomiasis; and a target to achieve at least 75% regular deworming treatment coverage amongst preschool and school-aged children in all countries endemic for soil-transmitted helminths. / DFID’s Human Development Department operational plan 2011-2015 outlines the headline results the UK will achieve through directly financing global public goods to support reduced prevalence of NTDs. This business case compliments these commitments through the commissioning of intervention research to enhance the cost-effectiveness and sustainability of NTD control programmes on the ground and represents £15 million of the £20 million new ministerial commitment for NTD research. / Generating Evidence and Facilitating the Transfer of Research into Use / Decision-makers across the world need to base their decisions on information from reliable sources. DFID uses research to release the power of knowledge and technology to fight poverty, achieve the MDGs, inform discussions about future development frameworks and make sure development continues for future generations. We work with developing countries to identify major research challenges and then help tackle them with good scientific advice. We have a strong reputation for feeding useful research into the work of the international development community and our commitment to research has been growing in recent years. / DFID’s investment in research has three main aims – 1) developing new technologies and innovations that have impact on poverty or its effects, 2) finding better and more cost-effective ways of delivering development to those who need it, including stopping things that do not work, and 3) better understanding of key development questions and background to support the best policy decisions. This business case pertains to the second aim and is intended to inform the more cost-effective and sustainable scaling up of integrated NTD control programmes and thus better enable the achievement of the WHO 2020 NTD control, elimination and eradication targets.
B. Impact and Outcome that we expect to achieve / This programme of NTD Implementation Research is intended to contribute towards the ultimate impact goal of achieving the WHO 2020 NTD control, elimination and eradication targets[14] through informing improved Integrated NTD Control Programmes on the ground (outcome). / The results chain below indicates how this will be achieved. / While at this stage we cannot be clear exactly what new evidence will be generated, examples of the types of knowledge that might be gained include, but are not limited to, information about: / How best to integrate preventative chemotherapy for schistosomiasis and/or trachoma within MDA programmes for river blindness, sleeping sickness and the soil transmitted helminths; / Levels of and factors influencing drug adherence; / The potential for drug resistance; / Optimal frequency of MDA under different levels of disease endemicity; / Optimal delivery mechanisms for cost-effective and/or equitable delivery of NTD control activities; / When and how to integrate NTD MDA activities into general health services to ensure a sustainable approach to NTD control while not undermining wider health systems strengthening efforts. / Inputs / - £15 million (over 5 years) / Processes / - Competitive call for programmes of NTD Implementation Research / - NTD Implementation Research conducted on the ground / Outputs / - Open access data sets / - Increased knowledge for cost-effective, sustainable Integrated NTD Control in disease endemic countries / - New knowledge communicated within and beyond programmes alongside which research is conducted / Outcome / - Ongoing and new NTD Control Initiatives informed and improved by research evidence / Impact / - 2020 NTD Eradication and Elimination targets achieved
[2] Liese et al (2010) Programmes, partnerships and governance for elimination and control of neglected tropical diseases. In Lancet v375: 67-76
[3] Buruli ulcer, Chagas disease, Cysticercosis, Dengue, Echinococcsis, Elephantiasis, Fascioliasis, Leishmaniasis, Leprosy, Rabies, River blindness, Schistosomiasis, Sleeping sickness, Soil-transmitted helminths, Trachoma, Yaws.
[4] Fenwick A, Molyneux D & Nantulya V (2005) Achieving the Millennium Development Goals. In Lancet v.365 (9464): 1029-30.
[5] Two other business cases seek to address these deficiencies, namely investments to the Drugs for Neglected Diseases Initative (DNDi) and the Foundation for Innovative New Diagnostics (FIND)
[6] Albendazole/mebendazole, ivermectin, praziquantel and azithromycin
[7] Molyneux D (2004) “Neglected” diseases but unrecognised success – challenges and opportunities for infectious disease control. In Lancet 3664: 380-83; Hotez PJ et al (2007) Control of Neglected Tropical Diseases. In New England Journal of Medicine 357: 1018-1027
[8] Brady MA, Hooper PJ and Ottesen EA (2006) Projected benefits from integrating NTD programs in sub-Saharan Africa. In Trends in Parasitology v22: 285-91
[9] Kabatereine NB et al (2010) How to (or not to) integrate vertical programmes for the control of major neglected tropical diseases in sub-Saharan Africa. In Plos Neglected Tropical Diseases v4(6) e755
[10] For the purpose of this business case we focus on implementation rather than operational research as, while the two are similar, implementation research is wider in scope and aims to produce ‘more generalizable knowledge that can be applied across contexts and settings’ (WHO & TDR 2011, p32)
[11] Boatin BA et al (2012) A research agenda for helminth diseases in humans: Towards control and elimination. In Plos NTDs v6(4)
[12] Marchal B et al (2011) Neglected Tropical Disease (NTD) control in health systems: The interface between programmes and general health services. In Acta Tropica v120S: S177-S185
[13] Gyapong JO et al (2010) Integration of control of neglected tropical diseases into healthcare systems: Challenges and Opportunities. In Lancet v375: 160-65
[14] WHO (2012) Accelerating Work to Overcome the Global Impact of Neglected Tropical Diseases: A Roadmap for Action.

2 Appraisal Case

What are the feasible options that address the need set out in the Strategic case? / A recent RED review of research models[15] identified six basic models in common use across DFID that aim to deliver a complementary mix of high quality relevant research, facilitate research-into-use, and strengthen capacity to undertake and use research: / Core funding to international research organisations; / Product Development Partnerships (PDPs) selected through open competition; / Research Programme Consortia (RPCs)[16] / Direct funding for defined areas of research (not through RPCs) selected through open competition; / Funding relationships with UK Research Councils; / Collaborations with other bilateral donors around research areas of mutual interest. / This business case considers models 3-6 for investing in a programme of Neglected Tropical Diseases Implementation Research alongside the ‘do nothing’ counterfactual: / Option 1: ‘Do Nothing’ Counterfactual / This option considers the implication of not DFID not funding a programme of NTD implementation research. This option however is not considered viable given public ministerial commitment to spend an additional £20million on NTD research. It is therefore not considered in the more in-depth options appraisal. / Option 2: Direct funding of NTD Implementation Research / This option explores the option of DFID directly funding a programme of NTD implementation research either via a specific call for proposals or a larger consortium approach. / Option 3: Funding Relationships with others / This option considers the option of joint funding with other funders, for example the Bill and Melinda Gates Foundation. / Other options considered but not included in the appraisal: We also considered presenting an options appraisal that explored the scope of the NTD research to be commissioned. For example, two types of research are needed to support the control, elimination and/or eradication of the NTDs: / For some diseases new diagnostics, drugs and preventive technologies (e.g. vaccines, insecticides) are required. / For many NTDs however, functional tools for their prevention, treatment and control exist but we lack the know-how to cost-effectively scale up their use. For these diseases, operational and implementation research is required to inform the large-scale delivery of NTD control interventions on the ground and ensure that investments represent the maximum value for money possible. / However, this business case focusses on the second type of research only as separate, complementary business cases for supporting the first via support to Product Development Partnerships (PDPs), for example DNDi, FIND and IVCC, have either been submitted or are currently under development separately. Together these business cases ensure that we are supporting both health product research and development, and research to support the delivery of disease control activities on the ground. / Scoping studies identified three key areas where more operational and/or implementation research could inform NTD control programmes – scaling-up of Integrated NTD Control activities centred around mass drug administration to control 7 NTDs; intensified disease management (through stronger case-detection and simplified case-management to prevent mortality and reduce morbidity from diseases such as sleeping sickness, river blindness and visceral leishmaniasis and interrupt disease transmission); vector control for those NTDs spread by insect vectors (e.g. sleeping sickness, river blindness, leishmaniasis). / We propose to focus this research programme on the first of these three areas – implementation research to inform the scaling-up of Integrated NTD Control activities – as with the 2012 signing of the London Declaration and launching of the WHO NTD Roadmap for Implementation with its bold 2020 disease elimination and eradication targets, and the growing movement towards the scaling up of integrated MDA programmes on the ground, research in this area is needed now and we are presented with a unique opportunity to ground it in the scaling-up process as it happens. However, should proposals received include elements linking to intensified case-management and/or vector control these will not be ruled out so long as there is clear rationale for their inclusion in the bid and evidence that such activities are included within national NTD control strategies.
B. Assessing the strength of the evidence base for each feasible option including delivery routes / In contrast to most development interventions, there is limited published evidence comparing the effectiveness of different funding modalities for delivering high quality, policy-relevant research. Therefore it is not possible to present formal evidence ratings for each option using the DFID standard criteria. Instead, the decisions regarding which funding mechanism to use is based upon a largely qualitative assessment of the different options. / Option Evidence rating / 1 N/A / 2 Weak / 3 Weak
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / Under option 2 (the preferred option), the research is to be commissioned via an open competition, which will include an assessment of the capacity of the proposed team to identify the most implementation and policy-relevant research questions, engage with the end users of the research and, most critically, conduct high quality implementation research on the ground. Thus, the competitive process will ensure that there is enough capacity to design and deliver a high quality, relevant, research programme. / Under option 3 it is not guaranteed (and in fact unlikely) that the research would be commissioned through open competition, reducing our ability to ensure groups demonstrating the strongest proposals and associated capacity to implement the research and associated activities are selected to conduct the work. / While the focus of this programme is not capacity building, the process of engaging with disease control programme and policy staff will increase their capacity to understand and utilise research. / This programme also complements DFID’s recently renewed investments in the WHO Special Programme on Tropical Diseases Research (WHO-TDR) whose major focus is on increasing research and research uptake capacity in low- and middle-income disease endemic countries.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 N/A N/A / 2 C B / 3 C B / This programme will have limited impact on the environment though there may be some adverse environmental impacts associated with the drugs delivered by the NTD control programmes alongside which the research is conducted. For example, studies on the use of Ivermectin (the drug for treating river blindness) in animal husbandry suggest that it is toxic to invertebrates found in dung and responsible for its breakdown and incorporation in to the soil. In humans, the drug is also poorly metabolized and is thus excreted in the faeces. This might slow the decomposition of faeces and thus present environmental hazard in communities where open defaecation is common. However, it is not clear that slower faecal decomposition increases the survival of disease-causative agents in the faeces and the possible side-effects for public health are likely to be marginal, particularly as Ivermectin is only sparingly soluble in water, minimising the risk of drug residues entering water systems. There may be similar effects for the other drugs included within the MDA rapid impact package but any environmental impact is likely to be limited, especially when compared to the health benefits of MDA. / However, these risks are associated with the delivery of NTD control programmes rather than the research conducted alongside them. Further, research that contributes to our understanding of how best to integrate NTD control activities may in fact have positive environmental impacts through such factors as informing the required frequency of MDA, reducing the need for parallel outreach activities (involving transportation), enhanced incorporation of environmental hygiene promotion into disease control programmes, and reduced drug wastage through increased drug adherence. / Climate change is very likely to have an impact on the future prevalence and geographical distribution of many of the NTDS. For example, the combined effects of changing temperatures and precipitation (which will have major effects on river basins and watercourses) may lead to a more favourable environment for the survival and transmission of pathogens in the environment. This increases the imperative for action to control and eliminate NTDs as quickly as possible and to prevent the spread to new areas. This research is intended to inform and enhance our ability to deliver cost-effective, sustainable NTD control programmes at scale, thus enhancing our ability to tackle the NTDs in a timely manner and reducing the risk of geographical spread in the face of climate change. / We will work with the preferred bidder(s) to ensure that they manage the carbon footprint associated with carrying out this programme of research. For example, they will be encouraged to use electronic channels for dissemination of research findings and minimise travel. Where air travel is necessary, DFID will encourage the use of economy class flights which are not only cheaper but also three times less carbon intensive per flight than business travel[17]. / While overall the climate change and environmental risks and opportunities are broadly similar for both the options considered, it is likely that the carbon footprint associated with option 2 (direct funding) would be lower than that associated with option 3 (funding partnership) as research is likely to be conducted in fewer settings and with significant involvement of disease endemic country researchers (thus requiring less travel).
E. If any, what are the likely major impacts on social development? / NTDs affect the poorest, hardest to reach people, who often live in remote or conflict-affected areas with minimal access to health services. Part of the rationale for eliminating NTDs is to help break the poverty cycle and improve economic prospects for the poor. Preventing morbidity from NTDs will reduce out-of-pocket expenditures on treatment and contribute to increased school attendance and productivity. There is also some evidence of inequities in the distribution of the disease burden associated with some NTDs – for example, adult women are more than twice as likely to be afflicted with eyelid abnormalities associated with trachoma than men[18], whilst the schistosomiasis (bilharzia) and the soil-transmitted helminths is greatest amongst children; the effects of anaemia resulting from STH infection are also more pronounced amongst pregnant women and children. Thus research in the field of NTD control may have a disproportionate impact on the poorest and most marginalised in society, including women and children.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / While this research programme is unlikely to have any major direct impacts on conflict and fragility, it is worth noting the huge burden of NTDs in fragile states, particularly in Africa – South Sudan, for example, is burdened with more of the NTDs than any other country. Mass drug administration programmes for NTD control do not necessarily require the presence of a functional health system and often, for example, utilise schools as an alternative drug delivery system. It may even be that systems developed for MDA can be piggy-backed by the wider health service, acting to strengthen health systems and increase access to healthcare in fragile states. By addressing questions of integrated approaches to NTD control across a range of contexts, this research programme has the potential to provide broader insights into healthcare delivery in conflict-affected and/or fragile states. However, in order to minimise the risk of research programme failure it will be important to ensure that not all research commissioned is in fragile settings.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / DFID Business Cases require a cost-benefit analysis to be done for the feasible delivery options. A cost-benefit analysis requires the identification, quantification and assigning of monetary value to costs and benefits. This is a particular problem for research because: / The exact nature and scope of the questions to be considered are often defined during the research programme itself / The ultimate beneficiaries cannot easily be identified at the start of a research programme / The knowledge outputs are potentially global and can be used in diverse ways / Much of what DFID invests in are global public goods / The results chain is extremely complex / In this case it is also difficult to conduct an accurate cost comparison across delivery modalities as different research partnerships tend to be set up to do different things. Therefore it is not appropriate to present a quantitative cost-benefit analysis and a qualitative approach is utilised instead. We do this in two stages, first comparing options on the basis of a broad financial costs comparison and secondly conducting a more in-depth analysis on the basis of three core critical success criteria. / Stage 1: Comparing Costs Across Options / Commissioning and managing a programme of NTD Implementation Research entails 3 broad cost categories: / Core Costs: These include central management, programme monitoring and information dissemination / Implementation Costs: This includes resource materials, equipment costs, research costs (design, implementation and analysis), travel and research staff costs / Coordination Costs: These relate to efforts required for DFID and contracted research programmes to work with others to ensure complementarity across research efforts. / Option 2: Direct Funding of NTD Implementation Research [Preferred Option] / Core costs: Central costs associated with the management of the research programme(s) may be higher as these are all held in-house. However, there may be significant management costs associated with programme design and the drawing up of a co-funding agreement. / Implementation costs: DFID would likely have more control over these through directly commissioning research programmes itself. A competitive bidding approach to commissioning is likely to drive costs down as bids can be compared to the wider market across both technical and commercial criteria. / Coordination costs: These will depend on the geographical location of principal investigators, research staff and other institutions engaging on similar work plans. However, they are likely to remain constant across the two main options. / Further, as discussed in the options appraisal, a direct funding approach affords DFID greater control over research programme procurement, design and implementation, potentially reducing overall delivery risks and hence the risk of non-delivery. / Option 3: Co-Funding / Core costs: In converse to a direct funding model, there is scope for reduced costs associated with research programme management. However this is not guaranteed and there is likely to be a significant management cost associated with joint programme design and the drawing up of a co-funding agreement. / Implementation costs: Through a co-funding model this may be harder for DFID to control, particularly in the absence of a competitive bidding process. / Coordination costs: As stated above, these are likely to remain constant across the two main options. / Stage 2: In-depth Analysis on the Basis of Critical Success Criteria / Here we qualitatively compare options 2 and 3 on the basis of a small number of critical success criteria: / Control over programme content, risk and delivery (as measured by opportunities available to measure and manage performance) / Likelihood that research directly influences Integrated NTD Control programming and policy on the ground / Timing and resources required before the intervention can start and implications on the timing of the benefits / Option 2: Direct Funding of NTD Implementation Research [Preferred Option] / Within this option, we propose to use an open competition to directly commission 1-3 substantial independently-funded programmes of Implementation Research to inform the effective and sustainable scaling-up of integrated NTD control activities on the ground. The key advantage of this approach is an increased ability to control programme content, risk and delivery (as ensured through a competitive process to identify the strongest potential providers and ability to use DFID procedures to measure and manage performance). Direct commissioning, through our ability to focus programme content and require that researchers engage with key stakeholders throughout the research process, further allows us to maximise the likelihood that research will directly influence integrated NTD control programming and policy on the ground. While direct commissioning might, theoretically, require increased management inputs once research has been contracted, it is likely to involve less time and management during the design and contracting process as no negotiations with potential funding partners are required. / While similar in design to our pre-existing (and building upon our experiences using) Research Programme Consortia[19], the programme(s) commissioned will be more focussed in scope, likely involve fewer partners and countries, and will emphasise the production of high quality research and research uptake activities. These investments will complement UK investments in the WHO Special Programme of Tropical Diseases Research (TDR) which has a focus on capacity-building in this area and has recently been awarded a further 5years of core funding from DFID. A reduced number of research partners allows for a more focussed and coherent research programme and reduces risks associated of a large consortium, while the reduced emphasis on capacity-buildings the focus on and likelihood of producing high quality research. / To ensure the independence of research findings while maintain programme relevance and impact, we will commission this research in parallel to (but not as part of) DFID’s Policy Division support to the implementation of integrated NTD control activities in Nigeria and/or South Sudan. While embedding research within programme delivery (funding the same organisations to conduct both implementation and research activities), can increase research relevance and acceptance by programme staff such an approach has some important disadvantages. Programme staff often have limited research skills and/or experience leading to increased capacity-building needs and lower quality research outputs. For example, in the Malawi National TB Control Programme (NTP), several research activities that were initiated within the programme were never completed due to inaccuracies in data collection, poor adherence to study protocols and inadequate supervision[20]. The independence of research is critical to its wider credibility (and thus potential impact) beyond the implementation programme under the lense. For these reasons we propose to commission an independent programme of integrated NTD control implementation research with a focus on the production of relevant, high quality, independent and hence credible new knowledge[21]. To maximise programme relevance and the likelihood of research uptake in countries within which the research is conducted however, bidders will be expected to demonstrate strong working relationships with relevant NTD control programme and policy staff and present a credible stakeholder engagement and research uptake strategy. DFID’s own Research Uptake staff have been and will continue to be involved in the design of this research programme in order to maximise its potential impact on the cost-effective and sustainable scale-up of integrated NTD control activities across multiple countries. / Research relevance, quality and impact will further be maximised through the use of a 2-stage open competition to identify preferred bids. Under this model, bidders will be first asked to submit a pre-qualification questionnaire (PQQ) within which they must demonstrate their understanding of the practical challenges to delivering integrated NTD control activities on the ground, pre-established relationships with in-country policy-makers and implementation staff, and capacity to deliver a relevant, high-quality, multi-disciplinary research. Bids short-listed at this stage will then be asked to submit full proposals within which they will describe their approach, areas of research focus and theory of change more fully. Should no bid meet the required minimum standards we will reserve the right not to award funding. / DFID has a significant track record in the commissioning of high quality operational and implementation research via this method, and is well-placed to make strategic investments in the area of NTD control, particularly given strong working relationships between our staff working in NTD policy, programming and research, as well as research uptake. Direct, DFID-only funding of NTD Implementation Research maximises our ability to utilise these relationships and ensure complementarity between this investment and other related DFID-supported NTD programmes. These include the funding of 2 Integrated NTD Control Programmes in Africa; investments in trachoma, schistosomiasis, and soil-transmitted helminth control; co-funding of research to improve the control of zoonotic infections affecting both animal and human health (the Zoonotic Emerging Livestock Systems, ZELS, Programme, jointly funded by DFID and a number of UK Research COuncils); and core funding to the WHO Special Programme on Tropical Diseases Control (WHO-TDR). / DFID also has a strong comparative advantage in the field of health systems strengthening which well places us to ensure that the research is embedded within a wider systems based approach. This allows exploration of the important questions around whether and how NTD control efforts can leverage the wider health system and vice versa[22], allowing for greater value for money through more integrated approaches to disease control programming and wider health systems strengthening. / Option 3: Funding Relationships with Others / Scoping activities identified two other potential major funders of NTD implementation research – the Bill and Melinda Gates Foundation (BMGF) have awarded a US$28 million grant to the Taskforce for Global Health (referred to herein as ‘the Taskforce’) to manage a portfolio of NTD operational research and the Wellcome Trust have been exploring the possibility of making a strategic investment in this area. We have explored the possibility of joint-funding with both partners and have maintained regular contact as our programmatic design has evolved. Other funders, for example the Children’s Investment Fund, may also be considering commissioning work in this area. / The major advantages of a joint-funding relationship include the potential to ensure complementarity and minimise duplication across investments, reduce the management burden to DFID (if the funding agreement assigns management to the co-funder) and incentivise stronger working relationships between the various research groups working in the field of NTD control. However the process of agreeing a joint-funding framework and mechanism can be time-consuming and messy, significantly slowing down the initiation of research activities, particularly where different funding partners are used to operating in different ways and/, or where research priorities, although similar, are not fully aligned. Once the funding agreement is up and running, individual funders may have less control over programme content, risk and delivery. / Bill and Melinda Gates Foundation (BMGF) / The BMGF are the single biggest funder of NTD Implementation Research. DFID have a good working relationship with both the BMGF and Taskforce staff working on their large NTD grant. While a co-funding model has been explored, and was discussed with the BMGF, this option has been rejected, though all parties have committed to working closely together to ensure a joined-up approach to NTD implementation research. Reasons for rejecting a co-funding agreement with BMGF include differences in research focus, divergent approaches to the research prioritisation and commissioning, the risk of reduced DFID control, and the importance placed on maintaining competition in the market place. / While the BMGF is taking a very disease-specific (vertical) approach to the research, DFID is more focussed upon questions of when and how to take a more horizontal, integrated approach to NTD control and health systems strengthening. The BMGF research prioritisation process has been greatly based upon consultation with academics while DFID places more currency on the involvement of NTD control implementation and policy staff to ensure that research conducted is directly relevant to and influences control activities on the ground. / While the BMGF grant to the Taskforce is large (US$28 million), funds will be distributed to a large number of different research groups each addressing a very specific research question (often applied to a specific disease), resulting in a disperse set of research activities on the ground. In contrast, DFID’s focus on learning from the experiences of on-going attempts to scale-up integrated NTD control programmes on the ground, points towards investment in a smaller number (1-3) of substantive research programmes which address multiple diseases and answer multiple questions using multiple research methods and disciplines within a single framework. Within this approach DFID is also placing a strong emphasis on the engagement of disease control implementation and policy staff throughout the research process in order to maximise the relevance of research and the likelihood of research findings being taken up by the intervention programmes alongside which the research was conducted. BMGF, in contrast, is focussing its policy interface with the WHO. / In short, while there are strong complementarities between BMGF investments in NTD implementation research and DFID’s proposed research programme, there are also divergences in both research focus and approach which may make a co-funding agreement difficult particularly given BMGF have now awarded their grant and conducted their research prioritisation process, limiting DFID’s ability to influence programme design and/or management. Such an agreement may also be viewed as undesirable on the basis that it may reduce competition in the global market place which in turn can drive down the quality of research conducted, while driving up the costs. / Other Funders / Funding relationships with other partners were also explored, particularly with the Wellcome Trust (WT) who have been considering making an investment in this area and with whom Research and Evidence Division already have a number of funding agreements with. This history of joint-working gives us the advantage of having an established understanding of and working relationship with each other. Discussions with WT staff also suggest a strong alignment of thinking around NTD implementation research priorities and delivery modalities. However, the WT are not yet at the stage of committing to make a substantial investment in this area and even when ready, the process involved in awarding a strategic grant is a long-one. Thus, a co-funding relationship with the WT would, at this time, delay the final initiation of the research. Given, this research is intended to contribute to the global community’s ability to meet the WHO 2020 NTD elimination and eradication targets, delaying our investments in NTD implementation research would significantly reduce our likely return on investment. For this reason we do not recommend pursing a co-funding agreement for NTD implementation research with WT. We will however maintain regular contact with them in order that, should they decide to make a strategic investment in this area in the future, they might build on the research conducted under the DFID investment. No other major funders were identified to be currently making or exploring future investments in NTD implementation research. / Summary Statement for Preferred Option: / While there can be advantages to joint funding agreements our landscape analysis suggests that, in this case an independent direct funding approach is most appropriate. In particular, independently funding our own research programme maximises our control over programme content, risk and delivery which in turn: / Increases the likelihood that research will directly influence NTD control programmes on the ground, through the conduct of comprehensive research packages alongside the control programmes they seek to influence, and the requirement that proposals demonstrate programme staff and policy maker buy-in to the research process from the outset; / Increases our ability to ensure complementarity between this investment and other UK NTD control investments / Likely reduces the amount of time and resource investments required before the research commence and thus maximises the potential of the research to contribute towards the achievement of the WHO 2020 NTD control, elimination and eradication targets. / Critical Success Criteria (Score: 1-5) Option 2 – Independent Research Programme Option 3a – Joint Funding Agreement w BMGF Option 3b – Joint Funding Agreement w WT / Control over programme content, risk and delivery 4 2 3 / Likelihood that research directly influences NTD control prog & policy 4 3 4 / Timing and resources required before intervention can start 4 3 2 / Total Score 12 8 9 / While we propose to commission an independent programme of NTD implementation research it will be critical that we work closely with other funders in order to minimise duplication and maximise complementarity across efforts. We have already stayed in close contact with the BMGF and the Taskforce for Global Health and attended the recent presentation of the findings of their research prioritisation exercise. We have also accepted an invitation to be an ex-officio member of the Advisory Panel for this grant. We continue to hold discussions with BMGF, the Taskforce and others including the Wellcome Trust regarding mechanisms for ensuring that our contract-holders work together, ideally working towards a common research framework and utilising a common set of research metrics where appropriate. Ultimately, choosing to make an independent investment in this area will allow us to maximise flexibility in our approach to working with other funders currently supporting NTD operational and/or implementation research, and potentially others who may come on board later.
H. Theory of Change for Preferred Option / This programme of NTD Implementation Research is intended to contribute towards the ultimate impact goal of achieving the WHO 2020 NTD control, elimination and eradication targets[23] through informing improved Integrated NTD Control Programmes on the ground (outcome). / The results chain below indicates how this will be achieved. / The overall theory of change (ToC) assumes that the production and communication of research evidence, particularly when conducted alongside intervention activities on the ground, ultimately contributes to the reduced burden of neglected tropical diseases through the influence and up-take of new evidence on health policy and disease programming. / The ToC is based on four broad assumptions that contribute to the sustained adoption of evidence-based disease control policies and programmes on the ground: / Open competition allows the selection of the highest quality bids and maximises the potential relevance and quality of the research conducted within the grant; / Policy-makers and programme managers in disease endemic countries (DECs) should be involved in the generation of research priorities and research processes that reflect and accommodate their needs; / Research is needed to generate new evidence and inform the most effective delivery of disease control tools and strategies / Engagement of disease endemic countries in the research process ensures that new solutions and implementation strategies respond to the health needs of DECS and are put into practice. / The ToC assumes that researchers: / Will produce high quality research / Understand the current state of the evidence base / Have a shared interest and established relationship with policy makers and intervention programme staff / Understand what drives programme and policy-making decisions and how these impact research design / Develop the right research questions and associated methods / Take a pragmatic to research design so that it reflects the reality of implementation activities and schedules on the ground / Produce research that is appropriately contextualised / The ToC also assumes that policy makers and implementation programme staff: / Value research and have established relationships with research staff / Participate in the research process, particularly in the defining of the research questions to be tackled / Are willing to work with researchers and, where sensible, adapt disease control implementation plans in order to maximise the potential for high-quality research / Are open to responding to new evidence and changing policy and practice where appropriate / These assumptions will be monitored and tested as the research programme progresses, with lessons being fed in to future commissioning. / Inputs / - £15 million (over 5 years) / Processes / - Competitive call for programmes of NTD Implementation Research / - NTD Implementation Research conducted on the ground / Outputs / - Open access data sets / - Increased knowledge for cost-effective, sustainable Integrated NTD Control in disease endemic countries / - New knowledge communicated within and beyond programmes alongside which research is conducted / Outcome / - Ongoing and new NTD Control Programmes informed and improved by research evidence / Impact / - 2020 NTD Eradication and Elimination targets achieved
I. What measures can be used to monitor Value for Money for the intervention? / The overall level of investment presented in this business case reflects both ministerial commitments to NTD research and the value of previous similar investments. / Initially VfM will be assessed through the competitive tender exercise. At the full proposal stage, bids will be reviewed on the basis of both a technical and a commercial evaluation. The commercial evaluation will review proposed budgets to ensure proposed costings are proportionate and in line with the rest of the market. The management arrangements of the contract(s) aim to both scrutinise and to support the conduct of high quality research and research outputs, hence ensuring VfM. / Once the preferred bid(s) and associated research questions and approaches have been identified we will work with the bid leads to develop a full log frame against which activities will be monitored. Contract(s) will be based on the delivery of a number of defined outputs, including the production of satisfactory reports and other deliverables. Payments to the supplier(s) will be contingent upon the delivery of agreed outputs. / A short inception phase will tighten the focus, design and plans for the research programme(s). VfM will be an integral component of inception reports. / While the precise VfM measures cannot be defined at this stage, the types of measures that might be included within reporting log frames include: / Economy: / Use of existing research partnerships and infrastructure / Costs of data collection and/or analysis / Travel costs (transport, accommodation and subsistence) / Efficiency: / Number and size of studies implemented / Number of scientific publications (in peer-reviewed, open access journals) / Effectiveness / Number of NTD Control Programmes adopting research findings/recommendations / Number of NTD Control Policies responding to research findings/recommendations / Progress towards WHO 2020 NTD eradication and elimination goals / NTD burden in countries within which research is conducted / Cost-Effectiveness: / Evidence of collaborative working with other groups conducting NTD implementation research (both DFID and non-DFID funded) / Proportion of expenditure on operations versus administration and staff salary / Detailed value for money measures will be identified once contracts are awarded and the exact nature of the research to be supported is known.
J. Summary Value for Money Statement for the preferred option / Option 2 [directly funded research programmes(s)] offers the best VfM (and lowest risk) for DFID. / While we recognise that a co-funding agreement could reduce the administrative burden (and associated costs) this is not guaranteed and we believe that the potential disadvantages and risks associated with such a commissioning model outweigh the potential management advantage.
[15] Piper J (2010) Working Paper. Research & Evidence Division. DFID Internal Document
[16] RPCs represent consortias of primarily academic partners from across high and low-income countries working together to explore a set of research questions around a common theme (e.g. nutrition, health systems, reproductive health).
[17] UK Department for Forestry and Rural Affairs (2009)
[18] Carter Centre (2009) Women and Trachoma.
[19] RPCs = groups of researchers from a number of institutions across a number of countries working on a common, but relatively broad, research theme Each consortium has 4-6 partners, at least 3 of which must be in developing countries. They aim to 1) deliver quality research, 2) link research to policy and facilitate research in to use, and 3) help develop research capacity in developing countries.
[20] Zachariah R et al (2009) Operational research in low-income countries: what, why and how? In Lancet Infectious Diseases v9: 711-17
[21] Remme JHF et al (2010) Defining Research to Improve Health Systems. In PLoS Medicine v7(11)
[22] Marchal B et al (2011) Neglected tropical disease control in health systems: The interface between programmes and general health services. In Acta Tropica v120S: S177-185.
[23] WHO (2012) Accelerating Work to Overcome the Global Impact of Neglected Tropical Diseases: A Roadmap for Action.

3 Commercial Case

Direct procurement through a contracted supplier
A. Clearly state the procurement/commercial requirements for intervention / A 2-stage open competition will be used to identify the research and associated providers to be supported. Bids will be assessed on the basis of both commercial and technical criteria. / All proposals must include researchers based within the countries in which the research is to be conducted and should also demonstrate the buy-in of NTD programme staff and policy-makers.
B. How do we expect the market place will respond to this opportunity? / This is a highly competitive market with a large number of potential, high quality providers, many of whom are UK-based. A number of these providers are aware that DFID has made a public commitment to funding NTD research and are anticipating a call for proposals. This includes programmes that have received previous or are currently receiving DFID or other donor funding. We anticipate strong competition for funding and are confident that this will enable us to secure high quality bids offering excellent value for money.
C. How does the intervention design use competition to drive commercial advantage for DFID? / The funding will be awarded following a 2-stage open competition. Tender documents will emphasise the importance of value for money and make clear that DFID reserves the right not to award funding in the event that proposals received to not meet our requirements. / At the first stage, interested parties will be asked to indicate their interest through the submission of a pre-qualification questionnaire (PQQ). Submitted PQQs will be internally peer reviewed and the strongest bidders will be invited to submit full proposals. Short-listed bidders will be offered pre-implementation grants of up to £10,000 to support the proposal development partnership by allowing disease-endemic country partners to participate in the process fully. Past experiences of using this mechanism suggests that it significantly improves both the appropriateness and quality of bids received, while driving ownership of the research proposal and its content by all partners from the outset. Thus, while this step will result of an additional spend of up to £100,000 it will ultimately improve the value for money associated with the overall investment. / We will advertise the competition widely through our own networks and via those of other funders in an effort to encourage high volumes of high quality applications. This will allow us to select only the best value research offers.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Many research programmes allocate funds to support international experts who have to travel to research sites and might have higher fee rates than in-country staff. Where possible, research funded under this call will be conducted in close contact with national disease control programme and policy staff. We will further be calling for bids to demonstrate the involvement of researchers from local institutions within the countries where research is being conducted. This will act to both reduce costs and to enhance the likelihood of sustained research capacity and impact in the target countries. / The budget breakdown will be reviewed and agreed before the contract is issued so that any cost or spending issues can be identified early and dealt with accordingly. Successful bidders will be expected to conduct an inception phase, with subsequent funding being contingent on the successful submission of an inception report. Further contract gates may be built in if appropriate. / We recognise that delivering this research will involve substantial human capacity and may involve significant travel. We will manage the cost of this by ensuring that staff and travel costs are in line with those seen in the wider market. / We will explore innovative financing models including milestone-based contracting and payment by results, though the finance model is likely to depend ultimately on the nature of the research and host institution(s) contracted.
E. How will the contract be structured and how will contract & supplier performance be managed through the life of the intervention? / There will be at least one break clause in the contract (s). Successful bidders will be expected to submit an inception report at the end of a pre-defined inception period at which point their performance and plans will be reviewed. If performance is unsatisfactory at this stage we will have the right to terminate the contract. Successful research programmes will be expected to submit annual reports within which they will report their performance against a pre-agreed log frame and associated budget. The log frame and budget breakdown will be agreed with the client before contracts are awarded. / The Programme Manager and Health Advisor allocated to this research programme will hold regular formal and informal meetings with programme staff throughout the year. These will enable discussion and early detection of any potential issues either party might hold regarding the delivery of the work plan and/or associated costs. / We will explore innovative financing models including milestone-based contracting and payment by results, though the finance model is likely to depend ultimately on the nature of the research and host institution(s) contracted.

4 Financial Case

A. Who are the recipients of all proposed payments? / The lead research institution(s) that are selected initially to prepare full proposals and then conduct the research.
B. What are the costs to be incurred directly by DFID? / The table below provides an indicative budget breakdown on the basis of a maximum spend of £15million distributed across up to 3 substantive research programmes. More accurate financial forecasts and breakdowns will be finalised as contracts are drawn-up with successful bidders. Quarterly forecast spend for each financial year will be agreed with the Research Deputy Programme Manager at the start of each financial year. The DPM will also be responsible for the authorisation of payments. / Year 0 Year 1 Year 2 Year 3 Year 4 Year 5 TOTAL / Pre-implementation grants £100,000 £100,000 / Inception Phase £1,500,000 £1,5000,000 / Main Delivery Phase £3,000,000 £4,500,000 £4,500,000 £1,500,000 £13,500,000 / TOTAL £15,100,000
What are the costs to be incurred by third party organisations? / Not applicable
Does the project involve financial aid to governments? If so, please define the arrangements in detail. / Not applicable
Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / Financing will come from the Human Development Team, Research and Evidence Division, budget.
What is the profile of estimated costs? How will you work to ensure accurate forecasting? / Profile of estimated costs will be developed once preferred bidders have been identified and contracted. Accurate forecasting will then be discussed with lead contractors and performance on forecasting will be part of the on-going monitoring of each research programme contracted.
What is the assessment of financial risk and fraud? / Proposals will be expected to set out the financial risks to the institution and the programme, including descriptions of fraud and financial management arrangements in place to mitigate against risks. / Financial issues and practices, particularly those open to fraud, will be discussed during the annual review process.
How will expenditure be monitored, reported and accounted for? / Programmes will be required to supply annual forecasts of expenditure and to report on expenditure when submitting quarterly invoices. Expenditure will be monitored against forecasts and discrepancies resolved ahead of payment. An annual audited statement of accounts will be required.

5 Management Case

What are the Management Arrangements for implementing the intervention? / Funded research programme(s) will be managed by the Human Development Team in Research and Evidence Division. This involves: / Following DFID’s programme management guidelines / Overseeing programme performance, including carrying out an inception phase stock-take, annual reviews of each individual research programme and a project completion review (PCR) for the overall funding investment / The assignment of a lead Research Manager and Health Advisor to the overall programme / Ensuring and facilitating inter-linkages between the individual research programmes (and those funded by other funders) where appropriate / Ensuring that activities generate learning and providing partners with opportunities for cross-partner learning
What are the risks and how these will be managed? / Risk Probability / (L-M-H) Impact / (L-M-H) Mitigation Measures / Insufficient market interest to apply for funds Low High Open competition / Advertise call widely and distribute via our networks / Poor quality research proposals Low Medium Clear Terms of Reference and scoring criteria / Seed funding to support full proposal development / Lack of engagement from NTD programme staff and policy-makers High Medium Require demonstrated engagement of NTD programme staff at the earliest stage of bidding (PQQ) / Seed funding to support the involvement of programme and policy staff in full proposal development / Require programme to develop a research uptake strategy / No or limited new knowledge is generated Low High Require bidders to situate their proposed research focus within the context of the wider evidence base and demonstrate how their research will contribute to the knowledge base / Work with researchers to encourage publication irrespective of the findings (in an effort to minimise publication bias) / Research findings from different control programmes and/or countries are non-comparable limiting the ability to generalise results Medium Medium Embedded approach to research, whereby research activity is conducted directly alongside intervention activities on the ground / Require that individual research programmes work across a minimum of two different NTD control programmes / Utilisation of a nested approach to log frames whereby individual programmes report to a common set of indicators / Facilitate cross-research programme working and encourage the use of common research indicators and designs as appropriate / Research fails to influence NTD control programme and policy practice Medium Medium Require demonstrated engagement of NTD programme staff at the earliest stage of bidding (PQQ) / Seed funding to support the involvement of programme and policy staff in full proposal development / Require programme to develop a research uptake strategy / Monitoring of relationship between researchers and implementation programmes as part of the annual review process / Programme duplicates the efforts of other research or funding partners Medium Low Require bidders to situate their proposed research focus within the context of the wider evidence base and demonstrate how their research will build on and contribute to the knowledge base / Require bidders to identify ongoing NTD research activities they are aware of and indicate how they will ensure complementarity between ongoing and new research activities / Use of external technical reviewers for evaluation of full proposals / Continue to work closely with other NTD research funders and identify opportunities for cross-fertilisation of efforts / Misuse of funds Low High Require successful bidders to have strong fraud and financial management policies in place / Following of strict DFID programme management guidelines / Rigorous annual reviews will include financial audits
C. What conditions apply (for financial aid only)? / Not applicable
D. How will progress and results be monitored, measured and evaluated? / Individual nested log frames will be developed for each research programme funded before contracts are signed. These will be used for monitoring and evaluation purposes and annual reviews will report progress against log frame milestones and projected budgets. / Individual research programmes will be required to product annual reports and final programme reports which cover: progress against log frame milestones and towards outcome and impact goals, risk assessments and financial issues. / We will expect research programmes to use a mixture of quantitative and qualitative methods to measure progress and results.