Type of Review: Annual Review

Project Title: Support to Civil Society in Tanzania: Foundation for	Civil Society Programme

Date started:	Jan 2011 Date review undertaken: July 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing £8m to support Civil Society Organizations (CSOs) in Tanzania through the Foundation for Civil Society (FCS). This support aims to ensure that by March 2015 more citizens (especially the poor and marginalized) are empowered to influence and monitor policies that address their needs and participate in promoting budget transparency and call for improvement of service delivery in Tanzania. This support is an extension of a programme started in 2009. / This intervention seeks to deliver the following outputs: a) Citizens are more aware of their civic rights and responsibilities; b) Ability of CSOs and citizens to participate and influence policies and budgeting processes is strengthened; c) Increased CSOs involvement in promoting rights of minority groups - women, persons with disabilities and pastoralists; d) Strengthened CSOs organizational capacity and effectiveness; and e) Foundation for Civil Society delivers high quality services and is efficiently and effectively managed and governed. / Donors that supported FCS in 2012 included: UK, Swiss, Canada, and Netherlands. Others were Norway, ILO, Comic Relief and American Jewish World Service (AJWS). During 2012, the total FCS spend was USD 13.2 million. UK support accounted for 34% of this spend.

What are the expected results?
Two million men and women enabled by DFID to access quality and user friendly information on services, entitlements and rights / 150 new CSOs have strengthened their organizational and institutional capacity, especially in the areas of: resource mobilization, report writing, strategic planning, financial management and M&E / 200 CSOs trained to demand greater accountability and transparency from governments, with 75 CSOs effectively monitoring budgets and decision-making processes at national and district levels / 200 CSOs trained to mainstream gender equality in their organizations and interventions and at least 50% showing evidence of the impact of their work on promoting gender equality. / 100 Disabled People’s Organizations (DPOs) receive grants and capacity building support to better promote rights of their members / Annual CSO Forum bringing together CSO representatives to promote learning, networking and sharing of lessons / Annual CSO Exhibition at the National Assembly (Dodoma) and House of Representatives (Zanzibar) to facilitate consultations between civil society representatives and Members of Parliament – a platform for mutual learning, exchange and advocacy / Strengthened capacity of the Foundation for Civil Society to professionally manage and deliver small grants to civil society organizations and showing evidence of improvements in the area of results monitoring and reporting.

What is the context in which UK support is provided?
Views of the People (VOP) report for 2012 provided a comprehensive assessment of Tanzanians’ knowledge and attitudes towards key public policies contained in MKUKUTA. VOP found that, while many Tanzanians see substantial progress since independence in creating social and economic infrastructure, many still lack remunerative work, adequate housing, and access to clean water. The majority complained that their standard of living has been seriously eroded by inflation, most see youth unemployment as a major problem, and many claim they sometimes go hungry. / A major review of the Constitution of the United Republic of Tanzania was put in place in 2012 aiming to be completed by November 2014. The Government appointed a Constitutional Review Commission (CRC) to gather the public’s views and compile a draft constitution. CRC collected direct views from an estimated 300,000 citizens across the country by Dec. 2012. This was followed by meeting with 19 political parties, 22 religious organizations, 72 CSOs and 43 prominent persons including senior GoT officials. Issues of access to and control of land are a particular focus of some CSO submissions to the review process. / Citizens in Tanzania are increasingly becoming vocal and assertive outside formal processes. This was demonstrated by protests by citizens in Mtwara demanding to benefit more from natural gas discoveries in their region. / Government of Tanzania developed its Open Government Partnership (OGP) Action Plan through a consultation process with civil society groups. The plan is positive as it has included a focus on three priority social sectors (education, health, water) and on budget transparency. It also has a good section on technology and innovation. However, despite presidential commitment to the OGP, implementation of detailed work plans appears some way off and cabinet level engagement uncertain, with limited civil society appetite for investing time and effort in open government reforms. Tanzanian leadership in the OGP needs to improve to ensure Tanzania lives up to its commitments. / Some of the negative accountability trends in Tanzania during the period under review include: a) the dissolution of the Parastatal Organisations Accounts Committee (POAC) and the rolling of its responsibilities into the Public Accounts Committee (PAC); b) amendments of sections 38, 39 and 40 of the Public Audit Act 2008; and c) different incidents of intimidation and attacks towards media professionals. Increased levels of religious tension were also witnessed during the period under review.

## Section A: Detailed Output Scoring

Output 1: More citizens are more aware of their civic rights and responsibilities;
Output 1 score and performance description: / Score A++ / Indicator / - # and quality of new CSOs supported to promote civic rights (A) / - # of citizens enabled to access information on services, rights (A) / - # of new CSOs supported to increase citizens involvement in local government planning and budgeting exercises (A) Milestone / 15 / 1m / 15 Achieved / 33 / 2,737,973 / 11
A = Attributable to DFID at 34%; C = Contributory / Progress against expected results: / FCS supported 98 district and regional CSOs (33 attributable to DFID) to facilitate and increase citizens’ constitutional literacy and competency, increase awareness of the current constitution and mobilize citizens’ participation in the constitution debates in their constituencies. FCS grantees worked closely with the Tanzania Citizens Information Bureau (TCIB) who played a central role in increasing citizens’ and CSOs’ participation in the constitution review process; / During the year, FCS directly reached a total of 8.05 million beneficiaries[1] with different types of information on their rights, roles and responsibilities. Out of the total number of citizens that were reached by FCS, 2.7 million citizens are directly attributable to DFID, as UK’s support to FCS during 2012 was equivalent to 34% of its total budget. Number of citizens reached through FCS and attributable to DFID will contribute to DFID corporate indicator reporting (including DFIDT Operational Plan target). Number of citizen’s reach through FCS has been arrived as follows: a) a total of 1,089,247 citizens (47% being women) were directly reached by 817 grantees who received support from FCS and implemented activities across districts and village levels in Tanzania; b) 6.96 million citizens is an estimated reach by FCS and grantees work through use of radio, newspapers, television and dissemination of large numbers of printed materials. / The main focus of FCS’s civic empowerment activities during 2012 were centred on the on-going constitutional review process. FCS was the single main source of support towards citizens and CSOs across the country to increase their understanding, participation and contribution of citizen’s voice to the new constitution. Below is a summary of some of achievements by FCS in promoting civic empowerment during the period under review: / FCS supported a coalition of CSOs to analyse the Constitution Review Bill and prepare a submission to the President of the United Republic of Tanzania and the Chief Parliamentary Draftsman outlining CSO’s views and proposals to revise the bill; / FCS re-printed and distributed over 350,000 Swahili copies of the current constitution of the United Republic of Tanzania; / FCS supported and facilitated the conduction of 300 specific public dialogues at constituency level across Tanzania where over 284,351 citizens (126,100 being females) were able to directly participate and air their views on the constitution making process; / FCS sponsored three TV programmes through Tanzania Broadcasting Corporation (TBC1) to provide citizens more opportunity to further dialogue on the constitutional review process; / FCS supported and facilitated CSOs’ Annual Forum that was held in Dar es Salaam with a theme “The role of civil society in the New Constitution Making process”. The forum was attended by 522 participants representing CSOs from all over the country. / The forum included four plenary sessions and a number of thematic workshops, which all together significantly contributed to enhance CSOs’ knowledge on constitutional related issues and develop a clear focus on how to broaden citizens’ participation in the New Constitution Making process. Key issues which were discussed fall under Key Constitutional Pillars in observation for a democratic Constitution Making Process, Leadership ethics in the New Constitution, State Organs and its Authority in the New Constitution, Union Issues in the New constitution, Which Ideology should Tanzania follow: socialism or capitalism? And Land issues in relation to the New Constitution-making. / Conclusions and views of CSOs from this annual forum were submitted to Constitution Review Commission (CRC). / 31 CSOs (11 attributable to DFID) were supported by FCS to increase citizen’s engagement in key statutory meeting including a focus on planning and budgeting processes at the local level. Example: Tanga Youth Development Association (TAYODEA) was supported by FCS to increase youth in all seven districts and 161 wards of Tanga Region to participate in planning and monitoring of development activities. TAYODEA has established Youth Parliaments in every ward in Tanga Region to serve as through which youth engage with planning and budgeting processes at the local level. / Recommendations: / FCS plans to increase its support to CSOs towards the remaining processes of the constitutional review. FCS needs to actively engage and collaborate with other actors especially with the DFID funded consortium of LHRC-Restless Development-Oxfam to ensure better synergy on constitution review work; / Impact Weighting 25% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[1] Note that all other references to numbers of beneficiaries in this document are a sub-set of 8.05 million.

Output 2: Increased CSOs role in contributing to improved transparency at a local level i.e. how LGAs/GoT allocate and utilize public resources;
Output 2 score and performance description: / Score: A+ / Indicator / - # of new CSOs supported to implement PETS (A) / - # of new CSOs supported to implement SAM (C) Milestone / 9 / 5 Achieved / 12 / 7
A = Attributable to DFID at 34%; C = Contributory / Progress against expected results: / During period under review, the Foundation managed to approve 34 projects that implemented public expenditure tracking surveys (PETS) and another seven that implemented social accountability monitoring (SAM) in a number of sectors such as education, health, agriculture, infrastructure and marketing. These interventions were successful in mobilizing over 53,588 citizens (27,212 male and 26,376 female) to directly participate and ensure proper utilization of public resources at the local level. / Following implementation of PETS/SAM projects, the following results were recorded: / 53,588 Citizens have increased their knowledge on SAM and PETS following PETS/SAM training conducted countrywide. / Formation of 54 PETS committees that led and championed citizens’ participation in promoting transparency over utilization of public resources; / Capacity of citizens in making follow up on utilization of public resources allocated during the year under review has been strengthened; / Increased ability of citizens to demand their rights from the local government officials and political leaders; / Some of the outcomes from PETS/SAM interventions included the following: / PETS committees rescued public funds from being stolen/misused. For example medicines worth 6 million Tanzanian shillings were rescued from being stolen during PETS exercise at Mvule dispensary in Pugu, Dar es salaam; / The government has set aside some amount of funds for development programmes following PETS/SAM advocacy. For example, Kinondoni municipality has set aside TZS 55 million for the development of Tandale market and TZS 85 million has been set aside for building dispensary in Manzese, Dar es salaam. / Different information, particularly budget, income and expenditure of local government authorities, can easily be accessed by different stakeholders through notice boards. / Recommendations: / FCS needs to continue to strengthen its monitoring and information system to better aggregate results under different outputs and themes e.g. PETS, SAM etc. to clearly articulate overall achievements and results. / Impact Weighting 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3: increased CSO involvement in empowering women, and addressing gender inequities and issues affecting other vulnerable groups;
Output 3 score and performance description: / Score: A / Indicator / - # and quality of new CSOs supported to sensitize women on their rights (C) / - % of women enabled to take up leadership positions in CSO/communities (C) / - # and quality of CSOs supported to address issues affecting people with disability, pastoralists and other minority groups (A) Milestone / 36 / 42% / 20 Achieved / 44 / 36% / 45
A = Attributable to DFID at 34%; C = Contributory / Progress against expected results: / A total of 44 CSOs were supported to sensitize and provide women with information on their rights to own assets and resources, especially land resources. Through FCS support, community groups were sensitised on the following policies and law that have a bearing on women’s rights and access to resources: the National Land Policy (1995); the Women and Gender Development Policy (2000); Islamic laws of Inheritance; the Law of Sexual Offenses; and the Marriage Act of 1971. / Examples of progress from supported FCS grantees include the following: / Women Rights: 44 CSOs were supported to specifically increase women’s participation in development processes. / Society for Women Aids in Africa (SWAA) managed to lobby the Mvomero District Development Committee to establish the District Education Fund for improving level of education, specifically targeting female students who are reported to be worse affected (by poor education levels) As a result the formed committee is in the process of establishing hostels for girls in each secondary school across the district; / The Pastoralist Women’s Council (PWC) from Ngorongoro has managed to establish special committees for advocating for women’s rights in eleven wards; / As a result of training conducted by Upendo Disadvantage Partnership, two widows managed to repossess their properties which were left for them by their deceased husbands. The organization has also managed to reach 2,332 people (1184 men and 1148 women) in six wards of Coast Region through training sessions and public dialogue. / GBV: During 2012, FCS supported AFNET - a CSO based in Dodoma - to empower communities in Iringa and Dodoma to change attitudes towards GBV, including addressing issues related to female genital mutilation (FGM). The project focused on mobilizing community members to increase their awareness on GBV and willingness to report such cases to the authorities. Some of the reported achievements by AFNET during 2012include: 50 community based facilitators on GBV were identified, trained and involved in carrying out sensitization activities to different groups in the communities ; 92,744 people in Iringa and Dodoma were reached of whom 74,128 were reached through GBV-focused interventions while 18,616 were reached through FGM-focused interventions; 18,000 copies of print materials (including newsletters, leaflets and posters) were printed and disseminated; over 100 community leaders - ward executive officers, village executive officers, police officers and magistrates - were trained on GBV and FGM issues; 33 journalists were trained and empowered on GBV and FGM issues. Training of journalists has led into increase in reporting of FGM and GBV issues The project has also been able to put in place a data bank on media reporting on GBV and FGM issues as well as ensuring that the victims of GBV/FGM who need legal aid are linked to the legal aid organizations. Leaders from faith-based organizations were also sensitized. As a result of this project, six GBV cases were reported to the police and primary courts and hearings are in progress; two cases were resolved by ward tribunals; one case was resolved by the ward executive officer; and one case was resolved by the district education officer; / Elderly Rights: Saidia Wazee Karagwe, (CSO in Kagera Region), managed to increase the capacity of 18,750 older people (8,976 men and 9,774 women) to participate in various developmental processes through advocacy and lobbying for their rights and entitlements. One of the key results following the activities is the formulation of seven Older People’s Self Advocates Groups. So far, these groups have succeeded in meeting with the ward councillors, District Commissioner (DC) and District Police Commanding Officer to address the increased incidents of human rights violations such as raping, assaulting and killings of old persons. / These efforts have resulted in decreased incidents of violations of the elderly’s rights. More elderly people are also reported to have accessed free medical services as per the National Ageing Policy of 2003; / Land Rights: FCS supported 19 CSOs during the period under review to engage citizens in campaigns to achieve better land rights and practices. Supported interventions focused on: increasing citizens’ awareness on duties and rights as highlighted in the National Land Policy of 1995 and Land Act No. 4 of 1999, as well as Village Land Act No. 5 of 1999; training and capacity building of village and ward land tribunals; and provision of legal aid to over 50,128 citizens (29,677 being females) on issues related to land and inheritance laws; / Persons with Disability (PWD): During 2012, FCS provided support to over 134 CSOs (45 attributable to DFID) that implemented interventions to address issues affecting persons with disability. These ranged from supporting the deaf to increase their engagement in community affairs through provision of sign language to advocacy campaigns that for example led to enabling 25 persons with disability to get sponsorship to attend vocational training in Dodoma and Iringa. / A total of over 48,579 (24,519 female) persons with disability were mobilized and directly participated in airing their views during the constitutional review process; / FCS sponsored a 1hr live TV show on Channel Ten to discuss the event and challenges facing people with Disability in the country. Representatives from the national Disability Association and the general public got a chance to ask questions and to participate in the discussion; / Zanzibar Association of the Disabled was able to reach over 5,075 people altogether in Zanzibar and achieved the following successes: a) Provided information to at least 120 PWDs through awareness training on Community-Based Rehabilitation (CBR), the UN Convention on Rights of People with Disabilities and the Zanzibar Disability Act; b) Supported training on community-based rehabilitation and early detection of disabilities for CBR volunteers, health workers, traditional birth attendants and traditional healers and Madrassa teachers; c) Supported 8 outreach programmes to initiate community-based rehabilitation for 240 children with disabilities; and d) Provided socialisation and recreation for 360 children with disabilities through the formation of eight playgrounds; / FCS supported the printing of 4,000 copies of current United Republic of Tanzania Constitution in Braille so as to enable persons with visual disability to actively participate in the constitutional review process. / Recommendations: / FCS needs to strengthen its monitoring and information capture system and find better ways to aggregate results under different themes e.g. MCV, GBV etc to clearly articulate overall achievements and results. Current information provided is only limited to grantee level achievement; / Impact Weighting 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 4: Strengthened CSOs organizational capacity and policy engagement effectiveness;
Output 3 score and performance description: / Score: A / Indicator / - Number and quality of new CSOs supported on institutional and organizational capacity (A) / - % increase of policy dialogues with active participation of CSOs (C) - Proportion of FCS supported CSOs with improved overall impact capability(C) Milestone / 100 / 70% / 67% Achieved / 92 / 76% / 68% / A = Attributable to DFID at 34%; C = Contributory
Progress against expected results: / Capacity Development Services: Through a systematic approach towards strengthening the capacity of supported grantees, a total of 1594 representatives from 1,031 CSOs were involved in various institutional and capacity building interventions to address identified organizational capacity gaps, as follows: / Manage Your Grant trainings: a compulsory training for each CSO receiving grants from FCS. A total of 818 participants representing 409 CSOs were trained; / Tailor-made trainings: a total of 19 sessions of tailor made trainings session were conducted for 731 representatives from 622 CSOs. Topics covered in these sessions included: project design and management, M & E, financial management, strategic planning, documentation, participatory planning approaches, and fundraising techniques; / Policy Dialogues / In efforts to build a stronger, more focused sector, FCS organized platforms for dialogues between CSOs and government officials, MPs and other officials. They included: / East Africa Community: FCS in collaboration with TMEA and EAC Secretariat organized a Civil Society Forum which brought together over 110 CSOs from across East Africa Community partner states to discuss issues related to East Africa Community and more specifically the role of CSOs in fostering citizens’ engagement in the EAC integration processes. In order to strategically influence EAC issues to be pro-poor, CSOs in Tanzania are working to establish East Africa Civil Society Forum- Tanzania chapters. This will serve as a forum through which CSOs can unify their voice and communicate EAC-related issues to the Government, EAC Secretariat and East Africa Legislative Assembly; / Annual National Policy Dialogue: FCS collaborated with the Ministry of Finance and Economic Affairs in promoting civil society participation in Annual National Policy Dialogue (ANPD) in 2012. Its objectives were to discuss progress reached in implementing MKUKUTA IIand making the general public aware of the 5 Year Development Plan as a new national framework for facilitating development in the country. The forum was attended by 200 participants drawn from CSOs, farmers, private sectors, faith-based organizations, government, development partners and representatives from bilateral organizations, etc.; / Statements by CSOs during this dialogue focused on three key areas, namely; a) budget transparency, b) poverty reduction, and c) constitutional review process. / Nine (9) Policy Dialogues were conducted by an FCS grantee (Economic and Social Research Foundation – ESRF) from which four (4) Policy Briefs and six (6) Discussion Papers were produced, published and disseminated within the project duration, up to end of 2012. These included: / i) Poverty Escape Routes in Central Tanzania: Factors affecting Mobility in the Case of Dodoma Region. Vol. I, II and III; ii) How Can Africa and Tanzania Benefit From The Experiences of a Prosperous China? iii) Strengthening Micro-enterprises in Tanzania: Small Scale Non-Traditional Agricultural (Horticulture); iv) The Role of Mobile Phones on People’s Sustainable Livelihood in Tanzania. The Case of Arusha and Zanzibar Regions. 2011; v) Land Governance amidst Conflicts and Corruption in Tanzania. 2011; vi) Inter household Private Income Transfers and Poverty in Tanzania; vii) Governance Breakdown in the Urban Malaria Control: Policy Reflections in the Outburst of Msimbazi Valley Mosquitoes, Dar es salaam; and viii) Land Factor in Mining Gold Reserves in Tanzania. 2011; / Improved CSOs relations with House of Representatives (HoR) in Zanzibar: FCS supported the Association of Zanzibar NGOs (ANGOZA) to organize CSO exhibitions during the HoR sessions in Zanzibar to showcase advocacy work being done by CSOs in Zanzibar. Over 55 CSOs were able to showcase their work to the Representatives during the two-day event. This event resulted in improved relationships and partnership between CSOs and members of HoR, especially focusing on identifying ways to further enhance citizens’ participation in implementation of MKUZA II; / Strengthening CSO networks for increased policy influencing: during period under review, FCS formulated 84 CSOs Regional Working Groups. The aim of these groups is to ensure that CSO networks are better organized in influencing governance and budgetary process at LGA level with a view to: making policies and decisions of the officials at subnational levels reflect the needs of citizens and become pro-poor; stimulating the culture of transparency and accountability of decision makers; making LGA budgets and plans more pro-poor; increasing active members of CSOs in one or more networks / Recommendations: / It is very positive to see FCS mobilizing its grantees and citizens to better engage in promoting East Africa regional integration. FCS could consider including CSO increased role in regional integration as one of its new result areas in its new strategy 2014 - 2017 / Impact Weighting 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 5: Foundation for Civil Society is delivering high quality services and is efficiently and effectively managed and governed;
Output 3 score and performance description: / Score: A / Indicator / - % of CSOs supported to implement projects in the rural areas(C) / - number of monitoring visits to grantees (C) / - number of applications received and processed on time (C) Milestone / 65% / 200 / 2,000 Achieved / 51% / 236 / 2,462
A = Attributable to DFID at 34%; C = Contributory / Progress against expected results: / FCS has made good progress in ensuring that the organization and services provided are of high quality and are efficiently and effectively managed and governed. Results attained under this output include the following: / Audited Financial Statement produced by independent auditors and available on time to DPs as stipulated in MoU. FCS got clean opinion and management letter showed few and minor queries raised by external auditors. All queries were adequately responded to by FCS management / Two FCS-DPs meetings were organized and implemented as per MoU. Documents were provided on time and proper agenda and minutes clearly indicate implementation of agreed key action points; / One joint FCS-DPs Monitoring visit was organized and conducted as per MoU. The visit was conducted in Morogoro and Iringa regions; / 513 support visits were conducted compared to the annual target of conducting 500 visits. The visits were aimed at providing support to grantees on various technical areas so enable them to improve their performance; / 20 information sessions (100% of the annual target) were held, aiming to encourage more applications from rural areas and give unsuccessful applicants opportunities to raise questions or issues to help them improve their future applications. About 1000 CSO reps attended; / By December 2012, a total of 2,462 grant applications were received and processed, surpassing the annual target by 23%; / Due diligence was conducted to a total of 874 CSO applicants after the initial application screening. Out of those, 70.4% were recommended for final approval. / Recommendations: / FCS has an extensive system of carrying out due diligence (DD). DFID programme management team will in 2013/14 seek to review FCS due diligence tools to ensure compliance with DFID recent guidance on DD. / Impact Weighting 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: A+ / The programme has performed well across all of the outputs. / 1.3 Direct feedback from beneficiaries / FCS has good mechanisms to ensure beneficiaries provide direct feedback on the implementation of supported projects. Some of these mechanisms include: / Joint Monitoring visits: each year FCS organizes joint monitoring visits, providing opportunities for funding partners to meet and interact directly with grantees and beneficiaries. During the period under review this visit was conducted in Morogoro and Iringa regions. All beneficiaries met had a clear understanding of what objectives FCS grantees were seeking to achieve and in a number of cases beneficiaries are also making in-kind contributions to support those objectives; / Annual pre-award visits and regular monitoring visits to grantee through the FCS Monitoring Unit. In 2012, a total of 513 monitoring visits were conducted; / Information sessions – during 2012, FCS conducted 20 information sessions throughout the country to insure that CSOs and community beneficiaries are more aware of activities funded and implemented by the FCS. These sessions serve as a good platform for FCS to receive direct feedback from beneficiaries.
Summary of overall progress / FCS supports very many small CSOs across Tanzania. During 2012, 570 new CSOs were supported. This brought the total number of on-going projects by end of December 2012 to 990. Other key achievements include / Reaching a total of 8.01 million beneficiaries with different types of information on their rights, roles and responsibilities; / A total of 2,462 grant applications were received and processed, surpassing the annual target by 23%. 616 new CSOs were approved to receive grants pending a successful due diligence exercise; / Provision of support to over 134 CSOs that implemented interventions to address issues affecting persons with disability; / A total of 44 CSOs were supported to sensitize and provide women with information on their rights to own assets and resources, especially land resources; / Supported 34 projects to implemented public expenditure tracking surveys (PETS) and another seven to implement social accountability monitoring (SAM) in a number of sectors such as education, health, agriculture, infrastructure and marketing; / supported and facilitated the conduction of 300 specific public dialogues at constituency level across Tanzania to increase citizens engagement with the constitution review process; / distributed over 350,000 copies of the current constitution; / Production of six documentaries and Television Programs of which a) two showcased the role that Paralegals are playing in helping the poor to access justice; b) three focused on constitutional review dialogue; and c) one on disability
1.5 Key challenges / Due to sheer volume of grantees supported and diversity of issues covered under the broad themes of governance and accountability, it is quite a challenging task for FCS to find better ways of aggregating results beyond the headcount aspect. Most of the supported grantees have a grassroots focus and implement projects at a relatively small scale.
1.6 Annual Outcome Assessment / The outcome of the programme is “more citizens are more empowered to participate, influence and monitor pro-poor policies and budgeting processes for improvement of services in Tanzania by 2015.” Results generated through this annual review indicate that the programme is delivering results that contribute to the achievement of the outcome. / Support to interventions that reached over 8 million citizens and increasing citizens’ engagement in the on-going constitutional review process are among the key examples of the outcomes of the FCS’s work during 2012. During the period under review, FCS commissioned a citizens survey (sample size of 626) to measure progress over its outcome indicators. The following are the key findings from this survey of beneficiaries: / 83% of the beneficiary citizens said that they made a difference by publicly expressing their views on local issues that affect them; 63% organisations supported by the Foundation were aware of key policy processes; 85% of Citizens were aware of their civic rights and responsibilities (against FCS target of 77%); 56% of the citizens expressed satisfaction on the quality of basic services delivered by the government institutions (against FCS target of 60%); and 27.4% of citizens said that they have seen their local government budget posted in a public place (against FCS target of 13%) / Drawing from a much larger sample size (of 5,136), findings from the Views of the People Report (2012) shed more light on outcomes of citizen engagement and empowerment in Tanzania that FCS and other actors have made a contribution to: / 68% and 42% of respondents were aware (knowledge) of Kilimo Kwanza and MKUKUTA respectively. Large majorities (over 90%) of respondents across research sites were aware that pregnant women, old people, the poor, People Living with HIV/AIDS (PLHA) and children under five were entitled to free medical services in public institutions; / Respondents’ participation in various activities: attended full council meeting (50%); attended a civic education course (9%) and helped prepare a village/ward plan (20%); / About two-thirds (66%) of respondents agreed with the view that Tanzania was better off with a competitive political system; and nearly three-quarters (72%) of all respondents had a positive view of the opposition’s performance; / Twice as many respondents (62%) saw official abuse of position as opposed to ‘culture’ (30%) as main cause of corruption; and 51% believed that their local councils misuse financial resources. / Other examples of outcomes that have been reported by FCS from its annual implementation report include: / Tanzanian Shillings 140 million were set aside for development programmes by local government in Kinondoni municipality as an outcome of FCS grantee’s advocacy efforts; / Medicines worth Tanzanian Shillings 6 million were rescued from being stolen/misused at Ilala Municipality in Dar as an outcome of increased citizens participation in following up public resources and increased transparency through local PETS; / Over 560 community resource persons were empowered with legal and human rights skills (as paralegals) who in turn were able to reach out to over 45,000 community members with legal aid services in hard-to-reach, remote areas in Tanzania; / 31 Disabled People Organizations representing over 50,000 persons with various disabilities were directly supported to engage with the constitutional review process. This engagement is believed to have contributed to shaping the content of Chapter Four section 44 of the draft constitution, where there is now an explicit mention on the rights of persons with disabilities.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers: Recurrent/operational costs for the delivery and implementation of the programme on behalf of DFID are the key cost drivers. During 2012, these costs were at 14.7% of the total annual spending. This is consistent with the projection made in the approved business case. / 2.3 Is the project on-track against original timescale: Yes.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / FCS’s Theory of Change remains relevant. Results during 2012 confirm that support being provided to civil society organisations is contributing to increased awareness of rights and improvements in the utilization of public resources. This will contribute to improvement in service delivery. The provision of small grants and capacity building to a diverse range of civil society groups has contributed to increasing quality and quantity of information reaching citizens about their rights, resources and policy. Results during 2012 further indicate that some CSOs have directly engaged elected representatives. There are good examples in this review which indicate how supported CSOs have contributed towards directly monitoring and defending citizens’ rights e.g. through provision of legal aid. / 3.2 Where an evaluation is planned what progress has been made? / DFID do not plan to do an evaluation of FCS as it was not identified as a priority when compared with other programmes in the office’s portfolio.

4. Risk
4.1 Output Risk Rating: Low / Assessment of the risk level / Overall, the risks of this project not achieving its outputs should be seen as low. This is largely due to the nature of specific interventions and the current operating environment in Tanzania where at local and national levels CSOs are allowed to operate without state or political interference. The on-going constitutional review process is another key milestone. CSOs have managed to mobilize and increase citizens’ engagement in the constitutional review process.
Risk of funds not being used as intended / FCS implements a small grant scheme where applicants are supposed to provide detailed activity-based budgeting. FCS has in-house mechanisms that ensure proper funds utilization by grantees. They include: / Manage Your Grant (MYG) training course. This training is mandatory and designed to enhance the capacity of selected CSOs to properly manage their grants. A total of 818 participants from 409 (173% of the annual plan) CSOs were trained during the reporting period; / Auditing of Grantees: a sample of 242 grantees was audited by external auditors. Scope of auditing included bank reconciliation, expenditure management, proper coding, supporting documents, record keeping and cash book maintenance. Other areas include: adherence to financial management regulations and procurement procedures, and how the accounting system operates, including segregation of duties, payment vouchers etc. 83% of audited CSOs received clean audit reports; / Due diligence: A total number of 874 prospective grantees were visited after the initial screening. Out of those 615 (70.4%) were approved for funding. / FCS has an anti-corruption policy which states that: The Foundation for Civil operates a Zero Tolerance policy on all forms of corruption, both within the Foundation and its services, and externally with all whom the Foundation may have any association. Any member of the Foundation found guilty, following a full in depth investigation of inappropriate corrupt practice will be severely dealt with under the Foundation’s disciplinary procedures. / Where any member of the public has any cause of concern with regards to any individual associated with the Foundation, he should contact the Executive Director, in full confidence, and inform him of the issue as early as possible, in writing if possible, or any other means available, providing as much evidence to support his/her claim immediately after being alerted or directly approached. The Executive Director will ensure that the matter is investigated confidentially and sensitively within the Foundation’s complaints procedure and guarantees the anonymity of the complainant, so as not to place the complainant in a position of vulnerability. The complainant will not be discriminated in any way as a result of making a genuine complaint. / 4.4 Climate and Environment Risk / FCS intervention is rated as category C: No / Low risk but medium opportunity. Most of expected outputs will also have a positive impact on i) delivery of environmental services ii) management and use of natural resources, and iii) the collection and use of revenues collected. During 2012, FCS supported about 47 CSOs whose interventions had a direct contribution towards enabling more citizens to have access to information about natural resource management, environmental policy and water resources. Examples includes: / Community Development and Environmental Conservation Organization Zanzibar managed to conduct a 3 days open forum to 255 community members from 29 Shehias in Unguja on environmental management. The project reached 226 people (118 women and 108 men). These forums were suitable avenue for citizens to air their environmental concerns, and were strongly able to make call to the government to speed up the review of National Environment Policy. Participants formed environmental protection clubs as a measure to continue reducing environment destructions in their Shehias. / Journalists Environmental Association of Tanzania (JET) was engaged in the fight against dynamites fishing through use of media. Through its network of journalists, JET produced 16 newspaper features on illegal fishing that were published in the Tanzania local papers: Raia Mwema, Rai, Nipashe and the Guardian. It also produced 4 TV programmes aired through TBC1 (2 programmes) Star TV (2 programmes); and 4 radio programs through TBC Taifa. The project has collected about five case studies of fishermen abandoning dynamite fishing as a result of JET programmes that were aired on TV and radios.

5. Value for Money
5.1 Performance on VfM measures / VfM measures identified during the BC submission of FCS include the following: / Economy: During 2012, programme management costs were at 14.7% of the total annual spending. This is consistent with the projection made in the approved business case; / Efficiency & Effectiveness measures: as a follow up to DFID’s recommendation in the last annual review, during 2012, FCS commissioned an independent VfM assessment of its training and capacity building work to measure its efficiency and effectiveness. / FCS contracted Social Return on Investment (SROI) Africa consultancy to understand the impact of the 2012 tailor-made courses, which comprised courses in: Project circle management; Financial management, peer learning, Monitoring and evaluation, Organisation development, Proposal writing. SROI consultants used DFID guidance on capacity building which states that: The goal of capacity building, for DFID, is to facilitate individual and organisational learning which builds social capital and trust, develops knowledge, skills and attitudes and when successful creates an organisational culture which enables organisations to set objectives, achieve results, solve problems, and create adaptive procedures which enable them to survive in the long run (Guidance for Capacity Building, DFID Research Consortia, 2009). / Conclusions from SROI assessment: The SROI evaluation included calculations for attribution (who else influenced), deadweight (what would have happened anyway), displacement (were changes made at the expense of someone else) drop off (how long the change lasted) and calculated net present value, across the change period of five years. This establishes the ratio of investment to social value delivered. It is concluded that for the sum of Tzs 605 m a massive Tzs 23.5b is produced. This gives an SROI ratio of 1 to 61. Meaning that, for every one Tanzanian Shilling invested, just over 60 have been generated in social, environmental and financial capital. To large groups of people that have limited access to information, exposure or inclusion, the value of the work the civil society organisations do is inspiring. This has resulted in a ratio of over 1:60. This type of result would be impossible in the UK for instance, where the average ratio would be 1:3.5 or 1:4. It should be noted that the GDP per capita is nominally $599 in Tanzania and nominally $38,589 in the UK, which is over 64 times greater. Therefore a relatively small sum of money makes a far greater impact than if the same amount was spent in the UK. / 5.2 Commercial Improvement and Value for Money / The nature of the Foundation’s work means that it does not undertake large procurement exercises. As a grant-giving institution, selection of grantees, disbursement and monitoring of grants are the core business of the Foundation. / A procurement assessment of FCS was done in 2011 by DFID (as part of DFID’s extension of its support to FCS). It confirmed that FCS has an adequate system for procurement of goods and services. / Role of project partners / Majority of FCS grantees are smaller CBOs. They all contribute to the vfm agenda through ensuring that their project proposals are adequately focused in terms of outputs to be achieved. Detailed budget to activity level is also required. Through FCS capacity building interventions, grantees are regularly trained on financial management, m & e and reporting requirements. All these aspects are meant to promote vfm. FCS has recruited an internal audit function to strengthen internal controls and ensure compliance with all standards / 5.4 Does the project still represent Value for Money : Y/N / Yes / FCS programme continue to offer good vfm. Results achieved and input costs (especially management costs) are in line with those outlined in the business case. Providing over 8 million citizens with information on their rights or entitlement, as well as recording cases of incidents where officials at national and or local levels have made specific decisions or taken action as a result of citizen engagement is a notable achievement of the FCS programme. / The outcome of the programme is “more citizens are more empowered to participate, influence and monitor pro-poor policies and budgeting processes for improvement of services in Tanzania by 2015.” Results generated through this annual review indicate that the programme is delivering results that contribute to the achievement of the outcome. / SROI ratio of 1:60 is impressive and confirms that work by FCS is generating social, environmental and financial capital. / 5.5 If not, what action will you take? / 5.6 VfM lesson learnt / Through this annual review, an initial good attempt has been made by FCS to employ a tested and systematic approach to measure efficiency and effectiveness of its interventions through the use of SROI methodology. One key lesson from the SROI exercise is the need for FCS to have a more comprehensive approach to data collection and management.

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The programme is performing well, meeting the majority of output milestones. The following are main conclusions and actions: / FCS needs to strengthen its monitoring and information capture system and find better ways to aggregate results under different outputs and themes to clearly articulate overall achievements and results. Current information provided does not provide a comprehensive picture of achievement. / FCS plans to increase its support to CSOs towards the remaining processes of the constitutional review. FCS needs to actively engage and collaborate with other actors especially with the DFID funded consortium of LHRC-Restless Development-Oxfam to ensure better synergy on constitution review work; / It is very positive to see FCS mobilizing its grantees and citizens to better engage in promoting East Africa regional integration. FCS could consider including CSOs’ increased role in EA regional integration as one of its new result areas in its new strategy 2014 - 2017 / FCS has an extensive system of carrying out due diligence (DD) with its grantees. The DFID programme management team will in 2013/14 seek to review FCS due diligence tools to ensure compliance with DFID guidance on DD. / FCS also needs to ensure every supported grantee continues to pay greater attention to the issues of governance and oversight, putting in place mechanisms that ensure funds are properly utilized and that grantees are vigorously fighting all forms of fraud and misuse of funds; / 2013/14 provides FCS with an opportunity to review and develop its four-year strategic plan for 2014 – 2017. FCS will need to make a comprehensive analysis of its first 10 years of supporting CSOs in Tanzania and ensure that experience adequately informs the next strategy. The strategy needs to adequately respond to accountability needs of Tanzania post-2015, taking into account new political and economic prospects, and bearing in mind potential changes and challenges that will be brought by the envisioned new constitution.

8. Review Process
This review was drafted by DFID staff based on FCS Annual Report (2012).