Type of Review: Annual Review

Project Title: Humanitarian Emergency Procurement Programme

Date started: 1 August 2012	Date review undertaken: 20 August 2013

 Introduction and Context

What support is the UK providing?
The UK will provide up to £7.25 million over a three year period to ensure non-food items can be delivered to those in need, rapidly in sudden onset emergencies. Complementary specialist logistics and supply chain management support will be provided through the on-going Humanitarian Emergency Operations Support Services programme. Following an interim review of UK government humanitarian stockholdings in November 2012 it was agreed that there should be an immediate uplift of £4 million to enhance the range of emergency supplies held in UK stocks and increase official deployment capability. An evaluation after two years of the programme will consider an extension of support at a similar level for a further two years.

What are the expected results?
The results of this investment will ensure the UK Government can respond quickly, effectively and appropriately to a broad range of humanitarian crises (including urban crises), drawing on equipment and materials that enable them to meet the needs of affected communities, and ensure they can support the field deployment of DFID and key partners for up to three simultaneous events. This investment will also inform current and future engagement with the wider international humanitarian procurement system.

What is the context in which UK support is provided?
As part of the toolkit needed to ensure an effective direct bilateral response to a sudden onset or emerging slow onset emergency it is vital that DFID holds or is able to rapidly access lifesaving and essential shelter materials and other specialist non-food items (NFIs) that can be quickly and effectively deployed to meet the immediate humanitarian needs of affected communities. It is equally important that the UK Government is able to access, and use, high quality and effective equipment and materials to support the deployment of field teams and, where common support platforms have been agreed, partners’ specialist teams where we support their deployment. / In order to meet these needs DFID has established UK Government humanitarian stockpiles, currently mainly located in Dubai and Kemble, of materials and equipment that can be drawn on in a response. DFID has also developed a network of suppliers, including an awareness of their production capacities and stockholdings, who can supplement these resources as needed; which has been particularly important in enabling the UK Government to meet more specialist or less predictable needs. The humanitarian stockpile works in parallel with a similar Stabilisation Unit (SU) support package and shares warehousing, labour and maintenance services. To meet future challenges DFID needs to maintain these resources while undertaking an on-going process that reviews needs and the performance of the materials they hold or procure and the locations of stockpiles, and ensures the UK takes advantage of innovation and new technology. Additional items may be procured where they are necessary or desirable, or to support innovations in the humanitarian response. / Following an interim review, in November 2012, of the current holdings of emergency relief items it was proposed that an immediate uplift of £4 million be added to the humanitarian response capability. This uplift will enable the UK Government to meet the needs of 38,750 people, an increase of 21,250 over the original stockpile capability, and increase the range of non-food items that can be delivered during an emergency response. The uplift will also improve the quality of UK government response by enabling us to provide support which meets the wider needs of disaster affected populations. The uplift also extends the ability of field teams to rapidly deploy by increasing the range of mission critical equipment at our disposal and by improving our logistical capability to move field teams and equipment at short notice.

## Section A: Detailed Output Scoring

Output 1: UK Government humanitarian stocks can meet the needs of affected communities across a wider range of humanitarian crises.
Output 1 score and performance description: / A – Outputs met expectation
Progress against expected results: / Output Indicator 1.1: UK stockpile (quality, content, volume) is kept under review to ensure it is able to meet humanitarian needs on an on-going basis and respond to emerging needs. / Progress against this output has been delivered as expected, with the stockpile composition having been reviewed for both NFIs and support equipment. The reviews have been undertaken by means of an assessment led by CHASE Operations Team (CHASE OT) logistics experts coupled with the benchmarking of the scale and type of holding of partners and other donors. / The reviews led to an uplift of the project budget from £3 million to £7.25 million to enhance the range of UK emergency supplies held in stocks and increase official deployment capability. / Since the interim review there has been an increase in the issuance and completion of the range of framework agreements. The revised NFI holding has enabled a focus on the provision of family based sets with options for cold climate and urban settings (e.g. human waste bags). / The procurement process for the NFIs is on-going, with the first additional commodities expected by the end of the 2013. Support equipment reviews have thus far focused on specific country responses such as Syria with the tailoring of support equipment to specific environments, including the provision of appropriate vehicles to the UN. / A review of shelter items was conducted by CHASE OT which identified a manufacturing fault in approximately 1 in 10 stockpiled tents. Remedial actions were initiated with manufacturers for 2,100 tents (due to be completed August 2013). / Installation of new portable satellite system (ISAT) and digital VHF and the development of digital radio networks has been completed. / Support for the distribution of emergency NFIs for hurricane preparedness from the Cayman Islands to Overseas Territories in December 2012 was undertaken. / The procurement of equipment in support of Syria crisis preparedness, including both NFIs and preparatory equipment for Syria deployment was completed. Scoping visits were also undertaken to Turkey and Jordan to prepare for the movement of goods and equipment to the region. / The following has also been achieved in direct support to meet humanitarian needs: / In January 2013, 21,000 blankets, 500 tents and 1000 shelter kits were delivered to UNWRA in Lebanon. These were subsequently shipped to Damascus to assist displaced populations there. These stocks have since been replenished / 12 armoured vehicles and body armour for use in Libya, Nigeria and Syria. Replacement procurement completed for 2 vehicles with procurement of 2 underway. / 14 armoured vehicles were provided to WFP, UNHCR, UNICEF and OCHA in Syria and stocks replenished. / Procurement of medical consumables for RRF Sierra Leone cholera response, and assessment of NGO proposals. / Recommendations: / Further development and procurement work will be required on the NFI range in association with relevant partners. This will also need to be undertaken due to a number of existing frameworks expiring in 2014. Specific elements of support equipment will also need to be programmed for review in 2014. / Impact Weighting (%): 50 / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A

Output 2: Agreements in place to provide rapid access to essential materials and equipment held outside the stockpile.
Output 2 score and performance description: / Output met expectation
Progress against expected results: / Output Indicator 2.1: Effective links made to agreements under the Rapid Response Facility that enables rapid access to goods, equipment, materials not held in UK stockpile. / Output Indicator 2.2: Links made with potential private sector suppliers and innovators of international humanitarian products. / In January 2013 a tender was launched for the establishment of new framework agreements under the Rapid Response Facility that would enable the UK Government to meet the challenges of bigger, more frequent and complex emergencies. The range of products identified in this first tender complement existing holdings to form a family support package for beneficiaries with the following items: Buckets, hygiene kits, water treatment and filtration, toilet bags, solar kits, kitchen sets, sleeping mats and hand tools. This has led to overall framework agreements for NFI commodities being increased by 18. Recent frameworks focus on ability to access goods for stock, from production in a response and also for supplier held stocks (such as part finished goods like solar lighting). / CHASE OT has developed an innovations filter to assess the products and services presented to DFID on behalf of manufacturers for their potential use in humanitarian emergencies. Products are assessed against criteria including whether they are fit for purpose, meet relevant international specifications, and if their procurement would represent good value for money. Subject to the outcome of the evaluation, a recommendation will be made on whether the UK Government should purchase products for the stockpile, whether they should add the supplier to those who may be approached on an “as needed” basis or whether the product is not appropriate for use. In some cases the potential supplier is introduced to other organisations. The first field trial of goods which have successfully passed this filter is currently underway with Oxfam for the Lifesaver water purification jerry can. / CHASE OT procurement and logistics staff have attended numerous trade events and organised shared lessons learned events to increase the UK Government’s own networks and understanding of commodities. An example of this is the armoured vehicle procurement workshop held with the UN. / Recommendations: / The further development of framework agreements should be continued, in particular with those that will allow for devolved stock responsibility. In 2014 work should begin on developing improved airfield handling capabilities. / Impact Weighting (%): 10 / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A

Output 3: UK stockpile(s) appropriately located
Output 3 score and performance description: / Output has met expectations
Progress against expected results: / Output Indicator 3.1: That the UK is assured that the location of the items in the stockpile programme are optimally located to reduce suffering and morbidity, offer value for money and are resilient. / Output Indicator 3.2: DFID held relief items linked effectively with DFID air service provider (Air Partners) operations and those of other logistics/transport providers to ensure a seamless supply/deployment process. / A review of geographical locations is being undertaken linked to the on-going development of the stockpile holdings in terms of both their scale and the potential devolved nature of holdings to suppliers. This is also considering the extent to which the UK Government should or could have more regional deployment holdings. / CHASE OT are reviewing whether it would feasible to establish mini-hubs of immediately deployable kit that would be available in at risk priority countries including Ghana, Kenya, Nepal, and Pakistan. / A review of the current policy of holding stocks in the United Arab Emirates is underway and discussions continue with potential partners to undertake further reviews of the appropriateness of current locations to DFID’s anticipated areas of operation in the coming years. / Recommendations: / Continued work will need to be undertaken on reviewing locations and appropriateness with a target date of December 2013 anticipated for the delivery of this work, as per the business case. / Initial work needs to be undertaken on developing the DFID approach to air movements in collaboration with the DFID air broker. / Impact Weighting (%): 5 / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A

Output 4: Implementation of agreed recommendations to support, improve and replace existing international systems
Output 4 score and performance description: / N/A
Progress against expected results: / Output Indicator 4.1: Effective system in place that ensures all members of the international humanitarian community can quickly identify and access NFIs and deployment equipment held by individual organisations in the community. / Output Indicator 4.2: Support to improve international stockpile monitoring systems. / Not yet begun, in line with logframe expectations at this stage. / Recommendations: / A study is required to understand the current international capability in this area, its shortcomings and how improvements can be made. This is likely to form the basis of an outsourced research agenda. / Impact Weighting (%): 10% / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A

Output 5: Implementation of agreed recommendations on standards and dissemination and compliance.
Output 5 score and performance description: / Output has met expectations.
Progress against expected results: / Output Indicator 5.1: Effective system in place to establish and monitor minimum acceptable standards for shelter materials and NFIs provided in response to emergencies. / Meetings have been held with water, sanitation and hygiene (WASH) partners to better co-ordinate the contents and application of hygiene kits as well as household water treatment solutions. / Advice has been provided to humanitarian advisors regarding the specification of goods listed in partner proposals to highlight value for money (VFM) issues as well as the understanding of appropriate quality and specification. / DFID has amended its own inspection regime to better determine reliability of quality in production. DFID does not have a baseline for commodity specifications funded (nor the on-going quality and assessment of provided goods) which has made engagement with partners difficult. / Recommendations: / A greater outreach from DFID is required to understand variation across partners, and to better co-ordinate DFID’s expectations on meeting international specifications and the needs of quality provision. / Impact Weighting (%): 10 / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A

Output 6: Innovations and emerging technology in essential humanitarian equipment and materials are properly assessed and, where appropriate, brought into standard stockholdings. Results of assessments shared with wider humanitarian community
Output 6 score and performance description: / A – Output has met expectations
Progress against expected results: / Output Indicator 6.1: Effective system in place to enable innovation in NFIs to be properly assessed and, where appropriate, brought into standard practice for both DFID and the international community. / Output Indicator 6.2: Review undertaken to establish a range of NFIs/complex equipment/difficult to obtain materials that would not be appropriate for the UK stockpile (short expiry date, rapid innovation in sector, high value, high maintenance costs etc etc) but where we would want assured provision. / The recent RRF tender process focused in part on new and emergent technologies in order to encourage approaches form the commercial sector globally (solar power, human waste disposal etc). The results of the tender were mixed, with a number of the commodities received not deemed to have met the requisite standards. / CHASE OT has begun a process of quantifiable, repeatable testing on the solar power products to assess suitability of different products to differing response scenarios. The results of this will be disseminated to partners. / Installation of new portable satellite system (ISAT) and digital VHF, and the development of digital radio networks has been undertaken. / On-line training for armoured vehicles in development for use by local drivers and personnel overseas in a bid to improve understanding and operation has been carried out. / Development work is planned on the emergency shelter holdings of DFID, which are due for re-tender in 2014. This has been undertaken in conjunction with the Building Research Establishment (BRE) with a particular focus on defining more accurately the thermal capability of existing tent designs. / Recommendations: / Continued development and refinement of commodities with further outreach to the private sector for engagement in the humanitarian sector. / Impact Weighting (%): 5% / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A

Output 7: DFID held stocks support the deployment of DFID staff (and / or those of partners specialist teams) into a range of environments for up to three simultaneous deployments
Output 7 score and performance description: / Output has met expectations
Progress against expected results: / Output Indicator 7.1: DFID has the equipment and resources in place to enable the immediate deployment of up to twenty people to a range of environments and which can be scaled up in line with changing UK response capability. / Output Indicator 7.2: Instigate on-going review and testing of innovations and emerging technology in deployment platform holdings to ensure they are properly assessed and, where appropriate, brought into standard stock holdings - and referred to other relevant actors in the international humanitarian community and UKTI as appropriate. / Deployment equipment has been tailored for potential deployments to Syria with the establishment of equipment focused on urban settings. / DFID’s deployment capabilities continue to be supported through the availability of 20 person, 5 person and 2 person deployment kits. / The vehicle fleet has been augmented with petrol vehicles (allowing for their provision to UN partners and DFID overseas offices) whilst maintaining a baseline diesel fleet for relevant countries. / A specific medical support module has been created to support UK-MED in their deployments whilst the UK International Emergency Trauma Register is prepared. / The equipment and the UK Government facility at Cotswold Airport has been used for pre-deployment training of staff as well as for enhancing the international system through initiatives such as the Armoured Vehicle Procurement Workshop run for various UN agencies. / Recommendations: / Further development work in key areas (communications, vehicles) as well as the benchmarking of equipment against liked minded organisations during the forthcoming TRIPLEX exercise. TRIPLEX is a regular, International Humanitarian Partnership-run, full-scale simulation exercise, enabling a range of humanitarian actors to practice their response mechanisms in a sudden-onset natural disaster scenario. The next TRIPLEX will take place in the Danish-German border region from 28th September to 4th October, 2013. / Impact Weighting (%): 10 / Revised since last Annual Review? N/A / Risk: Medium / Revised since last Annual Review? N/A

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? / Yes. An interim review of UK Government humanitarian stockholdings was undertaken in November 2012 at which point the logframe was amended to take into account the uplift in the programme budget. / 1.2 Overall Output Score and Description: / A – Outputs have met expectations. / 1.3 Direct feedback from beneficiaries / On-going monitoring of this project has been undertaken in line with the requirements as defined in the contract for the Humanitarian Emergency Operations Support Services and in the monthly meetings of the combined management teams. At the initial meeting (March 2013) DFID said it was satisfied with CHASE OT’s overall performance, particularly ability to initiate and manage change. / Following the deployment of NFIs to UNWRA in support of the response to the Syria crisis, DFID has received extremely positive feedback regarding both the swiftness and efficiency of their delivery, and the quality of the items supplied.
1.4 Summary of overall progress / Progress against the expected outcomes for this project has been good, meeting all of the expectations plotted in the logframe by this period. This is particularly impressive in light of the uplift in the project budget and the additional administrative pressures this has placed on the CHASE OT procurement team to meet the revised logframe. The primary function of the stockpile, to quickly, effectively and appropriately deliver humanitarian relief supplies, has been fulfilled following the successful deployment of a significant tranche of materials to support the response to the humanitarian crisis in Syria. / Additionally, considerable work has been undertaken to review the quality of the items currently held in stock, and the acquisition of additional goods where it has been perceived that they will complement and enhance what is already available. The completion of the first tender to establish a set of new framework agreements under the RRF has also been important both in terms of providing access to materials that the UK Government would not normally hold, and in providing information regarding what the market has to offer in respect of supplying humanitarian goods. / Work on influencing and improving the effectiveness of the humanitarian system is at a fairly nascent stage with a number of small initiatives having been undertaken with partners in the areas of WASH and vehicle procurement. This is broadly in line with expectations planned in the logframe, with the review of the existing system not expected to be completed until March 2014.
1.5 Key challenges / For the next phase of the project the key challenge will be the continual implementation of the project uplift into existing workloads. This will entail the careful management of resources to ensure capability is in place to respond to multiple emergencies, particularly given that the past year has not seen this tested in the context of a sudden onset emergency. / The nature of the project in attempting to bring in the use of innovative products as part of the suite of resources which the UK Government has access to will continue to be demanding. Any supplies which the UK Government may wish to use must undergo a comprehensive regime of testing and assessments, and the manufactures of these items should have a clear understanding of the standards to which relief items should comply. In particular, the first tender for items under RRF framework agreements identified that this gap in knowledge amongst manufacturers was a significant impediment to the success of their bids. / The next year of the programme will also test the assumption as to whether the international community has the appetite and will seek to drive up the quality of procurement. The success of this element of the programme is therefore contingent on the UK Government’s ability to influence its partners to instigate real change.
1.6 Annual Outcome Assessment / Outcome performance is measured against the following indicators: / The expected results of this investment will be that we can respond quickly, effectively and appropriately to humanitarian crises by drawing on equipment and materials that enable us to meet the basic shelter and emergency survival needs for affected communities across a wider range of humanitarian crises. Equipment was provided in support of DFID’s response to the Syria crisis and the distribution of emergency NFIs in support of Caribbean hurricane preparedness. The capacity to deliver an effective humanitarian response to up to 3 crises has also been maintained. The on-going review and testing of items to complement the existing stockpile of materials will provide a greater breadth in terms of the type of response that the UK Government is able to commit to. Already, this process has involved the installation of new satellite communications and digital radio equipment, and armoured vehicle modifications designed in-house. / Effective system in place that ensures all members of the international community can quickly identify and access the shelter materials and NFIs (and complex and “hard to access” specialist equipment and materials) held by individual organisations in the international humanitarian community. Performance against this outcome cannot yet be measured as the review phase to test the appetite for delivering change in the international system and recommendations for subsequent work, has not yet been completed. This corresponds with the timeline expressed in the logframe for this review phase to be completed by March 2014.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / The project is on-track against financial forecasts. A budget increase was approved following an interim review of the UK Government humanitarian stockpile in November 2012. / The increase in the budget reflects the need to enhance the range of emergency supplies held in UK stocks and increase official deployment capability. This uplift will enable the UK Government to meet the needs of 38,750 people, an increase of 21,250 over the original stockpile capability, and increase the range of non-food items that can be delivered during an emergency response. The uplift will also improve the quality of UK Government response by enabling it to provide support which meets the wider needs of disaster affected populations. The uplift also extends the ability of field teams to rapidly deploy by increasing the range of mission critical equipment at their disposal and by improving the logistical capability to move field teams and equipment at short notice. / 2.2 Key cost drivers / The key cost elements that affect the overall cost of the programme are (i) the cost of warehousing and maintaining the DFID stockpiles and (ii) the indicative cost of the additional materials that will be added to the existing stocks following the reviews of needs and new and innovative products and technologies. Both elements have been and, where a refresh is needed, will be subject to open competition that follows public procurement rules and best practice. Costs will be passed on to DFID without any additional procurement/management fees beyond those already included in the Humanitarian Emergency Operations Support Services (HEOSS) contract. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The overall rationale established in the business case for the continued maintenance of a UK Government humanitarian stockpile remains valid. This is namely that this intervention will ensure that existing UK stocks, and our access to stocks held by others, will be maintained and refreshed and increased to meet the basic shelter and emergency survival needs (excluding food) for affected communities across a wider range of humanitarian crises. This will also ensure that innovations and emerging technology in essential humanitarian equipment and materials are properly assessed and, where appropriate, brought into standard stock holdings. It will also ensure the UK Government is able to effectively support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of emergency environments, including insecure/conflict affected environments, for up to three simultaneous deployments. / Where there has been a significant revision in evidence and its impact on the project has been following the interim review conducted in November 2012. This identified a need to increase the stockholdings to provide essential life-saving support for a larger beneficiary population and provide additional bespoke stockholdings in high priority vulnerable countries. / The following expected results have therefore been incorporated into the project to reflect this: / an increase the quantity of tents held from 3,500 to 7,750 (enabling us to meet the needs of 38,750 people); / an increase in non-food items (household equipment and supplies) so that each tent (capacity five people) is a humanitarian family support unit with a package consisting of: a cook set; 10 blankets; three buckets; five sleeping mats; a solar charging system and lights; two treated bed nets; laundry and bathing soap; and, 600 toilet bags. Holdings will be kept under review so that innovations coming from the evaluation process can be fed into the family support unit; / an increase in the space in Dubai to accommodate the extra stocks; / an increase in deployment support capacity by (i) increasing the number of diesel armoured vehicles in DFID’s fleet by five (to 15), (ii) purchasing additional satellite communications equipment and (iii) purchasing an extended package of aircraft handling equipment that can be used either at Kemble or for rapid deployment overseas to enable affected airfields to offload aircraft quickly, reducing the congestion that can hamper relief operations; / an indicative amount to allow the investigation of a bespoke containerised emergency relief aid/module to be sourced and transported to an ‘at risk’ post. This would contain a range emergency items suitable for a particular location, e.g. Nepal; / And, costs (£2,500) for larger DFID signage at the Kemble Emergency Operations Response Centre. / 3.2 Where an evaluation is planned what progress has been made? / N/A

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The overall risk level of medium remains unchanged. / The current intervention follows a series of previous projects (Stockpile projects 1 through 5) which maintained the high quality stocks of UK Government NFIs and support equipment deployed into a range of humanitarian emergency operations using the CHASE OT supply management and logistics team. / The scale of ambition to drive up the quality of procurement in the overall humanitarian system necessitates a larger risk appetite. Success is contingent on the UK’s ability to influence other partners who may, possibly, not be committed to delivering real change. Anecdotal evidence suggests that there is scope and appetite for a well-designed intervention, with the risk needing to be mitigated by thorough investigation as part of the review process. For each of the low value reviews detailed Terms of Reference will be agreed in advance between CHASE HRG and CHASE OT. The recommendations of each review will be agreed by CHASE HRG before further resources are committed.
Risk of funds not being used as intended / The overall risk for this is very low. Crown Agents are one of DFID’s three approved procurement agents and have in place stringent anti-corruption and anti-bribery policies and practices. The provision of the services being supplied under the Humanitarian Emergency Operations Support Services contract, which will provide the bulk of the resources needed to implement the Humanitarian Emergency Procurement Project were subject to competition. As part of the management arrangement for that contract a Partnership Board has been established to oversee the on-going management of the CHASE OT contract including the work of the supply chain management/logistics team. This Partnership Board meet on a quarterly basis to discuss progress, performance and any other issues arising. The Board comprises the Stabilisation Unit (SU) and CHASE Senior Responsible Owners (SROs) for the contract, the Crown Agents Commercial Director and Crown Agent’s Project Director. / Additionally, the Crown Agents Project Director convenes a leadership meeting with the CHASE SRO and SU SRO separately, on a monthly basis. The Crown Agents Commercial Director is available to attend these meetings on a regular basis as required. Weekly meeting of the Humanitarian Response Group and CHASE-OT leadership groups discuss and resolve any day to day issues. / 4.4 Climate and Environment Risk / Climate and environmental impacts are considered in both preparation and responses. Humanitarian specialists are aware of the standards applicable in humanitarian response, including environmental impact. Procurement and logistics specialists manage the selection and storage of emergency humanitarian items in accordance with appropriate environmental guidelines to ensure that any items despatched are suitable for local climate conditions.

5. Value for Money
5.1 Performance on VfM measures / Value for money for this programme is assessed against the following two criteria: (i) Output Performance (ii) Flexibility Performance. / Output performance: time from date of request to delivery at first point of distribution. / Flexibility performance: number of different types of items held in stock or subject to a manufacturer framework agreement (precise indicator to be developed following the reviews of the NFI and deployment stockpiles and the establishment of the agreements for rapid access to goods, equipment and materials that we will not hold directly). / Additional quantitative indicators have been developed to measure the quality of the Central Register and Global Mapping of Emergency Stockpiles System as part of the review process and in the design of any programme to follow up agreed recommendations. / Additional outcomes metrics are also employed, which indicates the benefits received by the recipient (capturing appropriateness, quality and timeliness): Recipient satisfaction, measured by a survey 6 months after the intervention, is also an integral component of any evaluation process for individual humanitarian responses. / 5.2 Commercial Improvement and Value for Money / Commercial improvement for this intervention is driven through the establishment – following open competition as per public procurement rules and best practice – of relationships with suppliers. This is mediated by CHASE OT and through open procurement for materials and supplies that are held in the stockpile. Suppliers identified through the Rapid Response Facility process are also invited to participate in these procurement processes to formalise any agreements that need to extend beyond the EU Procurement Directive thresholds. / 5.3 Role of project partners / Crown Agents are the sole implementing partner. They have arrangements with suppliers to ensure adequate supplies of non-food NFIs are maintained in storage, and maintain relations with suppliers to ensure delivery of NFIs in humanitarian responses. / 5.4 Does the project still represent Value for Money : Y / The benefit of maintaining a stockpile of relief items is still relevant with the overriding necessity that the UK Government has to have the continued ability to make a large direct, bilateral, in-kind contribution if necessary. The project will also improve the quality and appropriateness of response due to greater breadth and depth in the stockpile, and drive higher standards and practice in humanitarian procurement stockpiling and coordination in the international system. The costs of the procurement work needed to increase the stockpile and provide on-going management support is met from within current resources within the CHASE OT logistics team. This support is covered by the CHASE OT contract, won by Crown Agents through a competitive tender process. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The project has maintained the UK Government’s ability to provide essential humanitarian relief through the provision of life-saving equipment and NFIs. The extent of this support will continue to grow as the financial uplift in the project is fully implemented through both the increase in the volume of supplies available, and the greater range of goods which will be accessible. For the next phase of this project there will continue to be an extensive process of testing and refinement of commodities. There will also be a greater emphasis on understanding the variations across partners in terms of their own standards and capabilities, and how the UK Government can improve any shortcomings identified in these areas.

8. Review Process
DFID desk review based on reporting against the project logframe.