Type of Review: Project Completion Review
Title: International Partnership for Microbicides (IPM) 2008-13

Date started: December 2008	Date review undertaken: 8th August 2013

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
To prevent HIV infection by accelerating the development and availability of safe and effective microbicides for use by women in developing countries, DFID will provide £20 million over five financial years 2008/9 – 2012/13 to fund the programme

What were the expected results?
The development of safe, acceptable and effective microbicides that can be initiated by women to protect against HIV infection, and will have a major public health and financial impact worldwide. / The expected results of IPM’s work are: / a) Expedite the development of female-initiated HIV prevention products; / b) Increased African capacity to plan and conduct clinical trials in high HIV incidence countries; / c) Effective advocacy to promote and sustain favourable public policy and long term predictable funding for microbicide development. / The results from previous trials have helped this programme to focus on moving forward. The International Partnership for Microbicides (IPM) has gone through a difficult re-prioritising process along with other efforts to reduce costs, in order to ensure the ability to implement its dapivirine ring licensure programme. The global financial situation has presented significant challenges to IPM and others working in microbicide development.

What was the context in which UK support was provided?
There are research gaps in essential technologies (such as microbicides, vaccines and medicines) to treat neglected diseases that affect the world’s poorest populations. For many of these diseases there are no current products or those that exist are either too expensive, difficult to access, difficult to use, no longer produced, have safety or tolerability concerns, or are ineffective. / HIV and AIDS is a major cause of mortality and morbidity throughout the world and particularly in Sub-Saharan Africa. HIV and AIDS has a higher impact on women, yet women often lack effective tools that they can use to prevent infection. / The aim of the programme is to reduce deaths and illness from HIV and AIDS, through preventing HIV infection by accelerating the development and availability of safe and effective microbicides for use by women in developing countries. / This funding fits within the DFID research strategy to address the need for new or improved products to combat diseases of the poor. It is also consistent with the DFID approach to HIV and AIDS, with its focus on treatment and prevention. Development of new prevention technologies for HIV will help to achieve the Millennium Development Goals (MDGs), notably to combat diseases such as AIDS, reduce poverty and child mortality, improve maternal health and promote gender equality and empower women.

## Section A: Detailed Output Scoring

Output 1: Accelerate microbicide product development
Output 1: final score and performance description: A+: Output moderately exceeded expectation
Final results: / Over the funding period IPM have worked to speed up the development of safe and effective female-initiated microbicide products containing antiretroviral (ARV) drugs. They have conducted 1 product acceptability study and 13 epidemiological studies, implemented 14 clinical trials, supported the development of 15 research centres with new/strengthened capacity and trained over 350 research centre staff and enrolled over 17,000 study volunteers for their research studies. / The main achievements are: / Dapivirine ring now in Phase III safety and efficacy trials (first phase III of a ring) / Dapivirine gel Phase I/II expanded safety trials completed / Maraviroc and dapivirine-maraviroc rings Phase I safety trial completed / A novel microbicide tablet (DS003) advancing through the pipeline / In the latter part of the funding period IPM focused its work on the dapivirine ring licensure programme and partnered with other groups, such as the US National Institutes of Health (NIH), to advance a carefully limited pipeline of microbicide products. IPM began work on a multipurpose prevention technology (MPT), a vaginal ring containing dapivirine along with a contraceptive hormone, with funding from the US Agency for International Development (USAID). / From 2010 IPM has worked with the Microbicide Trials Network (MTN) on the dapivirine ring licensure programme. In April 2011 MTN designed the MTN-020 large scale effectiveness trial, as part of IPM’s licensure programme. The ‘IPM 027’ study was redesigned as a Phase III long-term safety and efficacy study. The MTN and IPM phase III studies are now both underway. If both studies show the ring to be safe and effective, IPM will seek regulatory approval and subsequent introduction of the ring in sub-Saharan Africa. / IPM is currently focusing on addressing challenges in the conduct of the safety and efficacy trial IPM 027. Since adherence is very important to interpretation of the Phase III trial data, measuring and encouraging adherence will continue to be crucially important to the ability to detect efficacy in the trial. In addition, participant and research centre fatigue will be proactively managed. Staff turnover at the research centres due to high expected workload remains a high risk. / IPM has prioritised work to increase the adherence to the dapivirine ring rather than developing dapivirine gel beyond Phase I/II clinical trials at this time. / IPM used data from safety and acceptability studies of microbicide candidates to inform the development of products and trial designs. For example data from safety, acceptability, and pharmacokinetic studies formed the basis of the decision to move the dapivirine ring into Phase III, helped inform the dapivirine ring phase III (IPM 027) protocol and facilitated subsequent regulatory approval to initiate the trial. The data also served to inform discussions with the European Medicines Agency (EMA), the US Food and Drug Administration (FDA) and other regulatory agencies about IPM’s plan for dapivirine ring licensure. / IPM built a state-of-the-art clinical trial manufacturing (CTM) facility to accelerate prototype gel and ring production. In 2011 in preparation for Phase III production scale-up, IPM transferred its dapivirine ring manufacturing process to an external vendor (QPharma AB; Sweden), which is producing the ~130,000 rings needed for both Phase III clinical trials. / IPM and CONRAD hold co-exclusive licenses to tenofovir for development as a microbicide, and until 2011 IPM supported CONRAD’s efforts to develop tenofovir gel. In 2011 IPM’s role decreased and CONRAD largely coordinated manufacturing and regulatory filings of tenofovir gel alone. / In 2008 IPM entered into a royalty-free licensing agreement with Pfizer (now ViiV Healthcare) for maraviroc, which has a different mechanism of action from dapivirine. Following completion of preclinical work, in 2011, IPM and MTN launched a Phase I trial of a maraviroc ring and a combination dapivirine-maraviroc ring, the first topical microbicide combining two ARVs. IPM is also developing the ARV DS003, a gp120-binding entry inhibitor, and discussions are on-going with respect to IPM’s potential to gain access via formal licenses to develop protease inhibitors and integrase inhibitors as microbicides / Impact Weighting (%): 40% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 2: Increase clinical trial capacity in high HIV-incidence settings
Output 2: final score and performance description: A: Output met expectation
Final results: / Fifteen (against a target of 20) new or updated research centres carried out nine clinical trials or HIV incidence studies and four of the sites are implementing the ‘IPM 027’ dapivirine ring Phase III trial. A number of the sites are also participating in clinical trials sponsored by other organisations. / During the programme IPM reviewed the requirements for clinical trial sites and reduced the target number from 20 to 15 with the agreement of the funding agencies. / IPM helped build the capacity of 15 research centres in six countries in sub-Saharan Africa. IPM worked with the research centres to improve infrastructure and train staff on good clinical practice, good clinical laboratory practice, social-behavioural science, standard operating procedures, participant recruitment techniques and communications strategies. / Comprehensive clinical trial training was augmented with the installation of rigorous financial management procedures, information technology systems and other critical management-related processes. Preparation for the large-scale Phase III trial, which has almost 6 times the number of participants of the largest previous Phase I/II study, required intensive training and the support of IPM staff and contractors. / Impact Weighting (%): 40% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 3: Develop policy and advocacy programmes to support timely access to microbicides in selected countries
Output 3: final score and performance description: A+: Output moderately exceeded expectation
Final results / IPM’s support work has been crucial in developing ongoing clinical trials in Africa. They have worked with communities and local media to ensure continuing support for this type of research, sometimes in the face of disappointing results from other microbicide development activities. / IPM has used a variety of strategies including briefings and workshops in Kenya, Malawi, South Africa and Zambia to strengthen scientific literacy around HIV prevention in general and microbicide research and development specifically. They have provided strategic input on microbicides to government officials, local regulatory and ethics committees and briefed policymakers/ parliamentarians (in countries hosting clinical trials and donor countries). African regulatory officials participated in IPM’s annual clinical affairs meetings (2008 - 2011. / IPM has helped to build communication and advocacy capacity among civil society organisations in Kenya, Malawi and Zimbabwe in support of their advocacy activities. / IPM has become involved in a number of global activities to ensure that commitments to health and development targets include commitments to the support the development of microbicides. For example:
Towards zero Infections – the UK Government’s position paper on HIV/AIDS mentions the promise of ARV-based technologies. IPM contributed to the civil society recommendations invited by DFID for the paper. / South Africa's National Strategic Plan (NSP) on HIV, STIs and TB for 2012–2016 supports microbicides. IPM worked with several organisations working in the microbicide field (such as, CAPRISA and the Global Campaign for Microbicides) to influence this policy.
IPM has worked with partners to ensure that commercial manufacturing capacity and distribution strategies are in place for any successful microbicide product launch. This has included analyses of potential demand in high-incidence countries and discussions with possible local manufacturing partners. / IPM has interacted with regulatory agencies in developing countries, and also with stringent regulatory authorities, such as the European Medicines Agency (EMA) and the US Food and Drug Administration (FDA), to define the regulatory pathways for microbicides. IPM have participated in an access working group, co-convened annual Microbicide Access Forums with WHO and the US Agency for International Development, and worked with access to medicines experts to develop and refine an access strategy for microbicides, once available. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? No / 1.2 Final Output score and description: A+: Outputs moderately exceeded expectation
Direct feedback from beneficiaries / IPM has worked closely with local populations to raise awareness about HIV and HIV prevention and the need for prevention methods that can be initiated by women. The acceptability studies have explored the views and preferences of women using ring-, gel- and film-based microbicide products. / At the clinical trial sites IPM have strengthened local staff capacity and upgraded existing facilities – providing services, and infrastructure, equipping clinical labs and training health service personnel in good clinical practice and ethics, patient treatment and evaluation, accurate diagnosis and follow-up. / IPM established a community advisory group (CAG) at each research centre. The CAGs review draft versions of protocols, informed consent documents, and translations of data collection instruments and provide feedback on issues that may be of concern for, or confusing to, trial participants and community members. / IPM’s document, “Microbicide Research: Hope for the Future, Benefits for Today,” (2010) describes trial participant feedback and is available on the IPM website. The document indicates that participation in trials improves awareness of HIV and AIDS, empowers women to seek health care and negotiate safer sex, and reduces stigma. / IPM’s emphasis on ensuring strong stakeholder involvement has resulted in continued commitment to microbicide development, at a time when research progress has been patchy. Without this work the risk of developing country governments withdrawing support for microbicide trials would have been far higher.
1.4 Overall Outcome score and description: A+: Outcomes moderately exceeded expectation / 1.5 Impact and Sustainability / To ensure sustainability, IPM has worked with existing organisations, to build and enhance capacity at 15 clinical trial sites. Each site has developed strong links with their communities and these links have been strengthened over the funding period. There is strong community engagement, raising awareness of HIV and methods for HIV prevention, through all of IPM’s research at each of the trial sites. / A number of the trial sites have worked on HIV prevention research with other organisations and have attracted funding from other sources, to support ongoing development and research. / IPM’s partnerships with a range of different organisations, including researchers, policy and advocacy groups and communities, has meant that support for the development of women-controlled methods for HIV prevention has been strengthened. / With the move to include technologies that provide contraceptive as well as HIV prevention possibilities IPM has been making links between family planning and HIV prevention communities which will be important for the future.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / 2.2 Key cost drivers / The main challenge during the period of the grant was the global financial downturn and decreased donor funding. IPM responded by scaling down the organisation to align operations and staff profile to funding realities without significantly compromising programme goals. A second major challenge was the redesign of the Phase III trial, partly as a result of the involvement of the MTN and also to accommodate the reduced funding levels. / IPM increased its operational efficiencies in order to respond to constrained funding through expanded partnership and collaboration and by implementing a new operating model. / Product development is a very costly process, especially in the latter stages of development. As new products progress through the pipeline they enter into successively more costly phases of development. IPM has partnered with the MTN to leverage resources to ensure that there are funds available to test the dapivirine ring to regulatory standards. They have also received funds from USAID to begin the development of dual purpose (microbicide and contraceptive) technologies. / IPM has strong working relationships and operates in partnership with both public and private sector entities. IPM has negotiated non‐exclusive, royalty‐free licenses from five pharmaceutical companies for antiretroviral drugs (ARVs) for development as microbicides for use in developing countries; developed new drug delivery formulations and analytical testing methods; developed and advanced a monthly dapivirine vaginal ring into Phase III testing; recognised the potential advantages of combination ARVs and advanced a dapivirine‐maraviroc ring into clinical testing; initiated a contraceptive‐microbicide ring development programme; successfully manufactured and supplied GMP vaginal gels and rings for Phase I/II clinical trials, and scaled up ring manufacturing infrastructure and technology to support Phase III requirements. / 2.3 Was the project completed within the expected timescale: Yes / It was accepted from the outset that the process of microbicide development is lengthy and will be on-going for many years. DFID funding for five years has made an important contribution to the process, but no products in IPM’s portfolio have reached the point of licensure. The original projections for IPM 027 trial assumed enrolment would be completed by Q1 2013 and last participant visits completed by Q1 2015. Currently, the timeline is delayed by 6 – 9 months, due to the intentional slowing of enrolment in the four South African sites to address missed visits over the holiday season, monitoring backlog and focus on adherence. Delays in recruitment are also the result of fewer research centres participating in the trial. IPM 027 was originally to be conducted in 5 – 7 research centres; however, two centres did not participate, due to the absence of local regulatory approval and laboratory qualification.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / There have been important findings from recent studies of antiretroviral (ARV)-based prevention methods — including treatment as prevention (TasP), pre-exposure prophylaxis (PrEP) and microbicides. In 2010 the CAPRISA 004 trial showed that a vaginal gel containing 1% tenofovir was able to lower the HIV infection rate by 39%. More recently, clinical trials such as HPTN 052, iPrEX, Partners PrEP, and TDF2, have shown that oral ARVs can reduce the risk of HIV infection in certain populations. These studies have provided the “proof-of-concept” that pre-exposure prophylaxis with an ARV in healthy adults, whether delivered systemically or locally, can prevent HIV infection, when used correctly and consistently. The picture is mixed however, as trials conducted by other research groups have not shown any significant impact on HIV prevention. / 3.2 Set out what plans are in place for an evaluation. / Plans for an evaluation will be considered during the next funding period.

4. Risk
4.1 Risk Rating (overall project risk): High / Did the Risk Rating change over the life of the project? No / The development of new products, including microbicides, is high risk with the potential for new products to fail at any stage in the development process. IPM has demonstrated strong results and a balanced approach to portfolio management and strategic partnerships have minimised potential risks. The product development partnership (PDP) model represents a mechanism to mitigate the risk associated with the development of new technologies where there is little likelihood of pharmaceutical companies recovering development costs. In addition the portfolio approach ensures that there are a number of different candidates at different stages in the development pipeline, mitigating against the risk of individual failures. / In common with other PDPs, IPM and its partners have robust mechanisms in place to manage their portfolios, drawing on global experts to identify milestones and stop/go decision points. / The main risk associated with new product development is that the products developed are not rapidly approved for use or are not deployed to those people who need them due to supply chain constraints. IPM has systems in place, including an access strategy, to work with the relevant authorities to minimise these risks. / IPM’s ability to achieve its full business plan objectives, largely within budget and original timelines, attests to the effectiveness of the various risk mitigation strategies adopted. / 4.2 Risk funds not used for purposes intended / This is low – DFID provided core funds to IPM to support the development of microbicides for HIV prevention. This means that, if one area was unsuccessful, the development of a particular product was halted. IPM was then able to reassign funds for more promising projects, ensuring that work continued. Each year their accounts are externally audited and approved by the Board. / IPM has a strong governance structure, including anti-fraud, anti-corruption and whistle-blower policies, and there is little risk of corruption. / 4.3 Climate and Environment Impact / IPM and its partners, like all pharmaceutical research and development, have to comply with a wide range of international regulations including Good Manufacturing Practice (GMP) which includes regulations about environmental impact reduction. Compliance with these regulations, which include safe laboratory and disposal practices, are essential to maintain registration status. No significant negative environmental impacts of the programme have been seen to date, during annual monitoring. / In disease-endemic countries, use of microbicides developed through the programme will eventually raise issues of packaging and distribution. The programme has worked to ensure that packaging and distribution will be designed to minimise environmental impact and ensure appropriate operations practices in logistics chains. IPM is exploring whether the current ring formulation would be effective for a longer duration; continuous use of one ring for 60 or 90 days will result in fewer rings used overall and less environmental impact. IPM is also assessing the use of a degradable polymer in developing a next-generation dapivirine ring, and has in its pipeline other microbicide formulations with potential for even lower environmental impact, such as vaginal films and tablets that do not require an applicator. / Drug volatility and stability under conventional distribution practices are carefully considered and formulations are developed to minimise the need for refrigeration or other storage requirements and continuously evaluated to support extension of product shelf life. / In the longer term the environmental impact of the programme should in fact be positive through the reduction of the need for HIV drugs, tests and consumable products.

5. Value for Money
5.1 Performance on VfM measures / Funding microbicide development through a PDP such as the IPM provides value for money through: / The use of a portfolio approach which allows funding to be redistributed if individual projects are stopped, when they do not meet their milestones; / The leveraging of contributions (resources, expertise, funding, access to products and other in-kind resources) from the private sector; / Support for the continued development of the most promising microbicide candidates / Facilitating opportunities to explore innovative partnership with private and public sector organisations to reduce costs / Strengthening medical research capacity in developing countries and benefiting clinical trial participants and their communities / The partnership with the NIH-funded MTN has leveraged resources to ensure that there are funds available to test the dapivirine ring to stringent regulatory standards. / IPM has worked hard to ensure that lessons learned from their own, and other groups, microbicide trials have been fully incorporated into the design of their clinical trials. For example the choice of participating clinical trial sites was made on the basis of incidence of HIV infection, to ensure that the required number of end points for the IPM 027 trial will be met as rapidly as possible, thus shortening the time (and associated costs) for the trial. / IPM has been through significant restructuring during the funding period. They have learned lessons about being ‘right-sized’ and how to ensure the correct skill mix in the existing staff, in particular to support programming areas. There is a balance to be struck between costs of outsourcing or having in-house staffing. IPM has moved from a model which focused on reducing the FTE number of staff, towards one that identifies the most cost-effective staffing levels for implementing the programme, whether in-house or through consultancy inputs. / 5.2 Commercial Improvement and Value for Money / Through its internal processes, identifying the most promising new microbicide candidates from different organisations across the world, IPM is able to provide a competitive environment for innovation and improved value for money. In addition, working with the pharmaceutical industry has also shown improved value for money, by leveraging in resources from other organisations, for microbicide discovery and development. / 5.3 Role of project partners / Ensuring value for money in developing microbicides for use in low income countries where there is no viable commercial market is central to the way PDPs work. PDPs bring together partners from a range of different backgrounds, including pharmaceutical companies, other private sector organisations, academic researchers, advocacy organisations and local community groups. / DFID is one of a core group of donors supporting IPM’s work and we are involved in regular discussions both with the organisation directly and indirectly through such mechanisms as the PDP Funders Group. / IPM’s relationship with its partners has evolved over the past five years. Following the restructuring IPM has worked more effectively with partners to ensure that it can deliver on all of its objectives and has become more fully integrated within the wider HIV prevention community. / 5.4 Did the project represent Value for Money : Yes

6. Conditionality
6.1 Update on specific conditions / No specific conditions attached to this funding.

7. Conclusions
Over the funding period IPM have worked to speed up the development of safe and effective female-initiated microbicide products containing antiretroviral products (ARV). They have conducted 1 product acceptability study and 13 epidemiological studies, implemented 14 clinical trials, supported the development of 15 research centres with new/strengthened capacity and trained over 350 research centre staff and enrolled over 17,000 study volunteers for their research studies. / The main achievements are: / Dapivirine ring now in Phase III safety and efficacy trials / Dapivirine gel Phase I/II expanded safety trials completed / Maraviroc and dapivirine-maraviroc rings safety trial completed / A novel microbicide tablet (DS003) advancing through the pipeline / IPM has focused its work on the dapivirine vaginal ring licensure programme. IPM also increased its operational efficiencies in order to respond to constrained funding through expanded partnership and collaboration and by implementing a new operating model which made a smaller staff profile feasible. IPM has partnered with other groups, such as the US NIH, to advance a carefully limited pipeline. IPM began work on a multipurpose prevention technology, a vaginal ring containing dapivirine along with one or more contraceptive hormones, with funding from the US Agency for International Development.

8. Review Process
This review was conducted by members of the Human Development Research Team in DFID. / Materials used included a review meeting with IPM staff in August 2013, internal programme documents, IPM reports and email updates, IPM annual PDP Funders Report and documents produced for a meeting of IPM donors in July 2012. / A competition for PDP funding, for the period 2013 to 2018, was launched in February 2012 and was ongoing during the last year of the funding period. There was minimal recent contact with IPM to minimise the potential risk of conflict of interest. / Communication has been restricted to reviewing progress of the existing performance framework, risk issues and general financial and programme management at a number of meetings with IPM staff over the year, including side-meetings at international gatherings such as the Product Development Forum in Seattle. We have also informally discussed IPM’s performance with other key funders including the Bill and Melinda Gates Foundation, USAID and IrishAid.