Business Case

Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA)

Phase 2 (2013-2017)

 August 2013

Contents

Acronyms and Abbreviations

AIDS	Acquired Immunodeficiency Syndrome
ALB	Albendazole
API	Active Pharmaceutical Ingredient
BMGF	Bill and Melinda Gates Foundation
CBA	Cost Benefit Analysis
CIFF	Children’s Investment Fund Foundation
CNTD	Centre for Neglected Tropical Diseases, Liverpool School of Tropical Medicine
DALY	Disability-adjusted Life Year
DFID	Department for International Development
DRC	Democratic Republic of Congo
ERP	Expert Review Panel
EU	European Union
GBD	Global Burden of Disease
GIS	Geographic information System
HIV	Human Immunodeficiency Virus
ICOSA	Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa
IEC	Information, Education and Communication
IHME	Institute of Health Metrics and Evaluation
LATH	Liverpool Associates in Tropical Health
LF	Lymphatic Filariasis
MANGO	Management Accounts for NGOs
M&E	Monitoring and Evaluation
MDA	Mass Drug Administration
MoH	Ministry of Health
MDGs	Millennium Development Goals
NGO	Non-Governmental Organisation
NTDs	Neglected Tropical Diseases
PCT	Preventive Chemotherapy
PZQ	Praziquantel
RTI	RTI International
SAC	School-age children
SCH	Schistosomiasis
SCI	Schistosomiasis Control Initiative
SNNPR	Southern Nations, Nationalities and People's Region
SP	Service Provider
STH	Soil-transmitted Helminths
TB	Tuberculosis
UNDP	United Nations Development Programme
USAID	United States Agency for International Development
WHA	World Health Assembly
WHO	World Health Organization

Intervention Summary

Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA): Phase 2
What support will the UK provide?

DFID will provide an additional £25 million to support an expanded phase of an existing programme: Integrated Control of Schistosomiasis and Intestinal Helminths in Sub-Saharan Africa (ICOSA). Phase 1 of this programme began in 2010 with a £25m budget and will end in October 2016. Investment in Phase 2 will therefore bring the total budget to £50m for the period 2010-2017.

The combined programme provides technical support, equipment and other services to expand treatment in eight existing Phase 1 countries (Niger, Uganda, Tanzania, Zambia, Mozambique, Malawi, Cote d’Ivoire and Liberia) and two new countries: Democratic Republic of Congo (DRC) and Ethiopia.

The programme will provide 200 million treatments in total (over its two phases), directly benefitting at least 60 million individuals. Treatment consists of administering two drugs – praziquantel (PZQ) for schistosomiasis (SCH) and albendazole (ALB) for soil-transmitted helminths (worms), mainly to school-age children who are most at risk from the diseases. These drugs will mainly be provided through Mass Drug Administration (MDA) in schools. During Mass Drug Administration the entire at-risk population is treated, rather than diagnosing and treating individual patients. Additional measures will be supported to reach out of school children and other high risk groups. PZQ supplies in Phase 2 are expected to be 65% donated by Merck Serono, whereas they were to be entirely purchased from programme funds under Phase 1. ALB supplies are wholly donated by GlaxoSmithKline (GSK).

The programme’s treatment strategy of using MDA follows guidelines developed by the World Health Organization (WHO) for preventive chemotherapy, which is considered the most cost-effective strategy for reducing the impact of Schistosomiasis and Soil Transmitted helminths (STH) in the medium term. Together with other measures, in particular water and sanitation interventions, this approach aims for the eventual elimination of Schistosomiasis, a goal that WHO member states agreed on through a World Health Assembly resolution in 2012: to eliminate Schistosomiasis as a public health problem by 2025. The programme will make a major contribution to this goal, in particular by addressing infection in the two new countries, DRC and Ethiopia.

The programme will be managed by the Schistosomiasis Control Initiative (SCI) at Imperial College in London, supported by the Centre for Neglected Tropical Diseases (CNTD) at the Liverpool School of Tropical Medicine, with the procurement of drugs and equipment managed by Crown Agents. Governments in partner countries are responsible for implementation, with this programme providing technical support to programme design, monitoring and evaluation.

DFID will provide funds to the Schistosomiasis Control Initiative (SCI) for technical support operations and to Crown Agents for procurement. SCI in turn will provide funds to CNTD and to governments for the services they provide for treatment campaigns.

Why is UK support required?

UK support is needed as part of a renewed international effort, supported by donors, foundations, NGOs and the private sector, to control and, where possible eliminate, ten neglected tropical diseases (NTDs) by 2020[1]. This renewed effort recognises that progress to date has been too slow, although the tools are there to reduce dramatically the health and economic impact of these diseases, which affect more than a billion people, mainly the poorest. That is why DFID announced at the high profile London Declaration on NTDs in January 2012 an increase in its commitments to fight NTDs from £50 million to £245 million. Part of this increase was committed for ICOSA Phase 2.
[1] Guinea worm disease, lymphatic filariasis, leprosy, sleeping sickness (human African trypanosomiasis) trachoma, schistosomiasis, soil-transmitted helminthes, Chagas disease, visceral leishmaniasis and river blindness (onchocerciasis).

The two diseases addressed by the programme – schistosomiasis (bilharzia) and soil-transmitted helminths (parasitic worms) account for a significant proportion of the overall burden of NTDs. It is estimated that around 240 million people require treatment for schistosomiasis every year, at least 90% of them in Africa. In 2011, about 28 million were treated. Although this was a sharp increase on 12 million in 2006, there is clearly a large unmet need for treatment which the proposed programme will address in a significant way by providing a total of 200m treatments.

More than 1.5 billion people are infected worldwide with soil-transmitted helminth (worm) infections. Over 270 million preschool-age children and over 600 million school-age children live in areas of high parasite transmission, and need treatment and preventive interventions. In 2009, over 300 million children were dewormed in endemic countries, corresponding to only 35% of the children at risk globally.

Schistosomiasis is a disease resulting from infection with parasitic worms, acquired when parasite larvae penetrate through the skin of people exposed to infested freshwater. The economic and health effects of Schistosomiasis are very considerable. Children, and adults whose occupations make them vulnerable (e.g. fishermen) are the highest risk groups. Because of their recent exposure to infection, and consequently the early stage of their chronic lesions, it is children who benefit most from treatment interventions, which prevent the chronic morbidity that otherwise blights later years. In children, Schistosomiasis can cause anaemia, stunting and a reduced ability to learn, although the effects are usually reversible with treatment. Chronic Schistosomiasis may affect people’s ability to work and can result in death.

Soil-transmitted helminth infections are caused by parasitic worms (helminths) that are transmitted to people through contaminated soil. They are transmitted by eggs that are passed in the faeces of infected people. Adult worms live in the intestine where they produce thousands of eggs each day. In areas that lack adequate sanitation, these eggs contaminate the soil. The worms result in malnutrition that may have a significant impact on growth and physical development.

While there has been significant progress in both Schistosomiasis and Soil Transmitted Helminths control, this has been far short of targets set in 2001 by the WHO. DFID is the largest donor for Schistosomiasis control. USAID is the next largest bilateral donor (and overall the largest donor for Neglected Tropical Disease delivery programmes). The pharmaceutical company Merck Serono recently announced plans to scale up their donations of PZQ, the drug used to treat Schistosomiasis. However additional funding, along with technical support to countries, is needed in order to ensure effective use of the donation. Governments are ready to scale up treatments and DFID’s contractor has the capacity and skills to help those countries.

The expanded programme will include new entry into DRC and Ethiopia, two of the three heavily populated and high prevalence countries in Africa still to be addressed. The other country is Nigeria, which is being funded separately by DFID and USAID. The combined population of these three countries is over 200 million, and in order to reach the WHO goals of elimination all three need urgent intervention and support.

What are the expected results?

DFID’s enhanced support will enable at least 60 million children and adults to benefit directly in terms of their health and productivity. Phase 2 would add 124 million treatments to the 76 million supported by Phase 1 funding, giving a total of 200 million treatments over the total period of DFID support.

Table A: Treatments delivered by the programme (Phases 1 and 2)

Treatments delivered / (millions)	(Already delivered)	(Forecast)	(Forecast)	(Forecast)	(Forecast)	(Forecast)
	2011/12	2012/13	2013/14	2014/15	2015/16	2016/17	Total
Phase 1	14.25	14.41	15.32	16.32	15.81		76.11
Phase 2			13.30	26.49	32.50	51.71	124.00
Total	14.25	14.41	28.62	42.81	48.31	51.71	200.11

The much larger number of treatments made available for the same amount of funding in Phase 2 is mainly a result of the enhanced donation programme for PZQ announced by Merck Serono, as well as economies of scale. Phase 2 budget will include funding for purchase of the non-donated PZQ. The combination of donation and purchase will maintain incentives for producers to remain in the market, enhancing supply security and supplier performance.

The main programme activities (mapping to determine the geographic spread of the disease, training, logistic support, drugs and equipment procured) are all necessary intermediate steps to ensure treatment uptake, which is the main programme outcome. Treatment for schistosomiasis at regular intervals benefits the individuals treated and also, once adequate coverage is achieved, reduces the transmissibility of the disease so that new cases are reduced. Thus the principal result (impact) will be a reduction in morbidity and mortality, the latter principally as a result of treatment for Schistosomiasis . In particular treating children has a longer term impact - reducing their susceptibility to re-infection in later years - and reduces their chance of dying prematurely from Schistosomiasis -related conditions.

The programme aims to reduce the mean intensity of infection (number of worms in a person) in the areas chosen for treatment (where infection is heaviest) by between 65% and 90%. It will aim to achieve the WHO-mandated goal of at least 75% of school aged children treated regularly in the areas treated and, in some cases, the whole country.

For Phase 2, the cost per Disability Adjusted Life Year (DALY) averted (the usual measure of the cost-effectiveness of interventions) is estimated at about £67 in economic terms and about £35 in financial terms (reflecting the value of the donated medicines). These figures are in line with, or better, than other health care interventions financed by DFID and well below well below the WHO cost-effectiveness bar of a cost/DALY at or below gross national income per capita.

DFID’s input of £50 million will combine with and help secure an estimated contribution of £10 million by participating governments and drug donations valued at £21.7 million. The average cost to DFID per treatment will be 26 pence, 60% of the total. The programme will monitor the direct financial costs of treatment with the objective of achieving further reductions from baseline costs in at least eight programme countries. Overall this represents excellent value for money.

The results achieved will be measured by the monitoring and evaluation undertaken by the programme and by independent evaluation.

Table B: Summary of benefits (for the whole programme including both DFID and non-DFID funds)

Type of benefits
Health benefits during the programme	At least 75% of school aged children in target areas received treatment for schistosomiasis regularly. / 200 million treatments delivered to school aged children and high risk adults. 124m of these treatments will be in Phase 2. / Mean intensity of infection reduced by between 65%-90% (depending on starting endemicity), thereby reducing morbidity due to infection and preventing future morbidity. / Estimated 1.2 million DALYs averted within 6 years. 720,000 DALYs averted in Phase 2
Longer term benefits	25% reduction of infection in untreated children due to reduction in transmission. / Capacity for implementing integrated NTD control increased in endemic countries leading to longer term sustainability of programmes. / Robust evidence of appropriate strategies to move towards elimination of SCH contributing to the global goal to eliminate SCH as a public health problem by 2025.
Economic benefits estimated from the programme	Cost per DALY averted estimated at £67 in economic terms and £35 in financial terms.[2] / One treatment is estimated to result in additional future earnings with a net present value of $30.
[2] Financial costs include those costs funded by DFID, channelled through SCI and Crown Agents to cover programme delivery and management costs and procured goods and drugs respectively. For economic costs, the estimated government contribution of 18% is added as well as the cost of donated drugs

Strategic Case

A. Context and need for a DFID intervention

Schistosomiasis (SCH – also known as bilharzia) is a debilitating disease caused by parasitic trematode worms (blood flukes) of the genus Schistosoma. SCH transmission has been documented in 77 countries. However those at most risk of infection are in 52 countries, of which 41 are in Africa.

The latest estimates by WHO (March 2013)[3] indicate that in 2011 at least 240 million people required treatment for SCH, at least 90% of them in Africa. The number of people reported to have been treated (in the same year) was 28.1 million (or 11.7% of those needing treatment). WHO also reports that in sub-Saharan Africa, more than 200,000 deaths per year are due to SCH.[4],[5]
[3] WHO Schistosomiasis Fact sheet N°115, updated March 2013 www.who.int/mediacentre/factsheets/fs115/en/
[4] Ibid.
[5] The Global Burden of Disease 2004 Update put the figure at 41,000 global deaths. Other studies have suggested that up to 280,000 may die in Africa annually from conditions caused by SCH (Van der Werf MJ et al. Quantification of clinical morbidity associated with schistosome infection in sub-Saharan Africa. Acta tropica. 2003 May;86 (2-3):125-39.)

Although the number of people treated has sharply increased since 2006 (when those treated were 12 million)[6], there is still a large unmet need for treatment which the proposed programme will address in a significant way.
[6] Schistosomiasis progress report 2001 – 2011 and strategic plan 2012 – 2020. WHO, Geneva, 2013. (Henceforth referred to as ‘SCH progress report and strategic plan 2012-2020, WHO 2013.’

Soil-transmitted helminth (STH) infections are among the most common infections worldwide and affect the poorest and most deprived communities. WHO estimates that more than 1.5 billion people are infected.[7] STH infections are widely distributed in tropical and subtropical areas, with the greatest numbers occurring in sub-Saharan Africa, and South and East Asia. Over 270 million preschool-age children and over 600 million school-age children live in areas where these parasites are intensively transmitted, and are in need of treatment and preventive interventions.[8] WHO estimates that in 2004 global deaths from STH were 6,000. Although the evidence is debated (see below), other studies have suggested that STH may be responsible for 150,000 deaths annually.[9] In 2009, over 300 million preschool and school-age children were dewormed in endemic countries, corresponding to only 35% of the children at risk globally.[10]
[7] Soil transmitted healminth infections. WHO Fact Sheet No 336 June 2012
[8] Ibid.
[9] Deworming children brings huge health and development gains in low-income countries. Disease Control Priorities Project Factsheet, August 2008.
[10] WHO Fact Sheet No 336. June 2012

Nature of the diseases

Schistosomiasis

SCH is a chronic illness that damages internal organs. In children it can cause anaemia, stunting and a reduced ability to learn, although the effects are usually reversible with treatment.[11] The impact of the disease can be severely debilitating and long term, mainly affecting the poor and exacerbating poverty. Children with chronic infection are at risk of anaemia and malnutrition, which has an impact on school attendance, undermines their learning, and can have lifelong nutritional and health impacts. Studies have found a correlation between SCH and childhood stunting.[12] Urogenital SCH in girls and women is believed to increase their risk of HIV, as lesions in the vulva, vagina, cervix and uterus caused by the disease, become entry points for HIV.[13] In Zimbabwe, women with urogenital SCH were found to be three times more at risk of having HIV.[14] Several studies have indicated that individuals infected with helminths and SCH may be less likely to fight off malaria infections.[15] Mortality as a result of infection is primarily due to serious complications of the liver and bladder. Liver enlargement and hypertension of the abdominal blood vessels leads to the development of oesophageal varices (swelling of the blood vessels that become like blood blisters and can burst) which can rupture. Death is due to haematemesis (vomiting blood) secondary to liver fibrosis. There is also a form of bladder cancer caused by urogenital SCH infection which has accounted for many deaths, particularly in Egypt.
[11] WHO Fact Sheet No 115, March 2013.
[12] Assis et. al (2004) quoted in Watts, S., “The social determinants of schistosomiasis”, Report of the Scientific Working Group on Schistosomiasis, 2005, WHO.
[13] Stoever K., Molyneux D., Hotez P., Fenwick A. HIV/AIDS, schistosomiasis, and girls. Lancet 2009; 373: 2025-2029.
[14] Kjetland EF, Ndhlovu PD, Gomo E, et al. Association between genital schistosomiasis and HIV in rural Zimbabwean women. AIDS 2006; 20: 594.
[15] Nacher, M. et al. Intestinal Helminth Infections are Associated with Increased Incidence of Plasmodium Falciparum Malaria in Thailand. Journal of Parasitology 88.1 (2002): 55-8.

People become infected when larval forms of the parasite (released by freshwater snails) penetrate their skin during contact with infested water. In the body, the larvae develop into adults. Adult worms live in the blood vessels where the females release eggs. Some of the eggs are passed out of the body in the faeces or urine to continue the parasite life-cycle. Others become trapped in body tissues, causing an immune reaction and progressive damage to organs.

The rates and intensity of infection typically increase from an early age, peaking around the age of 8-15 years, and then decrease as children move into adulthood. In a community the disease tends to be unevenly distributed with a small number of individuals carrying most of the parasites, and the majority of the population having light infections. Studies of infective behaviour show that children play a particularly important part. Children have high intensities of infection, and tend to urinate and defecate in water sources during play, spreading the disease. A study in northern Senegal found that two-thirds of school children rarely or never used a latrine though they were available to 90% of the village population and some 24% of the children studied defecated in or near water.[16]
[16] Sow S. et al. Low awareness of intestinal schistosomiasis in northern Senegal after 7 years of health education as part of intense control and research activities” Tropical Medicine & International Health, 2003 (8):744-749.

Figure 1: Life cycle of schistosomiasis

The diagnosis of schistosomiasis is difficult, and significantly costlier than treatment. Definitive individual diagnosis involves collecting stool and urine samples, followed by concentration. Having prepared a concentrated stool sample, it is examined on a slide under a microscope, but the examination is not as sensitive as would be ideal: finding the eggs, particularly in stool samples is difficult. Because such a small sample is examined, false negatives are common. Similarly, the currently available antibody tests are less than ideal, and are recommended only for mapping purposes and not for individual diagnosis. Antigen tests have been recently developed but still need to be verified on a large scale, and they are a more expensive diagnostic technique.

Soil-transmitted Helminths

STH are caused by parasitic worms (helminths) that are transmitted to people through contaminated soil. The main species of STH that infect people are the roundworm (Ascaris lumbricoides), the whipworm (Trichuris trichiura) and the hookworms (Necator americanus and Ancylostoma duodenale). They are transmitted by eggs that are passed in the faeces of infected people. Adult worms live in the intestine where they produce thousands of eggs each day. In areas that lack adequate sanitation, these eggs contaminate the soil.

Figure 2: Life cycle of the whipworm

Morbidity is related to the number of worms (i.e. intensity of infection). People with light infections usually have no symptoms, while heavier infections can cause a range of symptoms including intestinal manifestations (diarrhoea, abdominal pain), general malaise and weakness. Hookworms cause chronic intestinal blood loss that can result in anaemia. Soil-transmitted helminths can cause malnutrition of the people they infect in multiple ways. The worms feed on host tissues, including blood, which leads to a loss of iron and protein. The worms cause malabsorption of nutrients. According to WHO the nutritional impairment caused by soil-transmitted helminths may have a significant impact on growth and physical development, although the evidence is debated (see below).[17]
[17] WHO Fact Sheet No 336 June 2012

Control strategies

Schistosomiasis

Prevention and control of SCH has been based on combinations of preventive treatment, snail control, improved sanitation and health promotion.

WHO draws a distinction between:
- the control of morbidity (achieving less than 5% prevalence of heavy-intensity infections in all SCH endemic countries);
- elimination of SCH ‘as a public health problem’ (achieving less than 1% prevalence of heavy infections in all endemic countries); and
- elimination (interruption of transmission of the disease).

In the long term the only way to eliminate SCH is to control and eliminate transmission by reducing soil and water contamination. This has been achieved in some countries over a long period of time (e.g. Japan) but inevitably such improvements can only come with the improvement of water and sanitation standards and other measures. Elimination of transmission may also require significant changes in farming practices or living conditions that include proximity to animals that can act as hosts. Japan is one of the few countries to have completely eradicated SCH, along with some smaller islands in the Caribbean. It declared itself free of SCH in 1976 having used a variety of methods focussed on controlling the vector. Apart from improved sanitation and water arrangements, this also included switching from buffaloes (a reservoir for infection) to horses in rice farming. China, Egypt and other middle income countries have achieved substantial reductions in infections, through both chemotherapy and other interventions, but elimination of the disease completely is difficult to achieve without sustained environmental interventions, and endemic pockets remain.

That is why in the medium term WHO and its member states have focused on preventive chemotherapy (PCT) as the most immediate and cost-effective means of reducing the public health burden of the disease. As endorsed by the World Health Assembly (WHA) in 2001, WHO’s strategy for SCH control focuses on reducing disease through periodic, targeted treatment with praziquantel (PZQ). This involves regular treatment of all people in at-risk groups.

The WHA set a target of regular administration of chemotherapy to at least 75% of all school age children at risk (of both SCH and STH) by 2010.[18] In May 2012 the WHA adopted a resolution which called for the elimination of SCH and, inter alia, urged Member States “to provide support to countries endemic for schistosomiasis to expand control programmes”. It notes that the goal of achieving 75% treatment coverage of at risk school age children had not been achieved by 2010.[19]
[18] Schistosomiasis and soil-transmitted helminth infections. WHA54.19. 22 May 2001
[19] Elimination of schistosomiasis. WHA65.57. May 2012

PZQ is a safe, effective and inexpensive drug. There are two sources of PZQ in this programme; a donation from Merck Serono through WHO which will increase annually, and PZQ procured through Crown Agents. The cost of purchasing PZQ from the manufacturer averages about 15 pence per treatment (exclusive of delivery cost) where not donated. Frequency of treatment is based on the level of prevalence of infection in an area (which signals the level of risk in a community). Treatment is administered once a year in areas of high prevalence, and once every two years (sometimes less frequently[20]) in moderate or low prevalence areas. Treatment is repeated until prevalence is reduced below a defined threshold (see Annex 1 for details on the treatment strategy).
[20] Twice during the period of primary schooling age, in areas of low risk.

Because of the low cost of treatment, it is cheaper to treat whole populations at risk rather than diagnosing individual infection levels and then only treating those infected. School children typically have the highest intensity of infection and the benefits of treatment will be higher than in long-infected adults with irreversible damage to their organs. Moreover, schools provide an appropriate infrastructure for the cost-effective delivery of drug treatment, with skilled staff able to administer drugs safely when supported by appropriate, but limited, training. In Egypt the prevalence of SCH in rural areas has been reduced from about 50% to less than 10% now, in particular through the mass administration of locally produced PZQ beginning in 1988. PZQ has also been used successfully over the past 20 years to control SCH in Brazil, Cambodia, China, Morocco and Saudi Arabia.

Chemotherapy provides a degree of protection to the individual in later life in reducing the impact of subsequent reinfection, as well as the immediate impact on morbidity. Sustained chemotherapy in an infected community can also reduce transmission significantly in the medium term, but will generally require other measures to avoid recurrence in the long term.

Soil-transmitted Helminths

There has been a debate about the value of treating STH through chemotherapy (deworming) using the drug albendazole (ALB), which is the strategy recommended by WHO and endorsed by the WHA. A Cochrane review of the evidence, recently updated, could not confirm that deworming treatments of children had positive effects on nutritional indicators, cognitive functioning or school performance.[21]
[21] Taylor-Robinson DC et al Deworming drugs for soil-transmitted intestinal worms in children: effects on nutritional indicators, haemoglobin and school performance. The Cochrane Library July 2012

In the context of this programme doubts about the effectiveness of deworming are of secondary importance because the Cochrane authors agree that the “evidence for the benefit of treating populations with schistosomiasis is fairly clear..., as the infection has a very substantive effect on health.” Two previous Cochrane reviews, in 2008[22] and 2009[23] confirmed the effectiveness of PZQ. As ALB is co-administered with PZQ in the proposed programme, and the drug is provided as a donation by the manufacturer, the additional cost of deworming is very small. The benefits would therefore only need to be correspondingly small to justify the cost. In addition, the Cochrane review does note that where deworming treatment is provided after screening there is some evidence of a positive effect. There is also very strong evidence that STH treatment is highly effective in curing major types of worm infection,[24] although reinfection is common in the absence of further treatment.[25] It should be noted, as detailed in the appraisal case, that studies suggest that the great majority of health and other benefits in co-treatment for SCH and STH derive from the impact on the former. In the light of the above, it is considered that co-treating for STH is justified where STH is shown to be prevalent along with SCH. This is consistent with WHO’s recommendation and is the practice in countries affected by STH.
[22] Danso-Appiah A et al. Drugs for treating urinary schistosomiasis. Cochrane Database of Systematic Reviews, issue 3. 2008.
[23] Sacanato,H and Atallah,A. Cochrane Database of Systematic Reviews Issue3. 2009
[24] Utzinger J, Keiser J. Schistosomiasis and soil-transmitted helminthiasis: common drugs for treatment and control. Expert Opin Pharmacother. 2004 Feb;5(2):263-85.
[25] Jia TW, Melville S, Utzinger J, King CH, Zhou XN. Soil-transmitted helminth reinfection after drug treatment: a systematic review and meta-analysis. PLoS Negl Trop Dis. 2012;6(5):e1621.

Mass Drug Administration (MDA)

Prior to MDA there is essential awareness raising in the community especially when MDA has not previously been carried out. It can include mass media (often local FM radio) and local community awareness initiatives or can be mainly based around schools. These are organised on the advice of the national NTD department but carried out by their local counterparts. The norm is for MDA for schistosomiasis to be delivered in schools but where prevalence is over 50%, treatment is also offered to the entire community. In some countries school based MDA is carried out entirely by teachers, in others e.g. Malawi it is done jointly by teachers and health staff. Distribution in the community is done by community volunteers. Mapping and collecting the data for monitoring is done either by trained technician staff from the ministry or from a local academic institution. SCI provides technical assistance, training and supervision as needed at all stages.

Integration with other NTDs

Integrated approaches to NTDs are being promoted where the geography of the different diseases coincides to ensure that the limited resources available are used most effectively. Studies indicate that integrated delivery of six drugs to treat a variety of NTDs could be achieved for as little as $0.40-0.79 per person per year in sub-Saharan Africa.[26] Cost savings on integrated programmes have been estimated at 26-47% compared to non-integrated programmes.[27] The benefits of integration were highlighted during the high profile London Declaration on NTDs meeting, held on 30 January 2012.
[26] Hotez P et al 2007. Control of Neglected Tropical Diseases. New England J. of Medicine 357:1018-1027.
[27] Brady MA, Hooper PJ, Ottesen EA. 2006. Projected benefits from integrating NTD programs in sub-Saharan Africa. Trends Parasitol 22: 285-291

Where possible, administration of drugs is combined. Currently, most countries with three or more NTDs provide a MDA twice a year. For example in January they may distribute ivermectin (mectizan) and albendazole which would tackle LF, onchocerciasis and STH. Then in July they may distribute PZQ with albendazole which would treat schistosomiasis and STH infections. Some years ago, using a WHO approved protocol, controlled trials were carried out which demonstrated the safety of giving Ivermectin, PZQ and Albendazole together. Two states in Nigeria and the two islands of Zanzibar were selected for these trials. As a result of these trials the WHO now recommend that these three drugs can be given together safely - but only to people who have had treatment previously. This is on the grounds that if a child has not previously had treatment they are likely to have a heavy worm load and the shock of the worms dying maybe great and this could result in severe stomach pain. However, given that in any round of treatment there will be many people who will be receiving treatment for the first time because previous participation rates may be less than 85% and new cohorts of children will need treatment, most countries have elected for practical reasons not to implement the three drug regime, but to continue with two treatments a year. The programme will work with WHO to see where it is possible to find situations where it would be safe and expedient to give a single treatment of the three drugs.

In practice integration may be challenging for a number of reasons.[28] These include the different geographic distribution of the diseases and that the main focus of schistosomiasis treatment is school aged children with the entire community only treated in high prevalence areas/high risk groups e.g. fishermen. However, even when drug delivery is not combined there will still be potential for cost savings on common programme elements, for example the training of health personnel, social mobilisation, mapping and M&E.
[28] Kabatereine NB et al. 2010. How to (or not to) integrate vertical programmes for the control of major neglected tropical diseases in sub-Saharan Africa. Plos Neglected Tropical Diseases 4:6 e755

Mass Drug Administration (MDA) is carried out as a vertical campaign but once prevalence falls and MDA can be discontinued it will be important that surveillance and management of cases is integrated within the health system.

Integration with water, sanitation and hygiene activities

SCH and STH are strongly related to unsanitary excreta disposal and the lack of nearby sources of safe water. Schistosomiasis occurs by lakes and slow moving rivers. Provision of safe water and sanitation will be needed for the elimination of schistosomiasis and STH in Africa; however it will take time for these services to be rolled out especially in rural Africa where schistosomiasis is so prevalent. In the meanwhile we can prevent people getting ill from schistosomiasis through MDA with PZQ which is the WHO recommended strategy for reducing the mortality and morbidity from schistosomiasis.

While PCT is the most important component in schistosomiasis control, other operational components, such as health education for behavioural change, provision of safe water and sanitation, environmental management and snail control are necessary for a comprehensive control programme. WHO recommends them in areas approaching elimination as a public health problem, and considers them essential when the aim is interrupting transmission. Provision of safe water and sanitation were essential to the significant reductions in transmission achieved by countries such as China, Egypt and Morocco, after intensification of SCH control efforts.

Similarly, WHO states that while PCT is a cost-effective and easy-to-implement short-to-medium term strategy for eliminating morbidity associated with soil-transmitted helminths, improved access to sanitation is a long-term strategy towards the same goal.[29]
[29] Soil-transmitted helminthiases: eliminating soil-transmitted helminthiases as a public health problem in children: progress report 2001-2010 and strategic plan 2011-2020. WHO, 2012.

The Bill and Melinda Gates Foundation hosted a meeting of organisations working on NTD control, child health, and WASH sectors in 2012 to discuss opportunities and barriers for collaboration. The group agreed on a common vision, namely "Disease-free communities that have adequate and equitable access to water and sanitation, and that practice good hygiene." Four key areas of collaboration were identified, including (i) advocacy, policy, and communication; (ii) capacity building and training; (iii) mapping, data collection, and monitoring; and (iv) research. The programme will work with countries to take forward these recommendations.

Therefore it remains important to advocate for investment in water and sanitation services and infrastructure in SCH/STH endemic areas. In addition, in planning PCT interventions for SCH and STH control, there is a need to take into account and wherever possible influence where water and sanitation projects are implemented or planned.

Examples of activities the programme should undertake are:

- Including governmental and non-governmental representatives of the water and sanitation sector in programme stakeholder meetings;
- Working with other agencies to improve water and sanitation in areas in which the programme is active;
- Monitoring progress towards integrating with water and sanitation programmes in a more structured way.

The Gates Foundation have run a special ‘Grand Challenge’ to encourage development of better toilets; SCI have approached the Foundation with a view to testing these new toilet designs in some ICOSA countries. The role of environmental interventions in achieving elimination is still under discussion. The Bill and Melinda Gates Foundation will be supporting operational research on elimination of schistosomiasis in Barundi and Rwanda. These countries only have S Mansoni and have been doing MDA for a number of years so have achieved low prevalence. This work may include environmental interventions and the use of snail control methods to develop the optimal approach to achieve elimination.

In areas of high transmission, for example residents on the banks of the lakes in Africa, special attention will be given to integration of MDA with improving access to safe water and improved sanitation. However, certain occupations e.g. fishermen will need to continue to enter the lakes and children are likely to continue to play in the lakes and so will remain at risk. Irrigation schemes can also be high transmission areas and in these areas efforts will be made to integrate water and sanitation, but also where appropriate to investigate whether snail control would be appropriate. For 20 years, snail control has been discarded as too expensive for only a small effect. However as we get closer to elimination of transmission, snail control may be the important extra intervention needed to complete the journey.

In conclusion, detailed planning needs to be done by countries to facilitate integration with other sectors, with the health system, and with other NTDs where appropriate. In practice this will require planning district by district, and disease by disease (because of the different distribution and intensity of NTDs and local variations). ICOSA needs to support ministries to achieve this. (See also Appraisal Case, section B, on the impact on climate change and the environment).

Research on NTDs

DFID is planning a new research programme of up to £15.1m on neglected tropical diseases implementation. This research could consider questions such as how can we ensure we reach the right people at the right time and how best to integrate efforts on different NTDs. It is intended that they work closely with the NTD implementation programmes that we support to ensure that the research is relevant and can directly and rapidly influence policy and practice. In addition DFID also supports work on the development of new drugs for some NTDs. The Bill and Melinda Gates Foundation also support research on implementation of NTDs; an example of this is the work on trying to achieve elimination of schistosomiasis mansoni in Rwanda and Burundi as described above.

Need for DFID Intervention

In 2008 DFID committed £50 million over five years to tackle NTDs. Of this, £25 million was allocated to the control of schistosomiasis and soil-transmitted helminths, and channelled through the ICOSA programme. The decision to provide £25m for support schistosomiasis was based on a report DFID commissioned on NTDs that identified schistosomiasis as the most neglected of the NTDs that was addressed by mass drug administration. This was largely because the other diseases benefitted from drug donations that covered all the treatment needs unlike schistosomiasis where the drug donation only covered a small fraction of the needs.

Since then the national and international focus on NTDs has strengthened. As a result in January 2012 DFID joined with the World Bank, WHO, USAID, the Bill and Melinda Gates Foundation (BMGF), pharmaceutical companies and NGOs in committing to “a new, coordinated push to accelerate progress toward eliminating or controlling 10 neglected tropical diseases (NTDs) by 2020” (London Declaration on Neglected Tropical Diseases). At the same time, Merck Serono committed to increase its PZQ donation from its current 25 million to 250 million tablets per year by 2016.[30] DFID also announced an increase of its commitment to the control and elimination of NTDs over 2011-2015 from £50 million to £245 million, noting that it “is a tragedy that the lives of millions of the world’s poorest people are still being destroyed by these ancient and avoidable tropical diseases when we have the means to tackle them.”[31] In 2011 when ministers decided to increase our commitment to NTDs, we updated the report on NTDs and consulted widely with partners. Ministers decided that this increased funding for NTDs would include increased funding for the four NTDs we were already supporting (lymphatic filariasis, schistosomiasis, guinea worm and onchocerciasis) as well as funding for two additional diseases (trachoma and visceral leishmaniasis) and two new country NTD programmes (Nigeria and S Sudan). In deciding to allocate a further £25m for schistosomiasis we considered the unmet need for treatment of these NTDs as well as SCI’s capacity to deliver on a tight time scale and the need to maintain the PZQ market.
[30] See http://www.unitingtocombatntds.org
[31] Britain to protect more than 140 million in global effort to rid the world of neglected tropical diseases. Press Release. 21 January 2011.

DFID is now the largest donor for SCH control. USAID is the next largest bilateral donor (and overall the largest donor for NTD delivery programmes). USAID’s integrated approach since 2006 has been effective in distributing 222 million NTD treatments in 12 countries.[32]. Merck Serono and GlaxoSmithKline donate PZQ and ALB for mass drug administration and WHO works closely with them to coordinate the supply of drug donations to where they are needed. In support of these initiatives, WHO has intensified its strategic and coordinating work, including producing a Road Map for actions required to meet targets in 2015 and 2020 and drafting strategic plans for each of the NTDs for the period up to 2020, including for SCH.[33]
[32] Linehan M et al.2011. Integrated implementation of programs targeting neglected tropical diseases through preventive chemotherapy: proving the feasibility at national scale. Am J Trop Med Hyg 84(1):5-14.
[33] SCH progress report strategic plan 2012-2020. WHO, 2013.

While there has been significant progress in both SCH and STH control, this has been far short of the targets set in 2001 by WHO as efforts to control SCH only really expanded very recently. We are submitting the business case for Phase 2 at this time because funds are needed for Ethiopia and DRC. In addition it is now over 18 months since ministers made the commitment to increase our support for schistosomiasis at the high profile meeting for the London Declaration on NTDs.

Schistosomiasis: between 2006 and 2010 (when endemic countries began systematically reporting data on SCH treatment to WHO) there has been a signiﬁcant scaling-up in preventive chemotherapy for SCH, and the number of people treated almost tripled in the same period (Fig. 3).[34] However, this number still represented only 11.7% of the people requiring preventive chemotherapy for SCH.[35] Numbers treated in 2011 fell due to delays in the procurement of PZQ. Numbers in 2012 have increased sharply though we are still awaiting final data from WHO.
[34] Ibid.
[35] Ibid.

Figure 3: Progress on schistosomiasis: reported number of people treated, and treatment coverage globally, 2006-2011[36]
[36] Data from SCH progress report strategic plan 2012-2020 (WHO, 2013) and from PCT databank (for 2011 data).

Number of people treated (millions)
Year
Coverage (%)
15
17
20
26
28
24
Note: The numbers above the bars refer to the number of countries which have reported treatment that year.

Soil-transmitted helminths: similarly, coverage with preventive chemotherapy for STH in pre-school age and school-age children remains well below the WHO target at only 30.7% (Fig. 4), although there has been progress since 2003 when coverage was only 7.6%.[37]
[37] Soil-transmitted helminthiases: eliminating soil-transmitted helminthiases as a public health problem in children: progress report 2001-2010 and strategic plan 2011-2020. WHO, 2012.

Figure 4: Soil-transmitted helminths: number of school-age children treated and coverage*, 2009-2011 [38]
[38] Source: CNTD.

SAC: school-age children; GPELF: Global Programme to Eliminate Lymphatic Filariasis
*The number of children treated may include those who were not considered in need of PCT. However, estimated coverage uses the number of children requiring PCT as the denominator.

The commitment to the eventual eradication of schistosomiasis at the WHA in 2012 is testament to the political will in countries and the need for intensified effort to meet the targets the international community has set. The target population for annual treatment, currently estimated by WHO at 240 million, will gradually be reduced as treatment scales up. DFID’s new commitment will reach over 20% of the target population in Africa by the last year of the programme.

The programme will make a significant contribution to the achievement of MDG 6 (combating HIV/AIDS, malaria, and other diseases). The programme can also make a contribution to MDG 1 (poverty reduction), MDG 2 (education), MDGs 4 and 5 (child and maternal health), and MDG 8 (in cooperation with pharmaceutical companies, provide access to affordable essential drugs in developing countries).

The Programme

The Schistosomiasis Control Initiative (SCI) at Imperial College in London was selected through competition as Project Manager for the Phase 1 ICOSA programme. The focus of the programme was on the provision of technical support, equipment and other services in order to expand treatment through MDA to school-age children and high risk adults in eight African countries: Niger, Uganda, Tanzania, Zambia, Mozambique, Malawi, Cote d’Ivoire and Liberia. Crown Agents were selected as the best qualified organisation from DFID’s procurement panel to purchase drugs and equipment.

Phase 2 is an extension of that programme, approved by DFID in 2010. It is proposed that the programme expands to two new countries: DRC and Ethiopia. They are among the three heavily populated and high prevalence countries in Africa still to be addressed and which have only recently establish national NTD control programmes. The other country is Nigeria, which is being funded separately by DFID and USAID in collaboration. The combined population of these three countries is over 200 million, and in order to reach the WHO goals of elimination, all three need urgent intervention and support.

Democratic Republic of Congo (DRC). There is a clear need for intervention in DRC with WHO estimating that 17 million people require preventive chemotherapy for SCH. DRC is the 3rd most endemic country for SCH in sub-Saharan Africa (WHO estimates).

DRC has limited resources to allocate to NTD control and reduction of the associated morbidity. There is a level of government commitment, recently demonstrated by a National NTD strategic plan finalised in 2012 with the assistance of WHO. A number of existing NTD programmes are currently being rolled out, and a strong stakeholder group has been established, offering scope for integration with other NTD programmes.

There will be some governance challenges – DRC is ranked 51st out of 52 African countries on the Ibrahim Governance Index for African countries. The extension of ICOSA to DRC would aim to work with stakeholders in particular with CBM, an NGO established in and with experience working on onchocerciasis in DRC, and with the Liverpool Centre for Neglected Tropical Diseases (CNTD) which has already started work on Lymphatic Filariasis (LF) in DRC . The programme would complete a phased SCH mapping exercise and to develop a treatment strategy aimed at control of morbidity, targeting primarily school-age children and aiming for scale up towards national coverage. The Ministry of Health in Kinshasa have indicated their commitment and held a stakeholders meeting in January 2013 at which SCI and CNTD were represented.

Mapping is the first step needed. With CNTD support, some mapping has taken place and indicated that PCT is required because of the high prevalence. From early discussions with the government and other stakeholders, SCI believes that the conditions exist to make a meaningful impact in this country, in spite of the challenges posed by conflict and poor governance.

Ethiopia. Ethiopia has a population of over 84 million and a heavy burden of NTDs. WHO estimates that over 21 million people require annual treatment for SCH (the second largest requirement in Africa, after Nigeria). As recently as 2004, the Minister of Health in Ethiopia stated their priority was to tackle malaria and HIV and declined assistance to treat NTDs. However, there has been a recent change in prioritisation and attitude by the Ethiopian government, and there is now a high level of commitment to NTDs by the Federal Ministry of Health (MoH). The MoH has developed a five-year NTD master plan in conjunction with WHO AFRO, and in 2011 received a donation of PZQ (3.5 million tablets; enough to deliver 1.4 million treatments) from WHO. SCI has reached an agreement with the MoH to train staff and to fund delivery of these treatments as a pilot for the country. The 3.5 million tablets will be delivered with SCI assistance. Ethiopia has a decentralised political system. The health regions are increasingly getting involved in NTD control, but to date have little experience of controlling NTDs, and have approached SCI for assistance with mapping and with training of teachers and health officials.

During 2013 SCI, using funds raised from non-DFID sources, has started working with the Ethiopian MoH and the Ethiopian Health and Nutrition Research Institute (EHNRI) to undertake a scaled up mapping exercise across the country to determine the extent of the SCH distribution and subsequently the need for treatment. Meanwhile, in addition to assisting with the distribution of PZQ to treat schistosomiasis, SCI is providing financial and technical assistance to treat soil-transmitted helminths (STH). This will utilise a donation of 6.8 million mebendazole tablets from Children Without Worms (CWW). These activities are being agreed and documented in Memoranda of Understanding between SCI-Imperial College and the Federal Ministry of Health, EHNRI, and the regions. The importance of this pilot assistance is to establish SCI’s credentials with the Ethiopian government, gain experience of working in Ethiopia and to ensure the donated drugs are effectively used and do not expire. By supporting mapping during 2013, we will have a more accurate understanding of the number of people who will need treatment.

A number of NTD programmes are currently being established and rolled out in Ethiopia.
1. Mapping of LF distribution is being supported by CNTD Liverpool, through a separate grant from DFID;
2. Trachoma mapping funded by DFID through Sightsavers, is being carried out by the Carter Center and Fred Hollows Foundation.

Other donors are becoming engaged in NTD control in Ethiopia. The Children’s Investment Fund Foundation (CIFF) and USAID have both also expressed an interest in funding some NTD activities, with CIFF focusing on school children and USAID on a wide range of NTDs.[39] The inclusion of Ethiopia into the expanded ICOSA programme will allow the completion of mapping surveys for schistosomiasis in all areas in the country. It will also support the regional health bureaux to implement treatment strategies aimed at the control of morbidity, targeting at-risk populations for SCH and STH. By working with other potential donors (CIFF and USAID) and stakeholders, SCI would dovetail its approach to reach out to populations not covered by other programmes, aiming for scale-up towards national coverage of integrated control of NTDs.
[39] CIFF have stated they continue to be interested in supporting the Ethiopian Government’s implementation of deworming for children.

SCI calculates that if the estimate of 21 million people requiring treatment is confirmed, over 12 million school-aged children and 4 million adolescents will need to receive at least one treatment over the next four years using PZQ (donated by Merck Serono) and albendazole/mebendazole donated by GSK/CWW. A further 5 million adults will also need treatment against these infections. The inclusion of Ethiopia into the expanded ICOSA programme would allow the more rapid scale-up and more extensive reach of NTD control in the country.

The programme’s contribution

The combined ICOSA programme (Phases 1 and 2) will allow for the delivery of 200 million treatments to over 60 million children and adults in need of treatment, up to 2017. Reducing the morbidity and mortality associated with SCH and STH, apart from health benefits, is likely to contribute to poverty reduction through improving productiveness at work and school attendance.

Table 1: Treatments delivered by ICOSA (Phases 1 and 2)

Treatments delivered / (millions)	(Already delivered)	(Forecast)	(Forecast)	(Forecast)	(Forecast)	(Forecast)
	2011/12	2012/13	2013/14	2014/15	2015/16	2016/17	Total
Phase 1	14.25	14.41	15.32	16.32	15.81		76.11
Phase 2			13.30	26.49	32.50	51.71	124.00
Total	14.25	14.41	28.62	42.81	48.31	51.71	200.11

Of these treatments it is estimated that the drugs for over 80 million will be supplied by Merck Serono as a donation.

Beneficiaries. The programme will focus on school-age children, most of whom can be reached through school-based mass drug administration (MDA). But the programme will also undertake actions to reach children not in school, who may be particularly disadvantaged, and other high risk groups among adults such as those whose occupations bring them into contact with contaminated water (e.g. fishermen and farmers).

Reaching out-of-school children will be critical in terms of achieving public health and equity benefits, especially as they have been shown to have higher rates of infection.[40] A community-based approach, as well as school-based MDA, is therefore the appropriate response.[41] The extent of treatment out of school will be monitored with an indicator for this in the logframe.
[40] Husein MH. et al., 1996, “Who misses out with school-based health programmes? a study of schistosomiasis control in Egypt”, Transactions of the Royal Society of Tropical Medicine and Hygiene, 90(4):362-365.
[41] http://gnntdc.sabin.org/files/press_releases/Community-directed_vs_School-based_treatment_Tanz.pdf

Sustainability. Sustainability of schistosomiasis control has several dimensions, affecting the ability for eventual donor exit. Financial sustainability of the programme is one aspect, which is a function of government ability to pay as well as the size of the disease burden. The appraisal case considers in depth various choices the programme will take to facilitate the shift to sustainability. These include the increasing donation of PZQ by Merck Serono with analysis on how much PZQ we should continue to purchase to ensure that the market remains robust. The country selection also affects sustainability; we have included countries with a high disease burden that are just starting out on MDA but in some countries that have had several rounds of MDA there are prospects that treatment frequency could reduce and over time even stop in some areas. Technical capacity of the government’s NTD programme and health systems infrastructure is another key factor in sustainability, as is a stable supply of praziquantel, an essential input into schistosomiasis control. This programme will build national capacity and help ensure a stable supply of PZQ. In addition to capacity building in delivery of MDA, there is capacity building in a range of areas including in biostatics and data analysis and laboratory testing. There is also financial management training for the Heads of the NTD departments. As the programme including mapping, delivery and monitoring is done by national staff, this will facilitate sustainability.
B. Impact and Outcome that we expect to achieve

The programme impact will be the contribution to achievement of the health-related MDGs, and particularly MDG 6 (on HIV, malaria and other diseases) through the control and treatment of SCH and STH in ten African countries.

Impact will be measured by:
Reduction in intensity of infection, which can be considered a proxy for SCH-attributable morbidity (which is much less easily and affordably measured). This is because (as for most helminth infections) the number of worms affecting an individual, and the damage they cause, are directly linked.[42]
[42] SCH progress report and strategic plan 2012-2020. WHO, 2013.

The programme outcome will be to contribute to the global strategic plan for SCH (2012-2020)[43] by the provision of around 200 million treatments up to 2016/2017. The 2017 target for Phase 1 countries is 76.1 million treatments, and for Phase 2 countries 124 million treatments. Treatment coverage in school-age children (the highest risk group) will also be an outcome indicator; although strictly speaking this is a performance indicator, if individuals receive PZQ, they experience a reduction in morbidity. Therefore, according to WHO, it can be used as a proxy outcome indicator.[44]
[43] The goals of the Global Strategic Plan are: i) to control morbidity due to SCH by 2020; ii) to eliminate SCH as a public health problem by 2025; and iii) to interrupt transmission of SCH in endemic countries in all world regions (except Africa) and in a selected number of Africa countries.
[44] Ibid.

Table 2 summarises the benefits of the programme, both during its lifetime, and in the longer term.

Table 2. Summary of benefits (for the whole programme including both DFID and non-DFID funds)

Type of benefits
Health benefits during the programme	At least 75% of school aged children in target areas received treatment for schistosomiasis. / 200 million treatments delivered to school aged children and high risk adults. / Mean intensity of infection reduced by between 65%-90% (depending on starting endemicity), thereby reducing existing morbidity due to infection and preventing future morbidity. / Estimated 1.2 million DALYs averted within 6 years
Longer term benefits	25% reduction of infection in untreated children due to reduction in transmission. / Capacity for implementing integrated NTD control increased in endemic countries leading to longer term sustainability of programmes. / Robust evidence of appropriate strategies to move towards elimination of SCH contributing to the global goal to eliminate SCH as a public health problem by 2025.
Economic benefits estimated from the programme	Cost per DALY averted estimated at £67 in economic terms and £35 in financial terms.[45] / One treatment is estimated to result in additional future earnings with a net present value of $30.
[45] Reflecting the value of the donated drugs through Merck Serono.

The main benefits of PZQ treatment include the control of existing morbidity (e.g. reduced anaemia, reduced pain), prevention or reduction of the risk of developing new lesions; reduced mortality, and improved height, especially among children.[46] The full observed impact of preventive chemotherapy with PZQ among persons affected by SCH is shown in Annex 2.
[46] SCH progress report and strategic plan 2012-2020. WHO, 2013.

As well as improving the health of those directly treated, treatment can lower the rate of transmission of the disease in the population (particularly in areas with high coverage rates for MDA) as it reduces contamination of the environment with parasite eggs by infected people.

In addition to the health benefits arising from the programme, there is some evidence that treatment will increase school attendance and/or productivity at work. The economic benefits are described in the Appraisal case (section C) and can be summarised as:

- SCH and STH are associated with indirect impacts on productivity and income earning.
- Large externality effect: untreated children experienced infection reductions of about one quarter of those treated as a result of reductions in transmission.
- Reduction by one quarter in school absenteeism.
- Increased school attendance is speculated to have an impact on future earnings (one treatment is estimated to result in additional future earnings with a net present value of $30.[47]
  [47] Miguel, E and M Kremer. Worms: Identifying Impacts on Education and Health in the Presence of Treatment Externalities. Econometrica. 72.1 (2004): 159-217.

The main programme outputs (mapping, training, logistic support, drugs and equipment procured) are all necessary steps to ensure treatment uptake.

The specific inputs are detailed in the logframe along with the outputs, outcomes, measurable indicators and targets. The Management Case (section D) explains in detail how progress and results will be monitored, measured and evaluated.

Figure 5: Results chain

Inputs
  - DFID - £50 million (Phase 1 and Phase 2)
  - Company donations - £21.7 million
  - Governments - £10.1 million
Process
  - Priority areas identified through mapping of infected populations
  - Annual plans developed in all selected countries
  - Market effectively managed for procurement of drugs and equipment
  - Planning and training for PCT implementation conducted
  - National programmes refined through M&E results
Output
  - MDA campaigns implemented on expanded scale, and in more countries
  - Value for money achieved, balancing quality, cost per treatment and stable supply
Outcome
  - Treatment coverage of school age children at least 75%
  - Progress towards global SCH Strategic Plan
  - 200 million treatments delivered
Impact
  - Health improvements through reduction in intensity of SCH and STH infection by 65-90%
  - Contribution to MDGs
  - Reduced economic and health impact of SCH and STH

# Appraisal Case

Background and summary

The appraisal case evaluates the cost-effectiveness of adding a second phase to the programme with an additional investment of £25 million (Option 2 – with some suboptions within this) on the ICOSA programme as compared with the option of completing Phase 1 only spending up to £25 million - its current budget (Option 1).

As a result of Merck Serono’s decision to increase its donations of praziquantel (PZQ), the number of treatments that DFID Phase 2 funding can support is now much higher compared to ICOSA Phase 1, in which DFID funding is paying for of a much large proportion of the PZQ. Phase 1 was estimated to deliver 76 million treatments at a cost to DFID of £25 million. The additional £25 million, coming alongside the drug donation, is estimated to permit 124 million treatments, making 200 million treatments delivered in total. The additional 124 million treatments can be delivered at an estimated financial cost of £35 per DALY averted (Option 2), compared to £51 per DALY[48] averted for the first £25 million (Option 1). The estimated economic cost in each option is just under £70 per DALY averted.
[48] The disability-adjusted life year (DALY) is a measure of overall disease burden, expressed as the number of years lost due to ill-health, disability or early death. Originally developed by Harvard University for the World Bank in 1990, WHO subsequently adopted the method in 2000. The number of DALYs averted is becoming increasingly common in the field of public health and health impact assessment as a means of quantifying the health benefits of particular interventions.

A strategic decision was made by DFID to route the additional funding through the same mechanism as the current £25 million – with SCI leading the implementation work, and Crown Agents managing the procurement of PZQ. WHO provides internationally agreed guidance on the best methods to deliver control programmes as described in the 2013 “Schistosomiasis progress report 2001–2011 and strategic plan 2012–2020”.[49] Thus, the options deemed worthy of further analysis in the appraisal case were those of country selection and how the funds for Option 2 should be split between the purchase of PZQ and implementation and delivery costs.
[49] http://apps.who.int/iris/bitstream/10665/78074/1/9789241503174_eng.pdf

The appraisal case concludes that the country allocation proposed by SCI should be accepted – the existing eight countries plus two new countries (Ethiopia and DRC) which require a significant initial investment in planning and mapping, but also have large hitherto untreated populations and the potential for great health impact. An allocation of £8.4 million to Crown Agents for PZQ purchase would contribute towards maintenance of a diversified supply base, and allocating the remaining £16.6 million to SCI to distribute the purchased as well as the donated PZQ would achieve a good return on the investment of DFID funds.

Progress and lessons learnt to date

ICOSA Phase 1 is well on track to deliver 75 m treatments over 5 years. Much of the first year was dominated by establishing procedures and MOUs with countries and putting arrangements in place for the procurement of PZQ. During the first 18 months of the programme there were considerable delays in the procurement of PZQ, this was largely due to the time taken by suppliers to submit data required by the WHO Expert Review Panel which assesses the quality of medicines. These delays have been overcome; 100m tablets have been procured at a competitive price and delivered to countries. By March 2013 a total of 12 m treatments have been delivered to people. 6 of the 8 countries have completed mapping and it is due to be completed in the remaining two countries (Liberia and Cote D’Ivoire) this year. MDA has started in all countries except Zambia where it is about to start. Monitoring and evaluation protocols have been designed and are being implemented. Data including on value for money is becoming available.

Recommendations at the last review included:
-The importance of ensuring access to sufficient quality PZQ at a competitive price.
- The need to improve data management including the timely sharing of data and using data to inform the programmes.
-The need for detailed planning to facilitate integration with other NTDs including other NTD programmes supported by DFID particularly our support for lymphatic filariasis.
-Contributing to developing the evidence base on how to interrupt transmission including the on-going surveillance needs.
-The need to improve management capacity and succession planning.

The logframe of Phase 2 has been substantially revised based on the lessons learnt during Phase 1. We have included intensity of infection as a proxy for health impact as the higher the intensity the more likely the person is to develop serious health complications. There are now also indicators for reaching out of school children, validated coverage (which will be compared to converge reported by the health system) and greater attention to value for money.

Planning meetings in country provide a good opportunity for lesson sharing for country specific constraints and planning for integration. Sharing global lessons and best practice takes place through a number of different ways that include discussions at planning meetings in-country, international meetings as well as meetings with WHO who lead on the development of best practice guidance.

A. What are the feasible options that address the need set out in the Strategic case?

In order to assess whether the programme provides an acceptable return on investment, the following options were considered:

Option 1: Continue to fund the current ICOSA programme at £25 million (the “do nothing”, or counterfactual, option).
Option 2: Contribute an additional £25 million up to 2017. Under this option, several sub-options were evaluated:

- The percentage of funds which should be allocated for purchasing PZQ versus distributing donated PZQ, with implications for funds available for implementation.
- The country allocation:
1. Spending all the extra resources in the existing eight countries;
2. Spending all the extra resources in the two new countries (Ethiopia, DRC);
3. A combination of i) and ii).

Cost benefit analysis (CBA), in the form of cost per disability-adjusted life year (DALY) averted, was calculated for the two major options as well as the sub-options under the expanded programme (Option 2).

B. Assessing the strength of the evidence base for each option

An assessment of the strength of the evidence behind each of the six assumptions driving the anticipated programme outcome is provided in Figure 6 and in the text of sections B-D.

Figure 6: Theory of Change

The programme’s theory of change (Fig. 4) centres on the assumption that cost-effective delivery of preventive chemotherapy (PCT) to communities at risk for SCH and STH infection decreases morbidity and mortality associated with these infections, and in turn contributes to the MDGs and to increased economic productivity. For this change model to be effective, the following assumptions must hold true:

1. Reducing STH and SCH prevalence will contribute to realisation of the MDGs.
2. PCT is effective in reducing prevalence and intensity of infection.
3. The return from PCT will offset the costs sufficiently in terms of health and economic impact, given the following components driving the cost benefit equation:

- Secure supply of PZQ will be available for the programme’s duration at a relatively stable price;
- The countries included in the programme will offer the highest health impact return for each pound invested; and
- The programme’s implementation offers value for money, in terms of effectiveness, efficiency, economy and equity.

The evidence base for each of these assumptions is covered in the sections which follow, including an assessment of the strength of the evidence for each assumption. Sustainability is addressed through analysis of different country selection strategies as well as analysis of decisions which favour one aspect of the value for money equation at the expense of another.

Assumption 1. Evidence for MDG Contribution.
The programme can make a contribution to MDG 1 (poverty reduction), MDG 2 (education), MDG 4 (child health), MDG 5 (maternal health), MDG 6 (HIV/AIDS, malaria and other diseases) and MDG 8 (in cooperation with pharmaceutical companies, provide access to affordable essential drugs in developing countries). The evidence of this contribution is strongest in relation to reducing the prevalence and intensity of SCH and STH (other diseases under MDG 6) as explained in the next section (assumption 2). The MDG Africa Steering Group gave high priority to NTD control.[50] NTD control may also contribute to the fight against HIV and malaria. A Cochrane analysis found evidence that deworming HIV-1 positive patients potentially delays the progression of HIV to AIDS in those patients (MDG 6).[51] Another study found that infection with genital SCH may increase the sexual transmission of HIV.[52] Similarly, several studies have indicated that individuals infected with STH and SCH may be more likely to contract malaria.[53] Almost half of all deaths due to malaria among children under five are due to anaemia, and STH infections are known to exacerbate iron deficiency.[54] Anaemia is also particularly dangerous among pregnant women and may produce poor birth outcomes and low birth-weight.[55] Deworming has been increasingly recommended as essential to prenatal care, but evidence of the impact of deworming on pregnancy outcomes is scarce. The recently published DEVTA trial on deworming in India showed no significant effect on preschool mortality. An article in the Lancet discusses this study http://www.thelancet.com/journals/lancet/article/PIIS0140-6736(13)60600-5/fulltext including the importance of publishing results promptly irrespective of their findings. Evidence set out below (see section on Economic Benefits) suggests that SCH and STH control can increase school attendance, although the evidence on educational outcomes is inconclusive. The destitute and underserved in low or middle income countries are at highest risk for NTDs: experts argue that PCT can interrupt the vicious cycle of sickness and poverty, minimise lost productivity, and thereby contribute to poverty alleviation.[56] Leveraging the pharmaceutical industry’s PZQ contribution also contributes towards MDG 8 (affordable drugs available in developing countries).
[50] Achieving the Millennium Development Goals in Africa 2008 http://www.mdgafrica.org/index.html
[51] Walson, JL et al. Deworming Helminth Co-infected Individuals for Delaying HIV Disease Progression. Cochrane database of systematic reviews (Online) (3).3 (2009): CD006419.
[52] Kjetland, EF et al. Association between Genital Schistosomiasis and HIV in Rural Zimbabwean Women. AIDS 20.4 (2006): 593-600.
[53] Nacher, M. et al. Intestinal Helminth Infections are Associated with Increased Incidence of Plasmodium Falciparum Malaria in Thailand. Journal of Parasitology 88.1 (2002): 55-8. Sokhna, C. et al. Increase of Malaria Attacks among Children Presenting Concomitant Infection by Schistosoma Mansoni in Senegal. Malaria Journal 3 (2004): 43.
[54] Korenromp, EL et al. Impact of Malaria Control on Childhood Anaemia in Africa-A Quantitative Review. Tropical Medicine & International Health 9.10 (2004): 1050-65.
[55] Hotez, P.J. Empowering Women and Improving Female Reproductive Health through Control of Neglected Tropical Diseases. PLoS neglected tropical diseases 3.11 (2009):e559.
[56] Molyneux, D. Combating the “other diseases” of MDG 6: changing the paradigm to achieve equity and poverty reduction? Trans. Royal Society of Tropical Medicine and Hygiene 102 (2008): 508-519.

Overall, the evidence that NTD control is important to the achievement of the MDGs, particularly in Africa, is medium.

Assumption 2. Evidence that PCT is effective in reducing prevalence and intensity:[57] The evidence for the effectiveness of PCT in reducing SCH and STH prevalence and intensity is strong. Two studies found that the prevalence and intensity was lowest at the time of the first follow-up and increased at the time of the second follow-up, but remained significantly lower than the baseline prevalence and intensity.[58] A combined regimen of PZQ and albendazole (ALB) continued to reduce prevalence of SCH and STH in children and adults after one and two rounds of treatment.[59] A single treatment can have a temporary beneficial impact, especially in younger children. But recurrence is almost inevitable[60] which is why 2-3 years of annual treatments are recommended to make a sustained impact on those treated and in terms of reducing transmission.[61] When schoolchildren participating in MDAs in the 1980-1990s were followed up 10-18 years later, only those who received three or more treatments during childhood were fully protected from SCH-related organ damage when seen as adults.[62]
[57] Prevalence refers to the proportion of a population suffering from a disease. Intensity refers to the degree of infection in an individual or population.e. g. as measured by density of eggs in the body.
[58] Toure, S. et al. Two-Year Impact of Single Praziquantel Treatment on Infection in the National Control Programme on Schistosomiasis in Burkina Faso. WHO Bulletin. 86.10 (208): 780.Galvao, AF et al. Spatial distribution of Schistosoma Mansoni Infection before and after Chemotherapy with two Praziquantel doses in a community of Pernambuco, Brazil. Memorias do Instituto Oswaldo Cruz 105.4 (2010) 555-62.
[59] Zhang, Y et al. Parasitological Impact of 2-Year Preventive Chemotherapy on Schistosomiasis and Soil-Transmitted Helminthiasis in Uganda. BMC Medicine 5 (2007): 27.
[60] Hatz CF, et al. Evolution of Schistosoma haematobium-related pathology over 24 months after treatment with praziquantel among school children in southeastern Tanzania. Am J Trop Med Hyg. 1998;59(5):775-81; Leenstra T, et al Schistosoma japonicum reinfection after praziquantel treatment causes anemia associated with inflammation. Infect Immun. 2006;74(11):6398-407; Koukounari A et al. Schistosoma haematobium infection and morbidity before and after large-scale administration of praziquantel in Burkina Faso. J Infect Dis. 2007;196(5):659-69; Satayathum SA et al. Factors affecting infection or reinfection with Schistosoma haematobium in coastal Kenya: survival analysis during a nine-year, school-based treatment program. Am J Trop Med Hyg. 2006;75:83-92; Gurarie D et al. Modeling the effect of chronic schistosomiasis on childhood development and the potential for catch-up growth with different drug treatment strategies promoted for control of endemic schistosomiasis. Am J Trop Med Hyg. 2011;84(5):773-81.
[61] King CH, et al. Chemotherapy-based control of schistosomiasis haematobia. IV. Impact of repeated annual chemotherapy on prevalence and intensity of Schistosoma haematobium infection in an endemic area of Kenya. Am J Trop Med Hyg. 1991;45(4):498-508; Kjetland EF, et al. Prevention of gynecologic contact bleeding and genital sandy patches by childhood anti-schistosomal treatment. Am J Trop Med Hyg. 2008;79(1):79-83.
[62] Ouma JH, King CH, et al. Late benefits 10-18 years after drug therapy for infection with Schistosoma haematobium in Kwale District, Coast Province, Kenya. Am J Trop Med Hyg. 2005;73:359-64.

What is the likely impact (positive and negative) on climate change and environment for each feasible option

Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation.

Option	Climate change and environment risks and impacts, Category (A, B, C, D)	Climate change and environment opportunities, Category (A, B, C, D)
1	B	B
2	B	B

Summary: The environmental assessment for Phase 1 of ICOSA confirmed that the drugs are safe and efficacious, and deemed the environmental aspects of distribution, administration and disposal of expired batches to be minimal.

The climate and environmental assessment for Phase 2 focuses on the potential effects of climate change. Climate change is already having an effect on human health. Africa is one of the continents that is most susceptible and will be worst affected.

The 2007 report of the Intergovernmental Panel on Climate Change report predicts a change in distribution patterns of vector-borne diseases such as SCH. Recent modelling studies[63] suggest that an increase in transmission is likely in areas of sub-Saharan Africa likely to get warmer and wetter with climate change. The spread in the geographical range of snail vectors may also be to higher altitudes. In China, studies have suggested very significant increases in the numbers of people at risk from schistosomiasis as a consequence of climate change. Similar increases in populations at risk in African can be expected. Modelling studies in Africa do suggest that areas where the climate is projected to become hotter drier, snail vector may be discouraged, but these are already hot and dry and not the worst affected areas. Increasing temperatures in these areas may also discourage further irrigation development, a factor known to be important in the introduction of schistosomiasis in previously unaffected areas. Irrigation expansion in other areas of Africa would be more likely to be groundwater based, which may pose lower risks for schistosomiasis as these do not results in channels with slow-flowing water colonised with vegetation which are a preferred habitat for snail vectors.
[63] For example, Stensgaard et al (2009) Potential impacts of climate change on snail-borne disease in sub-Saharan Africa - b) experiences from sub-Saharan Africa. IOP Conf. Series: Earth and Environmental Science 6 (2009) 142003.

The potential impact on STH is less clear and specific, however it is noted that there is a growing agreement in the climate and health communities that changes in temperature and precipitation may lead to increasing risks. This will be particularly the case where sanitation is poor. Increased flooding of latrines leading to widespread distribution of faecal matter on land may lead to increasing problems with STHs. However, the impact of these factors over the length of the programme is likely to be unnoticeable and the project also provides significant environmental opportunities and some climate opportunities. The additional funds provided for Option 2 offer a significant opportunity to consider how to reduce vulnerability and improve poor people’s adaptive capacity. In addition, the programme already centres on reducing the vulnerability of the poorest and most susceptible communities, improving health and well-being. This allows the development of human assets and capital, and through which it is helping to build stronger and more resilient livelihoods.
There is also scope to use this programme to better understand the implications of climate change of schistosomiasis and STH prevalence, looking at whether there will be changes in habitats suitable for snail survival, which areas currently not affected will become vulnerable in the future and whether existing affected areas will become more vulnerable. The programme should also identify where water and sanitation or environmental interventions are required to prevent transmission and reduce prevalence.

The following actions are recommended:

ICOSA should undertake a piece of work to look at the implications of climate change. It should be forward-looking, identifying areas at risk, and covering issues such as: what are the vulnerable areas? Will there be a substantial habitat shift for snails? Will there be more areas at risk? Where will the hotspots be in the future? This piece of work can be done during the course of the programme and can be more qualitative than quantitative.

ICOSA should analyse where additional interventions (e.g. water and sanitation) are required to interrupt transmission and to make proactive links. This is already happening as part of the programme but its importance will be further emphasised.

Neither of the planned studies are likely to directly affect the long-term sustainability of the programme, but will both help inform future strategies to consolidate the gains from ICOSA
C. What are the costs and benefits of each feasible option?

Assumption 3: Programme provides an acceptable return on investment

Health benefits
The economic model considered the cost-effectiveness of Option 1 and Option 2. In the base case, it was assumed that 35% of the PZQ needs for Option 2 would be purchased, and the rest donated.[64] This would mean an approximate split of £8.4 million to Crown Agents for PZQ purchase and £16.6 million to SCI to cover implementation costs. The £50 million total will allow 200 million treatments to be delivered as compared to approximately 75 million treatments committed for delivery under the current programme of £25 million (Option 1).
[64] This balance of 35% purchased and 65% donated was determined to be the most likely, considering multiple factors, detailed under Assumption 4 below of the appraisal case.

Graph 1 shows the cost per DALY averted for Option 1 and Option 2. The lower blue diamond and red square show this in financial terms, including the cost of DFID’s investment in PZQ purchase, central overheads and management costs, and country level programming cost – in short, all the items in the budget to SCI and Crown Agents. The upper green triangle and grey cross show the results in economic terms, including all the financial costs as detailed above, plus the addition of estimated costs incurred by country governments, for example apportioning office space and staff time to SCH and STH control work as well as the estimated value of the donated PZQ and ALB. There is a larger spread between the Option 1 and 2 financial versus economic CBA because Option 2 relies heavily on PZQ donations whereas PZQ under Option 1 is entirely purchased. This donation is costed in the economic CBA, thus bringing the economic CBAs between Options 1 and 2 into relative equalisation.

Graph 1: Estimated Cost per DALY in Options 1 and 2 in financial and economic terms (£ per DALY averted)

The decline in (financial) average cost per DALY from over £50 under Option 1 to less than £35 under Option 2 demonstrates that Option 2 provides a much better financial return to DFID, mainly because advantage is taken of donated PZQ.

The breakdown of the cost components making up the £35 per DALY averted in the financial CBA of Option 2 is illustrated in Graph 2.[65]
[65] The .73 million DALYs averted is the total (average over four years) from summing up DALYs averted in all 10 countries per year. Each country’s DALY averted total is derived from taking total number of treatments delivered and dividing by 3 since most individuals will receive 3 treatments before health gains are achieved. The number of individuals treated is then multiplied by the DALY burden per case to derive the total DALYs averted. The DALY burden figure is comprised of the disability weighting per case taken from published studies (.045 mid-range), multiplied by the prevalence per country (which is a conservative indication of the percentage of people treated who will be infected and therefore stand to benefit from the treatment).

Graph 2: Break down of components under financial CBA Option 2 (in £ millions (%)
	£35 per DALY averted under Option 2 is comprised of the following costs summing to £25 million divided by the total DALYs averted under Option 2 of .73 million

The cost benefit results are considered conservative for several reasons:

- The national prevalence rates have been used to determine DALY impact, however it can be argued that this multiplier is too low because SCI targets areas within countries which have higher than average prevalence based on its mapping of disease prevalence.
- There is no credit given for interruption of transmission, an externality from PCT which has been documented but which is difficult to quantify. Countries which are able to reduce levels of high intensity infection to less than 5% are likely to experience longer term benefits in terms of a reductions in transmission rates and thus new infections and lower costs for PCT. As noted below this externality is potentially very important.
- Similarly, the benefit stream beyond 2016 is not included for the same reason – there is not yet enough information on the relationship between PCT and transmission reduction curves to allow modelling of the disease in its decline phase.
- No credit is taken for the benefits arising from treatment for STH.

The results of the analysis are highly sensitive to the DALY value assumption used in the model. The debate on the magnitude of the public health burden from SCH in terms of morbidity and disability is still on-going and therefore a range of DALY estimates found in the literature has been provided.[66] Graph 3 shows the results of the average financial and economic CBA - in £ per DALY averted – according to three different DALY per case value assumptions: low end estimate of .008, middle range .045 and a high end estimate of .098.[67]
[66] The debate on the magnitude of the public health burden of SCH in terms of morbidity and disability mainly relates to the ‘correct’ attribution of burden when symptomatology and pathology are manifest in persons affected by more than one infection or disease. Nonetheless, scientists agree on the fact that the burden of morbidity, disability and mortality (expressed in DALYs) attributable to SCH has been considerably underestimated in the past. In particular, studies have recognized the importance of counting in the co-occurring ‘subtle’ morbidity (i.e. those pathologic conditions beyond those readily attributable to SCH such as malnutrition, anaemia, chronic diarrhoea, and chronic pain that result in reduced fitness and therefore in poor school performance and reduced work productivity). There is also ongoing debate about the number of people affected by SCH; these estimates are expected to improve as mapping coverage expands.
[67] DALYs per case are derived by taking the DALY weight (a sum of morbidity and mortality attributed to a disease) and dividing this number by the estimated population affected by the disease.

Graph 3: Financial cost per DALY averted for Options 1 and 2 under a range of values for DALY burden (£ per DALY)
Cost per DALY averted Option 1: Sensitivity to 3 DALY assumptions
NB: Units on the y axis are cost in £ and units on the x axis are DALYs per case.

The .008 DALY per case weighting comes from the disability weights published in the December 2012 Global Burden of Disease (GBD).[68] By GBD’s approach, the bulk of the SCH DALYs come from schisto-associated anaemia. Leading experts continue to negotiate with GBD about the .008 weighting, arguing that it does not take account of recent mapping of disease burden and severity of morbidity. These experts have given SCH a DALY per case weighting of between .098 (under 15 years old) and .186 (over 15).[69].Estimates of the parameters influencing DALY weighting will improve as mapping work is extended, providing better information on country case counts, and the net impact of long term preventive therapy is felt. Under Option 2, DFID funding would be allocated to improve the evidence base around disease burden and PCT impact. Based on our reading of the evidence we think an estimate of between the .008 and the .098 is appropriate, thus .045, while still conservative, was selected as the most appropriate DALY weighting. See Annex 1 for a more complete discussion of issues around DALY weighting.
[68] Murray et al, Disability-adjusted life years (DALYs) for 291 diseases and injuries in 21 regions, 1990-2010: a systematic analysis for the Global Burden of Disease Study 2010. Lancet. December 2012; 380: 2197–223.
[69] Finkelstein JL, Schleinitz M, Carabin H, McGarvey ST (2008) Decision-model estimation of the age-specific disability weight for schistosomiasis japonica. PLoS Negl Trop Dis 2: e158. Also summarised in: King CH (2008) Schistosomiasis Japonica: The DALYs Recaptured. PLoS Negl Trop Dis 2(3):e203.

Conclusion: WHO’s Commission on Macroeconomics and Health considered that per capita income was a conservative valuation of the benefit of a DALY averted, and that even 3 times per capita income was a plausible valuation. Typically a cost per DALY of under $150 in a low income country would be regarded as highly cost-effective. DFID’s investment in pneumococcal vaccine through the Advance Market Commitment is estimated to cost on average $100 per DALY averted.[70] Impregnated bed nets for malaria have been studied extensively in various settings. A recent study in the DRC suggested a cost of $17 per DALY.[71] In most developing countries the standard short course treatment (DOTS) where TB is endemic is regarded as cost-effective at between $5 and $50 per DALY, although more complicated treatments for multi-drug resistant TB are much more expensive.[72]
[70] Sinha A, et al. Cost-effectiveness of pneumococcal conjugate vaccination in the prevention of child mortality:an international economic analysis. Lancet 2007 369:9559: 389-396.
[71] Sylvia I. Becker-Dreps et al. Cost-effectiveness of adding bed net distribution for malaria prevention to antenatal services in Kinshasa, DRC. Am J Trop Med Hyg, Sep 2009; 81: 496 - 502
[72] Disease Control Priorities Project 2006 Box 16.1 http://www.dcp2.org/pubs/DCP/16/Box/16.1

Assuming (very conservatively) a DALY impact based on country prevalence (rather than that in programme treatment areas) and not allowing for externalities through transmission interruption, a mid-range DALY per case value for SCH yields a cost per DALY averted of £35 per DALY averted for Option 2. Assuming a higher DALY burden of .098 offers an even lower cost per DALY averted of £16 per DALY averted. In the worst case scenario the cost per DALY averted would be substantially higher, at £200 per DALY averted.

Economic benefits
There is also evidence for economic benefits arising from SCH and STH control. A number of experts have described how poverty increases the risk of NTD infection both at an individual and community level and in turn, how NTDs can put and keep people in poverty. However, there is a lack of quantitative data on links and causality between poverty and NTDs, which has led for calls for Demographic and Health Surveys to include NTD questions so that the relationship between socioeconomic status and NTDs can be studied directly. There is similarly a dearth of evidence showing that PCT and SCH control directly influences economic productivity. However several studies point to indirect impacts on productivity and income earning associated with SCH and STH.[73]
[73] De Silva NR et al Soil-Transmitted Helminths: updating the global picture 2003. Trends in Parasitology 19: 547-51; Gilgen DD, Mascie-Taylor CG, Rosetta LL Intestinal helminth infections, anaemia and labour productivity of female tea pluckers in Bangladesh. Trop Med Int Health 2001;6(6):449-57; Kamel MI et al Impact of schistosomiasis on quality of life and productivity of workers. East Mediterr Health J. 2002 Mar-May; 8 (2-3):354-62.; Kamel MI et al. Impact of type and stage of schistosomiasis on quality of life and productivity of infected workers. J Egypt Soc Parasitol. 2001 Apr;31(1):153-67; Murray CJL, Lopez AD, Mathers CD (eds.) Global Epidemiology of Infectious Disease, 243-300, Global Burden of Disease (IV), 2004, WHO. Chapter 12. http://whqlibdoc.who.int/publications/2004/9241592303.pdf ; Blas BL, et al An attempt to study the economic loss arising from Schistosoma Japonicum infection and the benefits derived from treatment 2006 http://www.tm.mahidol.ac.th/seameo/2006_37_1/06-3557.pdf

Because children of school age are the principal target for this programme, along with other high risk groups in the adult community, the impact of control measures on children’s nutritional status, growth, school attendance and performance are of more relevance to evaluating the social and economic benefits of the programme. Kremer and Miguel published a study in 2004 which found that in-school treatment of STH and SCH results in multiple positive externalities in the short and long term, including a 20% increase in income.[74] Specific findings include:
[74] Miguel, E and M Kremer. Worms: Identifying Impacts on Education and Health in the Presence of Treatment Externalities. Econometrica. 72.1 (2004): 159-217.

- The externality effect is large – untreated children experienced infection reductions of about one quarter of the treated as a result of reductions in transmission. This effect is largely driven by a reduction in SCH infections in “untreated” schools, and a reduction in STH infections in the untreated within “treated” schools.
- The programme reduced absenteeism by one quarter but no increase in test scores could be detected – school participation increased by 0.14 years per treated pupil (including externalities – i.e. improvements in attendance in the “untreated” ).
- Based on a treatment cost of $0.49 per pupil per year, the cost per DALY averted was estimated at $5; 76% of the health benefit came from the externality benefit arising from untreated children located in communities where schoolchildren were treated and, and 99% of the benefit was attributable to SCH reduction. Thus treating SCH alone seems very cost-effective, but treating worms alone (STH) would cost $280 per DALY and is not therefore very cost-effective. This rather confirms the conclusions of the Cochrane review[75] about deworming alone.
  [75] Taylor-Robinson DC et al. Deworming drugs for soil-transmitted intestinal worms in children: effects on nutritional indicators, haemoglobin and school performance. Cochrane Database of Systematic Reviews 2012, 7.
- Apart from the direct health benefits, the analysis sought to identify other economic benefits. Based on the reductions in absenteeism quoted above, it was calculated that an additional year of school attendance could be achieved at a cost of only $3.50. A more recent study in Kenya estimated that providing free school uniforms cost between $48-83 per additional year of school attendance.[76] Miguel and Kremer therefore contend this is a very cost-effective means of boosting school attendance. More speculatively, based on calculations of the estimated rate of return on education in Kenya, and the estimated impact of extra schooling on future earnings, they calculated that one treatment (costing 49 cents) resulted in additional future earnings with a net present value of $30.
  [76] Evans D, Kremer M, Ngatia M. The impact of distributing school uniforms on children’s education in Kenya. 2008 http://siteresources.worldbank.org/EXTIMPEVA/Resources/evans_kenya_uniforms.pdf

The overall evidence base for assuming that the programme will deliver an acceptable return on investment is medium/high, if implemented as planned. The return is highly dependent on DALY weight assumptions as well as strength of evidence for the cost components evaluated under assumptions 4, 5 and 6 (and strength of evidence for assumption 4 has been graded as medium).

Assumption 4. Secure supply of PZQ at a relatively stable price
In order to achieve the benefits from PCT, there must be access to the drug PZQ in sufficient and predictable quantities and at reasonably stable prices. The functioning of the donor funded market is of prime importance to the sustainability of the PZQ supply, as apart from a small private veterinary market, PZQ is only used for treating SCH and is largely funded through donors.

The PZQ price has risen by 25% between Years 1 and 3 of the existing ICOSA programme. If the most competitively priced supplier exits the market, or for supply security reasons it is deemed appropriate to split tenders among suppliers, then Crown Agents may have to pay a higher overall average price, thereby reducing the tablets procured, and thus, the number of people who can be treated. Given the fact that the current programme relies 100% on procured product, it is very sensitive to even small price changes in PZQ. The non-donated (i.e. Crown Agent procured) portion of the PZQ costs of the additional £25 million programme would similarly be affected by any price changes.

In January 2012, Merck Serono announced plans for a tenfold PZQ donation increase to from 25 million in 2012 to 250 million tablets by 2016. Although it has stated that the timing and pace of this scale-up are dependent upon its ability to find new active pharmaceutical ingredient (API) sources meeting its quality and compatibility[77] criteria, Merck Serono expects that the following amounts will be available: 50 million tablets in 2013, 75 million in 2014, 100 million in 2015 and 250 million in 2016.[78] Merck Serono’s announcement provides opportunities as well as potential threats. The opportunity would be for the DFID programme to deliver the Merck Serono product and achieve a reduced cost per treatment delivered. The potential threat would be negative market impact on the paying market, further reducing supply security and price stability. A full consideration of issues in relation to this donation is provided in Annex 2. This section focuses on the economic trade-offs between gains in static efficiency (relying more on the donations to get better cost benefit results the short term) versus dynamic efficiency (preserving a more diverse supply base resulting in price and supply stability).
[77] Not all of the current API suppliers can provide API particle sizes which are compatible with the requirements of Merck Serono’s tableting facilities in Mexico, nor can all current suppliers meet Merck’s stringent quality requirements.
[78] To put this in perspective, the current total annual market is approximately 140 million tablets and total health need is between 400 and 600 million tablets.

Dynamic efficiency. A recent BMGF-funded study[79] concluded that the donor community should engage in activities – such as expanding the tender market size and splitting tenders – designed to lure in a third commercial formulator, as this would likely improve supply security and delivery time performance, which have been issues of late. It is not possible to know what size market would attract an additional formulator, although Shin Pong – a long-standing supplier which exited the African tender market in 2009 –- was interviewed as part of the aforementioned study and indicated a willingness to re-enter the market if they could generate at least $200k in gross profit, citing the example of making $0.01 profit per tablet on a volume of 20 million tablets.
[79] Praziquantel Sustainable Supply Project Confidential Report to Partners. Summary Report June 29, 2012 Results for Development Institute.

DFID's increase under Option 2 should increase the paying market by at least 110 million tablets in total (or 27.5 million per year), assuming that USAID does not change its purchasing volume.[80] A key factor to consider is whether the Merck Serono donation will expand the market size (Scenario A in Figure 5), or alternatively cannibalise existing market share (Scenario B in Figure 7). As DFID does not plan to decrease the size of its purchases, but will likely increase them by 27.5 million tablets per year under Option 2, DFID will not be making the market less attractive. USAID’s actions are the key. If USAID does not reduce the amount of PZQ procured, and the donation (which can be easily absorbed in terms of health need) serves to expand the market size, then there will be no market impact (Scenario A in Figure 5). If USAID decreases their money allocated to PZQ purchase, and the DFID increase is not enough to offset this, then Scenario B will result.
[80] DFID's increase under Option 2 would enlarge the procured market by 20% per year, given the market size of 140 million tablets today and knowing that the portion allocated to PZQ purchase translates to 27.5 million additional tablets per year.

Figure 7: Market Impact Scenarios

The impact in Scenario B could be quite significant, as demonstrated through theoretical economic modelling (Annex 3). Relying on realistic assumptions derived from the current market characteristics, the third smallest supplier would be expected to exit the market once Merck Serono makes a donation bringing its volume from 25 million to 50 million tablets (the amount Merck Serono expects to be donating as of 2013), and assuming (a realistic assumption) that this volume would replace that which the third smallest firm would have otherwise sold (Scenario B).

Static efficiency, as revealed by cost benefit analysis: Four scenarios were examined in terms of funds allocated to PZQ purchase (managed by Crown Agents) versus obtaining and delivering donated product, and with implications for implementation funds leftover (managed by SCI) – see Table 3 below. The percentage programme needs supplied by procured PZQ was altered to 15%, 30%, 50% and 75% (Column A), while the funds for central management costs remained unchanged at £4.3 million over the 4 year Phase 2 programme (2013/14 to 2016/17).[81] Thus the change in funds used for PZQ purchase (Column B) changed the amount of funds leftover for country programming (Column C), which is a function of funds allocated to SCI (central + programming funds). The changes in funds leftover for country programming (Column C) influenced the number of treatments that could be delivered (Column D) which in turn influenced the CBA. The country allocation figures are based on the diversified portfolio option, which is based on SCI’s proposed percentage allocations to existing eight plus two new countries. The CBA analysis includes financial but not economic costs and uses the middle range DALY estimate.
[81] This figure comes from SCI estimates and relates more to fixed (i.e. M&E, impact research, central management, overheads) than to variable costs, therefore there would be little change in this figure according to the variation in programme size being considered here.

Table 3: Sensitivity of key model parameters to percentage procured vs. donated

A. Percentage of programme needs for PZQ procured	B. / Option 2 funds for PZQ / (£ million)	C. / Funds left for country programming / (£ million)	D. Treatments delivered under Option 2 (millions)	F. / Financial CBA under Option 2 / using mid-range DALY estimate (cost/DALY averted in £)
75%	10.4	8.7	88	49
50%	8.5	10.6	108	40
35%	6.8	12.2	124	35
15%	3.7	15.4	156	28

As expected, the programme’s cost effectiveness is higher when the programme relies more on the donation and buys less PZQ.

If DFID chooses the scenario whereby 35% of programme needs are purchased and 65% of programme needs are met through donation, the breakdown of supply sources will be as follows:

Table 4: (Option 2) PZQ purchase quantities relative to donated supply available

DFID financial year	2013/14	2014/15	2015/16	2016/17
Total PZQ quantities required	33 m tablets	66 m tablets	81 m tablets	129 m tablets
35% purchased	12 m	23 m	28 m	45 m
Leaving 65% to be obtained from Merck	21 m	43 m	53 m	84 m
Merck announced availability	50 m	75 m	100 m	250 m

Thus under the 35% purchased scenario, SCI would expect to distribute approximately half of Merck’s annual donation during 2013 to 2015. SCI have confirmed that the organisation of this partnership has already begun, under the management of WHO, and WHO and Merck are in fact counting on the DFID implementation funds channelled through SCI to ensure that their product will be distributed in recipient countries.[82]
[82] Merck Serono donates all the tablets to WHO and will continue to do so in the future. Merck confirmed that SCI would be an important partner for many African countries and that the distribution figures assumed in Table 2 are consistent with their assumptions. Jutta Reinhard-Rupp, personal communication February 2013.

Conclusion: Economic modelling confirms the obvious point that relying on donations offers a better return for DFID’s money, but this must be balanced by a focus on supply security enabled by maintaining or expanding the size of the tendered market.

The key parameter to consider in deciding on the funding allocation is what USAID will do. USAID has suggested that they would plan to reduce their purchase of PZQ slowly over time as the Merck donation increases. This combined with the news of Merck’s donation increase – may result in a significant reduction in PZQ purchases.[83] The current situation in the US suggests this is a significant risk.
[83] USAID noted that they would not stop PZQ procurement unless Merck’s donation was sufficiently scaled up.

However, by increasing its allocation to PZQ purchase under Option 2, DFID will provide incentives for the two existing suppliers to remain in the market. If USAID does not reduce its allocation to PZQ, then DFID funds of £6.8 million for PZQ under Option 2 may even allow the total tender market size to increase from 140 million to more than 160 million tablets per year, potentially enough to lure in a third supplier with the aim of increasing supply security and supplier performance.

Due to the inability to predict US actions and inability to predict supplier actions and pricing, the evidence base for the “Secure supply of PZQ at a relatively stable price” assumption has been graded as medium. In order to mitigate risks, the following actions are required:

1. A PZQ co-ordination group is facilitated by WHO and meets once per year. DFID advisors with market dynamics expertise should attend, as should Crown Agents and SCI. It may be necessary to excuse Merck Serono representatives from some discussions involving commercially sensitive information on other suppliers. Partners need to improve accuracy of forecasts of need and implementation capacity for PZQ, to increase reliability and predictability of demand, to which the suppliers can respond with capacity investments.
2. Crown Agents should go through a new framework tendering exercise for PZQ procurement, for 3 reasons: i) the validity of the previous framework exercise will expire during the period of the second phase of the programme, and ii) the supply side has shifted since the last exercise, with signals that new suppliers could enter the space and signs that suppliers currently in the framework may be losing interest, iii) the demand side has enlarged due to the expansion of DFID’s commitment from £25 to £50 million, with 35% of new funds going towards PZQ purchase. The new framework should be designed explicitly to lower entry barriers for potential new quality suppliers, employing strategic procurement practices (e.g. splitting tenders).
3. Jointly with partners, DFID will commission work to analyse the PZQ market situation at key intervals (e.g. every 18 months). The last market analysis was completed in April 2012, making the next one due ~October 2013, and the following one ~ March 2015 (NB: The exact dates should be co-ordinated so as to happen prior to the WHO-led PZQ co-ordination group, in order to inform the discussion of the group.) This market analysis is different to the work of Crown Agents, engaged as one of several purchasers and concerned more with static economies gained for the ICOSA programme via prices and timely delivery of a quality product. The overall market analysis will need to be independent of buying agents and will need to factor in overall market demand as well as overall supply (formulation and API), number of suppliers and market share of suppliers to determine market fragmentation.
4. Periodic ICOSA programme monitoring should include market health monitoring via: i) number of formulations of “quality assured” PZQ registered with WHO/ERP and ii) market shares of each formulator, as available from periodic market studies, iii) prices paid by Crown Agents, iv) size of donor funded market for commercially procured PZQ
5. DFID’s allocation between Crown Agents for PZQ purchase and SCI should be kept deliberately flexible to allow for evolution of the market.

Assumption 5. Countries selected offer maximum health impact return on investment

Three options were considered for distribution of the funds to different countries:
1. spend all the extra resources in the existing eight countries;
2. spend all the extra resources in two new countries (Ethiopia and DRC)
3. a combination of i) and ii).

Given the effectiveness of MDA in reducing the burden of SCH and STH infection, and the rapid rates of reinfection (and disease) observed in the absence of adequate sanitation and hygiene, two competing (but not mutually exclusive) principles will influence the choice of countries supported: maximising health impact and achieving long-term sustainability. If the priority is long-term sustainability, then the choice of countries might be skewed towards Group III countries (see definitions below) where there is a possibility of eliminating SCH as a public health problem. If the priority is achieving the greatest short-term health impact, then Group I countries with the heavy infections and low treatment rates might be prioritised, even though operations in these countries may be more challenging.

Group I countries: The principle of maximising short-term health impact would argue for focusing efforts on areas where the intensity of infection is greatest – and where sanitation and hygiene are inadequate, political instability or conflict may be present, and infrastructure may be limited. Although the health benefit from treatment would be great for children in these areas during the next five years, it is unlikely that economies, complementary public health interventions and SCH control programmes would improve adequately to sustain these gains for subsequent generations. Thus, providing MDA for a minimum of three years would yield a very significant health impact for the generation of children treated (the greatest in terms of health benefit per dose) – but future generations would not directly benefit if the programme ends after several years. Malawi, Cote d’Ivoire and Liberia are Group I countries currently in SCI’s portfolio and SCI is proposing to work in two new countries: DRC and Ethiopia. (NB: These countries would be ‘new’ to the DFID programme, though not entirely new to SCI. SCI has already started SCH work in Ethiopia this past year and it already has relationships in DRC through work on cysticercosis.) Studies[84] have shown that costs of working in new countries are 30% higher in the first year, related to start-up costs such as mapping, training, and new equipment.
[84] Leslie J, et al. (2011) Schistosomiasis and Soil-Transmitted Helminth control in Niger: Cost effectiveness of school based and community distributed Mass drug administration. PLoS Negl Trop Dis 5(10): e1326. doi:10.1371/journal.pntd.0001326

Group II countries: Balanced between the principles of long-term sustainability and short-term impact lies a group of countries that have moderate to heavy disease burden (especially in endemic pockets), where short-term health impact from MDA would be high and long-term sustainability may be a reasonable goal. All Group II countries have delivered effective treatment for NTDs to some degree either through a single disease approach or as a pilot integrated programme. It may be possible to scale up MDA to national-level coverage, reduce the frequency of MDA, and mobilise efforts to improve sanitation and hygiene to the point where MDA can be eventually withdrawn in some parts of the country. Tanzania, Mozambique and Zambia are Group II countries currently in ICOSA’s portfolio.

Group III countries: The principle of long-term sustainability would argue for focusing efforts on endemic countries where programmes have been running for some years, where prevalence is falling, and can be reduced to below 5%. The ultimate goal in these countries is elimination (interruption of transmission) and the target is the reduction of incidence of infection to zero.[85] There is an indirect ‘externality’ of reducing local SCH prevalence to very low levels. Getting a community to <5% prevalence has two benefits. Risk of morbidity is substantially reduced, while transmission of new infections may be subsequently lessened for 4-8 years in intermediate-risk communities. Thus, over the next ten years, MDA can be withdrawn in some areas and the health gains that were realised through the MDA will be sustained. The current burden of SCH and STH in such countries is generally low or moderate; therefore the global short-term health impact of focusing exclusively on these countries would be relatively limited. Niger and Uganda are Group III countries currently in SCI’s portfolio.
[85] Schistosomiasis progress report 2001- 2011 and strategic plan 2012-2020. WHO, 2013.

Evaluating options for country selection: While a single-minded focus on either long-term sustainability or short-term impact could be justified, it could equally well be argued that a diversified portfolio of countries should be supported with DFID funds, given the fact that global SCH control will require progress in all three country groups. Second, the scale up of donated drugs and increase in donor funds for implementation and procured drugs makes it possible to be inclusive of all three scenarios. Third, successful control of SCH morbidity may lead to intensified efforts to interrupt transmission. Finally, lessons learned from the Group II and III countries will be relevant to the more challenging Group I countries.

The Group I countries currently supported by DFID exclude those with the greatest volume of need globally – Nigeria, Ethiopia and DRC. With the additional £25 million, SCI proposes to expand programmes not only in the existing eight countries but also to Ethiopia and DRC, where there are large populations requiring treatment, and donor funding had not previously been at a sufficient scale. The additional DFID funding enables SCH to be controlled in these higher risk, but potentially higher reward, countries.[86]
[86] The Ethiopian government has shown strong commitment in providing in-kind support - making staff available both centrally and in the Regional health bureaux. NTD control for them is very new and so no specific budget line items are in place yet, but they are discussing it in their “MoH retreat” in late March 2013 and will launch their NTD National plan on May 25 2013. The DRC Ministry of Health convened a stakeholder meeting in January 2013, and are keen to get SCH control started in conjunction with LF, but have not yet announced what budget the government is willing to contribute.

The weight of the economic benefit was explored through examining the trade-offs between greater health impact per dose achieved in Group I countries versus greater cost-efficiencies and progress towards elimination in Groups II and III countries.

Key criteria for country selection, include: leverage of existing resources, capacity and track record of delivery, scope for integration, governance, government commitment, and the need for intervention. Such a wide range of considerations (some of which rely on the contractor’s judgement gained from years of experience in the field) cannot be captured in an economic model, however the contractor’s proposed allocation of treatments informs one of the three options evaluated under country selection.

Modelling results: The share of funds allocated to PZQ purchase was left at 35% for all scenarios, thus 125 million treatments could be delivered under Option 2. The distribution of these treatments was altered according to three scenarios:

- Scenario 1: Spend all the extra resources in the existing eight countries
- Scenario 2: Spend all the extra resources in two new countries (Ethiopia and DRC)
- Scenario 3: A combination of 1 and 2, in proportions recommended by SCI based on health need not met by other donors/implementers and government commitment.

Table 5: Total PZQ country allocation scenarios 1, 2 3 as compared with need and prevalence
Total treatment numbers are provided in millions and include total quantities delivered over three years from Options 1 and 2 combined (in black) and according to three scenarios. Option 1 allocations are unchanging and shown in red, in order to show additionality from Option 2. (NB: this table excludes relatively smaller treatments delivered in 2011 and 2012.

A	B	C	D	E	F
Country	Scenario 1	Scenario 2	Scenario 3	Annual estimated need x 3 years[87]	Prevalence[88]
	Treatments	Treatments	Treatments
Uganda	26 (6)	6 (6)	9 (6)	24.2	25%
Zanzibar	4.3 (0)	0 (0)	6 (0)	Not available	20%
Niger	17.6 (2.5)	2.5 (2.5)	8 (2.5)	15.9	15%
Zambia	20.3 (6)	6 (6)	11 (6)	13.1	32%
Tanzania	31 (15)	15 (15)	22 (15)	28.6	36%
Cote d’Ivoire	17.9 (6.9)	6.9 (6.9)	17.9 (6.9)	11.1	40%
Liberia	9.9 (1.8)	1.8 (1.8)	10 (1.8)	2.9	55%
Malawi	23 (5.4)	5.4 (5.4)	22.9 (5.4)	19.2	47%
Mozambique	39.2 (12.6)	12.6 (12.6)	22.9 (12.6)	38.5	55%
DRC	0	53.2	20.9	51.2	28%
Ethiopia	0	66.5	27.8	63.3	32%
[87] Annex 2, Schistosomiasis Progress Report 2001-2011 Strategic Plan 2012-2020, WHO 2012.
[88] From "GBD Estimation Strategy Report for SCH", Report to Expert Group prepared by Rashmi Jasrasaria, Chris Murray, Mohsen Naghavi.

Scenario 1 assumes that all of the money would go to countries currently served. As can be noted from comparing columns B and E, the amounts distributed in this scenario exceed, sometimes by a large margin, the amounts estimated by WHO to be required to meet health needs.

Scenario 2 assumes that PCT would continue to be delivered under Option 1 to the eight countries. All the new money would be allocated to DRC and Ethiopia. Under this strategy, the amounts allocated would come very close to the estimated total health need in those two countries, which would require an unrealistic scale-up rate, given that government commitment is new and SCI is in initial stages of operations there. It also assumes that some of the health need in existing countries, where SCI is already operational and government commitment has already been tested, would not be met.

Scenario 3 assumptions are based on discussion with the contractor. This strategy would provide further treatments in existing countries as well as provision of treatments in the two new countries. As can be noted from comparing columns D and E of Table 5 above, some of SCI’s proposed allocations exceed WHO’s estimates of health need. The contractor explained that the health need (Column E) comes from WHO estimates and the contractor has more recent mapping data to suggest higher numbers are in need of treatment. In any case, this illustrates the need for some flexibility in country allocations, in the light of implementation experience and evolving estimates of the need.

Graph 4: Cost per DALY averted for Option 2 - under three country distribution scenarios / (£ per DALY)

The cost per DALY averted for Scenario 2 is the highest of the three scenarios – making it the least attractive on the basis of CBA – while Scenario 3 (the diversified approach) has the lowest cost per DALY averted and is therefore the superior option.

Conclusion: Scenario 3 is the recommended choice not only because it has the lowest cost per DALY averted, but it also is consistent with the contractor’s criteria, many of which cannot be incorporated into such a modelling exercise. Of the three scenarios, it is also the one which is least likely to over or under-provide treatments relative to what is currently known about the health need in those countries. The evidence base for selecting countries to offer maximum health impact return on investment has been graded as strong.

D. What measures can be used to assess Value for Money for the intervention?

Assumption 6. Programme implementation offers value for money
Standard value for money dimensions include economy, efficiency, effectiveness and equity.[89] The value for money dimensions are interdependent, for example interventions to raise quality of PZQ and thus enhance health impact/effectiveness can raise PZQ prices and lower apparent economies. Other interdependencies are detailed in the following paragraphs:
[89] www.nao.org.uk/sectors/third_sector/successful_commissioning/successful_commissioning/general_principles/value_for_money/assessing_value_for_money.aspx

Economy: Economy can be realised through decreased prices of PZQ but this is unlikely in the current market environment with only two suppliers and increased investments being required of them to meet quality hurdles required by WHO Expert Review Panel criteria. A balance also needs to be sought between seeking economies through over-reliance on donations and/or giving all the business to the lowest price supplier and the need to maintain a diversified base of commercial suppliers.

Efficiency: This programme provides efficiency gains through:
- Leveraging Merck Serono’s donation (static efficiency), while at the same time contributing to market health with increased investment of procured PZQ (dynamic efficiency) and
- Leveraging existing skills, structures and staff in the SCI programme over a wider scale of operations.

Efficiency can be monitored throughout the programme’s duration by analysing changes in cost per treatments. Costs can be disaggregated so that the following is monitored: central/management costs over time in relation to treatment numbers; programme costs (finances used in country) over time in relation to treatments delivered; PZQ cost in relation to treatments. At country level, costs can be monitored along the same categories as found in the literature and summarised in Annex 2[90] and compared against treatment numbers. Costs monitored longitudinally (comparing the programme to itself over time) will have some relevance but for several reasons (see in Annex 2), comparing data across countries and over time needs to be done with caution.
[90] Leslie J, et al. Schistosomiasis and Soil-Transmitted Helminth Control in Niger: Cost effectiveness of school based and community distributed Mass Drug Administration. PLoS Negl Trop Dis 5(10).

There should also be caution when evaluating costs in relation to treatment numbers, as incentives to boost the denominator, at the expense of appropriate targeting for maximum health impact, should be avoided. Finally, it should be noted that achieving economies on the side of programme delivery will be challenging in the first years in new countries; studies have shown that costs of delivery in the first year(s) are 30% higher than in subsequent years.

Graph 5 provides the breakdown of expected costs per treatments.

Graph 5: Per treatment cost components of Options 1 and 2 (in pence)
Option 1 breakdown of £0.35 pence cost per treatment delivered. (NB: The Crown Agent component includes the cost of PZQ, Crown Agents procurement fees and other goods procured for the programme). The SCI component includes the central plus delivery costs averaged over number of treatments delivered, / Option 2 shows the breakdown of £0.21 cost per treatment delivered (NB: The Crown Agent portion is significantly less due to a large portion of the drugs being donated, which reduces the average drug cost for the programme) / £0.35 / £0.21 / Cost in pence

Table 6 illustrates the impact on treatments delivered in Option 2, mainly as a result of donations.

Table 6: Summary of treatments delivered and DALYs averted under Options 1 and 2

	Treatments delivered (millions)	DALYs averted (millions)
Option 1	76	0.49
Option 2	124	0.73
Total	200	1.22

Effectiveness: Choosing countries with high prevalence and large hitherto untreated populations is a key parameter in achieving the highest health impact per pound invested, enhancing effectiveness. Effectiveness also relates to choosing the areas within a country where prevalence is highest, which is ensured through burden of disease mapping and consequent targeting, a key contribution SCI makes to the country level strategic planning process. Implementers are guided by the WHO Strategic Plan for SCH as to which operational choices are appropriate in different country contexts with different NTD goals; this relates to most appropriate target populations and distribution channels, treatment intervals, and complementary water and sanitation interventions.

Effectiveness also relates to central government commitment to control SCH and STH; this is a key criterion in the selection of countries to work in and it is monitored in the log frame as evidenced by the country having included SCH and STH control objectives in their National Strategic Plan, including budget. Health impact is crucially dependent on whether the PCT distributed is actually taken up by the target individuals. MDA for NTDs uses directly observed therapy, so compliance is expected to be 100% of those treated. In school-based distribution, the teachers observe the pupils taking the pill, while community based distributors do the same for community based programmes. SCI has developed a standard coverage protocol used to quantify and validate the coverage in the national target group; this protocol has been piloted in Malawi.

Equity: More than 1 billion people — one-sixth of the world’s population — are infected with one or more NTDs, an additional two billion are at risk, and each year, half a million people die as a result of NTDs.[91] Populations with high rates of NTDs includes indigenous groups, populations that have experienced prolonged or internal conflict, and those who live in urban slums.[92] Individuals living in extreme poverty are the most susceptible to NTDs, due to physical factors of poverty as well as social. On the physical side, poor living conditions place people at risk, including poor sanitation placing people at high risk of exposure, use of freshwater sources for collecting water and expelling faeces and urine, lack of access to medicines and exposure of feet due to lack of shoes. Exclusion and social inequity contribute to disease risk as well.[93]
[91] Hotez, P et al. Control of Neglected Tropical Diseases. New England J of Medicine. 357.10 (2007).
[92] Hotez, P et al The Neglected Tropical Diseases of Latin America and the Caribbean: a Review of Disease Burden and Distribution and a Roadmap for Control and Elimination Plos Negl Trop Dis. 2.9 (2008)
[93] Hotez, P. New antipoverty drugs, vaccines, and diagnostics; a research agenda for the US President’s Global Health Initiative. Plos Negl Trop Dis. 5.5 (2011)

Not only are the poor at risk of contracting NTDs but also NTDs contribute to and exacerbate poverty. NTDs have detrimental effects on growth and cognitive development of children, pregnancy outcomes, and worker productivity.[94],[95] They lead to long term disabilities and leave the poor in an endless cycle of poverty and ill-health, low productivity and catastrophic health expenditure.[96] While mortality from NTDs, estimated at just over half a million per year, is not as high as that of “the big three” (malaria, TB and HIV and AIDS), Sachs and Hotez[97] suggest that the combined disease burden, negative impact on economic development, and billions of dollars lost in worker productivity in low-income countries is greater than these three diseases. Because NTDs affect rural communities, in which there is a heavy dependence on agriculture for survival, individuals are continually being exposed to the parasites, further exacerbating the cycle of poverty.[98]
[94] Liese, B, M Rosenburg and A Schratz. Programmes, partnerships and governance for elimination and control of Neglected Tropical Diseases. Lancet. 375.9708 (2010):67-76.
[95] Hotez, P et al. Control of Neglected Tropical Diseases. New England J of Medicine. 357.10 (2007).
[96] Walraven, G. Health and Poverty: Global health problems and solutions. London: Earthscan, 2011.
[97] Hotez, P et al. Control of Neglected Tropical Diseases. New England J of Medicine. 357.10 (2007).
[98] Ibid.

School age children are especially at risk for SCH and STH infection.[99] Reduced school attendance and stunting associated with SCH and STHs can have adverse effects on future earnings prospects. A key issue in terms of equity is how the programme will reach children not in school and other high risk groups. A community based approach, as well as school-based MDA, is the appropriate response.[100] However it needs to be borne in mind, as noted above, that reaching out of school groups is more difficult and more expensive. Nevertheless it is necessary as a means of reaching adults likely to be suffering most from the disease and reaching more women and children (including girls who are more likely to be out of school).
[99] Hanson, C.A. et al. Integrated implementation of programs targeting Neglected Tropical Diseases through preventive chemotherapy: identifying best practices to roll out programs at national scale. American Journal of Tropical Medicine and International Health 4.5 (1999): 322-34.
[100] http://gnntdc.sabin.org/files/press_releases/Community-directed_vs_School-based_treatment_Tanz.pdf

For SCI’s standard coverage protocol mentioned previously, villages or communities have been chosen as the sampling unit to ensure all school age children have a chance of selection regardless of school enrolment. This allows SCI to estimate the proportion of all school age children treated. The coverage survey also determines gender-specific coverage and collects key information on why people do not take part in MDAs.

The evidence base for assuming that the programme will deliver value for money is medium/strong; areas which can be strengthened have been noted above.

E. Summary Value for Money Statement for the preferred option

DFID should fund Option 2, allocating an additional £25 million to expand the programme to £50 million. The country allocation discussed with SCI should be accepted. An allocation of £8.4 million to Crown Agents for purchase of goods and PZQ, and the remaining £16.6 million to SCI, would provide some increase in the DFID-funded tender market while maintaining a good return on investment of DFID funds. There should be some flexibility in the exact allocations to the selected countries and in the PZQ/implementation split, to accommodate some of the programme risks, primarily related to country uptake and speed of scale up. The extra funds allocated to PZQ purchase should be used strategically to shape the market towards greater supply security; this may imply the need for managing a new tender process allowing new participants to bid for the new funds.

Commercial Case
Direct Procurement
A. Clearly state the procurement/commercial requirements for intervention (distinguishing between direct and indirect procurement)
In Phase 1, two contracts were awarded following competitions launched during 2009. SCI was selected as the Service Provider from three shortlisted organisations following an invitation to tender published in the Official Journal of the European Union (OJEU). Crown Agents were selected as procurement agent for the required medicines and ancilliary equipment following a limited competition, in accordance with DFID procedures, between firms on DFID’s procurement panel. In addition, SCI entered into a sub-contract with Liverpool Associates in Tropical Health (LATH) and the Centre for Neglected Tropical Diseases at the Liverpool School of Tropical Medicine (CNTD) to provide additional support for SCI in three countries: Liberia, Mozambique and Zambia. Imperial College and CNTD also contract with each of the country recipients for the delivery of services to be provided by government with support from SCI.

Since these contracts were awarded recently, DFID’s Procurement Group agreed that a further competition is not required. It would be unlikely to produce a different result from the original competition and to do otherwise would result in considerable delay and threaten attainment of the targets set by Ministers to be achieved by March 2017.

The modus operandi of the enlarged programme will need to change because of Merck Serono’s commitment to step up its annual donations of PZQ tablets from 25 to 250 million annually during the programme period. A further procurement of medicines will be required by Crown Agents during the period in which Merck is building up its production capacity for the donation programme, as well as for additional vehicles and laboratory and computer equipment required to cope with the scale up of the programme. It is estimated that 65% of the tablets used will be donated. The allocation of the tablets donated by Merck is to be decided on a regular basis by a committee consisting of WHO, Merck, SCI and RTI, which is the agency responsible for USAID’s SCH programme.

Progress in PZQ procurement had been slower than expected because of problems motivating producers to supply PZQ meeting specified quality standards. However, suppliers have now been identified and deliveries are now being made to countries. A second procurement by Crown Agents is expected to present fewer obstacles and delays as a result of the experience gained in the first round.

The management of procurement, and the balance between purchased and donated supplies, will require careful handling for the reasons discussed in the appraisal case. There will be a need to maintain some flexibility in view of some uncertainty about the scale up of the Merck donation programme.

B.	How does the intervention design use competition to drive commercial advantage for DFID?
The contract is designed to deliver the outputs, outcomes and impacts specified in the logframe. The choice of service provider (SCI) was determined by a competition between three suppliers. SCI was chosen on the basis that it was competitively priced and its technical team and managerial arrangements were superior to the other tenderers. Similarly Crown Agents were selected from the DFID panel of procurement specialists as the the best qualified for this relatively technical area of procurement – including PZQ whose procurement presents challenges as detailed in the appraisal case and specialized equipment for use in the treatment campaigns.

C.	How do we expect the market place will respond to this opportunity?
Crown Agents will undertake competitive tendering for medicines and equipment required by the programme in accordance with current DFID and EU rules. As noted in the appraisal case, procurement of PZQ presents some special issues, particularly in view of the expanding level of donation by Merck. Provided the overall paying market does not decline it is expected that the programme will be able to procure the desired quantities. But there are risks and uncertainties relating to price and availability which we have sought to mitigate through extensive research into the market for PZQ and through utilising the expertise of Crown Agents.

D.	What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?
The procurement process has examined all the elements of costs with a view to maximising value for money. The main uncertainty, as mentioned, relates to the procurement of PZQ which we have sought to mitigate as described in the Appraisal Case. 81% of the procurement budget is for the allocation of PZQ.

This programme will increase efficiency and reduce costs during its lifetime through a number of strategies.

Programme efficiency through delivery
The key value for money measure in this programme is the cost per treatment delivered. Efficiency will be monitored throughout the programme’s duration by analysing changes in cost per treatment over time and comparing costs of treatment between countries. Costs of delivery in the first year(s) are estimated 30% higher than in subsequent years, as a result of the initial investment required. As treatment delivery is scaled up, the programme will benefit from economies of scale such that cost per person treated will reduce.

Costs will be disaggregated to provide information on the key cost drivers within the programmes, these will be analysed to look at where reductions can be made. Where feasible, value for money will be obtained by ensuring integration of activities where other NTDs are co-endemic. Advocacy, health education, training and drug delivery and monitoring and evaluation will be integrated as far as possible.

Programme monitoring and evaluation will identify the most appropriate measures to increase treatment coverage and therefore maximise impact with the most efficient use of resources.

Management efficiency
SCI works directly with the Ministries of Health/Education in each supported country with existing national staff and community volunteers implementing the programme within each country. SCI staff costs will be reduced further over the lifetime of the programme as local capacity is increased through the ongoing implementation leading to less frequent TA visits by UK-based staff. In addition, SCI has engaged a Ugandan-based capacity building advisor who is best placed to travel within Africa, resulting in lower travel costs.

E.	What is the intended Procurement Process to support contract award?
N/A. (see above, section A)

F. How will contract and supplier performance be managed through the life of the intervention?
Crown Agents provide SCI with monthly reports on the status of procurement. The milestones and targets set out in the logframe will be assessed on the basis of biannual reports from SCI (to which Crown Agents contribute). DFID will conduct an annual review of the programme (last undertaken in September 2012) to monitor progress and to consider any necessary revisions to programme strategy and the logical framework. In addition an independent review will be carried out in 2013/14 as the first phase of ICOSA will have completed 3 years.

Focus of the mid-term review

The objective of the mid-term review (MTR) is to evaluate and score the overall progress of the programme against the objectives set out in the logframe for Phase 1. Where possible the MTR will also comment on progress against the additional indicators in the new log frame. Key questions include:
-How well does the project meet the technical or management needs of countries given the different contexts?
-Assess the efficiency and effectiveness of the programme, its sustainability and its value for money.
-Consider how well the project links up work of other partners, for example:
- With other NTD control efforts, the integration of delivery or the sharing of resources where needed
- Links with water and sanitation
- Communication and co-ordination with other funders, purchasers and quality regulators of PZQ
-Is there more that can or should be done in these areas?
-Identify any key risks, opportunities or threats to the programme’s expected impact caused by changes in global context and assess mitigation strategies.
-Assess whether the project has the most appropriate skill mix
-Analyse the robustness of the planning and reporting processes
-Analyse the robustness of the financial management and reporting processes
The MTR will also help us to more clearly define the questions and data needs for the final evaluation of this programme.

Indirect Procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention?
The procurement in this programme is mainly direct: between DFID and, respectively, SCI and Crown Agents. DFID’s funding mechanism is a contract with both these parties. SCI in turn subcontracts to the CNTD and Liverpool Associates in Tropical Health (LATH) in three programme countries (as set out in their original tender document). Beyond this SCI or CNTD sign a contract with recipient governments which specifies the funding to be provided to governments, and the services government agrees to provide in return. DFID reimburses SCI and Crown Agents at regular intervals against supporting documentation provided by both organisations.

B.	Value for Money through Procurement
As noted the services of SCI and Crown Agents were contracted through competitive tendering. Crown Agents are responsible for procuring drugs and other equipment according to procedures laid down by DFID and the EU. These procedures are considered satisfactory by DFID and likely to provide best value for money.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting?
The overall costs of the programme are as follows, showing Phase 1 costs alongside the costs of this programme (Phase 2).

£ million	2010/11	2011/12	2012/13	2013/14	2014/15	2015/16	2016/17	Total

Phase 1	0.279	5.6	5	5	5	4.121		25
Phase 2				5.3	6.6	6.4	6.7	25

Total	0.279	5.6	5	10.3	11.6	10.521	6.7	50

The programme budget is £25m. SCI will implement the programme based on annual work programmes for each country and will provide quarterly updates on forecasting to DFID.

The breakdown of the budget is described in Table 7 below:

Table 7: Break down of components under financial CBA Option 2

Classification	Cost elements included	Total DFID funding for all years
Commodities	Drugs; equipment (recipient country and contractor); consumable diagnostic supplies; procurement costs	£ 8.43 m
Delivery	Mapping of priority disease risk areas; cascaded training of educators and health workers in treatment delivery; drug clearance, storage and transportation; drug delivery in schools, high- communities; supervision of implementers; medical supervision in case of adverse events	£ 12.23 m
Management costs	Management contractor costs; travel; auditing accounts;	£ 1.57 m
Technical assistance	technical assistance; monitoring and evaluation of programme effectiveness	£ 2.77 m
Total		£ 25.00 m

Please note:
1. These figures include an allowance for inflation over the programme lifespan.
2. Over 80% total value of commodity costs will be used for drug procurement.
3. All activities in delivery costs comprise non-UK spend across the supported countries.
4. The delivery costs available will support the distribution of a higher overall value of drugs than those committed through procurement due to the additional drugs available through the Merck Serono donation in certain countries.
5. DFID managed mid-term review and final evaluation included in Phase I costs.
6. Crown Agents charges a fee of 2.5% on all procurement.
7. SCI staff are paid according to the pay structure of Imperial College. DFID pays a daily rate for all staff working on the project. We will continue to review the staff structure including skill mix and staff time devoted to the programme to ensure we are getting value for money.

B. How will it be funded: capital/programme/admin?
The programme will be entirely funded from the programme resources.

C. How will funds be paid out?
Funds for SCI are reimbursed on a monthly basis under the terms of the contract with Imperial College which hosts SCI. Under their contract, Crown Agents periodically bill DFID when they have made payments under procurement contracts. We review electronic copies of invoices (or Remittance Requests) to check them against the monthly forecast before receipting them on the Aries system. Crown Agents don’t issue Remittance Requests until the relevant paperwork has been received confirming procured items have been delivered.

D. What is the assessment of financial risk and fraud?
The risk of fraud relating to monies used by Imperial College and SCI is rated as low because of the practical and specific experience gained by SCI during the last 10 years, and the audit and financial controls that have been and will be put in place. In the past decade SCI have experienced several major project-specific audits to the US Office of Management and Budget audit standards and compliance for Institutions of Higher Education and Other Non-Profit Organisations. In all previous audits, the accounts and records held centrally at SCI have satisfied external audits.

1. Before any money is transferred to a country programme, Imperial College develops a research contract with each country which states the annual budget ceiling available against specific work plans and deliverables.
2. Each contract is allocated a purchase order to ensure funds are committed from the total award budget and to ensure country transfers do not exceed the agreed budget ceiling.
3. Each country programme is allocated a unique sub account code to enable robust financial management of individual programmes. The sub account structure separates the country programmes, enabling in-depth analysis.
4. SCI continuously monitor and ensure all financial transfers match the agreed workplan and specific activity-based budget, and cover a limited time span.
5. A strong emphasis on robust internal financial controls, accounting records and reports from each financial transfer are received and reconciled in a timely fashion (monthly) and the receipts must be received before subsequent transfers are authorised.
6. Praziquantel and albendazole are donated by the pharmaceutical companies through WHO. When cleared from customs these drugs are stored and accounted for by the Ministry. There is no commercial market for these drugs therefore there is minimal risk of theft.
7. An audit is carried out in at least two countries each year, and more if any irregularities are detected or suspected.

Imperial College requires the country to submit monthly statements of expenditures against the workplan and budgets, supported by appropriate documentation of evidence, including bank statements, three proforma invoices for any procurement, and receipts, all supporting documents and cash book transactions for all expenditure. CNTD operates a similar contracting system in those countries where it takes the lead. In each country there is a local financial officer or accountant responsible for overseeing finances, he/she will disburse funds and then collect evidence centrally to reconcile expenditure with activities.

Each country programme manager will be responsible for their inventory and for the locking up of any equipment and vehicles out of hours. Programmes are encouraged to implement good vehicle policies and asset registers. Inspection and updating of the vehicle, medical and capital expenditure (including consumables and equipment) registers are an integral part of the routine annual financial checks with routine physical audits made during management visits to the programmes throughout the year.

The SCI team includes a financial manager and an accounts assistant responsible for reconciling all receipts against the cheques and/or programme cash books for all transactions every stage of the programme cycle. The SCI finance manager visits countries to carry out a financial review and an internal audit using the MANGO (Management Accounts for NGOs) systems. Immediate action is taken to address any weaknesses identified. In addition, SCI have a French, Portuguese & English speaking consultant auditor, based in West Africa who is able to assist at short notice with any specific audit or individual programme financial control and advice requirements.

The SCI finance manager has identified an appropriate fraud awareness and prevention course to be attended by all staff liaising with the country programmes. All SCI National Coordinators plus country accountants have undergone financial management training provided by MANGO.

The risk with respect to Crown Agents procurement is considered low. DFID is only invoiced once procured goods have been delivered.

E. How will expenditure be monitored, reported, and accounted for?
The expenditure will be monitored, reported and accounted for through DFID's internal financial reporting system Aries. The ICOSA Project Officer will also maintain a separate spreadsheet in order to track and monitor expenditure and to provide accurate monthly financing forecasting details for the ICOSA Programme. In addition, both Imperial College and Crown Agents will maintain separate monitoring systems in order to provide DFID with regular updates on programmes expenditure and to inform when they will submit their invoices for payment.

Management Case

A. What are the Management Arrangements for implementing the intervention?
As described, management of the programme rests with SCI at Imperial College under the overall supervision of DFID. The management arrangements are as below.

Reporting to Professor Alan Fenwick, who will devote 75% of his time to the programme, will be a Senior Project Manager and a Finance and Operations Manager. DFID funding accounts for approximately 80% of SCI’s budget.

Under the Senior Project Manager, there will be four UK-based programme managers to cover the existing eight ICOSA countries, two of whom will be from CNTD, Liverpool. For the two new countries, DRC and Ethiopia, two local coordinators will be recruited reporting to the Senior Project Manager. A Senior M&E manager will be recruited to be supported by a biostatistician, socioeconomist, an M&E coordinator at CNTD and a data analyst.

The Finance and Operations Manager will be supported by a Finance Manager at Imperial and a counterpart at CNTD. Local Financial Assistants will be recruited in each of the ten programme countries.

The SCI Advisory Board, chaired by Sir Roy Anderson of Imperial College, meets annually.

The ICOSA Programme Management Board meets quarterly and DFID staff will attend those meetings where work plans for the year ahead are made and where performance over the last year is discussed.
Crown Agents procure drugs and equipment under a separate contract with DFID but in response to requirements identified by SCI.

DFID conducts an annual review of the programme, the first of which under Phase 1 took place in October 2011 and the second in September 2012.

In DFID, the programme will be led by a health adviser (10%) and a Project/Finance Officer (10%).

B. What are the risks and how these will be managed?
Overall the risks to programme success are considered low to medium.

Risks	Probability / (3 high, 1 low)	Impact / (3 high, 1 low)	Mitigation strategy
PZQ shortage as a result of shortfalls in donations or procurement.	2	3	Successful procurement in Phase 1 after initial delays but continued close liaison with WHO, USAID, Merck Serono and manufacturers is required in order to ensure adequate supplies either donated or purchased. Continued market due diligence is required to determine best procurement strategy which manages supply and price risk (see appraisal case).
PZQ price rise	2	2	As above, under PZQ shortage. Crown Agents will manage PZQ market strategically, in liaison with other procurers and Merck Serono as a product donor. A new framework tendering exercise will need to be conducted by Crown Agents, to allow for shifts in the supply base, the increase in purchase funds, and the need for extension of contract validity over timeframe of Phase 2.
Poor compliance with treatment	1	3	Unlikely in schools as treatment is closely supervised by teachers who directly observe drugs being taken. Compliance in the community to be monitored by SCI through surveys. SCI uses distributors selected by the community (i.e. are trusted). The strategy of community-selected distributors has been very successful in other programmes, e.g. it is the mainstay of the African Programme for Onchocerciasis Control.
Difficulty in scaling up as a result of lack of country capacity for implementation and/or logistical difficulties	2	2	SCI support is intended to help build country capacity and overcome logistical difficulties. Utilise NGOs with capacity and continue to build capacity through community, government and NGO efforts to minimise this risk.
Difficulty in scaling up on part of contractor	1	2	Finding appropriate staff to manage scale up at SCI is not considered a major risk. SCI will continually appraise staffing levels, and DFID will monitor this aspect.
Conflict affects implementation	2 (in DRC)	2	There will be gradual expansion of implementation year by year in DRC. SCI will work with the government to select the areas to be treated in a five year timetable with emphasis on safety, prevalence and intensity in deciding which areas to include in the first two years. SCI will seek to work with trusted community leaders and established NGOs to minimise disruption in case of insecurity. SCI will also aim to ensure that the programme does not inadvertently create or exacerbate conflict.
Resistance to PZQ and side effects	1	1	Resistance not yet encountered and good evidence that risk is low. Very few side effects have been recorded (and are transient), and people are warned about them before taking the tablets. The programme will monitor this and investigate cases experienced through appropriate MoH channels in each country.
Climate change risk	1	1	Climate change impact is low in course of the programme. The programme will commission work on potential future impact of climate change.
Exclusion of hard to reach	2	1	Use community- as well as school-based programmes including community volunteers. The programme will place greater emphasis on reaching out of school children, and a specific indicator has been included in the logframe. Other strategies may include the use of Child Health days which concurrently deliver immunisation, bednets and micronutrient supplementation through the health system.
Motivation of community volunteers	1	1	This issue is not specific to this programme but a broader, well-recognised potential problem whenever community health workers/volunteers are involved in service delivery. SCI will work closely with governments and other partners to consider different ways to motivate volunteers, based on available evidence internationally.

C. What conditions apply (for financial aid only)?
Not applicable.

D. How will progress and results be monitored, measured and evaluated?
To ensure that the ICOSA programme is achieving its goals, monitoring and evaluation (M&E) will measure progress against the indicators set out in the logframe. In order to demonstrate the outcomes are being achieved M&E will focus on the five themes which the logframe indicators fall into.

Impact
The M&E programme will demonstrate the impact of the programme on morbidity of those suffering with SCH by measuring reductions in intensity of infection and reductions in the percentage of heavily infected individuals from baseline measurements. These reductions have been estimated using historical programme data from SCI. To collect the necessary data, cohorts of 6-14 year olds from selected schools will be followed up annually to assess their parasitological and clinical status and to demonstrate health improvements arising from the programme . Health improvements will be assessed by indicators such as level of blood in urine, anaemia and anthropometric measurements. A new cohort of 6 year olds is to be sampled each year to provide evidence on transmission within the community. Hygiene and latrine use data will also be collected in each sentinel school to understand better the impact of sanitary conditions on outcomes. Finally in a subset of schools data will be collected on markers of PZQ resistance to assess whether this is emerging.

Performance (Outcome)
The programme’s outcome will be determined by the number of individuals receiving the tablets for SCH and STH. This indicator will be measured by reported coverage from the implementing units within countries, with a further household survey to validate the treatment coverage in all household members, including school-age children. The validated treatment coverage, with the target of increasing to at least 75% over time, will provide evidence of the proportion of school-age children treated who are in school and those who are not. This information will be disaggregated by gender for each country. The household survey will also collect data on age of individuals who took (and didn’t take) the drugs, where individuals took the drugs from, and distance travelled to reach place of delivery, where they heard about treatment and also reasons for individuals not taking the tablets. To be conducted concurrently to the household surveys, those individuals who are involved in the primary implementation of the programme (i.e. teachers, community volunteers and health supervisors) will be interviewed to further assess the performance of the drug delivery to the schools and communities.

Process
The WHO recommends that countries carry out ‘process’ monitoring in order to evaluate their SCH and STH control programmes which is in addition to the ‘impact’ and ‘performance’ monitoring described above. SCI will be supporting the collection of process monitoring data to ensure countries are implementing MDA according to their National Strategic Plans. Reporting systems using questionnaires and excel spreadsheets will be put in place, in each country and in selected implementation units, along the distribution chain to ensure that losses are minimised, and that drugs and implementation tools (training materials, dose poles, health education posters) reach their intended delivery points and are utilised correctly. This system will also help to highlight why some targeted implementation units are not managing to submit MDA reports to the NTD departments at the MOH after 90 days and other challenges faced in implementation. Subsequent trouble-shooting will be targeted to these areas.

Mapping
In order to provide both a visual guide to where resources for the mass treatment of SCH & STH should be targeted in a country and a baseline of infection in a country, mapping using prevalence of infection data and GIS (geographical information systems) are used. SCI will support the development of country-specific mapping protocols for each of the countries with which it is partnering with the aim of scaling up to 100% of at-risk areas mapped in all Group 1 and 2 countries. Group 3 countries will conduct re-assessment mapping surveys which will be conducted in areas where treatment has been carried out over 5 or more years and in others where the threshold of prevalence was previously too low to warrant mass treatment, to identify where there are remaining areas of transmission hotspots of SCH and thus where adjusted PCT (i.e. biennial treatment, annual treatment or biannual treatments) should be focused. The reassessment maps will also provide a visual marker of how successful previous years of control efforts for SCH have been and where additional control interventions such as improved water and sanitation practices and snail control may be required.

Cost
Programme financial expenditure will be closely monitored at all levels of implementation. At the country programme level the direct financial costs of operation will be collected through the current national level financial system and in implementing units within a country. From this financial expenditure data the direct financial cost per treatment will be determined for each country. SCI will be monitoring each of the Group 1 and 2 countries annually to ensure that the direct financial cost per treatment reduces over time from the baseline value. It will be expected that, as seen by experience and in published literature, programme financial costs for ‘start-up’ will be higher in the first two years of programme implementation as well as less individuals targeted for treatment meaning the cost per treatment will be higher. In subsequent years, if a reduction is not seen, then the drivers for the costs in that particular country will be examined in more detail and an evaluation of what the obstacles are for achieving cost savings. In Group 3 countries, which are aiming for elimination of SCH as a public health problem in remaining hot spots of transmission, SCI expects that the cost per treatment will not decrease over time in the same way, and may even increase, as more expenditure will be required for more frequent treatments for fewer people.

In selected areas the economic costs of implementing the programme within a country will also be determined by collecting data on the opportunity costs of the Ministry of Health and Ministry of Education contributions, volunteer time and of donated drugs. Finally cost-efficiencies will be determined and measured over time indicating, for example, where resources have been shared with partner organisations, number of trainings reduced and numbers treated increased.

Reviews and Evaluation
DFID will conduct an annual review of the programme (last undertaken in September 2012) with SCI and Crown Agents to monitor progress and to consider any necessary revisions to the programme strategy and logical framework.

Given the size of the programme, a formal independent evaluation is envisaged on programme completion in 2017. The purpose of the evaluation will be to assess the impact of the programme and to identify lessons learnt that will be important for future interventions in SCH and STH and to governments, other funders, drug donors and WHO (the key users of the evaluation). A budget has been set aside for the independent evaluation and the mid-term review. It is too early to define in any detail the content of the final evaluation, or who should undertake it, but it will be important in the early stages of the programme that the M&E programme is directed at producing meaningful results on health and socio-economic aspects, particularly where the evidence is weak.

Independent evaluation

A budget of £100,000 has been allocated for independent evaluators who will be contracted to work with the project to ensure the necessary data is being collected. The evaluation is intended to broadly assess the effectiveness and cost-effectiveness of the ICOSA programme. To this degree it will explore such questions as:

-How successful has ICOSA been in reducing the intensity of infection in each country? Results by S. mansoni and S. haematobium.
-Has ICOSA demonstrated improvement in health signs?  % children with anaemia
-How successful has ICOSA been in supporting countries to deliver treatments; how does reported coverage compare with validated coverage. Coverage reported by 1) school children 2) Not in school children 3) targeted at risk adults.  Lessons learned on improving coverage. Comparison of school based delivery versus community delivery
-Comparisons of cost data and cost per treatment data for countries and using the data to inform programme design.
-What has been the contribution of the programme in developing a greater understanding of how to achieve elimination of schistosomiasis in low income countries? How has cooperation with other sectors contributed to this?
-How successful has the programme been in maintaining a regular supply of PZQ at a competitive price? This would include analysis on how successful the programme had been in balancing the use of purchased PZQ with donated PZQ.
-How have governments found working with ICOSA and to what degree non-ICOSA countries are utilising the findings from ICOSA’s work and why?

The data requirements include:
Baseline and subsequent data on intensity of infection (S. mansoni and S. haematobium), % children with anaemia, prevalence of schisto in selected areas of Group 3 countries (for S. mansoni and S. haematobium)
-Number of people treated in different groups, validated coverage in different groups (as above)
-Cost data on procurement of PZQ delivery costs, costs of mapping and monitoring.

All the data will be collected and analysed by countries with the support of the programme. The independent evaluators would not be expected do any additional surveys or to collect any primary data. ICOSA will work with the independent evaluators to ensure the right range of indicators and data collection design are in place. This evaluation will be disseminated widely and is intended to be used by all stakeholders working on NTDs, the aim being that lessons learnt will be incorporated into WHO’s future guidance to countries. Detailed plans for the evaluation will be made over Years 1-2 of ICOSA Phase 2.

Logframe

Quest No of logframe for this intervention: 4119061

Annexes

Annex 1: Recommended treatment strategy for SCH

Category	Baseline prevalence among school age children	Action to be taken
High-risk community	≥50% by parasitological methods (intestinal and urogenital SCH) / or / ≥30% by questionnaire for history of haematuria	Treat all school-age children (enrolled and not enrolled) once a year	Also treat adults considered to be at risk (from special groups(a) to entire communities living in endemic areas)
Moderate-risk community	≥10% but <50% by parasitological methods (intestinal and urogenital SCH) / or / <30% by questionnaire for history of haematuria	Treat all school-age children (enrolled and not enrolled) once every 2 years	Also treat adults considered to be at risk (special groups (a) only)
Low-risk community	<10% by parasitological methods (intestinal and urogenital SCH)	Treat all school-age children (enrolled and not enrolled) twice during their primary schooling age (e.g. once on entry and once on exit)	Praziquantel should be available in dispensaries and clinics for treatment of suspected cases

Special groups: pregnant and lactating women; groups with occupations involving contact with infested water such as fishermen, farmers, irrigation workers, or women in their domestic tasks, to entire communities living in endemic areas.

Note: A more intensified strategy is required in areas where the aim is that of interrupting transmission. The table shows recommendations for achieving control of SCH-associated morbidity and achieving elimination of SCH as a public health problem.

Source: Schistosomiasis progress report 2001-2011 and strategic plan 2012-2020. WHO, Geneva, 2013.

Annex 2: Observed impact of PCT with with praziquantel among persons affected by SCH

Parasite species	Observed impact
All species	Reduced prevalence of infection
	Reduced intensity of infection
	Reduced prevalence of anaemia
	Reduced mortality
	Reduced pain
	Improved physical fitness
	Improved linear growth (height)
	Improved weight status
	Improved nutritional status
	Improved cognitive functions
	Increased worker productivity
	Increased appetite
	Increased skin-fold thickness
	Increased lifespan (i.e. higher average age of death)
Schistoma haematobium	Reduced haematuria
	Reduced microhaematuria
	Reduced bladder wall abnormalities (polyps, masses, ulcers)
	Reduced upper urinary tract abnormalities (e.g. hydronephrosis) and obstruction
	Reduced genital lesions
	Reduced incidence of bladder cancer
S. intercalatum / S. japonicum / S. mansoni / S. mekongi	Reduced prevalence of diarrhoea
	Reduced prevalence of abdominal pain
	Reduced prevalence of bloody diarrhoea
	Reduced hepatomegaly
	Reduced splenomegaly
	Reduced periportal liver fibrosis
	Reduced portal hypertension

Source: Schistosomiasis progress report 2001–2011 and strategic plan 2012-2020 (WHO 2013).

Annex 3. Model Assumptions

Costs
The best data to inform delivery cost projections comes from a Niger study by Leslie et al 2011[101] which refers to 2006 data and prices. Table 3 in the Leslie paper identifies programme costs, which can be updated to 2009 prices (GDP inflator and relevant exchange rates) and gives a cost of 14 cents / treatment which in today’s exchange rate of $1.55 per £ equates to £0.09. The contractor SCI periodically conducts internal costing exercises and maintains that their current average treatment delivery cost is £0.092 per treatment delivered.
[101] Leslie J, Garba A, Oliva EB, Barkire A, Tinni AA, et al. (2011) Schistosomiasis and Soil-Transmitted Helminth Control in Niger: Cost Effectiveness of School Based and Community Distributed Mass Drug Administration. PLoS Negl Trop Dis 5(10): e1326. doi:10.1371/journal.pntd.0001326

The £.092 treatment cost reflects a balance between factors which elevate and factors which reduce average treatment delivery cost. As described by Leslie et al, cost per treatment will vary by country, according to the composition of the population treated, the numbers targeted and treated at school and in the community, the cost and frequency of training teachers and community distributors. It also varies according to maturity of the programme; Leslie found that the economic cost of the programme in the second year was 29% less costly than the first year. Higher costs in the first year are due to the cost of the initial start-up activities incurred in the first year only, including advocacy, development of information, education and communication (IEC) materials, prevalence surveys and data collection for planning and the establishment of M&E activities, in particular the longitudinal monitoring sites, and repair/maintenance of the national office. Coverage rates may also be lower in first year(s) as well. Cost per treatment will also depend on the distribution system implemented – school or community, or both, or as in Burundi via the schools, health centres and health posts only. Integration also affects costs; most of the countries of focus to SCI practice integrated treatment, and this happened post 2006, so then the costs of treatment should now be lower as the system has changed and resources for training/drug delivery/organisation/supervision are increasingly shared across diseases.

Leslie et al looked at full economic costs, which meant the addition of government costs for overheads such as salaries which are not paid by the programme but are apportioned. The government’s cost contribution was 18% of the total costs.

Data from Table 3
USD costs (Leslie et al)
2005/2006
% of total costs
% of total costs excl. drugs
Programme costs
49,455

21%
49%
Government costs
41,894

18%
41%
incl. only in economic costing
International tech support
9,810

4%
10%
Drug costs
129,166

56%
128%
Total costs
230,326

100%
228%
Total costs excl drugs
101,159

82%
Costs excluding government cost contribution

Our model allows calculation based on financial or economic costs. Financial costs include those costs funded by DFID, channelled through SCI and Crown Agents to cover programme delivery and management costs and procured goods and drugs respectively. For economic costs, the estimated government contribution of 18% is added as well as the cost of donated drugs.

Central overhead costs came from contractor’s assumptions and include costs of management, travel to countries, and M&E. For Option 1 total central costs are projected to be £4,465,604 and for Option 2 the total is £4,335,204.

The contractor expects to achieve increased operational efficiencies as the programme matures, as revealed in the decline in cost per DALY averted. This primarily results from access to donated PZQ but is also a function of apportioning central overheads across a wider scale. Under Scenarios 2 and 3 under country choice, programme costs per treatment delivered at country level would rise, due to entering new countries. This results in a higher overall cost per DALY averted because the increased cost is not fully offset by the increased health impact per treatment delivered in these countries with a higher prevalence rate.

Overall financial costs (programme costs, central overheads, procured goods and drugs combined) per treatment of the DFID programme were reassuringly consistent with financial costs in the Leslie study (i.e. excluding government contribution) of 50 cents (33 pence). This is the case even despite the fact that increased funds have been set aside for M&E and impact research/evaluation in this relatively under-researched area and a recent rise in PZQ prices.

Benefits
Numbers treated: In Scenario 3, we have relied on the contractor’s proposal for country selection and treatment numbers per country (comprising the “diversified portfolio” option). Scenarios 1 and 2 assume distribution of treatments according to different percentages, with Scenario 1 funds directed only towards existing countries and Scenario 2 funds directed only towards the 3 new countries. The methodology and results for this were already elaborated in the main text.

Translation from treatment delivered to DALY averted:[102]One treatment does not equate to a disability averted. Each treatment is not given to a unique individual; most individuals will receive 3 PCT treatments in total. Thus, treatments delivered have been divided by 3 to account for individual benefits.[103] Also, not every individual treated will benefit. Different countries have different prevalence rates and we have assumed that for each person treated, the health impact results from the disability weight from the disease, multiplied by the prevalence rate in the country (for example, for every 10 individuals treated in Malawi, 4.7 persons will be infected and will stand to benefit from the treatment).
[102] Method confirmed as appropriate by personal communication with Professor Charles King
[103] Method confirmed as appropriate by Professor Alan Fenwick.

DALY calculation:
Studies on the global, regional or national burden of disease continue to draw heavily on the set of disability weights derived in the 1996 revision of The Global Burden of Disease (GBD).[104] Mortality and morbidity are combined into a single, common metric, the DALY. DALYs are comprised of: 'Years of Life Lost' (YLL) and 'Years Lived with Disability' (YLD). DALYs are calculated by taking the sum of these two components: DALY = YLL + YLD. DALY scores range from 0 (for perfect health) to 1 (for death). The DALY total sum can be divided by the population affected by the condition in order to derive a “DALY per case” estimate. Relying on references from peer reviewed articles, a range of DALY per case estimates for schisto have been used to calculate DALYs averted for this programme.
[104] Murray CJL, Lopez AD. Evidence-based health policy – lessons from the Global Burden of Disease. Science 1996; 274: 740-3.

With support from the Bill & Melinda Gates Foundation, a research consortium based at the Institute of Health Metrics and Evaluation (IHME) has led a major revision of the global burden of disease, in collaboration with a network of hundreds of experts from around the world. This produces a periodic, comprehensive re-estimation of disability weights for the full set of around 230 unique sequelae associated with the array of disease and injury causes in the study. In its December 2012 publication, the IHME ended up using 3,122,717 as the total DALY figure (comprised of comprised of 2.8 million years lost to disability +.32 million years of life lost) and this, divided by total cases, gives a DALY per case of .008.[105]
[105] Murray et al, Disability-adjusted life years (DALYs) for 291 diseases and injuries in 21 regions, 1990–2010: a systematic analysis for the Global Burden of Disease Study 2010. Lancet December 2012; 380: 2197–223.

However, other experts believe that the IHME weightings still underestimate the disease burden. One study[106] relied on a literature search and found that the symptoms of Schistosomiasis japonica were 7 to 46 times greater than the current estimate. The team arrived at a disease burden weighting of 0.098 (for < 15 years) to 0.186 (for > 15 years). The author of this study has been in continuing negotiations with the IHME team about the disability weight of 'Acute mild infection', more appropriately termed 'active mild infection'. IHME gives this 'other' category a disability weight of 0.42% whereas recent Quality of Life surveys have shown a QoL deficit of 2-4% in school age children. This difference could make a large difference in the total DALYs calculated for SCH, because the IHME estimates that 220 million people live in this particular 'other SCH' health category; if the disability weight goes up to 2% (5 fold) the overall DALY count goes up another 3.5 million, to a total of 8.6 million.
[106] Finkelstein JL, Schleinitz M, Carabin H, McGarvey ST (2008) Decision-model estimation of the age-specific disability weight for schistosomiasis japonica. PLoS Negl Trop Dis 2: e158. Also summarised in: King CH (2008) Schistosomiasis Japonica: The DALYs Recaptured. PLoS Negl Trop Dis 2(3): e203.

Given the current state of disagreement amongst experts about the SCH DALY weighting, we have modelled CBA based on three scenarios: low end estimate of .008, a high end estimate of .098 from the expert studies, and a mid-range average between these two - .045. The mid-range value was used as our base case.

Annex 3: Overview of PZQ considerations

Several other issues need to be considered with regard to the donation: 1) the alignment of the donation with aid effectiveness principles 2) the programme risk of relying on donations and 3) market impact, with implications for supply security.

Aid effectiveness: DFID is committed to the principles of the Paris Declaration on aid effectiveness: ownership, alignment, harmonisation, managing for results, and mutual accountability.[107] Donors of medicines also need to comply with WHO guidelines on donations which have been developed to provide guidance to donors and recipients on how to improve donations and DFID funds should only be used to support delivery of donated product if the donation meets these guidelines.[108] Given that the Merck Serono donation is channelled through WHO, we would expect alignment with the donation guidelines, nonetheless, if DFID funds are used to deliver the donated drugs, then monitoring of alignment should form part of the DFID M&E programme.
[107] The Paris Declaration sets out an agenda to make aid more effective and efficient by reducing duplication, transaction costs, and misdirected aid. The essence of the Paris Declaration is a commitment by donors to help developing countries' governments formulate and implement their own national development plans, using their own prioritisation, planning and implementation systems wherever possible.
[108] http://whqlibdoc.who.int/publications/2011/9789241501989_eng.pdf

Programme risk: As with any donation, a change in leadership or in strategic direction of the donating company could place the donation offer at risk. Although Merck Serono’s management have committed to offer the donation in perpetuity, this would obviously be subject to continued management commitment. Merck Serono has also stated that the offer is contingent on being able to obtain the active pharmaceutical ingredient (API) of sufficient quality standards and compatible with their formulation requirements, as Merck Serono is only a formulator, i.e. they manufacture tablets after procuring API from other sources. Recent work funded by the Bill and Melinda Gates Foundation[109] has revealed that there is adequate API capacity of required quality available worldwide to supply circa 400 million tablets, as compared with circa 140 million tablets delivered annually at present, and as compared with projected health need of between 400 m and 600 m tablets per year. The former figure of 400 million is what experts deem to be a “more realistic” projection of what can actually be delivered today given near term capacity and the latter of 600 million is viewed as the “ambitious” projection based on theoretical health need. Despite the findings of the BMGF study, recent attempted procurements by USAID and DFID contractors have come up against supply constraints. The two existing commercial formulators say this is due to scarcity of quality API while the BMGF-funded research concluded that formulator duopoly is the reason for poor supplier performance. For different reasons, Merck Serono is also experiencing API supply constraints. Due to compatibility issues, Merck Serono is unlikely to be able to source from the same API suppliers as those that supply to DFID and USAID's formulators - Cipla and Microlabs. Merck Serono is in the process of identifying and pre-qualifying new API suppliers. It is as yet unknown whether they will successfully secure new API sources, therefore this presents a risk for relying on the donation.
[109] Praziquantel Sustainable Supply Project Confidential Report to Partners. Summary Report June 29, 2012 Results for Development Institute

Market Impact: Market impact is an important consideration in terms of supply security – how do we ensure that a healthy market is developed and maintained such that supply security and timely procurement can be enhanced?

The 2010 edition of the WHO Guidelines on Donations concedes: “The negative impact that donations may have on sustainable access to medicines is often not well appreciated ... Donations of these products may influence the market and suppress competition. The donation may eliminate or greatly delay the import of cheaper alternatives, which will be necessary once the donation programme has ended and regular provision from public health”

PZQ is supplied on a competitive market basis at present. The procurement agent for the ICOSA programme, Crown Agents, has learned that their main formulator/supplier Cipla is investing in new in-house API production facilities to be completed in early 2013. The producer states that “This will provide us with API of assured quality and not leave us dependent on API suppliers from South East Asia”. This should provide some increased API supply security from the procured market. A possible expansion in DFID's procurement would put some additional pressure on the API supply base (only under the assumption that USAID’s procurement levels remain constant), however it would not be "in addition to" pressure from Merck Serono on the API supply base, since these are primarily two distinct supply bases.[110] This does however mean that programme reliance on the donated supply base at the expense of the commercial supply base would indeed make the market less attractive (i.e. cut into the market share) of competing suppliers. This is especially a concern given the fact that PZQ is a low margin/high volume product, where market share volumes are paramount to making a profit. Short term thinking focused on static efficiency of achieving health impact at the least cost would argue for relying on the donation as much as possible and using DFID money for implementation/distribution of the donated product. However, the possibility that the donation would drive away competitive producers who could help maintain a level of supply security must be considered. Long term thinking about market health and dynamic efficiency would argue for preserving supply security through diversifying supply sources and maintaining a competitive market alongside the donated product.
[110] Claire Qureshi, Results for Development - Project lead on BMGF-funded work, personal communication

Precisely where the balance should rest between expanding procurement versus expanding funds for implementation is the subject of the economic analysis. If DFID allocates a higher share to PZQ purchase, it would send a more robust demand signal and pull to current API suppliers and formulators supporting the procured market, hopefully preventing them from fully dropping out and pursuing other markets. According to the BMGF-funded analysis, the real problem driving delays stems currently from the duopoly situation on the formulator side and resultant lack of ability to sanction poor formulator performance, not from limitations in the API supply base. Attracting an additional formulator into the market might enhance supplier competition and performance. According to the BMGF-funded analysis, we might expect to see even better supplier performance if we could expand (after allowing for potential decreases on the USAID side) the size of the current annual tendered market of 140 million tablets to at least 160 m tablets.

A key factor to consider is whether the Merck Serono donation will expand the market size or alternatively cannibalise existing market share. If the latter, the impact could be quite significant, as demonstrated through theoretical economic modelling (Box 1).

Box 1: Theoretical Modelling of Market Impact under Scenario B from Figure 2[111]
Assume: 140 m tablets is the size of the current market, roughly distributed as follows: / 25 m tablets from Merck Serono / 55 m DFID split by 75:25 Cipla and Microlabs in market shares / 60 m USAID, split by 60:40 Cipla and Microlabs market shares / We can examine theoretical impact through economic modelling of the loss of margin suffered by a firm competing with a donation: m* = m - RS*F/((1- RS)*R) [112] / [Read as new margin = old margin minus reduction in market share multiplied by fixed cost, divided by new revenue (which is equivalent to old revenue multiplied by 1 minus percent reduction in market share)]. / Using plausible assumptions based on what we know about the characteristics of the PZQ market - with three supplying firms including one who is a donor[113] - we can model loss in margin under various assumptions. / Donor firm has 18% market share, the smaller of two generic firms has 27% market share / Generic firm has profit margin of 5%[114] / Prior to donation, generic firm has a cost structure where fixed costs (F) are 80% of total costs; this is a very typical operating leverage of a generic producer / Donor firm makes a donation bringing its market share from 18% to 36%, resulting in a loss of market share of 67% for the smallest competing firm / Assume the third firm with the larger market share is left unaffected; it is correct to assume that the smaller of the two firms will be the one who loses business as a result of the donation, as this firm is likely to be the least cost competitive given lower scale and resultant higher cost structure / Donor firm makes a donation bringing its volume from 25 million to 50 million tablets; the resulting market share increases from 18% to 36% / (1) m = 5% / (2) The smaller generic firm’s market share decreases from 27% to 9% (hence RS = 67%) / (3) As F is 80% of total costs, F= 4*V, or V = F/4 / (4) Subsequently, the margin prior to donation can be expressed as follows: / (R – F – V)/R = (R – 1.25*F)/R = 1 – 1.25*F/R = 5% / (5) Subsequently, F/R = 95%/1.25 = 76% / Inserting values computed in (1), (2) and (5) in to formula for new margin: / m* = 5% - (67%/80%)*76% = -58%
[111] Scenario B in Figure 2 relates to a situation in which the Merck Serono donation will cannibalise existing market share of commercial suppliers.
[112] See Grace and Gehl Sampath, In-Kind Donations and Differential Pricing: Assessing the Potential for Market Impact ICIUM Poster 2011: http://www.inrud.org/ICIUM/ConferenceMaterials/969-grace-_a.pdf. Proofs provided in Annex 3.
[113] As stated above, the two commercial suppliers are Cipla and MicroLabs and donated product is provided by Merck Serono.
[114] We know that Sin Pong is willing to accept a 1% profit on 20 million tablets so it is reasonable, in fact conservative, to assume that the generic firm would be making a relatively healthier 5% margin.

In the scenario described, which reflects the reality of the current market situation, the smallest generic firm had its margin reduced from positive 5% to negative 58%. The firm would consequently exit the business. As identified in Grace and Sampath-Gehl 2011, key parameters to consider when thinking about the market impact of a donation are the underlying economics of the business (margins, operating leverage, power imbalances between suppliers) and the nature of the donation (how large it is, how long it will last). Such a significant negative impact results here because a) the economics of PZQ production, whereby margins are thin and volumes required to make a profit are large and b) the size of the donation, which is expected to scale from 25 million tablets per year to 50 million in 2013, a 100% increase. Merck Serono predicts an expansion to 250 million tablets by 2016.

Annex 3. Proofs[115]
[115] See Grace and Gehl Sampath, In-Kind Donations and Differential Pricing: Assessing the Potential for Market Impact ICIUM Poster: http://www.inrud.org/ICIUM/ConferenceMaterials/969-grace-_a.pdf.

Margin (m) is equal to profit [R – (F+V)], divided by revenue (R), where F is fixed costs and V is variable costs. Therefore. the margin can be represented as m = (R – (F+V))/R
- = R/R – (F+V)/R
- = 1 – (F+V)/R
- After reduction in the market share of Rs, Variable costs and Revenue change in the following way:
  - New variable costs:	V* = (1-Rs)*V
  - New revenue:	R* = (1-Rs)*R
- Substituting revenue and variable costs with their new values after the reduction in the market share of Rs, we obtain a formula for a new margin:
  - m* = 1 – (F + (1-Rs)*V)/((1-Rs)*R)
- We can rewrite fixed costs F, as:
  - F = F – Rs*F + Rs*F (where - Rs*F and + Rs*F cancel each other out)
  - = (1-Rs)*F + Rs*F
- Subsequently, we can substitute F in the formula for new margin (m*) with the presentation derived in the previous step:
  - m* = 1 – ((1-Rs)*F + Rs*F + (1-Rs)*V)/((1-Rs)*R)
- We can transform this formula by doing the following:
  - m* = 1 - ([(1-Rs)*F + (1-Rs)*V] + Rs*F)/((1-Rs)*R)
  - m* = 1 – ([(1-Rs)*F + (1-Rs)*V]/((1-Rs)*R + (Rs*F)/((1-Rs)*R)
  - m* = 1 – [(1-Rs)*F + (1-Rs)*V]/((1-Rs)*R - (Rs*F)/((1-Rs)*R
- Focusing on the “bold” part of the above equation, (1-Rs) can be taken out as it is both above and below the dividing line:
  - [(1-Rs)*F + (1-Rs)*V]/((1-Rs)*R = [F + V]/R
- Thus it can be seen that the new margin can be represented as:
  - m* = 1 – (F+V)/R - (Rs*F)/((1-Rs)*R, or
  - m* = m - Rs*F/((1-Rs)*R, as 1 – (F+V)/R is the old margin (m)