Type of Review: Annual Review

Project Title: iiG: Improving Institutions for Pro-poor Growth (Oxford)

Date started: January 2007	Date review undertaken: 28 June 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Improving Institutions for Growth (iiG Oxford) is a DFID-funded Research Programme Consortium (RPC). It was launched for a five year period in January 2007 with an allocation of £2,749,891. In July 2011 approval was given to extend the project to December 2013 and provide additional funding of £1,085,042 to support an extension to the programme’s work. Total funding now stands at £3,834,933. / In addition to DFID, the William and Flora Hewlett Foundation and the Open Society Institute provided funding to the project.

What are the expected results?
Phase 1 / To provide governments and civil society in Africa and Asia, and development agencies, with usable and useful knowledge as to how institutions can be redesigned so as to be more conducive to growth and empowerment. / Phase 1 focused on three themes: / Institutions to promote manufactured exports / Institutions for accountability / Institutions for rural development and empowerment / Phase 1 is produced outputs which include: / An accessible body of research output for skilled policy makers on the themes of the RPC / Accessible, non-technical output based on the research on institutions, growth and poverty. / New comparative and context specific quantitative data sets on institutions. / Strengthened capacity of partner institutions in RPC, especially in Africa, in analyzing the role of institutions and their reform for growth and poverty. / Phase 1 ended in December 2012. / Phase 2 / The research programme extension will study various means by which private sector activity and markets can assist growth and development in Africa, and the institutional constraints affecting this. The research will study three closely-related issues that are central to understanding the potential for market-led development in Africa: / what are the constraints to firm expansion in Africa? Does firm size matter for performance, and how can small firms grow large? / What role does innovation and entrepreneurship play in determining firm success? Can an entrepreneurial class be fostered? / What are the institutional constraints to making markets work better for growth in Africa? Can emerging private markets help to overcome failures in factor and output markets to ensure that markets work for the poor? / The research will focus on a range of projects aimed to provide strong and convincing evidence on these hypotheses. It will, in many cases, build on other work already happening/being funded and use the extensive research network that exists at the Centre for the Study of African Economies (CSAE). / An important part of the work will be to generate papers for dissemination. As well as producing a further 6 to 10 journal articles and 10 to 15 working papers, iiG will develop 3 specific synthesis papers on the three sub-themes.

What is the context in which UK support is provided?
Phase 1 / The following lines from the original submission outline the context in which the decision to fund was first taken: / The programme fits with DFID’s overall objective for research ‘to promote the production and uptake of technologies that will contribute to poverty reduction and achievement of the MDGs’. Nearly 60% of poor people outside India and China live in states affected by conflict or failing institutions. In many countries, public services do not work, states struggle to manage social tensions, and governments fail to secure broad and sustainable development for their citizens. / The evidence increasingly suggests that weak states represent both (i) the biggest challenge to achieving the MDGs and (ii) the greatest potential for increased global conflict and instability. Research on situations where states do not work for the poor is one of the priorities under the Research Funding Framework 2005 – 2007 and builds on some of the earlier work on ‘Drivers of Change’ in countries’ national development and poverty reduction strategies. / Phase 2 / High policy relevance is given to a Private Sector Development research agenda in DFID’s corporate objectives. As set out in DFID’s Structural Reform Plan, under ‘wealth creation’ private sector development has become a key priority. The extension to the programme is focusing on carrying out further work on firm development. Research on firm development has been slower to develop under the existing iiG programme and remains under-researched in general. A series of new opportunities for relevant and high quality research in firm development have been identified. A focus on firms will also complement our overall research programme in the area of growth and developing work on Private Sector Development.

## Section A1[1]: Detailed Output Scoring for Phase 1
[1] In an alteration to the standard Annual Review format, we have repeated section A separately for Phase 1 and Phase 2. Phase 1 is now complete, so section A1 is based on the Project Completion Review template. We also assign a provisional outcome score to Phase 1 in section B – on the basis that after 6 years it’s important to make an assessment of what’s been achieved.

Output 1: Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design.
Output 1 final score and performance description: / A+ iiG has exceeded the key targets under this crucial output by a substantial margin, with a strong publication record underpinned by a large volume of working papers. iiG has also released substantially more data over the last year, comfortably exceeding this target. An A++ was not awarded because a number of papers are still pending and relatively few of the remaining working papers have been submitted to journals.
Final results: / Indicator Target (Dec 2012) Achieved / 1a Number of papers accepted for publication in peer-reviewed journals 30 37 / 1b Number of papers submitted for publication in peer-reviewed journals 10 4 / 2 Number of working papers, book chapters and research reports 25 62 / 3 Number of datasets 3 5 / iiG has exceeded the target for indicator 1 (publication), supplementing the 26[2] papers at last annual review with the 11 below: / Timothy Besley and Torsten Persson, "The Logic of Political Violence", The Quarterly Journal of Economics, 126 (3) August 2011, pp 1411-1445 / Marcel Fafchamps and Pedro C. Vicente. "Political violence and social networks: Experimental evidence from a Nigerian election", Journal of Development Economics, Volume 101, March 2013, pp27-48 / Adrienne LeBas, "Violence and Urban Order in Nairobi, Kenya, and Lagos, Nigeria." in Studies in Comparative and International Development 48:3, forthcoming 2013 / Dercon, S. and Gutiérrez-Romero, R., "Triggers and Characteristics of the 2007 Kenyan Electoral Violence", World Development, 40:4, April 2012. / Gutiérrez-Romero, R., "The Role of Ethnic Identity and Economic Issues in the 2007 Kenyan Elections", Development Policy Review, forthcoming 2013. / Gutiérrez-Romero, R., "Decentralization, Accountability and the 2007 MPs Elections in Kenya", Journal of Development Studies, Volume 49, Issue 1, pages 72-94, January 2013. / Paul Collier · Pedro C. Vicente, "Violence, bribery, and fraud: the political economy of elections in Sub-Saharan Africa", Public Choice, Volume 153, Issue 1-2, pp 117-147, October 2012. DOI 10.1007/s11127-011-9777-z / Timothy Besley and James A Robinson, "Quis custodiet ipsos custodes: civilian control over the military", Journal of the European Economic Association, vol 8 (2-3): pp 655-663, April-May 2010 / Lisa Chauvet, Paul Collier and Anke Hoeffler, "Paradise Lost: The Cost of State Failure in the Pacific", Special Issue of the Journal of Development Studies 46(5) 2010 (Amelia Santos-Paulino, Mark McGillivray and Wim Naudé, eds.) / Paul Collier and Benedikt Goderis, “Commodity Prices and Growth: An Empirical Investigation”, European Economic Review, 56(6), 2012 / Benedikt Goderis and Samuel Malone, “Natural Resource Booms and Inequality: Theory and Evidence”, Scandinavian Journal of Economics, 113(2), 2011 / In addition there are 4 papers at the revise and resubmit stage. Although this pipeline is somewhat below the milestone target of 10, this reflects the fact that the actual publication target has already been exceeded i.e the pipeline has also largely been published! Taken together the two targets have been met. Nevertheless, there should be further submissions in future from among the abundant supply of working papers. / Tessa Bold, Mwangi Kimenyi, Germano Mwabu and Justin Sandefur 'Why did abolishing fees not increase net enrolment in Kenyan public schools? World Bank Economic Review revise and resubmit / Barr, A. and A. Zeitlin 'Dictator games in the lab and in nature: External validity tested and investigated in Ugandan primary schools' JEBO revise and resubmit / Barr, A. and A. Zeitlin 'Conflict of interest as a barrier to local accountability' WBER revise and resubmit / Rocco Macchiavello & Ameet Morjaria, "The Value of Relationships: Evidence from a Supply Shock to Kenya Flower Exports", Revise & Resubmit at American Economic Review, January 2012. / iiG had already surpassed the target for working papers etc. at the last review – and has continued to do so with a further 11 papers: / Oriana Bandiera, Niklas Buehren, Robin Burgess, Markus Goldstein, Selim Gulesci, Imran Rasul and Munshi Sulaiman, "Empowering Adolescent Girls: Evidence from a Randomized Control Trial in Uganda" - December 2012 is the most recent version. / Timothy Besley, Jessica Leight, Rohini Pande and Vijayendra Rao. "The Regulation of Land Markets: Evidence from Tenancy Reform in India". Dept Paper Series EOPP/2011/31, November 2011 / Selim Gulesci, “Labor-Tying and Poverty in a Rural Economy: Evidence from Bangladesh", IGIER working paper no 460, Feb 2012. / Cristina Bodea and Adrienne LeBas, "The Origins of Social Contracts: Attitudes toward Taxation in Urban Nigeria", CSAE Working Paper Series 2013-02 / Gutiérrez-Romero, R. 2012. An Inquiry into the Use of Illegal Electoral Practices and Effects of Political Violence, CSAE working paper CSAE 2012-16 / Tessa Bold, Mwangi Kimenyi, Germano Mwabu, Alice Ng'ang'a, and Justin Sandefur. Scaling-up What Works: Experimental Evidence on External Validity in Kenyan Education. CSAE Working Paper WPS/2013-04, March 2013 / Erlend Berg, Maitreesh Ghatak, R Manjula, D Rajasekhar, Sanchari Roy. "Motivating Knowledge Agents: Can Incentive Pay Overcome Social Distance?" CSAE Working Paper WPS/2013-06, March 2013 / Anke Hoeffler, Syeda Shahbano Ijaz, Sarah von Billerbeck, "Post-Conflict Recovery and Peacebuilding", World Development Report Background Papers 2011 / Anke Hoeffler "Growth, aid and policies in countries recovering from war", OECD Development Co-operation Working Paper 01-2012 / Erlend Berg, Maitreesh Ghatak, R Manjula, D Rajasekhar, Sanchari Roy. "Implementing health insurance for the poor: the rollout of RSBY in Karnataka". Paper No' EOPP 025, March 2011 / Anke Hoeffler and Verity Outram, Need, Merit or Self-Interest – What Determines the Allocation of Aid? CSAE WPS 2008-19. / The following 11 non-peer-reviewed publications (books and book chapters) also counted towards this target: / Special issue of the Oxford Review of Economic Policy, on the Political Economy of Economic Development. May 2009, Oxford University Press. / Stefan Dercon and Pramila Krishnan, “Land Rights Revisited”, in The Microeconomics of Institutions, Tim Besley and Raji Jayaraman (eds.), MIT Press 2010 / Paul Collier and Tony Venables, "Rethinking trade preferences: How Africa can diversify its exports", in 'The World Economy, Global Trade Policy 2007' Ed. David Greenaway. Wiley-Blackwell, Feb 2008. / Gutiérrez Romero, R., Kimenyi, M,. Collier, P. (2009) ‘Elections and Institutions in Kenya’, in Adam, C. Collier, P. (Eds.) Kenya Policies for Prosperity, Oxford University Press, 2010. / Tessa Bold, Mwangi Kimenyi, Germano Mwabu, and Justin Sandefur. “Determinants of Educational Achievement in Kenya since the Introduction of FPE.” in Adam, Collier and Ndung’u, Kenya: Policies for Prosperity, Oxford University Press 2010. / Paul Collier, "Wars, Guns and Votes: Democracy in Dangerous Places". The Bodley Head, 2009. / The Plundered Planet, 2010 OUP and Harper Collins / Timothy Besley and Torsten Persson, "Pillars of Prosperity: The Political Economics of Development Clusters", The Yrjo Jahnsson Lectures series. Princeton University Press. August, 2011. / Robin Burgess, chapter "Liberalization meets investment climate" in CESifo Seminar Series book “Institutional Microeconomics of Development” (edited by Timothy Besley and Rajshri Jayaraman), MIT Press 2010 / Lisa Chauvet, Paul Collier and Anke Hoeffler, "The Cost of State Failure and the Limits to Sovereignty" in "Fragile States: Causes, Costs, and Responses" Naudé, W.A., Santos-Paulino, A. and McGillivray, M. (eds) Oxford University Press / Benedikt Goderis and Christopher Adam, “Monetary Policy and Oil Price Surges in Nigeria” in "Economic Policy Options for a Prosperous Nigeria", Paul Collier, Catherine Pattillo and Charles Soludo (eds.), Palgrave Macmillan 2008. / iiG has exceeded the target for data with the release of 5 datasets and created a new data section of the website where they can be easily found. It had already published a dataset from Kenya on its website and while the original datasets for Bangladesh and Ethiopia are unlikely to be available soon, iiG has provided additional datasets from other projects. iiG confirmed that it would move to publish datasets wherever possible from phase 1 – DFID authorised the use of unspent funds[3] to clean, anonymise and release further data - with candidates for rapid release including 2 political economy projects in Nigeria and Uganda/Tanzania education work. / The overall picture therefore is one of a project that has comfortably exceeded its targets. Two issues however, do warrant some comment. The first is that despite good performance overall, there have been a number of non-performing and underperforming projects. Of the 48 projects that make up Phase 1, 9 have produced no output while a further 7 have produced intermediate outputs only i.e. datasets, presentations and reports but no working paper. The remaining 32 have delivered their outputs in full. / In terms of value, of the £2.2m allocated to sub-projects (rather than spent on programme-wide activities): / £25k was spent on abortive projects (7) / £67k was spent on projects that are delayed and yet to produce any output (2) / £158k was spent on projects that are delayed and yet to produce a working paper (but have delivered intermediate outputs) (7) / Most of the abortive fieldwork (4 sub-projects) was stopped before any money was spent. The bulk of the £25k loss is accounted for by one project abandoned in 2010 when it became clear that the policy under evaluation would not be implemented. The remaining projects are expected to deliver working papers albeit later than planned. While DFID will not review the score for Phase 1, iiG should continue to monitor and report progress on these outputs in subsequent annual reviews. / This relates to the second point, on monitoring outputs. iiG has among the most well developed output tracking systems in use by GRT programmes. Nevertheless, there was some confusion during the review of how many outputs there were and how many qualified under the various categories. Some mature outputs came to light for the first time this year, while others were re-classified. This indicates a failure to maintain the records in some cases. The output database has now been improved so that it is clear which outputs qualify (as opposed to records of incomplete outputs) and under which indicator(s) each output is included. It will be important for iiG to continue to use this enhanced tracker in future so that identifying further progress is a straightforward exercise. / Recommendations: / Continue to monitor and report progress using the enhanced output tracker. / Impact Weighting (50%): / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[2] 29 papers were reported at last Annual Review but 3 of these have been reclassified as they only qualify under indicator 2, not indicator 1, being published in collected volumes rather than journals
[3] The evaluation has first call on these funds – any remainder will be used to release data.

Output 2: Strengthened capacity of partner institutions in RPC in analyzing the role of institutions and their reform for growth and poverty.
Output 2 final score and performance description: / A iiG greatly exceeded the target for working papers, but just missed the target for journal publication, leading to an ‘A’ overall.
Final results: / Indicator Target (Dec 2012) Achieved / 1a Number of papers with co-authors from partner institutions published in peer reviewed journals, book chapters and in working paper series 10 18 / 1b Of which: number of papers with co-authors from partner institutions published in peer reviewed journals 4 3 / On this indicator the situation remains unchanged since last year. iiG produced many more papers co-authored with partner institutions than the target but just missed the publication target[4]. This serves to underline the very low publication rate of these papers relative to iiG’s output overall, where over half of papers make their way to journals. / A number of co-authored papers remain in the pipeline and iiG should continue to monitor progress. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[4] One paper with a co-author from a partner institution remains at the revise and resubmit stage.

Output 3: Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design, with a clear gender dimension
Output 3 final score and performance description: / N/A This target was introduced for Phase 2 (see below). For scoring purposes Phase 1 was treated as achieving an ‘A’ for this output, which is commensurate with the fact that it has delivered a number of outputs on women’s economic and political empowerment, despite not having this explicit objective.
Final results: / No target for phase 1, but it has nevertheless delivered a series of papers and other outputs with a gender component: / Papers: / Female empowerment through inheritance rights: Evidence from India, Sanchari Roy, CAGE working paper series, University of Warwick, no. 46, July 2011 / Intentions to participate in adolescent training programs: Evidence from Uganda, Oriana Bandiera, Robin Burgess, Markus Goldstein, Selim Gulesci, Imran Rasul and Munshi Sulaiman Journal of the European Economic Association, Wiley, vol. 8, Issue 2-3, pages 548-560, April/May, 2010. / Data: / Elections, ethnic polarization and managing post-electoral conflict in Kenya: dataset from Kenyan pre-election survey, Dec 2007, disaggregated by gender. / Evaluating the Impact of Relief Teachers on Academic Achievement in Kenyan Primary Schools – data on teachers & students disaggregated by gender / Policy brief: / iiG Policy Lesson 02, ‘Gender and Growth: Empowering women in the process of development’, March 2012 / These are the same outputs referred to in last year’s annual review; while there has been no advance since then, a number of outputs remain in the pipeline and iiG should monitor their completion. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 4: Effective communication of research outcomes
Output 4 final score and performance description: / A++ iiG had already exceeded all targets under this output and has continued to improve, justifying a top score.
Final results: / Indicator Target (Dec 2012) Achieved / 1 Number of briefing papers on research outcomes 20 28+4 / 2 Number of workshops with at least 5 relevant stakeholders 6 22 / 3 Project website, kept up to date All briefing papers, data and research papers available on website in structured form. Yes / iiG is far exceeding both the briefing and workshop targets. In addition to the 23 briefing papers produced at last review, iiG has completed a further 5: / "Do the Nigerian public trust their police?", iiG Briefing Paper 21, December 2012 / "Attitudes towards citizenship in Nigeria", iiG Briefing Paper 22, December 2012 / "Understanding electoral violence: Lessons from Kenya", iiG Briefing Paper 23, December 2012 / Stefan Dercon, Ruth Vargas Hill, Daniel Clarke, Ingo Outes-Leon, Alemayehu Seyoum Tafesse, "Offering rainfall insurance to informal insurance groups: evidence from a field experiment in Ethiopia", BREAD Policy Paper 032, November 2012 / "Encouraging tax compliance in the informal sector", iiG Briefing Paper 24, May 2013 / These have been disseminated at conferences and are available on the website together with the 4 longer policy lessons papers. / The target for workshops had already been exceeded at last review. Since, a further four events have been held: three policy seminars at DFID as well as a workshop on tax in Nigeria. / The website has been improved with a clear structure – including a data section - and is kept up-to-date with the latest outputs. Some older links appear to be broken and need to be updated. A final improvement to the site will be to ensure that outputs can be accessed regardless of the route used e.g. Kenya elections data should appear both on the data page and the Kenya elections page. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section A2: Detailed Output Scoring for Phase 2

Output 1: Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design.
Output 1 score and performance description: / C While publishing one article and its dataset very rapidly, Phase 2 has yet to produce any working papers. This is below the minimum performance level expected (of 3).
Progress against expected results: / Indicator Milestone (Dec 2012) / High/Med/Low Achieved / 1 Number of papers accepted for publication in peer-reviewed journals 5/2/0 1 / 2 Number of working papers, book chapters and research reports 8/6/3 0 / 3 Number of datasets 2/1/0 1 / iiG has scored some quick wins in Phase 2, publishing the below journal article and releasing the accompanying dataset: / Ali, D. A., Dercon, S. and Gautam, M. (2011), Property rights in a very poor country: tenure insecurity and investment in Ethiopia. Agricultural Economics, 42: 75–86. doi: 10.1111/j.1574-0862.2010.00482.x / However, iiG has failed to produce any working papers, which reflects something of a hiatus in fieldwork over the last year. The delay has been for two main reasons: / Unforeseen personnel changes: DFID’s recruitment of the previous Research Director and the retirement of his successor. / Delays to fieldwork: policies and programmes due to be studied had themselves been delayed, and in two cases cancelled outright / Recommendations: / While these delays are disappointing, DFID believes that the good performance of Phase 1 and the sunk investment in Phase 2 fieldwork justifies an 18-month no-cost extension to the programme (until June 2015) to allow this work to be completed, on the basis of the following measures: / Contract amendment to formalise the change of Research Director and the new Assistant Research Director role / TORs for the Research Director, Assistant Research Director and Admin Officer to clarify roles, assigning oversight for each research project to the RD or ARD / iiG should produce a back-up list of 2 or 3 research projects in case of further delays to fieldwork beyond its control. These should be within the thematic scope of Phase 2 or could include follow-up activities from Phase 1 projects. In December 2013 iiG will provide a progress report on the status of the 8 projects, and agree any final changes to the work programme with DFID. / A bar on new fieldwork commencing in the last 18 months of the programme (i.e. after December 2013) / The risk rating of this output and the programme overall will be raised to medium. / iiG and DFID will agree a revised work programme, logframe and financial forecast to reflect the extended schedule. / Impact Weighting (50%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y

Output 2: Strengthened capacity of partner institutions in RPC in analyzing the role of institutions and their reform for growth and poverty.
Output 2 score and performance description: / B Phase 2 has yet to produce any working papers co-authored with developing country researchers[5], placing it at the minimum performance level expected.
Progress against expected results: / Indicator Milestone (Dec 2012) / High/Med/Low Achieved / 1a Number of papers with co-authors from partner institutions published in peer reviewed journals, book chapters and in working paper series 2/1/0 0 / 1b Of which: number of papers with co-authors from partner institutions published in peer reviewed journals 1 0 / See above – this refers to a subset of Output 1, so it would be impossible to score well on this output given a poor score there. Having said that, the level of ambition on this output was significantly lower; it was anticipated that no papers might be produced by now, so it is fair to assign a ‘B’. / Recommendations: / As for output 1. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[5] Phase 2 does not involve any partner institutions, so for Phase 2 the interpretation of the output is the number of papers written in collaboration with developing country (LIC or MIC) researchers.

Output 3: Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design, with a clear gender dimension
Output 3 score and performance description: / B Phase 2 has yet to produce any working papers with a clear gender dimension, placing it at the minimum performance level expected. / Progress against expected results: / Indicator Milestone (Dec 2012) / High/Med/Low Achieved / 1 Number of papers with a clear gender dimension published in peer reviewed journals, book chapters and in working paper series 5/2/0 0
See above – this refers to a subset of Output 1, so it would be impossible to score well on this output given a poor score there. Having said that, the level of ambition on this output was significantly lower; it was anticipated that no papers might be produced by now, so it is fair to assign a ‘B’. / Recommendations: / As for output 1. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 4: Effective communication of research outcomes
Output 4 score and performance description: / C Phase 2 has yet to produce any briefing papers. This is below the minimum performance level expected (of 2).
Progress against expected results: / Indicator Milestone (Dec 2012) / High/Med/Low Achieved / 1 Number of briefing papers on research outcomes 6/4/2 0 / 2 Number of workshops with at least 5 relevant stakeholders 2/1/0 0 / 3 Project website, kept up to date All briefing papers, data and research papers available on website in structured form. Yes, but see recommendations / iiG has not produced any communications or dissemination material under Phase 2. The potential output was obviously limited by the lack of underlying research outputs making it impossible for iiG to achieve the minimum standard. / Therefore, no new recommendations have been made specific to communications, although we do reaffirm the agreement at last Annual Review that 2 of iiG’s future policy briefs will cover: / Gender aspects of private sector development / Poverty and job creation / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money

1. Progress and results
Overall summary of progress/results and guide to amended template / Overall output score: / A Across the two phases, iiG exceeded its milestones on all outputs. We have highlighted the internal variation that underlies that good overall performance below. / This Annual Review is made up of two distinct halves. It is effectively the Project Completion Review of iiG Phase 1 while also containing the first Annual Review of iiG Phase 2. The character, timing and performance of the two Phases is quite distinct so it seemed logical to do separate output scoring exercises for the Annual Review narrative above. However, ARIES[6] cannot record separate scores for the two phases but simply a project-wide score for each output and finally the overall score. The table below shows the two alternative breakdowns of the overall score. All aggregate scores (the 100% column and row) were generated by the project score calculator. / Output Impact weighting Phase 1 Phase 2 ARIES score by output / Impact weighting 72% 28% 100% / 1 50% A+ C A / 2 10% A B A / 3 15% N/A B A / 4 25% A++ C A+ / Overall output score 100% A+ C A / Outcome score A+ N/A N/A / 'N/A' scores Phase 1 did not contain output 3. Scoring options were to use different weightings for the two phases, or to use consistent weightings and treat phase 1 as scoring a de facto 'A' on output 3. That is the approach we followed when assigning the overall ARIES score. For an explanation of the outcome scores see below. / We regard the overall output score for Phase 1 as final. It will not be reviewed at Project Completion Review in 2015 but simply added to Phase 2’s final score to produce the overall output score for the whole project. Nevertheless, iiG should continue to monitor any further outputs from Phase 1 according to the enhanced system recommended in this review and include them in its final report in 2015. / By contrast, the outcome score we have assigned to Phase 1 is provisional. No outcome score will be entered in ARIES. Phase 1’s body of output will be included in an external evaluation of iiG to be commissioned next year in advance of the 2015 Project Completion Review to assess the overall impact and outcomes from its work. The 2014 Annual Review will focus on Phase 2 only i.e. the overall output score will be based on Phase 2 output scores alone. / Section 1 has been amended to: / Split some headings by phase / Add Project Completion Review headings for phase 1 / 1.1 Has the logframe been updated since last review? Y / The logframe was updated at last review which involved refining some of the indicators. The logframe has again been amended as part of this Annual Review – this time there has been no change to the indicators to be monitored, but the milestones and targets have been revised to match the extended schedule to June 2015. DFID and iiG will sign off on a final logframe after the Annual Review. / 1.2a Final Output Score and Description for Phase 1: / A+ Phase 1 performed well, substantially exceeding all major targets, and reflected also in work not captured by the logframe, in particular the close engagement with policymakers that has underpinned iiG’s success at translating these findings into action. An A++ was not awarded because a number of papers are still pending and relatively few of the remaining working papers have been submitted to journals. / 1.2b Overall Output Score and Description for Phase 2: / C Despite some early successes the bulk of Phase 2 activity has experienced a significant hiatus due to implementation problems on the ground and personnel changes at the centre. As a result, after two years only one sub-project has delivered any outputs. / 1.3 Direct feedback from beneficiaries / Questionnaires about Phase 1’s findings and impacts were circulated to all research teams and the responses form the basis for reporting on outcomes, impacts and sustainability.
1.4 Summary of overall progress of Phase 2 / Phase 2 is off track but new measures have been agreed to revise the work schedule, extending it by 18 months, formalise the process for any further changes, improve clarity of roles and enhance monitoring. Progress over the next year will be monitored closely.
1.5 Key challenges for Phase 2 / The key challenges for phase 2 now are to complete the actions recommended in this Annual Review. While both personnel and fieldwork risks remain, the new measures should address these if they are implemented fully and faithfully. Success will be judged by the outputs generated by June 2014.
1.6a Annual Outcome Assessment for Phase 2 / Indicator Milestone (Dec 2012) Achieved / 1 Number of major policy changes related to institutional design in the context of growth and poverty reduction. 2/1/0 0 / 2 Number of cases of significant impact on institutional design debates in the areas of the programme: / - firm development and exports 2/1/0 0 / Clearly in the absence of many outputs it is impossible for iiG to begin to influence debates or change policy. While iiG was set a zero minimum milestone for outcomes this year to reflect the delay in translating research outputs into policy practice, the delay in producing those outputs reduces time for dissemination and uptake activity. The extension should create space for iiG to achieve some substantial successes in this area before the programme completes in 2015, but it will be important for iiG to integrate uptake work into its activity from now on to ensure this takes place, drawing on DFID’s new research uptake guidance. / 1.6b Overall Outcome Score for Phase 1 / A+ iiG has exceeded the key targets under this crucial output by a substantial margin, with a strong publication record underpinned by a large volume of working papers. iiG has also released substantially more data over the last year, comfortably exceeding this target. An A++ was not awarded because a number of papers are still pending and relatively few of the remaining working papers have been submitted to journals. / Indicator Target (Dec 2012) Achieved / 1 Number of major policy changes related to institutional design in the context of growth and poverty reduction. 3 4 / 2 Number of cases of significant impact on institutional design debates in the areas of the programme: / - governance and accountability / - firm development and exports / - institutions for inclusive growth in poor settings 5 11 / Over its lifetime iiG has achieved 4 major policy changes. / Work on trade preferences was influential in securing more liberal rules of origin under the Economic Partnership Agreements between the EU and African, Caribbean and Pacific countries – in particular the single transformation rule for garments. / A paper on economic liberalisation in India has added considerably to debate in media and in policy circles on the nature of labour regulation and its consequences in India. / Evaluations of India’s RSBY health insurance scheme succeeded in influencing the future contract design of the scheme. In particular, research findings had shown low levels of take-up amongst the poor covered by the scheme. This was partly because the concessionaire insurance companies implementing the scheme had no incentive to provide information to ensure it was actually utilised. The design has now been altered so that the premium paid to the insurance concessionaire falls if utilisation falls below a certain rate. / iiG researchers worked with the Board overseeing the Constituency Development Fund (CDF) in Kenya to analyse its activites for the first time. The findings offered several recommendations to the Board on how the CDF could be modified, some of which were later implemented, in particular the suggestion that a stricter monitoring system on how MPs spend their CDF allowance be implemented. / In terms of influencing debates at the last review 5 clear examples were: educational reform in Kenya; agricultural strategy in Ethiopia; press coverage of and the Lagos State Government’s engagement with iiG’s findings on security in Lagos; Indian press reports of iiG’s findings that the rural work guarantee (NREGA) is a potentially important anti-poverty tool.”, and iiG’s work on education in Uganda which culminated in seminars with the participation of ministers and senior officials, as well as detailed press coverage. / A further 6 examples of influence seem to be clear as Phase 1 draws to close. Findings from several sub-projects were used in a thematic paper on supporting the OECD project ‘Global Factors Influencing the Risk of Conflict and Fragility’ and presented widely to policy for, as well as being cited in the IMF’s World Economic Outlook[7]. / Findings from iiG research into the 2007 elections in Nigeria influenced the design of NGO voter education projects around the 2011 elections[8]. / The President of Kenya, Mwai Kibaki, welcomed and praised iiG research conducted in Kenya before and after the disputed elections of 2007, particularly suggestions on the policies that could be implemented to prevent electoral conflict from recurring[9]. The President mentioned the work in several interviews he gave to the media[10]. / Project findings on the aspirations of rural Ethiopians informed the design of a $20m development programme called Graduation with Resilience to Achieve Sustainable Development (GRAD) by the NGO CARE. If successful, this will have implications for the redesign of the Ethiopian Productive Safety Net Program (PSNP) with an annual budget of about US$400 million. / iiG findings on the need to supplement microfinance in Bangladesh with other interventions received supportive comments from by Dr. Atiur Rahman, Governor of Bangladesh Bank, in remarks published on the website of Bangladesh Bank[11] and in The Financial Express[12]. / Finally, iiG researchers worked closely with the free Mozambican newspaper A Verdade, which published the findings of iiG research on electoral observation and voter education using mobile phones in their anniversary edition[13] achieving international press coverage from Time Magazine[14]. Most importantly, the hotline and ushahidi[15] platform that was designed in 2009 was adopted by the newspaper on a number of occasions[16]. / 1.7 Impact and Sustainability / While the impact in the logframe simply asks us to monitor poverty rates, the real question about impact is whether the policy changes referred to in section 1.6b led to real improvements in the lives of the poor. This assessment needs to be made as part of the external evaluation in 2015, once the policies themselves have had some time to have impact, and will always be a tentative exercise. / Nevertheless, we might reflect that even positive and promising policy changes can fail to deliver results. There is little evidence that the African garment industry has benefited greatly from the Economic Partnership Agreements – an area the CSAE continues to actively research[17]. The dismantling of the licence raj continues to be a perennial debate in India[18] while it will take time to assess whether the changes to RSBY have improved health outcomes for the poor. / In terms of sustainability there are three encouraging examples of collaboration with local partners that is likely to continue after DFID funding comes to an end. In relation the work on monitoring school performance in Uganda, as of 2013 the Ministry of Education and Sports has begun to implement schemes along the same lines of the original iiG intervention, where communities monitor schools according to the criteria they believe to be important. / Meanwhile the Ethiopian government has shown substantial interest in iiG’s work on vocational training in India to the point of commissioning some exploratory work itself on similar lines. / Finally, iiG’s close engagement with the Lagos State Government has led to an emerging research partnership. Governor Fashola has stated that he wishes to build survey research in to the heart of the policy process of the Government. An integrated research-policy programme will run for two years from early 2013, with a budget of around $180,000, and will ensure that the partnership between iiG and the Government lasts well beyond the period of DFID-funded activity
[6] DFID’s project management database
[7] Chapter 5 of World Economic Outlook, April 2008. OECD background report available here, contributing to the main report “Think Global, Act Global: Confronting Global Factors Influencing Conflict and Fragility”
[8] http://www.actionaid.org/nigeria/stories/actionaid-launch-action-against-electoral-violence-nigeria
[9] These policies were summarised in a book chapter written by Paul Collier, Roxana Gutiérrez-Romero and Mwangi Kimenyi “Elections and institutions in Kenya”, in Christopher Adam, Paul Collier, and Njuguna Ndung'u (Eds.) Kenya Policies for Prosperity.
[10] ‘Kibaki says New Constitution Key to Nation’s Growth’ Daily Nation, 9 February 2011, Kenya. ‘Kenya on the path of transformation, says Kibaki’, TV Broadcasting Corporation, 9 February 2011, Kenya.
[11] http://www.bangladesh-bank.org/governor/speech/dec182011gse.pdf
[12] http://www.thefinancialexpress-bd.com/more.php?news_id=143217&date=2011-12-19
[13] http://www.verdade.co.mz/nacional/13629-estudo-acerca-de-educacao-civica-eleitoral-em-mocambique
[14] http://www.time.com/time/world/article/0,8599,2039433,00.html
[15] See ushahidi.com
[16] the 2009 elections; the riots in 2010; now at http://www.verdade.co.mz/cidadaoreporter/
[17] See for example: www.csae.ox.ac.uk/workingpapers/pdfs/csae-wps-2012-12.pdf
[18] http://indiatoday.intoday.in/story/licence-raj-redux/1/280409.html

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / No. While Phase 1 is now complete and largely concluded as planned (with a small underspend of £10,539) Phase 2 has spent at about half the rate planned (£0.26m relative to £0.5m originally forecast) over the past year due to slow progress in implementing fieldwork. Activity was also suspended for the first 3 months of 2013 while the Annual Review discussions were taking place. DFID is granting an 18-month extension and iiG submitting a revised financial forecast through to June 2015. / 2.2 Key cost drivers / The key cost driver is (direct) research costs (i.e. fieldwork). / 2.3 Is the project on-track against original timescale: N / Phase 1 concluded broadly on-track, although continuing fieldwork (funded by other organisations) has delayed delivery of papers by 9 of the 48 sub-projects (about 10% of the programme in terms of value). / Phase 2 is severely delayed with 3 of the 10 sub-projects cancelled outright. The remaining 7 have been revised and rescheduled and a substitute introduced so that the Phase 2 portfolio is now made up of 8 projects with a total value (direct research costs only) of approximately £580,000. There is now a formal system for any further changes to the programme, which involves working sequentially down a list of preferred back-up projects should the need arise in 2013, while from January 2014 projects that experience further delays will be cancelled outright. / The project life has been extended by 18 months to complete the second phase of work focusing on the private sector until June 2015.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No new evidence is available that fundamentally challenges the rationale for this research programme / 3.2 Where an evaluation is planned what progress has been made? / The independent peer review of iiG outputs was not carried out as part of this Annual Review process; iiG in any case exceeded its target for peer reviewed outputs so paying for peer review of the remaining output simply for quality assurance did not appear justified. However, while Phase 1 was not originally resourced for an evaluation the £15,000 underspend creates an opportunity for iiG to commission a more ambitious exercise, comprising: / Expert review of a sample of outputs, including both journal articles and working papers / Assessment of iiG’s body of outputs as a whole – the extent to which these cohere and correspond to the original research framework / Assessment of iiG’s influence on policy and popular debates, and the extent to which the evidence it generated contributed to changes in policy or practice / A tentative assessment of whether the policy changes have led to real improvements in the lives of the poor / This review will be a comprehensive assessment of Phase 1 and Phase 2 taken together. iiG and DFID will agree a plan for commissioning this evaluation over the next year, but it should be carried out from July-December 2014, in good time for the iiG Project Completion Review.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / It is clear that a number of serious problems have hampered delivery over the past 12 months. The risk rating should therefore be raised to MEDIUM overall. Specific risks whose ratings have been revised below appear in italics; steps taken for mitigation listed here repeat the measures listed under Output 1. / Risk Probability Impact Comments/Revisions / iiG fails to gain access to high-level policy makers LOW HIGH / Key policymakers targeted by the programme cease to be influential. LOW HIGH / Insufficient time available for core research as well as writing papers. LOW LOW See below on delays to data collection and analysis: the impact rating should be raised to HIGH and the probability to MEDIUM. / Data collection and analysis delayed (due to external constraints e.g. project to be studied itself delayed) LOW LOW This risk has befallen the project and led to serious problems so the impact rating should be raised to HIGH. To mitigate this risk: a) the most problematic projects have been cancelled, b) a backup list of projects has been produced that iiG will pursue (with DFID's agreement) if there are any further delays to fieldwork on the remaining projects, and c) DFID has introduced a bar on new fieldwork commencing after 2013. In the light of these measures, the probability should be raised, but only to MEDIUM. / Co-authors from participating institutions cease to be involved or there is high CSAE staff turnover. LOW LOW CSAE staff turnover has been high with iiG currently on its fourth research director, and particularly since Stefan Dercon's departure for DFID. The impact on the project has been HIGH which should be the new rating. iiG have created an Assistant Research Director role to strengthen central oversight of the project and as part of this Annual Review DFID and iiG are agreeing the following measures to mitigate this risk in future: a) terms of reference for staff under the new structure, b) contract amendment to formalise this change and c) each project is assigned to one staff member who is responsible for oversight of that project. Given this should help to clarify roles and responsibilities and reduce the risk of further change in the programme's last 2 years, the probability rating should be MEDIUM. / Those whose skills were developed in terms of briefing paper writing cease to be involved in RPC. LOW LOW / Research does not produce any findings that are worthy of communication (i.e. the research is carried out properly but can't produce conclusive results) LOW LOW
Risk of funds not being used as intended / We judge the risk of iiG itself misusing DFID funds to be low: the University of Oxford is a known and trusted partner and an exempt charity regulated by the Higher Education Funding Council for England (HEFCE). The University has a well-developed risk management framework involving a series of internal controls and underpinned by annual external audit in line with HEFCE guidance. / As an additional safeguard, during financial year 2013/4 a DFID accountant will meet with project officers to discuss the University of Oxford’s new accounting system to confirm that it meets DFID’s requirements and conduct a follow-up visit to confirm that financial data is being reported adequately. / 4.4 Climate and Environment Risk / Climate change and environment risks and impacts: C (no/low risks) / Climate change and environment opportunities: C (no/low opportunities)

5. Value for Money
5.1 Performance on VfM measures / While no VFM measures were agreed for Phase 1, DFID performed an internal assessment in early 2013 by combining iiG’s earlier reporting with Google Scholar citation records and the results are worth including here. They found that iiG achieved an h-score of 18, meaning that it had produced 18 journal articles that had been cited at least 18 times. While there are few h-scores available for programmes of similar scale and maturity, this is a healthy result (some much larger programmes achieve similar scores). / Because of the extent of blending of funds with other donors at the sub-project level (i.e. researchers seek support from others beyond iiG) we cannot report any cost-effectiveness metrics in terms of full research costs but simply the DFID investment. That makes programmes where DFID is a substantial funder appear expensive relative to large pooled funds. The “cost to DFID” per journal article under iiG Phase 1 was £86,000 while the cost per article with 10 citations or more was £138,000 (see figure 1). We estimate that this reflects around half the full research cost. The fact the curve is quite flat indicates that iiG’s output is quite balanced: citations are not particularly concentrated in a small subset of papers. / The inclusion of working papers would make iiG’s output appear rather cheaper (about half the cost at the zero citations bar) but rather less balanced (i.e. few working papers garner lots of citations). / We intend to repeat this exercise for Phase 2 for which a full breakdown of research costs by sub-project will be available. / 5.2 Commercial Improvement and Value for Money / iiG’s regular financial reporting includes breakdowns of expenditure by category and (for Phase 1) by partner organisation. iiG have reconstructed a breakdown of direct research costs by sub-project for Phase 1 to allow us to perform some of the analysis for this Annual Review, but were not originally asked to keep accounts with this structure. / However, in October the University will introduce a new accounting system which will allow Phase 2 accounts to be structured by sub-project, making value for money calculations simpler in future. / More broadly, all procurement of goods and services by the University must be in accordance with the purchase to pay processes drawn up by the Finance Division. These require that the university seek value for money from suppliers for all purchases, with a tender process stipulated for purchases above £25,000 which must be carried out by the Purchasing Office for transactions over £100,000. / 5.3 Role of project partners / No longer active. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take? / Yes overall, but see the extensive actions agreed in part 7. / Fig. 1: Cost to DFID per iiG paper achieving x citations / Cost per paper / Citations per paper

6. Conditionality
N/A

7. Conclusions and actions
Excellent performance in Phase 1 has convinced DFID of the value of continuing a substantially revised second phase of iiG. This on the basis of the following actions: / Contract amendment to formalise the change of Research Director and the new Assistant Research Director role / TORs for the Research Director, Assistant Research Director and Admin Officer to clarify roles, assigning oversight for each research project to the RD or ARD / iiG should produce a back-up list of 2 or 3 research projects in case of further delays to fieldwork beyond its control. These should be within the thematic scope of Phase 2 or could include follow-up activities from Phase 1 projects. In December 2013 iiG will provide a progress report on the status of the 8 projects, and agree any final changes to the work programme with DFID. / A bar on new fieldwork commencing in the last 18 months of the programme (i.e. after December 2013) / The risk rating of this output and the programme overall will be raised to medium. / iiG and DFID will agree a revised work programme, logframe and financial forecast to reflect the extended schedule. / DFID will visit iiG/University of Oxford project teams twice during FY2013/4 to discuss and monitor financial reporting / Financial records for phase 2 will allow a full breakdown of research costs by sub-project. / iiG will use the enhanced output tracker to monitor and report results from now on. / On the website: iiG will ensure that old links are maintained (some are currently broken) and that output is available both via the ‘Research’ tab i.e. by research project and by the ‘Output’ tab i.e. by output type. / DFID and iiG will from now on hold regular quarterly progress meetings / DFID and iiG will agree measures to adopt as fully as possible new DFID guidance on open data access and research uptake

8. Review Process
The Annual Review process this year has been extensive. A team composed of DFID advisers and project officers led by the Growth Research Team first met iiG staff in November 2012 and there has been a number of rounds of discussion and negotiation, with iiG resubmitting a number of documents several times. / Both parties have learnt from the process and delivered, in June 2013: / a complete, coherent and faithful record of iiG’s achievements to date, including an enhanced output tracker that links all outputs to the logframe indicators / a complete financial record for Phase 1, with a partial breakdown by sub-project to improve value for money analysis / a clear plan for Phase 2 including a revised output schedule, a clear procedure for adjusting that schedule, a revised financial forecast and enhanced financial reporting arrangements / It will be important for both DFID and iiG to maintain this standard of reporting and management in future, which will also ensure future reviews will be short, efficient processes. Annual Review 2014 will run from April to May with a single round of submission. / DFID and iiG have been meeting quarterly during the Annual Review process and it will be useful to maintain this regular contact to monitor progress and agree any actions in relation to the plans set out above. This recommendation has been reflected in section 7.