Type of Review: Annual Review

Project Title: GDNet - Research Communication from and for the Global South

Date started: 1st May 2007
Date review undertaken: 29th – 30th April 2013

Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
GDNet is a Knowledge Initiative, which brings together and communicates policy-relevant research from the Global South. It has over 12,000 members (researchers from developing and transition countries) to whom it provides access to online journals, grey literature and other research documentation, data and access to information about research funding. GDNet supports southern researchers in making their research accessible and available to a global audience and strengthens their research communication capacity through training. It aims to be an internationally recognised organisation for sharing knowledge on development research to inform policy debate. GDNet is a partnership with regional networks and leading experts in the field. GDNet also receives funding from the World Bank.

What are the expected results?
The programme’s aim is to impact on research and policy audiences who will make better use of development research from the south. The longer term objective of the programme is contribute to ensuring that better policy for achieving poverty reduction is informed by better research. The programme aims to deliver on four results: / Southern research are better informed by current ideas and knowledge / Researchers are better able to communicate their research to policy / Knowledge networking between researchers and with policy actors is increased / Lessons about knowledge brokering best practice in the global south are learnt and communicated

What is the context in which UK support is provided?
Researchers in developing and transition countries (often referred to as “the South”) have valuable knowledge to contribute to decisions being made about development in their countries and elsewhere. However they face several challenges in being heard by government staff and other people involved in policy-making, such as lacking the confidence and ability to communicate their research effectively, or lacking access to the academic journals they need in order for their research to be published. DFID funds GDNet to build capacity of researchers to help them produce and share their research findings to reach as wide an audience as possible so that development decisions are more likely to be informed by the best available local knowledge. DFID, through its Research and Evidence Division, has a specific mandate and policy commitment to strengthen the science, innovation and research environment in the South.

## Section A: Detailed Output Scoring

Output 1: Southern research better informed by current ideas and knowledge
Score: B: The output moderately did not meet expectation / Progress against output 1 was varied. There was some significant progress in level of visitors as demonstrated by web analytic indicators. However there was a continued decline in use of e-journals. Finding relevant information to assess progress on this output was challenging and the programme could have done more to pull out and analyse relevant figures for the review period. The level of satisfaction with GDNet research oriented services continues to be high however the indicator of an increase in satisfaction of 5% was not met. The GDNet knowledge Base now represents a sizeable collection of southern global public good research. / Progress against expected results: / Indicator 1: Level of use of and satisfaction with GDNet research oriented online services / Baseline1.1: Level of use by male and female users (GDNet webstats available from 2010 GDNet Users web survey) - 23,617 visitors per month, of which 33% come from the Global South / Milestone 1.1 for this review: 10% year-on-year increase in use / This milestone was comfortably exceeded for the period of this review. There was a 51% increase in visitors on the baseline by December 2012, and more notably, a 31% increase between the first quarter of 2012 and the first quarter of 2013 (a comparable period). Average number of visitors per month was 34,709 by December 2012 and 47,425 for the quarter ending March 2013. / In 2012, visitors from the South averaged 11,169 per month, an increase of over 40% on the baseline. In the first quarter 2013, approximately 13,500 visitors per month were from the South, the highest numbers achieved to date and an 11% increase on the first quarter of 2012. However, the proportion of all visitors from the South has fallen. The review team did not feel this significant enough to merit concern, given the absolute number of Southern visitors has continued to increase steadily. In addition, there are questions around the reliability of webstats to measure location, as location information only relates to server location. The programme team also felt that the webstats may indeed reflect the balance of effort, as one of the implicit aims of the programme is for northern users to make better use of southern research information. The ‘Connect South’ campaign for example has probably also contributed to this trend. / Although webstats are difficult to triangulate, they do provide useful monitoring information for the project. One single measure does not represent a sufficient picture of how the programme is progressing, so this programme, like many others, relies on presenting a collection of statistics gathered on a monthly basis. Overall, there is an upward trend in webstat figures, which reflects additional effort on attracting traffic to the site via social media (e.g. Linkedin and twitter), the newsletter, and one-to-one contact. / Additional notable progress includes: / The GDNet Knowledge Base now contains approximately 20,000 documents and abstracts, which represents a considerable repository of Southern research. / Abstracts for over 2,000 documents were added to the Knowledge Base from January to December 2012. / There were over 333,000 abstract views from Jan-Dec 2012, which represented over 1,000 document views per working day: the only way abstracts can be viewed is by clicking onto the abstract link or landing on the abstract link page (via a Google or Yahoo search for example). / The number of new Southern organisation profiles made available on the site has more than doubled – from 15 per month to 33 per month. 396 research organisation profiles were added during 2012 / GDNet continues to rank well on search engines compared to similar service providers including Eldis and Development Gateway[1]. / However, the review team were disappointed that certain recent (Q1 2013) indicators of progress had not been identified by the programme team to highlight in the review. Indeed, though Q1 stats for visitors from the South were immediately to hand, these had yet to be included in any monitoring document and weren’t presented unprompted. Some time was spent discussing whether the number of Southern visitors was static or even falling before the upward trend in the latest quarter was belatedly established by the review team. Therefore, in future, the programme team should make more of an effort to analyse and present key information more effectively, and make use of data visualisation tools to assist with analysis. For example annual trend diagrams would be useful, and most web analytics tools should provide this function. / One trend which has continued to decrease in the last year however is the number of researchers accessing online journals, down to an average of 84 per month from 105 last year (almost 20%). The explanation for this continues to be unclear, but a number of factors may be contributing: / Free online journal access is presented as one of the key advantages of joining GDNet for southern users, and the online survey continues to highlight online journal access as one of the key advantages of joining GDNet, together with receiving the funding newsletter and jobs announcements. Only GDNet registered members can access journals, depending on location restrictions required by specific journals. However, the programme has not driven membership as much in the last year, as membership management is seen as quite a heavy administrative burden when people are generally changing their online behaviour. Users now have a number of online profiles (e.g. Linkedin, Twitter, Facebook, etc.) and keeping multiple profiles up to date is time consuming. It appears that site users typically come to GDNet looking for specific thematic information via a Google or Yahoo search, read the abstract, some click through to download the full paper and then leave. / Information on the benefits of joining GDNet is only apparent when clicking on “join GDNet”, and not immediately obvious to a visitor or potential member. Information could be placed more prominently on the homepage. / Other programmes offer similar services e.g. Programme for the Enhancement of Research Information (managed by the International Network for the Availability of Scientific Publications - INASP). / JSTOR now provides free access to African scientists through the African initiative (although some Jstor policy changes effective September 2009 mean that new members from India and Pakistan can no longer access JSTOR journals through GDNet, although services continue to be provided to researchers registered before that date). It is not clear whether this is a contributing factor, but some change might reasonably be expected on journal access figures. / Another contributing factor may be that access to journals is no longer the key issue it once was: research in Africa for example has shown that access to journals is not the primary barrier to use, rather lack of information literacy including lack of understanding of research[2]. / Given the small and decreasing number of researchers accessing online journals on a monthly basis, the programme were encouraged to explore whether continuing to offer this service provides value for money or whether signposting to other relevant free journal access points might be more cost effective, or whether increasing southern membership has a bearing on journal access figures. / In addition to this, the programme was encouraged to make available and prominent on the site the DFID How to Note on Assessing the Strength of Evidence[3]. At the time of finalising this report (August) the note is currently available as a Feature on the GDNet homepage. / Baseline 1.2: Level of satisfaction by male and female users (relevant GDNet webstats available from 2010 GDNet Users web survey) / Milestone 1.2 for this review: 5% year on year increase in satisfaction / Satisfaction with GDNet’s online services is assessed based on web survey findings, in particular through a question which asks GDNet users to rate GDNet services according to their usefulness. / Satisfaction with usefulness of GDNet services continues to be high in line with both the baseline and year 1 figures. / However, the aim of a 5% year on year increase in satisfaction was not met. / Services rated as most useful include Monthly GDN Newsletter (68%), GDN Announcements (67%), Funding Opportunities newsletter (67%), and accessing online journals (63%). / Awareness of specific GDNet services (e.g. thematic windows for example) continues to increase amongst survey respondents. / Satisfaction with GDNet services is measured by analysing responses to an online survey of members, of whom approximately 6% took part. While the survey does provide some useful information for the programme – and the staff do consider the findings carefully - it almost certainly does not provide information representative of the whole membership population, as the very low response rate suggest an unrepresentative sample and substantially biased estimates. The review team outlined the limitations of the survey to the programme team and discussed this with a member of the M&E team, suggesting consideration of improved methodology to capture data from a more representative sample, if the M&E budget allows. / GDNet conducted a Gender Audit during 2012, which analysed 2011 web survey responses. Findings highlighted differences in use for men and women: While the main reasons for registering with GDNet were the same for male and female respondents (gaining funding information, data for their research and access to online journals) there were differences in relation to use and satisfaction. The primary reason for using GDNet for women who responded to the survey is email newsletters, while for men it is the online database of papers; men were nearly twice as likely to visit the GDNet website on a weekly basis and were also more likely to have used GDNet’s social media products. The programme’s analysis and subsequent review of literature about the gender digital divide suggested the need for separate milestones for men and women for use of and satisfaction with GDNet’s services. From sharing the Gender Audit with others in the sector, it also became clear to the programme that there was little value in reporting on the ratio of men to women in terms of use of services unless a relevant benchmark is available e.g. the proportion of men to women among southern researchers. On the basis of the Gender Audit, a question was added to the 2012 survey to help GDNet identify if there are different content needs for men and women. The full report on the GDNet Gender Audit is available here: http://cloud2.gdnet.org/cms.php?id=implementing_gender_audit_of_online_knowledge_service / Indicator 2: Level of use of and satisfaction with themed services / Milestone 2.1: Establish baseline use of themed services at end of first year / Milestone 2.2: Establish baseline satisfaction of themed services at end of first year’ / Progress against milestones 1 and 2 met expectation. / Use of thematic windows, which were launched in November 2011, continues to increase along with awareness of this additional service, but at quite a slow rate. / The web survey points to a small but growing number of users who find the thematic windows extremely and moderately useful (43% in year 2). / There is also some improved awareness of the availability of thematic windows. / At present, the programme manages 23 thematic windows in additional to Regional Windows. These are (listed in decreasing web hit order): Agriculture, Education &Training, Environment & Climate Change, Health, ICT, Poverty & Inequality, Gender, Urban Development and the Global South, Development Finance & Aid Effectiveness, Macroeconomics and Economic Growth, Governance, Entrepreneurship, Migration, Energy, Domestic Resource Mobilisation, Globalisation and Trade, Water, Innovation, Labour and Social Protections, Private Sector Development, Law and Rights, Transport, International Affairs. / Each thematic window is updated with relevant information, news and highlighted research. Following review of use of the thematic windows, the programme has suggested rationalising the number of themes it presents to approximately 10 which was strongly supported by the review team.
Recommendations: / The review team recommend the following changes and adjustments: / For the next Annual Review, it would be useful to have to hand the key figures relating to the full calendar year immediately preceding the review, and also include January – March figures. This will help the review team make assessments based on the most up to date figures available. / The programme is expected to provide better data visualisation and analysis of the webstat information it provides, and to pick out meaningful data to report on. A substantial amount of time at the review was taken up trying to make sense of the figures, and pointing out that the programme had actually done better in some areas of this output than it had reported. / Information on benefits of joining GDNet should be placed more prominently on the site. / Milestones 1.2 and 2.2 should be revised to “maintain high level of satisfaction” with online services and themed services, which is a better reflection of what the programme actually does. / Action for DFID / As was highlighted in the last Annual Review, it is acknowledged that statistics are not easily available for comparison or benchmarking with other similar services. DFID will investigate how webstats data and other relevant M&E data from similar services (funded by DFID) might be compared, and find a mechanism to encourage better analysis and interpretation of webstats in monitoring reports. / Impact Weighting (%): 45 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[1] Source Alexa global site ranking on 4th July 213: Eldis (261,230), GDNet (320,310) and Development Gateway (1,560,260).
[2] https://www.acu.ac.uk/focus-areas/data-scholarly-communication/growing-knowledge
[3] https://www.gov.uk/government/publications/how-to-note-assessing-the-strength-of-evidence

Output 2: Researchers better able to communicate their research to policy
Output 2 score and performance description: / A – This output met expectation / Progress against this output met expectation as per the targets and milestones set in the Logframe. However, this review identified a weakness in the way the programme is measuring progress against this output. / Progress against expected results: / Indicator 2.1: Researchers’ confidence and ability to communicate their research – immediately following capacity building effort / Target 1 for 2.1: Consistent 30-40% increase in confidence at the end of each workshop regardless of starting point. Expect to see year-on-year improvement on value added in workshops / Achievement under this indicator met expectation. / GDNet conducted 3 capacity building events during Year 2: An Awards & Medals presentation skills workshop in Budapest, and 2 Policy Brief Training Workshops, 1 in Nairobi, 1 in Arusha. In total, 58 researchers and 6 policy makers were trained in face-to-face events during year 2. / In terms of confidence, across the 3 GDNet events from June – November 2012, participants’ self-assessed score (on a scale 0-5) increased on average by 50% immediately following a capacity building event. This matches the Year 1 figure. / Target 2 for 2.1: Consistent 50–60 % increase in ability at the end of each workshop regardless of starting point. Expect to see year-on-year improvement on value-added in workshops / Achievement under this indicator met expectation / Participants at the 3 capacity building workshops held reported an average 50% increase in ability immediately following the training event / However, this average was significantly down on last year (was 89%), though not on the baseline (was 39%). The programme team felt that one of the training workshops in particular (the Awards & Medals workshop in Hungary) required better targeting in terms of responding to participants specific needs (e.g. training on how to use social media rather than writing and presenting policy briefs). More advanced training was delivered at the GDN Conference in Manila in June 2013 on presenting papers at conference plenaries and dealing with challenging questions and answers. Content and objectives of this workshop was tailored to the training needs of specific subsets of Southern researchers. / Indicator 2.2: Researchers’ confidence and ability to communicate their research – sustainability of capacity building effort / Target for indicator 2.2: A rich portfolio of examples of researchers’ communications confidence and ability across a range of sectors and regions / Achievement against this indicator met expectation. / It has always been understood by the GDNet team that increased confidence and ability immediately following a capacity building event is a weak indicator for the effectiveness of the training. In order to assess sustainability of the capacity building effort, GDNet asks each training participant to pledge what they will do within 3 months of the end of the training, and follows up by email 3 months and again 12 months after the training event. This helps provide a richer qualitative assessment of the effect of the training. The review team were also impressed by the way in which this model raised expectation and ensured on-going commitment and engagement. / The pledge follow up reports[4] provide some useful examples of how the training provided by GDNet has been put into practice in relevant institutions, and often shared with others, demonstrating that the training continues to be of high value and use to participants, and demand for research communication training continues to be high. / The training is provided as an entry point for further support to individual researchers. The programme team also offers on-going support through “help-desk” type support, which involves a significant but highly valued time commitment. / The programme team has been working towards making the training sustainable as part of its exit strategy, and has developed a number of How to Guides and contributed to modules and content for the online course run with CIPPEC which is now available in English and Spanish. / The first English online course on Research Communication was launched in April 2013 (as a follow up to the Spanish version of the course launched in November 2011) and will last 7 weeks. It received 115 applications for 18 places, all with strong and relevant profiles. The course was previously delivered to a larger group but experience has shown that the course is more effective with smaller participant numbers. The course makes full use of participants experience and ideas through discussion, and aims to build supportive peer relationships, critical thinking and provides practical tools and approaches (e.g. writing and presenting policy briefs, social media, data visualisation, online tools, etc.). All 18 participants (9 male, 9 female) have stayed involved throughout. To date, 33 participants have been trained through 2 online courses. / Although there are different challenges associated with running an online course and the initial time investment cost is high, this is an excellent mechanism for improving the reach and accessibility for the training provided. However as it is debatable as to whether online courses can fully replace face-to-face training, the programme is encouraged to continue to work with Southern institutions to ensure the capacity to deliver this type of course is transferred to others in the regions. / Recommendations / The programme should continue to ensure that each training event is better tailored to the needs and expectations of participants, possibly exploring options to ensure that participants have the opportunity to suggest areas of particular interest prior to and at least at the start of each training event. / At present, the programme is reporting average (mean) ability and confidence data. Median data would also be useful and would provide a more complete picture. / The Evidence into Action Team is tracking the number of individuals who have been trained in research communication and uptake in the programmes it supports. However, this information is not available in the monitoring report. Please provide the number of individuals trained to date and per programme year (disaggregated male to female), the proportion of southern participants and where possible to measure, the percentage giving positive feedback. / The programme should consider strengthening its evaluation of training by for example testing written material produced before and after training, as self-perception of improvement may have little bearing on reality.
Actions for DFID / Explore the possibility of inviting GDNet to participate in a seminar (possibly with other programmes) on their experience and approach to training southern researchers on research communication, including some examples of training modules (e.g. data visualisation, open data). / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[4] Three month pledge follow ups conducted with 2012 workshop participants yielded 24 responses, and 1 year follow ups conducted with Dec 2010 to Dec 2011 participants yielded 15 responses.

Output 3: Knowledge networking between researchers and with policy actors increased
Output 3 score and performance description: / A – This output met expectation / Indicator 3.1: GDNet user base interaction / Milestone 3.1a: 10% year on year increase in use of electronic user base network / Milestone 3.1b: Good face-to-face user base interaction at conference and at 2 RNPs/Regions / Progress against expected results: / Progress as outlined for milestone 3.1a exceeded expectation. It must however be noted that the indicator and milestones require further clarification. / Interaction by GDNet with its user base at a capacity building event, conference, or community or thematic group is logged by the programme, and analysed on an annual basis. / Indicators of increased user base interaction relate to sustained or increased blog views and responses, sustained or increased subscriptions, views and “click throughs” to GDNet social media such as Twitter and YouTube, as well as more strategic and in depth collaboration with specific partners to produce research communication products, and panel presentations at workshops and conferences. / Interaction between GDNet and its “user base” continues to increase, as detailed in the Social Media Annual Report contained in Annex 6 of the M&E Report for 2013 (Quest n. 3955211). For example, GDNet’s blog views have increased from 12,809 in Year 1 to 15,916 in year 2 (approx. 25% increase), and Twitter Followers have increased from 450 in year 1 to 1673 at the time of this annual review. / Learning this year includes: / the need to continue to engage users using a variety of mechanisms, including but not limited to social media / social media has become an effective and powerful way for the programme to communicate, and team capacity to use different tools needs to be built and sustained accordingly / success metrics require definition and monitoring / while GDNet to user base interaction is relatively straightforward to track, user to user interaction metrics are more complex / Although the Social Media Annual Report provides useful information on how GDNet’s reach continues to expand through social media, and learning centres around continuing to engage the user base using a variety of tools (which complements monitoring information obtained under output 1) it remains unclear how this indicator and milestone is contributing to increased knowledge networking between researchers and policy actors, as this indicator and monitoring information gathered is tracking GDNet activity centred around specific events, particularly relating to social media coverage of the particular event. Whilst this tracks GDNet’s increased experience in this area, it does not really provide “interaction” information, which implies much more of a 2-way process than the activities described. / A linked issue is that was highlighted in the previous Annual Review is that GDNet’s “user base network” requires better definition: in the monitoring report, the user base is defined as southern researchers, and the survey, although not representative, does seem to support this, although the concept for the programme does imply that GDNet’s audience is much more global and more policy focussed. / Key learning from the programme under this indicator suggests that it will try to track user to user interaction better, but the review team question whether this is possible or achievable, beyond tracking mentions and re-tweets as described in the monitoring report. At a minimum, more work should be done to better define and understand the GDNet “user base”, and identify how the programme can best respond to segmented user needs. / Indicator 3.2: Researchers’ interaction with the policy domain / Milestone 3.2: At least one research-policy interface per year in one region plus one online space
Achievement under this indicator met expectation / In year 2, GDNet logged 4 distinct interactions between researchers and the policy domain. GDNet organised and provided social media support for a GDN event in partnership with the American University in Beirut, “Road to Democracy in the Arab Region, Latin America and Central Europe” in May 2012. GDNet also contributed to and provided social media support for the policy seminar Food Secure Arab World Conference – Organised by the International Food Policy Research Institute (IFPRI) and the United Nations Economic and Social Commission for Western Asia (ESCWA). The other 2 interactions took place during research communication capacity building support. / Facilitation was mainly event driven and based around organising and facilitating special sessions at workshops and conferences where researchers and policy actors are encouraged to interact and engage with each other. / Interactions are logged in Annex 7 of the M&E report (Quest n. 3955211), which tracks activity, results and lessons from facilitating interaction between Southern researchers and the policy domain. / Key lessons this year include: / Ad-hoc, one-off events such as Research to Policy seminars require follow-up to gauge lessons learnt and impact / Value of organising policy dialogue in collaboration with Regional Network Partners needs to be set within an on-going broader programme / A thematic agenda and targeted involvement of specific researchers works better than just convening spaces for interaction / The longer term “policy lab” model where there is an opportunity for researchers and policy makers to interact over time to address a specific policy concern would appear to be more useful, and GDNet proposes to pilot this approach in year 3. / The GDNet capacity building programme is providing practical tools to support researcher and policy interaction by establishing research to policy face to face interaction through policy panels, supporting policy brief writing and designing and delivering presentations to policy makers. This training is provided both during and post capacity building events through the GDNet help-desk function. / Although these lessons are valuable, there is still little sense of how the research-to-policy interface, outside of capacity building support, is operationalized by the programme. It is not clear how many researchers and policy makers participated, how many were women, what research was presented, whether this research was of a particular standard of quality, and what was taken up by policy makers? / From information available in the reports and obtained at review meetings and interviews, it appears that the programme is providing valuable support and has a number of positive figures and successes in the area of research uptake, but these are not analysed or presented in such a way that showcases achievement. For example, the programme has gathered a number of follow up pledges from capacity building events, but for the purpose of this review, there is little analysis of the particular skills that have been used and what research is being taken up as a result of this support (e.g. by theme, region, etc.). / Recommendations: / The programme team should consider what indicator 3.1 is attempting to measure, and whether data collected speaks more to output 1 rather than this output. In addition, the programme should re-define “user base network interaction” better, and make the indicator and target measurable within the remaining timeframe of the programme. / It is unclear how many “policy labs” have been planned for 2013/14, and which themes or policy questions will be pursued. As the programme only has 1 year to run, the programme team will need to balance ambition and realism, and concrete plans should be agreed at progress meetings with DFID. At the first progress meeting following this Annual Review held in July 2013, it was established that this activity is dependent on GDN plans which will be firmed up at a GDN Senior Management Retreat in Delhi in early October 2013. As this will further shorten delivery timescales, it was recommended that the programme prepare for this meeting by scoping out options/budgets, etc, to minimise further delay between planning and delivery. / The DFID Research Uptake Guidance has been shared with the programme. By way of follow up to the Annual Review, the programme is advised to consider any implications the guidance note may have on delivery, and suggest how these implications might be addressed. In the meantime, the guidance has been added as a link under the announcements banner on the front page of the site. / Impact Weighting (%): 15 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Lessons about effective knowledge brokering in the global south learnt and communicated
Output 4 score and performance description: / B: This output moderately did not meet expectation / Indicator 4.1: Generation of best practice lessons / Milestone 4.1: 1 further GDNet best practice product / Progress under this indicator met expectation. / The programme logs lessons learned under each of its activities and work areas. This log is available as Annex 8 in the M&E Report (Quest n. 3955211). / Key lessons during 2012/13 include: / Continuing to build the online infrastructure based on open data will be a key milestone for the sustainability of the knowledge base beyond 2014. / As stated previously, social media will be key to growing awareness of the Knowledge Base and services available through the programme, as social media tools actively reach out to an ever increasing user base. / Understanding indicator and usage statistics gathered through M&E are key elements to interpret and analyse user behaviour online and tailor services accordingly. / Online user behaviour has changed since the start of the programme, with more people using social media. In particular, the proliferation of individual profiles on a variety of platforms (Facebook, LinkedIn, Twitter, Google Communities, etc.) is generating a set of issues for the programme in terms of researcher profile management. This activity is time consuming, prone to hacking, and the programme is perceiving this is no longer seen as of as much benefit as it once was. GDNet needs to review use of researcher profiles and other engagement platforms, reflect on findings and decide on a course of action now, or momentum will be lost. / The GDNet gender study on ‘Implementing a gender audit of an online knowledge service: the experience of GDNet generated an interesting set of findings mentioned above, which has helped the programme to reflect on how to target services better for different users. / Additional learning work currently underway includes: a review of challenges faced by southern researchers in getting their research used, contributing to a book on building critical thinking capacity (with Enrique Mendizabal), running the Connect South Campaign. / In addition the programme has generated a series of How to guides in partnership with CIPPEC to help Southern researchers enhance their policy outreach and research uptake, including toolkits on how to build a policy influence plan, how to monitor and evaluate policy influence, and how to write policy briefs. These guides are also available in Spanish. / An area of work that the programme has significantly progressed is its Open Data Initiative, which unfortunately is not reflected anywhere in the logframe. The review team recognised however that there has been a significant commitment by the programme to this area of work in line with emerging trends and good practice; and also fulfils a mission to secure legacy, which DFID fully supports. / Indicator 4.2: Communication of lessons / Target for 2014 (4.2): At least one conference paper and one formal published paper, as well as other reports and electronic communications / The target for 2014 has been met. / The programme used a variety of channels to communicate lessons in the last year. Details are included in Annex 9 of the M&E report (Quest. n. 3955211). These include: / A paper ‘Implementing a gender audit of an online knowledge service: the experience of GDNet’ presented to IDS hosted workshop of knowledge Brokers in March 2013 / An online discussion Group on LinkedIn http://linkd.in/ConnectSouth / Attended a number of learning events (e.g. Event organized by ‘World Bank: Mobilizing Knowledge Networks for Development’ June 2012; Event organized by ITOCA[5] and IDS[6] ‘Mobilising Knowledge for Development Learning Event’ November 2012) / Presented a Case Study at the K* conference in April 2012 in Canada GDNet: from Knowledge Hub to Knowledge Broker. / Indicator 4.3: Instances of GDNet incorporating new thinking on innovation into its practices as a result of participation in knowledge brokering fora / Target 4.3: Launch of specialised micro-site dealing with research to policy building on GDNet knowledge brokering services. / The target for this indicator: launch of the specialist microsite ‘Politics & Ideas: a think net’, which was approved at the last Annual Review completed April 2012 (Quest n. 3546087) has been met. / However, there are a number of issues with this initiative. It would appear that a significant amount of time and resource has been dedicated to setting this up. Further clarification is being sought from the programme about level and proportion of spend. / It is unclear how this site differs from already existing initiatives dedicated to knowledge brokering and research uptake, aside from being southern led and managed. There is concern that the proliferation of web based platforms is in fact doing a disservice to research uptake. Linked to this is the concern expressed elsewhere by the programme relating to GDNet membership, that attracting members and contributors to a site has been challenging, and there is no reason to expect that this initiative will find this any less challenging. / It is not clear that this initiative will be meeting DFID’s objective to increase the use of rigorous research evidence. There little information on appraising/using research evidence and neither does it highlight or profile high quality research evidence. It does however collate a topic guide which highlights some of the key resources relating to research uptake. This guide could have been made available through GDNet. / In addition, it is unclear how the launch of the site reflects instances where GDNet is incorporating new thinking into its practices, as the ThinkNet seems to be another example of how lessons are communicated out from the programme. This activity seems to fit better under the previous indicator. / More could be done to analyse the monitoring data available to the programme. For example, the survey responses provide some information about GDNet’s journal access service, though this doesn’t appear to have been given much consideration in the report or learning. Although imperfect, the survey does provide some useful feedback from a more “engaged” segment of its user base, and their comments, positive and negative should be pulled out into lessons. / Recommendations & specific actions
The programme is well placed to build on this perceived disconnect between southern research, which is primarily seen as responding to real and practical problems, and northern research which is regarded by some as feeding into journal literature with little impact on real world problems. In its role as a knowledge broker, the programme should be in a position to showcase more how it contributes to informing specific policy questions and debates, and signposts good quality research evidence, regardless of provenance. This is something the programme does as a matter of course, but is not reflected sufficiently in monitoring reports. / The question of how to assess the overall quality of the knowledge base was raised during discussions with the review team. At this stage of the programme however, it was suggested that rather than retrospectively attempt to assess the strength of the knowledge base as a whole, the programme could at a minimum make the DFID ‘How to Note: Assessing the Strength of Evidence’ available prominently on the GDNet site, and identify options to incorporate tools from the note into programme activities. This recommendation was followed up at the progress meeting held in July 2013, and the document was added as a link under the Announcements banner of the GDNet homepage. / Target 4.3 should be replaced by a more appropriate target, in light of priorities for the programme and approved by DFID by September 2013. / Specific actions for DFID / Provide detailed feedback on Think Net to the programme in July 2013 (completed), and sign off revised target(s) under this output by September 2013 (a revised logframe was submitted to DFID on 29th August 2013). / Impact Weighting (%):20 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N
[5] Information, Training and outreach center for Africa (ITOCA)
[6] Institute for Development Studies (IDS)

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? N / 1.2 Overall Output Score and Description: / The overall output score is B - the programme moderately did not meet expectation. / Overall, the programme is making some good progress against the logframe that was agreed following the last annual review. However, some problems persist with the logframe in terms of definition of indicators and how these relate to the areas of work the programme is delivering, with a number of activities being reported against a number of different output areas. Despite these problems however, the programme continues to grow its knowledge base and refine its brokering and research communication capacity building practice, and to share lessons with the wider research uptake community. Significant progress has been made on the Open Data initiative - for which there is no indicator in the logframe and which consequently received far less attention than it merited during the review - and on making capacity building initiatives and materials more widely available. / However, there are concerns about delivery in some areas: / There were concerns about the rationale behind the development of the ThinkNet, as well as the amount of time and funds invested in this initiative. It is unclear how this initiative will promote uptake of rigorous research evidence. / Sampling for the survey which informs output 1 is weak. / Increase in satisfaction under output 1 was not met. / Logframe indicators on capacity building are based on participants’ perceptions of progress rather than attempting to measure more objectively if participants capacity has been improved. / Carrying out the review involved a significant amount of investigative work by the reviewers and they felt that the programme could have done a better job of summarising and highlighting key successes and challenges ahead of the review. / Direct feedback from beneficiaries / GDNet engages with southern researchers in a variety of ways and obtains direct feedback through the annual web survey, last administered in December 2012. The level of satisfaction with GDNet core services (e.g. newsletters, access to online journals, knowledge base abstracts and researcher profiles) has been broadly maintained. Detailed feedback is contained in Annex 2 of the M&E report, in particular under question 20 of the web survey (‘are you able to provide a short example where GDNet has informed your research?), which elicited 424 responses. A selection of examples of positive feedback include: / ‘After publishing my work on GDNet about three years ago, I was contacted by others interesting Researchers to know more and to invite me collaborating in similar works (projects)’. / ‘It allows me stay connected with a community of researchers. Though my own research has not been on policy or directly about development but it is more about historical and anthropological issues of urban life, an arena directly influenced by development processes. In this sense, GDNet is indirectly crucial to my research. Its online services i.e. jstor and project muse are particularly helpful for researchers like me who live in a non-metropolitan city devoid of good library’. / ‘Through conference, I attend GDNet greatly expose me to the pool of experts in my own specialized field and put me on the correct track towards my academic career. Thanks.’ / ‘Through South Asia research window, a German team of researchers contacted me for further research details’. / Summary of overall progress / GDNet key results during 2013/14 include: / Supporting 5,253 institutions through its GDNet Knowledgebase of which 2,740 are eligible for BLDS services (including 217 organizations from developing countries which have been particularly active using the BLDS document delivery services from April 2012- March-2013). The programme also supports a total of 12,611 individuals of which 9,474 researchers in the global south who are eligible to access J-Stor and MUSE online collections and journals through GDNet services and receive the GDNet bi-monthly funding opportunities newsletter. As a result of this work, 2012 saw 14,252 downloads of international journals resources and 138,943 downloads from the GDNet Knowledgebase. / Supporting the training of 133 southern researchers (71 in 4 face-to-face workshops and 62 in 4 online courses) and intermediaries in research uptake and/or communications. / Supporting the development of online repositories containing around 20,351 documents and summaries, 5,253 organizations profiles and 12,611 researchers and development professionals profiles, whose output stock increases by 2,877 new entries per year (11% increase in documents; 3% increase in organizations profiles, 5% increase in researchers profiles). / Research evidence in these online repositories is accessed by around 449,959 people per year (31% in the global South) and attracts 994 document views per day. The GDNet platform as a whole attracts an average of 5,164 page views per day. / GDNet provided social media support for 15 global, regional and thematic events; organized one regional policy seminar in partnership with American University in Beirut hosting some 100 participants and two policy panels during the Research Communications Workshops in Africa; supported 3 community groups and four online courses through Spaces for Engagement Program in partnership with CIPPEC; conducted an online survey of the network membership towards Post 2015 MDG debate attracting some 160 responses; produced 145 talking heads of southern researchers across various perspectives and published 104 blog posts on events and southern research perspectives. / Key challenges / In addition to the concerns highlighted by the review team above, sustainability of the programme has been and will continue to be a key challenge and priority in the year ahead, and the programme will need to plan its exit strategy very carefully. Commendable progress has been made on Open Access of the Knowledge Base and documenting and sharing learning through the online course and how to guides, but a key question remains as to where the knowledge base should go if GDN is unable to source funding to secure its future, and the fate of GDNet is now more fully tied to the fate of GDN as a whole. Related questions centre on what services the programme might be able to continue to provide with more limited funding. The programme urgently needs to put in place a clear exit strategy, whilst continuing to actively source funding for its future. However, the GDN President fully supports the work of GDNet, and sees it as an integral part of GDN. / However, the Programme Director is keenly aware of the funding and sustainability challenges, and will need to focus on ensuring that the contract with DFID is delivered to the highest standard. A clear plan of how this review’s recommendations will be taken forward will be identified in collaboration with the DFID Programme Manager by mid-September 2013. / The management of this programme within DFID has changed multiple times. This has resulted in some mixed messages being received by the programme. / The recent events in Cairo have increased uncertainty and added an element of risk to delivery of the programme, notably as the GDNet programme office was closed for some of July and August (also coinciding with Ramadan). The programme has taken steps to mitigate some risks relating to the security situation (further outlined in the risks section below), but management plans will need to be further discussed and agreed with DFID at the next progress meeting in September 2013. / Annual Outcome Assessment / GDNet Purpose: Diverse research and policy audiences make better use of development research from the global south
Purpose indicator 1: Southern researchers use of other southern research in own research / Milestone for this review: none set / Target 2014: Target increase to be defined once baseline set, including incidence of researchers citing GDNet as a source of information / Purpose Indicator 2: Cases of knowledge into use in policy processes in Southern countries / Milestone for this review: none set / Target (2014): A portfolio of 20 up to date cases of knowledge into use in the policy process (5 per year) / In line with DFID logframe guidance, the purpose level should be renamed to outcome level. / No outcome level milestones were set for the purpose of this review. DFID now requires annual milestones for every programme. / The 2014 target for indicator 1 has yet to be set, and should have been revised following the last logframe revision. However, the programme does report significant use of Southern research in Southern researcher’s own research – 64% of respondents of the online user survey use Southern research to a great or moderate extent, which is no more significant than their use of Northern research, and there is no apparent shift in use over time. / Responses to the survey hint at a potentially important niche for GDNet to more proactively fill: raising the profile of the best Southern research so that it is perceived as on par with Northern research in terms of quality but also highlighting it’s applied and practical nature, grounded in local contexts and addressing issues where there is strong demand or a clear evidence gap. GDNet already does this to a certain extent through its “showcase” tagline, but quality considerations could be improved. / At the time of the review visit, progress against indicator 2 was pending the GDN conference in Manila, which took place in June 2013, at which the final selection of cases was to take place. A further five cases were gathered at the conference, adding to the 8 cases previously gathered during the last 2 years of the programme. The timing of the next conference in June 2014 indicates that further progress against this indicator (number of cases) will not be available in time for the next annual review of the programme. Progress against this indicator will be further discussed at the September meeting with the Programme Director.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / 2.2 Key cost drivers / There are no anticipated changes in the near future to the cost drivers. / The key cost drivers are: / the maintenance and cost of servers and related software – these are kept as low as possible, through competitive tendering and also through managing the service from Egypt (rather than the UK) / Overhead costs: GDN related overhead costs were reduced after the last annual review (as a percentage of funds managed, rather than a flat rate). Funds paid for by GDN in Delhi include online services, cloud computing and regional network partner contracts. Funds paid to ERF in Egypt for the hosting arrangement include funding for staff payroll, legal, contracting, procurement, insurance, and office management which the programme would have to otherwise provide independently. The rent also paid to ERF also covers office space, security, maintenance, cleaning, internet and phone. / The team is kept quite small, although numbers have risen steadily, whilst consultant time has decreased. Existing team members have been trained and mentored to fill new and changing roles with increasing levels of responsibility. Although the programme does make use of international consultants, each contract contains an element of capacity building of local staff to ensure that skills are transferred where possible. / Flights and travel to GDN Headquarters in India have been reduced and meetings are held via VC/telephone where feasible. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / None. / 3.2 Where an evaluation is planned what progress has been made? / GDN has commissioned an independent evaluation. Terms of reference for this evaluation are available on Quest (n. 3947989). / The Evidence into Action Team is planning to commission an evaluation of platforms and portals funded through its portfolio during 2013-14 under the Research Communication Business case (Quest n. 3775584).

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / The risk level of this programme has been revised to medium. As detailed above in the challenges section, the primary risk to the programme remains availability of funding beyond June 2014. The EiA Programme Manager and Programme Director will meet in September 2013 to discuss progress on securing funding, and plan exit strategy if no funding has been secured through GDN.
Risk of funds not being used as intended / This annual review did not conduct a full financial review of the programme. Policies and procedures in place will be followed up as part of on-going progress meetings, but a full financial audit should be undertaken as part of the next and final annual review of the programme. / In the meantime, the programme has submitted the GDN accounting manual, which includes GDN’s written financial policies and procedures (Quest. 4130811). The GDN policies do not include anti-corruption policies, although GDN have signed anti-corruption statements for other another donor in the past and have provided a scanned copy of the signed declaration (on Quest). GDN are in the process of reviewing their accounting manual last updated in 2009 and have undertaken to incorporate anti-fraud and anti-corruption statements in their revised manual. The DFID EiA Programme Management team will review the accounting manual by September 2013, and provide further assessment as to whether this manual is of high enough standard and covers pertinent areas (e.g. financial management reports, audited statements, declaration of conflicts of interest, etc.). Where policies are not adequate, it will be advised that GDN take immediate steps to tighten up financial policy and procedures. / The programme Manager and Evidence into Action Team Programme manager have established a schedule of regular progress meetings, which will be held quarterly at a minimum. The first of these was held in July 2013, at which detailed activities, plans and budgets were discussed. An additional meeting will be held in mid-September to follow up and agree outstanding matters. / Climate and Environment Risk / This programme is considered low environmental risk, and presents high opportunity in terms of its ability to establish virtual networks of researchers across regions and continents. The online course delivered with GDNet is a specific example of this. / In addition, the GDNet programme team have increased efforts to use video conferencing for regular meetings, and have significantly reduced international travel. / Risks / Following this annual review, the risk rating for this programme will be changed to medium, to reflect the increased level of scrutiny required of the programme in terms of management, and additional risk in terms of overall success of the programme if it is unable to demonstrate achievement of outcome, and efficiency in terms of value for money. / The evolving security situation in Cairo has also been flagged as an increased risk, and this risk has been updated on the updated risk register, to be submitted to DFID by September 2013. To ensure continuous service delivery, the GDNet technical platform is based on two clouds, one in Egypt and the other in the UK so at no point in time has there been any service disturbance (even when Egypt telecommunications were cut off for 24 hours during 2011). Technical and managerial measures are in place to deal with risks relating to service delivery. Content management and work programme deliverables have been consistently managed to achieve targets, and support structures are in place to allow staff to work from home when necessary to ensure minimum disruption. The Programme’s updated risk matrix will be submitted to the DFID Programme Manager by mid-September 2013, and management and mitigation strategies further discussed and agreed, in line with DFID guidance and practice. / Another on-going foreseeable risk to GDNet is the funding situation of GDN. GDNet is now fully integrated within GDN, which should help remove the unhelpful confusion that can arise between GDN/GDNet, and present a stronger narrative of the organisation as a whole. The GDN Board is very supportive of the work of GDNet and the new GDN president, Pierre Jacquet, has a well-defined fundraising strategy, and is well placed to pursue it, whilst recognising the challenges that lay ahead.

5. Value for Money
5.1 Performance on VfM measures / For the purpose of the last Annual Review, GDNet produced a list of VfM indicators based on the three Es – economy, efficiency, and effectiveness. For the purpose of this review, the list of example indicators was revised as appropriate: / Economy (Minimising the cost of resources used whilst having regard to quality) / Cairo-based office costs - GDNet recently relocated to the ERF building which further adds to working efficiency, and provides a higher quality work environment at no extra cost. / Employees on local salaries / Economy air fares / Outsourced IT support / Independent experts and organisational partners are contracted on an output/deliverable rather than input basis / Efficiency (The relationship between outputs and the resources used to produce them) / Following successful pilot, the programme is rolling out new methods of enhancing efficiency (e.g. online capacity building courses for Southern researchers) / Comparison with other DFID funded knowledge services e.g. Eldis etc. Comparison benchmarks include, size of team (8-person core team), cost per researcher trained, cost per web site visitor, ratio between salaries and activities / Sustainability of capacity building efforts – GDNet is building the capacity of a team of Southern-based knowledge services and research communications experts in-house. This represents a direct and sustainable resource to support Southern research in the future. / GDNet’s outsourced web and IT support is based on a UK-based cloud server for security but managed and maintained by a Cairo-based outsourced IT expert for economy and efficiency / Effectiveness (The extent to which objectives are achieved and the relationship) / While this programme has demonstrated economy and efficiency, it is less clear that there are cost-effective. There is insufficient evidence to demonstrate that the funds invested in this programme lead to (or are likely to lead to) actual outcomes and impacts. In part, this is because the monitoring strategy does not objectively measure ‘capacity built’ but instead relies on participants’ perception of progress. In addition, the review team has some concerns about the likelihood of some activities – in particular the Thinknet – leading to sufficient outcomes and impacts which would justify the amount of funds invested. / The programme team is making efforts to ensure there will be sustainable change after programme closure – for example by establishing self-sustaining community groups and establishing the Knowledge Base as a global public good and long term sustainable legacy of the Programme / The research pledge system is an innovative approach for achieving outcomes and it would be useful to have further evidence of its effectiveness / Outcome level case studies of knowledge into use in policy process generated through most significant change process involving GDN Awards and Medals Finalists are useful indicator of outcomes. / 5.2 Commercial Improvement and Value for Money / This programme is an Accountable Grant, and whilst commercial imperatives may not be spelled out in the grant contract, DFID expects partners to ensure value for money. / In addition to monitoring progress against the indicators listed above, DFID will engage with the programme on a regular basis, to ensure compliance with proper commercial practice in terms of procurement and disbursement of funds. / 5.3 Role of project partners / Although composed of a small local team in Cairo, the GDNet programme makes use of a number of international partners and consultants to achieve its aims (e.g. ITAD, CommsConsult, etc.). / As detailed above, the programme sets up deliverable based contracts with partners, and each contract contains an element of transfer of skill to ensure that the expertise provided by specialists is retained within GDNet. / The programme has been asked for further details of the amount of funds going to these partners so DFID can reassure itself that this spend meets DFID value for money criteria. / 5.4 Does the project still represent Value for Money : Y / Overall, the project still represents value for money however the review team has identified a number of areas where the programme could improve on value for money and overall effectiveness. / Progress against review recommendations will be monitored through regular (quarterly) progress meetings with the programme. / 5.5 If not, what action will you take? / Where progress against recommendations in the review proves unsatisfactory, the budget for the programme will be adjusted accordingly. DFID reserves the right to close programmes that do not perform satisfactorily.

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Overall, the programme is making some good progress against the logframe that was agreed following the last annual review, but progress was often mixed under the output areas, and the review team did identify some areas of weakness in this logframe. Some clear recommendations to improve the programme have been made and will be followed up at regular programme progress meetings. The first of these meetings took place in mid-July 2013, with a follow up scheduled for mid-September, at which a realistic and achievable programme of work will be approved with specific deliverables (including a revised logframe, implementation plan, budget, updated risk matrix and exit strategy).

8. Review Process
Visit to GDNet in Cairo on 29th& 30th April 2013 by the Research Uptake Manager from the Evidence into Action Team and by the Evaluation Advisor of the Research and Evidence Division. / The review team consulted widely during and following the review with GDNet programme staff, partners and sub-contractors, including the monitoring and evaluation team. The review team also consulted with GDN management and financial staff. / This report was quality Assured by the Evidence into Action Team Leader and incorporates feedback from the programme partner.