Type of Review: Project Completion Review
(Multilateral Organisation Core funding)

Title of funding stream:
Asian Development Fund Ninth Replenishment – AsDF X

Date started: 15 May 2009	Date review undertaken: October 2013

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The UK has provided a contribution of £116 million over four years (2009-2012) to the Ninth Replenishment of the Asian Development Fund (AsDF X). This included a supplementary payment of just over £6 million contingent on good performance on agreed gender equality targets. The payments schedule was as follows: / 2009 - £27,461,488 / 2010 - £27,461,488 / 2010 - £ 6,154 049 (Performance based supplementary contribution) / 2011 - £27,461,488 / 2012 - £27,461,488

What were the expected results?
The Asian Development Fund’s (AsDF) overall goal is to eradicate poverty and achieve the Millennium Development Goals in Asia and the Pacific. The purpose of the AsDF is to contribute to economic and social development in AsDF developing member countries by providing concessional funding and grants for projects and programmes. It is expected that the Bank’s operations through the AsDF contribute to the overall development impact in the poorest countries in Asia through improvements in infrastructure (transport, energy, water-sanitation), education and strengthened policies and capacity at country and sector levels to manage development efforts. / The UK’s support to the AsDF is based on the fact that the development gap between AsDF countries and other countries in the region is widening, which could undermine social cohesion and political stability in the region, income poverty persists, with almost 60% (314 million) of the population living on less than $2 a day and 27% (about 148 million people) living on less than $1.25 a day and vulnerable to slipping back into absolute poverty, and, that, AsDF countries are on track to achieve only just over one third of the non-income MDGs by 2015. / Since 2005, Asia has made solid progress in reducing poverty and improving human development. Access to basic infrastructure increased, especially telecommunications, and governance indicators improved. The strong economic growth has had a major impact on reducing poverty, but in many countries growth has been accompanied by rising income inequality, which limits how much the poor can benefit from such growth. Data (e.g. in the AsDB 2013 Development Effectiveness Review) confirm that poverty remains the region‘s central challenge, with at least one in five people living on less than $1.25 a day. Indicators on child mortality and access to sanitation made insufficient headway to be able to achieve the 2015 targets. Progress lagged in AsDF countries as a whole, and gaps across countries remained. This context underscores the need for the Bank together with development partners to continue working together with a sharper focus on development results. / In 2009, the expected results (from AsDF X Contributors Report 2009) of AsDF X included (please refer to section “Impact” for our assessment on the outputs): / Expected outcomes (outputs in AsDB’s Results Framework) in 2009 for 2009-2012 Achieved AsDF outcomes for 2009-2012 (AsDB DER 2012, annex 5) / 29,970 km of national, provincial, district and rural roads and 490 km of expressways built or upgraded between 2009-2012 36,200 km of national, provincial, disctrict and rural roads and 27 km of expressways built or upgraded / 167,000 new households connected to electricity between 2009-2012 1,087,000 new households connected to electricity / 1,366,800 new households connected to water supply between 2009-2012 2,272,000 new households connected to water suppy / 19,000,000 students benefiting from education programmes between 2009- 2012 4,188,000 students benefiting from education programmes (did not reach due to delay in project delivery) / 636,870 microfinance loan accounts opened between 2009-2012 1,427,000 microfinance loans accounts opened or end borrowers reached

What was the context in which UK support was provided?
The Asian Development Bank is based in Manila, Philippines, and is owned by 67 members including 48 from Asia and Pacific. The UK with 2.038% is a small (14th largest) shareholder. / The AsDB is structured along similar lines to the World Bank, with two main lending windows: the Bank which lends at near market rates of interest to creditworthy countries and the private sector; and the Asian Development Fund (AsDF) which lends on highly concessional terms and provides grants to the less developed regional members of the Bank. The Asian Development Fund is replenished every four years. Negotiations on the ninth replenishment (2009 - 2012) concluded in May 2008 and were approved by Governors in August 2008. The UK agreed to contribute 4.8% for AsDF X (£116 million). The largest contributors were Japan (35.0%), the USA (10.0%) and Australia (6.5%). / The Bank’s mission is “to help developing member countries substantially reduce poverty and improve the quality of life of their people”. It is committed to reducing poverty through inclusive economic growth, environmentally sustainable growth, and regional integration. There is strong demand for its assistance as two thirds of the poor live in Asia and the Pacific. The Bank’s “Strategy 2020”, agreed in May 2008, mandates AsDB to “refocus its operations into five core specialisations that best support its agenda, reflect developing member countries’ needs and AsDB’s comparative strengths, and complement efforts by development partners”. / The key operational areas are: / Infrastructure, particularly transport, communications, energy and water; / Environment, including climate change; / Regional cooperation and integration, with AsDB taking a role as catalyst and coordinator; / Finance sector development; and / Education, focusing on basic, secondary and vocational education. / The UK set out clear objectives during the replenishment negotiations in 2009 and achieved the following outcomes: / $1 billion for an infrastructure programme for Afghanistan; / Bank is more poverty focused and has a good results framework to guide its work; / Climate change, gender and regional cooperation are all addressed in the Bank’s results framework (as evidenced in the annual Development Effectiveness Reviews), new guidelines for country programming, monitoring and evaluation (with an independent evaluation department); / Internal issues on human resource management are tackled through strengthening of country missions and improvements in recruitments of senior managers (merit-based processes); and / Resources will be available for targeted programmes in AsDF eligible countries that help prevent people falling back into poverty as a result of the global financial crisis. This includes employment creation, social safety nets and infrastructure investments that use labour-intensive methods reaching poor and vulnerable groups. / The UK Multilateral Aid Review (2011) of AsDB identified a number of challenges for, as well strengths of, the Bank. The MAR confirmed that the Bank plays a critical role in contributing to international and UK objectives and it was ranked as the top performing multilateral development Bank. It had a clear strategic vision which supports a focus on results but its performance could be improved by ensuring that its projects have a greater impact on the poorest communities and on addressing the needs of girls and women. The MAR identified the following as priority areas for development: / Accountability for results: Greater focus on inclusive growth in country strategies and projects, explicitly identifying the rationale and outcomes, including private sector projects. / Delivery of efficiency savings and value for money: Supporting partners to seek value for money in policy and programme choices, and to strive to reduce administration costs with explicit cost effectiveness measures / Human resource management: Effective decentralisation of staff (and devolution of decision making) to support policy dialogue with partner governments, / Delivering for women and girls: Continued improvement in addressing the needs of girls and women through the design and implementation of projects, / Climate Change: Tackling climate change, including leveraging private sector finance for projects in low income countries (LICs). / DFID’s 2013 MAR Update noted that the Bank had demonstrated progress but assessed that some weaknesses remained at project level implementation and reporting. The MAR Update found that the new Results Framework had stronger results focus at all levels including emerging evidence of greater attention to inclusive growth and a coherent approach to private sector development. The review noted that the Bank had improved business processes and reporting on portfolio performance and that the new Results Framework included value for money indicators. The review noted the lack of evidence on cost and value consciousness at project level. It assessed that the Bank had achieved reasonable progress in strategic and performance management in respect of its human resource management, especially on decentralisation to country missions and improved capacity at country level. The Bank had raised the gender profile across the programming and agreed more ambitious gender targets in its Results Framework. The MAR Update concluded that the Bank had more systematic evidence of an enhanced contribution to tacking climate change, including a substantial rise in private sector leveraging in climate change mitigation.

## Section A: Detailed Output Scoring

Output 1: AsDF X commits the full $11.3 billion for loans and grants during the period 2009-2012 and focuses on Afghanistan.
Output 1: final score and performance description: / A - Outputs met expectation / Final results: / Cumulative AsDF X commitments (2009-2012) exceeded the target of $11.3bn by $0.5 billon as it reached $11.8 billion. / AsDF approved grants to Afghanistan totalling $376 million in 2012 meaning that the Fund just exceeded the 2012 target of $1 billion. In line with the 2009 - 2013 Country Partnership Strategy, AsDF is active in energy, transportation and natural resources management. Projects focus on regional connectivity, energy security and food self-sufficiency. The AsDB managed Afghanistan Infrastructure Trust Fund is leveraging co-financing for critical infrastructure projects. / Indicator 1 / Cumulative level of AsDF commitments / Target $11.3 billion (2009-12) / Cumulative total end 2012 – $11.8 billion / $3 billion committed in 2012 / $2.5 billion committed in 2011 / $6.3 billion committed in 2009-2010 / Indicator 2 / Cumulative level of AsDF commitments to Afghanistan / Target $1 billion (2009-12) / Cumulative total end 2012 - $1,098 billion / $376 million committed in 2012 / $ 232 million committed in 2011 / $490 million cumulative committed in 2009-2010
Impact Weighting (%): 40 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: AsDF improves operational performance
Output 2: final score and performance description: / B - Outputs moderately did not meet expectation / Final results: / The Bank has made progress in a number of areas of operational effectiveness across the replenishment period, including quality at entry and portfolio performance, and financing for “Strategy 2020” priorities (including our tracked indicator - mainstreaming gender in projects). / Performance against financing for “Strategy 2020” priorities was especially strong. As well as the overall indicator for this, all five underlying results indicators exceeded the targets set for 2012 (promoting environmental sustainability, private sector development, and regional cooperation and integration, projects with gender mainstreaming). / These gains were somewhat offset by off-track ratings for successfully completed AsDF CPSs, and sovereign operations. The lower achievement and success rates of recently completed operations, and lower output delivery for operations funded by the Asian Development Fund were due to project delays and cancellations. The reasons for this, cited by the Bank in the 2012 Development Effectiveness Report, were: project designs often inappropriate, complex or overambitious, and lack of adequate assessment of the partner government’s capacity and commitment and local conditions. Project implementation problems were often caused by weak project management capacity of executing agencies, complex implementation arrangements and problems with procurement. The Bank has acknowledged these constraints and is implementing improvements, e.g. streamlining of business processes and capacity strengthening of partner countries implementing agencies, to tackle the weaknesses. Also, over the period, completed technical assistance projects showed a steady improvement across and the success rate of 82% in 2012 exceeded the target of 80%. / Indicator 1 / Quality at entry ratings for Country Partnership Strategies (CPS) % successful / The target for 2012 is 80%. Baseline 33% in 2006. / 100% in 2012 / No data for 2011 / Reached 100% exceeding the target in 2010 and reporting is biennial. This is on track. / Indicator 2 / Average annual combined ratings of project evaluations and completion reports (% satisfactory) / We have changed this indicator as it doesn’t represent a balanced reflection of performance in project completion as there are no non-sovereign operations and the overall performance rating is skewed by the consistently higher performance of TA projects as opposed to non-sovereign (the majority of Bank programmes). We have replaced it with the following: / “Completed sovereign operations rated successful (%)” / Target for 2012 is 80%. The baseline was 71% in 2006 / Reached 68% in 2012 / Reached 61% in 2011 / Reached 57% in 2010 / Indicator 3 / Proportion of projects with gender mainstreaming (%) / Target for 2012 is 50%. The baseline was 45% in 2006 / Reached 59% in 2012 / Reached 53% in 2011 / Reached 45% in 2010
Impact Weighting (%): 30 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3: AsDB improves its organisational effectiveness
Output 3: final score and performance description: / A+ Outputs moderately exceeded expectation / Final results: / The AsDF has shown good progress in organisational effectiveness during the period 2009 - 2012 and has met or exceeded all the 2012 targets set for our chosen indicators (below). / There are now more staff allocated to operations departments (56% matching the 2012 target) and resident missions are taking a stronger role in administering projects, leading country programming, portfolio review, and economic work. Staffing and procurement capacity have also been strengthened. Operations approved during 2010, 2011 and 2012 took an average of 10 months from approval to first disbursement for AsDF (exceeding the 2012 target of 12 months). / Indicator 1 / Proportion of budgeted professional and national staff in operations departments (%) / Target for 2012 is 56%, The baseline in 2006 is 52%, / 2012 was 56% / 2011 was 56% / 2010 was 55% / Indicator 2 / Sovereign operations administered by resident missions (%) / Target for 2012 is 43%. Baseline in 2006 was 36% / 2012 – 43% / 2011 – 41% / 2010 - 41% / 2009 - 37% / Indicator 3 / Average time from loan approval to first disbursement (months) / Baseline 13 (2006) target 12 (2012) / 2012 – 10 months / 2011 - 10 months / 2010 – 10 months
Impact Weighting (%): 30 / Revised since last Annual Review? N. / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money
1. Achievement and Results
1.1 Has the log frame been updated since last review? No / 1.2 Final Output Score and description / A - Outcome met expectation / 1.3 Overall Outcome Score and Description: / A - Outcome met expectation
Major Achievements and Results
For the AsDF X, the Bank has met the UK’s and other contributors’ expectations on financial commitments over the last four years. The Bank exceeded the $11.3 billion target for the AsDF X commitments for 2009 – 2012 by $0.5 billion and its commitment to Afghanistan (totalling $376 million in 2012). The main mechanism for support to Afghanistan has been the AsDB managed “Afghanistan Infrastructure Trust Fund” which is leveraging co-financing for critical infrastructure projects and plays a major role in developing key infrastructure to improve connectivity and expand access to electricity for people and businesses. / The Bank has reported (“Reforming AsDB for a more Effective ADF”, 2011, “Transforming AsDB: Next Steps on Reforms”, 2012) on how earlier reform initiatives have influenced its current improved effectiveness. Examples include: (i) the Bank’s operations are more closely aligned with Strategy 2020 priorities, including gender mainstreaming; (ii) project quality-at-entry is on track; (iii) project start-up has become more efficient; (iv) the level of co-financing has increased considerably; and (v) knowledge management and partnerships have steadily improved. In addition, there is a considerably greater gender balance at AsDB. Other areas, such as budget adequacy, business process efficiency, and empowerment of resident missions, have also advanced. There is also more systematic evidence of an enhanced contribution to tacking climate change, including a substantial rise in private sector leveraging in climate change mitigation. / The Bank has demonstrated solid progress across AsDF X on the key operational and organisational commitments agreed upon with donors including its commitment of available resources. The quality at entry (QAE) of country partnership strategies and sovereign operations is consistently high and the QAE of non-sovereign operations has improved significantly but some weaknesses remain at project level implementation and reporting. The Bank has acknowledged the need for actions to strengthen project readiness and supervision to raise project success and outcome achievement rates. It is streamlining its business process across its operations and it provides technical assistance to support capacity strengthening of the implementing agencies. It has also improved its own supervision of projects through strengthening of country missions on issues such as design, procurement, supervision and monitoring of programmes. / The 2013 MAR Update noted that the Bank has demonstrated its commitment to results as it continues to improve its results management systems, which were assessed as “satisfactory” by the MAR 2011. The recent revision of the results framework in January 2013 improved the measurement of key results areas, highlighted in the MAR, such as climate change, gender and budget management. It also included new indicators on inclusive growth and private sector, but further work is needed to improve those indicators. / The Bank has also strengthened its results focus at project, programme and country levels (country partnership strategies) which is monitored and reviewed annually as part of the Development Effectiveness Review (DER 2012, 2013). However, the quality of project design (including safeguard readiness), approvals, implementation and supervision still needs to improve as evidenced in the Bank’s annual reporting, the Development Effectiveness Review 2013 and country office feedback (2013 MAR Update). The Bank acknowledges the need to continue its efforts to improve project readiness (design, approval, bidding processes, safeguards) and implementation supervision. The 2013 Development Effectiveness Review includes actions to improve the effectiveness of AsDB’s operations in these areas through streamlined processes and increased staff skills in procurement and supervision. / The 2011 MAR identified gender as an important reform area and DFID has pushed the Bank to continue improvement in addressing the needs of girls and women through the design and implementation of projects. The Bank acknowledged the challenge in this area at the MAR 2011 phase and it noted that it had already identified the weaknesses in gender in the AsDB Development Effectiveness Review in 2009. As noted in the 2013 MAR Update, AsDB has undertaken measures to strengthen mainstreaming of gender aspects in its operations (going from 27% in 2008 to 41% in 2011 and 49% in 2012 of all Bank projects), but it will take some time before this is fully implemented across the organisation. The MAR Update scored the Bank’s progress on gender as “reasonable”. / The Bank’s support to regional integration contributes to more efficient trade and regional markets, which feeds into further economic growth in Asia. Regional cooperation and integration has increased from 7% of the AsDF VIII funds to 31% in AsDF X. The Bank has noted that the success of regional programmes largely depends on the level of interest of participating countries and their incentives for cooperation. / There has been reasonable progress in strategic and performance management in respect of its human resource management, especially on decentralisation to country missions and improved capacity at country level. AsDB has more staff to support operations, and almost half of them work in resident missions to increase responsiveness to clients and resident missions are more empowered. As a result, country offices now have more capacity to manage its operations, more flexibility to manage its human resources and some devolution of decision-making on operational issues. The Bank’s “Corporate Evaluation of the Decentralisation” (October 2013) found that the strengthening of country missions had improved the Bank’s policy engagement in country and programme supervision. / At the end of 2012, 56% (985 of 1,769) of all international and national staff positions were allocated to operations departments, matching the target. Of the staff assigned to regional departments, 49% (425 of 871) were in resident missions, exceeding AsDB‘s targets by one percentage point. In 2012, AsDB added 34 international and national staff to its operations departments at headquarters and in resident missions. Of the 25 new positions in regional departments, 16 (64%) were assigned to resident missions. / For 2012, the indicator “average time from approval to first disbursement” for AsDF projects was 10 months, compared to the 2012 target of 12 months. This positive achievement is the result of AsDB’s efforts since 2007, including stream-lining its business processes, to tackle the start-up delays that were hampering the Bank’s operations. The indicator used is a proxy for tracking the effectiveness of the Bank’s project management and the Bank uses it together with other targets on project performance, including disbursements. The 2012 Annual Evaluation Review (IED) noted that a third of project completion reports in 2011 and 2010 cited supervision problems, often due to insufficient supervision by AsDB missions in country and frequent changes of key staff. The Bank has acknowledged this problem and is strengthening its project supervision and monitoring functions. We will follow up on this issue through our board discussions, including the opportunities to discuss the findings from annual Development Effectiveness Reviews and other evaluations. / The Bank has over the last few years strengthened its risk management system, safeguards and monitoring and evaluation processes. The Bank has an Action Plan to improve its performance and management emphasise measures on project performance, timely project processing, gender balance at AsDB, budget efficiency and management for development results (using an updated results framework across the organisation). / In conclusion, the Bank has demonstrated good progress in implementing the AsDF X, which is evidenced in the annual Development Effectiveness Reviews with regards to concrete outputs. It has also showed good progress in the internal reforms as described above. The 2013 MAR Update concluded that the Bank has demonstrated reasonable progress on the MAR priorities, but it noted that some weaknesses remain at project level implementation and reporting. The new Results Framework has a stronger results-focus at all levels including emerging evidence of greater attention to inclusive growth and a coherent approach to private sector development. The Results Framework includes vfm indicators, but there is a lack of substantial evidence on cost and value consciousness at project level. There is reasonable progress in strategic and performance management in respect of its human resource management, especially on decentralisation to country missions and improved capacity at country level. The Bank has raised the gender profile across the programming and agreed more ambitious gender targets in its Results Framework. The Bank has also systematic evidence of an enhanced contribution to tacking climate change, including a substantial rise in private sector leveraging in climate change mitigation. / The AsDF – responding to the needs in poorer Asian countries / Over the last four years, the Bank has provided around US$3 billion per year through the AsDF. It is expected to continue at a similar level for the next few years with just over US$12 billion agreed for AsDF XI for 2013 - 2016. From 2002 - 2012, the Bank approved over $24 billion in AsDF loans and grants for 29 countries. The largest recipients were Bangladesh, Vietnam, Pakistan, Afghanistan and Nepal; accounting for over 60% of loan and grant approvals. Over that period, the AsDF contributed significantly to development in AsDF countries through outcomes such as students and trained teachers, improved access to roads, electricity and improved water supply and sanitation facilities. / The following table compares a few of the expected outcomes in 2009 for 2009-2012 to the achieved outcomes for the same period: / Expected outcomes (outputs for AsDB) in 2009 for 2009-2012 Achieved outcomes for 2009-2012 (AsDB DER 2012) / 29,970 km of national, provincial, district and rural roads and 490 km of expressways built or upgraded between 2009-2012 36,200 km of national, provincial, disctrict and rural roads and 27 km of expressways built or upgraded / 167,000 new households connected to electricity between 2009-2012 1,087,000 new households connected to electricity / 1,366,800 new households connected to water supply between 2009-2012 2,272,000 new households connected to water suppy / 19 million students benefiting from education programmes between 2009- 2012 4,188,000 students benefiting from education programmes (did not reach due to delay in project delivery) / 636,870 microfinance loan accounts opened between 2009-2012 1,427,000 microfinance loans accounts opened or end borrowers reached / As the table above indicates, there has been a substantial increase in outcomes for several of the targets, including roads; households connected to electricity and water supply and new microfinance loans. However, there was a substantial drop from expected students benefitting from education programmes over the period (from 19 million to just over 4 million). The AsDB has explained that this was mainly due to delays in project delivery after the planned completion period. On the positive side, the Bank managed to reduce the average time from loan approval to first disbursement from over 16 months to 10 months during the period. / For the Bank’s support to Afghanistan, which was one of the UK’s priorities for the AsDF X, the Bank assesses that the AsDF funded 750-kilometer network of improved roads have reduced travel time and that the four supported airports are providing access to remote parts of the country. Also, the new and upgraded transmission lines have improved power supplies in Kabul, where electricity is now available almost around the clock in 2012 compared to about four hours per day in 2002. / The well documented outputs and development results of the AsDF are in line with our assumption that the Fund’s strategy and ways of operating enables it to achieve real development outcomes for the poorest countries in Asia. As noted in the Bank’s evaluation study “The Asian Development Fund Operations: A Decade of Supporting Poverty Reduction in the Asia and Pacific Region” (IED 2011), attribution is difficult to establish given that AsDF finance only a small share of recipient countries’ investment expenditures. The evaluation concluded that the “AsDF has likely contributed to economic growth by helping countries (i) improve connectivity through transport investments; (ii) increase the level and reliability of power supplies; (iii) develop legal, regulatory and institutional frameworks for finance and commerce; and (iv) increase agricultural production”. / The evaluation also acknowledged that the AsDF sought to support efforts to make growth more inclusive and promote social development through measures to enhance access of smaller enterprises to resources and investments in rural and social infrastructure, albeit on a somewhat smaller scale than its support for core infrastructure investments. In a number of AsDF countries, this, as the evaluation states “seems to have helped to expand and improve urban and social services, increase rural connectivity and electrification levels, and enhance economic participation levels”. / The Bank’s Independent Evaluation Department (IED 2011 “Special Evaluation Study: The Asian Development Fund Operations – A Decade of Supporting Poverty Reduction in Asia and Pacific Region”, page iii) noted in its evaluation of the AsDF operations for 2001-2010 that the Bank had made solid progress on key operational commitments agreed with donors, although the promotion of good governance in AsDF countries remained a challenge. The IED report found that the AsDF operations had[1]: / Improved its gender focus during the period with 45% of project approvals including gender assessments and activities in 2010. However, a special IED (Independent Evaluation Department 2011) evaluation found that there is a need to have more specific gender classifications of projects (sex disaggregation at project and programme levels) during implementation and monitor results better, / Increased its focus on private sector development from 9% of operations in AsDF VII to 16% in AsDF IX, and then to more than 20% in the first two years of AsDF X, / Increased environmental sustainability as a theme to 30% of operations in the first two years of the AsDF X, / Improved its work on harmonisation and alignment (both are key Paris Declaration targets) and reduced the number of parallel project implementation units to link more closely with the systems of the partner country (strengthen country ownership as evidenced in OECD/DAC’s “Paris Declaration Evaluation” 2011). / Regional cooperation and integration was more prominent in its operations, with an increased focus on regional cooperation projects, from 7% in AsDF VIII to 31% in AsDF X. However, the success of regional programmes is mixed and largely dependent on the level of interest of participating countries and their incentives for cooperation. / However, the evaluation noted that the performance of public sector management operations, which account for a significant share of AsDF projects with governance objectives, was not satisfactory with a success rate of 54%. / The AsDF was assessed in the 2011 MAR as providing very good value for money, with a strong poverty focus and a good results framework, which provides comprehensive reporting on broad development outcomes and the effectiveness of AsDB programs and the efficiency of operations. An evaluation study of AsDB’s processes, “Managing for Development Results” (2011), found that this system is generally being used successfully within AsDB. AsDB’s results-based management was also rated highly in the 2010 MOPAN report and in AusAid’s “Multilateral Review 2012”. / In terms of the link between AsDF outputs and outcomes, on-going internal reforms within the Bank are expected to contribute to the Bank performing more efficiently and effectively through improved business processes, including programming and operational aspects such as HR (skills, capacity, institutional learning) and financial management. The Bank has made significant progress on internal reforms over recent years (AsDB “Development Effectiveness Review 2012), which has led to a clearer strategic focus and more results-oriented and transparent business processes as well as better organisational structures, including improved allocation of staff to country offices. / In summary, we assess that the Bank’s implementation of the AsDF X over the period 2009 – 2012 has contributed to poverty reduction in the poorer countries of Asia. However, it’s not possible to demonstrate a direct attribution link between the outputs of the Bank’s programme and the longer term development outcomes and impact in the AsDF countries. Evidence provided above does indicate that the AsDF provided a plausible contribution to the socio-economic development of the region, including poverty reduction through infrastructure and institutional investments in the AsDF-eligible countries. It also plays a role in climate change investments and regional collaboration and integration. / 1.4 Impact / The UK’s support to the AsDF is based on the following situation in Asian low-income countries: / the development gap between AsDF countries and other countries in the region is widening, which could undermine social cohesion and political stability in the region; / income poverty persists, with almost 60% (314 million) of the population living on less than $2 a day and 27% (about 148 million people) living on less than $1.25 a day and vulnerable to slipping back into absolute poverty; / AsDF countries are on track to achieve only just over one third of the non-income MDGs by 2015. / The MAR highlighted that reports from partner countries in the region also strongly supported the view that “AsDF is critical to delivery of the MDGs”, in particular the Bank’s high volume of financial support, focusing on poverty reduction, and strong involvement in both rural and urban development. DFID’s country visits to Bangladesh, Nepal and Tajikistan during the 2011 MAR found that its clear strategic focus, together with the size of its contribution make it a valued partner for delivering broad based economic growth and improving infrastructure that is so important for improving the quality of and access to services. / AsDF countries are constrained in their ability to deal with these challenges because they lag in economic and social infrastructure and suffer from weak governance and institutions as well as an environment that is not conducive to private sector development and investment. They are also vulnerable to high and volatile food and fuel prices, natural disasters and to the adverse effects of climate change. Recent evidence e.g AsDB “Strategy 2020” (2008), “Asia 2050; Realising the Asian Century” (2011) and the “UN MDG Report” (2010) indicates that there are more people in all of Asia living on less than a $1.25 than in Africa. Despite record growth in Asia, social exclusion has constrained poverty reduction. For the Asian low income countries which receive ADF funding, poverty is especially persistent with almost 60% (314 million) of the population living on less than $2 a day and 27% (about 148 million people) living on less than $1.25 a day and vulnerable to slipping back into absolute poverty. / AsDF countries as a group are only on track to achieve just over one third of the non-income MDGs by 2015. Additional progress is within sight but will require renewed efforts. Based on a set of 14 indicators covering education, health, and water and sanitation, AsDF countries as a group are on track to achieve only five (36%) of the non-income MDGs by 2015 and are close to achieving another two (14%). There are specific MDG indicators where AsDF countries are clearly lagging behind. For example, the maternal mortality rate in AsDF countries at 348 per 100,000 live births is more than twice as high as that in countries borrowing form the AsDB on non-concessional terms (153). The under-5 mortality rate at 74 per 1,000 live births is also much higher than in OCR countries (44). Child malnutrition is more acute in AsDF countries with 36% of children underweight, compared with 28% in OCR countries. The comparative figure for Sub-Saharan Africa is 27%. / Sustained economic growth is necessary for making substantial progress in reducing poverty and reaching the Millennium Development Goals (MDGs). Yet, growth in AsDF-eligible countries has been consistently lower than in other parts of developing Asia, thereby contributing to the increasing development gap and uneven progress toward the MDGs in the region. In addition, the on-going global economic crisis has dampened growth in the region. / In order that the AsDF is able to continue to contribute effectively to the regions development outcomes in the coming years, the Bank has initiated a “scoping process” to develop a long-term strategic vision for AsDF, adapting the fund’s role, mandate and financing structure to the evolving economic and financial realities. This was discussed at the AsDF consultations at the 2013 Annual Meeting and is to be further discussed during the AsDF XI midterm review during the fourth quarter of 2014. On the financial side, the expected graduation of 10 countries from AsDF assistance by 2024 might reduce demand for AsDF resources by a quarter of the envelope (currently $3 billion a year), partly offset by the re-engagement with Burma which is estimated to receive $150 million a year. At the same time, resources available to AsDF are likely to diminish. The reduction of reflow-based resources (due to forgone principal from grants) will amount to $250 million annually, while the trend of total donor contributions and the volume of future transfers from OCR net income remain uncertain at this point and are closely linked with the debate on AsDB’s capital adequacy.
[1] Please refer to “B. Impact and outcome that we expect to achieve” for further details on the Bank’s operational performance and what we expect in terms of further improvements.

2. Spending profile and timescale
2.1 Was the spend profile detailed in the Business Case followed: Y/N / N/A. The funding commitment was approved before the introduction of the DFID Business Case. However, the spending profile was in line with that laid out in the project documents produced at the time and in an Instrument of Contribution agreed with the Bank, namely that payment will be in four equal instalments from 2009 to 2012 with an additional payment in 2010 contingent on good performance on gender targets (see below). / 2.2 Were any additional payments linked to good performance been triggered:Y/N/Not Applicable / Yes. / The £6.154 million payment that was contingent on good performance on specific gender targets was paid in 2010.

3. Evidence and Evaluation
3.1 Assess any changes in evidence / The Bank has good sources of evidence, e.g through reviews, evaluations and not least the annual Development Effectiveness Reviews plus the Annual Report for the Bank as a whole. Data collection however continues to be weak in partner countries as their capacity remains overall weak. The Bank conducts project evaluations regularly through its independent evaluation department and is now moving towards real-time evaluations, impact evaluations and formative evaluations. / In July 2013, DFID published the “MAR Update” which assessed the progress made by multilateral organisations, including the AsDF, in addressing key reform priorities identified by DFID in order to strengthen the multilateral system and ensure that the UK continues to get VfM from the multilaterals it funds. AsDF was assessed to have made reasonable progress with respect to the cross cutting issues of gender, climate change and strategic and performance management. Some progress has been made on results and cost and value consciousness. / 3.2 Set out what plans are in place for an evaluation. / A Mid-Term Review (MTR) was carried out during 2010 and a review of AsDF by the Independent Evaluation Department was presented to shareholders during the AsDF XI discussions in October 2011. The AsDF XI MTR in late 2014/early 2015 will include an assessment of the Bank’s performance through the AsDF mechanism.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Low / Did the Risk Rating change over the life of the project? Y/N / No
4.2 Risk funds not used for purposes intended / The risk is low as the Bank has robust financial oversight mechanisms and provides externally audited annual accounts. In its operations, the Bank faces different kinds of risks, including financial, operational and organisational risks. AsDB has a comprehensive risk management framework that is built on the components; Governance, Policies and Processes. The Bank also maintains an independent risk management group and has various management-level committees with oversight responsibility for and decision-making authority on risk issues. / The Bank has generally good audit procedures. The 2010 Multilateral Organisation Performance Network (MOPAN) report rated the AsDB as strong in areas of internal audits, organisation–wide external audits and its anti-corruption policy. However, MOPAN found that external audits at regional, country and project level were more of a concern. The Bank has acknowledged this and has taken steps to strengthen its internal capacity at country missions and is working with the borrowing countries in the region to strengthen their audit capacity. / The AsDB acts on alleged fraud and misappropriation through its Office of Anticorruption and Integrity. AsDB produces Annual Reports that present the accomplishments of the Office of Anticorruption and Integrity and it highlights achievements made on case screening and investigations, project procurement-related reviews, and learning and development. / Climate and Environment Impact / The Bank has a strong focus on climate and environment risk management. AsDB's long-term strategic framework for 2008-2020 (or Strategy 2020) identifies environmentally sustainable growth as a key strategic development agenda, and environment as a core area for support. The 2011 MAR concluded that the AsDB is taking a leading role in promoting low carbon economic growth, renewable energy and private sector finance for climate change in Asia and the Pacific. AsDB promotes and invests in sound environmental and natural resource management, while promoting green growth, low carbon development, and adaptation to climate change. The Bank’s current results framework includes climate change indicators, for instance reduction in CO2 emissions and support for clean energy, and reports on them annually. To date the AsDB has reduced greenhouse gas emissions by 2 million tons of carbon dioxide equivalent per year by promoting more efficient and cleaner energy operations. / In 2012, for the second year running, clean energy investments topped $2 billion (albeit outside the AsDF), achieving the AsDB’s Energy Policy target for 2013 earlier than anticipated. AsDB now reports climate change mitigation and adaptation finance using an approach developed jointly by the multilateral development Banks (MDBs). Using this approach, AsDB’s total climate finance in 2012 amounted to $3.3 billion, with $2.4 billion expected to contribute to mitigating climate change and $896 million to adaptation. Of the 81 completed sovereign and non-sovereign operations reviewed in 2012, 25% targeted environmental sustainability and almost all achieved significant results. / The Bank also plays an important role in knowledge provision and in developing country capacity to address the consequences of climate change through technical support, knowledge resources, and partnerships.

5. Value for Money
5.1 Performance on VfM measures / The Bank scored “Satisfactory” (on cost and value consciousness) in DFID’s 2011 MAR, which assessed that administrative costs were relatively low compared to some comparable multilateral development banks and that administrative budgets had been controlled as volume of loans and grants had increased significantly. However, there was limited evidence of emphasis on securing efficiency gains or driving down costs in the design of development projects. The MAR summarised the AsDF as a relatively low cost operation, with good internal controls, but needing to concentrate more on project level VfM. As evidenced in the 2013 MAR Update, the Bank has made some progress in responding to the MAR recommendations and has incorporated work on cost efficiency at project level as part of improving its business processes. The main outstanding actions for the coming year is to implement the recommendations from the 2013 AsDB Procurement Governance Review, with a focuson (i) adopting a risk-differentiated approach to procurement; (ii) involving procurement specialists early on in complex procurement; (iii) strengthening staff skills and capacity for procurement through accreditation, training, and outposting; and (iv) streamlining AsDB‘s procurement processes and measuring efficiency against minimum service standards. / Other external assessments confirm our MAR conclusions. For example, the AusAid Multilateral Review 2012 found that cost control and value for money figure adequately in AsDB’s routine processes of preparing and monitoring budgets for operational projects and organisational programs, and in oversight by senior management and the Board of Directors. The AusAid review confirmed that the AsDB’s overall administrative costs are low relative to most of the other multilateral development banks. The AusAid review also points out that AsDB contributes to their partner countries consideration of value for money. It does this through its country-level advice and technical assistance on budget preparation, public investment programs, public financial management, project management and procurement, and its project-level work, seeking cost efficiency in designs and cost savings in implementation, especially through requiring competitive tendering for procurement. The review scored this part of the Bank’s work as “strong performance. / VfM is a key UK priority for our engagement with the Bank and we are pushing for improved cost consciousness in regards to both the Bank’s administration and programme implementation. DFID is active in raising VfM issues at all levels: Board meetings, bilateral discussions, appropriate Bank Committee meetings and through our MAR process. The Bank has shown strong commitment to improve performance and impact and has improved its transparency and accountability by updating its Public Communications Policy and reviewing its Accountability Mechanism. AsDB has implemented many efficiency measures to achieve savings including improving Human Resource (HR) management) and streamlining business processes. / Organisational cost effectiveness is an explicit concern of AsDB. It publishes information about costs in the annual Development Effectiveness Review. As evidenced in the AusAid Multilateral Aid Review of the Bank in 2012, in recent years the AsDB’s administrative costs (as a proportion of lending) has been low by comparison with other multilateral development banks. The AusAid review gives the example, that in 2010, the AsDB’s administrative budget was US$439 million, approximately 2.7 per cent of total lending. By way of comparison, the World Bank’s administrative budget in 2010–2011 was approximately US$2.3 billion, or approximately 3.9 per cent of total International Development Association (IDA) and International Bank for Reconstruction and Development lending in part reflecting their greater investment in global knowledge products. We will analyse further the details and definitions of each of the MDB’s administrative budgets to be able to improve comparisons between the banks with the aim of further strengthening our push for the banks to demonstrate efficiency gains. / Examples of actions the Bank has taken over the last couple of years to achieve savings, reduce expenses and optimise use of resources include: i) improving human resource management, ii) streamlining business processes (see below), iii) outsourcing selected activities wherever cost efficient, iv) improving institutional procurement, v) strengthening information and communication technology systems, vi) introducing environment-conserving and space optimising initiatives, and vii) continuing the organisational review of individual departments to improve efficiency[2]. The recent revision of the Bank’s Results Framework (January 2013) is a vital tool for continued measuring of progress of the Bank’s operations and organisational improvements. / Project implementation has been identified as an area for improvement. Over the last two years, the Bank has intensified efforts to improve its operations in line with the initiatives defined by the Project Implementation Working Group in 2010. This includes, for example; involving sector experts more systematically to ensure quality of implementation of (especially) multi-sector projects, streamlining of business processes and actions to improve efficiency, focusing more on gender balance targets (in line with the Gender Action Plan) and further use of results-based work plans across the sector and thematic operational plans and supporting developing member country capacity. The UK is in full support of these on-going actions and we expect that they will contribute to further performance improvements that will be captured in the annual development effectiveness reviews. / Based on the above, the UK will proactively push for, and monitor, further improvements in the Bank’s management and accountability systems with a strong focus on delivering of results and achieving value for money in programme and administrative spend. This includes the Bank challenging and supporting partners to take a hard look at value for money in their policy and programme choices, including procurement. / 5.2 Commercial Improvement and Value for Money / In summary, this still needs greater pressure and the recent (2012) AsDF negotiations have been important for agreeing a move in this direction. Changing the mind-set from one of budget adequacy in its indicators of organisational effectiveness to budget efficiency is vital. Our UK representative will continue lobbying for this in the planning and budgeting processes. We will also share tangible examples from within DFID of what this means in practice. / AsDB’s approach to procurement is to ensure open and fair competition in all its tenders, so that it procures high quality goods and services at the lowest cost. It requires procurement of goods and services through “International Competitive Bidding”, with limited exceptions, similar to those used by the World Bank and other multilateral development banks. Ensuring high and consistent international standards is crucial to promoting better procurement by recipient countries and ultimately to greater use of country systems in line with the Busan outcome. AsDB and other RDBs work together closely and coordinate with the World Bank. They have acknowledged the criticisms of their procurement systems and accepted the need for a full review. This review of procurement policies and practices is being undertaken initially by the World Bank (to be finalised in 2014, although preliminary findings and recommendations will be discussed within the MDB group), and AsDB aims to use this to inform decisions about its own systems. / The UK will continue to push at all levels within the Bank to encourage AsDB procurement to move from being overly bureaucratic and compliance focused to one that seeks to add value and embrace innovation. Adding value is essential and would include not just greater attention to design and contract management, which is important, but also use of country systems. This is where we require a wider definition of the value for money in the terminology, which includes a sustainable development consideration and not one which is preoccupied with price alone. We will encourage AsDB to engage in the World Bank reform process as the Bank will inevitably have to embrace much of this under the banks’ harmonisation agenda. Rather than wait for the outcome of the World Bank review we will encourage AsDB to be rather more proactive in the interim period by developing capacity building strategies and procurement approaches which accommodate and facilitate rather than undermine this. However, there are challenges to setting meaningful procurement targets for the Bank as much of the procurement is undertaken by clients rather than by the AsDB itself. Key procurement activities are effectively outside the Bank’s direct control. We will continue to encourage the Bank to review processes to strip out waste and focus on ways of adding value/reducing process costs “lean procurement”. This could usefully include the adoption of e-procurement technologies (e-tender, reverse auctions etc.) and the development of new contract models which better link payments to performance and results. / We will also recommend the Bank to use qualitative evaluation criteria focus on quality/VfM and not just price within the bidding process. Another procurement initiative for the Bank which might add innovative ways of working could be to support the development of the local supply base (Small and Medium Enterprises - SMEs) in partner countries – breaking large contracts into smaller lots, minimum content level set aside for SME’s, or an increase in the “National Competitive Bidding” thresholds in countries or sectors where capacity merits. Simple initiatives like these are measurable and we will, through our direct contacts with the Bank (through DFID’s Procurement Department) and collaboration through the global networks on procurement, encourage the Bank to consider how to include this into their results framework processes. / 5.3 Did the funding represent Value for Money: Y/N Yes. / The 2011 MAR, conducted in the third year of AsDF X, assessed that AsDF provides very good value for money and plays a critical role in sustainable economic development in Asia and offers very good value for money for the UK’s aid budget. The Fund is assessed as an effective means for reaching the poorest in the region, especially through larger infrastructure programmes and investments in projects that help to accelerate economic growth and expand the access of women, children and the poor to quality basic services (education and health care), reliable electricity and clean water. / As set out within this report, the Bank has performed well against the results offer detailed in the AsDF X Donors Report in terms of meeting financial targets, delivery of development outputs and outcomes and progress on internal reforms. It has a clearer strategic focus and more results-oriented and transparent business processes as well as better organisational structures. This has made it easier to implement the MAR agenda as effectively as possible to ensure good performance and reforms contributing to good value for money for the UK. / Also during the AsDF X cycle, the 2012 Independent Commission for Aid Impact (ICAI) report on the “Effectiveness of DFID’s Engagement with the Asian Development Bank” found that DFID’s support is delivering benefits for the poor and has promoted a focus on areas such as inclusive growth, gender, climate change and operational effectiveness. DFID’s performance as a shareholder and a contributor to the AsDF provides assurance that money is spent well and as intended.
[2] Source: AsDB letter, signed by Director General Kazu Sakai, to DFID, PS Mark Lowcock, 12 April 2012 in response to his letter to the MAR institutions on “value for money in international development”.

6. Conclusions
The AsDF X (2009-2012) has contributed to development outcomes in the AsDF eligible countries. The Fund managed to provide the expected lending and grants over the period and most of the expected outputs were achieved and some, e.g. in transport, electricity and water and sanitation, substantially exceeding the 2009 expectations. However, due to delays in programming, implementation and reduced demand from AsDF countries on primary education, the achieved outputs in education (students reached) were substantially lower compared to the 2009 expectations. / During the AsDF X negotiations in 2009, the UK pushed for actions to improve the Bank’s effectiveness, including a stronger results focus. The Bank’s internal reforms to improve its operational and organisation effectiveness have resulted in improvements across the organisation, including country missions, and the results agenda is embedded in the organisation. Also, the Bank is taking actions to strengthen project readiness and implementation supervision to improve the figures on project success and outcome achievements. / The UK’s objectives for the AsDF X programming were broadly met, including additional funding to Afghanistan, more focus on poverty and results, comate change, gender and regional cooperation. DFID’s reform priorities for AsDB, which were set following the 2011 MAR, reviewed in the 2013 MAR Update and remain relevant for the AsDF XI (2013-2016) are: / Greater focus on inclusive growth in country strategies and projects, explicitly identifying the rationale and outcomes, including private sector projects, / Supporting partners to seek value for money in policy and programme choices, and to strive to reduce administration costs with explicit cost effectiveness measures, / Effective decentralisation of staff (and devolution of decision making) to support policy dialogue with partner governments, / Continued improvement in addressing the needs of girls and women through the design and implementation of projects, / Tackling climate change, including leveraging private sector finance for projects in low income countries. / Over the last year, DFID has increased its policy focus with the Bank on issues such as anti-corruption, fraud and due diligence. We will also continue to push the Bank to demonstrate how it seeks value for money in its policy and programme choices (e.g. in procurement) in partnership with the borrowing countries. / We will continue to engage with the Bank on inclusive growth, gender and climate change and encourage the Bank to integrate these issues further in programming. Although the Bank has demonstrated good progress in decentralisation and devolution of authority to country missions, there is still scope for improvements in project readiness and supervision. We will push the Bank on this as part of our engagement at Board and committee levels. / We will proactively engage with the Bank on the recently started consultations on the long-term future of the AsDF (longer term visioning). As part of that, we will aim for the poorest countries in Asia to continue to receive appropriate concessional lending and grants for the coming years. We will engage with the Bank and stakeholders on the issue of “graduation” from the AsDF as countries moves towards middle-income status (MIC) and seek innovative and flexible mechanisms that can respond to the changing needs and demands from the poorer countries in Asia (low-income countries – LIC). Our engagement and influencing on the AsDF’s future will be inter-linked to two other crucial consultation processes for the Bank: the mid-term review of the Bank’s 2020 Strategy and the discussions on the Bank’s capital adequacy/sustainable lending levels (OCR). Our aim will be for the Bank, and the AsDF, to remain a credible and relevant financial institution and development partner in Asia for the next decade.

8. Review Process
This Project Completion Review was done as a desk-study using 2013 MAR update, the Bank’s Annual Report 2012, the Constituency Report for 2012, the Development Effectiveness Report 2012 and other Bank documents. The review was done by Adrian Miller and Bo Sundstrom in consultations with Richard Edwards, the UK (Alternate Executive Director) representative at AsDB in Manila, and Bank staff.