Type of Review: Annual Review

Project Title: Mining Sector Reform Project

Date started:	19/10/2011[1]
[1] Declared effective by the World Bank

Date review undertaken: June – July 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Between 2011 and 2015 the UK is providing £27 million through a World Bank-managed single donor trust fund for the ‘Growth with Governance in the Minerals Sector’ (ProMines) Technical Assistance Project in the Democratic Republic of Congo. It has also allocated an additional £0.5 million to share the costs of a senior mining specialist within the Bank’s Kinshasa office for Project management and sector coordination. The World Bank is contributing $50 million (£33 million) to the Project. / The UK also provides £1.24 million for General Support to the Minerals Sector of which the remaining £1.02 million was incorporated into this project from the Pilot Phase for DRC Minerals programme as a no cost extension in December 2012. Past activity against this funding line (before it was incorporated into this project) has, amongst other things, included support for an IMF Conference on Managing Natural Resources, an artisanal and small-scale mining review and support for ProMines preparations. DFID is in the process of identifying other possible activities that would complement and enhance the support through the World Bank, including support to civil society.

What are the expected results?
The intended impact of the project is to improve governance of the mining sector and increase its contribution to economic growth, sustainable development and poverty reduction. / At the outcome level, the project intends to strengthen the capacity of key institutions to manage the minerals sector, improve the conditions for increased investments and revenues from mining, and help increase the socio-economic benefits from artisanal and industrial mining. / At the output level, the project intends to: / Improve conditions for access to mineral resources to encourage increased investments in and revenues generated by the mining sector. / Strengthen the Government's capacity to manage the mineral sector. / Enhance transparency and accountability in mining sector revenue flows. / Improve the management of the social and environmental impacts of mining activity, both at the industrial as well as at the artisanal mining level.

What is the context in which UK support is provided?
DRC is a country with vast mineral wealth. According to World Bank calculations, the mining sector could contribute around 15-20% of GDP and 25% of Government revenues by 2020[2]. However, critical problems in the way in which the mining sector is governed have meant that the revenues generated from the sector have not been used effectively to contribute to sustainable economic development in DRC. / Rent-seeking and corruption, insufficient institutional capacity, lack of credible information on mining sector assets, a weak policy, legal and regulatory framework and ongoing conflict in the East have all contributed to the dysfunctional administration of the sector at the national level. The role of State-Owned Enterprises (SOEs) in mining sector deals remains a source of controversy. At the local level, artisanal miners face challenges related to their access to mining areas, their illegal taxation by a multitude of private/ armed group and public state security actors and the support they receive from the Supervision and Assistance Service for Small-Scale Mining (SAESSCAM - Service d'Assistance et d'Encadrement du Small Scale Mining). Artisanal and Small-scale Mining (ASM) sites are also associated with serious environmental and social problems, including child labour and the sexual exploitation of women. Finally, Congolese NGOs active in this area often lack resources and expertise to hold government and companies to account. / A number of developments have taken place since the last Annual Review. The IMF suspended its programme in late 2012 over insufficient mining sector contract transparency by the GoDRC. And even though the January 2013 Lubumbashi Conference, attended by both the President and the Prime Minister, was considered useful, follow-up has been limited. The business environment for mining companies has also become more challenging given the ad hoc introduction of export taxes and bans on concentrates and continued instability in the East of the country. This could be further accentuated should DRC not achieve EITI compliant status by April 2014 and be de-listed from the process.
[2] Figures from World Bank ProMines Project Appraisal Document

## Section A: Detailed Output Scoring

Output 1: Improve basic conditions for access to mineral resources to encourage increased investments in and revenues generated by the mining sector
Output 1 score and performance description: / A (Outputs met expectation)
Progress against expected results: / Expected results / Indicator Milestone Progress Substantially not met / Moderately not met /Met / Moderately exceeded / Substantially exceeded / (A1) Geodesic System 2012 Very limited geodesic network with 35 points exists in the south; system does not exist in north and centre of the country / 2013 Detailed plan for national coverage developed A literature review has been completed. / ProMines is in the process of hiring an international firm who will develop the plan for national coverage. This is on track to be completed by December 2013. Met / (A2) Availability of geological information for the country 2012 Contract for design of geological database awarded / 2013 Design of geological database completed The contract for the design of the geological database was awarded to MRAC in March 2013. / Preliminary reports have been produced to support the design of the database. / The design consultancy is on track to be completed by end-2013. Met / (A3) Communication and information flow within the sector including consultations with civil society 2012 The preparatory work to put in place the platform of accountability is launched (preparation of ToRs, preparatory meetings held) / 2013 The Congolese Government has formalised the creation and put in place the platform of accountability in the mining sector There are two platforms which are of relevance under this indicator. / 1) Lubumbashi Conference: In January 2013 the Government of DRC held a national conference on transparency and governance in the mining sector, which was widely attended by stakeholders from civil society, the mining sector and the government. / 2) ProMines Platform of Accountability: The final decree for agreement on the platform of accountability is currently with the Prime Minister for signature Met / (A4) Revision of the mining code and development of mining regulations integrates all stakeholders' recommendations (Government, Civil Society and private sector) 2012 Independent revision by the three stakeholders with the recruitment of a local consultant to assist the government and financial assistance for a meeting of civil society. / 2013 Recruitment of an international consultant to mediate on the recommendations of the three stakeholders. A local consultant was successfully recruited in October 2012 to coordinate consultations on the revision of the Mining Code. They produced a report containing the views of all the stakeholders. / The recruitment process for an international consultant to review the Mining Code is currently well underway and the consultant is due to start work in September. / The schedule agreed for revision of the Mining Code has been circulated by the Minister for Mines. Met / Comment / Progress against this output has met expectation, with milestones for all 2012 indicators met, and those for 2013 on track to be met by December 2013. Nevertheless, a number of milestones to be achieved by the end of the year are dependent on the successful recruitment of consultants. / It is unclear how the ProMines Accountability Platform relates to the Government-led Lubumbashi Conference, which already performs a number of functions foreseen in the Accountability Platform. The Government-led conference agreed to the principle of a national accountability platform with government participation and since February 2013 has had seven follow-up meetings. A Ministerial Decree is in the process of being finalised related to this, although a decree for the Accountability Platform is also with the Prime Minister for signature. / Recommendations: / Effort should be made by the Project Implementation Unit (PIU) to ensure that these processes are kept on track in order to ensure delivery of milestone results. / To ensure transparency in the sector, communication will be a crucial part of increasing accountability. It is recommended that ProMines re-considers its strategy for promoting communication and the flow of information for 2013 and 2014, including its plan for engaging with and possibly supporting the Lubumbashi Conference. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Strengthen the Government's capacity to manage the mineral sector
Output 2 score and performance description: / B (outputs moderately did not meet expectation)
Progress against expected results: / Indicator Milestone Progress Substantially not met / Moderately not met /Met / Moderately exceeded / Substantially exceeded / (B1) Presence and capacity of CAMI (Mining Titles Registry) 2012 Plan for strengthening CAMI's presence in 3 target provinces developed and endorsed by the Minister of Mines / 2013 One fully-functioning CAMI office at provincial level Terms of reference and a plan for the strategy were produced by CAMI and approved by the Minister of Mines. / One CAMI office in Katanga Province and one in Bukavu is now up and running, but neither of these are linked to the flexi cadastre IT system and are unlikely to be by the end of 2013. They can thus not yet be deemed to be fully functional. Moderately did not meet expectation. / (B2) Capacity and performance of SAESSCAM (Government Service to Support Artisanal Miners) 2012 National plan for SAESSCAM restructuring developed / 2013 Plan for SAESSCAM restructuring adopted by GoDRC The design of the plan for SAESSCAM restructuring is still underway. This will be informed by the recommendations in the recently completed Institutional Audit. Substantially did not meet expectation. / (B3) Status of technical and professional training institutes and programmes in Katanga 2012 Technical institutes in Katanga are run down and their programmes are not adapted to modern industry requirements / 2013 Improvement plan for technical institutes and university programmes developed and agreed. / Upgrading of selected institutes and university programmes being carried out in accordance with agreed plan. There are two areas of activity under this indicator. / Technical Institutes: The improvement of the professional centres in Katanga and Bukavu is well underway, with a 1st report already completed. / University Programme: Progress on the upgrade of universities has been more limited. A review of proposals following tender is currently being undertaken. The contract for the review and development of the improvement plan will be awarded shortly. It is not anticipated that the plan will be fully operational until next year. Moderately did not meet expectation. / Comment / The overall results under this output have moderately not met expectation. / The delay to the national plan for SAESSCAM restructuring (indicator B2) has been considered necessary in order for this activity to be informed by robust analysis and information. The Institutional Audit (a separate activity) in particular has provided a large amount of valuable information which will need to be considered as part of the reform of mining sector institutions. / Recommendations: / Going forward, more emphasis will need to be placed on the links between the Institutional Audit, including SAESSCAM, and the Mining Code revision as well as the resulting timelines for each activity to make sure processes are aligned. / A milestone or indicator relating to institutional effectiveness could usefully be included in the logframe to allow the capture of activity surrounding the institutional audit, and set out the next steps. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: Strengthen the Government's capacity and accountability in mining tax collection
Output 3 score and performance description: / C (Outputs substantially did not meet expectation)
Progress against expected results: / Indicator Milestone Progress Substantially not met / Moderately not met /Met / Moderately exceeded / Substantially exceeded / (C1) Production of Extractives Industry Transparency Initiative (EITI) reconciliation reports for increased transparency of mining sector 2012 Government and mining sector companies provide necessary information for cobalt, copper and one other resource for EITI reconciliation report for FY 2010. Recommendations from previous report acted on. / 2013 Government and mining sector companies provide necessary information for cobalt, copper and one other resource for EITI reconciliation report for FY 2011 recommendations from previous report acted on. EITI DRC adopted its 2010 EITI report on 15 January 2013. The EITI Board found that DRC had made significant progress with EITI implementation, but that it had not reached full compliance with requirements. DRC's candidate status was therefore suspended from 18 April 2013 for a year. / Efforts are now underway to ensure that the 2011 Report is completed by December 2013. Moderately did not meet expectation / (C2) Status of tax collection framework for mining sector 2012 Inventory of mining sector related taxes (formal and informal) and procedures for payment. / Training programme to reinforce proper implementation of tax regime developed / 2013 Modelling of mining taxation revenues No inventory completed. / A request has been received from the Secretary General of Mines for training of tax collectors. Terms of reference for the recruitment of a consultant to deliver the training are currently being drafted. Substantially did not meet expectation / (C3) Operational status of mechanisms for traceability and certification of minerals 2012 Support to initiatives underway namely the certification process of ICGLR and mapping of mine sites with IPIS / 2013 Financial support continues with projects from 2012 with additional financing to support the capacity of SAESSCAM in three provinces (Katanga, Maniema and South Kivu) 100,000 ICGLR certificates were acquired. These were launched in July 2013 with implementation expected within 3 months. / Data collection for the first IPIS map is complete. The first mapping report is due by mid-July. / The tender for a consultancy comparing the various traceability and certification systems has been launched. / Additional financing to support SAESSCAM has been deferred pending the institutional review. / ProMines has undertaken additional activity against this indicator, including coordination meetings on interventions in Eastern DRC and drafting terms of reference for the validation and certification of mines in Eastern DRC, in collaboration with BGR. Met expectation. / Comment / Results against indicator C1 moderately did not meet expectation, but it is recognised that the direct contribution ProMines can make to the outcome of EITI is limited. Nevertheless, the National Secretariat has acknowledged that the ProMines contribution was vital to the publication of the 2010 Report. / It may be that extra activity which complements the ProMines contribution to the EITI process, for example working with Civil Society Organisations, will be identified and funded through the General Support to Minerals sector funds. / Results against indicator C2 substantially did not meet expectation and results attributable to ProMines are lacking. What is more, there appears to be a limited understanding of how this project complements and fills the gaps of existing initiatives related to revenue collection, as foreseen in the Project Appraisal Document (PAD). Given the importance of this indicator to the overall output, it is judged that despite progress against the other two indicators, the overall progress against output 3 has substantially not met expectation. / Under indicator C3 some additional activity occurred. The project recognised the need to respond quickly and positively in support of the certification and traceability processes for mines in Eastern DRC. / Recommendations: / The success or failure of EITI in DRC is a high level outcome that cannot be fully attributable to ProMines activity, and over which ProMines has limited control. The project will hence need to consider where EITI related indicators are best placed to appear on the logframe.. / Progress against indicator C2 has been poor. ProMines activity in this area should be urgently revisited, and consider where the project can best add value. Furthermore, attention should be given to how possible future activity under this indicator can maximise synergies with the revision of the Mining Code, EITI reporting processes and the reform of mining sector institutions. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 4: Develop innovative approaches to improve socio-economic impacts of artisanal and industrial mining in three provinces
Output 4 score and performance description: / C (Substantially did not meet expectation)
Progress against expected results: / Indicator Milestone Progress Substantially not met / Moderately not met /Met / Moderately exceeded / Substantially exceeded / (D1) Monitoring of social and environmental impacts of industrial mining activities involving the participation of local communities 2012 Social and environmental impacts of mining activities not well understood and managed / 2013 Assessment (SESA) carried out in target provinces. Identify suitable mechanisms for community participation. / Policy and institutional reforms to reduce environmental and social risks from expansion of the mining sector identified and agreed with community involvement A consultant has been recruited to undertake the social environmental impact assessment on the mining sector. An initial inception report has been produced, with the next report is due at the end of November 2013. / Additional activity has occurred against this indicator as the terms of reference for a study on the mining sector’s environmental footprint in Katanga have been drafted. Met expectation / (D2) Formalization of artisanal mining 2012 Action plan to strengthen regulation and management of the ASM sector and to improve conditions on and around ASM sites developed and adopted / 2013 Successful implementation of at least two pilots Terms of reference for a consultant for the registration of artisanal miners have been developed. / Terms of reference for four pilot studies in artisanal mining areas have been drafted. The pilots have not yet commenced. Substantially did not meet expectation. / (D3) Improvement in the capacity of women to organise themselves through a national network 2012 Study on the conditions for women in artisanal mines (through pilot projects) / 2013 Launch a national network for women in the mines Study on ‘The Work of Women and Children on the Artisanal Mining Sites in Kolwezi’ was completed in June 2012 by the Nordic Trust Fund in association with the World Bank. / The intension to form a national network for women working in the mining sector was expressed in an official meeting with the Minister of Gender and was well received. Little progress has, however, been made to date on the establishment of such a network and it is judged that the network will not be fully functional by end-2013. / Terms of reference for four pilot studies in artisanal mining areas have been drafted but the pilots have not yet commenced. Substantially did not meet expectation / (D4) The work and presence of children in artisanal mines is reduced through a multi-sectoral strategy in the specific zones of the project (to be defined) 2012 Preparatory study in Kolwezi in Katanga province serves as a model to elaborate the strategy / 2013 One artisanal site of exploitation puts in place a strategy of prevention and improvement of the situation for children with accurately defined. Study on ‘The Work of Women and Children on the Artisanal Mining Sites in Kolwezi’ was completed in June 2012 by the Nordic Trust Fund in association with the World Bank. / There has not yet been any progress on the pilots Substantially did not meet expectation. / Comment / Progress against the 2013 milestones for indicators D2, D3 and D4 have been limited and milestones are not likely to be achieved before December 2013. Progress has been mostly around process (drafting ToRs, tendering etc.) rather than any achievements of substance. / Terms of Reference for the development of the Katanga Extractive Industries Development Initiative (KEIDI) have been launched, but progress against this activity is not yet captured in the logframe. / Recommendations: / The results against indicator D1 will continue to be an integral and important part of the entire project. ProMines needs to ensure that findings of the SESA inform all project activity, and that links to other reforms in the mining sector, particularly to the Mining Code, are maximised. / Whilst the study on the work of women and children in artisanal mining sites in Kolwezi was useful as a pilot study, it is considered to be limited in scope. More wide ranging studies should be undertaken in order to build a more comprehensive evidence base. / An indicator related to the development of KEIDI should be introduced to adequately capture progress against this activity. / The four pilot studies in artisanal mining areas will need to be taken forward as a matter of priority. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? / Yes, the risk rating of output D was changed at the point of the logframe review from medium to high to reflect the instability in Eastern DRC

Output 5: Establish monitoring and evaluation (M&E) framework for evaluating project implementation and its impact
Output 5 score and performance description: / B (Outputs moderately did not meet expectation)
Progress against expected results: / Expected results / Indicator Milestone Progress Substantially not met / Moderately not met /Met / Moderately exceeded / Substantially exceeded / (E1) M&E framework established 2012 M&E framework developed and agreed with all relevant stakeholders; baseline data collection / 2013 Implementation of M&E system. Biannual project monitoring reports produced. Biannual project supervision missions with participation from range of stakeholders Final stages of the set-up of the M&E database have been completed but the system has not been implemented yet. Biannual project monitoring reports are being produced, and supervision missions are occurring around three times a year with the participation of a range of stakeholders Moderately did not meet expectation / (E2) Availability of household economic data for mining areas 2012 Mining areas covered in 1-2-3 survey / 2013 Data (for 2012) available and disseminated. The 1-2-3 survey took place in 2012 and upload of the survey results began in April 2013. / Sections of the report relevant to the mining sector have been received. / The final report has not yet been disseminated by the Minister of Planning Met expectation / Comment / Under Indicator E1 there has been some progress. However, M&E reports are still judged to need strengthening in order to make this the fully robust monitoring and evaluation system that was anticipated. / Under Indicator E2 it has been decided that there is no longer any need to commission and conduct the project’s own baseline survey in these areas. This will be too expensive and time consuming to represent value for money. Instead baseline surveys will be conducted in areas where activity is taking place. / Recommendations: / Consideration should be given to the structure and content of internally produced M&E reports so that they provide all the information needed for DFID and World Bank central requirements. To include: / Monitoring of disbursement figures, disaggregated by donor / Short narrative on value for money (vfm) measures and performance against these, including any examples of where costs have been driven down, if possible. / Short update on assessment of risk to date. / The M&E function of ProMines as a whole needs to be strengthened. Consideration should be given to how this improved capacity and capability can best be achieved. / Impact Weighting (%): 5% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? / Yes. There were a number of recommendations relating to logframe revisions in the last Annual Review, and the logframe has been updated to reflect these as follows: / Milestones have been shifted by 18 months to reflect the actual start date of the project / A new indicator (A4) has been introduced to reflect the work being done on the revision of the Mining Code. / In indicator A3, the Accountability platform has been introduced as a concrete milestone / In indicator C3, more explicit reference has been made to certification and traceability work / A new indicator (D3) on women has been introduced to reflect this as a priority area. / Similarly, a new indicator (D4) on children has been introduced. / The risk rating of output D has been changed from medium to high to reflect the instability in Eastern DRC / Overall Output Score and Description / B (Outputs moderately did not meet expectation) / Direct feedback from beneficiaries / There is limited beneficiary feedback available as the project is still in the analysis / study phase. However, the Minister of Mines has appreciated ProMines support provided for the sourcing of ICGLR Certificates. The national EITI Secretariat has also been grateful for ProMines flexible support towards the compilation of the 2010 Report. Mining Companies and Civil Society Organisations appear assuaged over the fact that the revision of the Mining Code will contain a more open process of consultation thanks to ProMines support than would otherwise be the case.
Summary of overall progress / The project has made some progress since the last Annual Review. The logframe revision, agreed by all parties, has meant that milestones are now more accurate, reflecting the later start date of the programme. However, despite these revised milestones, the project continues to perform below expectations.
1.5 Key challenges / The following three areas present key challenges for the successful achievement of the project’s objectives: / The context in which the project is operating is becoming more complex and difficult / A number of developments have taken place since the last Annual Review. The IMF suspended its programme in late 2012 over insufficient mining sector contract transparency by the GoDRC. And even though the January 2013 Lubumbashi Conference, attended by both the President and the Prime Minister, was considered useful, follow-up has been limited. The business environment for mining companies has also become more challenging given the ad hoc introduction of export taxes and bans on concentrates and continued instability in the East of the country. This could be further accentuated should DRC not achieve EITI compliant status by April 2014 and be de-listed from the process. / The lack of an in-country Senior Mining Expert/ Task Team Leader coupled with the project’s move from the analytical to the implementation stage / Despite some action taken by the World Bank to increase its engagement on ProMines, DFID believes that current management arrangements fail to provide sufficient structure, direction and support to the Project Implementation Unit (PIU) and the project overall. This is primarily due to the lack of an in-country senior mining expert (see section on role of project partners), which unless addressed may provide an insurmountable challenge affecting the delivery of results. The project’s move from the analysis to the implementation phase will require even stronger management and oversight, therefore strengthening the case for an in-country Task Team Leader (TTL). / The broadening of ProMines scale and scope to cover additional areas / While DFID is in principle supportive of the potential extension of ProMines to cover for example the reform of State-Owned Enterprises, such an extension may turn out to be a threat to improved project delivery without increased World Bank resource in-country. This is underscored by the delicate yet robust handling this dossier will require given prevailing political economy constraints.
1.6 Annual Outcome Assessment / Although the trajectory of progress on ProMines has been in a positive direction, the programme is still not meeting expectations and is operating below potential. The project is therefore not currently on track to achieve its purpose by 2016, that is to strengthen the capacity of key institutions to manage the minerals sector, improve the conditions for increased investments and revenues for mining, and help increase the socio-economic benefits from artisanal and industrial mining. However, improved management arrangements in the form of an in-country TTL may provide the project with the necessary leadership and support required to meet its objectives. .

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / At the last Annual Review it was identified that project spending was not on track against original forecasts. This was largely a result of the delayed start date of the project. Two issues relating to ProMines disbursements were identified. / The first relates to appropriate split between DFID and World Bank (44.4% DFID, 55.6% Bank) disbursements. The project only drew on IDA/ World Bank funds initially, instead of the correct proportion of the two. The World Bank and the PIU have taken appropriate action to resolve this issue, so that DFID funds are now being disbursed at an increased rate, until the correct ratio is achieved. DFID will continue to monitor payments out of the Trust Fund to ensure this slippage does not happen again. / The second issue relates to DFID payments into the Trust Fund. The slow start to project activity meant that money was not being spent from the Trust Fund at the rate anticipated, and as such DFID payments became in advance of need. DFID has so far contributed £9 million (US $14,307,300) to the World Bank Trust Fund. In light of this, a revised disbursement schedule was agreed with the World Bank, and no more payments will be made by DFID into the Trust Fund until at least Q2 2014. / As at end-June US $ 7.4 m had been spent by ProMines, of which around US$ 3.2 m were DFID funds. This demonstrates that progress has been made compared to the same point last year – US$ 1.2 m of DFID funds had been spent by August 2012. Overall disbursement figures and projections, however, continue to support the understanding that there will not need to be another DFID contribution to the Trust Fund until at least Q2 2014. / 2.2 Key cost drivers / There have been no changes to the key cost drivers identified in last year’s review. Key cost drivers continue to be fees for the provision of professional services. World Bank procurement procedures are followed for all aspects of this project, with a high level of oversight. However, it is unclear to DFID what strategy is adopted to ensure that costs are driven down when awarding contracts. / 2.3 Is the project on-track against original timescale: N / As highlighted in the last Annual Review, this project was originally expected to become effective in September 2010, but the actual start was delayed to October 2011. A revised logframe with updated milestones to reflect the delayed start has been agreed with the World Bank. As noted in the financial forecasts section this had implications for spending and a revised disbursement schedule was agreed. The cost of the project is still set to remain the same.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Although after last year’s Annual Review questions were raised about the adequacy of the ProMines project design, it is judged that the theory and assumptions underpinning the project, and the project design itself, are still sound. The evidence for the need for Mining Sector reform continues to be strong, as outlined in the context section above. The multiple studies and assessments which are to be undertaken during the lifetime of the project, many of which have already occurred or are underway, will help contribute to the evidence base around the extractives sector in DRC. Those should in turn support improved future interventions, and other donor activity. / Nevertheless, there may be scope to improve the logframe’s reflection of the project’s focus and scope as part of the ProMines Mid-Term Review planned for March 2014. / 3.2 Where an evaluation is planned what progress has been made? / At the time of the last Annual Review, a monitoring and evaluation system was planned for the project, but was not yet in operation. Progress has been made on this, with quarterly monitoring and evaluation (M&E) reports received from the PIU and a M&E system having been developed. However, more work will need to be done to fully operationalize this system. / The ProMines Project Appraisal Document does not provide for one a separate impact evaluation, and as at the last Annual Review, one is not anticipated.

4. Risk
4.1 Output Risk Rating: / High / Assessment of the risk level / The following table, based on the risks identified in the original project memorandum , provides an overview of the main risks currently affecting successful project delivery: / Risk Probability Impact Mitigation Strategy / Uneven commitment/ political will for sector-wide reform High High Work with international development partners to achieve maximum influence over the GoDRC, including through the Groupe Thematique Mining, Hydrocarbons and Electricity and in consultation with the IMF / Politically back up the PIU on delicate issues such as the Institutional Audit and the reform of the Mining Code / Expand network of contacts in government, civil society and the private sector to inform debates through a number of entry points / Retain flexibility in terms of the project’s focus areas / Reputational risk High High Provide renewed impetus to ensure that ProMines is well-targeted, well-resourced internally, and well-managed by the World Bank / Conflict in Eastern DRC High Medium Retain flexibility in terms of the project’s focus areas / Strengthen coordination of interventions in Eastern DRC with partners operating there / Poor coordination with other sector interventions and activities and failure to take into account new developments High Medium Appoint in-country senior mining expert to better manage relationships with the Government, other donors, civil society and the private sector / Hold monthly donor coordination meetings / Share information and knowledge on ProMines widely and in a systematic manner / Actively seek to learn lessons from other donor projects in the sector / Map out other projects relevant to ProMines / The following risk originally identified in the project memorandum has come to pass. The original mitigation strategy has not been sufficient to prevent this risk from having an adverse impact on project performance. / Risk Mitigation Strategy / Reduced engagement from the World Bank following project approval, in particular the lack of a senior mining expert in Kinshasa Understanding with the World Bank that a senior mining expert will be based in Kinshasa during Project implementation / DFID will therefore seek to broker a new understanding with the World Bank, in line with the original one.
Risk of funds not being used as intended / The Project Appraisal Document (PAD) outlined a number of ways in which the risk of funds not being used as intended would be mitigated and these remain relevant. In addition to the standard Project Implementation Manual and Procedures Manual, a Governance and Anti-Corruption Action Plan was developed. This addresses both sector and project risks. / DFID funds through the World Bank Trust Fund are subject to World Bank financial management and audit procedures outlined in the PAD. World Bank procedures were judged to be robust in DFID’s Multilateral Aid Review. / As outlined above, it was noted that the delayed start to the programme meant that DFID payment into the World Bank Trust Fund was occurring in advance of need. This situation has been remedied by the agreement of a revised disbursement schedule. No further payments are scheduled until at least Q2 2014 when activity is judged to have caught up with funds. / Climate and Environment Risk / A history of industrial and artisanal mining has caused severe environmental degradation in DRC and a legacy of abandoned, un-restored sites, seriously eroded surfaces and contaminated watersheds. Authorised mining, but also more significantly illegal mining, presents serious challenges in terms of threats to the conservation of primary tropical forest and endangered wildlife species. Artisanal and small-scale mining can also be the cause of very serious health impacts, which serve to aggravate the environmental drivers of poverty. These hazards and risks are well known, and were identified in the initial project documentation, and again in the last Annual Review. It remains the case that most can be managed and mitigated. / The Mining Code requires that conventional environmental instruments (EIA, MRP and EMPP) are used, and that international codes of best practice are complied with. However the reality on the ground in DRC is that these are hard to both apply and enforce – a result of the weak environmental governance existing at all devolved levels, and the fact that the artisanal sector operates outside any regulatory framework. / ProMines is an enabling Project, which aims to create a climate for investment and growth in the mining sector while formulating a basis for strong environmental governance. As such it has no direct impact on the environment but technical assistance work facilitating mining development raises the prospect of indirect environmental impacts – as noted in the last Annual Review, the outcome is only one step removed. / Through technical assistance provided by ProMines this project is working to strengthen institutions, environmental legislation and regulatory processes, and promote new, environmentally friendlier mining technologies as appropriate. Since the last Annual Review some progress has been made on this. An international consultant has been procured to undertake a Strategic Environmental and Social Assessment which will identify the environmental and social impacts related to mining growth. The findings of this assessment will then inform the drafting of new environmental legislation and regulatory instruments. The international consultant’s first preliminary report is expected by October 2013 / Gender Review / Following a snapshot gender review using DFID DRC methodology it emerged that gender considerations will need to be given more weight going forward. DFID will do so by engaging pro-actively on the association of women working in the mining sector as well as the pilot study related to improving the conditions for women in mines.

5. Value for Money
5.1 Performance on VfM measures / As noted in the PAD, the project is a predominantly technical assistance project and so does not lend itself easily to economic analysis. Economic benefits and value for money measures are currently around leveraging, and the intention is that project activity will firstly strengthen the government’s capacity to more effectively manage the mining sector, thus increasing the sector’s contribution to revenues, and secondly, will help make the mining sector in DRC become more attractive to investors adhering to recognised responsible business values and practices, thus further increasing the revenues generated by the sector. Revenues can then be re-invested in poverty reduction. Conventional cost : benefit analysis cannot be applied to this as many other factors and inputs contribute to revenue generation, and so benefits cannot wholly be attributed to this project’s activity. / The key Value for Money measure for this project at the time of the economic appraisal was that project expenditure of US $ 90 million could help to leverage additional gross revenues to the mining sector with a value of US $8.1 billion. This is turn would create additional fiscal receipts with a cumulative value of US $2.8 billion by 2020, leading to additional poverty spending of $362 million. / The outcome indicator “Revenues from the mining sector collected at export point” was used as a proxy indicator for the expected increases in total revenues. Since the last Annual Review it had been judged that the strength of this indicator is limited, due to a poor baseline and a lack of tinely and adequate methodology around data collection for this figure. As such, the outcome indicator has been revised to be “Total fiscal revenues collected from the mining sector”, with the milestones used in the original economic appraisal in the Project Memorandum used as an indicator of progress (see the table below) / $ Millions, 2010 Net Present Value 2010 2011 2012 2013 2014 2015 2016 2017 2018 2019 2020 2021 Total / Base Scenario / Gross Revenue 1,415 1,382 1,541 2,245 3,009 3,157 3,597 3,450 3,138 3,097 3,115 29,146 / Fiscal Receipts 144 146 254 271 406 460 527 507 409 657 677 4,458 / Poverty Spending 13 19 33 35 53 60 69 66 53 85 88 574 / Improved effectiveness scenario compared with base scenario / Gross Revenue - - - - - - - - - - - - / Fiscal Receipts - - 6 24 37 79 92 107 103 82 135 140 805 / Poverty Spending - - 1 3 5 10 12 14 13 11 18 18 105 / More investment scenario over and above improved effectiveness scenario / Gross Revenue - - 194 465 1,029 1,099 1,096 1,075 1,095 1,062 1,027 8142 / Fiscal Receipts - - 36 38 81 265 276 271 259 258 251 242 1977 / Poverty Spending - - 5 5 10 35 36 35 34 34 33 31 258 / Milestones total fiscal receipts (Improved effectiveness plus more investment scenarios), 2010 Net Present Value 144 146 296 333 524 804 895 885 771 997 1063 382 7240 / Adjusted NPV milestones 317 / (2012 NPV) 369 / (2013 NPV) / Discount rate 3.50% Source: ProMines Project Memorandum Economic Appraisal – with scenario milestones adjusted to reflect delayed start date. / The improved effectiveness scenario and more investment scenario milestones have been shifted by one year to reflect the delayed start date. Total revenue collected from the mining sector in 2012 was US$ 382 m [3] which exceeds the shifted Economic Appraisal Milestone for 2012 of US $317 million (2012 NPV). Revenue for the first quarter of 2013 was US$ 123 which indicates that that fiscal receipts are also on track to meet the Economic Appraisal Milestone of US$ 369 million (2013 NPV) / Sensitivity analysis shows that even if higher discount rates are used, milestones would still have been met / be on track to be met. A 13% discount rate gives a 2012 milestone of US$ 378 million (2012 NPV) which is exceeded by the actual total revenue collected from the mining sector in 2012 at US$ 382 million. A 13% discount rate gives a 2013 milestone of US$ 480 million (2013 NPV) – revenue for the first quarter of 2013 at US$ 123 million would still be on track to meet this milestone. / It is important to reiterate at this point that increase in revenues in the mining sector as a whole are not fully attributable to ProMines – many other factors play a role. / 5.2 Commercial Improvement and Value for Money / For this project, spending is indirect via partner funding. The cost and value consciousness of the World Bank were both judged to be satisfactory in the Multilateral Aid Review. World Bank recruitment and procurement policies are adhered to during this project with a high level of World Bank oversight. However, it may be useful for DFID to explore possible strategies for driving down project costs with the World Bank. / 5.3 Role of project partners / Concerns about the World Bank’s engagement and performance were highlighted at the time of the last Annual Review. Some improvement has taken place since then in the form of: / Marginally increased staff resources: A part-time staff member based in Washington has been recruited to support the Task Team Leader on artisanal mining issues. / More frequent joint supervision missions: Missions are now taking place on a 4 to 5-month rather than 6-month basis. / Increased management engagement: The frequency of teleconferences between the WB, the PIU and DFID has increased, albeit from a very low rate. The Country Director has also been very supportive of the project. / Nevertheless, DFID judges that the above actions have not been sufficient for the World Bank to provide the vital structure and direction that the project needs. The continued lack of an in-country Task Team Leader (TTL) is in DFID’s view partially responsible for the project’s continued underperformance. This view is supported by the feedback provided by the PIU and other donors active in the sector. The high turnover of local World Bank staff providing operational support has further complicated management arrangements by creating disruptions that lead to further delays in project implementation. / There have also been a number of instances where the World Bank’s partnership behaviour, judged on the basis of DFID’s Multilateral Assessment Review (MAR) Framework Criteria, has fallen short of DFID’s expectations. Areas of particular concern include the work in partnership with others and the flexibility demonstrated to enable and reinforce a country-led approach. / Going forward, given ProMines’ inherent complexity, and the challenges and risks set out in sections 1.5 and 4.2., DFID considers that only an in-country, full-time Senior Mining Expert/ Task Team Leader dedicated to the project with not only technical knowledge on mining sector issues, but also broad competencies in leadership, strategic thinking, open collaboration with partners, diplomatic skills will be able to ensure that the project fully meet its objectives by 2016. / 5.4 Does the project still represent Value for Money : / The design of the programme and budget needed to deliver this is still judged to be sound and progress towards achieving outputs has been made. As such the project is deemed, at this point in time, to still represent Value for Money. The comparison above between fiscal receipts from the mining sector and the milestones in the original economic appraisal suggest that the project is achieving the expected vfm against the original measure, albeit to a revised timescale due to the delayed start. / However, given the problems with the project partner highlighted above, there is a risk that if this the project could cease to represent value for money due to slow or non-achievement of its objectives. / 5.5 If not, what action will you take? / New corporate rules require DFID projects that are failing to improve substantially (scoring a B following a C), such as ProMines, to introduce Performance Improvement Plans (PIP). A decision six months after the last Annual Review on whether to continue, restructure or exit a programme will also need to be taken. / DFID will therefore continue to press the World Bank to address the issue of an in-country Senior Mining Sector Expert/ Task Team Leader highlighted above and introduce a six-month Performance Improvement Plan for the project following this Annual Review. The success on both of these areas will determine the decision in February 2014 whether to continue, restructure or exit ProMines. This will also coincide with the ProMines Mid-Term Review.
[3] Source: Ministry of Finance: Comité Technique de Suivi & Evaluation des Réformes, CTR en sigle

6. Conditionality
6.1 Update on specific conditions / n/a

7. Conclusions and actions
Overall, despite the progress made since the last Annual Review, the project continues to perform below expectations. DFID considers this to be in part due to the lack of strong management, leadership and support to the project from the World Bank in the form of an in-country Senior Mining Sector Expert/ Task Team Leader (TTL) . / DFID will therefore continue to press the World Bank to address the issue of an in-country, full-time TTL with not only technical knowledge on mining sector issues, but also broad competencies in leadership, strategic thinking, open collaboration with partners and diplomatic skills. The need for an in-country TTL is further substantiated by the fact that the project will soon move from the analytical to the implementation stage, that it is operating in an increasingly difficult environment, and by the additional challenges that are presented by the planned broadening in the scale and scope of ProMines to cover the reform of State-Owned Enterprises. / DFID will also seek to agree a six-month Performance Improvement Plan following this Annual Review. The success on both of these areas will determine the decision in February 2014 whether to continue, restructure or exit ProMines, in line with new Corporate Rules. This will also coincide with the ProMines Mid-Term Review. / The remaining key recommendations and action points that follow from this Annual Review are as follows: / Specific changes to the output level of logframe identified in section 1 should be adopted. They include the introduction of indicators or milestones that monitor progress against the institutional audit and the Katanga Extractive Industries Development Initiative (KEIDI), a review of the indicator relating to ProMines’ contribution to the Extractive Industries Transparency Imitative (EITI) process and a consideration of ProMines’ potential contribution to the fiscal framework for the mining sector. / A more comprehensive review of the logframe will also need to be undertaken as part of the 2014 Mid-Term Review to ensure that the logframe adequately reflects the project’s scope and focus. / Gender aspects will need to be given more consideration, with DFID engaging pro-actively on the association of women working in the mining sector as well as the pilot study related to improving the conditions for women in mines. / The Strategic Environmental and Social Assessment (SESA) needs to remain an integral part of the project and findings of the SESA should inform all project activity. Links between the SESA and other reforms in the mining sector, particularly to the Mining Code, should be maximised. / The Lubumbashi Conference and the ProMines Accountability Platform should be streamlined to avoid duplication, with particular emphasis placed on reinforcing a country-led approach; / Timelines for activities financed by ProMines, such as the SESA, the Institutional Audit and tax reform should be coordinated with the Mining Code review, so that their recommendations can be adequately reflected therein. / The four pilot studies in artisanal mining areas need to be taken forward as a matter of priority. / The PIU’s M&E capacity needs to be strengthened / ProMines and the World Bank should make every effort to ensure a more systematic dissemination of knowledge generate and lessons learnt from the Project. Links to other projects will need to be sufficiently made, and activities coordinated, particularly on mining sector revenue reform and EITI. / The World Bank should also assume a stronger presence in the dialogue with the Government on the mining sector issues for example through its regular participation in the Groupe Thematique Mining, Hydrocarbons and Energy. It should also provide the PIU with the necessary support at the higher level on potentially sensitive issues, such as for example the Institutional Audit. / Active financial monitoring of funds into and out of the World Bank’s Trust fund needs to be maintained, given the slow disbursement of DFID funds. / DFID should seek to clarify its understanding of the World Bank’s procurement policy, and its strategy for driving down costs when awarding contracts.

8. Review Process
This Review was conducted by the DFID DRC Wealth Creation Team, drawing on evidence from the current Project Memorandum, logframe, PIAP, progress and financial reports produced covering the review period as well as from meetings with stakeholders. Cross-cutting inputs were received from DFID DRC advisors and a central Climate and Environment advisor as part of 10% time.