Type of Review: Annual Review

Project Title: Support to International Agriculture Research Centres that Benefits Poor People (ARIES Code 202748-101)

Date started:	August 2013	Date review undertaken: September 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is investing up to £40 million - see Table 1 below - in international agricultural research over four years from 2011-2015. In 2011, a business case was approved to provide £30m to scale up our core funding to four international research centres, i.e. CABI, icipe, AVRDC and GFAR, who were all pre-assessed as providing good or very good value for money to DFID. We discontinued funding to Crops for the Future (CFF) as it could not demonstrate it continued to provide value for money to DFID. However, we agreed to make one final allocation, apportioned over 2012/13 and 2013/14 financial years to allow them time to attract alternative sources of funding. / Each of the selected research centres identified 3 or 4 key objectives, e.g. new improved vegetables lines with good nutritional and/or disease resistant properties, roll out of new national plant health systems in 30 countries, scaling up of “push-pull” control of striga in cereals in Africa and an integrated pest management technology for control of African fruit fly and mechanisms for tracking investments in AR4D and for building user feedback into international agricultural research systems. Based on their performance against the agreed key objectives and good governance measures, i.e. robust financial systems, an environmental management system with targets for reducing carbon footprint, metrics on energy use, etc, and HR policy and operational plans for ensuring gender balance in organisational structures and research processes implemented. We review each centre’s performance annually against the key objectives and organisational behaviours and decide whether to award a 20% performance bonus for demonstrating good performance. / In November 2012, a business case was agreed to provide additional funding of £10m to two centres, CABI and icipe, which had demonstrated evidence of excellent research quality with development impact and value for money for DFID during the inaugural performance review. These centres also showed that they could scale up their work to meet strong Ministerial interest in the use of science and innovation in tackling poverty and in new forms of partnership with the private sector to deliver development outcomes. / Also during 2012, a new funding arrangement was finalised with ICIMOD, following an assessment of the value for money they present to agricultural research. / Table 1 / Centre 2011/12 2012/13 2013/14 2014/15 2015/16 Total / AVRDC 340,000 1,440,000 1,880,000 1,900,000 380,000 5,940,000 / CABI 900,000 4,567,600 4,966,000 4,967,000 827,000 16,227,600 / icpe 353,033 3,682,400 4,066,000 4,067,000 647,000 12,815,433 / GFAR 90,000 240,000 300,000 300,000 60,000 990,000 / ICIMOD 1,220,000 1,220,000 1,236,967 3,676,967 / CFF 135,000 82,500 82,500 300,000 / Project Evaluation 50,000 50,000 / 1,818,033 11,232,500 12,514,500 12,520,967 1,914,000 40,000,000

What are the expected results?
The intended impact of this programme is agricultural growth that contributes to poverty reduction and improvements in nutritional status. DFID will scale up support to high performing international agricultural research centres, linking funding to delivery in order to leverage higher performance, particularly around scaling up and robust systems for impact measurement. / The intended outcomes are: / • New technologies, products and knowledge to address agriculture yield gaps, hunger and malnutrition; / • Technologies, products and knowledge put into use at scale; / • A step-change in systems to measure impact.

What is the context in which UK support is provided?
Little progress has been made in reducing the number of hungry people over the past 20 years – particularly in Africa, where one in three of the population is malnourished despite the agricultural potential of the continent. The MDG target on tackling hunger remains off-track. / Between 2008 and 2009, the number of hungry increased by 105 million to 1.02 billion people, due to the food and financial crises. Although this forecast has now been revised to 925 million for 2010, new drivers of change in the global food system make the MDG target on hunger more challenging to achieve (FAO, Royal Society, UK Government Office for Science Foresight): / Global demand for food. Growth in population and per capita demand are likely to drive an increase in global demand for food by up to 40% by 2030 and 70% by 2050; / Growing scarcity of resources. Options for increases in production from expanding the area cultivated are limited. Agriculture already consumes 70% of fresh water available globally. Several major aquifers will be exhausted by 2050 (UK Foresight Study) Conventional agricultural systems are highly dependent on nitrogen fertilisers that are manufactured using fossil fuels and which contribute significantly to greenhouse gas emissions (GHG) and environmental pollution; / Climate change. Increased climate variability, and decadal changes temperature and rainfall will place increasing stress on crops and farming systems, bringing about profound changes in agriculture. / The Foresight Global Food and Farming Future Project programme predicts that these pressures will lead to imbalances in supply and demand, which may lead to increases and volatility in food prices in the long term, and as a consequence in the number of people who are malnourished and hungry. The poor are most likely to be affected by higher food prices, since they already spend 75% of their income on food. A sustained increase in food prices is likely to exacerbate pressures to expand agriculture into new land and to over-extract water resources, leading to further loss of forests, biodiversity and ecosystem services with impacts on GHG emissions. / Significant investment will be required just to maintain current productivity levels – to combat new pests and diseases and to ensure resilience of crops to drought or flooding. In the longer term sustainable global food supply will come from addressing the future threats to existing productivity and sustainable intensification of agriculture; increasing productivity at a rate significantly greater than has been achieved in the past two decades using progressively fewer resources. / The contribution of research and innovation: / Investment in agricultural productivity is not in itself sufficient to enable countries to develop, but there are very few examples of countries that have escaped chronic poverty without achieving rapid growth in the agricultural sector. The empirical relationship between agriculture and poverty reduction is well established. For example, in Africa, agricultural growth has been found to be four times more effective in increasing the incomes of the extreme poor than growth originating in other sectors. / Studies in Africa have emphasised the ‘multiplier’ effects of growth in agricultural incomes, with estimated income growth multipliers of between 1.5 and 3 across a number of African countries. This is a higher multiplier than in any other sector. / Dramatic rises in agricultural productivity have been based on the development and application of new technologies. Over the past 50 years global food production has more than tripled. Global yields per hectare of the major staple crops grew at an annual rate of 2-3% between 1961 and 1990, exceeding population growth rates and contributing to a long-term decline in food prices. Major food security successes – such as the Asian Green Revolution, and the expansion of improved maize varieties in East and Southern Africa, have been driven by agricultural innovation.

## Section A: Detailed Output Scoring

Output 1: Centres generating high quality research outputs.
Output 1 score and performance description: A met expectations / This output has four indicators with annual milestones: / Centres on track with agreed deliverables. / Research publications including in peer reviewed journals / High quality case studies / Gender specific research outputs / The second performance review of each centre was under taken in mid-2013. The review was carried out by members of the Agriculture Team, the South Asia Research Hub and DFID India. The assessment of performance of each centre was peer reviewed by one of the Senior Research Fellows. This annual review has been based on that performance review. In the main, the centres have met expectations against the major deliverables and in some cases have exceeded them, particularly CABI and icipe. / Progress against expected results: / Centres on track with agreed deliverables. / Five centres were reviewed this year as we started providing support to ICIMOD from late October 2012. CABI and icipe showed very good and good performance, respectively. AVRDC and ICIMOD demonstrated satisfactory performance. However, GFAR was unable to demonstrate clear progress against deliverables and milestones. / The World Vegetable Centre (AVRDC) / The Panel agreed that AVRDC has performed well against the programme milestones on development and release of new vegetable varieties. AVRDC has also made efforts to address the recommendations from the 2012 review on strengthening impact assessment, including the development of an internal monitoring and evaluation (M&E) document, the secondment of some additional M&E expertise and the design of two new impact assessments, one of which is a Randomised Control Trial (RCT). / Whilst there is a diversity of approaches to up-scaling, it is not clear that AVRDC is being sufficiently strategic with respect to the pathways to impact, what partnerships are needed, and what the researchable questions linked to up-scaling are. Some good partnerships have been developed with private sector and other players but significant challenges remain in tracking adoption rates, measuring results and learning lessons on up-scaling. / The Panel noted the efforts made on impact evaluation but considered that more work is needed to finalise a clear operational M&E strategy and operational plan specific to AVRDC – the current document is too generic. AVRDC need to embed the necessary skills in-house on impact evaluation, and demonstrate an understanding and application of robust evaluation methods. / The Panel felt that whilst AVRDC’s work often involves direct engagement with women, its report does not provide a focus on gender specific research outputs. The report contains some references to gender but these mainly draw upon the role of working with women’s groups on tomato grafting in Bangladesh. There are also some references to gender disaggregated data. This suggests that while there is some focus on women in AVRDC’s research projects, it is rather ad hoc and AVRDC still needs to do more to integrate gender into its work and ensure greater coverage of gender in research publications. None of the 286 papers and reports listed in the annual report has gender, women or social differentiation in their title. / After due consideration, the Panel concluded that it considered AVRDC’s performance as satisfactory but did not qualify for a performance bonus. Whilst recognising progress in increasing the scope and rigour in its impact evaluation activities, there is still some way to go. AVRDC must also demonstrate that it is using best practice in integrating gender into its work. / The Panel recommends three areas where AVRDC needs to strengthen its performance if it is to demonstrate a case for good or very good value for money for DFID research. AVRDC need to develop: / a clear gender strategy that will set out how it will operationalise gender across its research programme. Identify the training needs for staff on gender research and gender champions to push gender integration across the research programme; / an explicit M&E strategy that provides clear operational guidance to projects on monitoring and impact evaluation. Ensure dedicated internal capacity for monitoring and for the design of scientifically robust evaluations (both internally run and externally commissioned) including skills in both social and natural sciences and especially in the latest thinking on evaluation methods in agriculture; and / a clearer uptake strategy for flagship technologies, including consideration of impact pathways, partners and researchable questions around uptake. / CABI / The Panel considered CABI’s presentation and report and found that it had demonstrated strong performance against programme deliverables. This is combined with significant developments in terms of overall strategy development, programme delivery and a healthy financial situation. CABI has continued to perform well against its main programmatic milestones (Plantwise, Knowledge Bank, development of mobile advisory services). Milestones have been met or exceeded overall and CABI is on track to meet the main outputs/deliverables. / The Panel’s assessment was that CABI has understood the need to strengthen its monitoring and evaluation (M&E) capacity and taken action to address this. One impact assessment is under review in a peer-reviewed journal and new studies are underway. However, there have been some delays in further advancing impact evaluation (for unavoidable staff reasons). And whilst some progress has been made on Plantwise evaluation, this has also been slower than expected. / CABI has undertaken a number of concrete steps to improve gender integration into its work. A gender strategy has been approved which sets out clearly why gender is important for CABI’s research and provides a good overview of the issues that CABI staff will need to address in terms of planning, implementation and M&E. CABI has also conducted staff training on gender analysis and gender champions have been appointed within the organisation to promote the subject. However, at the moment, very few of CABI’s research papers appear to include reference to gender. A key indicator of the successful roll out of CABI’s efforts to mainstream gender will be an increase in the number of publications that make explicit reference to gender, including gender disaggregated data and analysis of the impact on women. / CABI has performed well on organisational behaviours, including peer reviewed publications and environmental management systems, and will need to continue to check that it sets challenging internal targets to maintain a strong positive trajectory. / The Panel concluded that it considered CABI’s performance as very good, thus qualifying for a performance bonus. The Panel commended CABI’s willingness to respond to recommendations in developing high quality impact evaluation and encourages continued leadership in this area to ensure this is fully embedded in the organisation and extended to all programme areas. / The Panel recommends areas where continued efforts are required to maintain and strengthen performance. / CABI needs to ensure the evaluation plans for major programmes such as Plantwise and Direct2Farmer are progressed, kept to a clear timeline and lessons shared across the organisation. / There is still much scope for improving gender analysis across the portfolio, including more gender disaggregated data, and for more explicit focus on gender in future publications. / GFAR / The Panel found that there was evidence of some progress. The Medium Term Operational Plan (MTOP) has been revised and the Governance Review has been completed. A monitoring and evaluation (M&E) company has been recruited to undertake a baseline survey and provide advice on monitoring. / However, GFAR was unable to demonstrate to the Panel clear progress against milestones and deliverables, and in several cases the Panel was unable to discern GFAR’s specific contribution. Whilst measurement of impact of organisations primarily focused on networking and advocacy is undeniably a difficult and challenging area, the Panel considered GFAR should be doing more in this area. The Panel was not convinced that there was yet a mechanism in place by which GFAR will be able to track its relevance and contribution to wider processes. As the 2013 GFAR Governance Review noted, ‘A credible monitoring and evaluation system has been initiated but not yet put fully into practice to support such oversight and accountability processes.’ / Justification for funding from DFID’s Agricultural Research budget depends on the extent to which GFAR is an indispensable part of the CGIAR reform process, bringing in voice of farmers organisations into discussions on priority setting and adding measurably to the relevance and quality of research. The Panel’s assessment is there is little evidence that GFAR is sufficiently results-based and able to demonstrate its impact. GFAR must become much more able to articulate its specific contribution to wider global processes. / As noted in the 2013 GFAR Governance Review, there is a need for fundamental governance reforms if GFAR is to achieve its global ambitions on agriculture for research and development. Following through on the recommendations of this review will be an important task for GFAR over the next two years. / After due consideration, the Panel concluded that GFAR’s current performance does not provide sufficient assurance on value for money for DFID research funds. The Panel does recognise that GFAR is about to undergo major governance reforms, which should help the organisation in ensuring greater focus and prioritisation of its work, and push the organisation to be more streamlined and cost effective. However, DFID will cease funding to GFAR at the end of the current financial year in March 2014, i.e. we will only make one further payment of £120,000, unless GFAR is able to demonstrate; / a) clear, concise reporting of results; / b) an effective strategy to measure impact; / c) significant progress towards the reforms indicated in the Governance Review; and / d) evidence of cost-effectiveness. / DFID would be prepared to hold a further review discussion in January 2014 if GFAR provide us with evidence by 30th November 2013 showing how it has met our challenge. / icipe / icipe’s programme milestones are on track and in a number of cases have been exceeded. A clear and well prepared report provided strong evidence of progress on all the programmatic deliverables. icipe has taken measures to strengthen their impact evaluation. In addition, icipe has performed well against organisational behaviours, making good progress on integrating gender and on incentivising staff to improve performance on peer reviewed publications. / The Panel agreed that further work is needed to develop icipe’s approach on / a) evolving uptake and partnership strategies b) strengthening quality and rigour in impact assessment and c) further integration of gender into its research programme. This assessment was confirmed during a visit in July to icipe HQ and to sites in Western Kenya where push pull technology had been implemented. icipe is strengthening its impact evaluation and requiring all new projects to set out plans for impact assessment. / By asking icipe to raise the quality of impact assessments, DFID is looking for: / greater use of external evaluation teams to strengthen credibility; / more use of experimental approaches in order to capture attribution; / research outputs leading to publication in peer-reviewed journals; / measures of cost-effectiveness as well as impact; / integration of gender specific analysis; and / dedicated internal capacity for monitoring and for designing scientifically robust evaluations both internal and external with skills in both social and natural sciences. These staff must be linked into the latest thinking on evaluation methods in agriculture. / icipe are meeting their targets for scale up, but given the potential benefits, it is not clear why growth is only projected to be linear rather than exponential and what strategy is in place to ensure up-scaling. Whilst there is a good diversity of approaches to up-scaling, it is not clear that icipe is being sufficiently strategic with respect to: / what the pathways to impact are: incentives/disincentives to adoption; how smallholders adapt the package as they adopt different trajectories; tracking of these different pathways and feedback; / what partnerships are needed: this includes partnering with private sector players such as agro-dealers and exploring links with AGRA, for example. Donors do not expect research centres such as icipe to do the bulk of the extension, but they expect them to identify and implement the partnerships which have the best potential to deliver the adoption of successful technologies; and / what researchable questions linked to upscaling need to be incorporated into the design of research projects and programmes: while there is much anecdotal evidence of who adopts and why, there is a need for a more systematic analysis of uptake pathways including a comparison of the cost-effectiveness of different delivery approaches and integrated packages and for better understanding of the gender aspects underpinning adoption. There are a number of positive indications in the report to show that icipe is taking gender seriously, including the adoption of the Gender Policy in November 2012 and some gender studies. / The Panel concluded that it considered icipe’s performance as good, thus qualifying for a performance bonus. The Panel commended icipe’s willingness to respond to recommendations, e.g. the establishment of a small impact evaluation unit, but is looking for a yet more rigorous approach to delivery of impact, involving a range of disciplines and a strategy for broader, independent (external) impact evaluation. / During the next year the Panel would like to see: / icipe further developing its strategy for monitoring and for impact evaluation, including strengthening of the skills sets available to it both in-house and through partnership with other organisations; / improved gender analysis across the portfolio, including more gender disaggregated data, and more explicit focus on gender in future publications; and / more in depth analysis on the constraints to uptake of new technologies leading to a more strategic approach to selection of partners best-placed to overcome those constraints and which are well-positioned to scale up the dissemination of the technologies and knowledge across Africa. / ICIMOD / This was the first Performance Review for ICIMOD, after only 5 months. The Panel noted good progress, in that a number of actions had already been initiated to facilitate progress towards meeting the specified milestones. The written report was generally concise (perhaps too much detail on the ‘greening’ strategy). The questions asked by DFID in the virtual meeting indicate areas where more detail might be appropriate next year. / At this early stage of the partnership, achievement of Milestones appears to be broadly on track, albeit with two areas within which the Panel would like to see more detail next year. The first relates to the interactions with potential users of the research outputs and the second relates to reporting on the potential benefits of ICIMOD’s work for agriculture and food security. / The Panel saw evidence during the meeting of a considered approach to strengthening monitoring and evaluation (M&E) within ICIMOD, although this is still at an early stage. The Panel welcomed partnerships being developed with J-PAL and the emphasis on capacity building and impact pathways. Similarly, the Panel welcomed the emphasis put on the importance of publishing research results and on incentivising scientists to publish in high quality peer review journals. / ICIMOD showed progress in integrating gender across their research programmes and have appointed strategic gender leads to push this. Furthermore, ICIMOD organised a major international conference on women in mountain development (with 150 people) in 2012. It is also looking at other forms of social differentiation, particularly caste. At the moment, it is difficult to assess the depth and breadth of gender integration within ICIMOD’s research programme but, if done effectively, this should lead to more attention to gender in research outputs, including publications. / ICIMOD is addressing the organisational indicators seriously. There is a strong emphasis placed on gender and implementation of the Environmental Management Plan is making good progress. ICIMOD has gender and diversity policies in place although they do not report on the current gender balance among staff. It would be useful to get a breakdown for both management and research staff. The Panel noted a well-considered approach to using DFID’s funds to support specific work relating to the objectives of strengthening M&E skills and research quality in a way which adds value to project activities. / The Panel concluded that it considered ICIMOD’s performance as satisfactory at this early stage of its partnership with DFID’s Agricultural Team. / During the next year, the Panel would like to see: / more attention being paid to how the potential benefits of ICIMOD’s research work can be captured in terms of agricultural productivity, food security and the livelihoods of poor people. This may flow from the greater emphasis on inter-disciplinarity and the partnership with, e.g. CCAFS, but the strategy adopted and the actions initiated will be issues of particular interest at next year’s review; / an increased emphasis on gender in specific publications and progress on the development of ICIMOD’s work on caste and other forms of social differentiation. On the organisational side, it would be appropriate to review progress in rolling out of the gender strategy and action plan in one year’s time; and / development of the strategy and approach for monitoring and for impact evaluation, and how to ensure this benefits from the latest thinking on impact evaluation in agriculture and natural resources. The need for rigorous impact evaluation work is increasingly being recognised as important by a number of donors and whilst recognising progress in increasing M&E, (as for other centres) there is still some way to go to identify how to provide robust evaluation. / Research Publications including the number in peer reviewed journals. / Milestone: Centres track publications including peer reviewed journals and assess whether internal incentives with regard to publications are appropriate. / Overall, the centres have shown good performance in the number of research publications and those published in peer reviewed journals – see Table 2 below. / AVRDC has made excellent progress in incentivising high quality research publications. The number of research publication produced by staff has increased by 54% and the number in peer reviewed journals by 140%. / CABI staff produced 100 publications in 2012, compared with 115 averaged over the previous three years. So, ratios are being largely maintained. 93 (93%) were in peer-reviewed titles compared with 95 (83%) in the previous 3 years. 37 (37%) of these peer reviewed publications appeared in journals with an impact factor >2 compared with 30 (26%) in the previous 3 years. In summary, this year’s total publications is slightly down on previous years, but the proportion that are peer reviewed is up, and the number and proportion in journals with impact factor >2 is also up. / GFAR reported a total number of publications of 302 with four peer reviewed publications. The number of research publications is higher than for other centres. But, it should be noted that the figures are not restricted to publications by GFAR staff and includes commissioned publications. / icipe has responded extremely positively to last year’s challenge of increasing the number of peer reviewed papers to between 80 and 110. And, has increased the number of research publication by 43% and the number in peer reviewed journals by 20%. / ICIMOD’s publications covered only five months and the proportion of peer reviewed to total research publications showed an increase from 35% (2011) to 57% (2012). / Table 2: Publications by centre / Centre Baseline 2012-13 / No of Research Publications No in Peer Reviewed journals No of Research Publications No in Peer Reviewed journals / AVRDC 186 40 286 96 (8 in a journal with an impact factor >2) / CABI 148 122 (26 in a journal with an impact factor >2) 100 93 (37 in a journal with an impact factor >2) / GFAR N/A N/A 302 4 (0 in a journal with an impact factor >2) / ICIMOD 19 11 (5 in a journal with an impact factor >2) / Icipe 86 80 123 96 (48 in a journal with an impact factor >2) / c. High quality case studies made available for publication demonstrating impacts at scale, and responding to issues of climate adaptation, empowerment of women, food and nutrition security. / Milestone: At least one case study for each research centre published on R4D and centre website / The purpose of setting this indicator was to incentivise centres to provide DFID with impact case studies on a regular basis to assist DFID with briefing and communicating agricultural research. At least one case study per centre has been achieved. And, the case studies have helped to raise the profile and publicise the work done by the centres through DFID’s support. / d. Research outputs with specific focus on women’s empowerment and gender analysis generated and widely disseminated. / Milestone: At least one research output per centre which demonstrates gender dimensions. / The progress made by the research centres in gender analysis and gender mainstreaming is mixed as is shown below. Some centres have made good progress in mainstreaming gender and developing gender strategies and while all acknowledge the importance of gender and have introduced gender strategies the actual integration of gender analysis into their on-going research programmes is much more limited. There are only a few research outputs that look specifically at gender issues and there is much scope for improvement. Some of the centres appear to have limited capacity and staff expertise in gender issues. This applies particularly to AVRDC and icipe and potentially ICIMOD although we know less about their capacity on gender. CABI appears to have more internal capacity and management commitment to gender although this still needs to translated into more concrete research outputs. / AVRDC / The AVRDC annual report for DFID does not give a clear focus on gender specific research outputs. There are some references to gender in the report but these are mainly draw upon the role of working with women’s groups on tomato grafting in Bangladesh. There are also some references to gender disaggregated data such as 35 of the 40 farmers trained on post-harvest losses in Tanzania were women. It suggests that while there is some focus on women in AVRDC’s research projects this is rather ad hoc and that AVRDC still needs to do more to integrate gender into their work. AVRDC needs a gender strategy that will set out how it will operationalise gender across its research programme. It would also be important to identify the training needs or AVRDC staff on gender research and also identify gender champions to push gender integration across the research programme. Ultimately this would lead to a more coverage of gender in the research publications from AVRDC: none of the 286 papers and reports listed in the annual report have gender, women, or social differentiation in their titles. / CABI / CABI has undertaken a number of concrete steps to improve gender integration into their work. A gender strategy has been approved which sets out clearly why gender is important for CABI’s research and provides a good overview of the issues that CABI staff will need to address in terms of planning, implementation and M & E. CABI has also conducted training for staff on gender analysis and gender champions have also been appointed within the organisation to promote gender. However, at the moment very few of CABI’s research papers appear to include reference to gender and a key indicator of the successful roll out of CABI’s efforts to mainstream gender will be an increase in the number of publications that make explicit reference to gender, including gender disaggregated date and analysis of the impact on women. / GFAR / GFAR believes that it has been instrumental in getting CGIAR CRPs and centres to take gender more seriously and supporting them in integrating gender into their research. One of GFAR’s staff is currently working with the Drylands systems CRP on gender and GFAR stated that people within CRPs come to GFAR for advice on gender. Supporting CGIAR on gender is not really a core role for GFAR although they could play a role in holding CRPs to account on gender integration, which if done effectively could make an important contribution to strengthening gender within the CRPs. / icipe / On gender there are a number of positive indications in the report to show that ICIPE is taking gender seriously, including the adoption of the Gender Policy in November 2012 and some gender studies. There is still much scope for improving gender analysis across the portfolio, including more gender disaggregated data and for more explicit focus on gender in future publications. / ICIMOD / ICIMOD has shown progress in integrating gender across its research programmes and has appointed strategic gender leads to push this. Furthermore, ICIMOD organised a major international conference last year on women in mountain development. 150 people participated in this. They are also looking at other forms of social differentiation, particularly caste. At the moment it is difficult to assess the depth and breadth of gender integration within ICIMOD’s research programme but if done effectively this should lead to more attention to gender in research outputs, including publications. DFID will also track the development of ICIMOD’s work on caste and other forms of social differentiation. / On the organisational side ICIMOD has gender and diversity policies in place although they do not report on the current gender balance among staff. It would be useful to get a breakdown for both management and research staff. ICIMOD has a gender policy in place and plans to develop a gender strategy and action plan and it will be important to review this next year and monitoring the roll out of this strategy will be important for DFID.
Recommendations: / For all centres there is still much scope for improving gender analysis across the portfolio, including more gender disaggregated data, and for more explicit focus on gender in future publications. / AVRDC still does not have a clear gender strategy; this needs to be developed next year in order to demonstrate how it will operationalise gender across its research programme. It also needs to identify the training needs for staff on gender research and gender champions to push gender integration across the research programme. / Impact Weighting (70%): / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? No

Output 2: Organisational behaviours which underpin effectiveness and value for money for DFID are strengthened.

Output 2 score and performance description: A (meeting expectations) / Overall each centre reported clearly against the expected organisational behaviours. The system is better understood by partners this year compared to the first performance review in 2012 and there is evidence that the system is leveraging improved performance from some centres, (e.g. AVRDC on strengthening environmental management and CABI on gender within HR policies). / Progress against expected results: / i. Robust financial systems and sources measured by: / a) Indirect/direct cost ratio, i.e. this ratio seeks to measure how much research programme activity a centre is able to support on its institutional cost base. / b) Audit opinion, i.e. an external auditor’s opinion on the centre’s financial statements indicates whether the centre’s financial accounting and reporting processes meet required standards. Depending on the nature of any qualification made, it may indicate financial “going concern” issues, the ability of the centre to account for its financial or physical assets, or the appropriateness of computations and estimates used in preparing the financial statements. Although an unqualified opinion does not provide absolute assurance about the reliability of the financial statements, a qualified opinion indicates an increase in the risk that the statements do not fairly present the true financial picture of a centre. / c) DFID costs as % of total funds, i.e. the ratio of DFID costs to total costs gives us an indicator of how dependent a centre is on DFID and how diversified its funding source. However, we note that these figures can vary considerably year to year and so 40% is set out as an indicative threshold and basis for discussion rather than an absolute figure over which we should not go. / These figures are reported in Table 3 below. / AVRDC / AVRDC has continued to maintain a downward trajectory in its ratio of indirect/direct costs - 20.9% (2012) compared to 23.2% (2010). AVRDC’s annual audited accounts have been signed off by external auditors, who have provided an unqualified report. DFID’s funding as a proportion of AVRDC’s total income has increased to 13% (2012) from 7.4% (2011). AVRDC has commented that developing specific processes to collect data on specific inputs of interest to DFID, has helped to guide AVRDC towards implementing internal changes to improve its performance. / CABI / CABI’s ratio of indirect/direct costs has remained steady between 2010 and 2012. This ratio is higher than other Centres primarily due to the nature of CABI’s printing business and definitions of indirect/direct costs. CABI will speak to the other Centres about whether a common definition can be achieved with a view to benchmarking such costs and sharing of best practice. CABI’s external auditors have given an unqualified opinion in its annual audited accounts. DFID funding (including membership fees) amounts to about 25% of CABI’s total income. / GFAR / GFAR has maintained its indirect/direct cost ratio at no more than 40% allocated to the Centre and 60% directed towards programmes. It was suggested that some Centre costs could be apportioned to programmes. Indirect costs are reduced by minimising travel through use of video conferencing and ‘piggybacking’ other events. GFAR has produced a fund statement certified by the Director of Finance, ICARDA. DFID funding represents 23.3% of total GFAR funding in 2012, compared with 11% in 2011. The fund statement does not show how DFID funds have been spent. / icipe / icipe works to achieve an indirect/direct cost ratio of 25%. For 2012, the ratio is 28% and was 20% (2011). icipe has met all its financial targets as set by its Board. icipe’s external auditors have provided an unqualified opinion in its annual audited accounts. DFID’s funding as a proportion of icipe’s total income is 14.9%, up from 6% (2011). / ICIMOD / ICIMOD’s ratio of indirect/direct costs is 17%. It has introduced full cost recovery across its programmes. Its external auditors have provided an unqualified opinion in its 2012 annual audited accounts. DFID funding represents about 7% of ICIMOD’s total income. / ii. A clear plan and strategy (Environmental management system or EMS) in place that incorporates: / a) specific targets for reducing the carbon footprint and wider environmental impact / b) metrics on energy use, waste, travel and transport / c) Processes for regular reporting to the Senior Management team. / Milestone: Environment management plan in place, with targets, metrics and reporting mechanisms formalised and in place. / AVRDC, CABI and icipe all have environmental management plans in place. Whilst, GFAR has taken action to reduce travel, they are hosted by FAO and are bound by FAO’s administrative arrangements. ICIMOD are new to this process and will develop an environmental management plan and reporting mechanisms by the end of 2013. / AVRDC has reduced its carbon footprint by about 12% since 2010. AVRDC’s regional and headquarters’ Green Committee monitor the carbon footprint through various activities and develop mechanisms to reduce them. / CABI monitor energy use at Egham and Wallingford monthly. Improved real-time monitoring and subsequent benchmarking has identified the most significant sources of emissions at each UK site. Electrical power monitoring at Egham being expanded with phased additional metering installations based on monitoring estimates of key high energy consumption contributors. / In 2012, icipe became a Regional Centre of the UN Stockholm Convention on Persistent Organic Pollutants. icipe complies with an independent audit by the National Environment Management Authority and is seeking donor funding to implement a conservation plan to reduce its carbon footprint. / iii) HR policy and operational plans for ensuring gender balance in organisational structures and research processes implemented. / Milestone: Maintain/increase ratios. / All centres have either maintained or increased the ratio of female to male staff. icipe’s Gender Policy has been approved by its Governing Council. Under this policy, female staff members held a meeting to discuss issues that may have an impact – either negative or positive – on their work and performance of their duties. icipe management will try to implement several important proposals from that meeting. Following the development of a CABI-wide gender strategy laying out the next steps to mainstream gender perspectives, the first training workshop in March 2013 introduced gender concepts to 15 staff from across CABI centres. In Plantwise, a study is planned for 2013/14 to evaluate how plant health clinics deliver services to different gender groups. / Impact Weighting (30%): / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Yes / The logframe has been updated to include ICIMOD and the deliverables identified under the additional funding approved for CABI and icipe last year.
1.2 Overall output score and description: A (meeting expectations) / Five centres were reviewed this year as we started providing support to ICIMOD from late October 2012. CABI and icipe showed very good and good performance, respectively. AVRDC and ICIMOD demonstrated satisfactory performance. Measured against the specific output indicators in the logframe, all centres have shown good performance in the number of research publications and those published in peer reviewed journals (see Table 2). All of them have produced at least one case study to demonstrate and communicate impact. However, GFAR was unable to demonstrate clear progress against deliverables and milestones, and it was difficult to measure progress clearly. Despite this, on an aggregate level, we assess progress against outputs as meeting expectations. / The purpose of the performance management funding system is to leverage improved performance in particular areas. One of these focused upon in this performance review was gender. Progress made by the research centres in gender analysis and gender mainstreaming is mixed. Some centres have made good progress in mainstreaming gender and developing gender strategies and while all acknowledge the importance of gender and have introduced gender strategies the actual integration of gender analysis into their on-going research programmes is much more limited. This is a priority for leveraging improved performance in 2014. / In terms of performance against organisational behaviours, centres better understood expectations than in the first performance review, and were largely able to demonstrate improved performance.
1.3 Direct feedback from beneficiaries / For this review, DFID solicited feedback from the partners on 6 questions. Out of the 5 partners, 4 responded. This section summarises their feedback. / Performance review process / The centres welcomed the annual review process and AVRDC said the standard reporting format introduced this year was very helpful and clarified how the work was to be presented. icipe greatly appreciated the unique review process as it provided ‘a distinctive avenue for two way discussion and provides suggestions that drive performance improvement’. CABI mentioned ‘it has sufficient flexibility that the reporting requirements are not onerous but it also succeeds in getting to the core of key performance issues in a challenging way’. ICIMOD said that ‘the review seemed like it came early after a half year into the programme, but actually that was positive as it allows us to think through our programme’. / Additional Effects of Funding / The centres commented favourably about the benefits arising from DFID funding. AVRDC said that ‘the flexibility of unrestricted core funding over several years is vital for longer-term planning and has allowed us to be more strategic’. It has allowed icipe to introduce its flagship ‘climate smart’ to drier regions, enter into novel partnerships with the private sector and enabled young African scientists, particularly women, at Postdoc level an opportunity to conduct high-quality research. CABI has been able to leverage substantial funding from a number of other donors and the financial security and predictability have allowed it to invest in new programmes such as Plantwise and the emerging work with mobile. / Delivery of Activities / AVRDC has been able to focus on the delivery of new improved lines which are vital for developing countries to keep ahead of biotic and abiotic vegetable production constraints. CABI said that longer-term funding has allowed it to plan and commit resources to programmes over a longer period, reducing programme uncertainties and allowing the building of a step-wise set of activities for Plantwise. icipe decided to form a small impact assessment/socio economic unit headed by a highly experienced economist and impact assessment specialist. This unit plays a crucial role in the formation of a centralised M&E platform. Through DFID’s contribution, icipe is in the process of mainstreaming its gender policy. ICIMOD has improved its impact orientation, both in planning and within its M&E system. / Organisational Framework / AVRDC has been able to provide better technical support to its regional offices due to continuity of DFID funds. And, it has been able to focus on managing its internal resources and interactions with the environment. The review process ‘has challenged CABI to introduce more effective ways of working and catalysed a major shift in views and attitudes towards M&E and gender mainstreaming in projects across the organisation’. ICIMOD have introduced rigorous impact pathway approaches to its programmes. / Improvements to current system / AVRDC commented that the performance management system keeps centres on-track for the agreed deliverables. ‘It could be relevant to re-address the agreed objectives as there appears to be a mismatch between DFID’s needs and the information AVRDC provides to DFID’. CABI would welcome if examples of effective approaches from other centres could be cascaded by DFID so they could learn from each other and avoid replicating possible mistakes. icipe noted that the emphasis within DFID’s internal performance management system for reporting on lesson learned is invaluable for the future strategic outlook of icipe. / What would happen without DFID funding / Three centres agreed that progress on their flagship programmes would not have moved as quickly as it has done without DFID’s support. ICIMOD made the valid point that it was too early to establish the counterfactual and provide concrete evidence on this question. / 1.5 Key challenges: / The main challenges arising from the analysis above relate to better sharing of best practice across the centres, and greater sharing of the approach with other donors. Other challenges – for example further raising the quality of outputs with respect to impact evaluation and gender analysis in research are covered in the centre specific recommendations. / 1.6 Summary of overall progress and Annual Outcome Assessment: A / As was the case in the last Annual Review, this year’s Outcome Assessment is based on two components. Firstly, are the centres performing as expected, meeting deliverables and is the assessment against outcomes on track? / Against these criteria, the annual outcome assessment is an A – i.e. outputs largely met expectations. For two of the 4 original centres, they have received a performance bonus (CABI and icipe) due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. Two other centres were largely on track against agreed deliverables and milestones, but DFID has used the mid 2013 performance review process to send a clear message on performance, and in the case of GFAR, has proposed to end funding unless there is clear evidence of progress on 4 objectives. For all centres, in order to leverage improved performance, specific recommendations for follow up action were made following the mid 2013 performance review. / The second aspect of the assessment looks more broadly at the introduction of a new performance based management systems. Is the system performing effectively, and meeting the objectives set out in the Business Case of using multi-year performance related funding to leverage higher performance, value for money, and closer alignment with DFID values and priorities? In relation to these criteria, the programme would appear to the review team to be meeting or exceeding expectations. However, this needs to be assessed independently of DFID. It should also be noted that there are no logframe indicators relating to this specifically, although it should be a major focus of the external evaluation planned for 2014. / In addition, the feedback from the centres, as well as the DFID Review Panel, indicates that the system is performing well. Standard reporting format was helpful, expectations clearer, and generally the review process and dialogue positively received. The centres commented favourably about the benefits arising from DFID funding, particularly the flexibility of unrestricted core funding over several years is vital for longer-term planning enabling more strategic funding decisions and leveraging new investments. Whilst benefits have been seen in several centres on gendered research and improved impact evaluation, more work is still required. Of the four centres who responded, three centres agreed that progress on their flagship programmes would not have moved as quickly as it has done without DFID’s support. ICIMOD made a valid point in that it was too early to establish the counterfactual and provide concrete evidence on this question.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / Yes. The centres have submitted their six monthly invoices on time which has meant that all payments have been made as planned. The annual performance reviews took place during late June / early July and centres were notified by the end of July about our decision to award a performance payment. A performance payment was made to CABI and icipe in August. We judged that three centres did not meet the qualifying criteria for a performance payment. These unspent funds have not been re-allocated. / 2.2 Key cost drivers: / We are providing multi-year core contributions to the centres with an annual performance payment based upon their achievements against some key deliverables and generic organisational behaviours set out in the logframe. We will continue to fund these centres for the period of the business case provide we are satisfied with the level of their performance against these indicators. Following the recent performance assessment meetings, we have notified GFAR that we will stop funding unless it is able to demonstrate: / Clear, concise reporting of results; / An effective strategy to measure impact; / Significant progress towards the reforms indicated in its Governance Review; and / Evidence of cost effectiveness. / 2.3 Is the project on-track against original timescale: Yes / The project is proceeding as intended with four out of five centres performing satisfactorily or better. As mentioned above, one centre has been put on notice that DFID funding will cease unless it is able to convince the Panel that its future performance will represent value for money to DFID.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project: / DFID will not undertake separate impact evaluations of centres, but will depend on the External Programme Evaluations undertaken periodically by each centre. It was originally envisaged that in 2013, DFID would reassess value for money presented by each centre, and the extent to which the performance based system set out in the Business Case has worked. However, the level and duration of funding was increased so it makes sense to undertake this task in 2014 after the centres have been through two annual performance reviews. This exercise will be undertaken by an external consultant. Planning for this work will start this year. / During the reporting period, icipe was reviewed by an external evaluation team looking at the period from 2008 – 2012. DFID fed into the review as part of interviews with key stakeholders and funders. The review concluded that icipe’s research is “of high to highest quality, a fact supported by the large number of peer-reviewed articles published throughout the review period. Furthermore, this research is undertaken in a reasonably cost effective manner; the production of one peer reviewed article costing ca. 250,000 USD, which compares favourably with, e.g. 239,000 USD (average 2008 – 2012) for a paper produced at SLU1”.’ The report also recommended that icipe builds up its socioeconomic skills and draw on external inputs to strengthen its cost benefit analysis in the interim. / 3.2 Where an evaluation is planned what progress has been made? / One of the drivers underpinning the centre deliverables is to generate a step-change in evaluation practice within the centres. Therefore there are a number of evaluations planned of specific technologies or activities undertaken at the centre level. Each centre has a different set of activities relating to improving the range and quality of their evaluation work. / One achievement over the last 6 months has been the commitment within CABI to undertake an external evaluation of Plantwise, using an experimental design. CABI has managed the procurement process, with support from 3ie. It is expected that the contract will be awarded by the end of the year. 3ie will provide peer review inputs to the process and it will be overseen by a donor advisory group. / icipe has undertaken a major tracer study of their capacity building work (Quest 3855610), and will use this to develop further evaluation work of their capacity building component. / Each centre has a rolling programme of external evaluations at centre level. As mentioned above, an independent evaluation of icipe, funded by SDC, has recently been undertaken.

4. Risk
4.1 Output Risk Rating: Low/Medium/High Medium / The overall risk, covering both management and research risks, is medium. This has not changed since the business case assessment. / 4.2 Assessment of the risk level: / Management risk: With regards to centres becoming complacent due to multi-year funding, the awarding of a performance bonus to only two out of 4 centres has sent out a clear message. Centres are also aware that DFID can withdraw funding if performance does not meet expectations. We monitor the proportion of DFID funding to total funding to ensure centres do not become over-reliant on our financial support. We also scrutinise centre’s audited accounts annually to ensure financial probity. We consider that the risk of failing to meet the milestones and deliverables agreed with each centre is low. / There is some risk that there is a strong element of self-assessment in the performance funding system, and that centres themselves set their own targets and milestones. This is mitigated against through an open dialogue and using the performance review process to produce a strong “challenge” function to the centres. / Research risk: The centres have been selected for their good track record in generating high quality research outputs, governance structures, scientific oversight and subject to regular external reviews. There is some risk that research does not have an impact on potential recipients, or that the targets for scale up of potential technologies are not met. / Risk of funds not being used as intended: / All of the centres have suitable financial management systems in place to provide DFID with the necessary financial information. Annual financial accounts have been received and examined to ensure DFID funds are recorded and being spent as intended. We were satisfied with four of the five sets of accounts. We queried the level of DFID funding recorded on AVRDC’s accounts. Its Director of Finance explained that in 2012 AVRDC had changed the way in which it attributed our funding to financial years, i.e. from the year in which the payment was made to the period for which the payment was paid. This explanation satisfactorily answered our query.
Climate and Environment Risk: / All centres have been required to set internal targets on strengthening their environmental management systems internally. These were reported against and assessed as part of the recent performance review. / The ‘Green@AVRDC’ initiative has raised awareness among its staff on the need to protect the environment and reduce the centre’s carbon footprint. AVRDC periodically collects and monitors its carbon footprint. And, has set itself a challenging target of reducing its carbon footprint by at least 2% annually. For icipe, as a result of their last external evaluation in 2007, adaptation to climate change has become one of the cross-cutting issues of their entire R&D portfolio. icipe is developing a comprehensive plan to implement solar and water harvesting technologies at HQ and across all stations with the ultimate goal of 'greening icipe' within the next 2-3 years. CABI also monitor its carbon footprint and as part of its UK HQ re-development plans it’s aiming for a carbon-neutral site-build by 2015/16.
5. Value for Money
5.1 Performance on VfM measures: / Table 3: Performance against financial indicators / Centre Centres meet internal targets for cost ratio / Target Actual Unqualified opinion from external auditors on financial statements DFID funding no more than 40% of centre’s overall funding / AVRDC 0.23 0.21 Yes 13% / CABI 0.37 0.28 Yes <25% / GFAR - - Yes 23.3% / ICIMOD 0.17 (baseline 2012) 0.17 Yes 7% / icipe 0.23 0.28 Yes 14.9% / A consistent ration between indirect to direct costs has continued to be maintained by three of the centres. ICIMOD has reported on its financial performance for the first time and is already starting from a very low base. / 5.2 Commercial Improvement and Value for Money: / N/A. / 5.3 Role of project partners: / Value for money is discussed with partners directly as part of the Performance Review process. / Does the project still represent Value for Money: Y / The performance management system for this programme was the subject of a recent Chief Scientific Advisers’ briefing. The briefing was well received, created a lot of interest and generated many questions. It was generally accepted that this process of evaluating centres against specific targets and recognising good performance with a bonus had delivered value for money. However, we need: / to be aware of gaming the system and how to manage that; / to triangulate through a rolling programme of field visits to each centre; / to be doing more with other donors to ensure that we are aligned, not increasing transaction costs unnecessarily, and using additional leverage through others. / 5.5 If not, what action will you take? N/A

6. Conditionality
6.1 Update on specific conditions: N/A

7. Conclusions and actions
There are a specific set of recommendations for each centre recorded in the section 1 above on progress against outputs. These have been communicated to each centre earlier in the year. This section records additional recommendations arising from the review process itself, and from feedback from each of the centres as part of this review. / Recommendations / For all centres there is still much scope for improving gender analysis across the portfolio, including more gender disaggregated data, and for more explicit focus on gender in future publications. This is reflected in the centre specific recommendations in the earlier section of this report. / AVRDC still does not have a clear gender strategy; this needs to be developed next year in order to demonstrate how it will operationalise gender across its research programme. It also needs to identify the training needs for staff on gender research and gender champions to push gender integration across the research programme. / DFID undertook a field visit to icipe in 2013, which helped ground truth findings from the performance reviews and strengthen mutual understanding between DFID and the centre. DFID should aim to complete field visits to AVRDC, ICIMOD and CABI during 2014. / DFID should proactively share the results of the Performance management system with donor representatives involved in each of the centres, and best practice on organisational behaviours from each centre with the others. / The 2014 External Evaluation should look not just at the log frame indicators for this programme but also at the added value of the performance funding mechanism as a whole. / There may also be value in stimulating a discussion within AIRCA on how to strengthen impact evaluation across the international agriculture research centres and setting out and benchmarking direct/indirect costs.

8. Review Process
This annual review draws upon the Performance review of the five centres undertaken in mid-2013. It is also informed by a field visit to icipe and its work in Kenya made by Rachel Lambert and Maggie Gill in July 2013. The annual review was led by an internal DFID team (Rachel Lambert, Alasdair Swift), supplemented by inputs from the two Senior Research Fellows, Maggie Gill and Alan Dangour and drawing on inputs from the Social Development Adviser (Andrew Clayton) and other Agriculture Research Team members. In the ICIMOD review meeting, the South Asia Research Hub and DFID India participated. The overall assessment for each centre was agreed by the performance review panel. The two Senior Research Fellows acted as independent evaluators in the process since neither of them is involved in the day to day running of this project. / The Performance Review involved each of the five centres providing a written report of their progress against the key deliverables and milestones in the logframe. Each centre was invited to give a presentation to the performance review team based upon their report. This allowed each centre to elaborate on the information provided. And, the performance review team to ask questions to inform the discussion about how each centre had performed. Following the presentations, which were held on 18th, 26th June, 8th, 10th and 16th July 2013, the performance review team shared their findings and produced an agreed overall assessment. Each centre was notified of this assessment which included feedback. The performance review team decided which centres merited a 2012 performance bonus. / The five centres were asked for their thoughts on how the 2012 performance review had gone, what impact DFID funding had made to their work and the outcome if DFID funding had not been forthcoming. This feedback also informed the review. / Documentation (Quest No) / Business case (3717589) / Logical framework (3719418) / AVRDC 2012 Performance Report (4123245) / CABI 2012 Performance Report (4123587) / GFAR 2012 Performance Report (4123727) / ICIMOD 2012 Performance Report (4123715) / icipe 2012 Performance Report (4123723) / AVRDC 2012 Annual Audited Accounts (4031117) / CABI 2012 Annual Audited Accounts (hard copy) / GFAR 2012 Annual Audited Accounts (hard copy) / ICIMOD 2012 Annual Audited Accounts (4047250) / icipe 2012 Annual Audited Accounts (4123835) / icipe 2013 External Review Report (2008-2012) (4240587) / BTOR Kenya 3-5 July 2013 (40864805) / Submission on funding to ICIMOD (3856329) / Submission to Secretary of State for Additional funding (3794820) / DFID Panel’s Assessment of Non-CGIAR Centres 2012 Performance (4083259) / Terms of Reference (4140406) / Annual Review Scoring Sheet (4140280) / Feedback from AVRDC (4141457) / Feedback from CABI (4141479) / Feedback from ICIMOD (4141468) / Feedback from icipe (4141484) / Team Leader’s Approval (4331611) / End of Workflow (4301310)