Type of Review: Annual Review

Project Title: Improving the way knowledge on forests is understood and used internationally (KNOW-FOR)

Date started:	July 2012	Date review undertaken: July 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context
What support is the UK providing?
The KNOW-FOR programme[1] aims to increase the value and impact of forest knowledge by improving research dissemination, strengthening knowledge pathways and increasing uptake by key forest sector stakeholders such as policymakers and practitioners. DFID is the sole funder of KNOW-FOR, providing a total of £20m over the 4-year period July 2012 – June 2016. All costs are provided through the UK’s International Climate Fund. The majority of funding is being disbursed to three project partners, as follows: / Centre for International Forestry Research (CIFOR) £8,000,000 / International Union for Conservation of Nature (IUCN) £4,000,000 / World Bank managed ‘Program on Forests’ (PROFOR) £6,000,000 / In addition to the £18m allocated to the three partner institutions, KNOW-FOR also sets aside £2m (£500,000 per year) to an internally (DFID) managed ‘rapid response mechanism’ that is used to finance catalytic and strategic knowledge products which UK Government can use to influence and inform policy, policy makers, decision takers and opinion makers internationally.
[1] Full programme title: “Improving the way knowledge on forests is understood and used internationally”

What are the expected results?
As stated in the programme business case and logical framework, the expected results from the programme are expected to extend beyond the lifetime of the programme to 2030. / IMPACT: Poverty reduction, biodiversity conservation and climate protection through improved management of forests, measured by the following indicators: / Increases in the average incomes of forest dependent households per year from £43 to £50 by 2030 / The area of degraded forest landscape restored increases from 0.15 m/ha/yr to 2.85 m/ha/yr / Reduction in deforestation per year resulting in 7.64 m/ha/yr of avoided deforestation by 2030 / Reduction in equivalent tonnes of carbon emissions from avoided deforestation and carbon sequestered from restored forests: 6484 MtCO2e by 2030 / OUTCOME: Policymakers and practitioners in developing countries are equipped with strategic knowledge, comparable evidence, reliable tools and systematic analysis on forests and climate, measured by the following indicators[2]: / Knowledge uptake on how forests reduce poverty and improve livelihoods / Knowledge uptake on the restoration and maintenance of ecosystem services / Knowledge uptake on ways to reduce and avoid deforestation and forest degradation / To achieve these results the programme is funding: / the development by PROFOR of 120 knowledge activities (toolkits, field notes, publications, videos, etc) which will be mainstreamed into the geographic operations of the World Bank, the International Finance Corporation and other donors, in at least 30 countries; / improvements in the way CIFOR applies knowledge and learning with key publications downloaded at least 100,000 times a year; / the Global Partnership on Forest Landscape Restoration (GPFLR), hosted by the IUCN, to mobilise knowledge on how to practically restore trees into landscapes in up to 15 partner countries across GPFLR’s learning network. / Note: A number of weaknesses with the original logframe and M&E systems have been identified since programme inception which has made it difficult to present progress against the logframe indicators. In summary, these are: / Assigning sole responsibility for delivery of individual outputs to each of the partners, limiting the ability of partners to report on other KNOW-FOR outputs and creating siloed working / Indicator methodologies that have not been well understood or developed / Lack of alignment between KNOW-FOR indicators and partner organisation reporting frameworks / To address these challenges a reformulation of the original logframe took place in July 2013 at a strategic planning workshop with KNOW-FOR partners. Central to the revised logframe (see Annex 1) are a set of outputs no longer assigned to individual partners, to encourage collaborative working and place increased focus on knowledge uptake and key audiences. / Although the logframe has been revised, this Annual Review (AR) necessarily uses the original logframe to assess project progress. The next AR in 2014 will assess progress against the new logframe (Annex 1) developed and agreed jointly by all partners.
[2] The suggested complex set of index methodologies suggested for the measurement of knowledge uptake have not been developed, rendering these indicators very difficult to measure.

What is the context in which UK support is provided?
Strong international consensus exists around the importance of forests to both development and climate change, this is reflected in the considerable international efforts and initiatives underway to decrease deforestation and improve forest management (e.g. REDD+, Forest Investment Programme, Forest Carbon Partnership Facility). The comparatively high levels of international support for forestry extend to knowledge generation, with a number of sizeable institutions well-supported to undertake forest-related research. / However, there remains a high demand from policymakers and practitioners for quality information and tools that are based on systematic, rigorous and well-founded evidence that can be aggregated and compared across sites and projects. The KNOW-FOR project is based on an assumption that such research already exists and that adequate support is already in place to undertake this research but that there is a continuing need for more and better quality targeted analysis and policy advice derived from high quality research. Instead of developing more basic research, KNOW-FOR builds on existing research and focusses on knowledge uptake, seeking to improve the way existing and emerging themes in international forest knowledge are understood, communicated and used to inform policy and practice. In doing so, KNOW-FOR will enhance the strategic nature and effectiveness of the overall international forest and climate effort. It will support a more systematic approach than has been taken in the past, tackling the specific risk of poor decision making by frontline policy makers and practitioners, and by addressing weaknesses in existing knowledge uptake pathways. / In order to maximise outreach and impact, KNOW-FOR supports three international institutions that are pre-eminent in the field of forest knowledge (CIFOR, IUCN and PROFOR). A beneficiary survey carried out as part of this review reinforces this view. / Context for this review: This Annual review has provided an opportunity to assess the challenges associated with knowledge uptake and the impact this might have on development objectives. It has also provided an opportunity to reflect on and to apply some of the newly developed thinking within DFID on “hard to measure” indicators, such as the extent to which knowledge influences policy makers, and in what way[3]?
[3] How to Note: Evaluating Influence, March 2013. Research uptake: Guidance for DFID funded research projects, 2013

## Section A: Detailed Output Scoring

Output 1: Toolkits, analyses and knowledge products are mainstreamed into operations and activities in countries, improving their success.
All project partners are making a contribution to this Output, but the logframe currently allocates all responsibility and accountability for Output 1 to PROFOR. As such, the following section concentrates on PROFOR’s contribution. / Output 1 score and performance description: B / While this output did not meet expectation, the current performance indicators within the original logframe against which this output is assessed are no longer considered suitable for the reasons noted earlier, and have been revised. The presentation of progress against Output 1 is therefore limited to an assessment of general performance against the overall Output statement. / PROFOR’s core reports do not provide evidence of specific, tangible results against KNOW-FOR Output 1 at this stage. However, there are strong indications that – for future years of KNOW-FOR – a significant proportion of PROFOR’s work will be directly relevant and attributable to Output 1. While PROFOR are already delivering strong uptake and mainstreaming of knowledge products, it is vital that future monitoring is capable of demonstrating how knowledge products improve the actual success and results of the work and institutions that they are informing. / Five PROFOR activities commenced during the DFID reporting period, and as such could be directly linked to KNOW-FOR’s investment. These are: / Development of timber verification field manuals, and handbook for forest inspectors / Engaging the UN Forests Forum and other international for a on how to improve current frameworks to mobilise forest sector finance / A study to assess the importance of tree based ecosystems for food security and climate mitigation, and what policy measures are needed to take such approaches to scale / Develop and test methods to improve the business environment for investment in wood production and processing / Develop policy briefs and guidance for consultation processes to ensure inclusion of indigenous and marginalised communities in Redd+ and land tenure processes, in Indonesia / Challenges with this output: / While all five of the above activities have clear potential to deliver against Output 1, meaningful results for these activities have – understandably – not yet been generated through the work. Indeed, this highlights another weakness with the KNOW-FOR logframe: any KNOW-FOR activity (whether delivered by PROFOR or other KNOW-FOR partners) is in very broad terms a two stage process – (i) the marshalling and validation of evidence and knowledge and (ii) the packaging, targeting and dissemination of that knowledge. It is perhaps unrealistic and unreasonable to expect significant progress against this second stage of work within the first 12 months of the project, yet the logframe milestones anticipate significant results within this timeframe. / These examples only provide strong evidence of PROFOR’s potential contribution to the first component of Output 1 (knowledge products are mainstreamed into operations and activities in countries), with only tentative evidence that the second component of Output 1 is being achieved (knowledge products improve the success of those operations and activities). Demonstrating progress against this second component is a common difficulty for knowledge uptake programmes such as KNOW-FOR – implementation partners such as PROFOR do not have direct responsibility for delivering the ‘improved success’ that Output 1 calls for, rather it is PROFOR’s knowledge audiences that must change/improve their practices and results. / Challenges with PROFOR reporting: / DFID’s contribution to PROFOR is made through a multi donor trust fund. PROFOR therefore does not have separate systems in place to report against KNOW-FOR indicators. This is discussed further in Section B.
Output Indicator 1.1: Number of Program on Forests (PROFOR) knowledge products used in design and implementation of country operations funded by World Bank, other donors and national strategies. / Milestone 1 (18 months): 70% (of PROFOR knowledge products referred to) in (design and implementation documents in) 30 countries / Progress: / PROFOR activities were focused directly on around 24 countries in calendar year 2012, but the indicator does not include several high-profile global and regional-level projects, and does not account for the fact that the influence of any country-level activity is potentially influential well beyond the borders of those countries. PROFOR has also suggested that measuring absolute country numbers is misleading as an indicator of success or impact – effective, well-targeted and well-communicated work in a single country could be far more influential than activities across several nations. / Of the 27 activities undertaken by PROFOR during calendar year 2012, 10 (37%) clearly report tangible evidence that knowledge was used in design and implementation of country operations and/or national strategies. It is possible that this proportion is higher, but PROFOR’s reporting format does not explicitly request detail from their project teams on the demonstrable influence and impact they have on the work of their knowledge audiences. / It should also be noted that while only 5 of the 27 activities were initiated during 2012 (and hence are more easily attributable to KNOW-FOR’s investment), 2 of these 5 activities already demonstrate some evidence of influence on country operations and/or national strategies. / Output Indicator 1.2: Number of Program on Forests (PROFOR) knowledge products that reach clients, who participate in their use, perceive them to be relevant and result in changed practices. / Milestone 1 (18 months): 5 index score / Progress: / The original Business Case proposed to track this complex, multi-dimensional indicator with an index that would be calculated using a broad variety of data sources. The index was never fully developed however (and has now been replaced), and therefore could not be used to track progress. Some comment can be made though, around progress towards elements of the output indicator. / The indicator has four elements: (i) products reach clients, (ii) products are used by clients, (iii) clients see the products as relevant, and (iv) use of the products results in changed practices. There is considerable overlap with the first indicator, with the contributions identified for that first indicator also applying to this second indicator. If a product has been “used in the design and implementation of World Bank country operations” it by definition has reached a client, has been used by a client and – if it has been mainstreamed into country operations – is clearly relevant to that client, with the influenced policies or plans already changing practice, or at least having clear potential to influence practice. Given the foregoing discussions around PROFOR’s progress, it can be said that PROFOR have made some progress against this indicator, and that they are well-placed to make future, tangible contributions to that indicator. However, the gap that needs to be addressed is whether clients’ changed practice actually results in improved success. / Examples of successful uptake of PROFOR knowledge products include: / Outcomes from the Forest Connect project have closely influenced the design of the FAO’s Forest and Farm facility and the Forest Investment Programme’s Dedicated Grant Mechanism for Indigenous People. / A toolkit produced through the Field Testing Governance Building Blocks; Field manual on Forest Governance Diagnostics project in Burkina Faso directly influenced the implementation of Burkina Faso’s Forest Investment Programme. The same toolkit was used in Russia, with World Bank staff indicating that the toolkit supported dialogue between Russia and China around illegal logging. / Findings from PROFOR’s Impacts of Climate Change on Rural Landscapes in Brazil project are being incorporated into national climate projection models that will directly inform decision making within Brazil’s national rural credit and insurance programmes. / Recommendations: / It is recommended that DFID makes use of its role on the PROFOR advisory board to advocate for programme-level M&E systems that increase PROFOR’s focus on impact pathways and boundary partners[4]. / In line with the outcome of the July 2013 strategic planning meeting, Output 1 be completely reformulated as per the suggested revised logframe. / Indicator methodologies should be developed that are accessible to all project partners and consistent with their M&E systems. / Impact Weighting (%): 30% / Revised since last Annual Review? No (First Annual Review) / Risk: Low / Revised since last Annual Review? No (First AR)
[4] Boundary partners are the intermediary users of knowledge products from organisations such as PROFOR and CIFOR that often transform and make use of the knowledge to influence other audiences beyond the direct reach of the original knowledge producing organisations.

Output 2: Greater knowledge on how forests reduce poverty, contribute to economic development and social welfare, and reduce carbon emissions improves the design and implementation of broader national policies and programmes.
All project partners are making a contribution to this Output, but the logframe currently allocates all responsibility and accountability for Output 2 to CIFOR. As such, the following section concentrates on CIFOR’s contribution. / Output 2 score and performance description: B / While this output did not meet expectation, the current performance indicators within the original logframe against which this output is assessed are no longer considered suitable for the reasons noted earlier, and have been revised. The presentation of progress against Output 2 is therefore limited to an assessment of general performance against the overall Output statement. / CIFOR experienced a change in Directorship since programme inception causing some delays in finalising the commitment of funds to projects. Only a limited number of activities commenced in 2012. / Despite the institution’s late start on the project, CIFOR have undertaken a number of significant standalone activities under the banner of KNOW-FOR, most notably around establishing a knowledge uptake focus and ‘culture’ within the institution. As with PROFOR, current monitoring systems within CIFOR fall short of systematic measurement of downstream results (i.e. the overall influence and impact of knowledge products). However, CIFOR’s primary work on KNOW-FOR this year has been the development of understanding and systems within the institution around knowledge impact pathways and boundary partners. A considerable amount of effort has been expended on the development of detailed theories of change that map out how CIFOR anticipate their research can influence policymakers and practitioners. Moreover, this work has been undertaken for each of CIFOR’s primary research themes – i.e. CIFOR have begun to map out how different audiences will access and use knowledge in different ways. This activity has also extended to the development of a concept for a partner network mapping tool, whereby the engagement of knowledge audiences in CIFOR’s monitoring would be undertaken on a far more rigorous, systematic basis. While this work doesn’t produce immediate tangible results against Output 2, it does lay important foundations for future KNOW-FOR activity and indeed for CIFOR’s broader research programme. / Aside from this work on impact pathways, other activities and results that were supported through KNOW-FOR finance include: / Forest Day 6 conference held during the UNFCCC COP in December 2012, attracting over 700 participants from 80 countries, including 241 climate change negotiators. A participant survey determined that 83% of attendees had found the conference at least an ‘important’ influence on the formulation of new government policy, 72% found it had at least an ‘important’ influence on spreading new or improved management practices, and 74% said it had at least an ‘important’ influence on suggesting changes to research objectives, methods or approaches[5]. / A communications workshop was delivered for more than 80 CIFOR scientists in February 2013, focused on improving presentation, media and written communication skills. The feedback was very positive, with many participants requesting on-going support and follow-up work. / The Evidence Based Forestry Initiative (cifor.org/ebf), which is central to CIFOR’s KNOW-FOR work, began in October 2012 with a formal agreement with Oxford University for CIFOR to engage one of their researchers, Dr Gill Petrokofsky, to advise on the development of the initiative. A first tranche of systematic reviews covering the following themes were underway during the reporting period: / Gender, Forests and Food Security; Impacts of biofuels on biodiversity; property rights and the environment; biodiversity benefits of alternative livelihood projects; the contribution of forest-based ecosystem services to agricultural production; role of land use change dynamics in Miombo woodlands in relation to REDD+; criteria and indicators for defining and measuring research quality in the realm of applied natural resource management. / CIFOR’s research on forests and food security closely influenced a set of recommendations developed during an international conference on forests, food security and nutrition held in May 2013 at FAO, with these recommendations likely to influence future high-level fora on the subject. / As with PROFOR and Output 1, the extent to which these examples can be said to be delivering against Output 2 is very limited at present. However, these early activities do provide an indication of what will be possible through KNOW-FOR in the coming years, particularly if knowledge uptake channels are further understood and strengthened through CIFOR’s promising work on embedding and tracking influence and impact pathways within the institution.
Output Indicator 2.1: Number of Centre for International Forestry Research (CIFOR) knowledge products, including from the Poverty and Environment Network (PEN) and the Global Comparative Study of REDD+ projects used in design and implementation of national strategies and projects. / Milestone 1 (18 months): 50% in 20 countries / Progress: / CIFOR published 9 PEN and 5 REDD+ related knowledge products during the project year, along with numerous other products relating to other research priorities. The PEN and REDD+ studies alone focussed directly on 7 countries, although several studies were global and/or regional in nature, and most have lessons that could be potentially influential well beyond the borders of any given country. / Challenges with this indicator: / CIFOR has raised concerns that both of Output 2’s indicators are very restrictive, as they primarily relate to only two aspects of their work and research programme (i.e. PEN and the REDD+ study). While these two activities are important, the indicators fail to capture the ambition and extent of KNOW-FOR’s intended influence across the whole of CIFOR’s work programme / As with PROFOR’s output, the extent to which any of CIFOR’s products can be attributed to KNOW-FOR this year are highly limited. Currently, CIFOR also have limited capability to demonstrate the influence and impact of any of their knowledge products, although there is a considerable amount of work underway to address this weakness. / Output Indicator 2.2: Coverage, relevance, participation and productivity of members participating in the Poverty and Environment Network and the Global Comparative Study of REDD+ Projects. / Milestone 1 (18 months): 5 index score / Progress: / As for indicator 1.2, the original Business Case proposed to track this complex, multi-dimensional indicator with an index that would be calculated using a broad variety of data sources. The index was never fully developed however (and has now been replaced), and therefore could not be used to track progress. / Apart from the methodological challenges associated with this indicator, it is too narrowly focussed on two specific knowledge areas, whereas CIFOR is making use of KNOWFOR resources to engage in other important knowledge themes not captured here. Examples include: the role of forests in food security and nutrition, and the role of the private sector and commercial agriculture in driving deforestation. / Recommendations: / In line with the outcome of the July 2013 strategic planning meeting, Output 2 should be completely reformulated as per the suggested revised logframe. / Indicator methodologies should be developed that are accessible to all project partners, and consistent with their M&E systems. / Impact Weighting (%): 30% / Revised since last Annual Review? No, this is the first annual review / Risk: /Medium/ / Revised since last Annual Review? No
[5] Living Landscapes: Solutions for a sustainable world (Forest Day 6 Report), CPF, December 2012

Output 3: Techniques and practices for forest restoration (the + in REDD+) create healthy landscapes
All project partners have made a contribution to this Output, but the logframe currently allocates all responsibility and accountability for Output 3 to IUCN. As such, the following section concentrates on IUCN’s contribution. / Output 3 score and performance description: A / This Output has met expectation by demonstrating good progress against the agreed activity plan set out in the MOU with DFID. The limitations with the indicators and milestones however, are equally applicable in this Output. / Output 3 benefits from a far clearer activity plan and set of deliverables than for any of the other Outputs. This is largely due to the contractual relationship established between DFID and IUCN: the IUCN finance is essentially an accountable grant. KNOW-FOR activities have been fully embedded within the framework of IUCN’s Intercessional Programme (IP) for the period 2013-16, meaning that progress will be subject to regular review. KNOW-FOR’s influence on this process has resulted in the IP, for the first time, placing deliberate emphasis on the generation and uptake of high quality knowledge, with the KNOW-FOR approach being firmly embedded within the new IUCN business model. / Progress by IUCN has been strong against each of the results areas identified in the MOU it has with DFID, leading to demonstrable progress against the overall Output. Work towards all deliverables is well under way, with a number of additional, ‘unforeseen’ deliverables also on track for completion, which had originally been planned for year 2. Moreover, some tentative results have already been reported, for example: / A feasibility study/assessment undertaken via KNOW-FOR directly informed the project document for a $53m Global Environment Facility investment in Rwanda. / A KNOW-FOR assessment helped to secure approval for an initially rejected Forest Investment Programme (FIP) proposal in Ghana[6]. / As with the other Outputs, KNOW-FOR-attributable results are limited at this stage due to the nature of the knowledge uptake process. Indeed, this limitation is partly codified within the MOU between DFID and IUCN: it was agreed that IUCN would take a “feasibility study approach” to KNOW-FOR, whereby the availability of knowledge and the audience demand for that knowledge would be scoped out prior to commencing KNOW-FOR investment on any given topic. As such, a great proportion of IUCN’s work to date has been around establishing knowledge gaps and audience demands. / Finally, it is important to state that IUCN did not commence work on KNOW-FOR until October 2012, so have only delivered 8 months of their year 1 work programme. The late start was primarily due to administrative delays in setting up the MOU.
Output Indicator 3.1: Number of countries carrying out forest landscape restoration assessments. / Milestone 1 (18 months): 4 countries / Progress: / IUCN report that the following country assessments are currently underway: Rwanda, China (detailed Miuyn watershed level and at meta level for all major urban watersheds), Brazil (Para State) and Ghana. The following countries have self-initiated the methodology and will receive support from IUCN to complete: El Salvador, Guatemala and Mexico. This milestone is therefore fully met. / Despite these achievements, the indicator does not adequately reflect the breadth of IUCN’s work on landscape restoration and, in any case, it will be difficult to directly attribute the application of national landscape restoration assessments exclusively to IUCN’s KNOW-FOR activity – many other actors will have a major influence on the implementation of such assessments. / Output Indicator 3.2: Coverage, relevance, participation and productivity of members participating in the Global Partnership on Forest Landscape Restoration and its learning network/s. / Milestone 1 (18 months): 5 index score / Progress: / As for indicator 1.2 and 2.2, the original Business Case proposed to track this complex, multi-dimensional indicator with an index that would be calculated using a broad variety data sources. As noted earlier however, this index was never fully developed (and has now been replaced), and therefore could not be used to track progress. Although IUCN has been unable to demonstrate progress against this indicator for reasons beyond its control, considerable progress has been made towards the deliverables agreed between DFID and IUCN, as discussed above. / Recommendations: / Where contractual relationships allow, activity plans and deliverables should be established for every Output annually. / In line with the outcome of the July 2013 strategic planning meeting, Output 3 to be completely reformulated as per the suggested revised logframe. / Indicator methodologies should be developed that are accessible to all project partners, and consistent with their M&E systems. / Impact Weighting (%):25% / Revised since last Annual Review? No, first annual review / Risk: Low/ / Revised since last Annual Review? No
[6] This was work initially funded by PROFOR, implemented by IUCN, and then taken forward by IUCN after PROFOR funding ended. The IUCN/PROFOR work leveraged direct WB interest and involvement and scope for revising the FIP proposal.

Output 4: Systematic, rigorous and comparable evidence of what works and what does not, rapidly reaches those who need it.
Output 4 score and performance description: C / Progress against this Output fell significantly short of expectation. This can be attributed to shortcomings in the Output description and in the indicators, and with difficulties in measuring the contributions of the three project partners. / Output 4 was originally intended as a means of drawing together aggregate contributions of the three project partners, and of improving understanding around the value of the KNOW-FOR partners’ collaborative work. It was also designed to include a mechanism for DFID to commission specific pieces of analysis that could inform policy across UK Government and provide information on emerging issues. However, Output 4’s elements are mostly explicitly or implicitly covered through the other Outputs – indeed, the statement is more akin to an overarching Outcome for the whole KNOW-FOR project. / As such, general performance against Output 4 is perhaps best described by summarising the aggregate performance of the three other Outputs. Reiterating a key point within this Annual Review, all partners have been involved in the identification of knowledge gaps and the generation of knowledge products (“systematic, rigorous and comparable evidence”), but it is unrealistic to expect significant progress on knowledge uptake (“evidence…rapidly reaches those who need it”). Nevertheless, some tentative results and evidence of influence have been reported by all partners. While these results can only partly be attributed to KNOW-FOR at this stage, they do provide encouraging signs for the future years of the project. / Although it is not well expressed, Output 4 was also established to measure and report on KNOW-FOR partners’ collaborative work. Unfortunately, performance against this element of KNOW-FOR has been weak, a point acknowledged by DFID and all three partners. Partner collaboration has been the slowest aspect of KNOW-FOR to get off the ground. Partners explained that it was not clear to them at the time of design that working in partnership was expected of them. / While there has been a degree of networking, planning and some joint activities, this has been somewhat ad-hoc in nature with little indication that any collaboration has been above-and-beyond the partnership work that would have happened through ‘business as usual’ between the three partners (i.e. in the absence of KNOW-FOR finance). The first formal KNOW-FOR meeting between partners was only held in February 2013. Whilst some progress has been made, notably between PROFOR and IUCN, the extent of planned joint-activities is still limited. More positively, there is a broad recognition of the need to improve this across all partners, and a clear, shared commitment to identify joint goals and increase collaboration within the second year of KNOW-FOR. In support of this, engagement and discussion has increased since the February 2013 meeting, and DFID convened a strategic planning workshop for partners in early July 2013, the outputs of which are reflected in this Annual Review. / A critical element of that July 2013 workshop was the identification and development of a joint plan for collaborative activity to be undertaken by the three partners during the next 1-2 years[7]. A total of 18 activities were identified. / Rapid Response Mechanism / The Business Case created a Rapid Response Mechanism under Output 4. This mechanism is administered directly by DFID, with DECC and Defra joining DFID on the management committee. Under this facility, members of the UK Government Forests and Climate Working Group can propose an activity or knowledge product, usually of short duration, that will help UK Government to influence policy, design new programmes and influence decision makers. The most common use of the RRM to date has been to finance strategic meetings and workshops, studies that have helped to inform high level discussion and or provide information where there are policy gaps. All three UK government departments have commissioned work this year. Although the template outlines a simple process, in practice this mechanism has proven excessively time consuming.
Output Indicator 4.1: Widespread learning and citations of specific knowledge products on international forestry directly supported by UK. / Milestone 1 (18 months): At least 20 citations (of international forestry related knowledge products developed through KNOW-FOR, including the RRM) / Progress: / As noted previously, the extent to which knowledge products are attributable to KNOW-FOR is limited at this stage of the project. Notwithstanding that caveat, CIFOR alone recorded 18 citations of KNOW-FOR-related knowledge products during this first project year. This sets a promising precedent, and it is reasonable to assume that the aggregated citations from all project partners will exceed this amount in future years of the project. / A citation-focussed indicator such as this could certainly play a role in KNOW-FOR’s reformulated logframe. On its own, it is an insufficient measure of ‘influence’, but the number of citations does provide useful data regarding the relative influence of individual knowledge products. This will need to be complemented by other more sophisticated metrics of “reach” from baselines agreed in each organisation. / Rapid Response mechanism initiatives funded this year include two significant workshop events. / Support to FAO’s Forests, Food Security and Nutrition conference held in May 2013[8]. This event attracted participants across disciplines, including a significant number working on food security and nutrition strategies. KNOW-FOR partners presented key papers at the event. FAO is undertaking a follow up survey on the influence and uptake associated with the event. This was not available for inclusion in this review. / Support to bring together national experts and scientists working on dryland forestry and agroforestry in Eastern Africa to document key learning and practice and to prepare policy and technical briefs for a range of audiences[9]. The organisers of the event, The World Agroforestry Centre (ICRAF) will track use of the briefs and uptake. / A Synthesis report on Drivers of Deforestation and Forest Degradation was commissioned by DECC to promote a common understanding among delegates of the United Nations Convention on Climate Change (UNFCCC) Subsidiary Body for Scientific and Technological Advice (SBSTA) on the key drivers of deforestation[10]. The report was well received in the UN climate change negotiations; the co-Chair of the SBSTA REDD+ negotiations referenced this work and it contributed to the draft decision between Parties on drivers of deforestation and forest degradation reached in Bonn in June 2013. / Whilst a number of important events and studies have been resourced under the Rapid response Mechanism, in the majority of cases it is still too early to establish the extent of their influence and/or uptake. This needs to be followed up closely by DFID, DECC and DEFRA. Once this information is available an assessment of the extent to which the RRM provides good value for money can be made. The high transaction costs associated with administering the RRM also need to be addressed. / Output Indicator 4.2: Coverage, relevance of knowledge, participation and productivity of clients for directly supported international forestry and climate knowledge products. / Milestone 1 (18 months): 5 index score / Progress: / As for indicators 1.2, 2.2 and 3.2, the index intended to track progress against this indicator was never fully developed (and has now been replaced), and therefore could not be used to track progress. Additionally, this indicator largely duplicates indicators 1.2, 2.2 and 3.2, illustrating the considerable overlap between Output 4 and the other Outputs. / Recommendations: / Given the importance placed on collaboration within the original Business Case, DFID to undertake a formal follow-up review with partners 6 months after the July 2013 workshop (i.e. early 2014), in order to formally assess initial progress of any collaborative work. / DFID should follow closely the uptake of RRM supported work, and undertake a separate review of the RRM with DECC and Defra by January 2014 to include recommendations for improving administrative efficiency.. / In line with the outcome of the July 2013 strategic planning meeting, Output 4 to be completely reformulated, as per the suggested revised logframe, to ensure that it captures collaboration and learning across the institutions. / Indicator methodologies should be developed that are accessible to all project partners, and consistent with their M&E systems. / Impact Weighting (%): 15% / Revised since last Annual Review? No This is the first annual review / Risk: Medium / Revised since last Annual Review? No This is the first annual review
[7] The full list of activities is presented in annex 3
[8] http://www.youtube.com/watch?v=TsP71ARE2mo
[9] A blog on the event is available at http://blog.worldagroforestry.org/index.php/2013/07/08/trees-to-increase-resilience-in-east-african-drylands/
[10] Drivers of Deforestation and Forest Degradation. A synthesis report for REDD+ Policy Makers. , Gabrielle Kissinger, Martin Herold, Veronique De Sy,2012

## If the project involves more than 4 Outputs please copy the box above and paste below.
## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No (this is the first AR) / The July 2013 strategic planning workshop with partners recommended significant changes to the logframe, including a complete revision of the Outputs. This is presented in Annex 1. The original logframe is used for the purposes of this review. / 1.2 Overall Output Score and Description: B / This score reflects: / The inadequacies of the KNOW-FOR results framework which has made it difficult for partners to report their progress. Limitations include: unsuitable indicators, limiting partners to reporting only on certain outputs, and a lack of alignment with partner organisation priorities for knowledge product development and their reporting frameworks, / but also, / Shows that despite these limitations, there are encouraging signs for the future development of KNOW-FOR. The three partner organisations are delivering high quality knowledge products deemed useful and relevant by their knowledge audiences. This is evidenced by the online survey of KNOWFOR partners’ knowledge audiences described in section 1.3 below. / Combined with the improvement measures set out by this review, we expect to see project performance pick up significantly by the time of the next Annual Review. / Direct feedback from beneficiaries / Monitoring and demonstrating results for a project such as KNOW-FOR is challenging. The project and its three implementation partners are focussed squarely on improving the dissemination and uptake of knowledge, with the expectation that the users of this knowledge (i.e. forest sector practitioners and policymakers) will then apply that knowledge to achieve tangible development results, such as decreased deforestation or increased income for forest-dependent communities. As such, implementation partners are essentially one step removed from the major development results and impacts that KNOW-FOR aims to bring about – it is the ‘third party’ knowledge audiences that will ultimately deliver, for example, the impacts outlined within the KNOW-FOR logframe. It is therefore recommended that KNOW-FOR’s knowledge audiences play a central role in programme M&E. / KNOW-FOR partners do not yet have a systematic process in place for analysing their knowledge audiences, or for gathering direct beneficiary feedback. However, all partners do engage in ad-hoc audience analysis, and all partners have been able to demonstrate at least some influence and impact through such ad-hoc analysis. Moreover, all partners have clearly expressed their ambition to improve understanding of their audiences and to systematise feedback processes. / In order to augment feedback collated by implementation partners during the year, a short online survey of key beneficiaries was undertaken as part of this Annual Review process[11]. The survey was circulated to 203 individuals/organisations that were judged by implementation partners to be important knowledge audiences[12]. Of those contacted, 96 responses were received. Key findings from the survey are highlighted below: / 86% of respondents felt that external analysis and knowledge is either “very important” or “essential” to their forest-related work. This validates a key part of KNOW-FOR’s original rationale and Theory of Change – i.e., there is clear demand for forest-related knowledge. / For all three implementation partners, the great majority of respondents felt that the analysis or support provided by the institutions was either “quite relevant” or “highly relevant” to their forest-related work (CIFOR = 88%; IUCN = 83%; PROFOR = 86%). / For all three implementation partners, a majority of respondents felt that the analysis or support provided by the institutions was either “quite influential” or “highly influential” to their forest-related work (CIFOR = 56%; IUCN = 62%; PROFOR = 54%). / The latter two sets of figures perhaps underline (again) the main monitoring challenge that KNOW-FOR faces: while the knowledge generated and shared by partners is unambiguously relevant, the extent to which it actually influences and changes policy and practice – the extent to which actual results are achieved – is far less clear cut. / This point is further emphasised when reviewing narrative responses to the survey question “Can you give an example as to how any of the analysis or support directly influenced your work in the forest sector?” While responses certainly indicate that knowledge and support is influential and frequently directly informs policy documents and project proposals, there is little evidence that explicitly links a knowledge product with a tangible ‘result’ such as changed practices, reduced deforestation or avoided emissions. / Overall the general feedback received from beneficiaries was highly positive and bodes well for the future of KNOW-FOR: the survey suggests that all implementation partners are trusted and valued, are regularly used as a source of forest-related knowledge for practitioners and policymakers, and already have a reasonable degree of influence within the sector.
1.4 Summary of overall progress / Progress against the indicators set out in the original KNOW-FOR logframe has been slow in year one. This is perhaps to be expected with an innovative project testing new approaches. . Reporting was also hampered by inadequacies in the way the Output and indicators were defined. There is however evidence of progress towards achieving the Output statements. The KNOW-FOR Outputs generalise knowledge uptake as a two stage process: (i) the marshalling and validation of evidence and knowledge, and (ii) the packaging, targeting and dissemination of that knowledge. There has certainly been demonstrable progress towards the first stage of this process, but progress towards the second stage is still very limited. / While the limited progress is partly due to a logframe that set unrealistic expectations and proposed complex indicators not well understood by partners, it is also clear that a systematic approach to collaborative working amongst partners has not yet developed. Furthermore, transition of key staff within DFID during the critical first six months of the programme, led to delays in addressing some of the challenges identified here. / Despite this limited progress against Outputs, there are encouraging signs for the future development of KNOW-FOR. The evidence that has been gathered during this first year does confirm that the three partner institutions are well-positioned to influence key audiences in the forest sector, with the online survey confirming that the institutions are well regarded and already have a reasonable degree of influence in the sector. There is a strong desire across the partners to increase their collaborative work, coupled with a clear ambition to markedly improve their analysis of knowledge impact pathways and boundary partners. / The following measures must therefore be put in place for the programme to live up to its potential by the time of the next AR: / Finalise and agree the new programme log frame (already well underway, see Annex 1) / Develop new indicators with clear supporting methodologies, including how to measure knowledge uptake and behaviour change, while ensuring coherence with partner systems. / Develop a systematic programme of collaborative working to ensure the added value of bringing the partners together and maximising the synergies and influence of the three organisations / Ensure a greater focus on understanding key audiences and their role in knowledge uptake, including an enhanced role in M&E / These measures are discussed in more detail under section 7
1.5 Key challenges / The Annual Review has presented a good opportunity to highlight a number of inter-related challenges. / Design and logistical constraints / A number of practical issues created challenges for programme management and delivery: / The logframe was developed with insufficient input from the implementation partners. / The challenge of monitoring of knowledge uptake was underestimated. It is unrealistic to expect KNOW-FOR to be able to demonstrate direct attribution. / Insufficient contingency was built in to allow for delays in contracting and start-up. / Funds for PROFOR are delivered through a multi-donor trust fund, and therefore DFID cannot prescribe that the funds it provides are allocated to specific activities, nor can it insist that specific monitoring processes be undertaken, making it difficult for PROFOR to report against KNOWFOR specific indicators. / The departure during programme inception of key DFID personnel involved in KNOW-FOR’s design caused a hiatus during a critical phase when design issues could have been identified and resolved. / The Rapid Response Mechanism has proven to be administratively cumbersome and has suffered from insufficient dedicated programme management staff input. / A lack of collaborative working amongst project partners / As noted previously, collaborative work amongst the three project partners needs to be strengthened. While some joint activity has been undertaken, it has not been explicitly within the framework of KNOW-FOR and therefore it is likely that this would have happened anyway, in the absence of KNOW-FOR funding. Partners feel that an understanding and emphasis on collaboration was not present during the project’s inception. However, clear measures are already in place to address this issue, including a plan for joint activities, developed during the July 2013 strategic planning workshop. Close monitoring from DFID will be required during the next 12 months. / An underdeveloped M&E system and lack of coherence with partner M&E systems / The original programme logframe has been problematic. Furthermore, the monitoring of knowledge uptake requires tools and processes that go well beyond logical frameworks. Qualitative data is arguably far more important than quantitative data, and – in order to fully understand KNOW-FOR’s influence and impact – it is necessary for knowledge audiences to be closely involved in any monitoring processes. An implicit objective of KNOW-FOR is to not just increase knowledge uptake, but to increase understanding of how knowledge is accessed and acted upon. As such, it is strongly recommended that additional impetus, resources and support are directed towards the development of improved M&E systems and processes that all project partners can apply through their work on KNOW-FOR, and which could potentially be of benefit to other knowledge uptake programmes and partners.
1.6 Annual Outcome Assessment / CIFOR, IUCN and PROFOR are producing knowledge products that are of a high quality and directly contribute to the project Outcome. As with the Output level indicators, progress at Outcome level was intended to be tracked using an index. As a methodology for the index was never fully developed reporting formally on progress against the project Outcome statement and indicators is not possible. The Outcome statement also does not capture the behaviour change (e.g. policy change) expected to result from the knowledge uptake, and has considerable overlap with the four Outputs. These practical challenges provide further support for the need to reformulate the original logframe. / Notwithstanding these design constraints, all partners have contributed towards the three Outcome level indicators in the first year. However, given the universality of the themes it is likely that that partners would have carried out such work anyway, making it difficult to attribute results specifically to the KNOW-FOR investment. It is therefore recommended that adjustments are made to the Outcome level indicators to ensure that they capture behaviour change resulting from knowledge uptake, and that that they do so for each organisation’s key themes supported through KNOW-FOR (where possible)[13].
2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The project is on track against financial forecasts. The Rapid Response Mechanism however has proved a challenge, with £289,558 (half of the total budget) having to be surrendered at the end of financial year 2012/13 due to an underspend. This occurred for the following reasons: / development of proposals and reaching agreement across the three UK Government Departments involved in the mechanism (DECC, DEFRA and DFID) on these has often taken longer than anticipated;the introduction of new internal financial rules and regulations since programme inception, particularly those relating to learning events and procurement. / It is recommended that underspent funds from the KNOW-FOR RRM be used to finance the proposed M&E external support for the programme. New guidelines for the use of the fund should be developed with a view to minimising the transaction costs associated with its implementation (see recommendation under Output 4). / 2.2 Key cost drivers / The Business Case implies that the reputation and pre-eminence of the three partner institutions was the primary driver in their selection for KNOW-FOR, so an open procurement process was not undertaken. However, overhead and administrative costs, particularly of CIFOR, were identified as key cost drivers that should be kept under continual review. / CIFOR, partly due to its operating location, has the highest management costs amongst the partners. CIFOR is committed to reducing its overhead costs from a high of 29% in 2009 to 15%[14] by 2015, in part through implementation of the CGIAR Cost Allocation Guidelines. CIFOR has been making good progress towards this goal over the last four years with current rates of 19%. CIFOR is currently investing significantly in new business systems and processes for improved efficiencies which will assist them in reaching their 15% target. / IUCN has also reduced its administrative fees from those originally set out in the Business Case. PROFOR’s management fee is set at the standard World Bank rate for multi donor trust funds. / Other cost drivers include the unit costs for the procurement of specialist inputs under the RRM, and the unit costs associated with the development of knowledge products and their uptake. Output based ToRs are used to compare offers from a range of suppliers at the mini-competition stage of the procurement process. Commercial criteria as well as technical are being used in the selection of proposals. However, as noted earlier, the RRM would benefit from being more administratively efficient (see recommendation under Output 4). / 2.3 Is the project on-track against original timescale: No; slightly behind schedule. / KNOW-FOR will remain off track until revised indicators and milestones are adopted (see relevant Output-level recommendations). As noted earlier, there have also been start-up delays. The project was approved in June 2012. Only PROFOR was able to make immediate use of KNOWFOR funds. CIFOR experienced delays due to the change of Director General at CIFOR; effectively, implementation only began in January 2013. IUCN received their first tranche of funding in October 2012 on signing their MOU with DFID after a prolonged approval process.
[11] Online Survey Results: Using forest-related knowledge, analysis and support, June 2013
[12] These included forest professionals and practitioners, researchers and academics, local and national government staff, NGO staff, international agency and donor staff.
[13] This will not be possible with PROFOR since DFID funding is pooled within the MDTF
[14] This includes the CGIAR 2% cost sharing percentage

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / An independent assessment of KNOW-FOR’s approach to M&E was undertaken in April/May 2013 as part of the preparatory work for this AR[15]. The most important points from that assessment and the foregoing review are as follows. / The original logframe is not helpful and requires reformulation; it is essential that all project partners are fully involved in that reformulation. / Similarly, the project’s original Theory of Change is inadequate and lacks any substantive detail, only providing a very high level description of the project rationale; again, it is essential that all project partners are fully involved in the Theory of Change’s reformulation. / Project M&E needs to focus primarily on monitoring of qualitative data, and in particular it will be necessary to closely involve knowledge audiences if a reasonable assessment of KNOW-FOR’s ultimate influence and impact is to be made. This should include an understanding of communicating to and about different audiences and stakeholder groups. All three organisations need to demonstrate how they have tailored knowledge products to suit different audiences, including women and girls. / Any M&E system should – as far as practicable – be shared by all project partners, which would in turn support the generation of more readily comparable data across the three institutions. / Key recommendations from the assessment, taken forward and endorsed by this AR: / Partners have agreed a reformulated Theory of Change and logframe (Annexes 1 and 2). The revised logframe will be further consulted over the next few months with a view to being finalised by January 2014. / DFID should commission M&E support to assist partners with developing a coherent M&E system for KNOW-FOR to ensure comprehensive reporting against the logframe, with a special focus on understanding audiences and boundary partners, and engaging them in the M&E. / 3.2 Where an evaluation is planned what progress has been made? / DFID will prepare ToRs for an independent evaluation of KNOW-FOR partners’ collaborative working by December 2013. The evaluation should be completed by May 2014.
[15] KNOW-FOR: Developing a programme-wide M&E framework. May 2013

4. Risk
4.1 Output Risk Rating: Low / The risk rating based on the current project logframe is low. Given that the logframe outputs have been substantially changed, a new risk assessment will be required. The primary risks as identified in the original Business Case are presented below, with additional commentary providing updated assessments as appropriate: / Originally identified risk Updated assessment / Despite the availability of information, the costs of implementing policies for more sustainable management of forests and to reduce deforestation are high and constrain implementation. This is a high risk. It will be partially mitigated by ensuring that knowledge that enables agricultural expansion on to degraded land is disseminated. Potential to be reduced by information being developed on the cost of implementing sustainable forest management policies. For example, IUCN’s cost benefit assessments being integrated into cost/carbon abatement curves for different types of landscape restoration interventions. PROFOR are also developing information on the cost effectiveness of different agroforestry and tree based technologies. / Countries benefiting from better information may reduce their deforestation, but “displace” this to other countries that do not benefit. This is a medium risk. It will, to an extent, be mitigated by ensuring broader access to information and extending planning and discussion of knowledge and evidence across borders at regional and global levels. Unchanged / Uptake pathways for knowledge are poor, for example knowledge does not reach decision-makers in a timely way. This is a medium risk and will be managed by including impact and user surveys in programme monitoring so that partners are mandated to demonstrate effective mechanisms for improved knowledge uptake as a “condition” of continued funding. The risk is unchanged, but the original assessment underlines the importance of integrating key knowledge audiences within KNOW-FOR’s approach to M&E. This risk should therefore reduce once the AR recommendations are implemented / There is a medium risk that, if broader budgets to each entity shrink, less priority will be given to the way knowledge is communicated, understood and used, with a focus on maintaining core functions of research and/or analysis and less on dissemination of information/uptake pathways. This risk is now low. It is not applicable to IUCN, given the clear set of results and deliverables agreed with DFID, and the mechanism used to finance the institution. The fact that “knowledge” generation and uptake is one of the four pillars of IUCN’s new business model for 2013-2016 provides additional insurance. / CIFOR’s overall budget has increased by 25% since KNOW-FOR began so the risk of overall budget contraction has diminished. / The risk is still partially valid for PROFOR. As noted in the foregoing assessment, DFID have very limited (if any) scope for insisting that specific activities and objectives be delivered when finance is provided via the MDTF channel. / 4.2 Assessment of the risk level / The programme is currently classed as Low risk overall. This rating is based on the risks set out in the project logframe. The risks outlined above however, are derived from the Business Base’s contextual analysis and remain valid even although mitigation measures are well in hand for some. With the revised logframe, a new risk assessment will also be required.
Risk of funds not being used as intended / Low – The jointly agreed revisions to the logframe have substantially improved clarity and expectations around how KNOWFOR resources are to be used. / Additionally for PROFOR, detailed Operational Guidelines outline how funds are to be used under the MDTF, and the PROFOR Secretariat is compelled to report to the Advisory Board that funds have been used in compliance with these Operational Guidelines – which are broadly consistent with KNOW-FOR’s strategic objectives. For IUCN, KNOW-FOR activities are fully integrated into IUCN’s monitoring and accountability systems. / 4.4 Climate and Environment Risk / The option selected for implementation scored a C in terms of climate change and environment risks and impacts, and an A for opportunities to make an impact on climate change and environment concerns. This remains valid. / The partner organisations selected to implement KNOWFOR are well placed to contribute to efforts to reduce emissions, sustain and enhance livelihoods and ecosystem services through the knowledge products that they produce. Key to this success will be how effectively the partners are able to target and communicate knowledge effectively. Measures are being taken to place additional emphasis on understanding boundary partners/knowledge clients, improving how knowledge is targeted, communicated and how it is used. This should ensure that information produced has the best chance of uptake and use. / All three organisations have corporate social responsibility or environmental/greening strategies in place to minimise their environmental and carbon footprints.

5. Value for Money
5.1 Performance on VfM measures / Through experience gained in this first year, it can be concluded that the original value for money assessment undertaken within the Business Case set overly ambitious impact-level results. However, the value of the knowledge products produced, as evidenced in the online survey, combined with the potential gains to be made from the measures to improve the theory of change and log frame, and to maximise the benefits of more joint working, are likely to deliver good value for money. / The Business Case frames the impact-level indicators and milestones as being attributable to KNOW-FOR, yet experience so far in the project’s implementation suggests that the project can only ever hope to contribute to such high level achievements. It is challenging to demonstrate results from knowledge uptake projects, as the implementation partners are essentially ‘one step removed’ from the delivery of development results. It is the KNOW-FOR partners’ knowledge audiences that will ultimately deliver the development results that KNOW-FOR seeks to achieve. Measuring these metrics – particularly CO2 reductions and ecosystem value – are notoriously difficult in their own right; attempting to measure those metrics when you are one step removed from the actual activity is arguably impossible. / Given the proposed revision to the logframe and the Project’s considerable monitoring challenges it is recommended that these VFM measures and their accompanying impact targets and indicators be reconsidered or, at the very least, treated as high-level goals that KNOW-FOR can only ever contribute to. Further work should be done to explore alternative measures of VFM associated more directly with the delivery of the project. / In addition to the VFM measures identified in the business case, the following can also be highlighted as significant leveraging contributions, in terms of influence and investment: / The DFID KNOW-FOR program provided the impetus to develop the CGIAR Consortium Research Programme (CRP) Forests, Trees and Agroforestry (FTA) theory of change using visual outcome mapping tools. This includes three CGIAR member organisations. Understanding how to articulate CIFOR’s contribution to the KNOW-FOR program has influenced CIFOR’s approach to the development of the FTA’s Phase 2 (2015-18) proposal development process. / IUCN successfully supported the Government of Ghana in the preparation of the Forest Investment Plan, successfully leveraging about USD10 million for investment in landscape restoration under the Plan. Work carried out with KNOW-FOR funds in Rwanda is leveraging a USD53 million Global Environment Facility programme. IUCN have also been able to make use of the KNOW-FOR support to achieve political influence/leverage. This includes for example, the pledges to the Bonn Challenge announced in December 2012 by ministers from Costa Rica and El Salvador. / PROFOR has very successfully used the platform provided by the World Bank to further its work on sustainable landscapes. The World Bank is currently preparing an “Action Plan for Forests and Trees in Sustainable Landscapes” which builds on and draws from the conceptual and analytic work supported by PROFOR. The Bank has also been a significant proponent of the Global Landscapes Forum (to be convened in Warsaw in November on the sidelines of the UNFCCC COP), which derives much of its analytical underpinnings from PROFOR’s work on climate-smart agriculture and the potential for restoring rural landscapes through tree-based systems. / 5.2 Commercial Improvement and Value for Money / CIFOR is working hard to reduce overhead costs as outlined in the cost drivers section. Partners are also working to identify unit costs for the technologies or approaches that are being developed for dissemination. IUCN, PROFOR and CIFOR have different organizational objectives and mandates. As organisations focussing on research and/or analysis, for CIFOR and PROFOR in particular, a large part of their absolute costs are staff related. These will remain significant since they require the continued input of highly qualified and experienced professionals. On-going monitoring will help ensure that there is a sustained effort to achieve further commercial improvement. A specific vfm indicator is proposed within the new logframe to ensure that partners track such improvements. / By improving the collaborative nature of work under KNOW-FOR, it is expected that the project will be able to deliver further benefits in terms of value for money, notably through better coordinated research production, dissemination and uptake. This will also include sharing technologies for dissemination and coordinated working with shared audiences for example. As mentioned above, this will lead to the three organisations becoming more than the sum of their parts in terms of impact, notably through economies of scale, improved synergies, and by bringing together their currently disaggregated target groups. This will be achieved through the development of a common M&E system under the newly agreed logframe and verified through the evaluation of collaborative working scheduled for next year. / 5.3 Role of project partners / Partners have shown a strong commitment to improving collaborative working in the programme, notably during recent discussions held in July 2013. KNOW-FOR is a recent project that the three organisations have made an effort to integrate into their systems and ways of working over the last year (since mid-2012 launch). It is expected that opportunities will emerge to exploit the economies of scale and greater impact that can be achieved by working together. An M&E input is planned to work with KNOW-FOR partners to harmonise and improve the ways in which they track the dissemination, uptake and impact of their research and knowledge activities. Once data has been collected for a period of time, the insights will facilitate improved allocation of resources. This will further increase the research dissemination and uptake that provides the tangible forest and environment impacts that KNOW-FOR was created to achieve. / As these coordinated efforts start yielding results, we expect value for money indicators to improve. Some possible indicators would include the cost per publication or study produced, cost per newsletter subscriber[16], annual funding secured per employee, number of citations per year, survey results improving relative to spending, etc. DFID should agree a number of these with partners to monitor over the coming year. The most relevant indicators of value for money will vary for each organisation, but together they should be able to construct a narrative illustrating how KNOW-FOR coordination is leading to continued improvement. The M&E support recommended under this AR will make recommendations to the project partners, which will facilitate the implementation of better practices and vfm. / 5.4 Does the project still represent Value for Money : Y / Although it is difficult for the programme to perform well against the very ambitious and perhaps inappropriate value for money measures set out in the business case, this is balanced by KNOWFOR already demonstrating; a) that knowledge audiences value the products so far produced; b) how it can leverage influence and investment (above), and c) the new focus on collaborative work (including a specific indicator on VFM within the proposed new log frame) bodes well for enhanced value for money going forward into year 2. / 5.5 If not, what action will you take? N/A
[16] Total cost of publication divided by number of subscribers = cost per subscriber, so more subscribers indicates increased dissemination of the research and improves this indicator. This can also be done for website users or on-site article hits for example.

6. Conditionality
6.1 Update on specific conditions / N/A: only applicable to projects where Financial Aid is provided directly to a partner government.

7. Conclusions and actions
Progress on KNOW-FOR has not proceeded at the pace originally envisaged, and there have been challenges with reporting progress given design flaws in the current logframe. This Annual Review is an opportunity to reflect on the original design and underlying Theory of Change and to work together with partners to agree a strategic way forward. Action to address the various challenges highlighted in this review is now well underway. / Despite performance appearing to be weak this year when measured against the (now revised) logframe, KNOW-FOR is still a potentially transformative project; the three implementation partners have considerable clout in the forest sector, but one of their primary barriers to success (and hence one of the main challenges to be addressed by KNOW-FOR) is an underdeveloped understanding around how to accurately measure knowledge uptake, influence and impact. / The following key measures will be taken and reviewed regularly (quarterly meetings with partners) for the programme to demonstrate improved performance at the next Annual Review. / Finalise the revised log frame and refine indicators; / Develop a system to report against the new log frame / Increase focus on understanding knowledge audiences and the measurement of knowledge uptake / Demonstrate collaborative working and the gains to be made from working to each other’s strengths / These are set out in more detail in the table below with suggested process and timeframes. / Measure to be taken Process Completion date Responsibility / Finalise revised theory of change and log frame Build on July 2013 workshop outcome / Indicator refinement with support from M&E consultancy (see below) By end of September 2013 / February 2014 DFID to convene virtual meeting / DFID to procure M&E consultancy services (see below) / Develop activity plans and deliverables for each output annually Where contractual relationships allow Align with each partner’s planning cycle CIFOR, PROFOR, IUCN / Assessment of progress in collaborative working 6-8 months into year 2 Independent evaluation By April 2014 DFID / Quarterly meetings with all partners together to assess progress and improve collaboration Virtual meetings First to be held by end of September 2013 DFID to convene / Procure M&E specialist services to support indicator refinement, develop knowledge uptake measurement methods, define baselines and establish reporting framework. Allocate resources from RRM to procure Consultancy services through Forestry Framework Agreement or PEAKs / Alignment with partner institution systems where possible Contract by end December 2013 / Consultancy completed by August 2014 DFID to procure / Partners to work closely with consultants / Improve understanding of knowledge audiences and ensure they play a central role in programme M&E Link with M&E consultancy, establish baselines April 2014 CIFOR, IUCN, PROFOR / DFID to use its role on the PROFOR advisory board to advocate for monitoring systems that increase PROFOR’s focus on impact pathways and boundary partners (preparatory work indicates a high chance of success) Discussions with Advisory Board members in preparation for next board meeting March 2014 DFID and PROFOR / Agree value for money metrics Agreement with partners, refinement of vfm indicator in logframe End of December 2013 DFID and partners / Review the RRM mechanism and revise accordingly to reduce transaction costs In consultation with DECC and DEFRA End of December 2013 DFID

8. Review Process
The review was conducted during June and July 2013 by DFID staff with consultancy support supplied via the DFID Specialist Evaluation & Quality Assurance Service (SEQAS). / Following an initial assessment of KNOW-FOR’s M&E strategy (conducted during May 2013), reporting templates were developed and circulated to the three project partners. Once project partners had completed and submitted these templates the AR team held follow-up discussions with each partner, in order to explore and clarify any outstanding points. In tandem with this process, an online survey was carried out, targeted at the project partners’ key ‘knowledge audiences’ (based on a shared understanding between DFID and the project partners that these audiences were the ‘direct beneficiaries’ of KNOW-FOR). A total of 201 individuals / organisations were contacted, with 96 responses received. / The foregoing analysis and findings of this AR were based on information from these three elements (reporting templates, follow-on partner discussions, online survey), along with the informal monitoring and interaction with partners undertaken by DFID staff throughout the year. / A strategic planning workshop was held in July 2013 involving DFID and all three KNOW-FOR partners. Considerable progress was made during that workshop to address some of the key findings emerging from the AR process, particularly around redrafting of the logframe, redrafting of the TOC, and development of a shared M&E system. The AR therefore reflects the agreements reached during the strategic planning workshop. / The following documents informed the AR: / Improving the way knowledge on forests is understood and used internationally (KNOW-FOR), Business Case and Intervention Summary (Quest Ref: 3717343) and logframe (Quest Ref: 3409906) / KNOW-FOR: Developing a programme-wide M&E framework, DFID SEQAS, May 2013 (Quest Ref: 4108121) / Draft concept for KNOW-FOR partner reporting format, DFID Annual Review 2013, DFID SEQAS, May 2013] / KNOW-FOR Year 1 Annual Review, Online Survey Results (Quest Ref: 4107634) / KNOW-FOR: Year 1 DFID Annual Review, CIFOR Report Template (Quest Ref:4118014) / KNOW-FOR: Year 1 DFID Annual Review, IUCN Report Template (Quest Ref:4117945) / KNOW-FOR: Year 1 DFID Annual Review, PROFOR Report Template (Quest Ref:4118032) / Progress Report and Completion Notes for Activities supported by PROFOR during CY 2012, PROFOR Secretariat, Feb 2013 / PROFOR Advisory Board Meeting DRAFT Summary Report, PROFOR Secretariat, Mar 2013 / Proposed Work Program and Financial Projections for Calendar Year 2013, PROFOR Secretariat, Mar 2013 / PROFOR Logical Framework for CY 2012, PROFOR Secretariat, Mar 2013 / CGIAR: Forests, Trees and Agroforestry – 2012 Annual Report (accessed 19/06/2013) / Living Landscapes: Solutions for a sustainable world (Forest Day 6 Report), CPF, Dec 2012 (accessed 19/06/2013)