(Annex-iii)

PUNJAB ECONOMIC OPPORTUNITIES PROGRAMME (PEOP)

Livestock and Dairy Component (L&D) - Closure Note

Background: PEOP comprised of two components, one focusing on skills and the other on the development of the livestock and dairy sector in 4 selected districts of South Punjab Bahawalpur, Bahawalnagar, Lodhran and Muzaffargarh. For each of the two components, £ 25 million had been allocated, with 50% contribution coming from the Government of the Punjab and 50% from the DFID. In addition, DFID is providing £ 5 million as Technical Assistance support for the effective implementation, and monitoring and evaluation of the PEOP.

Recommendation of the 2nd Annual Review (AR) - Closure of the L&D Component: The second annual review of the PEOP conducted in July, 2012 recommended the closure of the L&D component and diversion of its funds to Skills component i.e. Punjab Skills Development Fund (PSDF). The review concluded that though the interventions of the L&D component had been redefined and it had been capacitated with technical assistance support, the progress over 2 years had been negligible and the stipulated targets were unrealistic given the existing and potential alternative implementation arrangements for the component and the opportunity cost for DFID to explore and pursue latter. (for details - Outputs 4 onwards in the 2nd AR of PEOP, Quest No. 3658263).

Scale of Interventions: In two years, the L&D component managed to initiate/complete the following three activities:

  1. 26 Farmers Awareness Days (FAD) (2-day sessions focusing on raising farmers awareness about livestock and diary related issues and vaccination of 52,000 large and small ruminants) were conducted. Over 6,000 farmers participated. During the Annual Review 2012, beneficiaries gave very mixed feedback on the FADs, appreciating the vaccination services but expressing reservations about the benefits of the awareness sessions. A report on the FADs was prepared by Center for Economic Research Pakistan (CERP).
  2. Under a pilot collaborative effort with Telenor, the PIT provided contents for a messaging service to 2,000 farmers. The economic profile of the farmers is unknown and could not be verified during the AR 2012 field visit. Messages were of mixed quality. For example, often the message identified what should not be done (which may be obvious enough to the farmers) but mostly fell short of proposing solutions. No evaluation of this intervention has been conducted.
  3. Veterinary Assistants Scholarship Scheme (VASS), 2 year diploma for 170 students in 5 different universities was initiated in June 2012, (till June 2014). The selection process for students enrolled in the VASS did not take into account their socio economic backgrounds. Of the 6 students (3 male and 3 female) interviewed during the AR 2012, 5 belonged to modest middle class backgrounds and had higher qualifications than the required matriculation.
2. PIT was unable to initiate work in the areas of Policy and Regulatory Reforms of the sector, given capacity constraints and preoccupation of the TA support with filling the management gap within the PIT. (for details - Outputs 4 onwards in the 2nd AR of PEOP, Quest No. 3658263).

The Project Steering Committee in its 5th meeting decided that Secretary P&D will act as Team Leader Project Implementation Team from 1 Nov 2012 till its closure i.e. 30 June 2014.

Expenditure of the L&D Component: Out of allocated £12.5 million DFID released £2.2 million (PKR 300.183 million @ 1 GBP = PKR 136.4470) in March 2011. The Programme Implementation Team spent £394,627.67 (PKR 53.843 million) till 31 October 2012 on activities a), b) and partial c) above. In addition, £339,636.47 (PKR 46.340 million) was required to complete the VASS activity. Given that Government of Punjab didn’t contributed its funding till closure of L&D component, all spent and VASS required funds £734,264.15 (PKR 100.183 million) were made out of DFID funds.

Settlement of Funding: The settlement of matching funds was made during Annual Statement of Progress 2013. Government agreed to contribute on matching principal for all spent as well as for VASS activity and divert all remaining DFID balance funds to PSDF. DFID funds up to £1.83 million were transferred to PSDF in January and March 2013.

a	12,500,000.00	DFID commitment to L&DD Component
b	2,200,000.00	DFID Contribution to L&D component in March 2011
c	734,264.15	L&DD Total spend + Veterinary Assistants Scholarship Scheme commitment until June 2014
d	367,132.08	DFID share of total spend (i.e. 50% = c ÷ 2)
e	367,132.08	Matching funds contributed by GoPb
f	1,832,867.93	Total balance due to PSDF/DFID (b - d)
g	1,465,845.79	Funds Transferred to PSDF on 31/01/2013
h	367,022.13	Funds Transferred to PSDF on 13/03/2013

Audit and other financial compliance: During annual review 2013, P&D confirmed the Annual Audit Statements 2011-12 are ready at Auditor General Office to be issued. Furthermore, during the annual review Special Departmental Accounts Committee minutes were shared with DFID, which states that, 13 out of 31 observations are outstanding/ pending as of 30 June 2013. Most of outstanding observations are related to provision of documentary evidences i.e. tax exemption certificate, reports against which honorarium has been received and approval of revised PC-1. For year 2012-13 audit has been already been initiated. PEOP team is following up on i) sharing Audit Report and ii) outstanding/ pending observations, with P&D department. Note: due to early commencing of Audit 2012-13, the outstanding observations from 2011-12 issues might not have been resolved.

Transfer of Assets: Out of PKR 53.843 million expenditure, assets worth PKR 15.483 million (£113.472.63 - 28.75% of expenditure) were procured. Depreciated value of assets transferred to PSDF, P&D department and IFAD funded South Punjab Poverty Alleviation Programme (SPPAP) was PKR. 11.411 million (GBP 83,630). Assets spot check at PSDF Lahore office and P&D was held in April 2013 followed by spot check at PSDF and SPPAP Bahawalpur offices during annual review 2013 Quest No. () Complete assets lists are available on quest (3927783) as well as lists of L&D assets to PSDF, P&D and SPPAP (40251220). The later will be used for monitoring purposes on quarterly basis.

Monitoring of VASS: Being focal person VASS, Secretary P&D Department, commenced a status report of VASS conducted by Senior Chief Regional Planning, P&D Department in November 2012. Report available in DFID Pakistan. Quest Number 3927760. P&D department is leading on verifying outputs and release of funds to implementing partners. During annual review 2013, DFID and P&D department agreed to jointly monitor the VASS activity and link payments to outcome of monitoring visits.

Generation of Livestock and Dairy Related Database: A livestock supply side survey report covering the veterinary institutes, dhodis, milk collection centers, and cattle markets has been completed by the Center for Economic Research Pakistan (CERP). In addition the livestock component was covered in the household survey conducted by CERP to establish the baselines in the PEOP districts and understand the issues and practices of the livestock farmers in the PEOP pilot districts.

Other L&D Development Interventions Underway: In addition, a number of other donors and commercial players such as IFAD ($7m), Haleeb Foods ($25m), USAID/DRDF ($14m) and PRMP/ADB ($5m) are working towards the development of the L&D sector in Punjab, implying that DFID’s withdrawal from the sector will not create a major void. Moreover, the PSDF was keen to sponsor short term training in the agriculture sector (including livestock and dairy) given the dominance of this sector in the pilot districts and the number of people involved in it.

Lessons Learnt - Experience of the L&D Component: A summary of the lessons learnt is presented below.

  1. Programme design needs to be closely scrutinized for its Theory of Change and the capacity of the implementation arrangement to deliver: The PEOP had a weak design. Background studies commissioned are fragmented pieces that focus more on problems than on identifying solutions and leading to any programme design. The outputs of the log frame, for example, had to be substantially revised and rationalized as they covered a range of activities without a clear theory of change and ignoring the institutional capacity of the L&D Department which housed the L&D component. In the design phase, no institutional assessment of the L&DD was conducted. Consequently, there was no plan, departmental buy-in or political will to address the gaps in the department and boost its capacity to facilitate PEOP delivery and engage with the private sector.
  2. Programme design should clearly address how sustainability will be achieved, and what political support is required for it. Outputs and implementing partners need to be proposed realistically. Otherwise a Programme can end up conducting a series of interventions that culminate with the programme.
  3. The design phase should also settle modalities of funds transfer to projects housed in government departments. For example, considerable time was consumed in determining funds transfer mechanisms and opening of the assignment accounts. Subsequently opening of foreign currency and local assignment accounts also took considerable time.
  4. Robust and autonomous private sector governance arrangement is necessary for providing strategic guidance and support: The Steering Committee of the PEOP responsible for providing overall direction and facilitative support for PEOP was responsible for approving the work plans of the L&D component. It delegated this power to a Livestock Development Committee which was constituted in order to serve as the “Board” of the L&D component, inspired by the value that the PSDF Board was bringing to the Fund. However, P&DD raised the objection that the LDC could not provide financial approval of the sub-projects of the L&D component which required approval of the government forums. Private sector members of the LDC subsequently lost interest in the component and stopped attending its meetings. In addition, approval of the interventions was delayed as they were first approved by the LDC and then the GoPb forums. The L&D department was reluctant to engage the private sector as this would reveal its own shortcomings in delivery of extension services.
  5. Had the PC-I been more specific about the L&D interventions, the long approval processes could have been avoided, though at the cost of being inflexible. The lesson for future projects is to make this choice carefully and create a balance. Similarly, PC-1 should have allowed for following DFID Procurement Guidelines which would have expedited the procurement process or could have provided the project director with a choice between the donor and government guidelines, with precedence to the donor’s in case of a conflict between the two.
  6. Competitively hired management on attractive remuneration Packages is Indispensable for attracting competent Staff, Particularly for Programmes Located/Focusing on Far Flung Areas. Otherwise, dependence on Technical Support can be high contributing to Programme’s unsustainability. In future projects with the government, departmental ownership should be ensured through proper incentives. For future the competency profiling for each position should be given due importance and should be clarified between the donor and the government at an early stage, particularly since the hiring and firing process in government is cumbersome. Illustrative examples leading to this learning are as follows: a) The position of TL required programme management skills but the qualifying criteria included a PHD in veterinary Sciences. Changing the job criteria requires approval of several government departments and final approval of the Chief Minister himself, b) Hiring of the staff required in the PIT was delayed as one of the rejected candidates filed a petition in the court, which stalled in the hiring process c) As project jobs are temporary and were to be based in Bahawalpur, private sector professionals were reluctant to apply while a government notification barred government employees from getting allowances.
  7. DFID’s Areas of Competitive Advantage Should be borne in Mind, when making Decisions Regarding Fresh Investments. DFID is increasing its development investments in Pakistan and priorities focus on education, health, governance, and wealth creation (microfinance and skills) and to help build on the successes achieved through programmes in these areas. Moreover, the focus is on working through the private sector and effective PPP modalities that offer good value for money for UK tax payers’ money.

The livestock and dairy supply side survey reports should be shared with all livestock and dairy focused development programmes and Pakistan Dairy Association for sharing with all of its corporate members.