Type of Review: Annual Review

Project Title: Promines

Date started: 19/10/2011[1] Date review undertaken: August 2012
[1] Declared effective by the World Bank

## Introduction and Context

What support is the UK providing?
The UK is providing £27 million through a World Bank-managed single donor trust fund for the ‘Growth with Governance in the Minerals Sector’ (ProMines) Technical Assistance Project in the Democratic Republic of Congo. It has also allocated an additional £0.5 million to share the costs of a senior mining specialist within the Bank’s Kinshasa office for Project management and sector coordination. The World Bank is contributing $50 million (£33 million) to the Project.

What are the expected results?
The expected impact is to improve governance of the mining sector and increase its contribution to economic growth, sustainable development and poverty reduction. / One particular indicator from the logical framework that best reflects project achievement is: / “Annual tax revenues from the mining sector collected at export point increase from $75 million in 2008 to $150 million by 2011 and to $300 million by 2014”. / Higher public revenues from mining will enable the Government to invest in poverty reduction, including an increase in investment in health and education, which will improve human development across the country.

What is the context in which UK support is provided?
The DRC is a country with vast mineral wealth. In the past the mining sector has been a key driver of the economy and with improved prospects for peace across the country it has begun to play this role again in recent years (although in 2009 the impact of the global economic crisis and commodity price collapses has hampered the recovery). However, critical problems related to the way in which the sector is governed have meant that the revenues generated from the mining sector have not been used effectively to contribute to sustainable economic and social development in the DRC. In addition, on-going conflict in the East – at least partially driven by the illegal extraction of natural resources – is a drain on public resources and stands in the way of industrial-scale mining production. / Following the fall of the Mobutu regime and the period of civil war, the transitional government took some important steps to stimulate development of the sector including the passage in 2002 of a new Mining Law and regulations. These actions, combined with a period of high commodity prices between 2004 and 2008, resulted in a surge of exploration and exploitation activities. / Despite these positive aspects, there remain significant challenges that need to be tackled for the sector to reach its full potential. Corruption and low staff morale affects the mining administration as it does all parts of government. Mining laws and regulations – while sound from a technical perspective – are not consistently applied, which leads to confusion and creates opportunities for rent seeking by officials and private agents. Continued insecurity in the East makes it all but impossible for government agencies to control and manage mining activities. As to the demand for better mining sector governance, the Congolese NGOs active in this area often lack resources and independence to hold government and companies to account. / The Project was originally expected to become effective in September 2010, but in the event this was delayed to October 2011, primarily because of transparency and accountability concerns which led to the negotiation of an “Economic Governance Matrix” of performance indicators between the World Bank and the Government of DRC (GoDRC). Concerns around the transparency and accountability of mineral asset transactions also became the subject of conditions within the International Monetary Fund (IMF) Second Extended Credit Facility for DRC, and have delayed disbursement of the latest tranche. / In the intervening period since DFID approval in April 2010 and formal effectiveness in October 2011, the Project has become even more relevant for several reasons: / There has been increasing international publicity by the media and advocacy NGOs around transactions in GoDRC-owned mining assets. UK parliamentary interest in the topic has increased accordingly. Responsible investment and donor funding for DRC in all sectors are at risk if there is no improvement / DRC’s bid to be declared compliant under the Extractive Industries Transparency Initiative (EITI) is at a critical stage, with a very challenging final deadline of March 2013 / International demand for artisanal (hand-dug) minerals from eastern DRC has fallen sharply as a result of supply chain due diligence measures aimed at cutting off funding for conflict, including the 2010 US Dodd Frank Act. There is now an urgent need for the certification and traceability mechanisms envisaged under the Project, to sustain and expand the legitimate trade in these minerals, and the livelihoods dependent upon it / Although the November 2011 DRC Presidential and Parliamentary elections were widely considered as flawed, the resulting new Government formed in May 2012 has made a clear commitment to tackling the above issues.

## Section A: Detailed Output Scoring

Output 1: Improve basic conditions for access to mineral resources to encourage increased investments in and revenues generated by the mining sector
Output 1 score and performance description: / C (Outputs substantially did not meet expectation)
Progress against expected results: / Expected 2011/12 results are: / The geodesic system: Network upgrade being carried out / Availability of geological information for the country: Design of geological database completed / Communication and information flow within the sector including consultations with civil society: Satisfactory implementation of the strategy / Progress: / Tenders have been invited for a consultancy to project manage the upgrade of the geodesic system / Tenders have been invited for a consultancy to design the geological database, which is to be completed during 2012 / A communications strategy has yet to be developed. However, terms of reference have been drafted for an Accountability Platform, and a validation meeting scheduled for the end of August 2012. There has been considerable progress in recent months in the publication of mining concession contracts and amendments, at least partly attributable to pressure from the World Bank, IMF and other donors, as well as civil society. A few important documents remain unpublished, and there is also insufficient analysis and debate as to any abuses that may have occurred, and how to mitigate them in future. / Recommendations: / The results milestones for these and all other monitoring indicators should be reviewed, as they were set in expectation that the Project would become effective in September 2010. / A further indicator is needed to reflect the specific support the Project is providing for revision of the 2002 Mining Code. This includes support given, with other donors, to the development of civil society proposals for revision of the Code / High priority should be given to the development of a communications strategy and associated tools. The Accountability Platform would be one such tool, and warrants explicit mention amongst the milestones for this indicator. Its mandate for dialogue on issues of concern within the extractives sector should include more open discussion of the Economic Governance Matrix than has been the case to date. / DFID should be more active in its support for the IMF conditions on transparency and for the Economic Governance Matrix, including at the Executive Director level. / DFID should find ways of collaborating with international advocacy NGOs in support of common objectives of transparency and accountability. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Strengthen the Government's capacity to manage the mineral sector
Output 2 score and performance description: / C (Outputs substantially did not meet expectation)
Progress against expected results: / Expected 2011/12 results are: / Presence and capacity of CAMI (Mining Titles Registry): 1 fully-functioning CAMI operation at provincial level / Capacity and performance of SAESSCAM (Government Service to Support Artisanal Miners): National and provincial plan for SAESSCAM restructuring adopted by GoDRC / Status of technical and professional training institutes and programmes in Katanga: Upgrading of selected institutes and university programmes being carried out in accordance with agreed plan. / Progress: / CAMI is fully operational in South Kivu (Bukavu), and will open soon in two other provinces (Maniema and Orientale), although tenders are still under evaluation for the full institutional audit of sector organisations. The Project has also equipped CAMI at the national level with equipment for its website. One of the criteria in the Economic Governance Matrix is that the mining cadastral map should be published online, along with the list of mining titles; these are now available on http://www.flexicadastre.com/drcmapportal/ / The Project Implementation Unit (PIU) is preparing a restructuring plan for SAESSCAM, but again in advance of the full institutional audit of sector organisations / Tenders have been received and evaluated for preparation of a situation analysis and action plans for professional training centres / Recommendations: / Restructuring and capacity building of sector organisations should be based upon the findings of the full institutional audit, and caution is needed in proceeding with any proposals and equipment procurement in advance of this / Plans for SAESSCAM need to be closely integrated with activities under Output 3 on capacity and accountability in tax collection, to avoid simply increasing the capacity and opportunity for illegal and unaccountable taxation. The EITI reporting for 2008 and 2009 identified particularly huge discrepancies for the artisanal sub-sector between taxes reported as paid and those acknowledged as received. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: Strengthen the Government's capacity and accountability in mining tax collection
Output 3 score and performance description: / B (Outputs moderately did not meet expectation)
Progress against expected results: / Expected 2011/12 results are: / Production of EITI reconciliation reports for increased transparency of mining sector: Government and mining sector companies provide necessary information for cobalt, copper, and one other resource for EITI reconciliation report for FY 2010. Recommendations from previous report acted on. / Status of tax collection framework for mining sector: Modelling of mining taxation revenues / Progress: / EITI reports for 2008 and 2009 were published in January 2012, whilst the report for 2010 is scheduled for December 2012, with funding from Germany (definition of scope of required declarations) and Belgium (appointment of independent reconciler). The published reports do not distinguish between cobalt and copper, but they incorporate data for these and other minerals, as well as reporting separately on petroleum. Recommendations from the published reports are being acted upon for preparation of the 2010 report. Donor support was previously channelled through a separate dedicated World Bank Administered Multi-Donor Trust Fund (MDTF), but this has expired and the expected renewal has been delayed. GoDRC has reiterated its high level political commitment to passing the final validation assessment by the extremely challenging deadline of March 2013. 50% of the cost of this assessment has to come from GoDRC’s own resources, / The Ministry of Finance has been publishing quarterly statistics on natural resource tax revenues since the beginning of 2011. In April 2012 the International Monetary Fund (IMF) produced an analysis and recommendations on mining sector taxation. The Project has also been associated with a German-funded analysis and inventory of mining taxes through COREF (Comité d’Orientation de la Réforme des Finances Publiques). No tax modelling has yet been done through the Project. A training programme to reinforce proper implementation of tax regime has yet to be developed, although that was anticipated for the first year of implementation. / Recommendations: / The Project should give all possible assistance to DRC’s achievement of EITI compliant status, to compensate for delays in the MDTF. Failure to meet the March 2013 deadline will result in DRC being delisted from EITI, representing a huge blow both to DRC’s reputation and to investor confidence / Taxation analysis and modelling should be provided for the consultations around revision of the Mining Code. Much of the content of the expected training programme will be determined by the taxation provisions within the revised Code. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 4: Develop innovative approaches to improve socio-economic impacts of artisanal and industrial mining in three provinces
Output 4 score and performance description: / C (Outputs substantially did not meet expectation).
Progress against expected results: / Expected 2011/12 results are: / Monitoring of social and environmental impacts of industrial mining activities involving the participation of local communities: Policy and institutional reforms to reduce environmental and social risks from expansion of the mining sector identified and agreed with community involvement / Formalization of artisanal mining: Successful Implementation of at least two pilots / Progress: / Tenders for preparation of a Strategic Environmental and Social Assessment (SESA) for the sector were received on 21 June 2012, and the technical evaluation is substantially complete. Policy and institutional reforms have to await completion of the SESA / There is no evidence of the action plan for artisanal mining envisaged in the logframe for the first year of the project. However, artisanal miners in Katanga have organised themselves into cooperatives, and a certification and traceability mechanism has been piloted to comply with supply chain due diligence requirements for conflict minerals. Mine certification for the same purpose in North and South Kivu, around five centres de négoces constructed by other projects, cannot proceed because of the poor security situation. Under these circumstances it is planned to refocus activities in Maniema.The administration has attached high priority to implementation of the regional artisanal mineral certification mechanism under the International Conference on the Great Lakes Region (ICGLR). The Project has devoted considerable effort to coordinating the various actors (ICGLR, Organisation for Economic Cooperation and Development – OECD, ITRI – international tin industry body, PACT – NGO) and donors (USA, Germany). / Recommendations: / DFID DRC should engage with the SESA once the responsible agency is appointed, to feed in recommendations developed during its recent Climate and Environment Strategic Programme Review / The milestones for the second indicator should make more specific reference to the certification and traceability work, which is crucial to maintaining and expanding legitimate artisanal mining in Eastern DRC, and the livelihoods that depend upon it. / All activities related to artisanal mining should be guided by an action plan to strengthen regulation and management of the sub-sector and to improve conditions on and around artisanal mining sites, as envisaged in the logframe / The Katanga Extractive Industries Development Initiative (KEIDI) would make a useful and innovative contribution to the socio-economic impact of industrial mining under this output, with the potential for application in other provinces too. This initiative was planned by USAID and DFID, in partnership with the Katanga Provincial Government and industrial mining companies, to pool corporate social responsibility funds with matching donor funds to contribute to strategic development objectives within the province. KEIDI had been included within ProMines in the early stages of preparation, and is still referred to in the World Bank Project Appraisal Document (PAD), but was separated out when it seemed ready to proceed ahead of Promines. However, it too became delayed by reputational concerns over partner companies, but could now be reincorporated / A further indicator is needed to reflect Project activities towards elimination of the worst forms of exploitation of women and children in the sector, for instance through its partnership with the Nordic Trust Fund / The risk rating for this output should be changed from Medium to High, in view of the deterioration in the security situation particularly in the Kivus, which is preventing significant progress in the most important provinces for artisanal mining. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 5: Establish monitoring and evaluation (M&E) framework for evaluating project implementation and its impact
Output 5 score and performance description: / C (Outputs substantially did not meet expectation). Both results depend upon activities that remain in the early stages of procurement.
Progress against expected results: / Expected 2011/12 results are: / M&E framework established: Implementation of M&E system; Biannual project monitoring reports produced; Biannual project supervision missions with participation from range of stakeholders / Availability of household economic data for mining areas: Data (for 2010) available and disseminated / Progress: / An M&E system was developed as one of the effectiveness conditions for the project in 2011. However, implementation of the system awaits procurement of a consultancy to establish the required database, with Terms of Reference submitted for World Bank no-objection on 13 June 2012. No biannual monitoring reports have yet been seen by DFID. There have been two joint supervision missions since project effectiveness, from 10-21 February and 24 June to 7 July 2012. DFID and other stakeholders participated in both. / Household economic data for mining areas is to be drawn from surveys conducted by the Project and from routine 1-2-3 household surveys by the National Institute of Statistics. Neither of these datasets is yet available. The first awaits procurement of a consultancy to conduct the baseline survey, with Terms of Reference submitted for World Bank no-objection on 13 June 2012. The second awaits a Memorandum of Understanding between the Project and the National Institute of Statistics, for which World Bank approval was sought on 4 May 2012. / Recommendations: / Both the Project and the World Bank need to give much higher priority to M&E. The lack of reliable indicator baselines or progress monitoring almost a year into implementation is unsatisfactory. In particular, evidence is wanting for a thorough Annual Review in justification of DFID’s continuing support for the Project / The World Bank should increase its staff resources in DRC devoted both to Project supervision and to its donor leadership role in the sector. Not only is there a need to turn around procurement no-objection processes more quickly, but also for more proactive Project oversight linked with strategic dialogue with GoDRC and other partners. Donors reached agreement in May 2012 with the Ministry of Mines on revitalising the existing Thematic Group for mining sector coordination, but higher profile representation by the World Bank, as lead donor in the sector, is needed to effect real change. Similarly, much stronger World Bank representation at the regular meetings of the EITI National Executive Committee is needed to try and avert the failure of this process. On the basis of discussions during project preparation, DFID allocated a separate budget of up to £0.5 million to contribute to the costs of an in-country World Bank Task Team Leader (TTL). So far, the Bank has not taken advantage of this provision, and the current Washington-based TTL stretches to cover programmes in about ten countries. The TTL agreed, during the June/July supervision mission, to respond by September with the Bank’s proposals for addressing this issue. / As already noted, the results milestones for all indicators within the logframe should be reviewed, as they were set in expectation that the Project would become effective in September 2010, whereas actual effectiveness was in October 2011. / Impact Weighting (%): 5% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? N / Several revisions have been recommended in this Review / 1.2 Overall Output Score and Description: / C (Outputs substantially did not meet expectation). / 1.3 Direct feedback from beneficiaries / No beneficiary feedback is yet available, as the Project is not yet delivering on the ground.
1.4 Summary of overall progress / Almost all project activities are at the procurement or preparatory stage. The primary reason for underperformance against the logframe milestones is that the latter were set in expectation of the Project becoming effective 13 months earlier than it did. However, in most cases even the milestones set for the first year of implementation have not yet been achieved.
1.5 Key challenges / The key challenges, emerging from all the above, are: / The threat to donor funding for DRC in all sectors if there is no improvement in transparency and accountability in natural resource management / The real risk of failure of the current EITI process in DRC / The deterioration of the security situation in the Kivus preventing progress on artisanal mineral certification and traceability activities / The need for increased World Bank in-country representation in the sector
1.6 Annual Outcome Assessment / Outcome score and performance description: / C (Outcome substantially did not meet expectation). / Progress against expected results: / Expected 2011/12 results are: / Performance of key institutions in the minerals sector to enforce the legal and regulatory framework: Proposals for improvements to the framework and how it is enforced agreed / Status of transparency and accountability mechanisms: Dissemination and discussion of EITI Reconciliation Reports (national and provincial levels); Project accountability platform launched / Private investments in the mining sector (number of investments over 10 million dollars): 10% increase over baseline of 23 / Fiscal revenues from the mining sector: Revenues from the mining sector collected at export point increase from $75 million (2008 baseline) to $100 million in 2010/11 and $150 million in 2011/12 / Working and living conditions of artisanal and industrial mining communities in project areas: Milestones not yet set. / Progress: / Preparations are under way for revision of the 2002 Mining Code. Civil society has presented its proposals for the revision / DRC did not achieve EITI validation in 2010/11 as anticipated in the logframe. However, the reports for 2008 and 2009 were released in January 2012. A revised deadline of March 2013 has been set for validation. The Terms of Reference and format of the Accountability Platform have yet to be determined / The number of investments in the mining sector has fallen to 15, but this figure is subject to confirmation by the Ministry of Mines based upon the analysis of feasibility studies from mining companies. This indicator is in any case quite imprecise, given that investments could range from $10 million to over $100 million / The export revenues for calendar year 2011 amount to $101 million, based upon the Ministry of Finance’s quarterly reporting as analysed by the IMF / No data, baselines, or milestones are yet available on working and living conditions, pending completion of the Project baseline survey.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / The project is not on track against the original forecasts in the DFID Project Document, but a revised disbursement schedule has been agreed with the World Bank that is broadly consistent with the approved Project Action Plan to June 2013. The latter anticipates a cumulative total commitment of £21.8 million, of which DFID’s share is £9.68 million, against planned cumulative DFID disbursements of £11 million by March 2013 and £13 million by October 2013. However, the Bank has not so far drawn significant DFID funds from the single donor trust fund, and appears to have borne all costs from its own resources. The PAD is explicit that eligible expenditures should be funded by DFID and the Bank in proportion to their respective contributions (44.4% DFID, 55.6% Bank). An explanation of this situation is awaited from the Bank. / 2.2 Key cost drivers / Since this is a Technical Assistance Project, the key cost drivers are fees for the provision of professional services. / 2.3 Is the project on-track against original timescale: N / As already noted, the Project was originally expected to become effective in September 2010, but in the event this was delayed to October 2011. However, even allowing for this delay, in most cases even the milestones set for the first year of implementation have not yet been achieved. Since the lagging progress is entirely due to delays in activities, rather than ineffectiveness in those activities, there are so far no significant cost implications.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes in evidence are yet apparent / 3.2 Where an evaluation is planned what progress has been made? / A robust monitoring and evaluation system is planned for the project, but is not yet in operation. No separate impact evaluation is anticipated.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / Some of the risks identified in the DFID Project Document have come to pass as follows: / Conflict in Eastern DRC intensifies thus making it more difficult / impossible for ProMines to operate in that region. In mitigation, it is planned to shift activities around the certification and traceability of artisanal minerals from the Kivus to Maniema / WB fails to back up technical discussions on mining sector reform with political engagement. In mitigation, DFID is increasing its level of engagement around the Economic Governance Matrix at World Bank Board level. It has also recruited a dedicated Extractives Adviser to its DRC team, who will arrive in February 2013. Nevertheless, these measures are no substitute for higher profile in-country engagement by the World Bank, as below / Reduced engagement from World Bank following Project approval, in particular lack of senior mining expert in Kinshasa. In mitigation, DFID continues to press at all levels from Country Office to Vice President for the World Bank to take advantage of the financial provision made by DFID for an in-country TTL. The current TTL agreed, during the June/July supervision mission, to respond with the Bank’s proposals for addressing this issue during the next mission scheduled for 5 to 19 September. / The other risks in the Project Document have been reviewed and remain relevant. No previously unidentified risks have emerged.
Risk of funds not being used as intended / Special attention was paid to this risk during project preparation, in recognition that it is a particular concern in DRC. According to the PAD, in addition to the usual Project Implementation Manual and Procedures Manual, a Governance and Anti-Corruption Action Plan was developed, addressing both sector and Project risks. Robust financial and procurement management systems have been put in place by the World Bank. A minimum of two on-site fiduciary implementation support missions are conducted per year, in addition to desk reviews of Interim Financial Reports (IFRs), annual work programmes and budgets, and audit reports. Given that the procurement risk is high, Bank staff are carrying out both prior reviews and post reviews of procurement actions at least for the first 18 months of the project. / There has been no indication of any financial loss within the Project from fraud or corruption. Nevertheless DFID DRC should satisfy itself that the World Bank is adhering to the above provisions, including obtaining copies of the reports of fiduciary implementation support missions etc. / 4.4 Climate and Environment Risk / Industrial and artisanal mining has caused severe environmental degradation in DRC and a legacy of abandoned, un-restored sites, seriously eroded surfaces and contaminated watersheds. There are also challenges to the conservation of primary tropical forest and critically endangered/threatened wildlife species both from authorized mining and especially illegal mining in gazetted areas. Artisanal and small-scale mining is also the cause of very serious health impacts, which only serve to aggravate the environmental drivers of poverty. / These hazards and risks are well known and most can be managed and mitigated. DRC’s Mining Code requires the use of conventional environmental instruments (EIA, MRP and EMPP) and compliance with international codes of best practice, but in reality they are hard to apply and enforce as environmental governance is weak at all devolved levels and the artisanal sector works outside any regulatory framework. / Technical assistance provided by PROMINES to the mining sector will strengthen institutions, environmental legislation and regulatory processes and promote new, friendlier, mining technologies as appropriate. The Project is in the process of procuring a Strategic Environment and Social Assessment (SESA) to identify the environmental and social impacts related to mining growth from which new legislation and regulatory instruments will be drafted as necessary. / PROMINES is an enabling Project, creating a climate for investment and growth in the mining sector while formulating a basis for strong environmental governance. As such it has no direct impact on the environment but technical assistance work facilitating mining development raises the prospect of indirect environmental impacts – the outcome is only one step removed. Improved governance coupled with effective enforcement of codes of practice can overturn the exploitation of weak policy and legislation by corrupt officials and colluding investors and reduce the worst aspects of mining impacts on the environment. Providing technical assistance to artisanal mining will raise awareness of appropriate, less polluting technologies and help to reduce the long-term ecological impacts that are intrinsic drivers of poverty. / DFID’s June 2012 Climate and Environment Strategic Programme Review of its own portfolio took a fresh look at the risks and opportunities presented by ProMines, and made the following recommendations which will be communicated to the agency conducting the ProMines SESA: / Ensure that opportunities as well as risks are addressed in the SESA / Explore opportunities for energy efficiency with the large mining companies / Consider surface and ground water management in mining areas. This could be a potential source of conflict especially in Katanga which is likely to get drier / Ecosystem services being destroyed by artisanal miners could impact on livelihoods and climate change will exacerbate stresses on livelihoods so consider incorporating land reclamation component / Engage with civil society (especially those engaged with Kimberly process) with potential for advocacy on environmental and climate change issues in the mining sector / Consider opportunities to use mass media in the programme to change perceptions and practices of artisanal miners with regard to environmental management / Provide support to any national land use mapping exercise as a contribution to climate change policy and natural resource management planning / Ensure that Technical Assistance for institutional development of the Mining Environmental Protection Unit, SAESSCAM and the Ministry of Mines itself includes climate and environment policy and planning / Explore the extent to which the restriction of access to natural resources (including artisanal mining) on industrial mining concessions could be a driver of conflict.

5. Value for Money
5.1 Performance on VfM measures / The principal Value for Money measure in the Economic Appraisal is that Project expenditure of approximately $90 million in net present value (NPV) terms ($95 million in current prices) could help leverage additional gross revenues to the sector with an NPV of $8.1 billion, creating additional fiscal receipts with an NPV of $2.8 billion and in turn leveraging additional poverty spending with an NPV of $362 million. It is not appropriate to treat this as a benefit:cost ratio, as many other factors and inputs contribute to the economic benefits, but the balance is very positive. / Taking the outcome indicator “Revenues from the mining sector collected at export point” as a proxy for the expected increases in total revenues, the result of $101 million for calendar year 2011 has met the milestone for 2010/11 ($100 million) but not that for 2011/12. Although the Project was not formally operational for most of 2011, the increase in revenues could be attributed at least in part to efforts around EITI by the World Bank, DFID and other donors during its preparation phase. / It would have been very surprising if revenues had reached the 2011/12 milestone with project activities at such an early stage, but the result suggests that the assumptions about the potential for increasing revenue through improved systems etc are realistic. There is therefore currently no reason for concern over the Project on Value for Money grounds. / 5.2 Commercial Improvement and Value for Money / World Bank procurement guidelines are applied throughout the Project, with a high level of oversight. Although at least some of the delays may be attributable to this level of oversight, this is part of the price to be paid to operate in a high fiduciary risk environment. One area that tends to be less subject to market price competition is the staffing of the Project Implementation Unit. However, the Bank has recently made significant efforts to reduce these costs, both by eliminating one post that it saw as redundant and by reducing salaries. / 5.3 Role of project partners / There was a very close and fruitful partnership between DFID and the World Bank during the preparation phase of the Project. During this period the TTL, although Washington-based, worked almost full-time on ProMines. The individual concerned retired shortly after effectiveness. As noted in Section 4.2 and the comments on Output 5 above, the quantum and profile of Bank staff time subsequently devoted to the Project has been inadequate to maintain the expected rate of progress and to fulfil the Bank’s donor leadership role in the sector. / Collaboration during joint supervision missions has been good, with DFID having the opportunity to participate fully, including inputting to the draft Aide Memoire. Missions would, however, be more effective if they were conducted to pre-agreed Terms of Reference. / Biannual monitoring reports have not so far been seen by DFID. It is possible that none have been produced because the Project M&E system is not yet operational, but that in itself reflects an unsatisfactory lack of priority given to M&E. / 5.4 Does the project still represent Value for Money : Y / Assuming that measures are taken to bring delivery of the outputs back on track, there is no reason to doubt the Project’s Value for Money. / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The Project is currently off track and scores C at both the output and outcome level (substantially did not meet expectation). Some, but by no means all, of the deficiency arises from the fact that the results milestones for all indicators within the logframe were set in expectation that the Project would become effective in September 2010, whereas actual effectiveness was in October 2011. / The World Bank should be requested to propose a plan of action to rectify the situation. This should include, but not be limited to the following points discussed in more detail elsewhere in this Review: / The World Bank should increase its staff resources in DRC for both Project supervision and its donor leadership role in the sector. The TTL agreed, during the June/July supervision mission, to respond by September with the Bank’s proposals for addressing this issue / Both the Project and the World Bank need to give much higher priority to M&E. The lack of reliable indicator baselines or progress monitoring almost a year into implementation is unsatisfactory / The World Bank should ensure that DFID funds are drawn down in a timely manner from the single donor trust fund, in proportion to DFID’s share of the overall funding. Hitherto the Bank appears to have borne all costs from its own resources. / Supervision missions should be conducted to pre-agreed Terms of Reference. / The following strategic actions are also required by DFID: / DFID should be more active in its support for the IMF conditions on transparency and for the Economic Governance Matrix, including at the Executive Director level. / DFID should find ways of collaborating with international advocacy NGOs in support of common objectives of transparency and accountability. / DFID should satisfy itself that the World Bank is adhering to the provisions of the PAD in regard to financial and procurement management and progress, including obtaining copies of fiduciary implementation support mission and biannual monitoring reports etc. / The Review also makes a number of programme recommendations as follows: / The milestones for all logframe indicators should be reviewed, as they were set expecting that the Project would become effective 13 months earlier than was the case / A further logframe indicator is needed to reflect the specific support the Project is providing for revision of the 2002 Mining Code / High priority should be given to the development of a communications strategy and associated tools. The Accountability Platform would be one such tool, and warrants explicit mention amongst the milestones / Restructuring and capacity building of sector organisations should be based upon the findings of the full institutional audit / Plans for SAESSCAM need to be closely integrated with activities under Output 3 on capacity and accountability in tax collection / The Project should give all possible assistance to DRC’s achievement of EITI compliant status, to compensate for delays in the MDTF / Taxation analysis and modelling should be provided for the consultations around revision of the Mining Code / DFID DRC should engage with the SESA, to feed in recommendations developed during its recent Climate and Environment Strategic Programme Review / The milestones for the second indicator of Output 4 should make more specific reference to the certification and traceability work / All activities related to artisanal mining should be guided by an action plan, as envisaged in the logframe / The Katanga Extractive Industries Development Initiative (KEIDI) would make a useful and innovative contribution under Output 4 / A further indicator is needed under Output 4 to reflect Project activities towards elimination of the worst forms of exploitation of women and children in the sector / The risk rating for Output 4 should be changed from Medium to High, in view of the deterioration in the security situation particularly in the Kivus

8. Review Process
This Review was originally intended to draw upon the findings of the 24 June to 7 July joint supervision mission. However, the mission did not include an assessment of progress against the logframe. The Review was therefore conducted by the DFID DRC Wealth Creation Team, drawing on data provided by the Project Implementation Unit.