Type of Review: 3rd Annual Review

Project Title: Punjab Economic Opportunities Programme (PEOP)

Review Dates: July 1 – 5, 2013

Summary

The PEOP constitutes the skills development component, being implemented by the Punjab Skills Development Fund (PSDF). The Fund has delivered well on all of the outputs related to it. Over 30,000 poor and vulnerable have been trained as of June end, 2013, and private skill providers have been mobilized. The Fund has upgraded its institutional capacity and systems for improved monitoring, reporting, financial controls and management of complaints. Initial graduates’ trackers show increase in labour force participation of women by 10-30%%, that on average 56% graduates are employed and a 12% increase in incomes of men.

The TA being managed by DFID is delivering RCT based evaluation, building the capacity of the PSDF to deliver the Programme and help rationalize the skills policy and regulatory environment in Punjab. A series of external review and audits were conducted during the past year, in order to help build the Fund’s institutional capacity for expanding across Punjab. The recommendations of the last review have been met satisfactorily while the recommendations of the current review have been agreed under an action plan to be implemented by the Fund over the coming year.

Initial achievements of PSDF have won high political support and good market reputation. These factors have created space for DFID/PSDF to help rationalize the skills policy and regulatory environment not only at a provincial but the federal level too. Additionally, based on learning gained through the Fund, DFID is initiating design work to prepare a Business Case for expanding its investments in Skills Sector within and beyond Punjab. PEOP will be merged into the new Programme which is expected to be operational early 2015.

Overall scores
2012-13: A
2011-12: A
2010-11: 3

What support is the UK providing?
The UK/DFID is providing £25 million to the Punjab Economic Opportunities Programme (PEOP) to increase incomes of poor and vulnerable people by developing their skills and enhancing commercial opportunities available to them. PEOP is being implemented through the Punjab Skills Development Fund (PSDF), in four of the top ten poorest districts of the Punjab i.e. Bahawalpur, Bahawalnagar, Lodhran and Muzaffargarh. Over the coming months PSDF will expand its activities to a further 10 districts in Central Punjab. / The Government of the Punjab (GoPb) is matching DFID’s support by providing £25 million out of its own resources. In addition, DFID is providing £5 million as Technical Assistance (TA) to help build the implementation capacity of the partners, conduct monitoring and evaluation and rationalize the policy and regulatory environment governing skills. The total Programme value is £55 million.

What are the expected results?
At an overarching level, PEOP aims to help reduce poverty in selected districts in Punjab. It will do so by providing technical, vocational and other job relevant training to 80,000 poor and vulnerable people in Southern Punjab and to a further 55,000 in central Punjab. At least 40% of the total trained will be women. The training will help beneficiaries become more actively engaged in productive economic activities, help increase their earnings, and improve their well-being and sense of connectedness with the state / On the basis of the operational experience of and results achieved, the Programme will also aim to create a more conducive policy and regulatory environment for skills development and training. This will help to develop cost effective and market oriented solutions to address the skills gap and increase outreach of skill development opportunities for the poor and vulnerable men and women. / The Programme supports baseline household surveys and skills and livestock and dairy development surveys to fill the information gap at the districts level and help conduct a Randomized Control Trials (RCT) evaluation of the Programme. The surveys and the evaluation strategy are also enabling PSDF to design skill schemes that are relevant for market needs and people’s aspirations.

What is the context in which UK support is provided?
Punjab’s poverty analysis shows access to remittance income, irrigated land, ownership of livestock, and human capital attainment as the major drivers out of poverty for a household[1] . While employment is diversifying out of agriculture, Punjab’s growth rate has lagged behind that of Pakistan. Between 2006 -11, Punjab’s Gross Regional Product grew at 2.5% compared to the national GDP growth rate of 3.4%[2]. Numerous surveys of the private sector identify the lack of appropriate skills of workers as a significant constraint to improving competitiveness and business growth. / Meanwhile, for the over 1 million youth entering the job market each year, opportunities for acquiring vocational skills exist for less than 26%. The GoPb currently spends about Rs.7.5 billion annually through the Technical Education and Vocational Training Authority (TEVTA) which is the largest public training provider (over 300 training institutes) and also the provincial regulator of skills. The duplicity of functions has created conflicts of interest and together with weak management has contributed to undermining its performance. For example, TEVTA controls the testing body (Punjab Board for Technical Education). In addition, registration of new private providers requires cumbersome requirements and limited facilitation from TEVTA. It employs close to 10,000 permanent and contractual employees and trains 71,446 individuals annually. However, not only is the quality of training variable, TEVTA has limited capacity to guide skills research and develop a flexible training system responsive to province’s needs. / Post 18th Amendment with more devolution of power to the provinces, there are no clear provincial and federal skills policy and regulatory mandates. NAVTTC the apex body for skills regulation at the federal level is weak and has had an insignificant role in developing the sector. / In relative terms, poverty (calculated using the Poverty Head Count Rate) is an entrenched phenomenon in the south Punjab where district level HCR ranges from 31% to 59%[3]. The four PEOP districts have an average HCR of 53% (which translates into around 5 million people living below the poverty line). The importance, therefore, of finding job opportunities outside the region or starting own business, is greater in the South. Moreover, in South Punjab, in particular, extreme poverty and a historical presence of radical organisations (amongst others) have resulted in increased militancy among the poor youth[4]. Access to market oriented vocational skills can help halt this trend by opening up constructive opportunities for the poor youth. / Originally, the Programme had two components. In addition to PSDF, the second component focused on Livestock and dairy development (L&DD) in a partnership with the Livestock and Dairy Development Department of the GoPb. DFID had originally committed £12.5 million to each component with GoPb matching DFID funds. / Due to consistent poor performance of the L&DD component however, DFID and GoPb agreed at the last annual review (July 2012) to (i) discontinue with the livestock component/programme, (ii) transfer assets to PSDF and (iii) reassign unspent and uncommitted L&DD funds to PSDF. This has increased the funds allocated to the Skills component to £49.26 million (taking into account the £0.37 million already spent by L&DD). Consequently the target number of people to be trained has also increased from 80,000 to 135,000 (40% women) to be accomplished by December 31, 2015. / To accommodate the extra funding and revised targets DFID and GoPb have agreed to expand the activities of PSDF to 10 additional districts in central Punjab. This responds to a direct request by the Chief Minister to consider expanding the operations of PSDF across the entire province. More importantly, it allows PSDF to test its model in districts which not only have larger numbers of absolute poor, but also have a much more robust economic base and thus a greater demand for skilled and semi-skilled labour. The six new districts where PSDF will start operations in 2013-14 (Chiniot, Faisalabad, Gujranwala, Lahore, Sargodha and Sheikhupura) which collectively are home to around 8 million poor. / Other Donors in Skills: / Currently, DFID is a major player in the skills sector due to the successful experience of PSDF. The World Bank (WB) is planning a $50 million investment in the sector, the design of which is currently under consideration though its focus will be predominantly on TEVTA Punjab. USAID is planning to initiate a workforce development programme with elements such as trainer grants, scholarships, apprenticeships, post-training support and institutional capacity building in south Punjab. GIZ and EU have a TEVT sector reform programme at the federal level with the National Vocational and Technical Training Commission (NAVTTC) which is a comprehensive programme focusing more on developing the TEVT infrastructures i.e. skills standards, revision of curricula, teachers training, and development of a National Qualification Framework (NQF) rather than making systemic changes in the sector. In response to the opportunities provided by these potential investments, DFID is liaising proactively with the WB, USAID and GIZ/EU so that their programmes can be shaped by the practical experience of PSDF, funds are not invested cross purpose to each other and few pilot collaborations are launched to inform the larger skills strategy for the province. For example, coordination with the WB and International Finance Cooperation (IFC) is underway to pilot test a few TEVTA institutions to be run on PPP basis.
[1] Ali Cheema and Lyla Khalid; The Geography of Poverty in Punjab.
[2] The State of the Economy: The Punjab Story (2012): Fifth Annual Report by the Institute of Public Policy, Lahore
[3] Calculated using data from MICS 2003-04 and Ali Cheema and Lyla Khalid; The Geography of Poverty In Punjab.
[4] Terror’s Training Ground; Ayesha Siddiqa (2009); Newsline Pakistan issue of 9th September, 2009; accessed on 13th August, 2012; 2. From FATA to South Punjab – The Looming Leap of Islamic Radicalism in Pakistan; P. K. Upadhyay; Institute for Defense Studies and Analyses; 2009. 3       Pakistan’s New Generation of Terrorists; Jayshree Bajoria; Backgrounder prepared by Council on Foreign Relations, USA; 2011

## Section A: Detailed Output Scoring

Output 1: Sustainable model for funding competitive training delivery
Output 1: Score and Performance Description / Indicator: Level of Maturity of PSDF as an innovative model for skills financing / Baseline: Prior to PSDF no such skills funding agency existed. / Milestone (2012-13): PSDF Model refined for target population (use of research to design 2nd Generation Products).
Progress against expected results: A+ Output moderately exceeded expectations. / The project team, in consultation with the implementing partners should consider revising the indicator and milestone as on their own, they do not allow for progress in this area to be fully captured. / The Punjab Skills Development Fund (PSDF) was set up in 2011 as a Section 42 not-for-profit company registered under the Companies Ordinance 1984. The company has a competitively hired private sector management and a multidisciplinary independent Board of Directors (Board) also lead by the private sector. A Programme Coordination Unit (PCU) based at the Planning and Development Department (P&DD) liaisons between the sponsors and the implementing units for smooth operations of the Programme. An overarching Programme Steering Committee with representation of the sponsors and policy experts is providing overall policy and facilitative support to the Programme. / PSDF aims to increase and strengthen delivery of market oriented skills by private sector providers. To do so it has established a mechanism under which grants to training providers can be provided on a competitive basis. Since inception PSDF has developed and refined, 5 distinct training products. / First Generation (2011- 2013) / Skills for Employability (SFE): a very generalised and did not take into consideration urban/rural divide, literacy levels, social issues or demand for trades. / Skills for Model Villages (SfMV): a generalised one-off initiative implemented in the flood hit district of Muzaffargarh for assisting the affected population. / Second Generation (2012 – present with additional rounds planned over 2013-14): / Skills for Jobs (SFJ): Targeted at urban men with some basic levels of education and focuses on mainstream trades needed in the market such as, driving, welding, cooking etc. The training is certified either by the Punjab Board of Technical Education (PBTE) or an accredited international/national awarding body (such as Ed Excel, The London Chamber of Commerce or City and Guilds). / Skills for Markets (SFM): Targeting women in rural areas with limited education and mobility. Training includes small scale dairy farming, home decoration, producing garments and handbags, hairdressing, and beautician. / Third Generation (2013 – present) / Skills for Farms (SFF): Providing training in the agri-livestock sectors, the main economic activity in South Punjab in such trades as artificial insemination, drip irrigation. / The second and third generation products have been developed by explicitly building on the learning from the first generation skill schemes, and evidence generated from the household skills survey, employers survey and interactions with the business people. / For example, experience from SFE revealed that in order to achieve a higher probability of successful course completion, skill providers (TSPs) preferred enrolling students education levels that were higher than the basic primary level. The household survey showed that a minimum requirement of primary education will exclude 80% women. / Women’s mobility also emerged as a major issue in women’s uptake of training in the voucher roll out experiment conducted as part of the programme evaluation. In addition the Employers Survey underlined the difficulty in connecting women with formal employers and a stark bias against hiring women. Only 8.6 of the multiple worker firms employed women even though women made up 13.5% of the total employed labour force. / As a result the SFM training product was designed specifically to address these challenges. The training is now provided within the village/community so that women are not constrained by mobility issues and are easily able to attend. The focus is on trades popularly demanded by women such as embroidery, tailoring and home decorations. SFM also includes literacy, numeracy and entrepreneurial modules, as evidence suggests the need for these components in order to enable women to take full advantage of the skill training and run their out-of-home business. Interactions with beneficiaries reveal employment opportunities for women in non-traditional jobs such as graphic designing, secretarial services and salesperson (in the pharmaceutical sector). Efforts should be made to explore new opportunities for women and in all skill scheme adverts women should be explicitly encouraged to apply. / Likewise, the SFJ scheme was developed to enhance the employment prospects of the trainees. Building on the employers’ survey, it identified specific trades that were suffering from skills shortages and provided access to local and international certification schemes to trainees. The later it was found, would give trainees a distinct competitive advantage in securing employment as it would provide employers with more security on qualifications but also potentially open up international employment opportunities for the trainees. With regards to cost, SFJ has used the experience of SFE to define specific cost ranges for each trade individually rather than lump them all together in one generalised group as had been the case previously. This allows for not only much better planning, forecasting and budgeting of operations but also gives PSDF to negotiate more effectively with TSPs to keep costs to a minimum. / Product sophistication has increased from SFE to the first and then second round of SFJ. The latter schemes gradually added new components allowing training service providers adjust to new requirements over time. SFJ (2012-13) included accreditation certification as an essential component. SFJ (2013-14) requires compulsory on-the-job-training for trainees thus stimulating linkages between training providers and employers. By the third quarter of 2012-13, PSDF has completed two rounds of product revisions based on evidence. Its product portfolio has expanded with three schemes on offer instead of two envisioned at the onset of the year. PSDF invited proposals for third generation schemes: SFJ (2013-14); SFM (2013-14) and SFF (2013-14). All three schemes are guided by evidence from CERP Employers Survey (first draft available in March 2013) and the operational data. / In 2011-12, 47 contracts were signed and managed to deliver SFJ and SFM, representing a 50% increase on the previous period. As of June, 2013 end, 10,669 people have been trained under SFJ while 3,377 women have been trained under SFM. First generation, SFE scheme (6,006 trained in 2012/13) also continued during the first half of 2012-13. / A number of additional initiatives and activities over the past 12 months have contributed to establishing the credibility of PSDF as an influential player in the Punjab skills development sector and strengthening its institutional and operational capacity. / Partnership with the Punjab Board of Technical Education (PBTE): PSDF has signed an output based agreement with PBTE, which will enable PSDF get certification for its trainees while building latter’s capacity to carry out large scale trade tests independently of TEVTA and offer testing services on a commercial basis. Of the total people to be trained under SfJ, until June, 2013, PBTE had tested 5,965 (56% of the SFJ target). / Increasing scale of international certification: PSDF has expanded trainees’ job mobility prospects by commissioning providers offering internationally accepted certification. More than 10% of the training places (6 providers) are offering international qualifications under SFJ 2012/13 and students will be tested by City and Guilds, Ed Excel and London Chamber. In comparison, under Skills for Employability only one provider offered international certification. / Engaging a Third Party Monitor of International Repute: Ernst and Young, was selected as a Third Party Monitor for the year 2012-13 through open competition. The firm set up offices in Southern Punjab, reviewed PSDF’s monitoring tools and developed new reporting formats. The current system of reporting and monitoring has now been fielded for more than a year with tangible evidence on improvement in observable parameters such as trainer and trainee attendance, availability of consumables and training supplies. PSDF implements an innovative monitoring model that can be emulated by other public, donor-funded and private sector training providers to improve efficiency. / Strengthening graduates market links: During 2012-13 there has been a major shift from training uptake to labour market performance of trainees. Overall, training providers report that 56% of the students are employed. PSDF is considering a sample-based tracer for validation of the findings. After considering different placement models, the Board of Directors has recommended an indirect approach to trainees’ placement without being involved in employment guarantees which are governed by labour contracts, sector practices and other labour laws. Following steps are being planned to improve employment outcomes: / PSDF will be actively sharing its trainee database with job portals. A pilot agreement with “Kamatapakistan” was signed in June, 2013. Other similar agreements are expected to follow. / The Board has approved additional positions for a Placement Cell to be housed within PSDF. The cell will offer matchmaking services to employers by recommending suitable trainees and tracking progress of institutional arrangements for placement. / Compulsory on-the-job training has been included in the contracts with the TSPs. / PSDF Institutional Strengthening Measures: Including the current Annual Review a number of additional reviews and audits were conducted over the past 12 months including: / Peer review of PSDF scale up strategy (by DFID funded Employment Fund in Nepal) / Annual statement of progress (ASP) / Institutional and operational audit / Annual Audit commissioned by the PSDF Board / Annual Audit by Accountant General of Punjab / Asset Audit / The reviews conducted, more than would be usual under normal circumstances, were due to a combination of those which were (i) mandatory requirements for all DFID/GoPB programmes (i.e. ASP, GoPB Ag Audit), (ii) required as a result of the closure of the Livestock component (i.e asset transfer and audit), and (iii) discretionary, but forward looking with a view to better positioning PSDF in anticipation of scaling-up its activities across Punjab. These reviews/audits have placed a heavy burden on the PSDF programme team and the DFID team. Going forward DFID and PSDF should work together to try and better rationalise the timing and efforts required to comply with required safeguards. / Key recommendations focused around the automation and centralisation of procurement systems and internalising selected audit functions. Many actions have already been taken as a result and others are in the pipeline. A time-bound action plan to address the outstanding issues is being developed together with PSDF. / Board of Directors: The Board has been meeting on a quarterly basis and providing effective leadership for the programme. Board members are very capable and demonstrate a high level of commitment to, and ownership of the programme. Since October 2012, DFID has been attending the meetings in an ex-officio and advisory capacity. 3 positions on the Board have been vacant for some time, but despite repeated efforts, the Government has yet to make any new appointments. As a result some of the sub-committees (i.e. finance & technical committees) have not been able to constitute a quorum and this has delayed some decision making. / Complaint remedial system: Individual complaint management has been outsourced by setting up a toll-free number. Complaints are forwarded to the Monitoring Department which investigates and recommends remedial action. The frequency of 7-8 daily complaints is within an acceptable range given that this number represents less than 0.1% of total enrolled trainees at any one a time[5]. Additionally, complaints/queries are often made by TSPs who do not qualify for grants. A central Complaint Handling Cell, under the supervision of CEO could add further efficiency to the system by efficient tracking and follow up. / Prospects of Long Term Sustainability of PSDF: PSDF has won high political level commitment. The Chief Minister Punjab has frequently praised PSDF in public, is keen for its province wide expansion and has committed to matching funding by DFID for its expansion. This political buy-in and the engagements planned with industry in future, auger well for long term sustainability of PSDF. PSDF can potentially become the sole window for all public funds spend on training in the province. Other donors keen to sponsor training can also work through PSDF. PSDF is planning to pilot employer led schemes which is a step towards involving industry in paying for training sponsored by PSDF. Thus, beyond tapping corporate social responsibility funds, PSDF can potentially become a public-private partnership vehicle for managing the needs of trained workforce for the corporate sector players. Lastly, PSDF must also explore sources of continued and assured fund such as the Federal Workers’ Welfare Fund. / Communications: PSDF produces a quarterly newsletter, featuring human interest stories, and highlight its activities, successes and making other official announcements. It also manages an active website and has held several outreach activities (such as participation at trade & employment fairs) over the past 12 months. These have helped to enhance its visibility and build a strong brand for the organisation. / Recommendations: / Revise the indicator and milestones for this output. The revised indicator and milestones should enable to more adequately capture the full scale of progress achieved by PSDF towards becoming a mature innovative skills financing model. / Continue to refine and expand the current PSDF product offer (PSDF). There is a need to offer an entrepreneurship training module as an option available to all successful candidates of SFJ and SFF, given that the Employers Survey shows that 80% of employers employed only 2-3 staff in the last one year and have no substantial hiring plans. Linkages with the microfinance providers also need to be strengthened to enable eligible students avail financial facilities for setting up their own business. Training providers offering on-the-job training should explore mentoring and also be required to invite visiting faculty from the industry and successful established entrepreneurs to deliver inspirational lectures on their experiences, emphasising challenges and their surviving strategies. These actions will help improve linkages with the industry and exposure of students work to potential employers. Similarly, on a regular basis, PSDF should organize exposure visits of established Pakistan brand owners to the PEOP districts to enable them gain direct access to the workforce being developed and the quality of its work. / Continue and enhance its partnership with CERP or other research organisations (PSDF/CERP). Evidence is needed to further refine and expand the PSDF product offer especially with regards to women and to strengthen market linkages. The partnership with CERP should continue to test variations under SFM but the focus should shift from uptake to post-training success. Discussions to this effect are on-going. / Develop and implement an Action Plan to implement various audit/review recommendations (PSDF). Internal controls need to be strengthened to support the scale up of PSDF across Punjab. The ASP, Audit and Operations and Institutional Assessment/Due Diligence recommendations need to be implemented following the action plan agreed with the PSDF. These actions will further strengthen PSDF’s operational capacity and reduce risks. / Develop a comprehensive communications strategy (PSDF). There is a need to prepare a comprehensive communications strategy that identifies various constituencies of the Fund and has clearly thought out action plan of how to reach each, while also show casing PSDF’s work to existing and potential stakeholders. The strategy should identify the activities that need to undertake toward different ends. For example, road shows among the corporate sector for raising awareness about the Fund and mobilizing funding support for it, and preparing case studies of students following nonconventional careers and businesses. PSDF can better leverage its accomplishments, enhance its visibility and make inroads among new stakeholders through a comprehensive communications strategy. The strategy can also serve as a tool for linking students with potential employers, creating awareness about skills needed in the market and increase communities acceptance and support for working women. PSDF should develop a strategy and an action plan for achieving institutional sustainability which enables PSDF have permanent flow of funds from various stakeholders. Given that it is still early days for PSDF, the strategy should have short, medium and long term horizons. / Impact Weighting (%): 20% / Revised since last Annual Review? Yes / Risk: Medium / Revised since last Annual Review? No
[5] On average, there have been 7564 trainees enrolled with TSP during a month. The figure has been calculated from reported enrolments from June 2012 to May 2013.

Output 2: Skilled Trainees – Number of people trained by PSDF in PEOP districts
Output 2: Score and Performance description / Indicator: Number of individuals trained by PSDF in PEOP districts / Baseline: 0 / Milestone (2012-13): 20,000 trained (40% women) / Progress against expected results: A. Output met expectations. / Total trainees (completed) over the past 12 months (as of June 2013) are 20,410 of which 40.3% were women. This covers four PSDF schemes, namely (i) Model Villages Programme, (ii) Skills for Employability, (iii) Skills for Jobs and (iii) Skills for Markets schemes (details below): / Name of Scheme Number of Completed Trainees Gender Breakup of Completed Trainees Percentage / FY 2011-12 FY 2012-13 Total %age Male Female Male Female / Model Villages Project (MfVP) 651 - 651 2% 442 209 68% 32% / Skills for Employability (SFE) 9,459 5,978 15,437 51% 8,014 7,423 52% 48% / Skills for Jobs (SFJ) - 11,080 11,080 36% 8,623 2,457 78% 22% / Skills for Market (SFM) - 3,352 3,352 11% 1,123 2,226 34% 66% / Total 10,110 20,410 30,520 100% 18,202 12,315 60% 40%
As of June end, 2013, a total of 30,520 individuals have completed their trainings since inception as against a target of 30,000. A further 6,853 are currently enrolled[6] and are expected to graduate within the next few months. Over the next reporting year a total of 37,000 will be trained. It is expected that 5000 of these will be in new districts. In addition, the Veterinary Assistant Scholarship Scheme (VASS), the only on-going activity of the now closed L&DD component is supporting 170 students to complete their diplomas by June 2014. / The monitoring system is now also capturing quality aspects beyond merely recording the number of individuals trained. Going forward, all SFJ trainees will appear for accredited trade tests, a quality benchmark of 80% trainees qualifying the tests has been set and providers face penalties for falling short of this requirement. / During 2012-13, 4,383 trainees (20%) appeared in a trade test held by the Punjab Board of Technical Education achieving an average pass rate of 88%. The pass percentage has improved over time for the 3 month trainings, from 80% (December 2012) to 92% (March 2013). With the exception of just two providers, this signals a qualitative improvement in training by providers as the improvement is not just isolated to a just a few (more capable) providers. / Figure1: Pass Percentage by Provider under the SFJ Scheme / The impact of training on the incomes and lives of the graduates is also a measure of training quality. Voucher roll out experiments are underway to create a robust sample size for RCT evaluation of skills. Meanwhile, initial results show an increase in incomes of men by 12% and 10-30% increase in the Labour Force Participation of women. Skill providers report that on average 57% graduates are employed. PSDF is planning trackers for independent verification of employment rates. / Other key findings include: / Quality of training materials remains an issue: Even though courses and curricula have been standardised to a large extent under the SFJ scheme, absence of quality training and learning resources remained an issue. Only forty or so manuals (containing lesson plans) exist for more than 100 regular TEVTA courses. Past engagement with TEVTA and NAVTTC (the national regulatory body) on the matter has not produced significant results over the last one year. / MIS for monitoring TSP’s contract compliance and quality: A TA-financed customised MIS system was installed and is currently being pilot tested. A wide variety of reports can be generated using the web-enabled system which will reduce the data collection lags by PSDF while reporting to its sponsors and meeting its own report needs. For example, reports can be generated at the provider, course and trainee levels. The system is being regularly updated and a second Data Entry Unit is being set up in Lahore, in addition to the one in Bahawalpur. / Standardisation of courses under Skills for Farms: The Fund plans to train 10,000 individuals under Skills for Farms Scheme which was to commence in May, 2013. Approximately 2,500 of the trainees were expected to complete their trainings by end June, 2013. However, training has been delayed due to lack of standardized courses. The Board has suggested that in the absence of accredited agriculture and livestock courses, recognised universities will act as certifying agencies with control over curricula and content. The scheme is being launched after consultation with the Livestock Department. / Overall, PSDF scores better on delivery and relevance than quality of training. Its efforts to support third party testing and certifications are commendable but rely for majority of the training places, on inputs (standards, training manuals, teachers training etc) which urgently need review and are currently beyond PSDF’s immediate mandate. / Recommendations: / Aggressively lobby for revision and development of training and learning resources by TEVTA/NAVTTC within a given timeframe (DFID/PSDF) and draw on the TVET Reform Programme and ensure that private sector is a key feature of all of its initiatives. To overcome the objections raised on Skills for Farms Scheme, it is suggested that PSDF should request the NAVTTC and TEVTA (Punjab) to recommend new courses in the agriculture and livestock sectors. In the meantime, course durations may be rationalised in consultation with the qualifying training service providers. Similarly, under the TVET Reform Programme training should also be provided for private skill providers rather than only the public skill providers as is being done presently. PSDF may offer to use its leverage with the private sector to ensure its involvement. At the provincial level, competency based manuals being developed under the TVET Reform Programme should be piloted/applied for PSDF sponsored training. / PSDF should also test remote access facility to the MIS by the providers who should update their monthly reports in real time. / A dedicated Complaints Cell should be set up during 2013-14 in preparation for the proposed scale (PSDF). This will help address grievances in an organized manner and more importantly feed into the design of the programme. / The performance of the Placement Cell being established during 2013-14 should be measured against delivery of targets. / Impact Weighting (%): 50% / Revised since last Annual Review? Yes / Risk: Medium / Revised since last Annual Review? No
[6] PSDF Monthly Report for May, 2013.

Output 3: Private training places mobilised
Output 3: Score and performance description: / Indicator: Percentage of private sector places created as a result of PSDF funding. / Baseline: 0 (as PSDF was established under PEOP). / Milestone (2012-13): 70% of total PSDF training places were in the non-state sector
Progress against expected results: A+. Output moderately exceeded expectations. / 91% of the new training places created under the SFJ scheme in 2012-13 were in the private sector i.e. not-for-profits, private colleges, higher educational institutes and public-private partnerships. TEVTA and PVTC delivered only 9% of the scheme. No public provider was contracted under SFM. 86% of the total non-state training providers was delivered by not-for-profits and only 14% was delivered by a private companies. Cumulatively, only 7% of the new training places were offered by public providers and 13% by private companies. / Given the high uptake and involvement of not for profit training providers the DFID and PSDF might consider revising the indicator and milestone to focus either on promoting an appropriate mix of providers and/or for profit making private companies. Especially as the later were non-existent in the south of Punjab prior to DFIDs intervention and changing this dynamic was a key objective of PSDF at the outset. / Figure 2: Mix of Providers Engaged by PSDF Since its Start / The share of public sector fell from 23% to a mere 7% between 2011-12 and 2012-13 as TEVTA headquarters failed to submit a proposal although two of its individual institutes won bids and signed contracts with PSDF, independently. / At the provincial level, there has been a 27% increase in the number of private registered technical and vocational institutes between 2010 and 2013 (Source: Punjab Board of Technical Education). These include technical colleges, and computer, special education and vocational institutes. Excluding technical colleges, the number of registrations has risen by 52%. While this cannot be directly attributed to PSDF, it is very likely it has had some impact on these numbers. PSDF’s operational evidence indicates that local NGOs have expanded their outreach reach and capacity for vocational training, in the South of Punjab. / PSDF has introduced an upper limit of 1,000 trainees per contract[7]. The aim is to encourage a greater number of small and medium providers and prevent large providers from overstretching themselves as they were providing very ambitious proposals. Most classroom suspensions (under the monitoring system) occurred in cases of large and medium sized providers indicating issues in managing large contracts. Evidence from DFID funded Employment Fund in Nepal suggests that taking a small provider from a small scale to a reasonable capacity takes at least 2-3 years[8]. Seen in this perspective, the new policy appears to be justified yet must be reviewed on an annual basis. / Recommendations: / Revise the indicator and milestone to promote a mix of for and not for profit skill providers. Given the high uptake and involvement of not-for-profit training providers the DFID and PSDF might consider revising the indicator and milestone to focus either on promoting an appropriate mix of providers and/or for profit making private companies. Especially as the later were non-existent in the south of Punjab prior to DFID’s intervention and changing this dynamic was a key objective of PSDF at the outset. / Government of the Punjab may consider a one-time moratorium on registration fee which is considered on higher side by private providers (i.e. Rs.22,000 for 3 years). With this concession NGOs can be encouraged to register as formal training institutes with TEVTA/PBTE. / Develop a mutually beneficial partnership with TEVTA to influence policy changes (PSDF). Especially in the area of development of training inputs and more cost effective delivery of training. TA money can be utilised for financing some sector development activities by TEVTA especially where it is cash-strapped and piloting public private partnership modalities for a select group of TEVTA institutes. Close coordination with World Bank is also necessary in order to inform its potential programme for TEVTA with practical experience of PSDF. / Lobby for making TEVTA institutes effective and market oriented. Individual TEVTA institutes should be formally allowed[9] to bid for PSDF funds, while maintaining safeguards against uncompetitive practices such as use of subsidies to bid down prices. / Periodic assessments of TSPs will help determine how the provider is maturing and building its capacity for larger contracts. This information will also serve as a proxy indicator of PSDF’s development impact on skill providers. / Organize TSP conferences periodically. This will help cross fertilization of ideas, mutual learning, possibilities of collaboration and improved understanding about their work environment and emerging trends among potential beneficiaries. Over a 100 TSPs ranging from small NGOs to corporate skill providers have engaged with PSDF. There is considerable variation in their know-how and implementation approach. / Impact Weighting (%): 10% / Revised since last Annual Review? Yes / Risk: Low / Revised since last Annual Review? No
[7] Under SFJ, the average contract was for 507 trainees.
[8] Peer Review of PSDF Expansion Strategy by Siroco Messerli.
[9] Since there is no clear regulatory guidance on whether individual institutes may bid or not.

Output 4: Policy and Regulatory Environment
Output 4 score and performance description / Indicator: Policy and regulatory environment support to GoPb for skills policy framework provided / Baseline: 0 (as PSDF was established under PEOP). / Milestone (2012-13): Scale up strategy for PSDF and request for technical assistance by government met.
Progress against expected results: B. Output moderately did not meet expectations. Skills development has historically not received the attention from policy makers that it should. During the past year, the sector moved up the priority list and received considerable attention from Chief Minister Punjab. This has been driven to some extent by the accomplishments of PSDF and the concerns raised by DFID/PSDF for rationalizing the skills policy and regulatory framework, although PSDF does not have any mandate in the skills policy and regulatory area. The Board had decided to steer clear of policy and regulation and focus on building PSDF’s core competencies and deliver its mandate. DFID’s TA is the main instrument for influencing policy and regulation, based on practical experience of PSDF and its recognition as one of the three main implementation agencies (TEVTA and PVTC being the other two) and a key driver of change. / 2012-13 was the election year and the government was justifiably reluctant about initiating any far reaching structural reforms. However, a number of meetings were held on skills policy and regulation, all of which PSDF attended and made contributions to in order to influence thinking on sector reforms. Key issues included the dual control of TEVTA and PBTE over private institutes, gaps in the accreditation regime proposed by the federal government and division of regulatory responsibilities between the two governments (federal and provincial). / DFID/PSDF has helped identify gaps and anomalies in the current and proposed initiatives. For example, the CEO PSDF and the Skills Advisor PEOP were actively involved in the discussions for setting up the Youth Skills Development Authority (YSDA). Inconsistencies and overlaps of the proposed authority with existing structures were pointed out and comments were provided on the draft law for YSDA. The Authority has not been established. / PSDF/DFID’s lobbying efforts have helped highlight the importance of providing the private providers a fair and conducive playing field alongside public providers. GoPb’s attention has also been drawn towards deficiencies in the skills regulatory regime such as the dual control of TEVTA and PBTE over private institutes, gaps in the accreditation regime proposed by the federal government and division of regulatory responsibilities between the federal and the provincial governments. Consequently, a key policy decision was made by the GoPb to set up a Committee to establish a regulatory framework for skills. Soon afterwards, a Federal Committee on Skills Regulation was also established by the National Vocational and Technical Training Commission (NVTTC). Punjab was represented on the Committee by the Department of Industries. / PSDF/PEOP contributed in all of the above provincial and federal committees. The following inputs were shared: / Both CEO PSDF and PEOP Skills Advisor were members of the high level Provincial Committee which reviewed the Constitutional Provisions for exercising regulatory powers in the skills sector at the provincial and federal levels and provided policy recommendations to the Chief Minister. / Based on a) above, the GoPb firmed up its negotiating position for the Federal Committee on Skills Regulation. PEOP Skills Advisor prepared a brief for the Preparatory Committee explaining the arrangement of skills regulatory functions in federal and unitary forms of government. However, the process could not be carried further due to a lack of progress at the federal level. / With four main implementing agencies (TEVTA, PSDF, Punjab Vocational Training Council and Punjab Board of Technical Education), the need for a central coordinating agency at the provincial level is evident. DFID under its TA component, continued to engage with the provincial stakeholders on this issue. Discussions with the Government have led to a request by the Industries Department to carry out an Institutional and Capacity Assessment (ICA) of itself. The ICA was deliberately delayed due to elections to ensure a buy-in from the new government and is planned to be conducted soon. The study is expected to clarify questions on institutional jurisdictions and assess the capacity of the Industries Department to play a stewardship role for the TVET[10] sector. / Recommendations: / DFID should contribute to rationalising skills policy and regulation both at the provincial and federal policy levels. Using the TA, and drawing on PSDF’s experience, the (proposed) new Business Case for expanding DFID’s investment in skills across the Punjab should take a more strategic approach to this issue. / PSDF should share its experience and views more widely. PSDF should share its experience of working in a TEVTA governed skills sector with the World Bank, in order to help shape latter’s potential skills programme in Punjab. To promote efficiency in public skills delivery, it can share its experience on institutional monitoring with TEVTA and PVTC. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? Y
[10] Technical and Vocational Education and Training

Output 5: Knowledge Management and Sharing
Output 5 score and performance description / Indicator: Publication and sharing of reports and data. / Baseline: CERP Phase One Baseline HH Survey Reports (Skills and Livestock) Produced / Milestone (2012-13): RCT Impact Evaluation Reports giving immediate outcomes (Skills and livestock) / Progress against expected results: B. Output moderately did not meet expectations. / The Centre for Economic Research Pakistan (CERP) has been contracted (under an Accountable Grant Agreement) to conduct a baseline household survey covering skills and livestock and dairy (Dec 2012), and an employers’ survey (March 2013) to inform the work of the PSDF and the livestock component. All of these reports have been completed and have been shared with DFID, the GoPb, PSDF and other donors and development organizations. / The plans to conduct a suppliers survey as part of the baseline survey was dropped as PSDF had gathered sufficient information about skill providers through its bidding process. From the funds saved, CERP conducted voucher roll outs in the SFE scheme to support an RCT assessment, which would inform a mid- term impact evaluation scheduled for 2012/13. / Unfortunately the uptake of vouchers was low (5%) and resulted in too small a sample size to be statistically significant and suitable for an impact evaluation. The experience was contradictory to the very high awareness and value for skills that had emerged in the household survey and pointed to other factors that were constraining the ability of the poor, especially women from taking advantage of opportunities. In spite of the methodological flaws, the sample showed that men had increased their incomes by 12 % as a result of the skills training that had been provided. / CERP prepared and shared a Skills Intervention Report on voucher disbursement for the SFE scheme and proposed strategies to improve uptake. As mentioned earlier, CERP and PSDF have worked closely to use this knowledge to improve access and outreach of the programme interventions - in particular, the role of stipend, distance and community mobilisation in stimulating enrolment for training and their effects have been quantified. This learning is being internalized to reassess PSDF’s outreach and redesigning the voucher roll outs. However, the RCT experiments have also highlighted the challenges in implementing this methodology as part of an on-going programme. / As a result of this learning, CERP is currently conducting a series of redesigned voucher roll-outs to help improve uptake of skills in the general population of the four PEOP districts. This will help build a mass of voucher users for end of the Programme RCT evaluation of PEOP. So far, three voucher delivery rounds have been carried out; one each for SFE, SFM and SFJ. While the uptake and retention for SfE and SfJ have not exceeded 11%, the retention of SFM was 30% in the last round. Findings from the SFM tracker have been obtained and will be shared by early Sep, 2013. An important finding of this tracker is the improvement among graduates of being connected with state as opposed to the control group.
Another SfM voucher roll out is planned in Sep, 2013 to study the impact of transport, community mobilization and stipends. Tentative plans for SFJ include a pilot voucher roll out in Jan/March, 2014 followed by voucher delivery to obtain a larger sample in June/July, 2014. / Continued low uptake of SFJ, despite increasing stipends, raises the question of how SfJ scheme can be evaluated especially since it constitutes 80% of PSDF’s training. An evaluation workshop was held in April to rethink the evaluation strategy. The workshop endorsed an encouragement design for the SFM scheme (based on voucher delivery to households) but recommended an Over-Subscription approach for SFJ. / In addition, in light of the voucher uptake experience DFID, CERP and PSDF are discussing changes in the activities and log frame targets with reference to the evaluation plan for PEOP districts and in preparation for the proposed scale-up to new districts. The later will require PSDF and DFID to agree on a robust evaluation strategy and action plan for the new districts. In the meantime, the plan is to include trackers of voucher users and additional voucher roll outs with varying levels of stipends and job placement support. / PSDF management has shared its operational difficulties with RCT experiments. It has recommended better planning to reduce the time lag between the date vouchers are received by individuals and the date the training begins. CERP is inclined to voucher based RCT due to insights that it can provide about the demand for training among the target population, particularly the poor. Other research agencies have demonstrated their interest in CERP’s work. Part of the funding for the on-going SFM RCT is contributed by the Bonn based Institute for Study of Labour (LIZA). / Recommendations: / The target dates for the Evaluation Reports should be revised (DFID/CERP/SDF). Given the difficulties in obtaining an RCT sample, a new schedule of voucher roll outs for SFM and SFJ trainees should be included in the log frame milestones. Additionally, the PEOP logical framework should be revised to reflect new dates for SFM and SFJ roll outs in 2014-15 with the target of achieving a statistically robust sample for the final evaluation. / The mid-term RCT evaluation may be dropped (DFID) in favour of repeated trackers of SFJ and SFM trainees of the samples obtained in 2013-14. This will allow for sufficient time lag for graduates to find jobs or start businesses. / An updated evaluation strategy and action plan for the new districts should be developed (PSDF/DFID). Implementation modalities, roles and responsibilities of partners involved should be clearly spelled-out in order to save time and avoid administrative bottlenecks. This should also include (i) a revised proposal covering the planned voucher roll outs (ii) a practical methodology that helps assess working with employers and addressing skills gaps in select sectors. iii) Finally, it should propose a log frame indicator to capture the outcome of the PSDF in the new districts. / Publish a paper on CERP/PSDF learning (CERP). With specific reference to SFM scheme, utilising baseline reports on households and employers and be shared with academia and development practitioners locally and abroad through a series of structured outreach events. CERP should be requested to produce/ / Impact Weighting (%): 10% / Revised since last Annual Review? Yes / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Yes / The logframe was revised in November 2012 after the closure of the Livestock Component and the decision by DFID and GoPb to approve the expansion of PSDF to the new districts from the released resources. (In early July, 2013 in a meeting with the Chief Minister Punjab, the Secretary of State committed to increase the number of districts to a total of 18 instead of 14). The impact and outcome statements remain the same. However, the meaning of “vulnerable individuals” has been broadened to include those threatened by social and gender exclusion, food insecurity, natural calamities, deprivation from basic services, extremism and environmental changes[11]. / The review resulted in change in the milestone for output 1 for the year 2013-14 and was changed to read: ‘PSDF consolidates its products and tests the model in 6 new districts’. However, the number of districts in the log frame will now be increased to a total of 18. / During the current review the impact target has been revised to 2.5% since the livestock component has been closed. The output indicators pertaining to knowledge management have also been revised, given the implications of the low uptake of vouchers on mid and final evaluation of the Programme. Additionally, an indicator for capturing the impact of the Programme in the economically robust districts will be included, based on the evaluation proposal that is due from PSDF by the end of August. / 1.2 Overall Output Score and Description: / A - Outputs met expectations. / The outputs pertaining to PSDF delivered well and have scored A and/or above. The Programme may have scored higher, however, due to the challenges associated in delivering outputs 4 and 5 related to policy and regulatory work and RCT based evaluation of skills (both outputs have scored B) the overall score is an A. / 1.3 Direct feedback from beneficiaries / Over July 1-3, 2013, the Lead Adviser, and the Programme Officer, PEOP had a series of meetings with a range of skill providers (comprising of well- established institutes, NGOs, and mediocre local training institutes) and SfM graduates, SfJ/SfE graduates and students currently enrolled under the SfJ scheme. Overall impressions and conclusions drawn from the meetings are presented below. Refer to Annex-1 for the list of institutions visited and beneficiaries met. / The targeting approach of the Fund aimed at the poor and the vulnerable is effective. Students and graduates belong to either poor or vulnerable families, as has also been verified through PSDF records. The students and graduates were cross questioned to check their family backgrounds and economic status and invariably they belonged to either poor or vulnerable families. / Relatively better education level of a student i.e. matric, intermediate or even bachelors and masters does not imply that the individual is not poor/vulnerable. The individual may be the only one with education in the family, may have obtained the degree studying part-time or been studying free of cost at a local government school. Many students had spent considerable time unemployed despite having an academic degree because they did not have a practical skill that could get them a job. The biggest value of vocational training among beneficiaries is that it equips them with skills that can be applied in the market to make a living. Students said that potential employers are not interested in general education of an employee per se but what he/she can do for their business. / Rural and less educated women trained under SfM by the Lodhran Pilot Project (LPP), were very happy with the quality of instructors and what they had learnt. Repetitively they appreciated the fact that the training facility was close to their home and they did not need to go farther than a few minutes-walk. Though very excited about the range of home use items (i.e. bed-covers, cushion covers, mirror frames, hand bags etc.) they had learnt to make they were uncertain about how much they had earned through their sales. / The exhibition of ladies products organized by the LPP served as an attractive outing opportunity in Lodhran, attracted big local crowds and all products were sold out. In addition, women received orders for home products particularly from families preparing dowries for their daughters. Women were very keen for follow on training and improved linkages with the market. The appreciation for the training is so high that they are willing to undertake follow up training without stipend, and even willing to pay a nominal fee for it (Rs.50-100 per month) but provided the training remains at short walking distance from home, particularly for women with responsibilities at home. / Social imperatives restrict women’s mobility. However, social acceptability for women leaving their towns and living in boarding while receiving training is also gradually improving. Three factors are facilitating this: One, parents like to check the training facility and talk to the training provider and if assured will allow their daughters to enrol. Second, parents feel comfortable if the skill provider also belong to the region and enjoys good reputation. Lastly, other girls in the communities and their parents are inspired by the skills learnt by girls, stories of their training experience and the money they are able to earn. All of these factors are gradually broadening the social space and acceptance for girls training away from home. / Conversations with male students revealed increasing appreciation for working women, particularly as this enables coping with growing economic pressures. When asked all male students said that they would allow their wives to work, if they so desired. While women are largely interested in traditional crafts and stitching, opportunities in more non-traditional areas are also emerging. For example, women photographers who can cover ladies segregated wedding functions. Similarly, women graphic designers see growing opportunities for themselves in the local market for designing advertising instruments such as bill boards, brochures, etc. Reportedly, the pharmaceutical sector, prefers engaging women secretaries rather than men. / Overall, students were content with the quality of training and appreciated the vocational programme of PSDF. However, demand for follow up training, market linkages and job placement services was very high. / Recommendations / Skills schemes should be designed keeping perspective of the demand for services and products of local consumers/communities in villages and towns, who frequently need to travel to the nearest town/city to meet their needs. It may be helpful to have focus group discussions with communities to identify their unmet needs for services and products or for which they currently need to go afar so that appropriate skills can be developed to meet these needs. Additionally, entrepreneurship training and linkages with microfinance providers will be helpful in enabling skilled people to start their own business. / Skill providers should be encouraged to organize ladies markets/exhibitions. These events help introduce trained women’s products to the local market, enable sales, help women get orders for their products and increase demand for training among other women while also providing a good recreational activity for the community. / Training schemes for rural women should have a stronger enterprise development component through which women can learn how to develop their products according to market needs, pricing, costing, book-keeping and calculating profits etc. Maintaining books should be mandatory. Records will help women gain better understanding of their business, determine which products can help earn better margins and will also help the training provider monitor progress of the trainees. / PSDF’s communications strategy should have a special component for broadening the scope of women in broader economic activities. The strategy should include among others, increasing local communities’ acceptance and support for women’s education and training and exposure of communities to successful women from the region who can serve as role models for women from the PEOP districts.
1.4 Summary of overall progress: / PSDF’s business model represents a successful innovation. It has a lean management, cost effective delivery of skills and a rigorous monitoring system that is assuring quality within a constrained skills ecosystem. PSDF is enabling private skill providers to compete for public funds on a regular and systematic basis for the first time. It is taken as a serious skills player at the highest political level, which in turn has created space for DFID/PSDF to influence skills policy and regulation and earn political support for scaling it across Punjab. / Overall, PSDF has met its targets in a very disadvantaged region of Punjab where initially eliciting a provider response was thought to be difficult. Based on practical experience and research, on-going skill schemes have been improved and a new skill scheme for improving farming skills has been introduced. Most importantly, PSDF has made concerted efforts to facilitate job placement and is setting up a system for tracking the income earning status of students. The third party monitoring system has been refined further and a policy has been put in place to prevent/deal with violations by training providers. An MIS has been set up with an interactive dashboard, agreement with a web-based job portal and use of an outsourced call centre service to support the enrolment drive. So far, the Board has made all decisions independently without any interference from the provincial government. / The Fund’s good reputation in the market and high political support along with the politically conducive environment at the federal and provincial level, post national elections, has created space for DFID to play a more decisive role in the skills policy and regulatory arena. Additionally, DFID has initiated work for engaging a team to design DFID’s investments in skills beyond Punjab. Interventions at the policy and regulatory level will be a major focus of the new Business Case. / The coming year will be taken up in preparations and actual expansion of the PSDF to initially 6 economically active districts and then additional 8 districts. An Accountable Grant to PSDF is in final stage of approval. It will help to prepare for the scale up and boost its institutional capacity (AG covers sector studies, institutional strengthening, staffs capacity building etc.). / A detailed note on closure of L&D component, as per recommendations of last annual review is attached as Annex-II.
1.5 Key challenges / Delay in revised project’s approval: A revised PC-1 (project concept), which officially approves the re-profiling of funds committed by the Government of Punjab to the Livestock Component to PSDF (and adds 10 new districts) has been delayed by at least by six months. The document is now pending approval of the Executive Committee of National Economic Council (ECNEC) at the federal level. PSDF cannot commence training in the new districts unless the final approval is accorded. Delay in receiving this approval beyond June, 2013 will compromise PSDF’s ability to deliver against the targets of 2013-14. / Vacant Positions on the Board: Out of fourteen, there are currently three vacant positions on the Board. Current incumbents are therefore required to invest more time in Board’s Committees. Each Committee has up to three Board members. Due to increasing demand on directors’ time, Committee meetings have been cancelled or were postponed over the last year, leading to delays in recruitments and training projects. With the new government in place, there is a need to fill the vacant positions with mutual agreement of the sponsors as quickly as possible. / High Employee Turnover: The organisational turnover surged during the last one year. The management reports that in April 2013, 8 employees left the organisation during the last twelve months compared to 2 employees over the same period last year. / The number of resignations went up from less than 10% of the working strength to 29% of the same. Most of the staff members resigned due to better salary options or for pursuing higher studies. 50% of the resignations were from Management Assistants who were fresh university graduates. / New Donor-Assisted Projects: New donor investment is being planned. The most significant intervention, from the point of view of PSDF will be the USAID funded Workforce Development Programme that will also operate in South Punjab. Both DFID and PSDF have had meetings with the project design team at USAID and have identified three possible issues: / Staff poaching as USAID salary rates are expected to be higher; / Price distortions in the training market if the project award contracts at higher prices or offers higher stipends to trainees; / Providers’ may try to serve both and as a result training quality declines. / The USAID team has been suggested to sequence its entry into southern districts so that its entry in PSDF districts transpires at a later stage, say, in 2014-15. Requests have also been made to avoid staff and provider poaching. / Quality Assurance for SFM Scheme: The SFM scheme combines literacy and numeracy with vocational training for the less educated in the pilot districts. There are currently no standards for such training and no provincial authority is able to test and certify the trainees. The scheme has succeeded in reaching out to the poor and vulnerable especially in the rural areas[12]. The scheme, cannot, however, be expanded without sufficient confidence in quality of delivery and outcomes. / Operational Requirements and the RCT: The scale and ambition of the RCT design, especially for the SFM scheme, has created operational pressures for the PSDF team in a number of instances. Most significantly, the need to synchronise scheme roll out with voucher delivery led to a delay of two months in the start date of SFM. Provider unwillingness to participate in the evaluation has also resulted in unforeseen operational challenges. / Pressures to Diversify Operations: Employability of PSDF’s trainees will be the result of multiple, coordinating development interventions and not a single one. Even with the early resolve of the Board to specialise in skills financing alone, PSDF finds itself entering into other areas in order to facilitate employment. For example, placement functions have been outsourced by PSDF and a small cell is being established in PSDF in the absence of public job search services such as Employment Exchanges. Availability of microfinance, for graduates a much needed support for those starting own ventures would have been easier had there been an efficient network of micro-finance providers at the grass root level. PSDF and its providers are making efforts to establish working linkages with financial institutions to help start-ups. Similarly, since no marketing networks exist to link cottage industry producers in villages to urban sales outlets, PSDF has had to arrange exposure fairs for women artisans to introduce them to potential buyers. The risk involved in taking on these functions is that unrealistic expectations may be created of PSDF leading to a lesser focus on its core competency i.e. evaluating and financing training proposals and an upward creep in unit costs. / Tensions emerging due to divergent understanding of the role of an independent company: A recent audit of PSDF operations by the Auditor General of Pakistan observed that a section 42 company was bound not only by the objectives but also the operational details laid down in the Government’s programme document/PC-1. This view, held by many in the government creates conflicts with the prevalent law governing section 42/Not for Profit companies. For example, the recent Not-for-Profit Regulations 2013 of the Securities and Exchange Commission of Pakistan states that the appointment, remuneration and terms and conditions for the Chief Financial Officer, Company Secretary and the Chief Internal Auditor shall be approved by the Board (rule 16(2)). Given that the programme document also lays down conditions of appointment for the same personnel, question of precedence arises. The Government audit functionaries, have in the recent instance, accorded priority to the PC-1. Even though, the document has now been revised to ensure the Board’s supremacy (and a response to audit’s observations), there is still a possibility that the issue of the respective jurisdiction of governments and Company Board resurfaces, if not resolved at a higher level. / Recommendations / The Programme Steering Committee (PSC), GoPb, DFID and the Board needs to proactively lobby for the early approval of the PC-1 by the ECNEC and ensuring that the autonomy of Section 42 Companies under the Companies Ordinance is protected and they are not subjected to dual regulations and compliance requirements . / A PSC meeting should be organized as early as possible to suggest potential Board members to the Chief Minister’s office. / A salary survey should be undertaken covering public companies comparable to PSDF in order to ensure that PSDF staff salaries are competitive and market based. / Close coordination with USAID and other donors needs to be maintained in order to avoid market distortions and ensure that the larger investment of DFID in the skills sector draws on other donors and capitalizes on their strengths. / The TVET Reform Programme and ILO should be approached for assistance in developing certified courses that are offered under SfM. Trades typically include: stitching, and home decorations (preparing cushion covers, bedspreads, household linen etc). / PSDF should consider assigning the responsibilities of creating market linkages to the newly appointed Job Placement staff, given the relevance of market linkages for a skills programme. If required an additional staff person should be appointed.
1.6 Annual Outcome Assessment / Positive movements in indicators capturing beneficiaries’ income, their engagement with the state and well-being (the latter for women) will be used as evidence of PEOP/PSDF’s contribution to the intended outcome. All three indicators will be tracked under a mid- and end-of-term RCT evaluation and reported relative to a control group. Being the gold standard for evaluation, the Randomised Controlled Trials methodology has elicited a lot of interest from the academia. However, the low uptake of vocational training amongst the general population has led to an increase in the sample size for voucher distribution and experimentation with various interventions to encourage enrolment. So far, the RCT team has not been able to obtain a sample of sufficient power to report reliable results. / In the absence of RCT results, what we have, so far, is a self-reported assessment of employment rates by PSDF, changes in beneficiary incomes under a sample (considered too small by CERP to be statistically valid) and anecdotal evidence from individual trainees. / From the first source, the employment rate was calculated as 57% i.e. out of 6,786 SFE trainees, 3,856 were reportedly employed. Even though this rate is expected to have an upward bias, a safe estimate would be between 30-40%. PSDF plans to corroborate this data through its planned period trackers. / CERP has shared results of its first tracker with a number of caveats mainly based on a small sample size. Certain similar trends can be detected between results of a conventional tracer (of the Model Villages Tracer Study also conducted by CERP) and the RCT tracker results: / Female labour force participation rate significantly rises after training. The MVP tracer reports a 70% labour force participation rate (LFPR) of females post-training while the SFE tracker reports the same as 91%. The Baseline Survey had earlier reported a 60% LFPR for rural women. / LFPR for males drops after training completion in both reported trackers. / The SFE tracker also indicates that an increase in incomes (12%) may be expected for males but not for females. There is preliminary evidence to suggest that women also accept unpaid employment and join the labour force after completing training while males may need more time to get absorbed in the labour force. / Anecdotal evidence exists for women starting own entrepreneurial ventures and overcoming financial and social constraints while doing so. Participation in vocational training programmes funded by PSDF is contributing to a social change as women are applying for both conventional and non-conventional courses and even moving to non-PSDF districts for training. Training Service Providers have not reported any serious difficulty in recruiting females for PSDF-funded courses. / 1.7 Value for Money metrics / Value for money is assessed across the entire programme cycle, assessing cost of inputs to ensure resources are well used (economy), productivity as captured through cost of outputs (efficiency) and whether investment justifies the results (cost effectiveness). A value for money analysis conducted in 2012-13 and quality assured by PEOP Economic Adviser endorses the VfM of PSDF. Key highlights of the VfM are presented below. / Economy / PSDF’s cost per training product varies from Rs. 23,000 (£147) to Rs. 51,000 (£322). Given the different range of products that are evaluated, PSDF has a strong evaluation system that scrutinises the cost structure of bids. The closest in-country comparator is TEVTA, whose cost of delivery is twice that of the Fund. PSDF is also cost effective in comparison with a mix of other donor funded programmes whose fully loaded costs vary between Rs. 38,000 to Rs. 245,700 per training product. / The second Annual Review identified key cost drivers as: duration of training, type of trade and accommodation and stipend. The accommodation allowance is based on an independent market survey conducted by DFID, while the stipend is based on household survey data and actual experience of PSDF in the field. For within district training the stipend is Rs. 500/month and it increases to Rs. 1500/month for out of districts training. Meanwhile, the stipend being offered under BISP is Rs. 6,000/trainee. / Regarding the duration and cost of trade, using the bids received for SFJ, the specific cost range for each trade has been defined, rather than lumping all trades together as one generalized group as was the practice earlier. This provides PSDF more negotiating leverage with the TSPs to rationalise costs. Open competition for delivery of training has led to substantial and increasing number of private training providers entering the market of publicly-funded provision. Price of training is also expected to reduce with increased competition. PSDF does not limit itself to a defined number of trades/skills, therefore, there is a delicate balance to be maintained between stimulating innovation and achieving cost efficiency. / Efficiency / Capturing the core value of delivery is much more challenging. PSDF is maintaining focus on efficiency through effective management of the Fund, and its operations and quality of training to the extent within its mandate. As a section 42 company, PSDF has complied with high financial discipline. Overall management expenses remain well within the Board-fixed ceiling of 7% of programme expenses. A series of reviews and audits conducted during the year have endorsed the effectiveness of the Fund’s systems and proposed additional measures to boost the institutional capacity of the Fund to expand across Punjab. Following DFID recommendations to improve its financial system and drive VfM, PSDF has set up an internal audit system and a dedicated internal auditor has been hired to oversee/monitor financial processes. / PSDF uses Punjab Public Procurement Rules, 2009 for operational purchases and principles of the Consultant Selection Guidelines for purchase of training services. All programme expenses are made after open competition. The management engages in six-monthly procurement planning and payments are made strictly on the basis of delivery conditions. Additionally, a procurement specialist is being hired to advise the Fund on procurements and to participate in the procurement processes. His/her specialised expertise is expected to improve compliance of the organisation with defined rules and encourage better and transparent procurement practices / Regarding efficient delivery of skills, addressing the gaps in the skills eco-system (skill standards, manuals, curricula etc) is not within PSDF’s mandate and is/will be addressed through better coordination with other donors and TA. However, PSDF has put in place a robust third party monitoring system, which is its distinguishing feature. 80% pass percentage and attendance requirement is ensuring better quality of training than that offered by TEVTA even though both PSDF and TEVTA trainings are certified by PBTE. 10% of training under SFJ is certified by City & Guilds. A compliance remedial system has also been put in place which feeds into operational improvements. The monitoring system coupled with contract management practices developed internally minimize wastage of resources and have improved skill providers performance. / An output-based payment system means that PSDF does not invest in creating vacant capacity. Wastages are further controlled by sifting out drop-outs and paying for trainees who actually receive training. To discourage habitual trainees and maximize programme reach, a system to detect dual or earlier enrolments checks has been put in place. Identity frauds are immediately detected with the help of a national database of citizens. Providers face serious penalties in case a ghost/fake trainee is detected on their rolls. / Cost Effectiveness / The programme to date has led to the establishment of a viable business model that encourages private firms to conduct TVET. Continued investment in PSDF will be contingent on ensuring that the private and social returns to TVET under this model exceed the cost of provision. The initial evaluation proposed using Randomised Control Trial methods to assess the returns of the programme. While the voucher uptake was only 5% in the first round of SFE, retention increased to 30% in SFM once constraints in the way of uptake were addressed. Additional rounds of the roll out are planned in both SFM and SFJ which will help build a mass of voucher users for a statistically valid final evaluation of the Programme. However, initial experience of SFE shows 12% increase in income of men. Moreover, on average skill providers report over 50% of trainees as employed. PSDF is setting up a regular tracer system to check the employment status of all of its graduates and verify the number reported by employers. In addition, women’s labour force participation has increased. Early results also show trainees feel more connected with the state as opposed to those who did not receive any training.
[11] The non-income aspects of poverty and vulnerability will be captured through logframe indicators: the index of state engagement and the index of well-being.
[12] CERP Uptake Reports

2. Costs and timescale
Is the project on-track against financial forecasts: / The programme is behind the original financial projections by almost 3 years. This was due to: / DFID released a first tranche of £5 million to PEOP in 2011 (£2.8 million Skills; £2.2 million L&D). While PSDF had a slow start due to time consuming procedures for registering a Section 42 Company, the livestock component never really got off the ground. Due to poor performance the Second Annual review recommended closure of L&D component and re-profiling of the balance funds (unspent and uncommitted) to PSDF. Only £0.37million was spent by the livestock component in over 2 years of implementation. This brings DFID contribution of £4.63 million to the Skills component and £0.37 million to L&D component. / Since then DFID has been waiting for the GoPb contribution to match the initial DFID release. This was achieved in May 2013 when GoPb’s contribution exceeded that of DFID’s for the first time. DFID and GoPb disbursements are now better aligned and will in future be reconciled on a quarterly basis. / Financial projections for FY 20113-14 are now on track. DFID released £3.62 million in response to Government of Punjab request for funds in July 2013. Actual projection for the period April – September 2013 was PKR 759.812 million i.e. £5 million. DFID contribution PKR 379.906 million i.e. £2.5 million (50% of request). However, the released funds include funds required to match government’s excess contribution to expenditure of £1.74 million and reducing available DFID funds £0.50 million with government. / Financial Position on DFID Systems as on 20 August 2013 and comparison with government inflow of funds is as below / (GBP in Million*) / Activity DFID Government Total / Programme Budget £ 30 £ 25 £ 55 / Programme £ 8.6 £ 6.0 £ 14.6 / TA £ 1.1 £ 0.0 £ 1.1 / Total spend to-date £ 9.8 £ 6.0 £ 15.8 / Remaining Funds £ 20.2 £ 19.0 £ 39.2 / * figures are rounded off and includes exchange rate differences / Since inception to date against available £ 30 million DFID has spent 32.67% (that includes latest tranche of funds £3.6 million, which will be matched by government). The government’s allocated £ 25 million budget has spent level of 24%. / Against this years’ projection of £8 million, the remaining funds £4.56 are forecasted as £2.3 and £2.0 million in November 2013 and February 2014, respectively. For large payments team is making efforts to ensure implementation of matching funding principle right at the onset of payments, with the government. / PSDF has so far posted a utilisation rate of 70% in 2012-13. The underspend is due to unforeseen developments such as the following: / Delay in launch of a new Scheme Skills for Farms due to standardisation/certification issues; The scheme was to be implemented between February and June, 2013 and was costed at Rs. 237 million; / Transfer of fixed assets from the Livestock Component to PSDF reduced requirements for capital outlays; / Budget for certain contingencies (such as legal expenses), though required was not spent. / Budgeted and Actual Costs (July 2012 to May 2013) / Budgeted (in million Rs) Actual (in million Rs. & percentage of the total) Utilisation Rate / Programme Costs 1,333.61 933.881 70% / -96.30% / Operating Costs 44.559 31.756 71.30% / -3.27% / Capital Costs 7.04 4.14 58.80% / -0.43% / Total 1385.209 969.777 70% / -100% / 2.2 Key cost drivers / The Second Annual Review identified key cost drivers as: duration of training, type of trade; accommodation and stipend. It also pointed out that cost per trainee was drastically different than that assumed in the original project document and therefore, required a reworking of annual and total targets for trainings to be funded by PSDF from 250,000 to 80,000. / PSDF introduced funding for international certified trainings in 2013-14. Under SFJ 2012-13, 10% of the total funded training places were to be certified by international bodies with rates significantly higher than the national testing authorities. In case, the share of such trades is enhanced, the totals per trainee costs are expected to increase further. Capacity of local trainers continues to remain an important cost driver as it determines the scale of training conducted by out-of-district providers. High prevalent inflation and electricity shortages are also expected to contribute to increase in training costs resulting in higher average unit prices. / 2.3 Is the project on-track against original timescale: Yes / The project is on track against the timescale indicated in the Revised Programme Document according to which the Programme will end in December 2015.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There have been no major changes in the evidence underpinning the initial rationale and root causes for initiating the PEOP/PSDF intervention. Rather, new evidence is emerging which suggests that the link between the outputs (more skilled people) and the outcomes (higher incomes and employability) are not that straight forward. / For example, the Employers’ Survey, completed in November 2012, provided useful insights into hiring practices and growth prospects for firms in the pilot districts. A stark finding was that 85% of multiple worker firms hired on average only 2-3 workers each year. Only, 10% of such firms said that they would expand over the next year. Shortage of skilled workers was not the binding constraint for most firms wishing to expand. More than 60% of the firms viewed electricity shortage as the major barrier to growth. This is not unexpected as the dire energy shortages in the country over the past 24 months in particular have had a significant impact on economic activity. / Given the above evidence, there is a high possibility that PSDF funded trainees, while entering the labour market, might be displacing existing workers rather than necessarily accessing new jobs. Also, some evidence from household surveys suggests that networks (family, kinship etc) may have a larger impact on peoples job prospects than levels of training might be expected to have. These findings are being constantly evaluated by PSDF management and CERP to ensure that such learning can be incorporated into product design and PSDF activities/interventions. / Recommendations: / Project outcomes and impact should strictly be measured with reference to a control group or following a practical methodology that is statistically robust. In case, employment rates are to be measured and reported, these should be measured over a longer time span allowing for the effect of better economic conditions to be factored in. / The PSDF model should be tested for districts where economic activity is more robust and there is more tangible evidence of job growth. / 3.2 Where an evaluation is planned what progress has been made? / Randomised Control Trail (RCT) evaluations have been embedded in the programme from the outset. Specific deliverables are referenced under Output 5. / A mid-year evaluation was expected to be conducted in the second half of 2013. However, uptake of vouchers by the sample population during the initial phase of the programme was very low and has resulted in sample frame that is too small to deliver statistically significant results. Revisions have since been conducted to the structure and methodology of the RCT to address this. As a result, outputs from the mid-term evaluation are not expected until mid-2014. Next steps in the planned evaluation have been mentioned under the relevant part above.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / The outputs and their risk ratings are as follows: / Output 1 - Sustainable model for funding competitive training delivery: Medium risk / Output 2 - Skilled trainees: Medium risk / Output 3 – Private training places mobilized: Low risk / Output 4 – Policy and regulatory environment: High risk / Output 5 – Knowledge management and Sharing: Medium risk / Risk rating is assessed as medium for outputs 1, 2, and 5. Risk rating for output 3 is low given that PSDF is the only institutional mechanism for private providers to access public funding support and the number of registered private training providers has increased during the year under review. / Reforming the skills policy and regulatory environment is high risk given the scale of the reforms and the coordination efforts required to align all existing and potential donors to a common vision. In addition, reforms will require consistent high political commitment in a country where there are a range of issues requiring political attention on a priority basis. / 4.2 Assessment of the risk level / The risk level is assessed as medium. Based on the experience of the past one year, potential areas of risks and mitigation measures have been presented in the table below. / Risks Mitigation Strategy Type/ / Probability / 1 Delay in approval of the revised PC-1 at the federal level (by CDWP) Lobby with federal and provincial governments at high political levels for early approval, highlighting the fact that PSDF’s initiation of work in new districts is contingent upon approval of the PC-1. Given the PML-N’s keenness to make popular public announcements, there is likely to be high pressure on the bureaucracy to approve the PC-1. H/M / 2 Inability of the GoPb to match DFID’s funding support to PSDF, in turn affecting PSDF’s ability to meet its target for 2013/14 Given the high public appeal and political support for jobs for youth, it is expected that GoPb will meet its commitment. We will get confirmation of the earlier assurance from GoPb M/M / 3 USAID’s intervention in the skills sector in South Punjab: i) Skills market distortions due to payment of higher training fee to skill providers and stipends than PSDF and poaching of PSDF staff ii) Given USAID’s strong political motivations, donor sponsored skills programmes can suffer a strong public backlash. Proactive coordination with the USAID team by the PEOP team at DFID and the management of PSDF. However, avoiding operational ties and visibility with the USAID programme at the field level. H/M / 4 PSDF suffering bureaucratic bottlenecks being a government sponsored company Ensuring strong board members are enlisted who can push back on bureaucratic pressure and proactively facilitating the Board to protect its autonomy. M/M / 5 Political pressure to expand PSDF model across Punjab and Khyber PakthunKhwa (KPK) without allowing time for the due diligence. Through proactive lobbying with GoPb and Federal government create awareness about introducing competitive principles underlying PSDF into public sector delivery of skills e.g. making access to public funding for the public skill providers competitive and performance based. 2. Well-considered options have been drafted for intervening at the federal and KPK levels which will be investigated further through the design phase for the Business Case for expanding investment in the skills sector. M/H / 6 Delay in implementation due to audit observations by the Auditor General of GoPb. The AG does not recognize the authority of the Board of a publically owned corporate body. Consequently, the audit of the AG has raised several observations. Delay in clearing these observations can impede the PSDF from following its work plans in the existing districts. 1 Lobby for the autonomy of the Fund as a corporate body governed by the Companies Ordinance, 1984, using examples of comparable public sector corporate bodies which are functioning autonomously under independent Boards. 2 Lobby for the early approval of the PC-1 by the ECNEC 3. Ensure experienced private entrepreneurs continue to be well represented on the Board. H/M / 7 Lack of reforms of the skills regulatory functions at the federal and provincial levels which can undermine quality of training. A focus on these issues in the proposed Phase II scale-up. H/M
Risk of funds not being used as intended / Risks, of funds not being used for the intended purpose is minimal. / PSDF Board of Directors of PSDF, has been actively engaged in overseeing PSDF operations. It has insisted on strong fiduciary controls and is determined to avoid any incidents or even perceptions that funds are being misused in order not to undermine the mandate of PSDF. / PSDF: / As recently concluded DFID corporate reporting of Annual Statement of Progress, Institutional and Operational Audit/Due Diligence, concludes sufficient systems in place for the existing work of PSDF, however, there are recommendations like automation of procurement system, custodian role of procurement function; refining Internal Audit function and adoption of human resource operational manuals, which will enhance PSDF efficacy and efficiency for its future expanded manifesto. In addition, a two tier remedial system i.e. first tier Internal Auditor and Programme and Design Committee as the second tier. / Government: / The ASP recommended automation of accounting system of PCU (sync with PSDF accounting system) along with adequate training of finance officer. In addition, funds matching report should be share on quarterly basis with monthly financial progress reports. / CERP: / CERP has been advised to develop procurement and financial manuals along with development of SOPs for the outsourced vendor for accounting and book keeping. / 4.4 Climate and Environment Risk / There are no serious risks to the climate and environment emanating from this Programme.

5. Value for Money
5.1 Performance on VfM measures / Management Expenses: / As a section 42 company, PSDF has complied with its self-imposed financial discipline. Overall management expenses remain well within the Board-fixed ceiling of 7% of programme expenses. On the whole, the Fund’s expenses have remained below planned budget levels. For example, during 2012-13 till May, 2013, PSDF’s operational budget has been 74% and 33% less than the amount budgeted in the original programme document and the revised programme document, respectively. / A value for money analysis conducted in 2012-13 and quality assured by PEOP Economic Adviser endorses the VfM of PSDF. / Figure 3: Programmed and Actual Expenses of PSDF (Opex and Capex) / (In Rs. Million) / Programme Expenses: / Open competition for delivery of training services has led to a substantial and increasing number of private training providers entering the market of publicly-funded provision. Under SFE, 117 training providers submitted their Expressions of Interest. This number rose to 143 under SFJ 2012-13 and 180 under SFJ 2013-14. However, since PSDF does not limit itself to a defined number of trades/skills, there is a delicate balance to be maintained between stimulating innovation and achieving cost efficiency. Nevertheless, prices of traditional trades are expected to be reduced with increased competition over time. A cost review system is in place at PSDF. Costs are also reviewed in a Product Design and Evaluation Committee and then in the larger Board. Efforts are made to be continuously informed about costs of other public schemes. / The programme continues to demonstrate that a supply response for skills delivery can be flexible and free from requirements of heavy prior investments in physical infrastructure. / On trainees’ stipend, PSDF appears to have followed a prudent approach. The Household Baseline Survey conducted in 2011, recommended a monthly stipend of upto Rs 3000 per month. PSDF’s current stipend for day trainees is half of the recommended level with only one revision so far. PSDF revised the stipend being offered to trainees for both SFJ and SFM trainees (receiving training with the four districts) from Rs 1000 per month to Rs. 1500 per month during 2012-2013. (BISP’s Waseela-e-Rozgar Programme offers a monthly stipend of Rs 6000). / The accommodation support was also enhanced from Rs. 4000 to Rs. 7000 on the basis of a market review of costs. The new accommodation support however also covers the cost of trainees’ meals. / PSDF’s third party monitoring system has been a distinguishing feature of the programme promoting efficiency. This coupled with contract management practices developed internally minimize wastage of resources and has been found to improve provider performance wherever observable parameters indicate a decline in quality. Specifically, / An output-based payment system means that PSDF does not invest in creating vacant capacity. Wastages are further controlled by sifting out drop-outs and paying for trainees who actually receive training. / Actual training output is verified by a reputed third party monitor (currently Ernst and Young) which records deviations from delivery standards by providers. These deviations are linked with penalties have a positive effect on overall class attendance and facilities being offered by the TSPs. / Going beyond verifying actual trainees, the Fund collects data on observable quality indicators through the third party monitor. There is early evidence of quality improvements in areas such as exam results and trainer attendance. / To discourage habitual trainees and to maximize the programme reach, a system to detect dual or earlier enrolments checks whether a trainee is availing PSDF trainings for a second time, and bars him or her from abusing the system. / Identity frauds are immediately detected with the help of a national database of citizens. Providers face serious penalties in case a ghost/fake trainee is detected on their rolls. / Commercial Improvement and Value for Money / PSDF uses Punjab Public Procurement Rules, 2009 for operational purchases and principles of the Consultant Selection Guidelines for purchase of training services. All programme expenses are made after open competition and following a two-stage tendering process. A Bid Evaluation Committee scrutinises every procurement and reviews costs. / On the operational side, a three tiered process is followed under Government Rules: / For purchases upto Rs. 25,000 direct contracting is used; / Three quotations are invited for procurements under Rs. 250,000; and / All purchases above Rs. 250,000 are made using open competition. / Procurements under b) and c) are recommended by a Procurement Committee which reviews and scores each bid according to a defined selection criterion. All advertisements are placed on PSDF’s own website and Government of the Punjab’s official website. / The management engages in six-monthly procurement planning. All contracts are written and payments are made strictly on the basis of delivery conditions. / In 2012-13, PSDF introduced competition at trade/course level for its SFJ scheme. Its proposal evaluation work increased manifold, however, training service providers were put through much rigorous scrutiny and competition. To engage multiple providers, reference prices were set as benchmarks for price negotiations with providers bidding more than these rates. The Fund reports having held successful negotiations with many providers who were engaged at lower than quoted prices. / PSDF runs an automated accounting and financial management system using SAP software. The SAP system was purchased in 2011-12 and was implemented during 2012-13. Through the system, PSDF maintains records of programme and operational expenses, tracks invoices and payments and also extracts specific reports for each service provider such as calculation of penalties under the defined business rules. / The Fund has implemented two important DFID recommendations to improve its financial system and drive VfM: / An internal audit system has been introduced and a dedicated internal auditor has been hired to oversee/monitor financial processes. / A procurement specialist is being hired to advise the Fund on procurements and to participate in the procurement processes. His/her specialised expertise is expected to improve compliance of the organisation with defined rules and encourage better and transparent procurement practices. / 5.3 Role of project partners / Overall, PSDF has been able to demonstrate good value for money by imposing and adhering to a ceiling on operational expenses and by strictly following competitive principles for programme procurements without exceptions. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take? Not Applicable

6. Conditionality
6.1 Update on specific conditions / No official conditionalities apply in the traditional sense. However DFID has agreed in principle with the GoPb that going forward, matched funding will be reconcile on a quarterly basis prior to the release of further DFID funding.

7. Conclusions and actions
The recommendations have already been discussed with the PSDF management. Upon completion of the Annual review they will also be shared with the Board of Directors. Together the recommendations from the Annual Review, the Annual Statement of progress and due diligence assessment will be consolidated into one document. The document will include proposed timelines by when the recommendations will be implemented. During the proposed management reviews progress against this action plan will be monitored. In parallel, the DFID logframe will be revised and updated within 6 weeks, in consultation with PSDF, CERP and Government. / A summary of recommendations has been categorized under 4 main areas: i) Boosting institutional systems and capacity ii) Strengthening operations iii) Strengthening linkages with other stakeholders and enabling environment and iv) DFID programme management. / Boosting institutional systems and capacity: / Develop and implement an Action Plan to implement various audit/review recommendations (PSDF). Internal controls need to be strengthened to support the scale up of PSDF across Punjab. The ASP, Audit and Operations and Institutional Assessment/Due Diligence recommendations need to be implemented following the action plan to be agreed with the PSDF. These actions will further strengthen PSDF’s operational capacity and reduce risks. / PSDF should also test remote access facility to the MIS by the providers who should update their monthly reports in real time. / A dedicated Complaints Cell should be set up during 2013-14 in preparation for the proposed scale (PSDF). This will help address grievances in an organized manner and more importantly feed into the design of the programme. / The performance of the Placement Cell being established during 2013-14 should be measured against delivery of targets. / Strengthening operations / Continue to refine and expand the current PSDF product offer (PSDF). There is a need to offer an entrepreneurship training module as an option available to all successful candidates of SFJ and SFF, given that the Employers Survey shows that 80% of employers employed only 2-3 staff in the last one year and have no substantial hiring plans. Linkages with the microfinance providers also need to be strengthened to enable eligible students avail financial facilities for setting up their own business. Training providers offering on-the-job training should explore mentoring and also be required to invite visiting faculty from the industry and successful established entrepreneurs to deliver inspirational lectures on their experiences, emphasising challenges and their surviving strategies. These actions will help improve linkages with the industry and exposure of students work to potential employers. Similarly, on a regular basis, PSDF should organize exposure visits of established Pakistan brand owners to the PEOP districts to enable them gain direct access to the workforce being developed and the quality of its work. / Develop a comprehensive communications strategy (PSDF). There is a need to prepare a comprehensive communications strategy that identifies various constituencies of the Fund and has clearly thought out action plan of how to reach each, while also show casing PSDF’s work to existing and potential stakeholders. The strategy should identify the activities that need to undertake toward different ends. For example, road shows among the corporate sector for raising awareness about the Fund and mobilizing funding support for it, and preparing case studies of students following nonconventional careers and businesses. PSDF can better leverage its accomplishments, enhance its visibility and make inroads among new stakeholders through a comprehensive communications strategy. The strategy can also serve as a tool for linking students with potential employers, creating awareness about skills needed in the market and increase communities acceptance and support for working women. PSDF should develop a strategy and an action plan for achieving institutional sustainability which enables PSDF have permanent flow of funds from various stakeholders. Given that it is still early days for PSDF, the strategy should have short, medium and long term horizons. / PSDF’s communications strategy should have a special component for broadening the scope of women in broader economic activities. The strategy should include among others, increasing local communities’ acceptance and support for women’s education and training and exposure of communities to successful women from the region who can serve as role models for women from the PEOP districts. / Periodic assessments of TSPs (PSDF) will help determine how the provider is maturing and building its capacity for larger contracts. This information will also serve as a proxy indicator of PSDF’s development impact on skill providers. / Organize TSP conferences periodically (PSDF) should which will help cross fertilization of ideas, mutual learning, possibilities of collaboration and improved understanding about their work environment and emerging among potential beneficiaries. Over a 100 TSPs ranging from small NGOs to corporate skill providers have engaged with PSDF. There is considerable variation in their know-how and implementation approach. / Skills schemes should be designed keeping perspective of the demand for services and products of local consumers/communities in villages and towns, who frequently need to travel to the nearest town/city to meet their needs. It may be helpful to have focus group discussions with communities to identify their unmet needs for services and products or for which they currently need to go afar so that appropriate skills can be developed to meet these needs. Additionally, entrepreneurship training and linkages with microfinance providers will be helpful in enabling skilled people to start their own business. / Skill providers should be encouraged to organize ladies markets/exhibitions. These events help introduce trained women’s products s to the local market, enable sales, help women get orders for their products and increase demand for training among other women while also providing a good recreational activity for the community. / In addition to financial literacy, training schemes for rural women should have a stronger enterprise development/entrepreneurship component through which women can learn how to develop their products according to market needs, pricing, costing, book-keeping and calculating profits etc. Maintaining books should be mandatory. Records will help women gain better understanding of their business, determine which products can help earn better margins and will also help the training provider monitor progress of the trainees. / PSDF should consider assigning responsibilities of creating market linkages to the newly appointed Job Placement Staff given the relevance of market linkages for a skills programme. If required additional staff should be engaged and a few pilots should be tried which may be scaled up/inform operations in the new districts. / Continue and enhance PSDF’s partnership with CERP or other research organisations (PSDF/CERP). Evidence is needed to further refine and expand the PSDF product offer especially with regards to women and to strengthen market linkages. The partnership with CERP should continue to test variations under SFM but the focus should shift from uptake to post-training success. Discussions to this effect are on-going. / The mid-term RCT evaluation may be dropped (DFID) in favour of repeated trackers of SFJ and SFM trainees of the samples obtained in 2013-14. This will allow for sufficient time lag for graduates to find jobs or start businesses. / An updated evaluation strategy and action plan for the new districts should be developed. Implementation modalities, roles and responsibilities of stakeholders should be clearly spelled-out in order to save time and avoid administrative bottlenecks. This should also include (i) a revised proposal covering the SFJ scheme through an RCT approach and suggest, especially with regards to the new districts, (ii) a practical methodology that helps assess working with employers and addressing skills gaps in select sectors. Finally, it should propose a log frame indicators to captures the outcome of the PSDF in the new districts. / Publish a paper on CERP/PSDF learning (CERP). With specific reference to SFM scheme, utilising baseline reports on households and employers and be shared with academia and development practitioners locally and abroad through a series of structured outreach events. CERP should be requested to produce/ / Strengthening linkages with other stakeholders and creating an enabling environment / Aggressively lobby for revision and development of training and learning resources by TEVTA/NAVTTC within a given timeframe (DFID/PSDF). To overcome the objections raised on Skills for Farms Scheme, it is suggested that PSDF should request the NAVTTC and TEVTA (Punjab) to recommend new courses in the agriculture and livestock sectors. In the meantime, course durations may be rationalised in consultation with the qualifying training service providers. / At the federal level there is the need to draw on the TVET Reform Programme and ensure that private sector promotion is a key feature of all its initiatives (DFID/PSDF). e.g. trainers’ training programme should also be provided for private skill providers rather than only the public skill providers as is being done presently. PSDF may offer to use its leverage with the private sector to ensure its involvement. At the provincial level, competency based manuals being developed under the TVET Reform Programme should be piloted/applied for PSDF sponsored training. / Government of the Punjab may consider a one-time moratorium on registration fee which is considered on higher side by private providers (i.e. Rs.22,000 for 3 years). With this concession NGOs can be encouraged to register as formal training institutes with TEVTA/PBTE. / Develop a mutually beneficial partnership with TEVTA to influence policy changes (PSDF). Especially in the area of development of training inputs and more cost effective delivery of training. TA money can be utilised for financing some sector development activities by TEVTA especially where it is cash-strapped and piloting public private partnership modalities for a select group of TEVTA institutes. Close coordination with World Bank is also necessary in order to inform its potential programme for TEVTA with practical experience of PSDF. / Lobby for making TEVTA institutes effective and market oriented. Individual TEVTA institutes should be formally allowed[13] to bid for PSDF funds (PSDF), while maintaining safeguards against uncompetitive practices such as use of subsidies to bid down prices. / DFID should contribute to rationalising skills policy and regulation both at the provincial and federal policy levels. Using the TA, and drawing on PSDF’s experience, the (proposed) new Business Case for expanding DFID’s investment in skills across the Punjab should take a more strategic approach to this issue. / PSDF should share its experience and views more widely. To promote efficiency in public skills delivery, it can share its experience on institutional monitoring with TEVTA and PVTC. This experience should be shared with other donors particularly the World Bank which is planning a skills development programme with TEVTA. / DFID’s programme management / Revise the indicator and milestones for Output 1 i.e. sustainable model for funding competitive training delivery. The revised indicator and milestones should enable to more adequately capture the full scale of progress achieved by PSDF towards becoming a mature innovative skills financing model. / Revise the indicator and milestone/Output 3 i.e private training places mobilized to promote a mix of for and not for profit skill providers. Given the high uptake and involvement of not-for-profit training providers the DFID and PSDF might consider revising the indicator and milestone to focus either on promoting an appropriate mix of providers and/or for profit making private companies. Especially as the later were non-existent in the south of Punjab prior to DFID’s intervention and changing this dynamic was a key objective of PSDF at the outset. / The target dates for the Evaluation Reports should be revised (DFID/CERP/PSDF). Given the difficulties in obtaining an RCT sample, and a new schedule of reports for SFM and SFJ trainees should be included in the log frame milestones. Additionally, the PEOP logical framework should be revised to reflect new dates for SFM and SFJ roll outs in 2014-15 with the target of achieving a statistically robust sample for the final evaluation / Key Challenges: / The Programme Steering Committee (PSC), GoPb, DFID and the Board needs to proactively lobby for the early approval of the PC-1 by the ECNEC and ensuring that the autonomy of Section 42 Companies under the Companies Ordinance is protected and they are not subjected to dual regulations and compliance requirements . / A PSC meeting should be organized as early as possible to suggest potential Board members to the Chief Minister’s office. / A salary survey should be undertaken covering public companies comparable to PSDF in order to ensure that PSDF staff salaries are competitive and market based. / Close coordination with USAID and other donors needs to be maintained in order to avoid market distortions and ensure that the larger investment of DFID in the skills sector draws on other donors and capitalizes on their strengths. / The TVET Reform Programme and ILO should be approached for assistance in developing certified courses that are offered under SfM. Trades typically include: stitching, and home decorations (preparing cushion covers, bedspreads, household linen etc). / PSDF should consider assigning the responsibilities of creating market linkages to the newly appointed Job Placement staff, given the relevance of market linkages for a skills programme. If required an additional staff person should be appointed. / Evidence and Evaluation: / Project outcomes and impact should strictly be measured with reference to a control group or a practical methodology that yields statistically valid results. In case, employment rates are to be measured and reported, these should be measured over a longer time span allowing for the effect of better economic conditions to be factored in. / The PSDF model should be tested for districts where economic activity is more robust and there is more tangible evidence of job growth.
[13] Since there is no clear regulatory guidance on whether individual institutes may bid or not.

8. Review Process
The Review team included: Fatimah Afzal, Lead Adviser PEOP, Sohail Wajid, Programme Manager, FMJ, Akhlaq Ahmed, Programme Officer PEOP, Dr. Arif Raza, representative of P&DD and Sarah Saeed, Skills Strategy Adviser. Since a number of independent perspectives on PSDF have been had from a number of reviews concluded recently (scale up strategy review, institutional assessment, and audits) no external evaluator was invited. / Over July 1-3 field visits were undertaken in Multan, Bahawalpur and Lodhran. A cross section of male and female graduates and enrolled students in SfJ and SfM were met. The team also met with the skill providers, teachers and the PSDF staff in Bahawalpur and Lahore, in addition to Board members (Dr. Ijaz Nabi and Baligur Rehman), and CERP.