ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	BEAM
Country or region targeted	Malawi
Type of cost extension	17 months cost extension
Original project budget	£18,839,872 / Amended through cost extension in November 2014 to £20,457,729
Original project start and end dates	7 December 2010 – 31 March 2018 / End date amended in November 2014 to 30 June 2016
Cost extension value	£4.5m
New project end date	30 November 2017
Business Case Quest Document No.	3008367 (Project Memorandum revised version)

INFORMATION
What is the project’s purpose?
The goal of the Building Empowerment and Accountability in Malawi (BEAM) Programme is more accountable, responsive and inclusive governance in Malawi, to support progress on off-track MDGs. The purpose is to empower citizens to hold the Malawi state to account and improve the delivery of basic services
What is the objective of the cost extension?
The cost extension will facilitate an extension of the £14 million fund manager contract for BEAM’s multi-donor Tilitonse civil society governance fund. This will allow for a responsible phasing out of the existing management arrangements for Tilitonse, maintaing momentum while the fund gets set up as a foundation in accordance with the Tilitonse Board’s recommendations. The Tilitonse foundation will receive UK funding from a new Empowerment and Accountability programme which is expected to be operational in March 2016.
What is the additional and total support the UK will provide?
The UK will provide up to £4.5 million additional funds for the BEAM programme, bringing the total budget for BEAM to £24,957,729. The additional funds will be allocated to BEAM’s Tilitonse component to enable an extension of the fund manager contract which is managed by the UK on behalf of the other donor partners, Irish Aid and the Royal Norwegian Embassy.
What are the expected results?
The overall impact that Tilitonse aims to achieve is “Governance in Malawi is increasingly inclusive, accountable and responsive.” / The expected outcome of Tilitonse is “Citizen voice in achieving more inclusive, accountable and responsive governance in Malawi is strengthened.” / The outputs are: / Capacity of CSOs to enable citizens, particularly poor and excluded groups, to claim their rights increased; / Access to information on rights, entitlements and responsibilities increased particularly for poor and excluded citizens; / Monitoring by Malawian organisations of policy and budget commitments, service delivery and public resource management strengthened; / The engagement of Malawian organisations in influencing policies, strategies and resource allocations at local and national levels improved. / The additional £4.5m will enable a responsible phasing out of the current fund manager arrangements while Tilitonse is established as a foundation. This will allow capacity building and financial support to Malawian civil society to continue, and enable the fund manager to consolidate and build on results already achieved while the supporting the set-up of the foundation through a transfer of knowledge on systems, procedures and risk management that have worked well thus far in Tilitonse. / The £4.5m is expected to buy the following additional results, assuming a 30% increase on targets for the initial £14m contract: / 60 documented cases of influence at national and decentralised levels on government and non-government actors achieved by BEAM programme partners / 113,190 people supported to have choice and control over their own development and hold government to account / 54 information products developed in funded projects / 465,000 people informed through funded projects about their rights to public services / 180 representations based on monitoring initiatives made to traditional leaders, officials responsible for public service delivery, MPs / 6 practices and issues promoted by CSO grant partners that are adopted by other CSOs and development actors / These additional results will be subject to confirmation as part of the negotiations on the extension of the fund manager contract. / Compliance with the Gender Equality Act / We have considered the likely impact of the programme on gender equality. The BEAM programme’s focus on improved service delivery for the poor sets a critical challenge to achieve more accountable and inclusive governance, including for women and girls. The programme is continuing to systematically track results delivered for this group by disaggregating data by sex in all instances where this is relevant.
What is the approach to implementation?
The management, contracting and procurement arrangements etc. remains as set out in the revised Project Memorandum (EDRM 3008367). However, following the recent fraud cases involving Tilitonse grantees and the subsequent review of its financial and fund management systems, Tilitonse has instituted additional robust measures and requirements across its entire portfolio of downstream partners to cope with the high levels of fraud and corruption risk. The measures include intensified routine and unannounced financial monitoring visits to the recipient organisations by the Tilitonse Secretariat.
Describe any key changes to the original business case?
BEAM was originally conceived as a portfolio programme bringing together a total of 14 planned components. Some components were in the process of being designed at its approval stage, some were short extensions to existing projects, and others were still to be fully defined. In BEAM’s first two years, the political context was increasingly restrictive and unpredictable and the expected final components of BEAM were not all fully realised. Following a rationalisation of BEAM’s components during the programme’s third year, it is now focused on implementing the three components that deliver the greatest contribution to the BEAM objectives: the Tilitonse civil society governance fund, the Kalondolondo score-carding programme, and the support to Public Financial Management (PFM) reform through the World Bank’s PFM Multi-donor Trust Fund.