Type of Review: Project Completion Review

Project Title: Special Programme for Research and Training in Tropical Disease (TDR)

Date started: December 2008	Date review undertaken: 20 August 2013

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The UK provided a total of £15.5 million to support the Special Programme for Research and Training in Tropical Disease (TDR) over five years 2008/09 to 2012/13.

What were the expected results?
Formed in 1975, the Special Programme for Research and Training in Tropical Diseases (TDR) is a global programme of scientific collaboration that helps coordinate, support and influence global efforts to combat a portfolio of major diseases of the poor and disadvantaged. It is hosted by the World Health Organisation (WHO) and co-sponsored by the United Nations Children’s Fund (UNICEF), the United Nations Development Programme (UNDP), THE World Bank (WB) and WHO. / With a vision of making research and innovation improve the health of those burdened by infectious diseases of poverty, TDR aims to: / Foster research on infectious disease of poverty that leads to health improvement / Engage disease endemic regions and countries in setting the health research agenda and harmonising the global response / Strengthen the capacity of individuals and institutions in diseases endemic countries to perform research related to their own priority health issues / Develop innovative knowledge, solutions and implementation strategies that respond to the health needs of disease endemic countries / Translate innovation, knowledge, solutions and implementation strategies to policy and practice improving health / Promote the involvement of individuals, communities and societies in the use of research evidence to reduce the burden of endemic diseases in their countries. / To achieve this vision and the associated aims TDR developed two main programmes of activity: / Intervention and implementation research / Intervention research / Implementation and operational research / Research of vectors, environment and society / Research capacity strengthening and knowledge management / Research capacity strengthening / Gap analysis for agenda setting / Partnership and engagement

What was the context in which UK support was provided?
Through the UK’s Framework for Results, DFID is committed to supporting nations to achieve the universally agreed Millennium Development Goals (MDGs). Through its focus on infectious diseases of poverty, TDR’s work has supported disease endemic countries (DECs) to better control malaria and other infectious diseases including Neglected Tropical Diseases (MDG6, Framework for Results Pillar 3 – health). In addition TDR’s research, aimed at improving infectious disease control, contributes to MDG4, to reduce child mortality and to MDG1, to eradicate extreme poverty and hunger. The strong emphasis on capacity building contributes towards a sustainable approach to research, supporting disease endemic countries to conduct their own research now and in the future. / During the funding period TDR went through a major funding crisis, which was caused by an over ambitious research programme and assumptions, made by the senior staff and the Joint Coordinating Board, that significant additional funding would be forthcoming. With the global financial crisis, support for TDR was reduced and the shortfall in funding precipitated a major reorganisation including the appointment of a new director. The new director has made substantial progress in developing a new research strategy, reorganising the research portfolio and institutional structure. TDR is now well positioned to meet future challenges.

## Section A: Detailed Output Scoring

Output 1: Countries and major funding agencies use TDR scientific and strategic reports to set research priorities
Output 1: final score and performance description: A – Output met expectation
Final results: / TDR is a well-established and globally respected organisation and despite the upheaval of the past 2 years it has maintained this position. / Progress during the life of the grant has culminated in the publication of the Global Report for Research on Infectious Diseases of Poverty in 2012. The report had 14 authors, 8 from disease-endemic countries and was produced after an extensive consultation period, involving many different stakeholders. / When the report was launched a commentary in The Lancet (April 2012) stated: ‘we welcome this report, as well as TDR’s new director, John Reeder. The vision expressed by TDR should earn wide new commitment and partners. It deserves commitment.’ / The report has been influential, in particular the EU expressed strong interest in using it to develop strategy for research on infectious diseases. An Action Report was prepared specifically at the request of the Directorate General of Research and Innovation of the European Commission in order to provide recommendations and options for future support and engagement in the research into infectious diseases of poverty. It is envisioned that the recommendations will be considered by the European Commission as part of the development of the new Horizon 2020 and other key EC funding mechanisms focussed on global health. / Building on its expertise in implementation research and in consultation with others TDR has developed and published the reference document Implementation Research for Control of Infectious Diseases of Poverty, discussing a collection of case studies on how implementation research can strengthen the evidence base for the access and delivery of new and improved tools, strategies and interventions. / TDR provided the secretariat for Essence for Health Research Initiative. With partners TDR conducted a wide consultation that resulted in the publication of two strategic good practice documents intended to harmonise support to implementation research and capacity building: / Planning, Monitoring and Evaluation Framework for Research Capacity Strengthening, / Five keys improving research costing in low and middle income countries. / TDR led the development of a framework for the introduction of rapid tests on sexually transmitted infections in country programmes. There is increasing public health concern about antibiotic resistant infections, particularly for gonorrhoea and syphilis. Seven countries changed their policy to adopt rapid syphilis testing into their prenatal screening programmes. / In May 2011 the Global Health Council on behalf of the Bill and Melinda Gates Foundation awarded TDR the Gates Award FOR Global Health, demonstrating the influence of their research and capacity-building efforts on both the BMGF and wider development community. / Impact Weighting (%):25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Disease Endemic Countries (DEC) are leading new/strengthened health research initiatives
Output 2: final score and performance description: A – Output met expectation / Final results: / TDR has a long and effective history of capacity building, largely focusing on strengthening the capacity of individual Disease Endemic Country researchers and clinicians. More recently there has been a focus on strengthening the capacity of disease programme and institutions in disease endemic countries. TDR alumni are to be found in senior positions in ministries of health, leading academic institutions and disease control programmes in many low and middle income countries and WHO. / TDR have been monitoring the percentage of publications with first author from disease endemic countries and in 2012 this had increased from 61% to 65% of the over 200 peer-reviewed publications acknowledging TDR support. This means that TDR's 2015 target had been reached and roughly two thirds of all publications originate from disease endemic countries. This confirms TDR’s commitment to strengthening research capacity in developing countries. / TDR ha continued its programme Career Development Fellowships, with pharmaceutical and research institute partners. 12 candidates from developing countries have completed their fellowships and have developed specialised skills to lead major research and development projects. Since it started in 2000 the programme has supported 27 fellows from 16 countries. / Chittagong Medical College (Bangladesh), National Institute of Medical Research (Tanzania) and Navrongo Health Research Centre (Ghana) were all part of a multi-centre trial on rectal artesunate which was sponsored by TDR together other donors. Several researchers involved in the trial have been awarded funding to complete PhDs on malaria and have been trained as clinical monitors. Together with the Mahidol Oxford Research Unit, these institutions have now been awarded a major grant by Grand Challenges Canada to implement a study to understand whether malaria is responsible for reducing child development potential by causing cognitive damage. / The African Network for Drugs and Diagnostics (ANDI) is now operational with recognition of 38 centres of excellence and funding of 2 projects. An external evaluation of ANDI which highlighted achievements and challenges in the implementation of the initiative such as being under-resourced and understaffed. Two Research and Development projects to be led by Diseases Endemic Country scientists were selected and funded; agreements for training/capacity building have been finalised with the centres of excellence. / Plans for a similar programme for Asia, ASEAN Network on Innovation, have progressed with a strategic business plan completed by its secretariat, including a review of the Research and Development landscape, a business model, governance and organisational structure.
Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: New/improved knowledge, tools and implementation strategies are used in DECs
Output 3: final score and performance description: A – Output met objective
Final results: / TDR has contributed to the development of numerous tools and strategies designed to tackle the problems caused by tropical diseases in low and middle income countries. TDR work through funding and coordinating research and development activities, or by supporting researchers to pursue innovative ideas, as well as by facilitating dialogue and interactions between various institutions and stakeholders. The following are some of the important achievements in recent years: / WHO guidelines now recommend rectal artesunate for severe malaria in paediatric populations living in remote areas / WHO now recommend against the use of immunodiagnostic tests for active or latent TB infection based on the results of TDR’s review of tests / TB fluorescence microscopy – research results informed the introduction of LED-FM in high burden countries / A simple, revised, evidence-based disease classification system for dengue adopted in Latin America and Asian countries / Visceral Leishmaniasis active case detection methods, developed by TDR-funded researchers, have been applied at large scale by control programmes in the Indian subcontinent / Evaluation of rapid diagnostic tests have led to quality improvements and the rapid diagnostic tests have become part of the overall strategy for malaria: ‘Test, Treat, Track’ / TDR have also supported a major study designed to assess whether the elimination of river blindness was feasible in endemic areas in Africa. The study conclusively showed that treatment with ivemectin not only controls river blindness, but also interrupts transmission and has been able to eliminate the parasite in some areas. / TDR has been involved in long term research to improve the prevention and management of childhood fevers. The research has shown conclusively that trained community health workers can be instrumental in providing primary health services in underserved remote areas. New research will test whether community health workers can reliably diagnose and treat fever, which may be a symptom of malaria or caused by pneumonia or diarrhoea in children. A supplement of the American Journal of Tropical Medicine and Hygiene was co-edited by TDR on this topic and the 16 research articles were widely disseminated in the supplement. / As part of the reorganisation TDR reassessed priority areas, taking into account other major tropical disease research programmes, and decided to focus in future on Implementation research and capacity building activities. As a result of this process TDR has incrementally closed a number of research programmes that will not be the major focus in the future, ensuring that these came to an orderly conclusion or were passed onto other organisations, by mutual agreement. / Impact Weighting (%): 50% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Achievement and Results
1.1 Has the logframe been changed since the last review? N / 1.2 Final Output score and description: A – Outputs met objectives
Direct feedback from beneficiaries / TDR has had a long lasting and substantial impact. TDR beneficiaries are to be found in almost every Ministry of Health or research institution in senior positions. During the restructuring the widespread goodwill generated by TDR was particularly important as difficult funding and staffing decisions had to be made. / I t might have been expected that the significant change in direction would have resulted in criticism by beneficiaries, but this has not happened. There has been widespread support for the changes made and this is positive basis to move forward in the future.
1.4 Overall Outcome score and description: A – Outcome met objectives / 1.5 Impact and Sustainability / Over its 40 year history TDR has built the capacity of individual researchers and clinicians in many different disease endemic countries. Over the years TDR research has filled important gaps and some of these research areas have been taken up by other organisations, to take the lead, for example TDR’s research in product development is now largely under the remit of the PDPs. TDR is changing and filling an important niche on implementation research, along with building on its extensive expertise in capacity development. / After a very difficult period, the programme has been extensively redesigned and is now in a far stronger position to be more sustainable in the future. / Internal collaboration within WHO has been significantly strengthened over the last two years and TDR is has been moved to the HIV/AIDS, Tuberculosis, Malaria and Neglected Tropical Diseases cluster of WHO. This move is already making a difference to the collaborations with the various disease control programmes within WHO.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y / 2.2 Key cost drivers / Key cost drivers include the significant programme staff costs; the appreciation of the Swiss Franc against the US Dollar impacted on the running costs of the programme. The programme contracted during 2012, to reduce staff costs as a proportion of the total spend, and the WHO finance department actively worked to mitigate the impact of the currency fluctuations. With the arrival of the new Director TDR implemented a number of changes to its systems including a more accurate project costing system together with enhanced processes for handling restricted and unrestricted funding and grant reporting, in order to prevent budget overspends. New policies and processes have been developed to ensure effective cost recovery, covering the whole process from proposal development to final reporting. / 2.3 Was the project completed within the expected timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / Not applicable / 3.2 Set out what plans are in place for an evaluation. / Due to the funding challenges experienced during 2010-11 an External Review scheduled for 2012 was brought forward and undertaken in 2011. The lessons and recommendations from the review contributed significantly to the development of a new TDR strategy and new reporting structures to improve efficiencies, and to change the governance structure.

4. Risk
4.1 Risk Rating (overall project risk): High / Did the Risk Rating change over the life of the project? Y / The risk rating was upgraded to High when the funding crisis became apparent in 2010-11. / 4.2 Risk funds not used for purposes intended / This is relatively low risk as the programme follows WHO financial management practices and procedures and the accounts are audited annually by the WHO’s Internal Audit Department. WHO itself, including the special programmes, is audited by external independent auditors. Funding agencies have the right to call for additional external audits if required. / The Joint Coordinating Board (JCB) scrutinises the accounts and audit arrangements in June at its annual meeting. / At country level funds are channelled through the WHO country office and the financial procedures there are subject to the same scrutiny and internal audit as at Head Quarters. / 4.3 Climate and Environment Impact / There are unlikely to be any major negative impacts of this programme though they have had specific work streams on ‘environment and infectious diseases’. This reflects TDR’s understanding of how the environment plays a powerful role in the transmission of infectious diseases, including vector-borne and soil-transmitted infections. Their research not only explores how to improve vector control measures for disease prevention, but also how policies of health, environment and development can be aligned, in this manner having a potentially positive impact on climate and environment. Recent and on-going examples of TDR research and/or publications that might have a positive impact on climate and environment include a project exploring community-based ecosystem and management interventions against Dengue and Chagas disease vectors in Latin America, and another looking at the effect of environmental and climate change on major vectors and vector-borne diseases (this work supports the WHO African Regional Committee for Africa’s Framework for Public Health Adaptation to Climate Change in the Africa Region).

5. Value for Money
5.1 Performance on VfM measures / TDR is a unique organisation, no other organisations have the scope and reach of research partners in developed and disease endemic countries. In addition TDR has a wide range of resource contributors (developed and disease endemic countries (DEC)). TDR is able to carry out a broad base of activities contributing to DFID priority areas. The value for money of the programme is considerably greater than supporting smaller projects commissioned on an individual basis. TDR produces high quality research and trains high class DEC scientists, the results of which have a significant impact on the control of a core set of neglected infectious diseases of poverty and, consequently, for the outcomes of the populations in the poorest countries. / 5.2 Commercial Improvement and Value for Money / TDR has undergone significant restructuring to overcome the financial challenges it has faced. DFID has worked with TDR through its governance structures to ensure its systems are designed to provide value for money. At its meeting in June 2013 the JCB praised TDR and its staff for the manner in which it had successfully overcome the significant challenges, in a relatively short period of time. / 5.3 Role of project partners / TDR has worked closely with the co-sponsoring agencies, chair and vice-chair of the board to develop solutions to the challenges faced during the last few years. The Joint Coordinating Board (JCB) has endorsed the new, realistic, budget and changes to the Governance and accountability of the organisation. TDR has moved from its own, stand-alone, offices to WHO HQ which has allowed far greater integration with the WHO disease departments (neglected tropical diseases, malaria, TB etc). / The TDR JCB, currently Chaired by DFID, encourages all resource contributors and disease endemic country partners to have a strong input to the programme. / DFID has chaired the JCB during the last three years and has played an important role I supporting the structural reforms and the recruitment of the new director. In addition the competent and committed Assistant Director Generals (ADGs), who have overseen the programme, have driven these reforms through WHO and overcome a number of significant internal barriers. / 5.4 Did the project represent Value for Money : Y

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions
The JCB should not have agreed to an aspirational budget with little chance of attainment, given the evolving financial crisis. There are lessons here for DFID and other funders – be much stronger in expressing concerns about over ambitious budgets and ensure that internal structures to monitor new research approvals are closely linked with the availably budgets. / At the end of this five year funding period it is remarkable that TDR has emerged from such a major crisis, not only intact, but actually significantly stronger and more efficient than before. Two years ago there were significant concerns that the special programme would not survive. Now, under the leadership of an effective new director, and strong support from senior WHO managers, the prospects for the future are bright. / It is a credit to TDR staff, past and present, that they continued to produce high quality research findings and publications throughout the funding crisis and at a time of considerable personal uncertainty.

8. Review Process
This review was completed by members of the Human Development Team, Research and Evidence Division. The review used the findings of the external evaluation, discussion with the evaluation team, key documentation produced by TDR, personal contacts with the programme, donor partners and the co-sponsors of the programme together with the discussions and outcomes of the Joint Coordinating Board meeting in June 2013.