Type of Review: Annual Review

Project Title: Bihar Governance & Administrative Reforms Programme

Date started: September 2008	Date review undertaken: Sept 2-3, 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £13 million in financial aid to the Government of Bihar (GoB) to design and implement governance and administrative reforms in two phases of three years each (2008-2014), and £5 million in technical cooperation to procure Technical Assistance to support reforms prioritised by the Government of Bihar.

What are the expected results?
As a result of the programme interventions, the quality of governance will improve in Bihar. This will be reflected in the improved capacity of the government to deliver public services, mobilise more revenue and build institutional capacity. This assessment will be based on independent citizen feedback and other independent sources. / The purpose of the programme is better governance (improved government capability, accountability and responsiveness) enables better delivery of basic services to all its citizens, particularly the poorest and most excluded. / The main programme outputs are: / Improve human resource management by streamlining the recruitment process, training of personnel and their performance appraisal / Enhance the quality of public service delivery by selected departments such as commercial taxes, registration, education, home etc. / Improve service delivery at the frontline level by leveraging information technology and streamlining systems and processes

What is the context in which UK support is provided?
Bihar is one of the poorest states in India, accounting for over 13% of the country’s poor. In 2005, it ranked at the bottom of Indian States for a range of governance indicators including law and order, corruption, legal structure and security of property rights, revenue collection, and investment climate. There are systemic weaknesses such as out-dated administrative functions, poorly managed, demotivated and low skilled workforce with large number of unfilled posts; and weak accountability at all levels. Since 2006, the government of Bihar has demonstrated a real intent to improve governance and there have been significant improvement in law and order, financial management, accountability of public institutions, and delivery of public services. Through this programme, DFID support the Bihar Government to undertake governance reforms for improving its capability to deliver better quality services to all its citizens, particularly the poorest and most excluded. / DFID is providing financial assistance to the Government of Bihar through a dedicated Mission set up for undertaking administrative reforms in the state. This will enable the government to improve its human resource management, develop stronger institutional capacity and enhance quality of public service delivery, particularly at the frontline level. / The technical cooperation funds will be used to contract a technical support team that will provide technical assistance to the Government of Bihar on prioritised reform areas.

## Section A: Detailed Output Scoring

Output 1: Quality of human resource management viz. recruitment, training, performance management is more efficient and effective.
Output 1 score and performance description: B
Progress against expected results: / Indicator: Proportion of vacancies against currently sanctioned strength for Bihar Administrative Service (BAS), Bihar Financial Service (BFS) and Bihar Registration Service (BRS) cadres / Milestone (August 2013): Less than 25% (Baseline ~ 50%) / Based on restructuring of BAS, the entry level of a BAS officer has been upgraded from that of a Block Development Officer (BDO)/ Circle Officer (CO) to Sub-Divisional Officer (SDO) resulting in a surplus of 403 officers as on August 2013 against the new sanctioned strength. GAD has notified 403 positions as floating posts to accommodate the surplus officers. / For the BRS cadre, with the final selection of 56 probationers by BPSC in August 2013 the final vacancies in the Department have reduced to 5%. / For the BFS cadre, though 83 probationers have been finally selected by BSPC (August 2013), due to creation of additional 258 new posts in June 2013, the overall vacancy has increased to 47% compared to that reported in last review. / Therefore, the milestone has been achieved for BAS and BRS and overall, though has not been met for BFS. / Table 1: Sanctioned and filled positions for BAS, BRS and BFS (as on August 2013) / Cadre Sanctioned Strength Posts Filled Vacancies % vacancy Remarks / BAS 1254 (includes 403 ‘floating posts’ created on a temporary basis to accommodate surplus BAS cadre officers) 1235 (including ex-cadre posts for BAS) 19 - / BRS 149 141 / (includes 56 probationers selected by BPSC as per final results declared in August 2013) 8 5% - / BFS 783 414 / (includes 83 probationers selected by BPSC as per final results declared in August 2013) 369 47% 258 new BFS posts sanctioned in June 2013 / Total 2186 1790 396 18% / Indicator: Training of BAS, BFS and BRS Officers / Milestone: All BAS probationers and 40% in-service BAS, BFS and BRS officers given training as per new training plan. / As on August, 2013 the actual strength of BAS cadre is 1235. Of these about 570 officers form the target for in-service training as per the provisions of the new training plan (The new training plan excludes those officers who have crossed 55 years of age. Also the in-service training plan covers only those officers who have completed more than 6 years of service but should not have completed more than 20 years of service). / Till date 165 BAS have received In-service training from reputed institutions in the country as per the new training plan. This forms about 30% of the total target (570). The details of the BAS batches sent for the training are given as follows. / Therefore this milestone has not been achieved. / Table 2: Status of In-service Training for BAS / Sr. Level of Officer No. of officers Institute Period of Training / 1. M1 (6-10 years) 30 Administrative Training Institute, Gurgaon 13.02.2012 to 24.02.2012 / 2. M1 (6-10 years) 25 Administrative Training Institute, Bhopal 21.02.2012 to 03.03.2012 / 3. M2 (11-15 years) 25 Administrative Staff College of India, Hyderabad 01.10.2012 to 12.10.2012 / 4. M2 (11-15 years) 25 Administrative Staff College, VIT, Vellore 03.10.2012 to 20.10.2012 / 5. M2 (11-15 years) 25 Anna Institute of Management, Chennai 03.12.2012 to 19.12.2012 / 6. M2 (11-15 years) 35 Kerala Institute of Local Administration, Thrissur 29.06.2013 to 16.07.2013 / Total 165 / Indicator: Proportion of appraisal reports for BAS officers which are initiated and accepted every year / Milestone (August 2013): 60% of the officers complete self-appraisal using the new PAR form. / This milestone has not been fully achieved. 65% (803/1235) of the officers have completed self-appraisal using the new PAR form (based on information from register maintained by GAD). / The process of performance appraisal has been institutionalized with all the BAS officers required to fill their self-appraisal in PAR formats with the following timelines: / Completion of self-appraisal- By 30th April / Completion of review/ acceptance- By 30th September / Indicator: Establishment of a Centre for Good Governance (CGG) / Milestone (August 2013): CGG staffed and provides technical & research support to GoB departments. / The CGG was constituted by GoB resolution dated 22.11.2011. Its Governing Council (GC) was reconstituted by GoB resolution dated 8.8.2012 and operates out of Lalit Bhavan, Patna. / Total 88 Posts have been sanctioned by Cabinet including 4 management committee members, 30 subject matter experts, 5 administration and finance personnel and 49 support staffs. / Management Committee members in position comprising Director General (Senior IAS officer), Director-Governance (IAS officer). However, further recruitment is yet to be completed. Deputy Director Administration and Deputy Director Finance (both BAS officers). / The first GC meeting was held under the Chairmanship of Chief Minister (CM) on the 22nd of February 2013 to discuss the matters of official business. / Human Resources (HR) Manual, Procurement Manual and Finance & Accounts Manual have been finalized by the Governing Body headed by CM, vetted by the Finance Department, GoB and is awaiting State Cabinet clearance. / Job responsibilities mapped to educational qualifications and work experience have been defined for the created posts approved by Management Committee. / An HR agency has been identified to provide recruitment support for CGG society. / Budgetary provisions in the form of Grant in Aid of Rs. 5 crores for CGG Society has been made under the Departmental Budget (GAD) for FY 2013 -14. / Although progress has been made, the milestone has not been fully achieved. / Recommendations: / GTAST to follow up with GAD on inclusion of BFS/BRS officers in the new training plan. / GoB should accelerate the staffing process and funds allocation for CGG besides setting up mechanism for engagement of CGG with BPSM. / Old performance appraisal system to be phased out immediately with making the new PAR format mandatory / Impact Weighting (%): 30% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N

Output 2: Performance of focal Departments is made more effective, efficient and accountable.
Output 2 score and performance description: A / Progress against expected results: / Indicator: Improved systems for revenue mobilization (Commercial Taxes & Registration Departments) / Milestone (August 2013): Revenues generated by the transport department = 600 Crores / Transport Department recorded a total tax of Rs. 644 in FY 13 (Budget Estimate) (source: Economic Survey of Bihar 2012-13) which accounted for a year on year growth of 13% over FY 12. There were no new intervention for the Transport Department for FY 12 and FY13 but the benefits of earlier reforms continue and this milestone has been achieved. / Milestone (August 2013) Revenue generated by Registration, Excise and Prohibition department = 1700 crores. / The total revenue generated by the Registration, Excise and Prohibition in the review period was Rs. 1782 crores. Therefore this milestone has been achieved. / Our estimate is that a collection of Rs. 330 crore (against the total collection of 1782 crores) can be attributed to the interventions carried out by the GTAST (see table 3). / Table 3: Est. Additional Revenue due to interventions in Commercial Tax Department and Registration, Excise and Prohibition / Department Revenue in FY13 in INR and Growth over FY12 Impact due to interventions Related interventions Additional revenue Generated (INR) in the review period Remarks / Registration 918 crores for period April 2013 till July 2013 / Growth of 49% (Rs. 616 crores for the corresponding period of FY12) 94% Comparative study of Registration Fees and Duties in select Indian states 280 crores Since the stamp duties were revised in February 2013, the impact has been mapped since March 2013 till July 2013 / Excise 864 crores for the period April 2013 till July 2013. Growth of 44% (Rs. 599 crores for the corresponding period of FY12) 19% Comparative study of Excise Duties in select Indian states 50 crores Since the excise duty revision was brought into effect from January 2013 and the impact was assessed from April 2013 till July 2103 / Registration, Excise & Prohibition Dept. sub-total 330 crores / Milestone (August 2013): No. of registered dealers reaches 250000. / No. of registered dealers in FY12 (191,967 dealers) has increased by 19.4% over FY11 (160,777 dealers) but the milestone has not been achieved. / Technical inputs leading amendment of Central Sales Tax (Bihar) Rules, 1957 in December 2012, facilitating online issuance of statutory forms. Presently more than 11000 existing dealers are being benefited by this intervention. / Department Revenue in FY13 in INR and Growth over FY12 Impact due to interventions Related interventions Additional revenue generated (INR) in the review period Remarks / Commercial Tax 10,910 crores / Growth of 29% (Rs. 8,458 crores) over FY12 20.4% Enactment of “The Bihar Tax on Professions, Trades, Callings and Employments Act, 2011”. 40 crores The impact was directly for BGARP intervention for the period of FY13. / Streamlining of check-post management practices. 460 crores This intervention also includes augmentation of infrastructure at the check-posts by the department and implementation of check-post management system. / Grand total Rs. 500 crore / Milestone (August 2013): 50% of the Registration records digitised (Registration Dept) / Till date, out of 7.2 million documents which needed to be digitized, 1.52 million documents have been scanned across all the districts in the state. This accounts for about 50% of the target until August 2013. Therefore this milestone has not been achieved. / Note: Till June 2013, Rs. 38.43 million was spent from FA funds on digitization initiative primarily in the Patna district. GoB has since then been financing the initiative across the state including the additional costs needed for the Patna office. / Indicator: Creating a more sensitized and citizen friendly police force. / Milestone (August 2013): 30% of police personnel trained by master trainers across the state. / Total 120 Master trainers have been trained from April to July 2012. / Till date around 4000 police personnel were trained by the Master Trainers out of total 50000 (of which about 10000 personnel are expected to join the force in 2013) target personnel (Sub Inspectors and Constable) on citizen centric policing across the state. There was positive feedback from the trainees regarding the courses and the training imparted based on letter from the Assistant Director, Bihar Police Academy on January, 2013. The Training were held across all 38 districts of the state. / Currently the training process has slowed down due to change of senior staff at the leadership level (Director, Bihar Police Academy) and the prioritization of ongoing National Disaster management Training. Therefore the milestone has not been achieved. / Note: DFID support was to the extent of about INR 16 lakhs under TA under which Training of the Master Trainers under ToT mode was held. The rest of the training are being conducted by the Bihar police with the infrastructure and logistics support provided by the District SP office. / Indicator: Strengthening of Prisons in Bihar. / Milestone (August 2013): Prison Manual implemented across prisons in Bihar. / As a part of the intervention, the project reviewed the earlier jail manual (last revised in 1914) based on the review of prison manuals from select state like Haryana, Kerala, West Bengal and the model prison manual prescribed by Bureau of Police Research and Development (BPR&D). / New prison manual is accepted by Cabinet on December 2012 and its provision implemented across 57 prisons in Bihar. Therefore this milestone has been achieved. / Jail inspectorate renamed as Inspectorate of Prisons and Correctional Administrations. / A one-day sensitization cum training workshop on the new provisions of the Jail Manual conducted by GTAST was attended by around 100 officers & IG, Prisons himself. / Prison Management System, Visitor Management system, Prison ERP already implemented in Beur Model Central Prison, as per the provision of the Manual to include computerization of key processes- to be rolled out across all the prisons of Bihar. / New recruitment is in progress for Prison inspectorate which includes the following: / 10 Prison Superintendents (currently undergoing training in BIPARD). / 55 Probation officers (currently undergoing training in BIPARD). / 46 Assistant Superintendents (from Ex-service and home guards). / 1500 warders (currently physical examinations underway). / 70 dressers. / Recommendations: / Delivery of training on citizen centric policing need to be focused in one district (Nalanda) for systematic study on outcomes and mechanisms for its replication in other districts. / Aligning to the GoB’s decision to induct about 35% women in police force, their training need analysis and strategy for training should be taken up. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3: Strengthened district level administration and service delivery.
Output 3 score and performance description: A
Progress against expected results: / Indicator: Quality of service delivery at district & sub-district level and its effective monitoring / Milestone: Effective implementation of Right to Public Services Act (RtPS) and its monitoring; / RTPS implementation has continued at scale, with additional performance improvements. Therefore this milestone has been achieved. / Status of application for services & their disposal under RTPS improved from 95% in last year to 97.5% this year. / Table 4: Status of Application received under RTPS and their disposal / Period Total Applications Received (Million) Total Disposal of Applications (Million) Percent of Applications disposed / 15 August, 2011 to 15 August, 2012 19.5 18.6 95% / 16 August,2012 to 15 August, 2013 30.1 29.7 97.5% / There was an improvement in infrastructure support for RTPS implementation which included: / citizens amenities such as counters, sun-sheds for citizens queuing up and designated waiting places. / Display boards relating to services under RTPS as per the provisions of the Act. / Table 5: Extent of citizen friendly amenities set up at RTPS application counters / %age of offices where counters have been constructed %age of offices where information regarding RTPS act written on the wall/ Board %age of offices where shed are available for queue people %age of offices where waiting place for Applicants are available. / As on 15th August, 2012 100% 100% 81% 64% / As on 15th August, 2013 100% 100% 99% 99% / Two more services were included under RTPS: / National Family Benefit Scheme / Kanya Vivaha Labh Yojana / High level of citizen satisfaction was reported in the large scale user feedback survey with about 80% of the respondents expressing their satisfaction in case of some of the services based on a survey of applicants in a block in Nalanda carried out in December 2011. / Simplification & improvement in application for character certificates which included: / self-declaration instead of notarised affidavit. / limiting to only one copy of application in place of three as was the practice earlier. / withdrawal of application fees of Rs. 10 in case of character certificates. / Reduction in stipulated time period for delivering services such as certificates reduced from 21 days to 14 days. / Draft report on audit of back-end processes developed and findings discussed with the then MD, BPSM. / Indicator: Quality of Grievance Redressal. / Milestone (End of Term): Review of system undertaken and changes effected / Detailed assessment of public grievances received in Nalanda District Collectorate Janta Darbar in FY13 was undertaken for 3600 public grievances / Table 6: Typology of Grievances received at Nalanda Collectorate in FY 13 / The Public Grievance Cell office arrangement has been reogranised making it more comfortable for the personnel in terms of space for walking, lighting of the cell etc. / The Nalanda Collectorate and GAD has agreed on the recommendation treating Public Grievances similar to a service under RTPS in terms of fixed timelines and responsible personnel. / GTAST to work with Nalanda collectorate for developing an application software for receiving the application and streamlining the process. / Indicator: Implementation of Reform Strategy for Collectorate Modernisation / Milestone (End of Term): Reforms rolled out across all Collectorates. / The Inception Report on Strengthening District Administration has been submitted in the month of May 2013. / An initiative was undertaken to re-organize the Establishment Section on the May 2013 to provide for better working arrangements for the staff, while at the same time improve access to citizens. Preliminary results show that the initiative has yielded positive results. / Three application software prototype namely 1) Retirement Benefit System 2) court Case Management System and 3) Scheme Monitoring System ready for deployment in the Nalanda Collectorate. / Draft presentation highlighting key findings and suggestions/recommendations has been made before the officials of Nalanda district in joint presence of the incumbent and new DMs (District Collectors) and other senior officials on 29th August, 2012. / The recommendations have been categorized in to short term, intermediate and long term. / Implementation of applications for speeding back office operations like retirement benefit calculator etc to begin immediately. / Categorisation and classification of communication received at collectorate would begin immediately in September second week. / Design of front office and standardized application forms for services received from the collectorate would begin from September. / Implementation of Information management system from October. / Implementation of new structure and delegation of powers from October. / Functioning of new front office and restructured centralized receipt and distribution centre from November-December 2013. / Recommendations: / The software proto types for Nalanda Collectorate needs to be implemented and the outcome be tracked. / There is a need to review the current system of file movements from the Collectorate to sub-district level functionaries to devise mechanisms for systemic efficiency. / Unreliable grid electricity was observed to be an impediment in smooth delivery public services in Nalanda district. There is a need to explore possibilities for introducing renewable energy based power generation system in the district headquarters. / Impact Weighting (%): 40% / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? / Yes. The logframe has been updated to reflect new initiatives and some revised milestones. / 1.2 Overall Output Score and Description: A / Overall, it is observed that the outputs have almost met the expectation. The major achievements have been in the reforms around delivery of public services, training of BAS cadre, and improvements in revenue collection. The outputs that have moderately underachieved include operationalization of CGG, roll out of Maitri training across the state using the master trainers’, and training of BRS and BFS cadre staff. / Since in majority of indicators the outputs have met the expectation (7 indicators) and a few outputs have moderately underachieved (3 indicators), therefore, the overall scoring is A. / 1.3 Direct feedback from beneficiaries / A large scale citizen survey was undertaken in 2012 to assess citizen feedback on quality of service delivery for a range of services. This survey covered 31,556 households across all 534 blocks in rural Bihar. The findings of the survey indicate that more than three-fourth of the respondents were satisfied with 5 of the 8 public services viz., Pensions, Health Facilities, Certificates and Ration Shops. For two more services viz., Schools and Anganwadis, three quarters of the respondents were satisfied with the service delivered. / Direct feedback from citizens was also obtained during the annual review. Separately, feedback was also obtained from beneficiaries by the technical assistance team which undertook a study to assess implementation of RTPS.
1.4 Summary of overall progress / The programme has completed five years and has achieved significant results. It has been able to deliver effectively on all the three outputs. / On the first output that pertains to institutional development and capacity building, the programme in its fifth year has provided support for the establishment of the CGG and operationalization of the state training policy. Further it has also facilitated the state on implementing a number of initiatives as recommended by the 2nd Administrative Reforms Commission. These are important reforms, though have taken longer than was originally envisaged and they need to be embedded. For example, the CGG will only deliver the role envisaged for it in the project design when it is staffed. / Under the second output, there has been a focused engagement with the select partner departments who demonstrated considerable appetite for reforms. This includes departments of Registration, Excise, Commercial Taxes and Home / Police/ Prison. With RTPS, these are the most significant (and potentially transformational) results that have been achieved under the project. / Based on the opportunities identified in the last review vis-à-vis the frontline- the districts, a number of studies related to effectiveness of RTPS implementation were conducted. District & block study was initiated for the pilot district of Nalanda which is in the final stages of completion. This is significant but implementation has taken far long than was originally planned. The findings of the citizen report card was also shared with the media and public and subsequently a dashboard was developed which is in the process of being incorporated across the state. / At the institutional level, the programme has reinforced the role of Bihar Prashasnik Sudhar Mission (BPSM) as the nodal agency for governance reforms in Bihar. / The programme has also supported policy development in critical areas. This includes the State Training Policy, change in Registration fees, Stamp duties, excise rates as well as process of fixing MVR. / The revised Prison Manual has been approved by the state cabinet and has been brought into force.
1.5 Key challenges / A key challenge facing an aspect of the programme related to CGG is the need for more permanency regarding the top management of CGG. This further gets accentuated by the lack of operational manpower who are yet to be recruited. / Another key challenge is to ensure an holistic approach to reforms encompassing various arms of the Government such as imbibing the Administrative Reforms framework. / The third key challenge pertains to the regular transfers of key officials in partner departments, which often results in changing priorities. Stronger and direct engagement with partner departments/officials will be necessary to maintain consistency in reform priorities as well as to create demand for wider reforms. / Strengthening the capacity of the nodal agency, BPSM, to manage the wide portfolio of interventions is also a challenge
1.6 Annual Outcome Assessment / The project is by and large on track on majority of indicators, thus, also in its goal and purpose. Significant improvements have been noticed in the areas of / revenue collection, / delivery of public services under RTPS, and / implementation of prison reforms / However, there has been slow progress against some indicators such as training of the police personnel on citizen centric policing and operationalization of CGG. Limited progress on these two areas could be attributed to frequent changes in senior officials and unexpected delays in approval processes.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The overall budget of the programme is £18.00 million (£13.00 million FA and £5.00 million TA) over a period of 6 years. By June 2013, the programme had spent FA of £7.7 million and TA of £5 million (including £0.6 million for Bihar Language Initiative for Secondary Schools). / 2.2 Key cost drivers / The Governance and Administration Department (GAD), Government of Bihar (GoB) is the key cost driver of the programme. The Governing Council, chaired by the Chief Secretary, along with representation by DFID and other spending departments approves all expenditure at the beginning of the financial year and disburse allocation to various departments. DFID’s contribution is reimbursed on submission of expenditure statement and claimed bi-annually. The details of the FA spending is presented as follows: / Sr. No. Department FA Allotment in INR Lakhs Expenditure till June 2013 in INR Lakhs / FY10 FY11 FY12 FY13 Total / 1. GAD, BPSMS & Capacity Building 571.90 1,517.14 1,555.90 2700.00 6,347.17 5,358.10 / 2. BIPARD - - 111.60 111.6 109.80 / 3. BPSC - 17.00 30.00 47 38.95 / 4. F&CP - - 52.50 52.5 52.50 / 5. Registration 448.00 - - 448 384.43 / 6. CTD 75.10 - - 75.1 73.72 / 7. Transport 180.00 - - 180 180.00 / 8. Education 300.00 600.00 - 900 684.25 / 9. IT - 138.00 - 138 138.00 / 10. SC ST Welfare - 2.86 - 0.63 0.63 / 11. Home - 25.00 - 25 22.75 / Grand Total 1,575.00 2,300.00 1,750.00 2700.00 8,325.00 7043.13 / TC funds are spent directly by DFID. These funds are used to procure staff/consultants, provision of training and contribute to running costs of the GTAST. DFID reimburses GTAST expenditure following the submission of quarterly invoices using standard agreed procedures. / 2.3 Is the project on-track against original timescale: Yes / The programme is in the final year (6th) year of DFID support and has achieved significant results. The programme will end on 30 June 2014. The annual review mission has done an assessment of overall performance of DFID supported interventions against all three outputs and identified areas that need more focused engagement from GoB and GTAST to achieve targeted results between now and end of the project. A list of key action points for GoB, GTAST and DFID project team is drawn with target dates and shared with all parties. DFID project team will monitor the progress on a regular basis.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There are 3 areas where we see emerging evidence which could have significant implications for the programme. / With the RtPS completing its 2nd year, there has been more than 54% increase in the volume of applications. Thus, there is a need for increased manpower support, capacity building of the same as well as further streamlining of the back-end processes ensuring reliability in service delivery. Further, it is important to analyse the base data to ascertain the extent to which RtPS improved service delivery to the citizen / There is a need to evaluate the impact of police training (Maitri) to understand the shifts in attitudes and behaviour of the police personnel. Further, integration of global best practices in citizen centric policing into the training processes could be attempted. / A quantum surge in revenue collection by the Commercial Tax and Excise, Revenue and Prohibition Departments. In the coming months, the extent to which BGARP interventions have led to surge in revenue collection needs to be studied and documented. / 3.2 Where an evaluation is planned what progress has been made? / The planned Citizen survey was completed in September 2012 covering around 32,000 households all across the state. The key findings have been publicly released in December 2012 following which a dashboard has been developed for better monitoring of various service delivery parameters and assessing citizen satisfaction on the same. The dashboard is to be shared shortly with the GoB for roll out and state-wide usage.

4. Risk
4.1 Output Risk Rating: Low/Medium / The programme is judged to be of low to medium risk with the potential of high return. / 4.2 Assessment of the risk level / There are two key risks. / One, we may miss attaining some indicators by the end of the project i.e. training of the police personnel on citizen centric policing and bringing other cadre personnel (BRS and BFS) under the fold of new training framework. / The second one is staffing and operationalization of CGG by the end of the project.
Risk of funds not being used as intended / The risk of funds not being used as intended is low. Approval for each spending proposal is given by the Governing Council, which is chaired by the Chief Secretary and its members include Principal Secretaries of all partner departments. DFID is a special invitee at the Governing Council meetings and is party to approval of each spending proposal. / DFID financial assistance is provided to BPSM on a reimbursable basis. Departments and districts submit utilisation certificates before the release of next tranche of funds. Audit of project funds for FY12 has been prepared and submitted. / 4.4 Climate and Environment Risk / The climate & environmental risk is judged to be low for the programme.

5. Value for Money
5.1 Performance on VfM measures / 5.1.1 Interventions in improving implementation of Right to Public Services Act, 2011 / A cost-benefit analysis of RtPS was done by GTAST in the month of August 2013. The benefits that were monetised include / time & labour savings for beneficiaries as s/he no longer needs to make multiple trips. / travel & other expenses saving by beneficiaries. / Savings from reduction in rent-seeking avenues due to ease of and transparent application process.. / The costs that were taken into account include / HR costs for staff deployed in districts & blocks. / Cost of providing uninterrupted power supply through Diesel Generator back up. / Contingency expenses on stationery, print cartridges, etc in field offices (RTPS counters in Block/ Circle) for which specific provision have been made. / Two different calculations were done – (a) costs & benefits for the last year and (b) potential benefits of delivery through Vasudha Kendras. / Against a cost of estimated Rs. 43 crore (£ 5 m), actual benefits are monetised to be Rs. 1170 crores (£ 13.7 m) for the period September 2012 to August 2013 (including savings due to not paying of bribes). It may be noted that DFID’s share accounted for 28% of total cost (Rs 12 crore). / Vasudha Kendra Potential: If the issuance of caste, income and residential certificates could be done through Vasudha Kendras (village level common service centres), the benefits could potentially be Rs. 1410 crores (£ 16.58 m) every year, assuming all the certificates are issued from Vasudha Kendras, translating into further saving in time and money for the applicant, who have to travel up to one such Kendra located in his/her panchayat. / There have also been significant efficiency improvements in the service delivery process in the last year. These include: / Further reduction in time period for services such as Certificates, which constitute the bulk of the demand for services. / Further improvement in amenities for citizens at the RTPS counters in terms of sheds, seating arrangements (coverage of 99% of RTPS counters from 81% coverage as recorded in August 2012). / Inclusion of two more services namely 1) National Family Benefit Plan, 2) Mukhyamantri Kanya Vivah yojana vide notification on January, 2013. / 5.1.2 Interventions for Commercial Tax Department / The two key intervention carried out for the Commercial tax department in the current review period were / Technical inputs leading to the enactment and implementation of “The Bihar Tax on Professions, Trades, Callings and Employments Act, 2011” / Head Amount Remarks / Benefit to state in terms of additional revenue / (Details provided by Commercial Tax Department) INR 75 Crores Collection of professional tax in the Review period / Cost equivalent of Efforts GBP 9,500 Total 40 Man-days / Streamlining of check-post management practices through inputs in: / Formulation of Integrated Check-post Authority Act & Rules / Strengthening the check-post management system / Head Amount Remarks / Cumulative benefit to state due to reduction of leakage at checkposts owing to improved integrated infrastructure and increase in collection due to streamlining of the check-post management practices / (Details provided by Commercial Tax Department) INR 460 Crores Growth in checkpost collection in FY 13 over and above the CAGR of 23.5% (for period FY08 to FY12) has been attributed to the efficient check-post management practices. / Cost equivalent of Efforts GBP 53,500 Includes about 5 Man-months effort and expenses due to study visits to Andhra Pradesh and Karnataka / 5.1.3 Interventions for Department for Registration, Excise and Prohibition / A. Registration: / The Stamp Duties in the state were revised based on the findings and recommendations by GTAST of a comparative study of registration fees and Stamp duties in select Indian states. The revised stamp duties were brought into effect from February 2013. The direct benefit was in terms of increase in revenue. The method of arriving at the quantum of increase in revenue due to the increase in stamp duty is given below: / The average revenue/ deed for the FY12, FY13 and FY14 (April, May, June & July) is given in the table below: / Period Average Revenue/ deed registered (INR) Growth Remarks / 2011-2012 13,645 - / 2012-2013 14,612 7% Natural growth of 7% / 2013-2014 22,642 55% Additional Increase in average revenue/ deed of around Rs. 6,995 in FY14 over that in FY13 attributed to the revised stamp duty rates / It is observed that at a regular growth of 7% (realized in FY13 over FY12), the Department would have realized revenue/ deed of around Rs. 15,647. / Benefit: Considering the total number of deeds registered over the period April till July 2013, the increase in revenue/ deed amounts to Rs. 284 crores (£ 33.41 m). / Effort: Total 4 Man-month of effort translating into cost of GBP 13,500. / B. Excise / The excise duty structures in the state were revised based on the initiatives of (i) Comparative study of excise duties and levies in select Indian states and (ii) Impact Assessment of revision of excise duties and levies. The new rates were brought into force since the 23rd January 2013. The direct benefit was in terms of increase in revenue. / The average revenue/ LPL (London proof Litre) of consumption for the last 3 years for the period of April till July are given below: / Period Revenue/ LPL of consumption in INR Growth / 2011-2012 339.84 / 2012-2013 426.72 26% / 2013-2014 569.93 33% / As is observed from the above table, considering a growth of 26% Y-o-Y in revenue/ consumption in FY14, the Department would have realized a revenue/ LPL consumption of Rs. 535. / Due to the revision of the excise duties in the state, the Department was able to increase its revenue realization by around Rs. 33.82 per LPL of consumption (accounting for a spurt in growth by about 7%) / Benefit: Considering the consumption for the period of April 2013 till July 2013, the increase in revenue of INR 51.32 crores (£ 6 m) due to additional increase in growth. / Effort: Total 5 Man-month of effort translating into cost of GBP 16,700 / 5.2 Commercial Improvement and Value for Money / To ensure commercial improvement and better value for money, DFID programme team regularly review performance of the Governance Technical Assistance Support Team (GTAST), whom DFID had directly procured through OJEU process at the start of the programme in 2009. GTAST’s contract also reviewed and extended twice after ensuring satisfactory performance for the previous periods. PrG team conducted an audit of third party procurement done by GTAST and ensured that they followed DFID agreed procurement procedures and made recommendations for further improvement. DFID programme team visited the interventions frequently and ensured the resources deployed are with right skills and as per the contractual agreement. GTAST fees and expenditures are reimbursed on a quarterly basis on receipt of satisfactory performance reports and detailed expenditure statement. DFID programme team maintains spread-sheet to monitor number input days and agreed fee rates of GTAST team. / All expenditures under FA are managed by the Bihar Prashasnik Sudhar Mission (BPSM) under the leadership of the Principal Secretary, Governance and Administration Department (GAD), Government of Bihar. FA allocation to other departments is based on annual work plan approved by the governing council. The governing council chaired by the Chief Secretary, Government of Bihar reviews all request for FA funds and disallows expenditure items which are not covered within the scope of BGARP. BPSM had carried out audit of FA expenditure for the financial year 2009-10, 2010-11, and 2011-12 and reports were submitted to DFID. The audit for financial year 2012-13 is underway and the report is due in October 2013. / 5.3 Role of project partners / DFID is the sole donor for the BGARP intervention. Principal partners are the Mission Directorate for coordination and leading government-wide reform, the General Administration Department (GAD), and line Departments identified for service delivery improvements. The Mission Directorate (MD), led by the Principal Secretary, GAD, is responsible for implementation of the programme and eventually overseeing other governance reforms to ensure coherence and co-ordination. / The Technical Support Agency (GTAST) provides consultancy support to the MD and help identify and procure specific expertise needed to achieve outputs and goals / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take? N/A

6. Conditionality
6.1 Update on specific conditions / DFID’s support is based on a shared commitment to three objectives of reducing poverty, respecting human rights and strengthening financial management & accountability. GoB continues to show strong commitment to poverty reduction, human rights and financial accountability issues.

7. Conclusions and actions
BGARP is on track to achieving its goal and purpose. The programme has contributed to the positive governance agenda of the State Government. It has delivered effectively against strengthening systems and service delivery in partner departments and improving delivery of services at the frontline level; but could have done better in the area of improving human resource management during the reporting period. The programme will end on 30 June 2014. DFID will conduct an independent evaluation of the overall achievement of the programme which will inform the preparations for the next phase of the programme. / The key action points emerged from the annual review are: / Department of Home / The on-going work on weeding of old records in the Home Department needs to be completed by June 2014. GTAST to review the progress and recommend options for fast tracking the process (October 2013). / The newly introduced industries in prison do not have participation of women prisoners. There is a potential to leverage support from JEEVIKA (World Bank supported women’s empowerment project in Bihar) for involving women prisoners in entrepreneurial activities. GTAST to facilitate coordination between JEEVIKA and Home department (December 2013). / GTAST to initiate a training need analysis and strategy for the women police personnel (about 37% of the total police strength in Bihar) by January 2013 / The department, with support from GTAST, will design a training module for the newly recruited Jail officials and implement the training by end June 2014. GTAST team to finalise a training plan, support in developing training module on new prison manual and other relevant areas (February 2014). / DFID to commission an impact assessment of Police Training “Maitri” and take necessary steps to roll out the training to all policemen in all districts by end June 2014. GTAST to facilitate fast tracking the roll out of training (February 2013) / Home department to initiate work on modernization of kitchens with improved infrastructure and hygiene facilities in Jails. GTAST to provide necessary support to inspectorate (March 2014) / GTAST to prepare an action plan for the design and implementation of staff Annual Confidential Reports online through email for cadres of both Indian Police Service and Bihar Police Service personnel. GTAST to develop an action plan in consultation with the Home department subject to acceptance by Police Department (April 2013) / DFID and GTAST to write to Home Secretary, proposing potential areas of common interest for further TA support and other activities before the end of the current project as part of a future DFID support package. We discussed common interests in offering peer learning and potential learning visits to the UK in the area of ‘social legislation and its implementation such as multi agency approaches (e.g. police, social workers, other agencies) to prevention, monitoring, and response to problems such as trafficking, destitution, integrated alcohol and drugs policy, gender sensitive policing, and preventing and responding to violence against women. / District Reforms / DFID TA team to review the current system of file movements from District headquarters to Block and Panchayat level for various verifications and approvals and come up with a recommendation and suitable software for simplifying the following processes: / separation of front office and back office functions (November 2013) / delegation of powers to sub-collectors and other middle level officers in order to reduce burden of all communication routed through the DM (October 2013) / capacity building of staff at district including provision for training staff at DM’s office (February 2014) / Action – GTAST to do a presentation to the Principal Secretary, GAD and the District Collector the softer from Service Plus for their consideration (October 2013). / Bihar Prashasnik Sudhar Mission (BPSM) Director may review recommendation of the renewable energy study and actively consider potential for piloting this on appropriate scale. GTAST to make a presentation of the study report before the Department (October 2013) / GAD / Department to play an active role of spearheading the implementation of the State Training Policy. GTAST to provide necessary support to expedite the implementation of the State Training Policy (January 2014). / GTAST to review the current practices on service delivery citizens, identify scope for further improvement and support the department in framing policies (January 2014) / Findings from the Citizen Survey on quality of delivery of public services conducted by DFID to be shared with the Principal Secretary, GAD, Principal Secretaries of identified departments, and Collectors of all Districts. DFID to discuss with Principal Secretary GAD the need for repeating the review on a regular basis. GTAST to make a presentation on the findings of citizens survey before the department (September 2013) / Implementation of Benefit Retirement System within GAD for use relating to caders such as Bihar Administrative Services, Bihar Secretariat Services and Bihar Steno Services. (GTAST to deploy and test run the software application with the Department (December 2014) / Industries / DFID will share Orissa experience on skill development with Industries Department, especially on facilitating third party certification and placement assistance, by October 2013. / GTAST to identify, document and share best practices in land acquisition for industrial development with Industries department by January 2014. / Commercial Tax Department / 1. GTAST to produce a “so what” story to communicate the impact of commercial tax reforms supported under the project. DFID to follow up with GTAST to quantify TA inputs and tax collection outputs, including estimate of attribution/contribution to increases in revenue.

8. Review Process
The annual review of BGARP was carried out during 2-3 September 2013. On the first day, DFID team along with the TA team visited Nalanda district of Bihar, reviewed progress of the RTPs service delivery functions, progress of district reform initiatives and held meetings with the District Magistrate and Collector. Second day the team visited the Beur Model Central Prison and reviewed the progress on modernisation of prison and training delivered to prison staff, reviewed the support provided by TA agency, and held meetings with Principal Secretaries of various departments responsible for the implementation and monitoring of the programme. The findings of the review and recommendations were discussed with the Mission Director of BPSM.