BGARP - Revised Logical Framework
	GOAL	Indicator	Baseline					MTR (Sep 2011)		EoP (Jun 2014)		Assumptions
	Fewer people live in poverty in Bihar	G 1. Per cent of households living below poverty line (BPL)	54% (2004-05)					-2%		-5%		GoB committed to achieve MDGs and significantly improve access and quality of basic services for the poor. / Strong political support for improved service delivery is sustained through programme period, including through and after state elections.
			Source
			National Sample Survey Organisation (NSSO) reports / Economic surveys estimates / GoB estimates
		Indicator	Baseline (2008)				Sep 2009	MTR (Sep 2011)		EoP (Jun 2014)
		G 2. Development Index[1]	0.8				1.2 / (Achieved - 1.1)	1.5		2.0
			Source
			State of the States – India Today
	PURPOSE	Indicator		Baseline (2009)		Sep 2010		MTR (Sep 2011)		EoP (Jun 2014)		Assumptions
	Better governance (improved government capability, accountability and responsiveness) enables better delivery of basic services to all its citizens, particularly the poorest and most excluded.	P 1. Quality of Service Delivery – Citizen satisfaction		To be determined				+10%		+20%		GoB commitment to enabling reforms, increase capability of Govt staff and is accompanied by improvement in processes and decision making systems within government.
				Source
				State of the States – India Today / Citizen Report Cards
		P 2. Own Tax to GSDP Ratio		4.84%		5%		5.5		6.5%
				Source
				GoB Annual Budget Documents
		DFID (FTEs) / 0.25 FTE (Task Team Leader) / 0.10 FTE (Senior Deputy Programme Manager) / 0.05 FTE (Senior Governance Advisor) / 0.05 FTE (Economic Adviser)

INPUTS (£)		DFID (£)			Govt (£)		Other (£)		Total (£)		DFID SHARE (%)
		18 million							18 million		100%
[1] This is a composite index that captures development on 8 dimensions – agriculture, primary health, primary education, investment environment, infrastructure, law & order, macro economy & consumer markets.

OUTPUT 1	Indicator	Baseline		End of Y2 (Sep 2010)	MTR (Sep 2011)	Sep 2013	EoP (Jun 2014)		Assumptions
Quality of human resource management viz. recruitment, training, performance management is more efficient and effective	(a) Proportion of vacancies against currently sanctioned strength for Bihar Administrative Service (BAS), Bihar Financial Service (BFS) and Bihar Revenue Service (BRS) cadres	~ 50% / (1471/2800) / No organised personnel database for BAS officers		Less than 45% / Development of HR database initiated	Less than 40% / HR database of BAS Officers completed	Less than 25%	Less than 10%		Broad political consensus for reform. / GoB continues to stay committed to undertaking administrative reforms. / Tenure of key GoB counterparts is stable. / World Bank supported DPL enables financial and administrative reforms and complements reforms under BGARP / GoB ensures restructuring of BAS by delinking revenue and RD cadres at the entry level / DPAR adopts the reform action plan and implements it in a timely manner / Strong political and administrative ownership of CGG; CGG enabled to take forward the BPSM agenda.
	(b) Training of BAS, BFS and BRS Officers	No structured GoB Training policy / plan		Comprehensive training plan developed for probationers and in-service BAS officers	All BAS probationers and / 40% in-service BAS, BFS and BRS officers given training as per new training plan / 50% of the reporting officers mention better on-the-job performance by trained officers / 50% of the trained officers mention improved capacity & skills due to training	148 BAS probationers (48th to 52nd Batch) and in-service training of 165 BAS officers (13% of total BAS officers) completed as per new training plan	All BAS probationers and / 80% in-service BAS, BFS and BRS officers given training as per new training plan / 75% of the reporting officers mention better on-the-job performance by trained officers / 75% of the trained officers mention improved capacity & skills due to training
	(c) Proportion of appraisal reports for BAS officers which are initiated and accepted every year	5-10%		20%	40%	60%	80%
	(d) Establishment of a Centre for Good Governance	No CGG in existence	Approval of Concept Paper & Constitution of Board			CGG staffed & operationalised		CGG provides technical & research support to GoB depts

Source
Relevant Notifications/ Circulars and Government Orders / Quarterly/ Monthly Report of GTAST approved by GoB / Validation through DPAR/ external agencies / Functional Review Report / Third party survey regarding the implementation / BAS training calendar; Reports from BIPARD / Survey of trained and reporting officers

IMPACT WEIGHTING	DFID (£)	Govt (£)	End of Y2 (Sep 2010)	MTR (Sep 2011)		EoP (Jun 2014)
40%
INPUTS (£)

Output 2	Indicator	Baseline	End of Y2 (Sep 2010)		MTR (Sep 2011)		Sep 2013		EoP (Jun 2014)		Assumptions
Performance of focal Departments is made more effective, efficient and accountable	Systems for enhancement of Tax Revenue / (a) No. of registered dealers (CTD) / (b Transport Tax generated (Transport department) / (c) Digitisation of Registration records (Registration Dept) / (d) Revenue generated by Registration, Excise and Prohibition Department	150000 / Rs. 303 Crores / No digitisation of records / Rs. 694 crores	175000 / Rs. 400 Crores / Completed in 2 pilot registration districts / Rs. 1150 Crores		200000 / Rs. 500 Crores / Digitisation extended to 10 districts / Rs. 1646 crores		250000 / Rs. 600 Crores / 21% of documents scanned across all districts / Rs.1700 crores		300000 / Rs. 700 Crores / Completed in all registration districts / Rs. 1900 crores		Focal Departments have stable leadership and build capacity to drive identified reform initiatives. / Priority reforms in each of the focal departments are identified and implemented. / Other Departments will be taken on board as and when they are included within scope of programme – specific indicators for each department will be identified and monitored. / Climate change initiatives separately taken up in consultation with concerned departments.
	Delivery of social sector services / (a) Online monitoring Systems in Education Dept. / (b) ) Sensitisation of police workforce	Manual reporting system for adult literacy programme	Information system developed and operationalised		Institutionalisation of the Information system / No Police personnel Trainined		2.47 crs Household survey data uploaded to map literacy status / 4000 personnel trained		Monitoring of centrally-sponsored adult literacy programme / 5000 personnel Trained
	Partner Departments are more efficient / Time taken for receiving monthly data from the districts						5-7 days
	Increase in number of SIPB application made						417 (FY 13)
	Number of cases where NHRC or BHRC has summoned Sr. Officers of GoB						3
	Amount of space freed up due to classification of files and moving them to the record room						32000 files categorised (about 50% of total files) freeing up upto 52 square meters (18 Cubic Mtrs)
	Number of Personnel training on the revised Manual						All Supdt., dy Supdt and Asst. Supdt (totaling 100)
		Source
		GTAST Quarterly Reports / Departmental Orders and Records / Annual reviews and project completion report / BPSM reports / Citizen/Client Surveys
IMPACT WEIGHTING	DFID (£)	Govt (£)		End of Y2 (Sep 2010)		MTR (Sep 2011)				EoP (Jun 2014)
30%
INPUTS (£)

Output 3	Indicator	Baseline		End of Y2 (Sep 2010)	MTR (Sep 2011)		Sep 2013		EoP (Jun 2014)		Assumptions
Strengthened district level administration and service delivery	(a) Monitoring of social sector and welfare schemes & services	Manual system in place		MIS for monitoring key programmes and schemes implemented	MIS institutionalised along with data validation / First round of Citizen Report Card (CRC) initiated		MIS for Monitoring scheme developed (to be implemented) / CRC survey completed; report and dashboard shared with GAD		Review of M&E system undertaken and changes effected / Final (3rd) round of Citizen Report Card (CRC) completed		State level authority coordinates & monitors district reform initiatives / Sustained support for government-wide M&E and grievance redressal mechanisms / Collectorates have stable and reform-oriented leadership / Strengthening of district administration by BGARP is complemented by necessary devolution of admin powers and responsibilities to these levels. / Commitment by GoB for undertaking regular citizen surveys
	(b) Quality of Grievance Redressal	Manual system for grievance redressal		Call centre for grievance redressal system implemented	Analysis of quality of grievance redressal undertaken		Public Grievance analysis for Nalanda District done		Review of system undertaken and changes effected
	(c) Implementation of Reforms in District Collectorates[2]	Functional Review completed & Reform Action Plan finalised		Reforms implemented in one Collectorate	Reforms implemented in at least five Collectorates		Reforms initiated in Nalanda District		Reforms rolled out across all collectorates
				Source
				MIS information / Annual reviews and project completion report / BPSM reports / Citizen Surveys / MIS reports
IMPACT WEIGHTING	DFID (£)	Govt (£)	End of Y2 (Sep 2010)			MTR (Sep 2011)				EoP (Jun 2014)
30%
INPUTS (£)
[2] The reform agenda for district administration is currently under discussion. The technical assistance team is undertaking a scoping study to develop an action plan for district administration reforms.