Project Memorandum

Building Debt Management Capacity in Nigeria (Support to the DMO: Phase III)

April 2009 – March 2012

December 2008

“In the midst of our euphoria (regarding the historic Paris Club debt relief), we have not lost sight of the fact that the post-relief period is a delicate one for a developing economy like ours. There is the risk of relapsing into debt unsustainability as a result of unguarded borrowing. With our exit from both the London and Paris Club debt overhang, the DMO is faced with new challenges, principal among which is managing domestic debt at both the Federal and State levels.” / His Excellency, President Umaru Musa Yar’adua, GCFR / at the inauguration of the Supervisory Board of the DMO, August 2007. / “While we immensely appreciate the accomplishments recorded in the country’s public debt management so far, we also recognise that a lot of challenges remain to be addressed. Broadly, there is the need to maintain overall debt sustainability at a time when the country needs to urgently and massively develop infrastructure and grow the economy, so as to achieve substantial poverty reduction. In particular, there remains the challenge of ensuring fiscal discipline and effective Sub-national debt management, especially given the complex nature of our fiscal federalism.” / His Excellency, Dr. Goodluck Jonathan, GCON, Vice President of the Federal Republic of Nigeria at the Forum on Sub-National Debt Management October 2007. / “We are all aware of the role and great achievements of the DMO, in not only the recent exit of Nigeria from its Paris and London Clubs debts, but also in the restructuring of the country’s internal debts. In the latter regard, the secondary market for FGN bonds, which was reactivated about 18 months ago, is now very active, and helping to power the rapid development of the Nigerian capital market. We intend to take the reforms to a higher level.” / Hon. Minister of Finance, Dr. Shamsudeen Usman, OFR / at his inaugural Press Conference in Abuja, August 2007. / “The DMO’s New Strategic Focus will enable it to contribute uniquely to Mr. President’s vision of transforming Nigeria into one of the top 20 economies in the world by 2020.” / Director-General, DMO, Dr. Abraham Nwankwo / While briefing Mr. President on DMO’s New Strategic Focus, July 2007.

Source: DMO Strategic Plan (2008-2012), Inspirations, page 1.
CONTENTS

1	SUMMARY AND RECOMMENDATIONS

2	PROJECT FRAMEWORK

3	PROJECT RATIONALE
	3.1	BACKGROUND
	3.2	POLICIES
	3.3	PROJECT APPROACH
		3.31		SOCIAL APPRAISAL
		3.32		ECONOMIC APPRAISAL
		3.33		INSTITUTIONAL APPRAISAL
		3.34		ENVIRONMENTAL APPRAISAL
	3.4	EVALUATION

4	PROJECT IMPLEMENTATION
	4.1		MANAGEMENT ARRANGEMENTS
	4.2		TIMING
	4.3		INPUTS
	4.4		PROCUREMENT
	4.5		ACCOUNTING
	4.6		MONITORING

5	RISKS

6	ANNEXES
	A		Environmental Screening Note
	B		Risk Matrix
	C		Consultation Matrix

ACRONYMS

CBN	Central Bank of Nigeria
CPS	Country Partnership Strategy
DG	Director General
DMD	Debt Management Department
DMO	Debt Management Office
DSA	Debt Sustainability Analysis
FGN	Federal Government of Nigeria
FMF	Federal Ministry of Finance
FSS	Financial Sector Strategy
HR	Human Resources
ICT	Information and Communications Technology
NASS	National Assembly
NEC	National Economic Council
NEEDS	National Economic and Empowerment Strategy
NPC	National Planning Commission
OAGF	Office of the Accountant General
ODI	Overseas Development Institute
PD/MMs	Primary Dealers and Market Makers
PPP	Public Private Partnerships
PRSP	Public Service Reform Project
PSC	Project Steering Committee
SLGP	State-Level Governance Project
SNDM	Sub-National Debt Management
TC	Technical Cooperation

SUMMARY AND RECOMMENDATIONS

DFID’s support to debt management in Nigeria began in 1998, before the DMO was established, when public debt management was an overlapping and inefficient function across government. £923,000 of support was delivered over the next three years, cumulating in the establishment of Nigeria’s DMO. A second phase of support, launched in 2003, delivered £4.28 million assistance to the DMO as well as some related organisations. This support was pivotal in enabling Nigeria’s historic exit from the Paris Club in 2005. This third and final phase of DFID support will provide £2.6m of support from mid 2009 to mid 2012. It will enable the DMO to implement its new strategic plan, helping to institutionalise macroeconomic stability, build capacity for sub-national debt management and strengthen Nigeria’s position as a global emerging market.

Nigeria’s recently achieved macroeconomic stability is in no small measure due to the hard work and achievements of the federal Debt Management Office (DMO), which was central to Nigeria’s historic exit from the Paris Club group of creditors in 2006.

Since this significant achievement the DMO has continued to embed and extend good debt management practices throughout government. Broadening their focus from foreign public debt to all public debt, the domestic debt market is again functioning after 17 moribund years and Nigeria largely exited the London Club of commercial creditors in 2007.

But like elsewhere in the economy, the policies and practices that underpin macroeconomic stability remain fragile, and will do so until good practice is institutionalised throughout all tiers of government.

The DMO thus faces new challenges. Central to this is how the DMO will develop and fulfill its potential to assist States improve their debt management capacity. With almost half of Nigeria’s government spending at the sub-national level, accompanied by high levels of expenditure autonomy and responsibilities, management of State finances has profound implications for Nigeria’s macroeconomic stability as well as its success in meeting the MDG’s.

Other key challenges the DMO faces are to develop Nigeria’s capital market so as to create the capacity for domestic and external resource mobilisation and to finance critical infrastructure needs of the government while maintaining debt sustainability and macroeconomic stability.

The DMO has responded to these emerging dynamics with a new 5 year strategic plan which repositions its structure, functions and objectives in order to develop and implement a forward looking debt and borrowing strategy that will help Nigeria fulfill its development finance needs.

However, the DMO does not yet have the capacity to fully execute its new strategic plan. Whilst its institutional and technical development over the life of the previous strategic plan has yielded some very real benefits, the new challenges it faces require a deepening of its expertise that it can not yet realise without external assistance.

In response, this project will provide a final phase III of DFID support to DMO to enable it to consolidate its capacity to deliver its enlarged agenda. DFID support will be in the form of technical assistance in the broad areas of institutional strengthening, domestic and foreign debt management and leveraging the DMO as a vehicle through which States can help improve their own debt management capacities.

# Recommendations
# DFID should allocate £2.6 million of Technical Assistance over three years from April 2009 to March 2012 for ‘Phase III’ of support to the DMO. The project will be delivered through a call down contract arrangement that will respond to the emerging strategic needs of DMO.

The goal will be that debt management best practices institutionalised at both the national and sub-national levels of government. The purpose will be to strengthen the sustainable capacity of the DMO to help meet its strategic objectives.

The project will be monitored against delivery of the following Outputs:

1.	DMO delivers an effective market for Nigeria’s domestic debt.
2.	DMO improves state-level debt management through support to Debt Management Departments (DMD’s).
3.	DMO facilitates Nigeria’s external debt sustainability while establishing a viable presence in the international capital market.
4.	DMO contributes to a more conducive and supportive institutional environment for efficient and sustainable debt management practices in Nigeria.

LOGICAL FRAMEWORK MATRIX

Narrative / Summary	Objectively Verifiable Indicators	Means of / Verification	Assumptions
GOAL:
Debt management best practices institutionalised at both the national and sub-national levels of government.	National Debt Management Framework developed and implemented.	DMO, CBN and FMF reports. / Gazetted legislation. / IMF reports. / Investor reports and financial press. / International credit rating agency reports.
	Adherence to debt management related legislation at the federal and state level.
	Internal and external debt sustainability analysis.
	Financial market indictors.
PURPOSE:
To strengthen the sustainable capacity of the DMO to help meet its strategic objectives.	OVI’s adapted from the DMO’s Strategic Objectives (Strategic Plan, 2008-12)
	DMO develops innovative approaches to optimally access external financing.	DMO annual reports. / New frameworks for PPP’s, JV’s, etc. / Extension of CSDRMS system. / State legislative reports. / Interviews with stakeholders and financial market participants. / Media and committee reports. / Client government reports.	Political disagreements between states and FGN do not impair overall macro-stability. / Fiscal responsibility legislation is largely implemented throughout government.
	DMO maintains a comprehensive, reliable and efficient public debt database.
	DMO contributes to the establishment of functioning state-level debt management departments (DMD’s).
	DMO builds an internationally competitive bond market.
	DMO exports debt management services.
OUTPUTS:
1. DMO enables an effective market for Nigeria’s domestic debt.	Robust FGN securities issuance and trading infrastructure in place by end 2009.	DMO Reports. / PDMM’s reports and interviews. / CBN Reports. / Central Securities Clearing Systems report / National Public Debt Management Framework / Annual auction calendar. / Bond issue details.	Effective collaboration with all stakeholders (CBN, PDMM’s, SEC etc). / Effective supervision and regulation by DMO. / Public and investor confidence is maintained/strengthened. / Reopenings are consistent with monetary policy.
	The National Public Debt Management Framework incorporates cash, asset and liability Management by mid 2010.
	The primary and secondary market for long-term domestic debt instruments expands through two of the following three by mid-2011: New derivative instruments; Retail bonds, 20 year bonds.
2. DMO improves state-level debt management through support to Debt Management Departments (DMD’s).	DMO finalises and secures financing for its sub-national debt management capacity building strategy by end 2009.	DMO Annual Report. / State-level PFM plans. / State-level DSA’s. / DMD reports and interviews with staff. / NPC reports. / Budget Monitoring Reports.	Political commitment and adequate resources to DMDs at State-level.
	DMO training to DMDs reaches at least 15 states by end 2009.
	Guidelines for on-lending and federal guarantees to States developed, adopted and effectively monitored by end 2010.
3. DMO facilitates Nigeria’s external debt sustainability while establishing a viable presence in the international capital market.	DMO develops guidelines for PPP with special reference to FGN guarantees to enable appropriate evaluation and treatment of contingent liabilities, by end 2009.	DMO annual reports. / DMO Guidelines. / IMF reports. / Financial market reports.	Other relevant government agencies offer reasonable level of participation. / Government’s institutional framework for PPP assigns clear roles and responsibilities. / International financial market stability. / DMO advice sought and taken by government.
	Risk management strategy codified and implemented, including Cost at Risk (CaR) framework, by end 2009.
	Bonds issued on the international market and a benchmark yield curve established, by end 2011.
4. DMO contributes to a more conducive and supportive institutional environment for efficient and sustainable debt management practices in Nigeria.	DMO’s ICT systems upgraded to support latest version of debt management software (CSDRMS) by end 2009.	DMO departmental self assessments and annual report. / Physical inspections. / Gazetted legislation. / DMO, OAGF and CBN reports. / FGN Fiscal Strategy Paper.	DMO’s ICT infrastructure is maintained. / DMO Supervisory Board and NASS prioritise and support amendments and their the early passage. / Political commitment to fiscal responsibility legislation remains. / Collaboration between agencies is maintained and strengthened. / DMO secures CBN-equivalent salaries for staff which reduces staff turnover rates.
	A Performance Management Framework embedded throughout DMO, including evaluation of training, by end 2009.
	Necessary amendments to the DMO Act (2003) are passed by the National Assembly by mid-2010.
	DMO assists States pass fiscal responsibility legislation. Reaching out to at least 15 States by mid-2010.
	DMO contributes to the successful Integration of cash management and debt management by end 2012.
ACTIVITIES:
Training DMO staff and those from other relevant agencies such CBN, OAGF etc on a variety of technical debt management-related issues. / Awareness arising for the general public and relevant members of the National Assembly. / Technical assistance on institutional issues such as DMO’s staff performance management system. / Technical assistance and advice to the DMO’s front, middle and back office on technical debt-related issues including legislation, modelling risk, developing new instruments, use of the software etc. / Facilitation of ‘train the trainer’ schemes. / Seminars and other consultations with creditors and financial market participants / Training for DMD staff to be managed and coordinated by the DMO. / Implementation of DMO’s revised IT strategy also utilising FGN funds.

# 3. PROJECT RATIONALE

# 3.1 Rationale

Nigeria’s exit from the Paris and London Club’s, in 2006 and 2007 respectively[1], signaled the end of ‘crisis debt management’ for Nigeria. However, the emerging challenges are no less significant or demanding. As reflected in its new strategic plan (2008-12), the DMO must now safeguard Nigeria’s hard-earned credit worthiness while exploiting the potential for proactive and prudential debt management to contribute to the development goals of the country.
[1] Paris Club relief amounted to a US$18 billion write-off, with the required balance of approximately US$12.4 billion paid by April 2006. Exit from the London Club through payment of Par Bonds, Promissory Notes and associated Oil Warrants was effected in 2007.

The DMO is embracing these emerging priorities and recognises the institutional change and strengthening required. DFID’s next phase of support will align behind the DMO’s new five-year strategic plan to both help ‘bed-down’ the institutional strengthening achieved in recent years as well as assist the DMO effectively respond to its emerging priorities.

3.2 Background

Nigeria’s previously impaired financial reputation meant that it could not access international capital markets for anything except enclave oil and gas projects, and domestic investors were no more willing than foreign lenders to buy Nigeria’s bonds. Nigeria’s debt burden was unsustainable, totaling US$36 billion in 2004, 57.8% of GDP.

The DMO’s stellar performance over the past seven years, ranging from its leading role in negotiating a historic Paris Club debt relief deal, to paying off London Club debts, to successfully issuing domestic bonds after 17 moribund years, has returned Nigeria to creditworthiness as reflected by her first ever sovereign credit of BB-[2]. Nigeria’s current debt stock is relatively low by international standards[3], totaling 14% of GDP (10% domestic debt and 4% foreign).
[2] Awarded by both Fitch and Standard&Poors in 2006, and maintained in 2007.
[3] Nigeria is now one of only a few countries outside the OECD with a debt to GDP ratio below 20%. It also compares well against competitor emerging markets and other BB- rated countries.

Domestic borrowing by government is no longer crowding out private borrowing in Nigeria: interest rates have generally fallen, maturity of issues has lengthened, and the government’s credibility of repayment has been restored, particularly with the securitsation of arrears. The rating agency Fitch recently upgraded Nigeria’s Local Currency Rating from ‘BB-‘ to ‘BB’ reflecting the impressive development of the domestic debt market since the rating was first assigned in January 2006.

The achievements of the DMO have been central to the government’s economic reform agenda. This has seen significant improvements in macroeconomic performance as evidenced by higher rates of growth (averaging around 6% between 2000 and 2006), single digit inflation, a dramatic decline in debt and accumulation of significant foreign reserves. Such progress is widely recognised (see box 1 below).

Box 1: Nigeria’s International Credit Rating, Fitch, June 2008

Nigeria’s public finances have also improved from the point of view of debt management. Nigeria has used its oil savings to settle its Paris and London Club debt. The public debt/GDP ratio at 12.5% of GDP in 2007 was much lower than the 34% ‘BB’ median. Most of the debt is in local currency, where small amounts are issued to finance the federal government deficit based on the benchmark oil price, for liquidity management and as a way of developing the local debt market. There has been impressive progress on developing the domestic debt market, which grew from the equivalent of USD11.8bn in 2005 to USD18.4bn at the end of 2007; maturities have been extended to 10 years, yields have declined and a secondary market has developed since 2006. The upgrade of the Local Currency Rating to ‘BB’ reflects these developments since the rating was first assigned in January 2006.

Despite these welcome reforms Nigeria still faces huge and daunting development challenges. With between 50 to 70% of the population living below the poverty line, huge infrastructural gaps remain and continue to constrain economic growth. The DMO’s imperative is now to help efficiently and prudently leverage the resources (whether public or private, and at federal or state level) necessary to finance Nigeria’s development.

## 3.3 Policy Context

3.3(i) Federal Government of Nigeria

Nigeria’s administration continues to pursue the economic reform agenda of recent years, underpinned by a commitment to the constitution, rule of law and due process. Improved fiscal discipline has underwritten recent macroeconomic improvements, centered on adherence to the oil-price fiscal rule. The previous government introduced fiscal responsibility legislation to institutionalise and deepen these reforms through, for example, better budget processes and prudent debt management. The new President quickly demonstrated his priority to cascade such responsibilities to the sub-national level, where the appetite for reform is mixed. State governors have agreed to introduce fiscal responsibility legislation (as well as procurement legislation) which, if and when implemented, will help the States contribute to Nigeria’s debt sustainability. This development reinforces the need for better debt management at the state level, where current capacity is generally weak but demand for assistance is increasing. These developments reinforce the role of the DMO in establishing and sustaining appropriate debt management practices throughout government.

As part of his 7-Point Agenda (currently being subsumed into a national development plan), the President has recognised that despite Nigeria’s oil wealth, government alone cannot tackle the country’s key constraints to growth. The President has called for the private sector to play a key role in securing effective and sustainable solutions, particularly in addressing the infrastructure deficit and urgently needed power sector reform. This expands the role of the DMO in advising on, and facilitating, the financing of these necessary investments; whether solely through government borrowing (domestic or external), or through collaboration with the private sector.

The Government has also prioritised the development of Nigeria’s financial sector as articulated in the current Financial Sector Strategy (FSS) 2020. The DMO has a key contribution to this policy framework through its efforts to deepen and modernise Nigeria’s capital market.

3.3(ii) DFID

Under the outcome ‘Improved Environment and Services for Non-Oil Growth’, the joint DFID-World Bank Country Partnership Strategy Partnership (CPS) recognises that technical assistance activities in debt management ”will be an important part of the support for strengthening government capacity in carrying out structural reforms.” This project also supports the governance pillar of the CPS through strengthening the governance of debt management across government, making it more transparent and accountable. It also supports the (non oil sector) growth pillar by seeking to channel private resources for infrastructural development.

3.3(iii) Nigeria’s Debt Management Polices

The DMO was created in 2000, with the DMO Act, formally mandating it as an autonomous agency, enacted in 2003. Prior to this debt management was performed by several government agencies resulting in inefficiencies including poor coordination, inadequate data recording, conflicting data and incomplete debt reconciliation. The DMO was therefore created to facilitate efficient debt management for the country. Its function is to assist in formulating and implementing the country’s public debt management strategy, ensuring appropriate linkages to fiscal and monetary policies, as well as overall macroeconomic management. A breakdown of its mandated functions is detailed in Box 2 below.

Box 2: Mandated functions of the DMO under the DMO Act (2003) / Maintain a reliable database of all loans taken or guaranteed by the Federal or state Governments or any of their agencies / Prepare and submit to the Federal Government a forecast of loan service obligations for each financial year / Prepare and implement a plan for the efficient management of Nigeria’s external and domestic debt obligations at sustainable levels compatible with desired economic activities for growth and development; and participate in negotiations aimed at realising these objectives. / Set guidelines for managing the Federal Government financial risks and currency exposure with respect to all loans / Advise the Federal Government on the restructuring and re-financing of all debt obligations. / Advise the Minister of Finance on the terms and conditions on which monies, whether in the currency of Nigeria or in any other currency, are to be borrowed / Collect, collate, and disseminate information, data, and forecasts, on debt management with the approval of the Board

DMO’s Strategic Plans

DMO’s first strategic plan (2002-06) articulated its vision ‘to build a world-class DMO capable of making Nigeria’s debt sustainable by 2006’, with a mission ‘to transform Nigeria’s debt portfolio into an asset for growth and development.’ The overall objective was to ‘rapidly achieve sustainable debt profile and continue to maintain growth-supporting debt portfolio for Nigeria’. Three subsidiary objectives were identified as crucial, to: 1) obtain substantial debt relief for Nigeria, 2) takeover control of, and effectively manage domestic debt, and 3) build a world class DMO with suitable institutional framework and arrangements for sustainable public debt management.

With Nigeria’s Paris Club exit the DMO has achieved the first objective. Ongoing progress was made on the other two which are now receiving renewed attention as the DMO moves from crisis management to process management, with a broadened emphasis on public, rather than just external, debt.

3.3(iv) DFID Support and Progress to Date

Phase I of DFID’s partnership with the DMO began in 1998 totaling £923,000 over three years. It helped the DMO establish an effective external debt recording and management system with an overwhelming focus on obtaining external debt relief.

Phase II of DFID support (2003-08) totaled £4.28 million and was closely aligned behind the DMO’s first strategic plan. The goal of this phase was ‘to achieve a sustainable debt position for Nigeria that supports growth and poverty reduction’ and its purpose to ‘strengthen public debt management through a program to build the capacity of the DMO to world-class standards and develop stronger relationships with stakeholders, financial institutions and the public.’

This comprehensive programme supported the DMO in shifting its institutional focus from external debt reduction to designing and managing a successful national debt policy. Institutional support ranged from organisational restructuring and developing HR and ICT systems and processes, to specific assistance to the DMO’s front, middle and back office including training and systems implementation. The assistance was delivered by Crown Agents and coordinated by their project manager/institutional development advisor initially resident at the DMO.

Ongoing M&E indicate that project is likely to meet most of its objectives within its term. The October 2007 and September 2008 annual reviews detail progress awarding the project a score of 2. DMO’s highly skilled and reformist management team is a leading model for civil service reform in Nigeria. In 2006 the project won the annual British Expertise International Award.

# 3.4 Approach

3.4(i) DMO Strategic Plan 2008–2012: Meeting new challenges

Post-debt relief realities have created the challenge of integrating public debt management to not only finance fiscal gaps but be proactively used for funding development projects at national and sub-national levels. DMO’s emerging challenges are summarised below:

- Avoid a relapse into unsustainable debt by instilling fiscal discipline in all tiers of government;
- Ensure new borrowing is on concessional terms in order to minimise the cost of foreign currency borrowing;
- Develop the domestic debt market to support financing of the government deficit and developmental needs, as well as providing access for the private sector to the long-term funds needed to develop the real sector of the economy;
- Effective coordination and regulation of borrowing by sub-national entities; and,
- Explore the use of federal government guarantees to support financing projects under public-private-partnership initiatives (PPP), Joint Ventures, etc.

This progression in the debt management agenda is reflected in the DMO’s evolving strategic focus and articulated in its new five-year strategic plan (2008-2012) which has a Vision to manage Nigeria’s debt as an asset for growth, development and poverty reduction, and a Mission to rely on well-motivated, professional workforce and state-of-the-art technology, to be among the emerging market’s top ten Debt Management Offices, in terms of best practice and contribution to national development.

The Objectives of the new Strategic Plan are as follows:

1. Establish and develop effective institutions and debt management capabilities at the sub-national level.
2. Maintain a comprehensive, reliable and efficient national and sub-national debt database, and to ensure prompt and accurate settlement of debt service obligations.
3. Build a first-rate and internationally competitive bond market, not only to support government financing needs but also to provide the private sector access to long-term financing, in line with the Financial Sector Strategy (FSS) 2020.
4. Develop innovative approaches for optimally accessing external financing.
5. Make Nigeria an exporter of debt management skills and major destination for out-sourced debt management services.
6. Build and maintain a well-motivated and professional workforce

3.4(ii) Phase III DFID Support to DMO Strategic Plan 2008-2012

In response to DMO’s challenges, Phase III will provide a final phase of DFID support to DMO to enable it to consolidate its capacity to deliver its enlarged agenda. Phase III will not simply be an extension of the current phase but will narrow its focus to in terms of building staff skills in high specialized and often new areas for DMO. The institutional focus of this phase of support will be limited to focus on development of effective performance management systems.

The main types of support are detailed below and will be consolidated into logframe activities during the first four months of Phase III, the inception phase.

Building the skills of the DMO staff. To facilitate successful implementation of the DMO’s new strategic plan. Training in new areas such as market development, infrastructure financing, contingent liabilities, bond market regulation. Building on existing training successes to deepen skills in the area of, for example, debt recording (CS-DRMS) and risk management. Mixture of training courses and longer term resident advisors to facilitate in-depth knowledge transfer and on-the-job training. Some training will be offered to State Government officials and other federal agencies where this is central to meeting the objectives of the DMO’s strategic plan, for example the CBN.

Capacity building of state Debt Management Departments (DMD’s). Assisting the DMO to transfer and share their knowledge and experience of debt management to build capacity of the State DMDs. For example through organising training and attachments to the DMO. At the same time helping the DMO strengthen their role in coordinating State DMDs with each other as well as contributing to an improved relationship between federal and state governments. As a response to the DMO’s plans for a Sub-National Debt Management Facility, the project could explore the establishment of a small grant facility, managed by the DMO, through which it could extend the reach of its assistance in key States.

Institutional strengthening of the DMO through new systems and process. This will require an updated training needs analysis to establish whether the DMO is properly equipped to manage the emerging domestic and sub-national debt issues encapsulated in its new strategic plan. Institutionalising the subsequent training and capacity building delivered will require a functioning and well monitored performance management system with a solid learning and development framework for staff.

Training and educating the DMO’s partner agencies. Support to partner agencies to equip them with the necessary capacity to assist the DMO in fulfilling its mandate. At the same time strengthening collaboration between the DMO and these key agencies using the DMO’s strategic plan implementation schedule.

Outreach and training to external stakeholders will help facilitate the work of the DMO and contribute to an external consistency supporting macroeconomic stability and sustainable economic growth. Stakeholders will include members of the NASS House Committee on Aid, Loans a Debt Management and Senate Committee on Local and Foreign Debts as well as key staff in the Vice Presidency given his role as Chair of the DMO Board.

Train the trainer programmes at the DMO. To help DMO staff deliver in-house training, reducing the cost burden, as well as strengthen their role in designing and delivering training for Nigerian stakeholders such as federal level agencies, State DMD staff, the general public and private sector.

3.4(iii) Sustainability and DFID Exit Strategy

Of primary concern to the DMO is independent revenue generation to secure higher CBN-equivalent salaries for their staff, to reduce staff turnover (which has been a problem in the past but is less so now), and attract the best possible people to work at the DMO. DMO expect to derive significant revenue from fees from public debt issues. Proposed amendments to the DMO Act to enable this have been approved by the DMO Supervisory Board and will soon be submitted to the National Assembly. Within five years the DMO also aims derive revenue from debt management advisory services to regional governments. Managed successfully, the export of services will bring benefits beyond income, such as prestige to Nigeria and lesson-learning. However, the DMO will have to manage the internal incentives carefully, to ensure a balance approach to serving their domestic and external clients.

DFID’s strategy for exiting from significant support to DMO will comprise:

- A project end-date before the end of the new strategic plan (2008-12), to allow the DMO time to adjust to the withdrawal of broad donor support.
- Strengthening the DMO counterpart relationship with the project to minimise loss of expertise or institutional memory created by the end of the project.
- Enhanced efforts to institutionalise training and support delivered under the project. For example through ‘train-the trainer’ activities and embedding robust training evaluation process within the DMO.

3.4(iv) Coordination of donor support to DMO

Several other donors also provide capacity building at the state level, including CIDA, the EC and the World Bank. There is also potential short-term technical assistance from the IMF on issues such as debt management, cash management and risk management. All these stakeholders have been consulted on the design of this project.

Within DFID, relevant support at federal and state level includes SPARC (capacity building for debt management at the state level) and NIAF (appraisal of investment projects). Close coordination between the current phase of this project and SPARC’s predecessor, SLGP (State-Level Governance Project) have demonstrated the value of coordination and cooperation which has often provided DFID with both a Federal and State perspective on the same issue. As DFID specific support to DMO ends under Phase III, SPARC could potentially deliver some support to the DMO. DFID’s Public Sector Reform Project (PRSP) may provide another means.

3.4(v) Alternative Project Approaches

Several alternative approaches to providing assistance through Phase III were considered. Continuation of the comprehensive institution building assistance provided under Phase II was rejected in preference of a model that better reflected the DMO maturing as a financially sustainable institution. The chosen option is for DFID to contract a managing agent to deliver all the required technical assistance and manage this assistance in collaboration with the DMO. This option facilitates a broad sourcing of project inputs (as requested by the DMO), limits the administrative and management burden on DFID, and ensures the project is professionally managed.

3.5 Economic Appraisal

DFID expect the returns to Phase III, through improvements in debt management, which will feed into better public financial and ultimately macroeconomic management, to exceed the £3 million cost. Borrowing is economically sensible if funds are used to generate economic growth, pay off higher interest-bearing debt or convert short-term debt to longer term. But as Nigeria’s experience demonstrates, too much debt can hamper economic growth and investment through the disincentives created by the presence of such significant ‘debt overhang’.

Nigeria’s historic Paris Club deal, the largest ever in Africa, secured US$18 billion of debt cancellation and generated savings from debt service of approximately US$1 billion per annum (US$8-12 billion over the life of the rescheduling). Phase III will assist the DMO maintain debt sustainability and identify the optimum borrowing strategy that will see debt service costs (whether from external or domestic borrowing) minimised and lowered. For example prudent debt management generates savings from the avoidance of penalties and fees. In December 2000 approximately 25% of Nigeria’s public debt stock was penalties and accrued interest.

Further development of the domestic debt market will generate significant savings for government through providing an alternative and often more cost effective source of finance, particularly for long-term investments. Prudent management of this debt is however critical to avoid excess costs emanating from, for example, high domestic interest rates and roll-over of short-tern instruments. Accessing this market will also help shield the government from foreign currency risk which can be substantial. The DMO estimates that without Paris Club relief Nigeria’s debt stock would have increased by approximately US$2 billion due to recent depreciation of the US dollar. As the domestic bond market develops and the interest rate on government debt falls, the cost effectiveness of domestic financing will fall further. The DMO is working to facilitate the establishment of a corporate bond market in Nigeria. This should help stimulate private sector growth as firms gain improved access to appropriate long-term finance. The eventual issuance of State government bonds will also generate substantive cost savings as currently most States are constrained in their ability to access low-cost long-term finance.

The DMO’s ongoing development of the domestic bond market presents a powerful growth strategy to support growth by generating long-term funding sources for government financed development projects, such as infrastructure, but more importantly, will help to realise the potential of Nigeria’s vibrant private sector to create jobs and wealth by opening up this new source of domestic financing.

Further gains should also accrue through the DMO’s strengthened involvement in various policy frameworks. For example integrating debt management and cash management to better align government spending and revenue flows can generate substantial savings through reducing the opportunity cost of inefficient cash management practises.

Clearly these economic benefits will only accrue if new debt is used productivity to generate returns sufficient to repay debts and grow the economy. Particularly within the new fiscal responsibility framework, the DMO is expected to play an increasing role in ensuring debt-financed investments are used productively across government. They fully recognise that the sustainability consideration at the heart of their mandate, must consider not just the quantum of debt, but also its productivity and development impact in terms of generating growth, shared prosperity and poverty reduction. This will also bring significant gains at the State level where the DMO is also hoping to contribute to the improvement of fiscal management capacity. The DMO will continue to help inculcate financial prudence and value for money into the national political consciousness.

In the climate of a post-debt relief world, sound debt management will ensure Nigeria never returns to unsustainable debt accumulation and crisis.

3.6 Social Appraisal

There are strong links between the debt relief DMO helped secure and making additional resources available to attain the Millennium Development Goals (MDGs) on another hand. One of the key benefits has been the elimination of unsustainable annual debt service payments to external creditors. The additional US$1 billion that the FGN will save every year for the next 20 or more years is now been spent on providing primary education, primary health care, rural infrastructure, electrification, water supply and other key poverty reducing sectors.

With the retirement of Paris and London Clubs debts, it is important that new external borrowings are properly managed within an appropriate debt management framework. Under its proposed agenda on external debt management, DMO will focus more broadly on areas such as mobilization of additional financing such as grants and concessional loans targeted at accelerating growth and poverty reduction and meeting other MDGs related targets; as well as accessing the international capital market on terms favourable to Nigeria for resource mobilisation geared towards the financing of key infrastructure projects. This should benefit the states because DMO is embarking on a holistic approach to debt management in Nigeria that seeks to integrate external, domestic and sub-national debt management in a way that debt can be used for effectively funding development projects at national and sub-national levels, in addition to financing fiscal gaps.

### 3.7 Institutional Appraisal

The DMO came into existence in 2000 but was formally established by the DMO Act in 2003. The Act provides for a seven-member Supervisory Board, inaugurated in August 2007, chaired by the Vice President, to provide policy direction and guidance. Other Board members include the Minister of Finance (Vice Chairman), Attorney General, Chief Economic Adviser to the President, Accountant General of the Federation and Governor of the CBN. Management is headed by the DG who reports to the Supervisory Board. The NASS has oversight responsibility to the electorate for DMO’s activities and results.

The DMO is one of the stronger public institutions in the country. It has adopted a Front-Middle-Back Office configuration, reflecting international best practice in organisational structuring for such an entity, with two support and oversight departments (Audit and Compliance Unit and the Executive Unit - see figure 1). To reflect its changing priorities, a new department, the Special Programmes Department was recently created whose responsibilities include SND, nationwide public debt education and establishment of Debt Management Institute.

Phase II supported broad institutional strengthening of the DMO which included organisational restructuring and development of new HR polices and an ICT strategy. The new DG has also prioritised the importance of introducing departmental self-assessment as planned within the DMO’s Accountability & Responsibility Framework.

Figure 1:	The DMO’s Organisational Structure

Director
General
Portfolio
Management
Department
Market
Development
Department
Strategic
Programs
Department
Policy Strategy
& Risk Management
Department
Debt Recording
Department
Organisational
Resourcing
Department
Audit and Compliance Unit
Executive Unit
Securities
Issuance
Unit
Loans & Other
Products
Unit
Market
Planning
Unit
Market
Regulation
Unit
Products
Development
Unit
Institutions &
Skills Development
Unit
Curriculum
Development
Unit
Associated &
Edernalities
Unit
Policy &
Strategy
Unit
Risk
Management
Unit
Monitoring &
Compliance
Unit
Research &
Documentation
Unit
Sub-National
Debt Recording
Unit
External Debt &
Special Accounts
Unit
Domestic Debt
Recording Unit
Debt Settlement
Unit
Finance &
Accounts
Unit
Human Resource
& Admin Unit
Corporate Affairs
Unit
IT-IS Unit
Supervisory
Board

One of the DMO’s key institutional weaknesses is its limited ability to recruit and retain adequately skilled staff within the current remuneration structure. Recruitment, particularly of middle office, has had a visible impact on the ability of the DMO to develop its expertise, and high staff turnover is costly due to the highly specialised training required for new staff. The DMO’s efforts to secure CBN-equivalent salary and staff benefits should receive a boost with the newly inaugurated Supervisory Board. The DMO is also exploring ways to generate revenue to secure financial sustainability. The ultimate goal to become a global exporter of debt management services reflects this ambition.

3.8 Environmental Appraisal

Much of DMOs work has no direct environmental impact. One area of indirect impact is DMO’s role in enabling investment in power and water infrastructure identified as a key Nigerian need that the DMO’s activities will target. Both of these elements are increasingly subject to due diligence and scrutiny around social and environmental criteria. Socially responsible investment (SRI) practices have pioneered the use of private capital to influence business practices on these issues. SRI is now a substantial part of the international market, and increasingly being applied to investments in emerging markets. The most common tools applied are portfolio screening to include or exclude specific investments, shareholder advocacy to influence investor behaviour, and community investment that targets, e.g. disadvantaged groups or environmental services that are neglected by traditional financial practices. DMO will need to have some familiarity with SRI approaches and application of social and environmental criteria in investment transactions.

3.9 LESSONS AND EVALUATION

3.9(i) Lessons Learned

Design of Phase III directly draws on the successes and lessons learned to-date. Box 3 below outlines some of the key lessons learned.

Box 3: Support to the DMO: Key Lessons Learned / The effectiveness of debt management depends on several other counterpart institutions that must have sufficient capacity to engage and work with the DMO. / DMO’s internal structures and skill requirements evolve as the institution strengthens over time, creating demand for new systems and training opportunities. / Evaluating the effectiveness of training is a challenge but essential. / Flexibility of support is crucial to enable the DMO to coordinate DFID’s assistance with that provided by others, as well as respond to changing or emerging priorities. / The relative merits of different forms of training should be considered in context and the source of training options should be as flexible as possible. / Domestic ownership and strong leadership are essential and have been largely achieved through close alignment of the project with the DMO’s strategic plan. / Adoption of best international practice in debt management and institutional development must be adapted to the Nigerian context. / Coordination with other donor activities, particularly as the DMO engages at the state-level, is vital, and a role which the DMO should assume. / -

3.9(ii) Best Practice in Supporting Debt Management

Debt management is a key component of macroeconomic management and cannot be executed in isolation. The DMO recognises the importance of effective collaboration with other institutions, both policymaking and the market. DMO’s credibility and autonomy depend on these collaborative roles and follow-through of its partner institutions. A strong relationship with the NASS and ministers is also crucial to DMO’s effectiveness. Going forward the DMO should facilitate greater cooperation with NPC to help rationalise the interface between donor and debt finance.

## 4. IMPLEMENTATION

## 4.1 Management Arrangements

A Managing Agent will be appointed to administer this project. The Managing Agent will employ an overall Project Manager to coordinate assistance, although with greater responsibility for the DMO as it gradually adjusts to withdrawal of support. The Project Manager will not be resident in Abuja but will visit every three months, or more frequently as appropriate, to oversee the project.

The Project Manger will work closely with the DMO’s own appointed Project Coordinator and be responsible for monitoring and implementation of the project. Clear TOR’s will be developed for both the Project Manager and Project Coordinator roles. The latter will be a ‘hands-on’ role to facilitate skills transfer and institutional memory regarding project management and coordination to the DMO.

The general management arrangements should remain as under the Phase II, as they are working well. The composition of the Project Steering Committee (PSC) should remain the DG, DMO management, Project Coordinator, Project Manager and relevant DFID staff. The PSC will continue to meet quarterly to discuss quarterly progress reports prepared by the Project Manager, in collaboration with the DMO. The Project Coordinator will be secretary to the PSC.

A smaller implementation team will meet approximately once a month or as necessary to resolve any emerging problems or issues. This team will comprise the Project Coordinator, Project Manager and other DMO and DFID staff as necessary. The Project Coordinator will be responsible for organising and minuting these meetings.

## 4.2 Timing and Funding

## Phase II will run for 3 years from April 2009 to March 2012. This covers the life of the DMO’s new strategic plan and so will facilitate alignment of DFID support to the DMO’s priorities as well as allow a more comprehensive project completion review drawing on the DMO’s own process of evaluation. The projects financial ceiling is UK £2.6 million.

Once contracts for delivering this support are in place, an inception phase of between 3 and 4 months will begin. At the end of the inception phase, the Project Manager, in conjunction with the Project Coordinator, will deliver an inception report which will include; an agreed workplan for the first year along with a costed budget; finalisation of the project logframe and; TOR’s for the Project Management and Project Coordinator clarifying their complementary roles and responsibilities. An indicative budget and cashflow for Phase III is set out in Table 1 below.

4.3 Inputs and Structure of Support

The main areas of support are as set out in Section 2 above. Specific activities to be undertaken within the project logframe will be agreed and finalised during the inception phase.

Table 1 - DMO CASH PROJECTIONS AND INDICATIVE PROJECT BUDGET (GBP '000s' cash (nominal) amounts)

	2009-10		2010-11		2011-12		TOTAL
	DMO	DFID	DMO	DFID	DMO	DFID	DMO	DFID
Debt Management Training	654	700	687	600	721	530	2,062	1,830
Human Resources/ / Organisational Development	0	20	0	17	0	12	0	49
Information and / Communication technology	83	12	42	9	0	0	125	21
Management Fees / (£500,000 over 3 years)	0	166	0	166	0	166	0	500
Contingency / (£100,000 over 3 years)	0	33	0	33	0	33	0	100
M&E Costs / (£100,000 over 3 years)	0	33	0	33	0	33	0	100
TOTAL	737	981	729	875	721	741	2,187	2,600

4.4 Contracting and Procurement

DFID will contract a consultant to carry out this project (the Managing Agent), selected in an open bidding process. DMO will sit on the selection board for assessing the technical bids. The Managing Agent will be responsible for all project activities. Procurement of equipment will be in line with standard DFID guidelines.

4.5 Accounting and Audit

DFID will fund the Management Agent to undertake the project. The Agent will be accountable to DFID for all programme spending above, apart from the contingency budget and M&E costs which DFID will administer directly. Full accounting records of incomes and expenditure will be maintained by the Management Agent and audited by an auditing company acceptable to DFID. The Project Manager will be expected to provide accurate, timely quarterly financial forecast to DFID and maintain an asset register.

4.6 Monitoring and Evaluation

During the inception phase the Project Manager, in conjunction with the Project Coordinator, will develop a budgeted workplan for the first one year of the project. This initial workplan will include refinement of the logical framework matrix presented in this document and reflect the changes recommended and agreed during the inception phase. A new workplan for the remaining period of the programme will be submitted by the Programme Manager to the PSC two months before the end of the first one year of activities for discussion and approval by the PSC.

The Programme Manager will work closely with the DMO and other donors to ensure coordination of monitoring and evaluation procedures, using common systems wherever possible, in particularly the planned self-assessment of departmental plans within the DMO.

DFID will undertake an annual review every year on the anniversary of the project start-up. The reviews will be undertaken by an independent reviewer, independently contracted by DFID, agreed by DFID and the DMO. The reviewer will work closely with DFID and the DMO to evaluate the project’s success as measured against the project logframe. The review will provide DMO with the information necessary to discuss any required changes to the project design or implementation arrangements with DFID. The Project Manager, in conjunction with the Project Coordinator, will prepare materials and undertake the planning and logistics for these reviews. A Project Completion Review (PCR) will be undertaken at the end of the project.
.

## 5. RISK ANALYSIS AND MITIGATION

5.1 Risks

The DMO is functioning well, achieving sound debt management and has built up credibility with the public. Nonetheless given the operating environment the project carries an overall medium risk rating. The principal risks are: untested state governments’ commitment to sound debt management; a weakening of fiscal discipline at federal level and staff turnover in the DMO. A risk matrix is attached at Annex B.

The project will mitigate the risks associated with poor political commitment and cooperation from state governments by helping to build the DMO’s capability to address state-level capacity constraints. It will also seek to strengthen the relationship between the federal and state-level institutions through improved communication and information exchange. Close coordination with other donor (including DFID) projects working on debt management issues directly at the state-level will also help mitigate the risks of poor results at the state-level.

At the national level, there is an ongoing risk to macroeconomic stability through lax fiscal discipline. A key source of this risk is currently the National Assembly, and as a result, the project will work with the DMO to build the NASS’s understanding and appreciation of the elements and importance of macroeconomic stability; central to which is debt sustainability. The project will also provide support to the Vice President’s Office, as Chairman of the DMO’s Supervisory Board. This will help mitigate the risk of political interference in the operation and advice of the DMO.

Within the DMO, an ongoing risk is that high staff turnover reduces the sustainability and effectiveness of assistance provided by the project. This will be mitigated by working with the DMO to reform their outdated and incomplete performance management system. A more robust performance management system will, in turn, complement the DMO’s efforts to increase remuneration levels to be on par with the CBN.

A final risk is that activities leading to independent revenue generation creates incentives to service external rather than domestic clients (such as States). The DMO will manage this risk through robust business planning which allocates their resources and energies appropriately between their strategic priorities.

## 5.2 DMO Undertakings

DMO undertake to continue to strive towards excellence in debt management, to invest in its staff with training and strong and supportive leadership, to avoid unnecessary bureaucratisation of DMO and to strengthen and retain a modern and professional working team. Specifically, the DMO has undertaken to deliver the above project and outputs within the agreed timetable. DMO also undertakes to:
1. Continue to honour its mandated functions as detailed in the DMO Act.
2. Provide counterpart project management support in the form of a staff member responsible for co-project management and office support and facilities to house a Project Management Unit of not more than five personnel at a time.
3. Advise DFID of any change to procedures;
4. Pursue, through its Supervisory Board, higher remuneration for staff to ensure DMO’s long-term financial sustainability.

ANNEX A: ENVIRONMENTAL SCREENING NOTE
Environmental Screening Note (ESN)

Section A – Basic Information
Project Title: / Help – F1	Phase III Support to Debt Management Office
Project Cost: / Help – F1	£3M
Duration: / Help – F1	4 years (21009-12)
Country: / Help – F1	Nigeria.
Department: / Help – F1	DFID Nigeria
Lead Project/Desk Officer: / Help – F1			Lindsey Block
Officer responsible for environmental screening: / Help – F1				Sean Doolan
Funding type:
Co-funders: / Help – F1		n/a
Brief description of intervention: Help – F1
Much of Nigeria’s recently achieved macroeconomic stability is due to the achievements of the federal Debt Management Office (DMO). Following Nigeria’s exit from the Paris and London Clubs, emerging challenges on debt management are no less significant or demanding. As reflected in its new strategic plan (2008-12), the DMO must now safeguard Nigeria’s hard-earned credit worthiness while exploiting the potential for proactive and prudential debt management (public and private) to contribute to the development goals of the country. The DMO recognises the institutional change and strengthening required. DFID’s next phase of support will align behind the DMO’s new five-year strategic plan to both help ‘bed-down’ the institutional strengthening achieved in recent years as well as assist the DMO effectively respond to its emerging priorities. / ‘Phase III’ will be delivered to the DMO through a contracted Technical Cooperation instrument housing a flexible call down contract arrangement that will be able to respond to the emerging strategic needs of DMO. The project will assist the DMO with implementation of its new five-year strategic plan. The project will be monitored against the following Outputs: / Strengthened capacity of the DMO through retention of an appropriately skilled, well-motivated and professional workforce. / Enhanced capacity to manage and grow Nigeria’s domestic debt market; / Enhanced capacity to manage Nigeria’s sub-national debt and its integration into the national debt management framework; / Enhanced capacity to negotiate foreign loans on appropriate terms and manage foreign debts on a sustainable basis; / DMO contributes to a more conducive and supportive external environment for sustainable debt management practices throughout government. / The DMO’s greatest asset is by far its pool of highly qualified and dynamic staff. Phase III will assist the DMO to maintain and grow this resource as operations of the DMO move into new and often complex areas. Training and support will also be extended to stakeholders in other institutions whose capacity is central to the achievement of the DMO’s strategic plan. This may include, for example, State government officials and certain departments at the Central Bank of Nigeria. It will include outreach to parliamentarians, the general public and civil society as appropriate.

Section B – Assessment / To find guidance on how to carry out the assessment click on the links below: / Environmental screening checklist / Guidance and best practice
Environmental issues: (Include environmental risks, benefits and opportunities, as appropriate. Also outline other environmental information such as compliance with relevant policy and legislation, capacity for environmental management in country, comments on relevant environmental trends in the country or region and information on related environmental projects implemented by government or other donors.)
Infrastructure, including both power and water investment, is identified as a key Nigerian need that the DMO’s activities will target, as is enhanced capacity to negotiate foreign investment. Both of these elements are increasingly subject to due diligence and scrutiny around social and environmental criteria. Socially responsible investment (SRI) practices have pioneered the use of private capital to influence business practices on these issues. SRI is now a substantial part of the international market, and increasingly being applied to investments in emerging markets. The most common tools applied are portfolio screening to include or exclude specific investments, shareholder advocacy to influence investor behaviour, and community investment that targets, e.g. disadvantaged groups or environmental services that are neglected by traditional financial practices. / One perceived strength of SRI practices is that they emphasise the importance of risk management and can identify risks that may otherwise be overlooked. Environmental and social controversies have the potential to affect the profitability of investments, increase political risk and expose parties to reputational risk. Given the long lifespan of these assets, the impact of climate change on investments is now a prominent element for most major infrastructure investments whether private, public or public-private partnerships. / In recognition of these evolving financial market requirements, the DMO will need to have some familiarity with SRI approaches and application of social and environmental criteria in investment transactions. The Equator Principles, derived from the IFC’s policies and guidelines, are now the de factor industry standard for lenders who provide the bulk of project finance around the world (www.equator-principles.com). Other sources of guidance include the UNEP Finance Initiative, which is supported by many of the same financial institutions that apply the Equator Principles, and the IFC.
Environmental actions: (List the actions required to ensure that the risks are managed and the benefits and opportunities maximised.)
It is recommended that this environmental appraisal is shared with the DMO and the service provider. / Any infrastructure investment will accord to Government of Nigeria regulations but is also likely to need to recognise international practices. / It is recommended that some DMO staff seek a grounding in the basic elements of such practices, including the Equator Principles. The IFC may be an appropriate service provider. / Environment Adviser to be kept informed of progress of programme including reviews. / Have these actions been recorded in the: / Logframe? N / Project Memorandum? Y
Responsibilities: (Identify who is responsible for implementing the actions.)
The service provider is responsible for implementing the actions. DFID Nigeria is responsible for monitoring the service provider and dialogue with the DMO. / Have they been made aware of and confirmed their agreement to their responsibilities?
Monitoring and evaluation:

Section C – Sign off
Environment adviser: Seán Doolan	Date : 26 June 2008
Lead project officer: Lindsey Block	Date: 26 June 2008

ANNEX B: RISK MANAGEMENT FRAMEWORK

OVERALL RISK RATING: medium.
The non-project external risk of government commitment to sound economic management is the biggest risk factor.

Risk	Probability of Risk	Impact of Risk	Mitigating Strategy
Weak political will at state level for debt management reform.	Med	Med	Existing DMDs (5 five states) used as demonstration projects. / DMO develops carrot (assistance) and stick (on-lending requirements) approach.
DSA process not self-financing or sustained.	Low	Hi	Supervisory Board review of budget requirements.
Stakeholder/public buy-in not secured for domestic debt issuance/market development.	Low	Hi	Public awareness and public debt education program. / Speeches by Supervisory Board members.
Weak capacity in DMDs leads to unsustainable debt accumulation by states.	Med	Hi	Training and secondment programs to DMO from states. / Criteria for on-lending enforced.
High staff turnover, due to insufficient remuneration or other reasons weakens DMO capacity.	Med	Med	DMO secures higher salaries through independent revenue generation. / Improved performance management systems help incentives staff to pursue a career at DMO.
Performance management culture resisted by DMO staff - unable to monitor or evaluate impact of training.	Low	Med	Incentive for performance management enhanced by increased salary structure. / Internal seminars on system clarifying benefits to staff.
Poor monetary/fiscal policy coordination weakens effectiveness of domestic debt management.	Low	Med	DMO Supervisory Board common membership with the Monetary/Fiscal Policy Coordination Committee.
Supervisory Board not engaged with DMO, or has opposing views on policy direction.	Low	Med	Supervisory Board meets regularly and discusses issues. / DMO presents views of Board and in speeches.
MM/DM fail to provide continuous price discovery (ie, provide both buy and sell price quotes) in bond market.	Med	Med	Annual reviews (and spot checks) of MM/DM licenses. / Competitive public awards by DMO for high quality intermediation.
Corporate bond market fails to develop.	Med	Med	Banking finance of corporations’ short-term needs increase lenders and PD/MM familiarity with financial demands. / Credit rating of corporations.
Government bond issues crowd out private sector access to finance.	Low	Low	Inflation, not government finance biggest impediment to private sector debt finance. / Public awareness and public debt education program.
Government does not adopt an internationally recognised definition of concessioanlity and/or deviates from DMO’s borrowing advice.	Low	High	Educating legislators and policymakers on value of policy targets. / DMO fully reflects risks of unsustainable borrowing in advice presented to government.
Activities leading to independent revenue generation creates incentives to service external rather than domestic clients (such as States).	Med	Med	Robust business planning and resourcing of DMO activities.

ANNEX C: CONSULTATION RECORD

Project/Programme Documents must be circulated to those listed below for comment prior to submitting proposal for formal approval.

1. Inputs throughout design stage	Members of Design Team
Programme Manager/Project Officer / Main Sector Adviser / Cross Cutting Advisers / Key Partners	Kevin Quinlan, Team Leader Growth / Lindsey Block, Economic Adviser / Scott Caldwell, Governance Adviser / Debt Management Office
2. For proposals above £7.5M (use the checklist proportionally for proposals in the range of £1M - £7.5M):	Names of those consulted	Date consulted	Date responded
Relevant Advisers – [identify those consulted by discipline] / Economic Adviser / Governance Adviser / SD Adviser / Relevant Policy Division Team(s) [identify Team(s)] / Africa Regional Department - Sustainable Development and Climate Change / Deputy Director Programme Support who will consult as appropriate FCPD: RMG, PGG, AG, PrG / Evaluation Dept / Senior Humanitarian Adviser (for emergency & conflict handling projects) / Stakeholders: including Government, Civil Society, Other Donors, BE/BHC[4] / Head of Spending Department / Divisional Director	Lindsey Block / Scott Cadwell / Graham Gass / Abdulkareem Lawal / None / Sean Doolan / Jim McIntyre – PrG / Not Applicable / Not applicable / Govt Agencies (CBN, FMF etc) and donors during last annual review and design mission. / Eamon Cassidy	(drafted PM) / July 08 / July 08 / June 08 / May 08 / Dec 07 / July 08	July 08 / July 08 / June 08 / June 08 / Dec 07 / July 08
3. For all proposals that are politically sensitive, novel and/or contentious (regardless of value):	Names of those consulted	Date consulted	Date responded
Not applicable. This is essentially an extension of an existing project.
[4] A full list of GoN, Civil Society, Private Sector and Other Donors consulted is available on request

I confirm that the necessary consultation process has been undertaken, that papers have been circulated and all comments have, unless otherwise stated, been taken into account in the final documents.

Signed (Project Officer): Lindsey Block

Grade: A2

Date: 13/07/2008