UPDATED LOGFRAME FOR DMO III: 18 APRIL 2011
GOAL	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2011)
Debt management best practices institutionalised at both the national and sub-national level	National Debt Management Framework implemented and debt management-related legislation at the federal and state level adhered to	1. Legislation in place-DMO Act (being amended) 2. Medium Term Debt Strategy (MTDS) in place 2008-2012 and adhered to in the main 3. High Government Debt management capacity at the National Level 4. All 36 states have DMDs but only 4 have public debt management legislation (PDML) while others implement debt management only administratively. There is no discernible State specific debt strategy in most of the states		1. DMO Act amended 2. Continued high government debt management capacity 3. 10 states have passed PDML and developed a State-specific debt strategy		1. MTDS to be adhered to in full 2. Further 10 states have passed PDML and developed a State-specific debt strategy		1. DMO Act amended 2. MTDS clearly driving borrowing decisions and includes rigorous risk analysis 3. High debt management capacity maintained 4. 30 States have PDML and a State-specific debt strategy

		Gazetted legislation, Debt Management Performance Assessment (DeMPA)
	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
	Debt sustainability and portfolio indicators	ED:GDP = 2.46% DD:GDP = 13.54% Total Debt:GDP = 16.00% LT foreign IDR BB- Local currency IDR BB ST foreign currency IDR B Concessional borrowing at $2,682.39million representing 84.54% of multilateral creditors		1. Emphasis on Concessional borrowing to remain but predicated on maintaining debt sustainability 2. The Annual Debt Sustainability Analysis shows that Nigeria is at a low risk of debt distress. Debt:GDP ratio remains sustainable (i.e. below 40% benchmark for similar countries)		1. Emphasis on Concessional borrowing to remain but predicated on maintaining debt sustainability 2. The Annual Debt Sustainability Analysis shows that Nigeria is at a low risk of debt distress. Debt:GDP ratio remains sustainable (i.e. below 40% benchmark for similar countries)		1. Emphasis to remain on Concessional borrowing while maintaining sustainability 2. The Annual Debt Sustainability Analysis shows that Nigeria is at a low risk of debt distress. Debt:GDP ratio remains sustainable (i.e. below 40% benchmark for similar countries)
		Source
		Debt Management Office (DMO) debt sustainability analysis (DSA) reports, IMF Article IV Consultations, IMF Annual Debt Sustainability Analysis,

PURPOSE	Indicator	Baseline		Milestone 1		Milestone 2		Target (date)	Assumptions
To strengthen the sustainable capacity of the DMO to help meet its strategic objectives	Debt sustainability and portfolio indicators	See Goal above		1. Emphasis on Concessional borrowing to remain but predicated on maintaining debt sustainability / 2. Annual Debt Sustainability Analysis shows that Nigeria is at a low risk of debt distress. Debt:GDP ratio remains sustainable (i.e. below 40% benchmark for similar countries)		1. Emphasis on Concessional borrowing to remain but predicated on maintaining debt sustainability / 2. Annual Debt Sustainability Analysis shows that Nigeria is at a low risk of debt distress. Debt:GDP ratio remains sustainable (i.e. below 40% benchmark for similar countries)		1. Emphasis on Concessional borrowing to remain but predicated on maintaining debt sustainability 2. Annual Debt Sustainability Analysis shows that Nigeria is at a low risk of debt distress. Debt:GDP ratio remains sustainable (i.e. below 40% benchmark for similar countries)	1. Political disagreements between States and the Federal Government do not impair overall macroeconomic stability 2. Fiscal responsibility legislation is largely implemented throughout Government 3. There will be no change in the election date
		Source
		DMO Annual DSA and Debt Strategy, IMF Article IV, IMF Annual Debt Sustainability Analysis,
	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
	Well-functioning State level DMDs in all States	All 36 states have DMDs but only 4 have public debt management legislation (PDML) while others implement debt management only administratively. There is no discernible State specific debt strategy in most of the states		1. 10 states have passed PDML and developed a State-specific debt strategy 2. 10 states have completed collation and reconstruction of domestic debt data 3. State DMD officials attended training		1. Further 10 states have passed PDML by 2011 2. Further 12 states have completed collation and reconstruction of domestic debt data		30 States have PDML and a State-specific debt strategy 2. All states have completed collation and reconstruction of domestic debt data
		Source
		State Level Governments, public sector debt indicators
	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
	Competitive and efficient bond market	1. Active FGN bond market 2. 21 Primary Dealer / Market Makers (PDMMs) and other participants 3. Overall, majority of bonds trade at a premium		1. Maintain no. of participants (PDMMs) 2.Bonds will continue to trade at a premium 3. Approval on tax exempt for corporate bonds		1. Maintain no. of participants (PDMMs) 2.Further improvement in bond trading though still at a premium		1. Market has been able to retain existing no. participants (PDMMs) 2. Visible improvement on cost to government (change in yields) on FGN bonds
		Source
		DMO statistics, Primary Dealer feedback, trade data from Central Securities Clearance System
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 1. DMO enables an effective market for Nigeria’s domestic debt
Sub-Output 1.1	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)		Assumptions
Robust securities issuance and trading infrastructure in place to support the participation of a wide spectrum of the financial sector	IT systems in place in the DMO and Primary Dealer Market Makers (PDMM) and trades carried out using the new systems	Disparate, inefficient, non-tolerant, systems in use by the PDMMs and regulators resulting in weak integration, inefficient primary and secondary activities, lack of transparency, settlement challenges etc.		1. IT system identified and procured 2. All users received training in new system(s)		1. Complete integration of systems in the market 2. Procedures of secondary market activities standardised		Requisite IT infrastructure for the market acquired and in operation in the DMO and PDMMs and integrated.		1. Agreement between stakeholders on most appropriate trading platform is achieved 2. Other infrastructure is in place (e.g. back-up power sources)
		Source
		DMO, PDMMs, Central Securities Clearing System reports
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
10%	Volume of trades on primary and secondary markets	1. Active secondary market transaction activities in FGN bond with an average trade of over N1 trillion per month 2. weak Repo and securities lending activities [record of repos not captured separately; securities lending not commenced]		1. Increase monthly trade volume [by a further quarter of a trillion] 2. Master repo agreements signed by all PDMMs 3. Commence separate recording of repo activities 4.Increase in secondary market activities by not less than 20% 5. 20% increase in Repo transactions		1. Increase monthly trade volume by a further quarter of a trillion 2. Increase in secondary market activities by a further 20% 3. Engendering price discovery by: * installing a robust IT system * establishing of Inter Dealer Broker System (IDB) system 4. Further 20% increase in Repo transactions		1. Increase monthly trade volume [by over N1 trillion] 2.Master repo agreements signed by all PDMMs and 50% increase in Repo transactions 3. Increase in secondary market activities by 40% 4. Engendering price discovery by: * installing a robust IT system * establishing of IDB system
		Source								RISK RATING
		Debt Management Office statistics, Money Market Association of Nigeria								Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

Sub-Output 1.2	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)		Assumption
Expansion of the primary and secondary market for long-term domestic securities	Holders of long-term government securities	1. Banks, Pension (PFAs), CBN, Discount Houses, Non-Bank Public, Parastatals, Brokers, Special Funds and foreign investors. 2. Captive investors (banks, discount houses, etc hold 50%)		1. Captive investors to reduce to 40; non-captive investors to increase to 60%		1. Captive investors to reduce to 35; non-captive investors to increase to 65%		1. Captive investors to reduce to 30; non-captive investors to increase to 70%		1. Collaboration between all stakeholders in Government and the markets (CBN, PDMMs, SEC) 2. Demand exists for new instruments (particularly 'exotic' instruments such as derivatives) 3. Limited impact of financial crisis and no adverse impact from banking reforms

		Debt Management Office statistics, Central Securities Clearing System reports
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
15%	Type of instruments issued by the DMO	1. 3, 5, 7, 10, 15 and 20 -year FGN bonds currently issued 2. Plain vanilla FGN bonds currently issued by the DMO; 3. Active spot trading.		1.maintenance of 20-year bonds 2. Introduction of new products e.g.., floating rate bonds 3. Engender more active secondary market products		Introduction of other new products		1. Deepen 20-year yield curve FGN bond varieties of instruments in the market 2. Introduction of new products e.g.., floating rate bonds 3. Engender more active secondary market products
		Source								RISK RATING
		Debt Management Office statistics								Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 2. DMO improves state-level debt management through support to Debt Management Departments (DMDs)
Sub-Output 2.1	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)		Assumption
Debt management departments (DMD) in all 36 States have trained staff and accurate debt records	Number of States whose officials have received training in basic debt management principles	1. Staff of 34 of the 36 States' DMDs have received basic debt management training 2. Staff from 36 States have had an attachment at the DMO		1. Staff from all 36 States have received basic training				1. Staff from all 36 States have received further basic training 2. Staff from all 36 States have had an attachment to the DMO		1. Political commitment at State Level 2. Adequate resources in DMDs at State Level (e.g. staff assigned to debt management, supporting infrastructure in place) 3. Availability and capability of DMO staff to design, deliver and monitor training activities
		Source
		Debt Management Office, State Level Governments
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
15%	Verified database of loans in all States, reconciled with DMO records	Reconstruction of Domestic debt not done		Collation and reconstruction of records of debts of 10 States		Collation and reconstruction of records of debts of further 12 States		Collation and reconstruction of records of debts of all States and reconciled with DMO records
		Source								RISK RATING
		State Level Governments, DMO records								Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

Sub-Output 2.2	Indicator	Baseline		Milestone 1 (2010)		Milestone 2		Target (2011)		Assumptions
Development and implementation of guidelines for on-lending and Federal guarantees to States	Number and nature of guarantees issued	About 312 guarantees to states on health, agriculture, social development, education and community based poverty reduction 1. Back to back guarantee 2. All external debt by the states are guaranteed by the FGN 3. Very few domestic debt guaranteed by FGN		1. All government guarantees on domestic debt collated and recorded 2. Standardised framework on government guarantees developed				1. All government guarantees on domestic debt collated and recorded 2. Standardised framework on government guarantees developed 3. All guarantees issued follow standardised framework on government guarantee.		1. Political commitment of Federal and State level Governments 2. Effective coordination between the DMO and DMDs
		Source
		Debt Management Office reports, State Level Governments, NPC reports
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2		Target (2011)
5%	Nature of on-lending agreements	1. External on-lending is pass through 2. Back to back collateral for the on-lending to States (tied to FAAC allocation) 3. There is an on-lending strategy in the National Debt Management framework		Detailed on-lending framework developed				All stakeholders are sensitised and educated on the on-lending framework.
		Source								RISK RATING
		Debt Management Office reports, State Level Governments, NPC reports								Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 3. DMO Facilitates Nigeria’s external debt sustainability and establishes a viable presence in the international capital market
Sub-Output 3.1	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2011)	Assumption
Risk management strategy codified that guides borrowing decisions through the medium term debt strategy	Medium term debt strategy guiding borrowing decisions (comparison with planned against actual)	Medium-term borrowing plan exists but no strategy that incorporates statistical analysis of different funding scenarios		A medium-term debt strategy produced by the DMO with rigorous risk analysis demonstrating the impact of different funding scenarios		Updated medium-term debt strategy comparing actual borrowing decisions against the scenarios		Borrowing strategy developed taking account of risk analysis and comparisons of different scenarios	1. Debt strategy supported outside of the Debt Management Office
		Source
		Debt Management Office Strategy, Annual Report and issuance calendar
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
5%	Clearly articulated risk management strategy and codified procedures in place	1. Risk management strategy/models in the process of being codified into an implementable framework.		1. Risk management framework finalised and signed off by the DG that defines risk tolerances 2. Expectations of the RMU clearly defined and processes for carrying out risk analysis codified		Risk analysis incorporated into debt strategy and analysis carried out for the DSA		Risk management framework published on DMO website and risk analysis incorporated into the DMO’s borrowing decisions.
		Source							RISK RATING
		Debt Management Office (Risk Management Unit, Organisational Resource Department)							Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

Sub-Output 3.2	Indicator	Baseline		Milestone 1 (2010)		Milestone 2		Target (2011)	Assumptions
Issuance of guarantees and support for PPPs based on rigorous analysis	Existence of guidelines for the evaluation and treatment of contingent liabilities (including Public Private Partnerships - PPPs)	No current framework on contingent liabilities; being put together		Framework on contingent liabilities and PPPs completed				Decisions to issue guarantees/ support for PPPs is based on rigorous analysis in line with the contingent liability framework	1. Participation of other relevant government agencies and agreement on the guidelines achieved 2. DMO advice sought and taken by the Government
		Source
		Debt Management Office
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2011)
5%	Reliable data on contingent liabilities and PPPs	Incomplete data on contingent liabilities and PPPs; this is not reported		Data on PPPs collated and reported in DMO annual report		Data on PPPs revalidated and reported in DMO annual report		Reliable data on contingent liabilities and PPPs reported in DMO Annual Report
		Source							RISK RATING
									Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

Sub-Output 3.3	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2011)	Assumption
Issuance of international bond and establishment of benchmark yield curve	Bond issued on international markets	FGN bond yet to be issued in the international market		Naira denominated bond issued in the international market		Trading in Naira denominated bonds		Continued Trading in Naira denominated bonds	1. Favourable international market conditions 2. Absence of political uncertainty
		Source
		DMO reports, international statistics (BIS, IMF)
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2011)
10%	Existence of benchmark yield curve	Currently a benchmark on domestic debt market of up to 20 years exists but not on international issuances		Establish yield curve on ICM through international bond issuance (following Naira issuance)		Establish secondary market pricing (price discovery)		Benchmark yield curve for Government of Nigeria bonds on international capital markets (Naira and other currencies)
		Source							RISK RATING
		DMO reports, international statistics (BIS, IMF)							High
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 4. DMO contributes to a more conducive and supportive institutional environment for efficient and sustainable debt management practices in Nigeria
Sub-Output 4.1	Indicator	Baseline		Milestone 1		Milestone 2		Target (2011)	Assumption
Debt issuance/ contracting driven by the debt strategy that is agreed on by all relevant stakeholders and governed by appropriate legislation	Debt strategy document, assessment of debt strategy (DeMPA)	1. MTDS recently produced but not institutionalised and borrowing plan loosely derived from MTDS 2. DeMPA scored DMO as C for debt strategy		1. MTDS and other risk analysis tools used to forecast market risks, including currency risk 2. Acceptance of relevant stakeholders of debt strategy scenarios and publication of risk analysis in the debt strategy		1. Annual review of MTDS carried out and review of strategy against actual borrowing 2. Market risk forecasts and methodologies revalidated		Debt strategy independently assessed as B or higher under DeMPA criteria	1. Agencies other than the DMO support the debt strategy process 2. Support for the amendments to the DMO Act across Government 3. Political support at State level for fiscal responsibility legislation
		Source
		Debt Management Office Annual Report, Debt Strategy
	Indicator	Baseline		Milestone 1		Milestone 2		Target (2010)
	Amended DMO Act passed by the National Assembly	DMO Act at the Public hearing stage at the House of Representatives		Amendment of the Act				Amended Act passed into law
		Source
		National Assembly records, legislative
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
15%	Integration of debt and cash management	Unstructured coordination (Committee) of debt and cash management		1. Assessment produced on current debt and cash management practices 2. Standardised debt and cash management framework developed		Relevant stakeholders on cash management sensitised and educated
		Source							RISK RATING
		Debt Management Office							Medium
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

Sub-Output 4.2	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2010)		Target (date)	Assumptions
Performance management framework embedded throughout the DMO	Staff appraisals linked with staff development plans for all staff	DMO appraises its members of staff quarterly and yearly but this has not been linked to staff development/reward system.		Existing appraisal system evaluated and new framework agreed with Organisational and Resourcing Department (ORD)		Performance management and reward framework agreed and implemented by all staff		1. Staff development activities clearly aimed at addressing development points highlighted in appraisals 2. Action plans developed by staff detailing how development activities will be adopted in the workplace	1. Staff salaries aligned to those of Central Bank of Nigeria 2. Revised DMO Act passed by the National Assembly
		Source
		Debt Management Office (Organisational Resource Department)
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2 (2011)		Target (2012)
10%	Staff retention	High staff turnover currently prevalent, e.g. 20 members of staff (over 16%) left the DMO between 2007 and 2009		Staff retention improved - from current turnover - to 10%		Staff retention further improved - from baseline turnover rate - to 5%		Staff retention further improved - from baseline rate of turnover - to 2%
		Source							RISK RATING
		Debt Management Office (Organisational Resource Department); staff engagement survey to be carried out by project, new DeMPA							Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

Sub-Output 4.3	Indicator	Baseline		Milestone 1 (2010)		Milestone 2		Target (2011)	Assumptions
DMO's ICT infrastructure upgraded to support all debt operations and systems (including CS-DRMS)	Feedback from staff on response rates of systems and IT support	1. No standardised ICT framework 2. Limited interface of DMO ICT and systems of other stakeholders, e.g. CBN, NSE. 3.Limitations of CS-DRMS in recording NTBs and bonds with reopenings		1. Standardised IT framework developed setting out response expectations 2. Linkages between DMO ICT system and other stakeholders established to automate some processes 3. Modified CS-DRMS to support reopenings				1. Staff feedback indicates improved system support and response times 2. Re-evaluated CS-DRMS and eliminated limitations in recording NTBs and bonds with reopenings	1. Steady power supply secured 2. Appropriate hardware is available
		Source
		Debt Management Office staff feedback and information from IT Department
IMPACT WEIGHTING	Indicator	Baseline		Milestone 1 (2010)		Milestone 2		Target (2011)
10%	Accurate and timely data reports	Data reports delayed typically by 2 weeks to a month depending on the instrument type		1. Linkages between DMO ICT system and other stakeholders established to automate some processes 2. Lag between data production and publication cut to 5 days				Lag between data production and publication cut to 1 day
		Source							RISK RATING
		Debt Management Office - feedback from staff							Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)