Type of Review: Project Completion Review

Project Title: PHASE III SUPPORT OF NIGERIA’S DEBT MANAGEMENT OFFICE

Date started:	August 2009	Date review undertaken: February 2013

 Introduction and Context

What support is the UK providing?
The UK is providing assistance to Nigeria’s Federal Debt Management Office (DMO), building on previous phases of support, to help the debt office progress on a more sustainable path. To help achieve this, the UK is providing support to the DMO to implement its strategic plan 2008 – 2012, help institutionalise macroeconomic stability, build capacity for sub-national debt management and help strengthen Nigeria’s position as a global emerging market. This phase has a budget of £2.6 million over 3 years.

What are the expected results?
The UK support will help transform the DMO into a modern institution that is equipped to handle all debt management operations in an effective manner. Through a strong institution and professional cadre, debt management best practices will be established at both the national and sub-national levels of government. The DMO will transform from being a user of external technical assistance to a provider of technical assistance. / Under the 4 outputs in particular, the Project would support the DMO in achieving the following: / An effective market for Nigeria’s domestic debt / Improved state-level debt management through support to State Government Debt Management Departments / Facilitating Nigeria’s external debt sustainability while establishing a viable presence in the international capital market. / Contributing to a more conducive and supportive institutional environment for efficient and sustainable debt management practices in Nigeria

What is the context in which UK support is provided?
Nigeria’s Federal Government does not need to borrow on either domestic or external financial markets in order to finance its national development. Almost every year the country accrues oil revenue savings beyond those that are spent through the Federal Budget. Yet to achieve better governance and accountability, as well as international credibility, the various sources of finance that contribute to the country’s expenditure matter. Oil revenue in Nigeria has traditionally had very limited accountability attached to it and has led to a range of poor governance issues as detailed under the ‘resource curse’ literature. Financing expenditure by borrowing from both the domestic and external financial markets imposes a fiscal discipline on public expenditure. Markets demand to be paid back, need to see good public financial management, and are far less forgiving to fiscal indiscipline than a system of financing budgets from oil and gas revenues. / The UK has provided support to the Nigerian Government’s debt management since 1998 at a time when Nigeria’s interaction with the international community had stalled, the country’s external debt burden has ballooned to $34 billion and public debt management was outright inefficient. Such initial support was instrumental in consolidating debt management functions under a new DMO. It also enabled Nigeria’s historic exit from the Paris Club in 2005. The third phase of UK support delivered over the last 3 years will transform the DMO from an institution that has traditionally relied on external TA and capacity building to one that is equipped to build capacity in the 36 States in Nigeria and become a hub of good practice in Africa. Assistance to the DMO would also contribute to efforts at achieving macroeconomic stability in the country. Despite the challenges faced by Nigeria on both the economic and social front and the pressure to increase borrowing domestically to support the budget deficit, the DMO has been able to operate soundly while adhering to its basic principles. Being increasingly saddled with added responsibilities by the Federal Ministry of Finance is a sign of the maturity of the DMO and the increasing role that it is called upon to play in the wider economic management of the country.

## Section A: Detailed Output Scoring

Output 1: DMO delivers an effective market for Nigeria’s domestic debt
Output 1 score and performance description: / Score: A (Output met expectations) / Output 1 required the development of robust securities issuance and trading infrastructure to support the participation of a wide spectrum of the financial sector, year on year increases in the volumes of trade on the primary and secondary markets, and expansion of the primary and secondary markets for long-term domestic securities. This was expected to require improvements in IT systems and infrastructure employed by the DMO and PDMMs, improvements in the volumes of trades on primary and secondary markets, and expansion of the primary and secondary market for long-term domestic securities by type and share of holders, as well as the types of instruments issued by the DMO. / Prior to the start of the project in 2009, the DMO and PDMMs relied on disparate, inefficient, and non-tolerant systems that resulted in weak integration, inefficient primary and secondary activities, lack of transparency, settlement challenges etc. Active secondary market transaction activities in FGN bonds amounted to an average monthly trade of about N1 trillion and Repo and securities lending activities were very weak. Captive investors (banks, discount houses, etc.) dominated the bond markets, holding an over 60% share, and the markets consisted mostly of short to medium term instruments (0-7 years).
Progress against expected results: / Over the course of the project, the DMO (applying its strategic plan and leveraging on Project III support) has largely succeeded in meeting the project objectives to broaden and deepen the domestic bond market. This was largely achieved through improvements in its IT infrastructure, the introduction of a variety of government securities, and improving its internal capacity as well as the regulatory framework for effective operations of the domestic bond market. / Nigeria’s bond market development has also benefited from the lifting of the 1 Year holding period restrictions on FGN bonds by the CBN in 2011 and a hike in interest rates, leading to attractive yields, and ultimately the addition of Nigerian Bonds to JPMorgan’s GBI-EM and the Barclays EMLC index. Yields on Nigeria’s naira-denominated 10-year bonds due in 2022 have fallen from 16.39% in August 2012 to 11.22% at the start of February 2013. This is also reflected in the decision by S&P to upgrade Nigeria’s long term foreign and local currency sovereign credit rating in 2012 to BB- in line with Fitch’s rating. Fellow ratings agency Moody's also expanded its coverage to include Nigeria in 2012, assigning a Ba3 rating with a stable outlook. / Capacity training, IT upgrades, enhanced consultations, and the development of standardised and documented procedures for primary and secondary market activities have contributed to largely transparent and predictable domestic debt market operations. Capacity building training on various IT features and developments for staff and stakeholders (including sub-nationals’ officials), included use of CS-DRMS, the Matrix Laboratory (MATLAB) tool, SAP, Advanced Excel, etc. General enhancements to the DMO’s IT infrastructure to consolidate and improve power supply, data storage and security (physical and cyber) were carried out with the assistance of the project. The internal DMO e-mail infrastructure and electronic document management system projects have also been successfully completed and are now gradually being put into operation. / The DMO has also finally received Presidential approval for the adoption of a new IT platform for auctioning FGN bonds, a major milestone for the project, and is now pursuing the necessary due process clearance. The review of the best auction platform for the DMO was one of the first activities under the project (Phase III). Progress in this area, as with other areas that involve stakeholders components/involvement, has been slow due to the limitations of the DMO’s and the Project’s control and influence over the external elements. / The constant refrain from all the stakeholders the reviewers met with referred to the transparency, reliability and responsiveness of the DMO and its operations. Debt management decisions are guided by the published Strategic Framework for Debt Management 2008-2012 (now replaced by the 2013-2017 edition) and from 2013 the draft Medium Term Debt Management Strategy (MTDS). An annual borrowing plan is prepared at the start of the financial year and shared with PDMMs (and published for each quarter in advance). A T-bond issuance calendar is shared a month in advance with PDMMs and is published on the DMO website. A revised debt recording manual was developed in 2008 and updated in 2010 and 2012. There are now also guidelines and frameworks on loan guarantees and on-lending, and for sinking funds (there is a provision of N100 billion in the 2013 national budget towards this fund). And a Master Repo Agreement was likewise developed during the period and all PDMMs have now signed on. Since the last annual project review (September 2011), the Monetary and Fiscal Policy Coordinating Committee (MFPCC) hosted by the DMO has resumed meeting quarterly to help with the coordination of monetary and fiscal policies. / The DMO continues to introduce new and innovative instruments into the market. In 2011, the FGN through the DMO developed and issued Sovereign Debt Notes (SDN), under the Petroleum Support Fund (PSF), to resolve the problem of scarcity of premium motor spirit (petrol) occasioned by late payment of subsidy to oil marketers. Similarly, approvals have been obtained for the issuance and redemption of the new FGN Commercial Papers (FGN Cash Adjustment Note), pending the launch of the Treasury Single Account (TSA). The introduction of commercial papers was first recommended in 2010 by a Project consultant. / However, trade volumes in the secondary market have declined over the period, from 132,374 transactions with a face value of N16.79 trillion to 44,822 valued at N7.35 trillion in 2012, again due to largely external macro-economic factors. The secondary market bond trading volume is nevertheless set to grow in 2013 as retail investors who are interested in FGN sovereign bonds can now trade through the secondary market, with the recent appointment of Stanbic IBTC Stockbrokers Ltd to manage the bonds. The trading of FGN Bonds on the Floor of the Nigerian Stock Exchange (NSE) has since increased from Nil transactions for the most part of July-October, 2012, to 4,750 transactions (with a face value of N4.75mn) in December 2012. / The number of PDMMs has remained relatively unchanged. There are now 18 (13 Commercial Banks, 1 Merchant Bank, and 4 Discount Houses); there were 2 mergers and 1 (bank) was taken over by the Central Bank during its intervention following the banking sector reforms. And the share of captive investors is just above the 50% mark (the 30% target of the Project log-frame was overly ambitious) / Recommendations: / The DMO should be encouraged to continue to pursue the acquisition of the new IT Auction Platform. DFID may wish to monitor the progress with this component in the event that upon acquisition the DMO may benefit from expert technical assistance with the installation and testing. / Similarly, the DMO should be encouraged to embrace the new internal DMO e-mail infrastructure and electronic document management systems and integrate them into their activities accordingly. / As one of the last key activities supported by the project, the DMO is looking to upgrade the platform for carrying out the re-opening of FGN bonds including a new FGN Bond Application form and Template, as well as the upgrade to enable the integration of the DMO’s CS-DRMS with the CBN’s T-24 system. This should be pursued vigorously as it will minimize errors in the computation of commissions to PDMMs etc., and make substantial reductions in the time in which the auction is conducted and the release of results to the market. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: Low/Medium/High: Low / Revised since last Annual Review? No

Output 2: DMO improves state-level debt management through support to State Government Debt Management Departments (DMDs).
Output 2 score and performance description: / Score: A (Output met expectations) / Output 2 aimed to facilitate the establishment of Debt Management Departments (DMD) and staff capacity in all 36 states (and the FCT) with a verified database of sub-national debt stock, as well as the development and implementation of guidelines for on-lending and Federal guarantees to States. This element has been a particular focus of the DMO Strategic Plan 2008-2012 and is carried on in the 2013-2017 Plan and the Project provided indirect support to all states via the initiative and direct support on DDR and PDDR to 11 and 6 states respectively. The DMO has engendered a productive working relationship with all the States (and the FCT), carried out extensive capacity building training (supported by the Project) for state officials, and completed Debt Data Reconstruction (DDR) exercises for all 36 states and the FCT and Post-Debt Data Reconstruction (PDDR) exercises in 22 states.
Progress against expected results: / All 36 state Debt Management Departments have been established based on the template developed by the DMO with Project support. Furthermore, the DMO has assisted the states in developing the necessary supporting legislation and by January 2013 18 states had enacted one form of legislation or the other (8 states have an operational PDML, 8 states have a FRL and 2 states have passed both laws). 15 States have commenced the process and are in different stages of completion (3 states have passed the FRL and are awaiting executive assent, 8 states have presented draft legislation to their state assemblies, and 4 states have drafted legislation). / Officials from all 36 state DMDs (and the FCT) have participated in various training and capacity building exercises, including in debt management principles, econometrics, CS-RDMS, DSA, etc. Debt Data Reconstruction (DDR) exercises for state domestic debt have been completed in all 36 states and the FCT, and 22 states have since successfully carried out Post DDR exercises. On external debt the final reconciliation and refund to states on previous London Club debt buyback was completed in 2011. / As part of the review exercise, the reviewers met with a cross-section of the heads of some state DMDs and observed that while there is still scope and need for continued support, the states are now starting to take on more ownership and responsibility for the initiative and even expanding their operations independently in some cases. / The DMO confirmed that sub-national borrowing guidelines, including on-lending and Federal Government guarantee have been developed and key stakeholders have been sensitised and educated on their specifics. The Framework for the issuance of FGN guarantees for the private sector has also been developed and is awaiting Ministerial approval, while one for the issuance of FGN guarantees to FGN public sector MDAs is yet to be developed but under consideration. / Recommendations: / The project should explore potential synergies with other development partners (WAIFEM, the Commonwealth Secretariat, World Bank and IMF, etc.) and state level programmes, such as SPARC, to build on the progress with the states, including moving beyond the collection of data to consolidation of some other aspects of debt management including debt analysis and debt sustainability. / The DMO should be encouraged to continue to pursue the pending approvals for issuance of FGN guarantees for the private sector and develop the framework for issuance of guarantees to public sector MDAs. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High: Low / Revised since last Annual Review? No

Output 3: DMO facilitates Nigeria’s external debt sustainability while establishing a viable presence in the international capital market.
Output 3 score and performance description: / Score: A (Output met expectations) / Output 3 sought to have the national risk management strategy codified, enhanced risk management analysis, and re-engagement with the international capital market, with an established benchmark yield curve. To this end, the Project provided expert training and capacity building support in risk management analysis, contributed to the development and execution of the annual Debt Sustainability Analysis exercise and development of a Medium Term Debt Management Strategy (MTDMS), as well as facilitating training on Public Private Partnerships (PPPs) and contingent liabilities among others (see Project Activities Breakdown).
Progress against expected results: / As at December 2012, Nigeria’s total debt stock stood at US$48.496 billion with external debt accounting for 13.5% of the total (mainly concessional loans which made up 80.7%). The Debt/GDP Ratio at 19.7% is well within the 40% threshold adopted in the Strategic Plan and MTDS. / As yet, no Naira denominated bond has been issued. But trading of the 10-years $500 million Euro bond issued in 2011 is currently on and a weekly report of the bonds performance in terms of yields and price is published on the DMO website. The FGN further plans to issue a $1 billion Eurobond in 2013, a $100 million Nigeria Diaspora Bonds, and N80 billion (about $500m) of FGN Bonds in Global Depository Notes (GDN) format, which are awaiting due approvals. This forms part of its debt management strategy of achieving a target ratio of 60% (Domestic) and 40% (External) distribution in its Debt Stock. / The DMO has adopted a draft Medium Term Debt Management Strategy (MTDMS), developed with the assistance of a WB expert and capacity training from the Project, that is awaiting Board, Presidential and Federal Executive Council approval. In the meantime, the DMO has already begun to implement aspects of it and was commended by the WB in 2012. / DSA has been carried out annually for the last 11 years and the number of scenarios considered has been increased from 2 to 4 in 2012. The analysis results, with concurrence from the World Bank’s assessment, concluded that Nigeria’s medium-term debt outlook remains healthy. / In other efforts to strengthen its debt management capacity and systems, Nigeria is currently in the process of undertaking its first Public Expenditure Financial Accountability Framework (PEFA) assessment; and a template risk management framework for the DMO for handling operational risks has been developed with support from the Project. Capacity building training on PPP and related contingent liabilities also continue to be pursued by the DMO with the support of the Project, and with the help secured from the Turkish Treasury, a training programme on risk modelling using the MATLAB platform took place in January 2013. This training was designed to expose DMO staff to the effective use of the MATLAB software in deriving the term structure of interest rates and build FGN Sovereign Bond Yield Curve; a skill requirement that was raised by stakeholders such as the CBN and PDMMs during the review exercise. / Recommendations: / The DMO should be encouraged to continue to pursue the pending approvals for the draft Medium Term Debt Management Strategy (MTDS), even as they are already guided by it. / Similarly, the DMO should be encouraged to continue to apply the recently acquired skills on PPP and related contingent liabilities and deriving the sovereign Yield Curve. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? No

Output 4: DMO contributes to a more conducive and supportive institutional environment for efficient and sustainable debt management practices in Nigeria.
Output 4 score and performance description: / Score: A (Output met expectations) / The framework provided by the MTDS was endorsed by the DMO with the preparation of its second strategic plan which coincided with the start of the Project Phase III and has been the basis for its borrowing strategy since. The project has worked to enhance the DMO’s analytical capacity, including in evaluating options to maintain an optimal debt portfolio. In 2008, the World Bank conducted a Debt Management Performance Assessment exercise rating Nigeria a ‘C’ overall, citing several areas of weaknesses. A follow-up exercise has since been conducted in 2012. / In addition to the institutional elements, the project sought to enhance the human capacity elements of the DMO to achieve the objective of developing a more conducive and supportive environment for efficient and sustainable DM practice in Nigeria. This support was tailored to contribute to long term staff development as well as operational processes and infrastructure, notably in ICT.
Progress against expected results: / Among some of the developments that Project sponsored training, capacity building and support activities have contributed to; A new draft DMO Strategic Plan (2013-2017) will be presented to the DMO Board in March 2013 for approval, while a draft MTDS for the period 2012-2015 has also been prepared and operationalized (with some assistance from WAIFEM). They, however, still require formal approval at ministerial and Federal Executive level. The performance of a national DSA exercise has become an annual event and the 11th DSA is planned for May 2013. This will eventually be extended to include DSA exercises for all states as well in future for which the DMO is already building capacity in the states through training and basic DSA exercises. / The DMO scored very highly for managerial set-up, debt management operations, and domestic and external borrowing practices in the 2012 WB Debt Management Performance Assessment (DeMPA), with substantial improvements noted in the management of operational risks, and debt reporting compared to the 2008 exercise. However, there is still some work to be done to raise Nigeria’s overall DeMPA performance to A/B across the board, notably in formalizing some processes, cash forecasting, and external audit. / The need for the DMO to have a robust IT system and recommendation of the right platform was made by the Project at the start of Phase III. This built upon a first assessment initially undertaken by the DMO. The on-going improvement of the IT platform is a clear illustration of how the DMO have used the Project support as an important catalyst to drive forward on its own the necessary modernisation in the existing institutional set up. / Targeted improvements were made to the DMO ICT infrastructure throughout the project phase III and these have contributed significantly to improvements in efficiency and delivery both internally and externally. External/collaborative system upgrades included the improvements to integrate the upload of auction results from the CBN’s T-24 auctioning module to the DMO’s CS-DRMS using the XML tool. Another successful upgrade under the project was on the DMO’s SAP system for accounting and personnel management in 2011. / The project supported staff appraisal and career development system is now in place, but hasn’t had a chance to be tried and assessed in practice. This has gradually been adopted across the DMO and contributed to the organisational restructuring and reassignment exercise in January 2013. It is expected that this reorganisation will streamline the DMO internal structure for greater efficiency and effectiveness. To complement this, new email and document management systems have been introduced after some initial delays and now provide the DMO with a single sign-on authentication and email system, and a robust document management platform. However, just as with the appraisal and personnel development systems, they have only just been introduced and therefore not tested. / One area of concern identified at the start of phase III, and expressed by stakeholders interviewed by the reviewers was the relatively high staff turnover (>16% baseline level recorded in 2009) and rotation rates at the DMO. At the time of this review the staff strength was 122 (permanent) staff; the same level as in 2009, with a high of 130 in 2011. The number of contract staff has been reduced from 12 to 4 in the same period. Staff redeployments within the DMO took place year on year in the preceding 3 years (24, 21 and 63 in 2009, 2010, and 2011 respectively). It is worth noting that the late 2011 redeployment exercise followed the start of the staff evaluation exercise and is part of the DMO’s HR strategy to provide all-round practical DM familiarization to its staff. / As recommended in the last project annual review, a comprehensive communications strategy and action plan has since been be developed, including an operations manual. Other actions include the creation of a public affairs unit, the conversion of the PDMI into a training unit, and a Monitoring and Evaluation (M&E) unit in the DG’s office. These are to further enhance the ability of the DMO to deliver on its mandate and enable it operate with greater efficiency and improved service delivery to the satisfaction of both its internal and external stakeholders. / Recommendations: / The DMO should be encouraged to complete and operationalize the development & implementation of the Employee Shared Services Portal (ESS) to take advantage of the SharePoint and Electronic Document Management System already deployed in the DMO, to provide a cost effective enterprise-wide, web-enabled Human Resource Management System. / There is still some work to be done to raise Nigeria’s overall DeMPA performance to A/B across the board, particularly with regard to cash forecasting and external audits. DFID may wish to explore DMO’s capacity in such areas as cash forecasting as an addition to previous cash management training. / The staff appraisal and career development system, new email and document management systems need to be applied, monitored and evaluated to ensure they are all meeting the expected objectives. / Similarly, public affairs, training, and monitoring and evaluation (M&E) units remain untested and should be monitored closely. / Impact Weighting (%): 35% / Revised since last Annual Review? No / Risk: Low/Medium/High: Low / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Y/N / No / 1.2 Overall Output Score and Description: / Score A – Overall, outputs met expectations. / 1.3 Direct feedback from beneficiaries / The staff and management of the DMO, as well as the participating stakeholders met by the reviewers, were overwhelmingly positive and complimentary of the support and conduct of the project, the project manager (Crown Agents), and DFID-Nigeria. Of particular note was the flexibility and consultative nature of the intervention which allowed all parties to take co-ownership and contribute towards the accomplishments of the objectives. The other notable feature of the intervention was its complementarity to the DMO’s existing Strategic Plans.
1.4 Summary of overall progress / Overall, DFID support under the project has been effective, and the project has met virtually all of its objectives and has provided value for money. The DMO has come a long way since its establishment, turning from a technical assistance (TA) user to also a TA provider. The DFID Project has played a major role in this progress. DFID’s support in Phase III has focused primarily on training and capacity building and ICT consolidation which have enhanced efficiency and economy, and which have been associated with growing skills, greater professionalism, and a build-up in long-term human capital, consistent with economic development principles which stress the critical role of institutions.
1.5 Key challenges / A number of the frameworks and processes developed and adopted during the course of the project remain untested. / The staff appraisal system was originally prepared in 2011, trialled and revised in 2012, and has only recently been applied and so remains untested. A similar situation exists with the untried staff development system. This may be in part because of the reliance of the DMO on the Project to provide capacity development / training which appears to affect their ability to plan ahead. / TA/Capacity Building through visiting experts were/are not maximised when conducted in residence due to the tendency for interference/distractions from daily operations. / Digitization of old and existing paper-based records and contracts appears to have stalled. / Sensitizing stakeholders, particularly the national and state legislatures, key political officials and the media in a cost-effective manner. The establishment of a dedicated Public Affairs Unit in the DG’s office should help focus this activity, but should ideally be guided by a defined strategy. / Maintaining the momentum at sub-national level given the Federal structure in Nigeria requires the DMO to invest heavily in building and maintaining its goodwill, networks, and persuasiveness. / Legislation and formalization/approval processes required to cement a number of documents and guidelines produced and adopted by the DMO are dependent of external institutions that are not subject to DMO control. These include the formal adoption of the draft MTDS, Guarantees Frameworks, legislation at Federal (e.g. the DMO Amendment Act) and state (e.g. FRL/PDML) levels, or large-scale purchases/investments (like the new auction platform).
1.6 Annual Outcome Assessment / N/A

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / Yes. Although the project was expected to be completed on schedule in July 2012, the project was extended till March 2013 in order to handle the phase-out of DFID support and to commission an independent project completion evaluation that considers the full 15 years of DFID support to Nigeria’s debt management. / 2.2 Key cost drivers / Providing targeted capacity building to staff. Enabling DMO staff to build capacity of state-level staff. Some select ICT infrastructure to enhance the effectiveness of debt-management. / 2.3 Is the project on-track against original timescale: Y/N / No. (see section 2.1)

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No changes in evidence base. / 3.2 Where an evaluation is planned what progress has been made? / An independent evaluation is proposed to take place in mid-2013 which will consider the full 15 years of DFID support to Nigeria’s debt management. It will look at successes, challenges and lessons about long-term capacity building with institutions.
4. Risk
4.1 Output Risk Rating: Low/Medium/High / Low / 4.2 Assessment of the risk level
Risk to outputs is low given the long-track record of partnering with the Debt Management Office, and the commitment of the current Director General (who has just had his term extended by the President), and the Ministry of Finance. / Risk of funds not being used as intended / Medium - A project team housed in DMO put together all proposals activities -these were then developed with the help and support of Crown Agents. There is a project steering committee which includes DMO, DFID and Crown Agents to help review progress and steer the direction of future support. / 4.4 Climate and Environment Risk / N/A

5. Value for Money
5.1 Performance on VfM measures / Value for money is considered through three “E”s—effectiveness, efficiency and economy of the programme, all of which demonstrate good value for money for the DFID-funded DMO III project. The total quantified annual value for money in 2012 is estimated at US$37 million, or £23.2 million. (Table 5.1) / Effectiveness Measures / The benefits for Nigeria of having an effective DMO are first and foremost lower borrowing costs both domestically and internationally. / The impact of the inclusion of Nigerian government bonds in the J P Morgan Government Bond Index for EMs is estimated to have resulted in a reduction of 400 basis points in the yield of such bonds. Assuming that only 100 basis points can be attributed to DMO III (100 basis points can be attributable to government policies, 100 basis points to World Bank support and training, and 100 basis point to the DMO) and applying the reduction to the last five months August-December) of 2012 will very conservatively yield a saving of US$ 8.6 million, or £5.4 million (such saving would be higher on a full year basis going forward). / Consider that an outside agency were to issue treasury securities and charge a fee. The reviewers thus propose a “minimalist” approach to assessing value for money of DFID’s support to the DMO taking into account attribution issues. It is thus assumed that the improved performance of the DMO in issuing debt instruments saves the treasury 0.1-0.2 percent in debt service costs annually. Such a “management fee” is generally on the low side by the standards of participants in the market for debt instruments (a minimum fee would typically be 0.25 of one percent). / Consider Nigeria’s external debt. Total external debt at end-December 2012 amounted to US$6.5 million, of which 500 million was on commercial terms—the 10-year Eurobond issue. Given that the lion’s share of the external debt is concessional, we focus on the US$500 million of the Eurobond. On this basis, the annual saving is US$0.5-1.0 million. It is also worth noting that the Eurobond issue, which had a coupon rate of 6.75 percent and an initial yield of 7.0 percent, was trading at a range of 3.75—3.8 percent in early February 2013, well below the yield on Italy’s 10-year government bonds! / Consider now Nigeria’s domestic debt. Total domestic debt at end December 2012 amounted to 6.54 trillion naira, equivalent to US$42,380 million, of which T-bonds were US$25,988 million and the remainder largely T. bills. Applying the fee rates of 0.1-0.2 percent to the stock of T-bonds results in an annual saving of US$26.0-52.0 million, or £16.3-32.5 million. / It can therefore be argued that the DFID support for the DMO has resulted in an annual saving of US$34.6 million in 2012, or £21.7 million. One can safely suggest that, as a minimum, the saving generated by a more effective DMO far exceeds the total cost of the three phases of the DFID project, let alone Phase III. / Efficiency Measures / The efficiency measures are reflected, inter alia, in the cost saving of DMO building debt capacity at all states instead of private consultants, the modernization of operations and IT at DMO which have saved on staff time. Total efficiency gains are estimated at US$2.0 million, or £1.3 million. / Consider the cost saving of the DMO building debt management capacity at all 36 states and the FCT. Assume that such a task is contracted out to a consultant at a cost of US$50,000 each, for a total of US$1.85 million, or £1.2 million. / The funding of a two-week input for a cash management expert (at a cost of £18,719) has resulted in the development of a comprehensive commercial paper programme by the DMO which is nearly ready to be launched on the domestic market. Once approvals from CBN and OAGF for the DMO to introduce FGN Commercial Papers - re-named Federal Government of Nigeria Cash Adjustment Note (FGN CAN) – are secured, it will markedly improve cash management practice of the Government. / Similarly, the Project supported study visit South Africa has contributed to improved understanding of new products and instruments that are being launched on the Nigerian domestic securities market. / These together with other actions to modernize operations and introduce IT are estimated to generate efficiency gains of about 10 percent of DMO’s labor time, or about US$0.15 million. / Economy Measures / The economy measures are derived in part from the innovative project management arrangement in Phase III of a non-resident project manager and the introduction of VfM principles in the design of DMO operations. The estimated total economy measures are US$0.4 million, or £0.25 million. / The innovative project management arrangements whereby responsibility on the ground was given to staff of the DMO was a more cost effective way of delivering the various inputs (The Project did not have to pay for a full time project manager and such savings were directed to TA/capacity building). For this to work effectively, the control arrangements put in place ensured that the quality of intervention was not compromised. The economy on a non-resident project manager which replaces a full time resident manager is about US$0.2 million. / • All activities delivered under the Project were closely scrutinised by the overall Project Manager (from CA) and DFID which in turn ensured that the optimal options for selecting the inputs were picked at all times. / • Over time, such close scrutiny sent the right VfM signals to the DMO - which started to adopt these basic principles while preparing budgets for specific activities. / • Another initiative brought in by the Project was a deliberate embargo on overseas training in support of locally-run programmes. That ensured that the training budget was able to benefit a larger number of staff than otherwise possible. That did not compromise quality. / • Activities such as media events were blanked out despite a strong case made to the Project by the client. / • In a similar vein, efforts have been made to give priority to mobilising local resource persons in project delivery - with access to external resources only for specialised areas and as a last resort. / • The Project management skills within the DMO have been beefed up thanks to the arrangements under Phase III. These have allowed staff to develop comprehensive concept notes on support needed with justification, links to output and impact, etc.; evaluate proposals from experts; produce the right costing of specific activities and; monitor project implementation. The DMO is in a better position to manage on their own programmes and projects funded by themselves or by donors, including at the sub-national level. That was an expectation of Phase III as highlighted in the Project Memorandum. / The economies on these measures are estimated about 10 percent of the DMO budget, or US$0.2 million. / Table 5.1: Value for Money in 2012 (US$ ‘000,000.00) (£ ‘000,000.00) / Effectiveness measures 34.6 21.6 / Private broker 26.0 16.3 / JP Morgan 8.6 5.3 / Efficiency measures 2.0 1.3 / Sub-national DMOs 1.85 1.2 / Modernisation and TI 0.15 0.1 / Economy measures 0.4 0.3 / Non-resident project manager 0.2 0.15 / Improved procedures 0.2 0.15 / Total VfM 37.0 23.2 / 5.2 Commercial Improvement and Value for Money / The programme was extended for an additional 8 months in order to manage the transition away from DFID support. Competition was not used to in deciding to continue with the existing service provider as the purpose of the short phase-out was to manage the transition away from future DFID support over a short-period of time. Given the short time-frame this could only be achieved through the existing service provider without being disproportionately disruptive. / Further details on how the programme ensures good Value for Money are provided in section 5.1. / 5.3 Role of project partners / The Project has made efforts to take into account other agency’s programmes in designing its own intervention – for instance cash management project at OAGF by the World Bank. It has also tried to create synergies with other programmes supported by DFID – especially DFID SPARC programme at the state level. / 5.4 Does the project still represent Value for Money : Y/N / Yes. The Value for Money indicators above provides solid evidence that DFID support to the Debt Management Office represented good Value for Money. / 5.5 If not, what action will you take? / N/A
6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
Overall, DFID support under the project has been effective, and the programme has met virtually all of its objectives and has provided value for money. The DMO has come a long way since its establishment, turning from a technical assistance (TA) user to also a TA provider. / The mode of intervention of Phase III, consisting of a non-resident Project Manager and a DMO Project Coordinator on the ground, while risky ex ante, has enhanced ownership and enabled the support to be applied more flexibly and be more closely linked to DMO’s priorities and needs. This has compensated for the initial costs concerns and attendant delays that were experienced in the early part of Phase III. / The programme has shown adaptability and responsiveness--introducing new procedures when needed, and addressing areas highlighted by the second-year review of the project in which additional work was required. / DFID support to the DMO has clearly provided good value for money. The total estimated value for money in 2012 is US$37 million, or £23.2 million. While not all activities and outcomes lend themselves to a quantification of VfM the DFID-funded Project can point to wider returns to the economy that far exceed the cost of intervention. / The DMO appears ready to “graduate” from the DFID supported programme and continue to manage Nigeria’s public debt and related activities. The strong sense of ownership and professionalism, its business-like approach, as well as the momentum of training and capacity building are likely to continue; the recently completed 2013-17 Strategic Plan aims to chart the road ahead. / There is some concern on sustaining the pace of the DMO’s current functions given the share of the Project component of the DMO’s budget. There is therefore a need for vigilance and careful management of the transition. It is hoped that DFID will be available together with other donors to provide targeted support to DMO over the medium term as specific needs arise. / Recommendations: It will be important to pursue the areas which have been delayed under the project including in particular the recently completed MTDS and begin applying the new risk management techniques and yield curve analysis; implement the recommendations of the communications strategy and make the public affairs and M&E units operational--the new M&E unit should develop an M&E approach, which should become an integral part of DMO’s operations; and apply the training received in contingent liabilities and PPP in coordination with other government agencies. It would be useful to build on this framework and develop a capacity to obtain budgetary data from all states in order to arrive at a consolidated fiscal position of the Federation. / Finally, the success of the 15-year DFID project in helping to build a professional and viable DMO in Nigeria merits a comprehensive independent evaluation to draw lessons on institution building in Nigeria and elsewhere in the developing world.

8. Review Process
DFID retained two independent consultants, Menachem Katz and Zakari Momodu, to conduct a project completion review (PCR) of support to Debt Management Office Phase III (DMO III). During the period February 14-20, 2013, the consultants held meetings in Abuja with the DMO management and staff, and other key stakeholders.