Business Case and Intervention Summary
Title: Improving the Quality of General Education in Ethiopia

Intervention Summary

What support will the UK provide?
DFID will provide £130 million over four years (2013 – 2017) to support the Government of Ethiopia’s (GoE) General Education Quality Improvement Programme (GEQIP) Phase 2 (£120 million) and a complementary managed fund for capacity building and technical assistance (£10 million). / The £120 million will go to GoE through a World Bank Multi Donor Trust Fund (MDTF) to help improve the curriculum and number of textbooks available (22%); to undertake teacher training (18%); to continue to provide grants to schools to implement improvement plans (46%); to improve the capacity and management of educational leaders (3.5%); and to develop the information and communication system to improve the quality of teaching and learning (7%). It would also contribute to programme coordination, monitoring and evaluation (3.5%). / The £10 million complementary fund will go to a contracted management agent for research and evidence building (22%), capacity building and technical assistance to the Ministry of Education (MoE) (68%) and up to 10% for management fee.

Why is UK support required?
What needs are we trying to address? / Over the past ten years Ethiopia has achieved a rapid expansion in education with 85% of primary school age children now enrolled in schools. About 25% of the population (over 21 million) are enrolled in full time education. However, they are not receiving a quality education. National Learning Assessments (NLA) have shown very low levels of learning outcomes. The 2011 assessment showed that 57% of sampled students scored below basic proficiency in grade 4 and 56% in grade 8. The main issues faced with respect to quality education are: / Lack of trained teachers: Although there has been a massive expansion of the teaching force (there are over 80,000 more primary teachers now compared to 2006) there are still many under-qualified teachers (only 30% are certified in lower primary) and teaching approaches are weak. / Lack of resources available at school level: Even though Ethiopia spends about 20% of its budget on education, resources available for non-salary costs at school level is exceedingly low which leaves little space for schools to make changes that will improve quality. / Weak planning and management: Some regional and woreda (district) governments have weak capacity to gather data and report on key performance indicators on time in order to manage and monitor effectively the implementation of education reforms / Inequalities in provision: Inequalities in access to quality education are widespread, as better resourced schools are generally located in urban areas and in the larger central regions. There are cultural barriers to school participation (especially for girls in rural areas) and there are financial constraints with households making significant contributions to the costs of children’s education. / Recognising the poor quality of education and shocked by the low results in the national learning assessment the Government of Ethiopia launched GEQIP as an eight year (2009 – 2017) programme to improve the quality of education in all primary and secondary schools. The UK has contributed £95 million to the first phase (2009 – 2013) of GEQIP. This support, along with government and other donor’s contribution has achieved the following results. / over 88 million high quality textbooks and teachers guides were developed, printed and distributed to primary and secondary schools, / the proportion of qualified primary teachers (grades 1 to 8) increased from 38% in 2009 to 56% in 2012, / more than 98% of the schools received grants and used them to fund their school improvement plans that are developed and agreed with school communities / However, there remain challenges specified above and there is a need to consolidate the work done in GEQIP 1 and sustain the gains. / What will we do to tackle this problem? / This business case proposes providing a £120 million contribution for the second phase of the General Education Quality Improvement Programme (GEQIP) and £10 million for a managed capacity building and technical assistance programme. GoE's commitment to education is well documented and spending on education is set to maintain a share of over 4% of GDP and well above 20% total government spending. A total of $550 ml is deemed to be required over the next four years to improve the educational levels at primary and secondary education. The proposed £130 million contribution from the UK takes three factors into account: 1) this level of funding will enable us to reach our Operational Plan commitment of directly supporting 1.94 million children in school, 2) to sustain a share of 35% as in GEQIP 1, and 3) very good evidence of need, performance and commitment of GoE for education. The Needs and Performance Framework developed by the Global Partnership for Education (GPE) to determine each country’s share of available GPE resources indicates that Ethiopia would be eligible to apply for about $220 million which is roughly the same as the £130 million requested by this business case. / This will support the provision of the following integrated set of inputs designed to improve the quality of teaching and learning in schools. / Curriculum, textbooks and assessment to improve the quality and relevance of the curriculum; maintain and increase availability of textbooks and supplementary reading materials; and develop a robust national assessment and examination system and a school inspectorate. / Teacher Development to improve the quality of teaching through initial (pre-service) teacher education, in-service teacher training and Continuous Professional Development and professional licensing and relicensing. / School improvement to strengthen school planning for improved teaching and learning conditions and outcomes, and to fund the improvement plans through per capita school grant provided on the basis of enrolment to all government primary and secondary schools. / Capacity building for planning and management including strengthening the Education Management Information System (EMIS) / Information and Communications Technology (ICT) for learning to provide a foundation for equitable, quality learning and teaching in secondary schools. / Programme coordination and evaluation to continue the GEQIP 1 emphasis on effective coordination, monitoring and evaluation, and add, as a third subcomponent, an emphasis on improved communications. / In addition, there will be a contracted out capacity for £10 million which will: / Mobilise and deliver capacity building and technical assistance to the Ministry of Education / Deliver funds for research and evidence generation. / The importance of strengthening capacity building in Ministries of Education was emphasised in the Independent Commission for Aid Impact’s (ICAI) recommendation following their review in 2012 of DFID’s education programmes in three East African countries including Ethiopia. / Who will be implementing the support we provide? / In line with aid effectiveness principles, GEQIP 2 will be implemented through the World Bank by the Government of Ethiopia through the Ministry of Education, regional and Woreda (district) education offices, universities, teacher training colleges, and schools. The technical assistance and capacity building fund will be managed by a DFID contracted managed agent.

What are the expected results?
At the impact level we aim to improve learning outcomes by 2017, with at least 50% of students scoring above basic level in the National Learning Assessment in language and mathematics. / At the outcome level, our support will contribute to improved learning conditions and institutional capacity for enhanced learning outcomes for 21.6 million children (of which 10.54 million will be girls) enrolled in all government primary and secondary schools and Alternative Basic Education Centres (ABECs). / About 35% of these results will be attributable to UK Aid if we contribute £130 million (complemented by PBS, PDP and RBA) and DFID’s funding at this level will contribute to delivering DFID Ethiopia’s Operational Plan commitment to support 1.94 million children in primary and 240,000 in lower secondary. / Investing in GEQIP 2 and providing complementary managed capacity building and technical assistance and working through government systems is assessed to generate results at better value for money than working through non-state organisations because of the higher overheads associated with the latter approach or doing nothing at all because of the negative impact that this would have on DFID’s other investments in the sector such as the Promotion of Basic Serves programme. A robust independent evaluation will be designed to determine whether the expected results have been achieved and to capture lessons. / The impact of GEQIP is anticipated to be sustainable beyond GEQIP 2. Based on past and current developments in the education sector, it is anticipated that Ethiopia nears universal primary education, system expansion will slow down and the demand for additional teachers will decrease. Salary costs are expected to stabilise as the demand for additional teachers reduces. This will result in salary costs taking a relatively smaller proportion of a growing education budget freeing up government own resources for non-salary related expenditure such as instructional materials and school running costs. This, coupled with the government’s growth plans and tax improvement, may mean that further external support to government to fund quality education improvement may not be needed beyond 2025.

Business Case

Strategic Case

A. Context and need for a DFID intervention / The Ethiopian Context[1] / Ethiopia matters to the UK for a range of development, foreign policy and security reasons. It is populous, poor, vulnerable but comparatively stable in the Horn of Africa. From a low base, Ethiopia’s growth and expansion of basic services in recent years have been among the most impressive in Africa. The UK Government has an opportunity to make our support more transformational and accelerate Ethiopia’s graduation from aid dependency. The Government of Ethiopia (GoE) is capable and committed to growth and development, and is a proven partner in making rapid progress towards the Millennium Development Goals (MDGs). But its approach to political governance presents both substantive challenges to sustainable development and reputational risks to partners. / Ethiopia lies at the heart of an unstable region that has experienced almost continuous conflict and environmental shocks in recent decades. Ethiopia and its neighbours – including Somalia, Sudan and Eritrea – languish at the bottom of the Human Development Index. Poverty and instability in the Horn of Africa are among the drivers of migration to Europe, and also contribute to an environment in which fundamentalism and radicalisation can prosper. UK interests in the region include progress towards the MDGs, resolving conflict, bolstering stability, accelerating sustainable growth and development, mitigating the impact of climate change, tackling migration, and countering terrorism. A stable, secure and prosperous Ethiopia is critical to achieving this. / Ethiopia has achieved a strong degree of political stability through decentralised regional government. Since it came to power in 1991, the Ethiopian People’s Revolutionary Democratic Front (EPRDF) has consolidated a capable government that is demonstrably committed to addressing poverty - with an impressive record of pro-poor spending, sound financial management and a strong commitment to fight corruption. There has been a smooth transition following the untimely death of Prime Minister Meles Zenawi with his deputy, Hailemariam Dessalegn appointed Prime Minister and continuing in much the same vein. The GoE play an important role on global and regional issues, including climate change, reform of the international financial architecture, and global health. Ethiopia has also made some progress toward establishing a functioning democracy, but there is still a long way to go. The UK Government continues to raise concerns about limitations on civil and political rights, and the longer term sustainability of Ethiopia’s tightly controlled political model. / Ethiopia has made impressive progress towards the MDGs and its own development targets. In the last five years, with substantial support from the UK and others, Ethiopia has: lifted 5 million people out of poverty and reduced child mortality by a quarter; rolled out an innovative social safety net to protect almost 8 million of the most vulnerable people; and put 4 million more children in primary schools. Macroeconomic leadership has helped Ethiopia achieve annual growth of over 7 per cent for the last decade although high levels of inflation threaten future growth. GoE’s Growth and Transformation Plan (GTP) targets a doubling of the economy and achievement of the MDGs by 2015, and a greater (if still limited) role for the private sector and accelerated industrialisation. The GTP provides a platform to align UK support with GoE’s ambitions, make it more transformational, and accelerate Ethiopia’s graduation from aid dependency. / Despite recent progress, Ethiopia remains one of the world’s poorest countries, with around 25 million people still living in extreme poverty, and most social indicators are below average for Sub-Saharan Africa (see Figure 1)[1]. Ethiopia suffers from recurrent humanitarian crises – the frequency of which has increased in recent years due to deepening vulnerability and the impact of climate change. It is comparatively under-aided, ranking the fourth lowest of all DFID priority countries in Sub-Saharan Africa. Strong progress towards some of the MDGs is from a very low base, and will be difficult to maintain due to the impact of humanitarian shocks and as the needs of harder to reach populations are prioritised. Population momentum will see the 83 million population increase to around 120 million by 2030, accompanied by rapid urban growth. Ethnic nationalism and underdevelopment fuel instability and insurgency in parts of the Ethiopian periphery, threatening the delivery of Ethiopia’s development objectives. External shocks, including climate change and fluctuating commodity prices, threaten growth. / Figure 1 / Ethiopia can absorb more aid and use it well. Partly because of its low per capita GDP, the ODA that Ethiopia receives, while significant in relation to its economy, is less than the median amount in relation to African countries as a whole. On the other hand, Ethiopia also has strong public sector management and institutions relative to other IDA countries and is thus able to receive and make relatively efficient and effective use of external funding. / We judge that financial aid is an appropriate instrument to consider, given Ethiopia’s performance against the UK’s Partnership Principles. An assessment of the UK’s Partnership Principles in Ethiopia was undertaken in November 2012 and recently updated. The Government of Ethiopia’s commitment to poverty reduction and the MDGs, and to improving public financial management and fighting corruption remains strong. Commitment to domestic accountability and to human rights remains mixed. Progress on economic and social rights is on a strongly positive trend, albeit with persisting challenges. Serious concerns remain about limitations on civil and political rights, especially with regard to the electoral environment, restrictive legislation and safety and security in peripheral regions. Overall, we assess that the Government remains committed to the underlying principles of our engagement. We do not consider there to have been a breach in the partnership principles since the last assessment in November 2012. / The context for improving general education quality / Increasing equitable access to quality general education has been a high priority of the GoE, especially since the launch of the Education Sector Development Programme (ESDP) III in 2006. Impressive progress has been made, especially with respect to access and equity, however this was from a very low baseline. / Net Enrolment Ratio (NER) for primary education (grades1-8) expanded rapidly from 24.9%in 1996/97 to 85.4% in 2011/12. Primary enrolment has reached almost 17 million with the number of out of school children dropped from 6.5 million to around 3 million between 1999 and 2008[2]. Enrolment of girls has shown a steady increase with the gender parity index (girls to boys ratio) in primary education now standing at 0.95 compared to 0.7 in 2001/02. First cycle secondary enrollment trends show significant increases (Gross Enrolment Ratio – GER - from 17.1% in 2001/02 to 36.9% overall and 34.6% for girls in 2011/12) and although second cycle secondary enrolment is low (GER of 8.8%) it is increasing. These achievements have been remarkable and have occurred at the same time as a major expansion of both the Technical and Vocational Education and Training (TVET) and higher education sub-sectors. / Ethiopia has also put in place most of the building blocks for quality improvement, including: / Strong government commitment and clear policy direction: Since the current government came to power in the early 1990s it has consistently prioritized education as key building block for development. This is reflected in consistently high shares (around 25%) of government expenditure on the sector. In addition, consecutive five year Education Sector Development Programmes (the first one covering the period 1995 – 2000) have outlined a clear policy direction, including a heightened focus on quality since 2006. / Expanded and well managed teaching force: Ethiopia has invested heavily in teachers – a key resource in any effort to provide and improve education opportunities. There are now more than 300,000 primary teachers – 80,000 more than there were five years ago – and these teachers are better trained and qualified. In an independent survey of woredas (the equivalent of a district) conducted in 2011, 73% of parents interviewed said that teachers are always available for work and the government has put in place a system of continuous professional development to enable teachers to keep up to date. The investment in teachers has also contributed to a reduction in the pupil teacher ratio, which is significantly associated with reduced drop in Ethiopia[3]. / Equitable provision of education services: especially at the primary level, Ethiopia has used education investments to close the gap between enrolments in rural and urban areas, between boys and girls, and between more developed and emerging regions. This includes the use of an innovative alternative basic education model to enable scaled up access for pastoralist communities, especially in Afar and Somali Regions. / A decentralized implementation structure – Ethiopia has built a system which provides autonomy to lower levels of the system to allocate finance and plan for improvements in service delivery. This includes year on year increases in funding flows to woredas via unearmarked block grants (supported by the Protection of Basic Services Grant since 2005). Woredas then allocate these funds to the basic service sector, and typically education receives over 50% of this funding. Woredas are also responsible for hiring and firing teachers and for monitoring and supervising schools in their area. / Accountability of schools to communities – Ethiopia has used a school improvement programme to trigger increased involvement of communities in school planning, monitoring, and financing. 98% of schools have in place a medium term plan that has benefited from inputs from the local community. Communities also provide significant additional resources to schools, both in cash and in kind, to fund improvements in the school environment. / A relatively robust Education Management Information System (EMIS) - The EMIS Education Statistics Annual Abstract contains a wealth of information to track sector performance with respect to access, quality and equity and almost all internationally required indicators are well covered, this includes data on key indicators of interest to GEQIP such as completion rates. An independent data verification carried out for the Results Based Aid pilot[4] in education judged Ethiopia’s EMIS including the system of handling national examination records and statistics to be robust. The timeliness and availability of EMIS data has improved in recent years with the report made available within three months of the end of academic years. However, the EMIS database is not structured in a manner that allows for analysis of how different variables interact and is therefore of limited utility in its own to fully assess the impact of programmes such as GEQIP. / Despite these remarkable achievements in expanding equitable access to schooling, and putting in place the foundations for quality improvements, a number of challenges remain that suggest the need for continued support. / Levels of learning achievement are still very low. Attempts to improve quality started in earnest only in 2008, and from a very low base. Consequently, the pace of improvement has been slower than the government anticipated. This is why the General Education Quality Improvement Programme (GEQIP), an eight year quality improvement programme, was proposed. The 2011 National Learning Assessment (NLA) shows 57% of sampled students below basic proficiency in grade 4 and 56% in grade 8 (boys performed better than girls across subjects)[5] These results suggest that the deterioration seen from 2003 to 2007 has stabilised, but there has been no improvement as yet (see figure 2 below).This slow response is in line with what we know about how long it takes to improve learning achievement[6] / Figure 2: Grade 4 and Grade 8 NLA Results: 2001, 2004,2007 and 2011 / The 2010 NLA conducted in grades 10 and 12 of secondary school shows 63.7% of sampled students below a basic level of achievement/proficiency in grade 10 and 55% in grade 12 (boys performed better than girls in all subjects)[7] / The 2010 Early Grade Reading Assessment shows that at least 80% of students were not reading at the expected oral fluency rate in their mother tongue (rural girls consistently performed below boys)[8] / Completion rates at grade 5 are 74% and 52% at grade 8 (Lower for girls in grade 8) 44 / Dropout rate is 16% for primary, but 1 in 5 children drop out before the end of grade 1 / Survival rate to grade 5 is 55% compared to a Sub Saharan average of 72%[9] / Access to quality education is still not entirely equitable as better resourced schools are generally located in urban areas and bigger more developed regions. Additionally, some children face barriers to accessing education especially females, the “most vulnerable children”[2], poor students and children in the emerging[3] regions of Ethiopia. For example primary gross enrolment rate (GER) in Somali and Afar is 75% and 44% respectively while the national average is 95% for the year 2011/12. The Ministry of Education is trying to address this inequality by providing special assistance to the emerging regions. / Access to secondary education is still low (GER is 36.9%). Girls’ enrolment and completion rates lag behind those of boys, especially in secondary school and beyond. Inequalities in access to quality education are widespread. There are socio-cultural barriers to participation in education (especially for girls in rural areas) such as poverty and food insecurity, child labour both at home and commercially, distance (especially to secondary school), early marriage, and a pastoralist way of life. There are also financial constraints with some households contributing a large share of non-salary recurrent education expenditures[10]. Attempts have been made to widen access through Alternative Basic Education Centres (ABECs - small community schools with flexible calendars and locally recruited facilitators). Over 800,000 children (36,000 girls) are now reached in this way, but the quality of the provision is often poor, and ABECs are not always in tune with the lifestyles of mobile populations. / Conflict and insecurity limit access to a number of woredas, particularly in Somali Region, for government workers, and NGOs alike. Useful lessons[11] have been learned about how services can be strengthened in conflict areas through DFID’s Somali Education pilot project and these are being rolled out in a separate service delivery programme under the umbrella of the Peace and Development Programme (PDP). / Despite enjoying a high proportion of government funding, education is grossly under-funded: Available financing is not commensurate with the scale of the challenge. For the Education Sector Development Programme III the gap between forecasted expenditure in the five year plan[12] and actual expenditure[13] averaged around 2 billion birr annually (over £68 million at current exchange rates). ESDP IV (2010 – 2015) has an estimated funding gap of over £1 billion. / In addition, a high proportion of the decentralized education budget (over 95% in primary and 87% in secondary) is allocated to salaries constraining the availability and predictability of resources for other inputs critical to support effective teaching and learning (e.g. training, textbooks and other materials, assessment, monitoring and evaluation systems, etc.) to enhance learning outcomes. Non salary recurrent expenditure of 15% or above is recommended by the Global Partnership for Education to enable systems to promote quality improvement. / The government has used a federal specific purpose grant (GEQIP Phase 1 - see below) to improve the situation. The non-salary expenditure share accounted for 15% of recurrent expenditure overall (based on figures provided in the 2010 GEQIP mid-term review), but it will be a challenge to maintain as the system continues to expand to reach the most marginalised groups. The ongoing funding gap means that GoE will not be able to fully implement elements of Education Sector Development Programme IV (ESDP IV). / Strengthened capacity to plan, manage and monitor, especially at decentralised levels, is still needed. In Ethiopia, the management and financing of primary and secondary education is the responsibility of regions and woredas based on the national policy and standards developed and approved by the Ministry of Education (MoE). The key challenges related to policy making, management and monitoring capacity include: (i) weak institutional capacity particularly at Woreda (district) levels for the delivery of general education, hampering implementation of a consistent and effective education policy; (ii) inadequate strategic planning and management capacity (at MoE and regional education offices) to support tasks such as policy development and medium to long term planning; (iii) limited monitoring and evaluation systems making the reform process difficult to operationalise. These were confirmed in a 2010 study[14] and an action plan was agreed to address them, although this has only been minimally implemented. Support for capacity building is generally fragmented because of the way different development partners operate, and a pooled fund that used to provide more harmonised and flexible support is being closed because the management agent, UNDP, is no longer able to manage it. / Some regional and woreda governments particularly those in remote underdeveloped pastoralist areas have weak human resource capacity to plan, implement and gather and report on key performance indicators on time to manage and monitor effectively the implementation of education reforms. Capacity building activities in GEQIP I was based around the commissioning of, and follow up to, the detailed analytical and design study14. This looked at the impact of previous support to capacity building in the sector, identified and analysed capacity gaps across all areas of the GEQIP project, and provided a capacity building strategy to respond to these needs focusing on: financial planning and management; human resource management; planning; EMIS; monitoring and evaluation. 4,400 primary and secondary school directors and supervisors undertook short term training through the Leadership and Management Program (LAMP). / The Management and Capacity Building including EMIS component of GEQIP 2 will continue to support the strengthening of the planning, management, and monitoring capacity of federal Ministry of Education, Regional Education Bureaus , Zone and Woreda Education Offices , enabling them to implement system-wide primary and secondary education programs effectively and efficiently. Special attention is paid to the four emerging regions. All GEQIP Phase1I activities will continue into GEQIP Phase 2, namely capacity-building for Education Planning and Management, for School Planning and Management, and for Education Management Information Systems (EMIS) at all levels. / The Special Support Directorate of the Ministry of Education is responsible for supporting the emerging regions including through posting national technical assistants to selected zones in order to fill capacity gaps in the short term and train staff to plan effectively in the longer term. The technical assistants will travel between woredas and schools in their zone, supervising the planning process and providing capacity building training. This program has already been running using funding from outside of GEQIP 1 and GEQIP 2 will strengthen this. / The policy context / Achieving the millennium development goal targets Given the size of the country and scale of the problem, achieving the education related MDG targets in Ethiopia will make a significant contribution to achieving the MDG targets in sub-Saharan Africa and globally. Ethiopia accounts for about 3 million (of whom 55% are girls) of the estimated 32 million children out of school in sub Saharan Africa[15]. / DFID’s Business Plan commitments - In its Business Plan (2011-2015) DFID committed to supporting actions to help achieve the MDGs, and also specifically committed to increasing the number of girls completing primary and secondary education. DFID is also committed to improving learning achievement. / DFID Ethiopia – Based on our analysis of need in the sector, the objectives for DFID’s support for education (as well as for health and water and sanitation) in our Operational Plan for Ethiopia are: / Increasing access to and quality of services / Increasing and measuring results and impact / Increasing equity. / The DFID E Operational plan includes a headline result for education – 1.94 million children supported in primary (of whom almost half will be girls) and 240,000 in lower secondary (almost half of whom will be girls) by 2015. The investment requested by this business case will contribute to the achievement of these result commitments. / National policy context: The GoE is ambitious in its goals and its vision for the next five years is set out in the Ethiopia Growth and Transformation Plan (2010 – 2015)[16]. This document includes very stretching targets for almost full primary enrolment (98% for both boys and girls) and an increase in lower secondary education GER from 38% in 2009/10 to 62% by 2015. The ambition of the GoE, the progress it has been able to make in the past and its focus on results provide a strong foundation for DFID’s efforts to support sector targets related to access, quality and equity. / Under ESDP IV the main goals of GoE for general education are to improve access to quality basic education in order to make sure that all children, young people and adults, with particular emphasis on females, acquire the competencies, skills, values and attitudes enabling them to participate fully in the social, economic and political development of Ethiopia and to sustain equitable access to quality secondary education[17]. GoE also recognises the challenges faced by girls and has laid out strategies in ESDP IV that seek to promote girls participation. / The GoE’s emphasis on quality of education is fundamental to its drive to reach middle income status by 2025. Relatively recent evidence shows that learning outcomes explain more of the difference in productivity growth than simply years of schooling[18]. Evidence from Ethiopia shows higher individual returns to higher levels of education adding weight to the GoE’s efforts to keep students in school and make sure they learn[19]. / ESDP IV also provides an excellent platform for DFID’s efforts to support GoE to reach the last 15% children who are out of school and to tackle equity concerns. There are specific programmes tackling limited access to education in the Developing Regional States and a separate strand on both gender and special needs. The programme recognises the importance of both supply and demand side interventions to tackle the problems of equity and access. / Based on lessons from the first phase of the Ethiopian General Education Quality Improvement Programme 2009 – 2013 and in view of current needs, the Ministry of Education has developed a project document for Phase 2 of GEQIP. The total funding required is estimated to be £368 million over four years (2013 – 2017). The project focuses on the same components as GEQIP Phase I with the addition of ICT for learning. Funding would be channelled through a pooled MoFED account, using government systems. / Current interventions to improve the quality of education / The first phase of GEQIP was designed to address the problem of low quality of education at national scale and with harmonised donor support. It seeks to increase the investment in key inputs to the system, such as textbooks, teacher development and school improvement[20]. GEQIP is now approaching the end of a four year first phase. A Business Case was developed in October 2011 which made the case for additional DFID funding to GEQIP Phase I of £50 million in the final two years of implementation (2011/12 and 2012/13). The Business Case was quality assured and received excellent feedback. The original programme design was for a two phase, eight year programme in recognition of the challenge of improving learning outcomes (2009 – 2017)[21]. / Between 2009 – 2013, DFID disbursed funds totalling £95 million to the programme via a World Bank managed Multi Donor Trust Fund (MDTF). Other contributing donors are the Education Fast Track Initiative ($168 million), the World Bank ($50 million), Italian Development Cooperation ($20 million), the Netherlands ($26 million) and Finland ($10 million). GEQIP has been showing good progress with respect to implementation and has increased the supply of inputs to Ethiopian schools and in the last internal DFID annual review[22] it was scored as “A+” (Outputs moderately exceeded expectation). / Major reforms were undertaken during phase one of GEQIP which focused on setting standards and foundations for quality improvements, providing essential inputs for improved teaching and learning conditions within the effective school model. Below are some of the key reforms achieved in phase one. / 1/ the implementation of a new school curriculum supported by the provision of teaching and learning materials, the alignment of student assessment and examinations with the new curriculum and a reform of the inspection system. / There were major drawbacks in the previous curriculum, notably a lack of relevance of some of the content and problems in the assumed methodology of teaching. Contents of textbooks which follow the subject syllabuses in the curriculum were highly overloaded and often conceptually too advanced. Moreover, although the policy advocates a student-centred approach, the teaching learning materials did not promote this method. The revised curriculum addresses these deficiencies, based upon international good practice in terms of curriculum design and teaching methodology. / More than 88 million textbooks and teachers guides have been developed based on the new curriculum and provided to primary and secondary schools covering all subjects of the curriculum. Phase 1 saw progress on the National Learning Assessments (NLAs), including the development of a NLA policy framework. Grades 4 and 8 were assessed in 2010/11, analysed, and the results disseminated at federal and regional levels in June/July 2012. Grades 10 and 12 were assessed in 2011/12. This involved the development of a Calibrated Item Bank. The Inspection of Schools in Ethiopia is at an early stage of development, but a major step forward was taken in GEQIP I in the creation and staffing of a new General Education Inspectorate Directorate within MoE. A National Framework for the inspection of schools has been developed along with plans for establishing and training inspectorates at regional, zonal and woreda levels. / 2/an increase in the supply of effective teacher educators, teachers and facilitators in primary, ABE and secondary education through new training programs for teacher educators and in-service and pre-service teacher development programs. The proportion of qualified primary teachers increased from 38% in 2009 to 56% in 2012. More inclusive entry selection criteria have been implemented successfully, following training, in all colleges of teacher education and in those universities training teachers. The comprehensive evaluation of GEQIP found out that teachers who underwent in-service training recently, perform significantly better than teachers who did not benefit from such training with respect to demonstrating student-centred instructional approaches. / 3/ A robust system for administering school grants has been put in place that disburses to and reports on around 30,000 schools and ABE centres. Every school has been provided with guidelines and training on the School Improvement Plan (SIP). The 2012 School Grant Annual Evaluation[23] reports that 98.3% of schools and ABE Centres prepared the SIP with the active involvement of communities, and 95.6% of sampled schools utilised their school grant for implementing their SIP. / GEQIP 1 has also delivered capacity development for planning and managing service delivery at all levels, with the support of education management information systems; strengthened coordination mechanisms and the establishment of robust systems for the monitoring and evaluation of service delivery. / GEQIP is designed to be complementary to the decentralised block grant (supported by the Protection of Basic Services Grant – PBS) which provides direct financing to regional and Woreda (district) governments to provide basic services (education, health, agriculture, water and sanitation, and rural roads). The block grant is supported by donors through the Protection of Basic Services programme (PBS). Over 50% of the decentralised block grant is spent on education, mainly teacher salaries. PBS remains GoE’s preferred modality for scaling up access to basic services, but GEQIP is regarded as critical in the medium term for ensuring complementary resources are available for quality related expenditures. / GEQIP is also designed to work in a complementary way with other instruments to tackle education quality, access and equity issues (see table 1 below). The innovative Results Based Aid (RBA) pilot in education (£30 million over three years 2011/12 – 2014/15) is testing whether payment by results can stretch and incentivise the government to achieve additional results in lower secondary education whilst at the same time positively impacting on aid effectiveness. We are also testing whether differential payment for girls and students in emerging regions would help accelerate progress on equity in access to lower secondary education. RBA is not considered appropriate modality for GEQIP 2 given that the pilot project is still in its 2nd year and whether it is an effective way of delivering aid is yet to be established through the independent evaluation. In addition there is a desire to support more GoE's quality programme more directly at this stage. / Several donors are working outside of the pooled GEQIP fund in support of the GoE’s overall general education quality improvement objectives. The most significant of these are: / USAID – is providing a big push on early grade reading[24], including investing in assessments of reading proficiency in the early grades and in development of materials and training to support teachers. Many of USAID’s interventions are focused on selected regions and schools and all programmes are delivered through contractors. / UNICEF – their focus has been on child friendly schools and Alternative Basic Education (ABE). More recently, they have also been prioritising early childhood education. They fund through GoE systems but with separate planning and reporting. / JICA - is focused on improving maths and science. All of their support is delivered through projects. / There are also a number of NGOs working with GoE to improve the quality of education. These include Save the Children (focusing on ABE), Link community Development (school improvement planning), and Concern (reaching marginalised children). / DFID-E contracted a consortium of NGOs (Save the Children UK, Mercy Corps and Islamic Relief) to pilot a programme of enhanced support to education in Ethiopia’s Somali Region. This approach is being scaled up including other basic services though the Peace and Development Programme (PDP). This aims to strengthen the basic service provision of health, education and water in Somali Region where there is a very low enrolment at both primary and secondary levels. / Ethiopia is also set to benefit from the Girls Education challenge fund. Two project proposals valued at over £11 million have been approved to reach an estimated 50,000 marginalised girls in target woredas in Afar, Oromia and Amhara regions. We anticipate further funding from the innovation window. Ethiopia also has a Girl Hub office which has a focus on girls’ education. / Table 1 below summarises DFID’s current and planned support to education and their focus and interdependence. / Table 1: DFID Ethiopia – planned support for education / No Programme/instrument What it is supporting/contributing to / 1 Protection (called Promotion in phase III) of Basic Services (PBS – 50% spend on education) - Recurrent expenditure mainly salaries of teachers (access) / 2 General Education Quality Improvement Programme Phase 1 (GEQIP) 2009 – 2013 Quality inputs and non-salary recurrent expenditure for general education (quality) / 3 Basic services in Somali Region as part of the Peace and Development Programme 2012 – 2015 Improving access to quality education in Somali region (equity in access) / 4 Quality Education Strategic Support Programme (QESSP) 2010 – 2013 Strategic support to MoE through a combination of advisory secondment, Technical Assistance and a pooled fund / 5 End Early Marriage Facilitating community conversation and providing school materials as an incentive to keep girls at risk of early marriage in school in Amhara Region (equity in access) / 6 Result Based Aid pilot 2011 – 2014 Payment for every student who sits and passes the grade 10 examination, with a premium paid for girls and students in emerging regions. (focus on aid effectiveness, results and transparency) / Feasibility of intervening / In this context, there are at least four key reasons why DFID should continue to provide support to improve the quality of general education in Ethiopia: / Although the decline in learning outcomes appears to have stabilised, student achievement is still well below levels set by GoE / The inputs that are needed to have a transformational effect on quality are still massively under-funded / There are still around 3 million children out of school, many of whom are girls, vulnerable children and children with special needs (it is anticipated that supply side improvements will attract and retain some of these students into school). / The social and economic consequences of low education quality include lower economic growth and increased fertility rates. According to a 2005 study, raising education levels for women is a key factor in accelerating demographic transition in Ethiopia. The same study stresses the importance of girls’ education in reducing early marriage and fertility and increasing economic growth[25]. Education leads to reduced fertility by enhancing women’s knowledge, decision making power, confidence in interacting with the outside world, closeness to their husband and economic and social self-reliance.[26] Improved levels of education have been associated with better health of children through parental education; increased life expectancy; improvement in spouse’s health and lowered mortality; and improved contraceptive efficiency[27]. / DFID is well placed to provide additional support to GoE’s efforts to improve the quality of general education in Ethiopia for three reasons. / DFID-E is a trusted bilateral donor with the resources, relationships, expertise and instruments available to help GoE to tackle the problem of improving quality at scale. / DFID-E is already taking a leadership role on the quality education agenda both in Ethiopia and globally. It can use its trusted position to accelerate progress on this important agenda and to use its influence to better understand what works through high quality evaluations. / DFID is a leader on aid effectiveness and has the commitment to align its funding behind a government owned programme and encourage other donors to harmonise their efforts thereby reducing transaction costs in the sub-sector and increasing impact. / Consequences of not intervening / The potential consequences would be, at best, maintenance at current low levels of learning outcomes and completion rates for many students. Without follow-on support to existing investments, GoE’s efforts to accelerate economic growth and gain the social benefits of education may be jeopardised and the impact of other DFID supported programmes such as the PBS would not be maximised. / Sustainability / Ethiopia spends a relatively high share of its Gross Domestic Product (GDP) on education by international standards relative to its level of per-capita income of $344[28]. It spends significantly more than India, (whose per-capita income of $1192 is almost four times as much), and only a little less than South Africa (whose per-capita income of $5786 is more than 16 times that of Ethiopia). / Despite this, the overall funding gap in ESDP IV is estimated at over £1billion as indicated above. Much of this funding gap is expected to be filled by external partners. With the GoE already spending around 4% of GDP on education and over 20% of its budget, there is little likelihood that the GoE will be able to mobilise additional domestic resources to tackle the challenge of improving quality of education in the next five years. In recognition of the time frame that would be needed to make sustainable improvements, GEQIP was designed as an eight year, two phase programme to address this challenge. / Based on financing and results trends in the sector, we anticipate that beyond GEQIP Phase 2 and PBS III, Ethiopia nears universal primary education, system expansion will slow down and the demand for additional teachers will decrease. Salary costs are expected to stabilise as the demand for additional teachers reduces. This will result in salary costs taking a relatively smaller proportion of a growing education expenditure which has seen historical average annual growth rate of 30.8%. This trend matched by government commitment to provide 15% of its education budget to non-salary expenditure as is recommended by the Global Partnership for Education will reduce the salary burden and begin to free up government’s own resources for non-salary related expenditure such as instructional materials and school running costs. This, coupled with the government’s growth plans, may mean that further external support to government to fund quality education improvement may not be needed beyond 2025. / Finally, improving the quality of education and learning outcomes in Ethiopia will itself contribute to economic growth. Amongst countries that have participated in the Programme for International Student Assessment (PISA - an internationally benchmarked measure of learning) shows that test scores of one standard deviation above the average are associated with an average annual growth rate in GDP per capita of two percentage points higher over 40-years[29] / B. Impact and Outcome that we expect to achieve / By 2017, using a mix of instruments and working closely with government and partners, we expect to see the following impacts at national scale: / Access: An increase in overall primary enrolment to 20 million (up from 16.9 million in 2011/12) and lower secondary enrolment from 1.4 million to 2.3 million over the same period. In addition, there will be a million more students completing grade 8 of primary school and 500,000 more completing lower secondary school. At primary level, government will be approaching the MDG target of universal access (primary net enrolment rate of over 90%), although there will still be some pockets that are not reached and drop out will not have been totally eliminated. At secondary level, we anticipate that the intake will rise to meet the demand for secondary places from primary schools graduates. / Equity: Our commitment to put girls at the centre should help further improvements in the gender parity index, especially at secondary level, and schools that are more conducive to girls’ participation and learning. Of the 2.3 million enrolled in government and non-government secondary schools, we expect 1.1 million to be girls. We also anticipate that access to students with special needs will increase, and that progress in terms of enrolment will continue to accelerate in the developing regional states, especially for pastoralist communities. / Quality: In parallel with the rise in the number of students enrolling and staying in school, we also expect a positive impact on student learning achievement. At a minimum at least 50% of students will score above basic level in the National Learning Assessment in language and mathematics. We also expect that the achievement gap between girls and boys and rural and urban students will continue to narrow. Finally, reading in the early grades is expected to improve across all the regions as a result of efforts from a range of partners. / At the outcome level, we expect GEQIP 2 to contribute to improved learning conditions and institutional capacity for enhanced learning outcomes for 21.6 million children (of which 10.54 million will be girls) enrolled in all government primary and secondary schools and Alternative Basic Education Centres (ABECs). Some of the changes we anticipate include the following. Around 35% of these results can be attributable to the UK’s support. / All 30,000 + government primary and secondary schools and ABECs receiving a per capita grant of on average £1.90 per pupil enrolled and using their finances to focus on improving learning achievement (28 million per capita grants attributable to DFID); / 1,600 principals and supervisors trained to ensure better managed, more accountable, primary and secondary schools and ABECs with focused school improvement plans in place (training for 560 principals and supervisors attributable to DFID); / approximately 140,000 more qualified teachers and Alternative basic Education Facilitators who are trained to use more participatory and inclusive teaching approaches in classrooms (46,000 teachers and facilitators attributable to DFID); / 83 million more textbooks and supplementary materials being effectively utilised by teachers and students to promote learning for all students, including the provision of braille books for the blind (29 million attributable to DFID) / 200 secondary schools using new ICT equipment to enhance learning (school equipment for 70 schools attributable to DFID). In addition, the coordination and management of ICT in education will be strengthened by providing a comprehensive policy framework, establishing a national ICT Infrastructure Improvement Plan for General Education; and through teachers’ professional development in ICT / Education officials in all 900 woredas with the skills and capacity to monitor and support school and ABE performance and help them to improve learning (training for staff in 315 woredas attributable to DFID); / a national monitoring and evaluation system which builds on the existing infrastructure to provide more comprehensive feedback on progress and helps to identify bottlenecks
[1] DFID Ethiopia (2011) Operational Plan (2011 – 2015), DFID Ethiopia, Addis Ababa.
[1] Ethiopia is one of three countries prioritised for early action in the New Alliance for Food Security and Nutrition G8 initiative announced at Camp David this year.
[2] Education For All (2011) Global Monitoring Report, Statistical Tables 2011 http://www.unesco.org/new/en/education/themes/leading-the-international-agenda/efareport/statistics/statistical-tables/,Accessed 27 July 2011 11:00
[3] Poppe, R, and Jennings, M. (2012) Drop out study. Ministry of Education
[4] DFID (2011) Baseline Data Verification Report for Results Based Aid Pilot in Education
[5] General Education Quality Assurance and Examinations Agency (20128), Ethiopian Forth National Learning Assessment Grades 4 and 8 Report, Addis Ababa
[6] Linn, R. L., Baker, E. L., & Betebenner, D. W. (2002). Accountability systems: Implications of requirements of the No Child Left Behind Act of 2001. Educational Researcher, 31(6), 3–16.
[7] National Agency for Examinations (2010), Ethiopian First National Learning Assessment of Grades 10 and 12 Students, Addis Ababa
[8] Piper, B. (2010) Ethiopia Early Grade Reading Assessment Report. RTI /USAID Ethiopia International
[9] UNESCO (2011) ibid
[2] The most vulnerable children in Ethiopia are “rural & pastoralist children, orphans, children in remote locations, street children and drop outs”, as well as those with disabilities (see GEQIP Social Assessment 2010).
[3] The so called emerging regions are the under-developed, peripheral and mostly pastoralist regions of Afar, Somali, Gambella and Benishangul Gumuz.
[10] DFID Ethiopia (2011) Social Assessment for the Education Sector. Addis Ababa
[11] Napier, A. and Echessa, E. (August 2011) BRIDGES Piloting the delivery of quality education services in the Somali Developing Regional State: Final Evaluation. Feinstein International Center, Tuft University
[12] Federal Democratic Republic of Ethiopia (August 2005) Education Sector Development Programme III. Ministry of Education, Addis Ababa
[13] Federal Democratic Republic of Ethiopia (October 2010) Education Statistics Annual Abstract
[14] Ministry of Education (2010) Management and Administration Programme Capacity Building, Study Report, Ministry of Education, Addis Ababa
[15] UNESCO (2010) EFA global Monitoring Report 2010 Reaching the Marginalised. UNESCO, Paris
[16] Federal Democratic Republic of Ethiopia (2010) Growth and Transformation Plan 2011 – 2015. Ministry of Finance and Economic Development, Addis Ababa
[17] Federal Ministry of Education (2011) Education Sector Development Programme (ESDP) IV 2010/11 – 2014/15, Addis Ababa
[18] Hanushek, E. and Wosman, L. (2007) Education Quality and Economic Growth. The World Bank, Washington DC
[19] World Bank (2005). Education Ethiopia: Strengthening the Foundation for Sustainable Development. Washington DC. World Bank
[20] World Bank (November 2008) Project Appraisal Document in Support of the First Phase of the General Education Quality Improvement Programme. World Bank, Washington DC.
[21] World Bank (November 2008) ibid
[22] DFID (2012) Annual Review of the General Education Quality Improvement Programme
[23] BDS Centre for Development Research (2011) School Grant Annual Evaluation Report to MoE
[24] USAID (Feb. 2011) Education: Opportunity through learning. USAID, Washington DC
[25] World Bank (2005) Ethiopia Well-being and Poverty in Ethiopia: The role of agriculture and Agency. Washington D.C., World Bank.
[26] Jejeebhoy, S. (1995) ‘Women's Education, Autonomy, and Reproductive Behaviour: Experience from Developing Countries.’ New York: Ox ford University Press
[27] Jimenez, E. and Patrinos, H. (2008) Can cost benefit analysis guide education policy in developing countries? World bank Policy Research Working Paper No. 4568 Washington DC: World Bank
[28] http://data.worldbank.org/indicator/NY.GDP.PCAP.CD/countries
[29] Hanushek, E. and Wosman, L. (2007) Education Quality and Economic Growth. The World Bank, Washington DC

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The Stage 1 Business Case identified five potentially feasible options for delivering the Theory of Change. These were as follows: / • Option 1 (Finance sector budget support): This option would provide ring fenced funding to the Ministry of Finance for the education sector. This would be used to support the objectives and strategies set out in the Education Sector Development Programme but would not be subject to any additional planning or monitoring requirements beyond those already in place through government systems (in contrast to GEQIP which requires detailed planning against an agreed project framework – see below). / • Option 2 (Finance through the Promotion of Basic Services Programme) to support education: DFID is providing support to the PBS programme which is a multi-sector Poverty Reduction Budget Support (PRBS) programme consisting of five components: The main component of the programme provides direct financing to regional and Woreda (district) governments to provide basic services (education, health, agriculture, water and sanitation, and rural roads). The funds are channelled through the block grant that transfers funds from federal to regional governments. Continuous audits and additional safeguards ensure that funds are used for the intended purpose. / • Option 3 (Fund GEQIP Phase 2): GoE has developed a project document for Phase 2 of GEQIP. The total funding required is estimated to be $550 million over four years (2013 – 2017). The project focuses on the same components as GEQIP Phase I with the addition of ICT for learning. Funding would be channelled to the Ministry of Education, universities, regions and schools from a pooled MoFED account, using government systems and based on annual plans. / • Option 4 (Fund quality improvements through NGOs, the private sector or the UN): This option would channel funding outside of the GoE channels in support of a project or programme that supports inputs, capacity and system development for a particular aspect of education quality improvement. In line with the priorities of Ethiopia’s Education Sector Development Programme IV these wold be a mix of the inputs identified in the theory of change. / • Option 5 (Do nothing): Under this option, DFID would not fund programmes to improve education quality. The Protection of Basic Services programme is assumed to continue under this option and the Results Based Aid Programme would also be implemented. The financing allocated in the Operational Plan for education quality improvement would be channelled into other sectors. / Since the Stage I Business Case was developed, the Business Case for PBS III has been approved. This Business Case has effectively ruled out options 1 and 2. Option 1 was rated very poorly against criteria related to leverage and results, development effectiveness and cost and risks. It is therefore no longer judged to be feasible. Option 2, channelling additional funds through PBS, is ruled out because the PBS Business Case makes the case for funding a programme focused on access to Basic Services which requires a complementary programme focused on supporting the quality of education services. / Two additional options were considered during the development of the full Business Case. / Funding private providers of education Across the world, alternative education providers, such as low-cost private schools, are increasingly filling a vital gap in educational services in order to help improve access to education. The quality of private schools and their ability to be accountable are important issues. Private schools can under some circumstances help increase girls’ enrolment as there may be more female teachers and they may be closer to home[30]. Enrolment in private schools in Ethiopia is currently only around 4% at primary level and 6% at secondary level. Consequently, it was agreed that this option should not be a focus of attention, although as efforts to expand access to secondary education continue it may become more relevant. / Funding a follow up to the Quality Education Strategic Support Programme (QESSP). QESSP has been used by DFID and other Donors to provide extra financing for capacity building and technical assistance for the GoE since 2010 and will close in September 2013. Through DFID’s secondment of a senior education adviser in the MoE, contributions to the UNDP managed education pooled fund (EPF), and DFID internally managed funds, QESSP has made the following significant contributions: / Improved the capacity of government to plan and implement quality reforms. This was most clearly seen in the leading and proactive role played by the MoE in the current process for developing phase 2 of GEQIP. With DFID support, the MoE’s Planning Directorate led and inclusive and participatory planning process which resulted in a strong, government-owned document which is being used as the basis for planning of a second phase of GEQIP. In addition, the MoE, in general, and the Planning Directorate, in particular, have demonstrated greater capacity to plan and propose specific projects for QESSP support. / QESSP has enhanced policy dialogue in the education sector. This has been achieved, in part, through the work of the DFID education adviser seconded to the MoE. His role has not only improved dialogue between the MoE and DFID, but also between the MoE and other development partners. / Improved the evidence base in the education sector in Ethiopia supporting studies that have contributed to high level policy dialogue on topics of importance, such as dropout from primary education. / The main benefit of QESSP is that it has provided the education sector with a financial instrument which is more flexible than other larger instruments. Elements of this flexibility include: / The ability to carry out an activity more rapidly or efficiently than might be possible with another instrument. These issues of speed and efficiency apply to activities of both the Ministry of Education and the World Bank. / The ability to conduct activities which are made difficult or impossible by particular rules, e.g. the hiring of international and/or national consultants. The MoE has particular challenges in this area because it can only pay in local currency and faces restrictions in the level of payments it can make. / The ability to finance activities which were not envisaged at the time of planning larger instruments. / The ability to finance activities which were previously funded by another development partner. Examples of this include accelerated teacher training in Somali region previously funded by USAID and capacity building of local education offices in pastoral and semi-pastoral regions previously funded by the Italian government. / Overall, it is QESSP’s flexibility in terms of speed, efficiency and the minimum of bureaucratic rules that has been the main factor in its success. It is this flexibility which is valued by stakeholders and which has resulted in QESSP being seen as a valuable adjunct to other programmes, such as GEQIP and PBS. / Based on the positive reviews and results it was agreed to design QESSP 2 in such a way that it closely complements GEQIP 2 and is covered within the same rationale and business case. QESSP 2 will provide separately managed funds to mobilise technical assistance and capacity building to enhance the quality of policy dialogue, programme implementation, and monitoring and evaluation across the education sector. The funds will be managed by an agent and would support complementary capacity building efforts across the whole education sector. The purpose of QESSP 2 would be to create an enabling environment to maximise the efficiency (see the cost benefit analysis below) and impact of all resources including GEQIP 2 flowing into the sector. / The limitations in the performance of UNDP in its role as management agent for EPF, and its ultimate withdrawal from the role, created challenges for DFID and other stakeholders. These have largely been overcome by DFID taking on the de facto role of management agent for QESSP with other agencies taking on roles previously handled by UNDP e.g. The British Council handled the organisation of the annual education conference. But, transaction costs have been high, particularly for DFID. The situation is not considered sustainable in the longer term. No other bilateral agencies have the capacity to manage QESSP. Therefore identifying a management agent for QESSP 2 through a competitive process is considered to be the only viable option. / The following four options will therefore be appraised in this business case: / Option 1 – Delivery via GEQIP Phase 2 + managed capacity building and technical support (QESSP 2) / Option 2 – Delivery via non state organisations + QESSP 2 / Option 3 – QESSP 2 only / Option 4 – Do nothing / A DFID contribution of £120 million over four years is assumed for both options 1 and 2 with an additional £10 million for QESSP 2. Under options 1 and 2, this represents DFID expenditure of £130 million or spending per pupil of approximately £1.50 per year. Coupled with other inputs, this would raise annual per pupil non salary recurrent expenditure to approximately 15% of recurrent spending (in line with international norms). / The proposed DFID financial contribution for 2013 – 2015 is slightly below our Operational Plan financing commitment, but should enable us to maintain aggregate spending at 10% of the government’s general education budget (just over £700 million in 2011/12 and predicted to rise to over £800 million by 2014/15). Coupled with our funding through PBS and RBA this will help us to achieve our headline result of supporting 1.94 million children in primary school by 2015. Funding at this level will also make a significant difference to the quality of education as measured by learning achievement by ring-fencing expenditure for quality related spending such as textbooks, teacher training and school grants.
B. Presentation of options / Option 1: delivery via the government in support of Ethiopia’s GEQIP phase 2 project (£120 million) + QESSP 2 (£10 million) / What it would consist of / Under this option DFID would channel financing of £120 million over four years in support of GEQIP Phase 2 (2013 – 2017) and £10 million over four year for Capacity Building, Technical Assistance and research and evidence building (QESSP 2). Other sources of funding for GEQIP Phase 2 are expected to be the World Bank (£53 million), the Global Partnership for Education (£66 million – because of resource constraints, GPE’s funding to Ethiopia was capped at $100 million otherwise Ethiopia would have been eligible for more GPE funds), USAID (£13 million), Italian Cooperation (£6.5 million), and Finland (£16 million). GoE has committed to budgeting for the remaining finance gap of £93 million if other sources of financing cannot be found. DFID’s contribution is around 35% of total projected GEQIP costs, which is consistent with our support to GEQIP Phase 1 and to PBS. The Government of Ethiopia has requested that DFID support this option. / The government programme is designed to improve learning conditions and achievement for over 20 million primary and secondary school students over four years from 2013 – 2017. It consists of £368 million of financial and technical support to six pillars[31]. The pillars are described below together with indicative cost estimates (including 5% contingency). The project is still subject to a final appraisal so the allocation of financing is not finalised yet. / Curriculum, textbooks and assessment (base cost of £77 million) which aims to: i) improve the quality and relevance of the curriculum; ii) maintain and increase the availability of textbooks and supplementary reading materials; iii) develop a robust national assessment and examination system; and iv) develop a school inspectorate. / Teacher Development Programme (base cost £64 million) which aims to: improve the quality of teaching in general education on three fronts: initial (or pre-service teacher education, in-service teacher training and Continuous Professional Development and professional licensing and relicensing. / School improvement (base cost of £159 million) which aims to strengthen school planning for improved teaching and learning conditions and outcomes, and to fund the school improvement plan through the school grant. Per capita grants are provided on the basis of enrolment to all government primary and secondary schools in Ethiopia / Capacity building for planning and management (base cost of £12.5 million) which aims to: i) improve the effectiveness and efficiency of education planning, management and resource allocation and utilization through human capacity development at federal, regional and woreda levels; ii) strengthen participatory school planning, management and monitoring in order to make schools more effective, efficient and accountable, and to improve teaching and learning; and iii) strengthen the EMIS by improving collection and use of system data for planning, evaluation and policy making. / ICT for learning (£23.5 million) aims to provide a foundation for equitable, quality learning and teaching in secondary schools through the use of Information and Communications Technology (ICT). The decision to include ICT in GEQIP 2 is informed by the fact that there is some improvement around the required infrastructure for ICT and that after a thorough consultation the Ministry of Education has developed a roadmap to ICT in education. The specific objectives of ICT component of GEQIP 2 are: i) to strengthen the coordination and management of ICT in education by providing a comprehensive policy framework; ii) to establish a national ICT Infrastructure Improvement Plan for General Education; and iii) to strengthen teacher professional development in ICT. It will support the qualitative use of innovative technologies in a limited number of schools in an attempt to demonstrate the value that ICT can add to the improvement in learning conditions, the learning experience and learning outcomes for learners in secondary schools. The project will support infrastructure in 200 schools in the first two years, and subject to availability of financing and evaluation of impact may extend to a further 200 schools after the mid-term review. Equity between urban and remote schools will be considered in the choice of appropriate ICT given the varying levels of infrastructure and energy supply. / Programme coordination and evaluation (base cost of £12.5 million) will continue the GEQIP 1 emphasis on effective coordination, monitoring and evaluation through this project component, and will add, as a third subcomponent, an emphasis on improved communications. / While GEQIP is primarily a project focused on quality improvement, the following ESDP IV cross cutting issues are mainstreamed across the project document: / Gender equity: this includes indicator disaggregation; ensuring curriculum and instructional materials are gender sensitive; attention to gender in teacher selection and placement; gender issues included in the school planning process; pro-active selection of women for capacity building activities; inclusion of gender in monitoring and evaluation activities. / Special needs and inclusive education: This includes attention to special needs in the development of instructional materials (there is a proposal for braille books, for example); development of teacher training materials with due attention to inclusive pedagogy; incentives for the retention of children with special needs through the school improvement programme; strengthened tracking of enrolment of children with special needs through EMIS. / Emerging regional states: The project includes special support for teacher training, capacity building and increased school grants for the four regions that are least developed (Somali, Afar, Benishangul Gumuz and Gambella). All key indicators will be disaggregated and tracked by region through EMIS and GEQIP semi-annual reporting. / In addition, attention will be paid to school health and nutrition through the curriculum and school improvement components. Malnutrition and ill health reduce children’s learning ability, school performance and attendance. Observational and experimental studies [32]have found evidence of impaired intellectual function and reduction of intelligence quotient associated with malnutrition. The proposed program is cognizant of biological determinants on capability of learning and quality education. The program collaborates with other Health and Nutrition initiatives by GoE and its partners. It strengthens education systems that enhance an uptake of health and nutrition services and promotion at school level. / How would it work? / GEQIP Phase 2 would be delivered by the government of Ethiopia together with six development partners (World Bank, DFID, USAID, Italy, Finland and the Global Partnership for Education). The government has requested that the pooled fund arrangement (see strategic case above) used in Phase 1 be maintained. Funds would flow through the GoE financial system to: a) the federal government (for management and oversight and for participating universities); b) the eleven regions and city states for capacity building activities and for the colleges of teacher education; and c) all districts for the per capita grants to 30,000 primary and secondary schools. In GEQIP Phase 1 bilateral funds, including DFID funding, flowed to GoE via an MDTF managed by the World Bank. / QESSP 2 is described more fully below – essentially a management agent would be contracted to manage funds on behalf of the government in order to provide capacity and technical assistance support for implementation and monitoring of programmes. / Strength of evidence for Option 1 (overall assessment = medium) / The most direct source of evidence that option 1 could work in the context of Ethiopia is the performance of the on-going GEQIP Phase 1 which is due to end in July 2013. The 2010 Business case made the case for an additional £50 million of funding to the programme, bringing the total DFID contribution to £95 million over four years. This represents 35% of total donor funding of approximately £285 million. GEQIP Phase 1 is subject to a 6 monthly process of Joint Review and Implementation Support which reviews in depth the progress of GEQIP against its targets and generates in-depth discussion, lesson learning and fine tuning of the programme. To date seven of these reviews have been conducted, including a more in depth mid-term review in 2011. In addition, there have been two school grant evaluations and a comprehensive evaluation of the whole GEQIP programme has been carried out. Option 1 is therefore very well grounded in evaluation and lessons learned from Phase 1. / The most recent DFID annual review of GEQIP Phase I was conducted in November 201222. The review confirmed that phase I was exceeding expectations with respect to the provision of key outputs, but that it was too early to tell whether it was impacting on learning achievement. The review also recommended that based on progress to date, and the scale of the remaining challenge, DFID should proceed with preparation for GEQIP Phase 2 / Equity: GEQIP Phase I included an explicit focus on gender. Attention was paid to the selection of female teachers for training courses and all data was disaggregated. EMIS data shows the following national achievements with respect to female participation in primary and secondary education since GEQIP was launched in 2009: / the proportion of female teachers has increased from 33% to 34%; / girls primary completion rate has increased from 45% to 52% at grade 8; / girls’ drop out has decreased from 19% to 15% / 17,000 more girls passed the grade 10 examination / The emerging regional states include sizeable pastoralist populations. GEQIP Phase I included support to Alternative Basic Education Centres which are designed as low cost alternatives to formal schools that use locally recruited facilitators to deliver the curriculum in a flexible way. Net enrolment rates in the two most under-served regions (Afar and Somali Regions) have increase by 5% and 13% since GEQIP Phase I was launched. However, challenges remain with respect to the capacity of these regions to implement reforms and there are plans in GEQIP Phase 2 to increase support to these regions. / With respect to the provision of support for Children with Special needs, GEQIP Phase I did not include this as an explicit focus. EMIS data indicates that enrolment has declined slightly (from 47,000 to 43,000) but data is incomplete. The GEQIP Comprehensive Evaluation reports that there is scarcely any provision for students with special needs at school level. The impacts of Phase 2 on children with special needs should be monitored closely. / Institutional capacity building impact: GEQIP Phase I contributed to the building of institutional capacity both as a result of using government systems and by including an explicit capacity building component (Management and Administration Programme – MAP). A capacity needs assessment was conducted during the first year of GEQIP Phase I implementation, which made a number of recommendations as to areas where capacity building efforts should be directed. Phase I has been relatively successful at building capacity at federal, regional and schools level, but there has been limited progress in woredas. GEQIP Phase 2 includes specific sub-components to address this. Other lessons with respect to capacity building that have been integrated into the Phase 2 project document and into QESSP 2 include: / Decentralising the developing, printing and distribution of textbooks and other instructional materials to regions in order to reduce delays and ensure materials are relevant[4]. This approach will take the burden off the Ministry of Education and enable it to provide capacity building support to regions. / Developing systems and human capacity at the National Educational Assessment and Examinations Agency to ensure the administration of high quality National Learning Assessments and grade 10 and 12 examinations, and building capacity at regional level for the grade 8 regional examinations. / Strengthening the capacity of inspectors at all levels needs to include their capacity to visit schools, and to ensure the effectiveness of their inspections. / Increasing capacity building efforts on woreda staff and staff in emerging regions / Improving decentralised monitoring, especially of expenditure in implementing entities / Stronger communication with school communities and the general public on whose support to a significant extent GEQIP depends. / The World Bank conducted an institutional assessment as part of the GEQIP Phase 2 appraisal process which basically confirmed that existing GEQIP implementation structures are fit for purpose and made some recommendations for increasing the alignment between the project and existing government systems. / . / Balance of advantages and disadvantages for option 1 / In terms of delivering on the ToC below, this option has the following advantages: / It supports all inputs requested by GoE for general education quality improvement using their preferred modality / It reinforces the social contract since it support the government’s delivery of education to all citizens with children in public schools / Aligns with, and complements, DFID financing the protection of Basic Services which cannot easily target resources for non-salary inputs focused on quality / Minimises transaction costs since it builds on existing federal mechanisms for delivering non salary inputs to sub national levels / It is immediately ready to deliver results whereas alternatives could delay delivery by at least a year. / The major disadvantages of option 1 are that: / Although GEQIP benefits from a range of safeguards (including detailed annual planning and World Bank fiduciary and no objection procedures), any perception that resources are being diverted from intended purposes could potentially expose DFID to reputational risks / Delivering through government systems in Ethiopia can be challenging due to weak procurement and financial management capacity, complex bureaucracy, and weak management. / Option 2: Delivery outside of government channels via NGOs or UN agencies (£120 million) + QESSP 2 (£10 million) / What would it consist of? / Under this option DFID would bilaterally deliver a programme of support to education quality improvement to regions and woredas through Non-Governmental Organisations that could be for profit organisations or charitable agencies and/or though the UN. Such an approach would be particularly attractive in the event that political or other risks made working through governmental channels impossible but where DFID still wished and was able to continue supporting education. This option could also be technically attractive if DFID wanted to accelerate progress in a particular area, as it is seeking to do through its partnership with NGOs in the delivery of basic services in Somali Region[33].It is envisaged that QESSP 2 would also be funded under this option. / In terms of delivering on the ToC, this option would still need to be national in scale and closely harmonised and aligned with the Government’s GEQIP Phase 2 document. One possible approach would be to agree to direct contracting in challenging areas where there are large technical challenges or procurement difficulties. This might include, for example, the ICT and textbook components described above. / How would it work? / DFID would directly contract NGOs to provide support to education quality improvement in partnership with the Government. Funding through NGOs would be off budget support and the activities of the contracted NGO would continue to come under government coordination as part of the consolidated planning process at federal and at regional levels, but would not be contracted directly by the government. / Strength of evidence for Option 2 (overall assessment –limited) / NGOs/Private providers / The main evidence that delivery through NGO/for profits at scale could work in the education sector in Ethiopia comes from the USAID education programme which has been operational in Ethiopia since 2000. USAID’s reliance on non-governmental delivery partners reflects the US government’s assessment of democracy and governance and transparency issues in Ethiopia which prevents USAID from using government systems.[5] / In the past, USAID support to basic education has tended to be projectised, focusing on a selection of schools, or in certain geographic areas. While this approach has generally been judged effective, it has been criticised for being over-complex and delivered by too many organisations[34] The recent launch of the Reading for Ethiopia’s Achievement Developed (READ) marks a shift to working more coherently at nationally scale and in a more aligned way with government programmes (including a USAID commitment of $20 million to the pooled funding for the government’s GEQIP Phase 2 programme). READ is a US $86 million five year project (2012 – 2017) focusing on quality of curriculum and instruction and evidence based early grade reading and writing instruction. The project seeks to benefit 15 million students in all primary schools across Ethiopia. / The READ programme is an interesting model and one which DFID should follow closely. It is too early to say how effective it is, but it does build on over ten years of USAID experience in delivering through non state actors outside of government channels. Generally, contracting out would give DFID more control over capacity building and equity aspects of the programme, although institutionalising change could be more challenging. / Delivery through the UN / As far as we are aware, there are no current examples of the UN delivering at scale in the education sector in Ethiopia. While there are excellent examples from contexts where working through government is problematic for DFID because of political reasons (the PBS III Business Case includes the example of health in Zimbabwe, and there is also a major education programme), these conditions are not currently judged to prevail in Ethiopia. Unless concerns around partnership principles emerge and that we couldn't work through or with government, this option would not be our preference for a nation-wide programme at scale. However we do not judge ourselves to be in that position. Also on grounds of costs and institutional impact/sustainability this option is not the most appropriate. The current UN admin charge of 7% will increase to 8% by 2014 for the main UN agencies including UNICEF who would most likely engage in this sector. We recognise using UN agencies can be beneficial for innovation and getting to specific marginalised groups and issues, but GEQIP 2 is also being developed to respond to equity issues and we have other equity focused programmes. This Business Case will therefore not include an appraisal of this sub-option. / Balance of advantages and disadvantages of Option 2 / Supporting the delivery of basic services outside of government systems i.e. through NGOs private sector providers would have the following advantages: / the ability to target specific aspects of the quality improvement agenda for specific groups but still in partnership with the government / more DFID control over all aspects of design , implementation and monitoring and evaluation / much higher protection of DFID from the reputational risks of association with a government which, under a political downside scenario, could become the subject of increasing criticism for human rights and other negative practices / However this option also has several disadvantages notably: / the opportunity to engage in meaningful policy dialogue might be reduced / it would be much harder to ensure additionality since government could simply offset the contribution made by DFID / it would be less likely to build on the social contract between government and people as it would not be using government systems to the same degree as option 1 / it would result in high overheads due to the administrative costs associated with international non-governmental delivery partners / it would also increase transaction costs for DFID (in managing a large complex project) and for government (in coordinating another set of inputs to the sector) / Option 3: QESSP 2 only (£10 million) / What would it consist of? / This option would consist of a pooled technical assistance and capacity building fund that would provide technical and administrative support to the Education Technical Working Group (co-chaired by the Ministry of Education). QESSP is designed to accelerate progress of sector reforms and ensure that an enabling environment is created to maximise the effectiveness of our sector programmes (particularly GEQIP2 and PBS 3) by providing targeted support to: / Improve the capacity of government to implement reforms to improve access, quality and equity in the education sector as a whole (including agreed support to aspects of GEQIP implementation) / Enhance policy dialogue in the education sector by improving evidence based decision making / Improve the evidence base on impact of education reform efforts; include piloting new initiatives and funding some aspects of GEQIP 2 monitoring and evaluation framework. / How it would work? / DFID-Ethiopia considered a number of options for implementing QESSP 2. The main delivery channels considered were as follows: / Continue a DFID secondment to the Ministry and contract enhanced support directly from DFID / Use the Bank’s GEQIP multi donor trust fund to mobilise enhanced support / Contract out to a management agent / The first option was rejected because it was considered to be too transaction cost heavy for DFID-Ethiopia and attracting a suitable adviser to undertake a partial secondment was felt to be difficult. The second option was rejected because despite the Bank’s considerable strengths, they do not tend to be very flexible in their fund management and delivery and that the MDTF will tie the scope of QESSP to be limited to supporting activities related to GEQIP. / Under the third option, DFID would contract a management agent through a competitive bidding process to manage the funds on behalf of the Ministry of Education and Development Partners that may contribute funding to QESSP. The agreed TORs also include provision for a technical adviser, embedded in the Ministry of Education, to help to manage the funds and provide advice and support to the Planning and Resource Mobilisation Directorate as needed. The funds would be accessed on a call down basis by the government in consultation with the education Technical Working Group (TWG). Support might include funding specific initiatives by federal or regional bureaus, short and medium term consultancy support, study tours, training courses, and workshops as well as commission studies and programme evaluations. The contract would stipulate that the management agent should be prepared to accept funds from a range of donors, including DFID. / Strength of evidence for Option 3 (overall assessment –medium) / Option 3 builds on the experience of the Education Pooled Fund (EPF) and subsequently the Quality Education Strategic Support Programme QESSP). The former was managed on behalf of the Technical Working Group by UNDP until 2012. EPF was established in 2004 in order to respond quickly and flexibly to the capacity development, research and implementation needs of the Ministry of Education, as they relate to policy formation and review, and implementation monitoring. From 2004 – 2008 the EPF attracted funds totalling £3.8 million from six donors, including £1.28 million from DFID. Expenditure averaged around £800,000 per year over that period. The TWG commissioned an independent review of the EPF as part of a redesign process in early 2009. The report[35] concluded that despite some administrative difficulties and occasional problems with taking up the findings of commissioned studies, the fund was effective and highly valued for its flexibility. Continuation with minor modifications was recommended. / DFID subsequently established a project called the Quality Education Strategic Support Programme (QESSP) which included contribution the EPF, but also expanded its scope. The project was initially for two years (March 2010 – March 2012) and its aim was to provide technical and advisory support to the government and its partners to maximise the impact of DFID and partner financing on quality reforms. Total resources of £2 million were mobilised to support: / The partial secondment of a DFID-E Education Adviser to the Ministry of Education to build MoE implementation, planning and monitoring capacity / A small TA fund to be managed by DFID-E in support of key sector policy and implementation issues / Finance for an Education Pooled Fund to provide harmonised support for the implementation of the Education Sector Development Programme / Baseline research into the impact of government quality reform efforts on schools and students to inform further design of GEQIP. / The 2011 DFID Annual Review scored the project a 1 (likely to fully achieve its purpose). Based on this rating, and a government request to extend the project, an eighteen month cost extension was agreed in 2012. Subsequently, UNDP withdrew from EPF fund management and returned funds to participating donors. DFID is currently handling these funds on behalf of the TWG, but transaction costs are high. Based on a request from the TWG, DFID has been requested to lead on contracting a new fund manager for a second generation EPF. / DFID mobilised an independent consultant to conduct the 2013 QESSP Annual Review[36] in order to fully learn the lessons to feed into the design of this proposed option in GEQIP Phase 2. The project scored as meeting expectations (see table below listing some of the key studies that QESSP directly supported). The review recommends providing support to technical assistance and capacity building through a management agent rather than through DFID. It also proposes the provision of long term technical assistance to the Ministry of Education to support the Planning Directorate and liaise with Development Partners. Finally, the review recommends that DFID continue to hold a small amount of bilateral funds to maximise flexibility and speed of support. The expanded scope of QESSP, including supporting aspects of GEQIP capacity building and evaluation mean that about £2.5 million per annum is judged as a reasonable contribution. / Table 2 : Selected activities supported by QESSP (2010 – 2013) / Comment / No. Title / 1 Joint annual sector reviews QESSP has contributed financing and advisery support to the government to conduct their regular sector monitoring through the annual review process. This is an important mechanism for federal government to hold regions to account for progress and provide input into evolving policy. The joint review involves government representatives, development partners and civil society who make field visits to schools. Thematic areas over the past three years have been aligned with GEQIP and provided important feedback on progress (teacher education, school improvement, and textbook development and provision) / 2 Young Lives Baseline Study Study completed – Young Lives have encouraged on-going policy use of learning generated including generation of policy briefs and holding an event in Ethiopia. The research provides some of the best available material on what is happening in Ethiopian classrooms and how this relates to learning. Findings have had a significant influence on the debate on quality but sample sizes are small and it is generally agreed that further research is needed to unpack the findings further at scale. DFID has subsequently focused on this rather than on funding further rounds of YL research. / 3 Drop-out study with MoE Quantitative analysis of the determinants of drop out using EMIS data showed how EMIS data could be better used to inform policy and shed light on the trend in drop out over the past five years. Overall drop out was found to be reducing and the effect was most pronounced in rural areas (which is in line with expectations around quality improvement). Dropout rates remain very high in grade 1. The significant determinants of reduced drop out that were uncovered by the model included better qualified teachers, smaller class sizes, the availability of textbooks, and separate toilets for older students. Findings influenced the decision to include additional grants for disadvantaged students in GEQIP Phase 2 and reinforced attention to maximising the complementarity between GEQIP and PBS. / 4 Factors that affect the participation of Pastoral Females in Education in Somali Region Funding was provided to the University of Jijiga, Somali Region, to conduct this study as part of efforts to build decentralised research and evaluation capacity. Focus group discussions were primarily used to understand the barriers. Significant findings include the importance of non-formal education, the role of female teachers, and increasing gender sensitivity in teacher training and instructional materials. The partnership with Save the Children in Somali Region and the inclusion of special support programmes in GEQIP Phase 2 are helping to embed these findings in policy and practise. / 5 Somali Region Accelerated Teacher Training This activity commenced in March 2012 and replicated a similar successful activity supported by USAID the previous year. Funding was provided to the Special Support Directorate of the MoE to train grade 10 and other leavers as teachers in this very under-served region. The programme has been highly successful in addressing teacher shortages in the region and now incorporated into GEQIP Phase 2 / 6 GEQIP Phase 1 Social Assessment Agreed as part of Phase 1 design and funded by DFID outside the pool to ensure high quality output, this has been a very influential study. It contains the best evidence currently available on who is excluded from school and why. It has been an important building block for other studies of exclusion including the drop out study (above) and UNICEF’s out of school children study. The need to be sensitive to the needs of different groups and to focus more on issues of inclusion have both been incorporated into GEQIP design. The 2011 study has also been the basis of a social assessment of Phase 2, which broadly endorses the design, and which QESSP also funded. Outside of GEQIP, here continues to be policy debate about whether more needs to be done to address infrastructure deficits and demand side barriers in the sector programme / 7 Education Research Conference Brought together researchers from two DFID funded Research Consortia (CREATE and EQIP) in order to review Ethiopia’s policies and approaches .It included inputs from the Ministry on the 2011 National Learning Assessment, USAID on the Early Grade Reading Assessment, the DFID funded social assessment of GEQIP Phase 1, and UNICEF’s out of school study. The research and discussion broadly validated GoE’s approach but suggested areas for increased emphasis. These include a focus on meaningful learning and effective pedagogy, improving classroom conditions, better management at decentralised levels, and more focused school improvement, including better data for parents and other stakeholders at school level. Many of these have been factored into GEQIP 2 design. / 8 Expanded Ethiopian Delegation to attend a conference on Achievable Education for All workshop in Tanzania This enabled experts from MoE to attend the workshop organised by Link Community Development who have been piloting approaches to improve school improvement planning and availability of data in Ethiopia for over five years. The outputs of the workshop have been used by government to strengthen the design of the school improvement planning framework and improve the use of data at decentralised levels. Discussions are on-going as to which other aspects of Link’s work are scalable in the Ethiopian context. / 9 Improving Performance Of Local District Education Offices in Pastoral and Semi Pastoral Regions of Ethiopia Involves support to the Special Support Directorate of the MoE. This involved the recruitment of national consultants to work with regions and woredas in order to build planning and management capacity at decentralised levels in the four most under-served regions. It built on a similar programme funded by Italian Co-operation which was positively reviewed by independent evaluators. The programme has now been incorporated into GEQIP Phase 2 / 10 To provide a forum for the Ethiopian Teachers Association to contribute to policy in the education sector This activity involved providing an accountable grant to the Ethiopian Teachers’ Association to conduct their annual conference. This event involved the presentation and discussion of technical papers. It was attended by more than 300 delegates. The Association represents the interests of all teachers in Ethiopia and the event thus provides an important platform for on-going professional development. / 11 Funding the national conference on special needs/inclusive education This brought government and non-government stakeholders together on the launch of Ethiopia’s revised strategy for special needs and inclusive education. The conference participants, through representatives, formulated an eleven-point statement which included: the need to do more on attitudinal changes on the concept of disability; public mobilization to sensitize the community about disability and related issues; utilizing the new guideline as a tool to effectively implement the SNE strategy; the provision of fertile condition for introducing IT for children with special needs; the urgency of facilitating accessible school environments; the need for establishment of resource centers; the provision of disability friendly educational materials; the need for exploiting best practices on SNE; equal participation of trainees with disabilities in TVET institutions; assignment of SNE professionals in areas where they could benefit children with special needs and the proactive initiation of persons with disabilities themselves to promote SNE. / Balance of advantages and disadvantages of option 3 / The main advantages of option 3 in delivering on the ToC are that: / It can create an enabling environment for reforms by building capacity whatever option is chosen / It would strengthen capacity in the MoE to take forward reform efforts / It would build evidence generation and evaluation capacity and ensure that government and partners have a clearer picture of the impact of the investment in quality through GEQIP / The main disadvantage is that in the absence of DFID support to broader general education quality improvement efforts, the support would have limited traction and leverage. / Option 4: do nothing / Under option 4 DFID would continue to fund education through the Promotion of Basic Services Programme III (around 50% of our £510 million contribution over the next five years, mainly to teacher salaries).The Results Based Aid pilot would also continue to operate until 2014 (a total of £30 million dependent on grade 10 examination results). It is difficult to predict what would happen to the quality improvement programme under this option. The funding gap for the government’s GEQIP Phase 2 document would be in the order of £200 million which is more than half of the total projected costs. It is difficult to see how the programme could be implemented at all under these circumstances, unless significant additional resources could be found. This currently appears unlikely, so the do nothing option would therefore have a catastrophic impact on non-salary recurrent input for general education. It would also not deliver on most aspects of the ToC. / Balance of advantages and disadvantages of option 4 / The main advantages of option 4 are that: / It would free up financing for other programme priorities / It would reduce DFID transaction costs / The disadvantages include: / The potential negative effect on education quality improvement in Ethiopia with knock on effects for growth and social indicators / Major reputational risk to DFID of withdrawing support / The impact of DFID’s support to education through the PBS programme would not be maximised. / Summary of evidence for the options / Table 3 below summarises the strength of the evidence underlying each option and the balance of advantages and disadvantages. / Table 3: Summary of options appraisal / Option Evidence rating Advantages Disadvantages / 1 Medium • Supports all inputs requested by GoE for General Education Quality Improvement; / • Reinforces the social contract / • Complements other DFID instruments • Could potentially expose DFID to reputational risks / • Weak government procurement and financial management capacity, and complex bureaucracy / 2 Limited • Targets specific aspects of the quality improvement agenda / • More DFID control over design , implementation and monitoring and evaluation / • Higher protection of DFID from reputational risks • The opportunity to engage in meaningful policy dialogue might be reduced / • Much harder to ensure additionality / • Would not build on the social contract between government and people / • It would result in high overheads / • It would also increase transaction costs for DFID / 3 Medium • It can create an enabling environment for reforms by building capacity whatever option is chosen / • It would strengthen capacity in the MoE to take forward reform efforts • Without DFID support to general education quality improvement, the impact is likely to be limited / 4 Not assessed • It would free up financing for other programme priorities / • It would reduce DFID transaction costs • The potential negative effect on education quality improvement in Ethiopia with knock on effects for growth and social indicators / • Major reputational risk to DFID of withdrawing funds / In summary, option 1 (GEQIP 2 through government + QESSP 2) is judged to be the right option to intervene towards quality education in Ethiopia. -We need to invest in quality improvement if learning outcomes are to improve and if we aim for a positive social and economic impact of education. The main instrument that is best placed to address the quality challenge is GEQIP. There is no strong evidence that the proposed complementary set of inputs in GEQIP 2 are the best set. However, international evidence supports the need for a mixed set of interventions. DFID have had a chance to influence the shape of GEQIP 2. Unfortunately the comprehensive evaluation of GEQIP 1 was not designed to give us the grounds to believe which set of interventions are working or not working. However, it tells us about improvements in learning conditions and how these are perceived by learners and teachers. There are positive trends in student achievement and completion rates that can be correlated with the implementation of GEQIP 1. The monitoring and evaluation framework of GEQIP 2 (see management case) will seek to measure the impact of GEQIP and address this gap in evidence. / Targeted work through NGOs or the UN might help us deal better with one or two specific issues, social groups or geographies, particularly innovating on a smaller scale so GoE can pick this up at scale. But on the one hand, as above, the evidence isn't overwhelming that we should be picking up a specific issue and DFID Ethiopia is already pursuing this approach through the Girls Education Challenge Fund, the Peace and Development Programme, the Girl Hub initiative and through the Results Based Aid pilot in terms of experimenting the impact of incentive based scheme on results. In this context GEQIP complements these programmes and the work of other donors such as USAID.
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / As noted elsewhere in this document, the Woreda is the lowest tier of the government responsible for the delivery of services and implementation of programmes based on federal and regional policies and guidance. However, the woreda level administration in general and education sector in particular have different capacity gaps that could be expressed in terms of staff capability for planning, monitoring and evaluation; in education materials like books, chairs and other class room facilities; and other gaps otherwise helpful for quality enhancement. Capacity and capability for planning, monitoring and evaluation are important not only for mainstream teaching activities but also for other support areas like information technology, financial management and procurement in education. / While education quality is a top priority for government, the existing financial capacity of government does not allow allocating sufficient fund to quality enhancement at large scale. Most of the woreda budget goes to salary cost, leaving very small proportion to other running costs at the discretion of woreda management. Any option that would allow additional fund for running cost like capacity development for monitoring and evaluation will have a significant beneficial impact. / The options are examined from different angles including scale/scope, sustainability, harmonisation and transaction requirements. The assessment of the options is as follows: / Option 1 would be the most preferred option as it provides opportunity to reach wider coverage using the government systems, integrate and complement capacity building with government’s own efforts contributing to durable capacity development, and improve aid effectiveness through reduction of transaction requirements while enhancing harmonisation. / Option 2 would be preferred option from the point of view of focus and deepening quality improvement but with limited scope and with more risk for sustainability. With this option, the capacity building support may have more depth but with limited scope and more transaction requirement. / Option 3 would contribute to the sustenance of already deficient capacity at local level but would not achieve sufficient coverage or reach alone / Option 4 would have relatively limited scope in terms of coverage and reach to local level.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / During GEQIP Phase 1, donors agreed that World Bank’s environmental safeguards would address all their environmental concerns. The environmental screening that was carried out by the World Bank as part of GEQIP Phase 1 rated the project as low risk with respect to impact on the environment and there is no reason to expect any major changes to this assessment in Phase 2. GEQIP Phase 2 does not include any major construction and the only major new component is the provision of ICT infrastructure. / Similarly, the other three options have low risk of negatively impacting on the environment. Donor support is focused mainly on soft inputs and the school grants programme as currently defined prohibits capital expenditure beyond rehabilitation of existing infrastructure. / There are some opportunities for mitigating climate change through our support to the government’s efforts to improve education quality. These potentially include: / Strengthening the curriculum, instructional materials and teacher training courses with respect to learning about climate change in Ethiopia – there are entry points through the Civics programme and through teacher training which may have beneficial impacts in the future. We will seek to assess teachers’ awareness of climate change issues through the comprehensive evaluation. / Focus on retaining girls in school as this may be one of the most cost effective interventions for tackling climate change because of its impact on fertility rates and population growth[37] / Supporting the use of low carbon technologies in the aspects of school infrastructure which are the target of the ToC, including for school lighting and water supply. This might include the introduction of solar lighting. / Procurement of energy efficient equipment, especially for the ICT component, and ensuring that equipment specification is commensurate with energy sources. / ‘Greening’ schools – the school improvement programme could do more to support schools to plant seedlings or to focus attention on local environment concerns. / Climate change does pose some risks to programme implementation. Ethiopia is becoming more prone to flooding and this can affect school buildings and the materials they contain. In addition, increased droughts may negatively affect food security which impacts on the attendance of children in school. Synergies will be sought with other aspects of DFID’s support to Ethiopia, especially climate change programme and with the Productive Safety Net Programme, in order to mitigate these risks. / Table 4: Climate change assessment / Option Climate change and environment risks and impacts, category (A,B,C,D) Climate change and environment opportunities category (A, B, C, D) / 1 C B / 2 C B / 3 C B / 4 C C / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation.
E. If any, what are the likely major impacts on social development? / Equity is a fundamental objective of the GoE, enshrined within the Constitution and the driving motivation for the decentralised system of service delivery. The overriding issue of equity recognised by official policy is that of differing levels of welfare across the regions. Four regions in particular are classified as developing regions: Afar, Benshangul Gumuz, Gambella and Somali. Together these regions comprise 10% of the country’s population but are also the locations with the greatest level of social need. The Social Assessment39 for GEQIP 1 highlighted the rural-urban disparity and pastoralism in terms of access to educational service with indicators for the developing regions being the worst. The poorest section of the population is typically less able to access educational services compared with the wealthiest[38]. / The Social Assessment[39] further identified a number of groups that suffered from unequal access to basic services including: child laborers, victims of gender based violence including early marriage, victims of child trafficking, orphan and vulnerable children, children with special needs. Specific barriers identified by the report included the following: / Gender: as already noted in the Strategic Case, girls in Ethiopia have less access to educational services than boys particularly at secondary school level. The assessment also highlighted parental attitudes to girls education, household responsibilities, fear of gender based violence, early marriage, inadequate sanitation and other schools facilities, low self-esteem and predominance of male teachers are some of the reasons for the gender disparity and lower educational performance among girls. / Rural- Urban Disparity: primary school gross enrolment rates in urban areas are double the rate of rural areas, distance is a key issue especially in accessing secondary school. In a context where only a small proportion of rural households are within a 10 km radius of a secondary school, the option for poor households being able to fund children particularly girls to stay in towns to attend secondary schools is minimal. Where they stay with relatives there is a risk of employment and sexual exploitation and many are not given the time to go to school. / Pastoralists are the least served with basic services. Formal education is seen in some pastoral households as a threat to the future contribution of children to the household and to the pastoralist way of life[40]. Girls’ access to education in pastoralist communities is also particularly constrained by parents’ perception that going to school furnishes girls with the opportunity to interact with boys. Girls in the education system would be looked upon unfavorably by boys and prospective in-laws given that their education would provide them intellectual maturity which is seen as a threat to the community. / Child Labour: Child labour is a major constraint to education; the Labour Law does not envision employment under 14 years yet many children are working from a young age e.g. as farm help or domestic workers. Hhouseholds’ need for child labour is a major driver of late arrival at school, absenteeism and dropout from school at all levels, and drop out amongst girls is highest. Child labour activities are influenced by family economic status; such factors include work within the home, work outside the home for income generation, abuse of girls brought to the cities, attractions of working in the Middle East. / Children with special needs: Despite government policy of inclusive education for children with special needs, they remain amongst the most marginalised, and inclusiveness is still at an early stage. Children with special needs are usually excluded from the community and hidden at home, parents are ashamed of them, and disability is considered as ‘misfortune’ though disability may also be caused through accidents on the farm, fights and poor health. There is considerable variation in social acceptance of disability, and significant differences in the approaches adapted to these children across the regions uniform. To a large extent, activities, services and interventions are left to NGOs and church groups to provide. / Commune Development Programme and Resettlement / The GoE is implementing the Commune Development Programme (CDP) in the four emerging regions of the country (Afar, Somali Region, Gambella and Benishangul Gemuz). This programme involves the movement of scattered populations into villages with the stated aim of improving service delivery. The GoE will deliver education to people in newly settled and existing villages. In pastoralist areas such as Afar and Somali Region, the CDP is based around providing alternative livelihood options through irrigated crop agriculture for those transitioning out of pastoralism. Here, GoE’s strategy is to provide education services to people in the region, whether in new villages or elsewhere. The GoE has also undertaken resettlement of people in areas such as South Omo linked to commercial agricultural production. Donor visits to resettlement regions have raised concerns including on the scale, speed, sequencing and implementation capacity, which could present a risk to delivery of this programme. / DFID and other development partners support to GEQIP is designed to support education quality improvement nationally without discriminating certain groups or sites. However we will continue to support the GoE to abide by international good practice in resettlement. / The GEQIP 2 and QESSP 2; non-government channel and QESSP only options would help improve the quality and accessibility of education to socially excluded groups in differing degrees depending on their scope for: / Innovating and testing new approaches to improve quality of education to socially excluded groups / Influencing national policy on improved approaches on equity issues / implementing national policy on equity issues by deepening and widening its application / Option 1: delivery via the government in support of Ethiopia’s GEQIP phase 2 project and QESSP 2 provide a better platform for influencing national policy on issues of equity and for deepening and broadening the implementation of national policy, with improved approaches at scale. The school improvement programme under GEQIP will also contribute to the improvement of local level accountability and relationship between service users and providers as it would give greater opportunity for community engagement. However, although GEQIP phase 2 will be working at all primary and secondary levels of the education system through the school improvement programme, due to the size of the grants and competing priorities schools may not be able to address the social issues in comprehensive manner. In addition, the sector-wide approach will be highly results driven and focus on replication of standard approaches at scale, and in itself is unlikely to drive more innovative approaches. / Delivering our support to GEQIP 2 nationally via the government does not constitute support to the CDP, but the overall principle is to deliver quality education services to all children in Ethiopia, without discrimination as to where they reside. Nevertheless, we have considered perceived reputational and substantive risks that may arise and have put mitigation measures in place (see the risk section in the management case). / To ensure that GEQIP is not compromised by the CDP or other GoE resettlement activities, DFID would seek to ensure both continuation of high-level dialogue and establishment of appropriate programme-level safeguards, monitoring and evaluation. The planning mechanism, the monitoring and evaluation framework, and the Joint Technical Reviews should include specific provision for “beneficiary” feedback and report if any concerns and advise on improvements required. The programme will need to continually assess any risks or opportunities to its delivery from the CDP process and integrate appropriate measures as appropriate. / The design of GEQIP 2 was subject to Bank’s safeguards for Vulnerable and Marginalised groups (OP 4.10). In line with this policy, an enhanced social assessment has been conducted with the purpose of assessing the potential impact of GEQIP 2 on the more vulnerable and disadvantaged regions and groups in Ethiopia and identifying strategies for mitigating risk and adverse impacts. / The draft report of this assessment notes that there are enabling factors including Ethiopia’s constitutional safeguard for the rights of all groups and that GEQIP 1’s explicit focus on gender and support to Alternative Basic Education Centres in the emerging regions is well received. While the assessment did not come up with any adverse effect of GEQIP 2 it recommends addressing specific equity and inclusion gaps by adapting component specific strategies and outputs to vulnerable and marginalised groups particularly pastoralist communities and special needs children. The recommendations will be discussed and agreed in the upcoming final joint programme appraisal mission and the summary of the social assessment will be published as part of the PAD. / Option 2: The option of delivery through non-government/ private channels is likely to allow for the greatest targeting socially excluded groups, such as girls and children with special needs although it is unlikely to result in the permanent institutionalisation of change at all levels. NGO sector have expertise working with the community as a whole and socially excluded groups in particular and experience in identifying and addressing the socio - cultural barriers to education. However the option of delivery via non-governmental channels alone would provide little scope for influencing national policy. / Option 3: The QESSP 2 only option would have no scope for testing new innovative approaches and less scope for influencing and implementing the national policy under the existing circumstances. In the absence of DFID support to the general quality improvement efforts, the support would have limited traction and leverage on social issues. However it might be targeted to create an enabling environment to improve equity issues by strengthening MOEs capacity to respond. / The overall implication is that support though the government in support of Ethiopia’s GEQIP 2 would provide the strongest option for scale-up and implementation. QESSP 2 would also complement by providing flexible component allowing for specialist technical support to ensure that equity and inclusion, gender, and social accountability issues are appropriately addressed.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / Option 1: This is the preferred option as it meets fragile states principles by providing significant financing in support of a government plan (ESDP IV). Ethiopia’s successive Education Sector Development Programmes have seen considerable improvements in the delivery of education services over the past two decades. From a conflict and fragility point of view, those achievements have helped to create and reinforce the sense that the government is delivering public expectations at the national level. A key consideration will be to ensure that programmes like GEQIP continue to make improvements that match those growing expectations. / That said, at the sub-national level, progress has been unequal, with certain regions notably the emerging regions seeing less progress against the MDGs than other regions. This has led to feelings of marginalisation and grievance, sometimes along ethnic lines, in those regions. GEQIP 2 includes efforts to provide special support to the DRS (additional teacher training, capacity building and increased school grants) which should help to bring them into comparatively greater parity with the rest of Ethiopia. We should see specific improvements in the Somali Region given DFID’s Peace and Development Programme for that region focuses, in part, on improving the quality of and equity in education service delivery. Based on lessons from DFID’s pilot project in Somali region 2010 – 2012 (Building Relationships through Innovative and Growing Education Services – BRIDGES) we will use GEQIP as a platform for policy dialogue and action to promote flexible education to suit the lifestyles and challenges of children living in pastoralist communities. / Even with advances within the Developing Regional States, there is likely to still be a gap in access, equity and quality of education in those four regions compared to elsewhere in Ethiopia, which is probably unavoidable. In order to mitigate this risk, the programme will need to demonstrate continual improvement in education services which will mean that any sense of grievance over inequality of service provision at the national level is tempered by a sense that services are steadily improving within regions. / Regional inequalities aside, the programme will also take specific measures to ensure equity in education for girls and for people with disabilities. Additional efforts may be required to ensure access by these demographics in the more fragile regions of Ethiopia. / The financial management systems by which GEQIP funding is delivered will be key to mitigating the risks mentioned above. The financial disbursement system outlined in the Financial Case has been well tested, not only under GEQIP 1 but also other comparable sector programmes. It offers the best method of getting maximum financial resources down to the school level. However, we should bear in mind that not all regions have such systems in place, to the same degree of quality and capacity, as others. Again, this is notably the case in the emerging regions. / GEQIP is beginning to reach the sub-regional level in the Somali Region[6] and the PDP Basic Services component will improve the systems for delivery, management, monitoring and evaluation of federal funds including those of this programme. However, institutional structures and capacities in the emerging regions are much weaker and more vulnerable to externalities (such as conflict and natural disasters) than they are in other regions. Government and donor partners will need to continually assess the effectiveness of those systems and ensure they are delivering the expected improvements. / The proposed approach of developing disaggregated indicators by region through EMIS and GEQIP reporting is welcome. Other indicators of relevance will be the extent to which children in pastoralists are learning, and how well woredas are reporting in the Developing Regional States. The Early Grade Reading Assessment which is planned to be conducted by EGRA can also be sued to track the progress of children from different language and ethnic groups. / Option 2 would aim to deliver the same outcomes but through a third party. The greater degree of control encapsulated in this option would enable DFID to accelerate the delivery and quality of education in the DRS, which would be an advantage over option 1 in that this would enable more of a tailored approach that takes accounts of the specific contexts of each region and thus would ensure a more robust conflict-sensitive approach as opposed to the standardised model discussed above, but this would have to happen without an equivalent deceleration of benefits in the non-DRS regions. If this were to happen, there is a risk that grievances currently felt in the DRS could become inverted. Given the PDP is operating education services in the Somali Region; an additional effort on this region may not be required under this option. The benefits of a region-specific model would have to be balanced against the scale and cost of delivery of option 1 versus option 2. / Option 3 alone would do little to directly address geographical inequalities in service delivery across Ethiopia and would also create a funding gap in the education sector, thus the same disadvantages as option 4 below apply. However, it would complement option 1 well by providing additional support for capacity building and support as requested in the four developing regional states, and ensuring robust monitoring and evaluation of the impact of GEQIP in different locations and on different groups. / Option 4 (Do Nothing) carries a high risk. Huge progress has been made on education from a low base and with that progress comes raised expectations. DFID’s withdrawal from GEQIP would leave a major funding gap that would affect the speed and/or scale of progress going forward, which would ultimately exclude certain sections of the population.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / GEQIP 2 will fund a range of non-wage, largely recurrent educational inputs that complement the largely wage costs covered by the Protection of Basic Services programme and the Federal Block Grant (FBG) more broadly. Neither GEQIP 2 (and other non-wage inputs to the sector) nor the hiring of adequate numbers of teachers through the FBG (including PBS) would themselves be sufficient to deliver an optimal level of educational output even if all the resources from one programme were to be transferred to the other programme. / To capture the complementarity of the various inputs to the education sector this economic appraisal assesses the costs and benefits for each option of the sum total of inputs to the sector, including GEQIP 2, and then attributes a share to DFID based on DFID’s contribution. The appraisal assumes that the marginal product of non-wage inputs represented by GEQIP 2 is broadly equal to the marginal product of the wage inputs represented by the PBS III programme and that therefore the Internal Rate of Return (IRR) for both types of input is also broadly equal. There are two pieces of evidence that support this assumption. First the relative contribution of FBG (including PBS) funding to other funding in the sector suggests a ratio of wage to non-wage inputs of approximately 80:20. This compares favourably with an average ratio among less developed countries of 85:15 and in Sub-Saharan Africa a ratio of about 90:10.[7] Second the overall progress in the sector in recent years has been impressive and, while performance could still be improved, suggests that the balance of inputs is not far wrong. / This integrated approach is also in line with the approach that was taken in the economic appraisal of the PBSIII programme approved in October 2012. In that appraisal an IRR was calculated for total inputs to the 5 basic sectors funded as a whole on the basis that there was complementarity not only between the FBG and other programmes, but also across the 5 basic sectors (health supports education and education supports health etc.). Thus while individual IRRs for each of the sectors was not calculated the general approach under PBS III was, it is argued, consistent with the approach adopted here. / Reflecting the mix of ‘hard’ (e.g. textbooks) and ‘soft’ (e.g. management) inputs in GEQIP 2 each option is expected to result in two main types of quantifiable benefits: / better educational services and hence better social and economic outcomes / more services per £ spent i.e. an increase in allocative and operational efficiency / In addition, as noted in the business case for GEQIP 1, a number of additional, non-quantifiable benefits are expected to flow from investment in GEQIP 2 comprising: / a demographic bonus based on an increase in the number of girls completing primary and secondary education and an improvement in the quality of their learning while at school which could be expected to reduce the prevalence of early marriage and reduce fertility rates. / improved health benefits resulting from better parental care of children, better nutrition, increased life expectancy, improved maternal health and greater confidence among girls and women. / increased equity as the investment in non-salary inputs in rural schools disproportionately helps poor children of pastoralists and others living in rural areas. / The following analysis makes explicit the underlying assumptions that should hold for GEQIP 2 and/or QESSP 2 programmes to deliver an acceptable rate of return. Some of these assumptions are grounded in the Ethiopian context - including the judgement of education professionals - while others are extrapolated from cross-country analyses that have been undertaken previously. To test the robustness of the assumptions and results a sensitivity analysis is also undertaken. The analysis thus provides a “sense check” of the logic of the proposed intervention and an explicit and coherent economic story to underpin and compare the various options considered. What it cannot and does not attempt to do (in the absence of a more rigorous estimation of Ethiopia’s underlying education production function) is to provide precise, advance judgements on the additional value of increasing particular types of input. / Option 1a: delivery via the government in support of Ethiopia’s GEQIP phase 2 project without a QESSP 2 component / Investment in the education sector is assumed, as it was in the appraisal of GEQIP 1, to result in a 10% return on investment for every additional year of education completed.[8] Students are assumed to benefit from an additional year(s) of schooling either because they have added a year (or more) in time to their schooling career e.g. because of higher demand for better quality education and/or because the higher quality of education enabled by GEQIP 2 effectively intensifies students’ learning experience even without elongating it. The latter would be reflected, e.g., in improved results in language and maths i.e. the outcomes targeted under GEQIP. We note that years of schooling gained as a result of the programme does not explicitly capture the gains from learning achievements and doing so presents methodological difficulties. / The translation of wage and non-wage inputs into educational outputs in the form of additional years (equivalent) completed is affected by: a) the number of additional years learning equivalent (over a 12 year school career) that educational inputs deliver and b) the share of students in a particular cohort who exhibit this improvement. This appraisal assumes that the overall impact of GEQIP 2, PBS III and other programmes in the education sector, during the 4 years of the GEQIP 2 programme, effectively adds the equivalent of 1.5 years to a student’s primary and secondary school career i.e. an increase in learning, on average, of 15% per year over a 10 year period (during which inputs such as textbooks could be expected to last) in the school career of a student. The relative conservatism of this approach can be seen by comparing the actual improvement in completion rates from 34% to 48% between 2004 and 2009 i.e. an improvement of roughly a third over a period of 6 years.[9] This improvement is assumed to apply to 60% of students.[10] / The impact of GEQIP 2 and other programmes on the years equivalent completed by a share of the overall student cohort and the return of 10% per year equivalent completed by these students of their future earnings translates into an overall monetary benefit when summed for all students benefiting. Assuming a discount rate of 12%, the total discounted benefit of better education attributable to DFID’s contribution to GEQIP 2 is £167 million. / Under this option there is no QESSP 2 and hence no additional efficiency gains realized. The net discounted value of efficiency gains under this option are therefore zero. / The costs of total inputs to the education sector comprise the programmed costs of GEQIP 2 including DFID’s contribution of £120 million, the education sector’s share of basic service spend funded by the Federal Block Grant including PBS III; and other inputs.[11] The total discounted cost of DFID’s GEQIP 2 contribution to sector funding is £88 million. This results (in line with inputs to the sector as a whole) in a benefit cost ratio of 1.89 and an IRR of 34.8% i.e. it would require an alternative project with returns of 34.8% or higher to reduce the NPV of GEQIP 2 to zero and imply that the project was not worth undertaking. The IRR of PBS 3 and the Results Based Aid pilot project in education are 23.1% and 12%, respectively. / Option 1b: delivery via the government in support of Ethiopia’s GEQIP phase 2 project with a QESSP 2 component. / In this option, in addition to the benefits described above, it is assumed that there is a specific management strengthening and capacity building component, QESSP 2, which will increase the overall efficiency of spend in the sector by 1% each year. Quantifying the gains arising from efficiency improvements is subject to considerable uncertainty. A McKinsey study in 2004 suggested that productivity could increase in the public sector in the USA and a number of other countries by anywhere between 5% and 20% over 10 years.[12] On the other hand the UK’s Office for National Statistics published a report in 2009 which estimated annual average productivity growth in the education sector during 1996-2009 at 0%.[13] Among developing countries a recent PER in Pakistan which focused on sub-national governance found a potential efficiency saving of up to 2.5% of public expenditure (0.5% of GDP) as a result of a wide range of measures comparable to those anticipated under PBS 3.[14] In the Africa region an estimate of one per cent of Government expenditure is often assumed to be a fair reflection of the efficiency gains arising from budget support programmes and that is the estimate adopted in this appraisal. / Given the modest returns to efficiency initiatives in the public sector, the additional discounted benefits arising from QESSP 2 and attributable to DFID, are also modest and are estimated over the lifetime of the project at £3.2 million. The overall benefit cost ratio rises slightly to 1.92 and the IRR increases to 35.9%. / Option 2a: delivery via non-state organisations without QESSP 2 / As noted in the business case for PBS 3, which also considered the option of delivery via non-state organisations, estimating the cost of delivery via non-governmental channels is not straightforward not least because the understanding among commentators of what is included under management and administration varies. / The business case for PBS 3 approved in October 2012 noted that procurement via Government channels often offered considerably better value for money than some NGOs. A recent study estimated the average administrative and management costs of over 900 US-based NGOs working in the area of international development at around 11.5% of total budgets.[15] Another study of 26 Bangladesh non-government organizations (NGOs) providing family planning services under a US Agency for International Development-funded umbrella organization found that “significant savings could be generated by containing administrative costs, improving operational efficiency, and reducing unnecessary or redundant fieldworker contacts. The magnitude of the potential savings raises a fundamental question about the continued viability and sustainability of this supply-driven CBD strategy.”[16] / Finally USAID in Ethiopia estimates that overheads as a share of total budget for its main delivery partners are between 15% and 30% depending on the program. An examination of the websites of some of USAID’s main delivery suggests a similar average overhead. However it is unclear if these data include overheads associated with individual projects also. / This appraisal assumes that administrative overheads in using NGOs as delivery partners in Ethiopia are likely to be at least 15% of total programme costs. Deliveries via UN agencies when employed as trustees of bilateral donor funds are typically about 7% of programme costs. Assuming (based on the experience of DFID in Zimbabwe) that 40% of DFID’s support for education under this option is delivered by UN agencies and 60% by NGOs then the weighted average of overheads as a share of total programme costs is approximately 11.8%. Administrative, advisory and other support costs in the Government of Ethiopia are estimated in the ESDP IV at 7.2%. But Government overheads associated with the administration of GEQIP 2 are likely to be lower than this since the bulk of actual delivery is at regional and woreda levels. This appraisal therefore assumes government overheads equivalent to 3% of programme costs resulting in a net additional overhead cost associated with non-state delivery of 11.8%-3%= 8.8%. / Under this option there is no QESSP 2 and hence no additional efficiency gains realized. The net discounted value of efficiency gains under this option are therefore zero. / It is also assumed under this option that the decision to go through non-state agencies causes a delay of a year before other donors join the project and then only 50% do so. The result is that the share of the school cohort that benefit from improved learning falls from 60% to less than 55% and those that do benefit gain only 1.35 extra years of learning equivalent rather than 1.5 years as under Option 1. / The result of these assumptions is that a benefit cost ratio for the non-state actor option of 1.4 and an IRR of 20% i.e. considerably lower than under Option 1. / Option 2b: delivery via non-state actors with QESSP 2 / In this option, in addition to the benefits described above, it is assumed that there is a specific management strengthening and capacity building component, QESSP 2, which will increase the overall efficiency of spend in the sector by 1% each year as described under Option 1b above. The result of this addition is a small increase (relative to Option 2a) in the benefit cost ratio to 1.43 and in the IRR to 21.1%. / Option 3: QESSP 2 only / Under this option DFID does not contribute to GEQIP 2 but provides a total contribution of £10 million to QESSP 2 spread over 4 years. In addition it is assumed that with DFID – as the lead donor in GEQIP – withdrawing completely from GEQIP 2 then donor confidence collapses, and GEQIP 2 does not go ahead at all. Without the outputs expected under GEQIP 2 teachers would remain untrained, students would lack textbooks and other basic pedagogically important material, sector and school-level management would remain weak. In short, the sector as a whole would suffer. The share of the school cohort that benefit from improved learning is assumed to fall to 48% and those that do benefit gain only 1.2 extra years of learning equivalent. The Return on Investment (ROI) is also assumed to fall from 10% to 8% i.e. broadly in proportion to the share of non-wage spending in total recurrent spending. Even the impact of QESSP is compromised under this option and the efficiency return falls to .75%. This option results in a benefit cost ratio of 1.1 and an IRR of 13.8%. / Option 4: do nothing / As under Option 3, the option ‘do nothing’ is not neutral with respect to the IRR that would be expected for the remaining programmes in the sector, especially wage supporting programmes such as PBS. This is proxied in the current appraisal by a significant drop in the expected ROI to 5% which is towards the lower limits of ROIs estimated by (World Bank 2002). The share of the school cohort that benefit from improved learning is assumed to fall to 15% and those that do benefit gain only 0.38 extra years of learning equivalent (because they are still being taught albeit without basic materials to support them). Under this scenario, the benefit cost ratio for the sector as a whole falls to approximately 1, the IRR drops to about 12% - i.e. returns are at the breakeven point - and overall sector net benefits fall to £12 million with zero attribution to DFID (other programmes excepted) by virtue of GEQIP 2. In other words funding to support teachers under PBS III and the FBG more generally is still just about worthwhile – even a teacher with little training and no materials is better than no teacher at all – but the returns are considerably less than under Option 1 where there is a balance of non-wage and wage inputs. / Summary of costs and benefits / The estimated IRR, benefit to cost ratio and Net Present Value (NPV) of net benefits for each of the options discussed above are summarised in the table below: / Table 5: Summary of CBA results for Options 1 to 4 / Option IRR Benefit/cost NPV £ (DFID) / 1a 34.8% 1.89 78,421,568 / 1b 35.9% 1.92 90,184,816, / 2a 20.4% 1.4 33,523,655 / 2b 21.1% 1.43 40,230,084 / 3 13.8% 1.1 876,675 / 4 12.1% 1.01 0 / Sensitivity analysis / As discussed above the CBA for all three options are based on a number of assumptions which may or may not be accurate in reality. To test the robustness of the CBA results to changes in these assumptions a sensitivity analysis was carried out by varying key assumptions to the point where the IRR under Option 1 equals the discount rate of 12% or equivalently NPV=0 i.e. the project loses economic value. (Unsurprisingly the impact on Options 2-4 is even more severe under these scenarios.) The variations required to make DFID’s support to GEQIP 2 no longer a viable investment are: / The Return on Investment for every additional year of education completed falls from 10% to 5.3%; or / The assumed addition of the average equivalent of 1.5 years to a student’s primary and secondary school career that GEQIP 2 and other programmes bring is reduced to 0.77 years; or / a drop in the share of the school cohort benefiting from additional equivalent years of schooling completed from 60% to 29% / a near doubling of overall costs (by 90%) / Under any of these scenarios the NPV of DFID’s contribution to GEQIP 2 would fall to zero. However each of the variations on its own comprises a major shock to the central assumptions of the appraisal. As such they demonstrate, it is argued, that the results of the CBA are relatively robust.
H. Theory of Change (ToC) for Preferred Option / The need for a multi-faceted approach to improve quality is set out in the strategic case above. The Government’s GEQIP Phase 2 project document describes the approach in detail. The Theory of Change, based on the Government’s document, is presented in diagrammatic form below. It is similar to the ToC underpinning GEQIP Phase I, but has been nuanced to reflect effort to maximise the impact on student learning during Phase 2. The ToC is based on a school effectiveness model[41] and the logic can be articulated as follows: / In order to bring about improvements in quality in primary and secondary schools as measured by learning achievement (the desired ‘impact’) it will be necessary to make sure parents and school management focus on learning for all, including ensuring that teachers are in their classrooms and have sufficient knowledge, skills and resources to enable them to engage all students in learning (the outcome). / This will require an integrated package of better quality and more relevant resources to be available in schools, including well-managed and trained teachers, instructional materials (including ICT), and basic school infrastructure such as desks, chairs, and roofs (the outputs). / The most significant requirement to achieve this increase in resources will be increased non salary recurrent spending, especially in schools and teacher training institutions (TTIs) / In order to maximise the effectiveness of this spending strengthened education and planning skills will be required, particularly at the school and woreda levels and improved upward accountability of schools and TTIs through better assessment and inspection systems. / In addition, in order to ensure that data and feedback inform decision making in an on-going way more and better disaggregated data are needed to measure results, learn lessons and contribute to a growing evidence base of what works to improve learning / Finally, the needs of communities need to be reflected in how school level budgets are formulated and executed through the identification of priorities: processes and capabilities have to be established for this ‘voice’ to be heard and responded to by the school. Building the social compact between citizens and schools through the School Improvement Planning process will be crucial to ensuring that additional resources to schools are well-managed, correctly targeted, and the intended results are actually achieved. / Figure 3 GEQIP Theory of Change (ToC) / Evidence underpinning the Theory of Change / The evidence underpinning the ToC and its key assumptions is summarised below. To the extent possible, the strength of the evidence has been assessed using the criteria developed for the DFID draft How to Note[42]. / GEQIP’s design is based on a school effectiveness model which makes the case for a holistic approach to improving learning outcomes. The Theory of Change predicts that the outputs in combination will make a difference rather than at the individual component level. A robust evaluation and component specific studies are needed to test this theory of change and to measure the impact of the programme. In line with the recommendations of the Independent Commission for Aid Impact (ICAI)[43] improving learning outcomes are at the heart of GEQIP 2 and the programme’s results frame work primarily focuses on measures of learning at the impact level. / Input to output: / Can a package of inputs be delivered to schools? / Since the current government in Ethiopia came to power in 1991, GoE has demonstrated that it is committed to the education sector (the education budget has tripled over the past five years) and can deliver education inputs at scale to all public schools. Recent achievements include: / 2.9 million more children enrolled in primary school between 2007 – 2012 (1.7 million girls) / 200,000 more children enrolled in lower secondary school between 2007 – 2012 (180,000 girls) / The number of qualified teachers in primary schools has increased from 115,000 to 175,000 (2009 – 2011) / The number of qualified teachers in secondary school has increased from 31,000 – 45,000 (2009 – 2011) / These achievements and others are highlighted in the MoE Annual Education Statistical Abstract[44]. GEQIP Phase 1 supported inputs such as textbooks and school grants which are also now reaching schools and beginning to lay the foundation for quality improvements. These achievements and others are highlighted in the mid-term review of project performance conducted jointly by the government and GEQIP donor partners[45]. They are further elaborated in the government’s GEQIP Phase 2 project document. / There is evidence that input based programmes and increased resources alone have a limited impact on learning outcomes[46]. However, this does not mean that increased spending does not matter in any context. The logic underpinning the GEQIP ToC is that at current levels of spending in Ethiopia and with large class sizes, inputs do matter. These additional inputs, coupled with a clear overarching policy framework related to how they can be most effectively deployed at district and school level, are the basis for GEQIP design. In the section below we attempt to provide evidence for the assumptions underpinning the Theory of Change. We present the evidence for each component separately, but argue subsequently that much less is known about which precise mix of inputs will maximise impact on teaching and learning. DFID-E plans to strategically use QESSP resources to work with GoE to develop a better understanding of what mix works best in the Ethiopian context. / Output to outcome / Can these outputs contribute to more effective schools? / The strength of the evidence that these outputs will contribute to improving school effectiveness in Ethiopia is presented below. / More relevant curriculum and associated instructional materials, assessment and inspection (evidence = strong) Recent evidence has pointed to the importance of a curriculum which is relevant and meets the needs of all pupils, including focusing on basic skills[47]. The GEQIP Phase 1 Business Case shows that while the evidence on the impact of instructional materials is mixed, this is most likely because in many cases learning materials are not appropriate to the achievement levels of pupils or to their home language and teachers are not adequately trained to use them. If those conditions are fulfilled, then instructional materials do improve learning outcomes in environments with limited resources[48]. These findings are confirmed in Ethiopia by the 2012 National Learning Assessment[17] which found significant relationships between learning achievement and textbook availability and match between school and home language in grade 4, and of textbook availability at grade 8. GEQIP Phase 2 will focus on maximising the relevance of instructional materials (including with respect to the language of instruction), ensuring that they are delivered to schools in a timely fashion and that they are well utilised in the classroom. Based on lessons learned from Phase 1, greater emphasis will be put on decentralising the development and provision of instructional materials to regional level in order to increase their relevance and timely distribution to schools. / Better trained teachers with clear career structure (evidence = medium) The Glewwe recent best evidence synthesis[49] found mixed evidence on in-service teacher training, but consistent results on teacher knowledge (in other words, the better a teacher understands their subject the more effective they will be at teaching it which lends support for lifting the basic qualifications of teachers). However, other sources of evidence consistently highlight the impact on learning achievement of better trained and motivated teachers both internationally[50] [51] and in the Ethiopian context[52]. In line with research into teacher preparation and continuing professional development in Africa over the past ten years[53] [54], GEQIP focuses on ensuring that pre-service teacher training is relevant and grounded in actual classroom reality (through support to the practicum), that high quality candidates are entered for training (through the selection process), and that more learner centred methods are imparted through training courses and associated training materials. In addition, the introduction of a teacher licensing system which Phase 2 will support is designed to address aspects of the issue of continuing professional development and teacher incentives, which evidence suggests is key if teachers are to put what they have learnt into practise. In addition, the teacher development component will be evaluated in the first year of GEQIP 2 as a means of learning further lessons for implementation. GEQIP does not include any element focusing on teacher remuneration and financial incentives, but this is an important element of policy dialogue through PBS 3. / Schools with inclusive development plans and increased per capita financing (evidence = medium) GEQIP 1 established an effective system of distributing and managing school grants and by 2012 over 98% of schools were receiving grants and using them for their intended purposes. A manual guides school grant spending and disallows spending on new school building and some electrical items, A separate process of school improvement planning with community participation agrees how all school finances, including the grants, will be spent. There is relatively strong evidence that school level expenditure on basic inputs (teaching materials, tables, chairs, roofs that do not leak) can have a positive impact on learning outcomes including a systematic review assessing twenty years of research[55]. However, these basic inputs need to be aligned with efforts to improve learning at school level. Building on lessons from Phase 1, a feature of Phase 2 is greater emphasis on getting schools to focus on learning through a better focused and more streamlined school improvement planning process. There will also be an increased focus on making information available to parents through school report cards at the woreda (district) level, which was piloted during Phase 1. A study of the impact of school grants on learning achievement in India and Zambia[56] found that predictable per capita grants tend to substitute for parental inputs at school level and are therefore unlikely to improve learning outcomes as they simply crowd out private expenditure. The available evidence from Ethiopia indicates that school budgets over the course of GEQIP Phase 1 have been increasing, and that this has impacted favourably on school level infrastructure[57]. Although community contributions remain an important source of school income, in the medium term policy makers in Ethiopia are seeking to reduce school reliance on them in order to address equity concerns. It is planned to maintain more equitable school level financing through decentralised government funding going forward. In GEQIP Phase 2, this decentralised financing will be monitored during implementation. The government will also experiment with payments linked to special needs and gender in order to further accelerate progress on equity. / Improved planning and management capacity (evidence = limited) GEQIP Phase 1 put in place a framework for capacity building efforts to help promote learning by supporting the MAP capacity building study. In terms of where to focus capacity building efforts, a recent study of how education systems improve, identifies a cluster of interventions which need to be implemented in a context sensitive way. For a system such Ethiopia’s, this suggests two clusters of interventions that are relevant to GEQIP: a) finding ways to provide motivation and support for low skill teachers and principals and b) bringing schools up to a minimum quality standard[58]. There is also some evidence that School-Based Management reforms are necessary but insufficient for improving the quality of teaching and learning in schools but the evidence base is limited[59] [60]. An impact evaluation from Uganda[61] presents positive results from a project focusing on strengthening both district and school level management capacity building in Masindi District, but more evidence is needed on the impact of such combined capacity building efforts. Based on the emerging literature and lessons from Phase 1, GEQIP Phase 2 will increase the emphasis on capacity building at the district level in order to push reform efforts down to school level and maximise impact in the classroom. It is also prioritising management and leadership training for school directors. QESSP 2 is designed as a complementary instrument to provide additional impetus to capacity building efforts at both federal and decentralised levels through the provision of complementary support. Institution building figures much more prominently in the results framework and is planned to be more of a focus of evaluation efforts. / Schools equipped with ICT for learning (evidence = medium) The recent best evidence synthesis by Glewwe et al found inconsistent results with respect to the impact of ICTs on learning outcomes[62]. The impact can be positive, but according to a UK focused secondary study it appears that the efficacy of ICTs is highly dependent on the relevance of the infrastructure to the learning context and the teachers’ ability to use it well to promote better learning[63]. The key message from the literature to date is to focus on pedagogy and not the equipment. For this, beyond equipment, GEQIP 2 will focus on strengthening the coordination and management of ICT in education by providing a comprehensive policy framework, establishing a national ICT Infrastructure Improvement Plan for General Education; and through teachers’ professional development in ICT. GEQIP 2 will pilot the introduction of ICT in 200 schools and will include a separate evaluation to test the impact of the ICT provision at midterm. / More effective sector coordination, monitoring and evaluation (evidence = medium) This type of input has not been the subject of much quantitative analysis, possibly because it is seen as pre-requisite for systems to improve learning outcomes. Both the Edqual and the CREATE consortia (funded by DFID) highlight the importance of monitoring and evaluation in order to generate information for systems improvement and better targeting of resources[64]. Bruns et al in their Making Schools Work study also suggest that information for accountability is one of three core mechanisms, together with school-based management and teacher incentives, for effective and accountable school systems[65]. Similarly, the McKinsey report highlights the importance of better data systems as one of the elements of successful reform. GEQIP Phase 2 includes an emphasis both on strengthening regular monitoring data and on building a better evidence base through evaluation. QESSP will provide complementary inputs to strengthen the evaluation component of Phase 2 as some aspects of the comprehensive evaluation undertaken in Phase 1 were disappointing. In particular, while the evaluation was able to identify change at school level which can be associated with GEQIP, it did not link these to any measurable improvement in the quality of learning (such as test scores). These issues, and how DFID proposes to address them in Phase 2, are further expanded on in the section on monitoring and evaluation. / Outcome to impact / Will these outputs in combination result in improved learning for all pupils? (evidence = medium) / The main source of evidence on learning achievement over time in the Ethiopian context comes from the Ethiopian National Learning Assessment, which is described in more detail above. This is a sample based assessment that has been conducted by GoE in key subjects in grades 4 and 8 since 2000. The assessment includes a sample of schools and students from all the regions in Ethiopia and is large enough to generalise to the population. Comparisons of student performance between tests are descriptive rather than analytic, and this is the data that is presented below. / GEQIP Phase 1 was launched in 2009; two years after the results of the 2007 National Learning Assessment were released. During Phase 1 implementation, another assessment was conducted after two years of implementation in 2011. The results of these two assessments for grades 4 and 8 are compared below. Data is now also available for grades 10 and 12 but only at one point in time so is not presented here but is included in the logframe baseline. / Table 6: Grade 4 results (Mean and standard deviation) / Year Maths Reading English Composite / 2007 40.3 (17.0) 43.9 (20.4) 36.5 (15.7) 40(11.8) / 2011 37.1 (16.82) 43.0 (19.9) 38.9 (18.7) 39 (15) / In comparing the 2007 and 2011 results, the 2011 NLA report concludes that while there have been no appreciable gains between the two tests, the fact that the previous decline in standards has been halted is a positive sign. They speculate that this may be partly attributable to the GEQIP intervention. The generally low levels of achievement across all subjects remains cause for serious concern. / Table 7: Grade 4 results by gender / Year Maths Reading English Composite / Boys Girls Boys Girls Boys Girls Boys Girls / 2007 40.4 40.2 44.1 43.8 37.6 35.2 41.4 40.3 / 2011 37.9 36 43.2 43.3 39.3 38.1 40.5 39.6 / In 2007 boys outperformed girls in all subjects, and the difference in maths achievement was significant. In 2011 girls are slightly outperforming boys in the reading test, but the maths result is significantly lower. In general, girls continue to slightly lag behind boys although the differences are relatively small. / Table 8: Grade 4 results by region (composite score only) / Region 2007 2011 / Amhara 45.2 43.5 / Addis Ababa 44.0 52.3 / SNNPR 42.5 42.2 / Oromia 42.3 38.5 / Tigray 41.8 38.2 / Dire Dawa 40.9 38.6 / Benishangul 39.5 36.3 / Afar 39.3 36.3 / Harari 38.9 40.2 / Gambella 34.3 32.1 / Somali 33.8 41.2 / The only two regions that have shown marked increases since 2007 are Addis Ababa (the capital of Ethiopia and urban centre) and Somali Region (one of the developing regional states with a large pastoralist population). Otherwise, most regions have either declined or stayed more or less stable. The three Developing Regional States of Gambella, Afar and Benishangul continue to lag behind the others. A number of regions with traditionally stronger policies and institutions (Amhara and SNNPR, for example) tend to perform relatively better than others on the grade 4 assessment. / Table 9: Grade 8 results (mean and standard deviation) / Year Maths English Biology Composite / 2007 34.1 (14.7) 38.4 (15.3) 38.3 (13.8) 35.6 (11) / 2011 25.5 (11.4) 36.9 (15.8) 42.1 (16.7) 35.3 (8.6) / The composite score for grade 8 is pretty stable over the two assessments. However, this masks wide variation, particularly in the maths scores. The 2011 result is extremely poor and indicates that the government’s attention to improving performance in this area at the higher grades is highly relevant. Science scores (only Biology is included in the table, but physics and chemistry are also assessed) all showed increases from 2007 to 2011. / Table 10: Grade 8 results by gender / Year Maths English Biology Composite / Boys Girls Boys Girls Boys Girls Boys Girls / 2007 35.9 31.5 40.3 35.5 40.2 35.5 37.3 33.1 / 2011 25.9 25.4 38.7 35.7 44.2 40.3 36.4 34.5 / As would be anticipated from the overall mean scores, performance for both boys and girls fell in maths and English in 2011 as compared to 2007. However, the gap between boys and girls in 2011 was much narrower in both subjects and in the composite score. This may indicate that progress is beginning to be made on reducing gender disparities in the higher grades. / Table 11: Grade 8 results by region (composite results only) / Region 2007 2011 / Amhara 36,9 35.5 / Addis Ababa 34.0 38.4 / SNNPR 35.6 36.9 / Oromia 37.1 36.5 / Tigray 42.1 38.7 / Dire Dawa 33.4 35.5 / Benishangul 32.1 34.2 / Afar 34.6 31.6 / Harari 35.6 34.5 / Gambella 30.8 31.2 / Somali 34.2 33.7 / Five regions increased their composite score from 2007 – 2011. These were Addis Ababa, SNNPR, Dire Dawa, Benishangul and Gambella. Of the others, Tigray, while showing a decline in 2011, was still the best performing region on both assessments. This is consistent with its relatively strong implementation capacity. The worst performing regions in 2011 were Gambella and Afar. These two regions have perhaps not had as much attention from government and development partners as the other two Developing Regional States (Somali and Benishangul) and Gambella in particular has had problems with conflict over the last few years. / Given that GEQIP was still only in its early days of implementation in 2011 and inputs were just starting to reach schools, the results should not come as too much of a surprise, Systems reform to improve learning outcomes at scale takes time (McKinsey’s estimate is six years), and GEQIP was designed as a two phase programme over eight years to reflect this. There will be a National Learning assessment in 2015 and the results of this NLA will be an important indication of whether the government’s policies are having the desired impact on learning achievement. Other possible complementary approaches to assessing GEQIP’s impact on learning are discussed in the section on monitoring and evaluation below.
I. What measures can be used to monitor Value for Money for the intervention? / The cost benefit analysis has demonstrated that for specific costs and assuming certain benefits Option 1 is preferred to Options 2 and 3 in terms of the associated IRR and benefit to cost ratio. In order at least to minimise costs and maximise benefits it will be necessary during implementation of GEQIP 2 to track closely the financial unit cost of inputs (the economic aspect of the programme), to maximise the outputs obtained for each input purchased (the efficiency of the programme) and to ensure that each output contributes to outcomes as much as possible (the effectiveness of the programme). / Economy / The largest single element of costs within GEQIP 2, about 44%, consists of the school improvement component which includes school grants and is designed to enable schools to meet recurrent non-wage costs subject to school grant guidelines developed by the project. The items purchased by schools under this component will clearly vary and cannot easily be specified in advance of the project. (Under GEQIP 1 the grant was often used by schools to purchase laboratory equipment and upgrade infrastructure but these types of purchases are likely to be limited under GEQIP 2.) The economy of these inputs will be monitored through the school grant evaluation and the school level audit. Other metrics proposed to track the unit costs associated with the main inputs of the programme are as follows: / Table 6: Measures of Economy / Efficiency / The efficiency of GEQIP 2 relates to the extent to which items such as textbooks purchased actually translate into textbooks used in schools: simply purchasing textbooks which are then left unused would be an inefficient use of resources. Suggested key indicators for monitoring the transformation of inputs into outputs are summarized below. All these measures (except the ICT indicator which is new) have improved during phase one of GEQIP. / Table 7: Measures of efficiency / Project output Measure of efficiency Baseline Target / More relevant curriculum and associated materials Availability of books in schools – textbook/pupil ratio 1:1.5 1:1 / Better trained teachers Proportion of qualified teachers in schools 56% in primary 95% / Schools with inclusive development plans % of schools using per capita grants to fund their improvement plan priorities 95% 100% / Improved planning and management capacity % of woredas producing annual work plans on time tbc 100% / Schools equipped with ICT for learning No. of schools have a new computer laboratory installed and operational 0 200 / More effective sector co-ordination No. of Implementing Agencies submitting reports by March and October each year tbc 100% / Effectiveness / The effectiveness of GEQIP 2 captures the extent to which the outputs described above – e.g. textbooks used in class – translate into the outcomes sought under the programme i.e. more effective schools focused on learning. Key metrics that could be used to track this transformation are as follows: / Table 8: Measures of Effectiveness / Project output Measure of effectiveness / Deliver better textbooks Textbook utilisation / Teacher development Teachers use more interactive teaching methods / Management capacity building Schools have functioning school improvement committees / ICT Teachers use technology to promote learning / M&E Woredas use data to inform their planning / These measures of effectiveness will be tracked thought the component specific evaluation and the rigorous impact evaluation discussed in the monitoring and evaluation section of the management case. / Cost effectiveness / In addition to the indicators identified above, the overall cost effectiveness of GEQIP and out other investments in the sector will be monitored through attention to: / Cost per primary pupil educated (current estimate is £20 per pupil / Cost per school grant (currently an average of £1.90 per annum / Teacher salary cost (tracked through PBS) / Total cost per primary teacher trained (current estimate is £475 per year)
J. Summary Value for Money Statement for the preferred option / Summary value for money statement / The above analysis together with the Strategic Case support the investment by DFID of £130 million in support of non-wage recurrent costs in the education sector through GEQIP 2 (plus QESSP 2) for the following reasons: / investment in basic education is a strategic priority for DFID because of its impact on poverty / the overall return on investment in education is high and there has been rapid progress in educational outcomes / however the GoE by itself is unable to invest what is needed to bring Ethiopia’s basic educational indicators in line with comparator countries / the high return on investment in education depends on an appropriate balance between non-wage and wage inputs which would not exist without GEQIP 2 / the choice of GEQIP as an instrument helps maintain a range of opportunities for engaging with GoE on education / The specific amount of DFID’s proposed investment in GEQIP 2 is in line with the overall priority accorded to education within the DFID Ethiopia budget. / Investing in GEQIP 2 (plus QESSP 2) via government is a better way of delivering DFID’s investment than working through non-state actors because of the higher overheads associated with the latter approach or doing nothing at all because of the negative impact that this would have on other investments in the sector such as PBS III. Ensuring the economy, efficiency and effectiveness of DFID’s investment in GEQIP 2 will be tracked using the indicators set out above.
[30] DFID HDRC Report, Low Cost Private Schools, 23rd February 2012
[31] Federal Democratic Republic of Ethiopia (December 2012) GEQIP Phase 2 project Document. Ministry of Education, Ethiopia
[32] Bleichrodt N, Born MP. A metaanalysis of research on iodine and its relationship to cognitive development. In: Stanbury JB, ed. The damaged brain of iodine deficiency. New York, NY: Cognizant Communication, 1994:195–200.
[4] The DFID Guidance Note ‘Learning and Teaching Materials: Policy and Practice for Provision’, based on an analysis of international experience and research in this area, recommends decentralised as opposed to centralised supply of textbooks.
[33] DFID Ethiopia, Peace and Development Programme: Support to the delivery of basic services in the Somali Region of Ethiopia. DFID Business Case
[5] USAID, May 2012
[34] Method et al (July 2010) Impact assessment of USAID education programme in Ethiopia 19994 – 2009. USAID
[35] Lillis, K (May 2009) Review of the Pooled Fund Project Education. TWG, Ethiopia
[36] DFID (2013) Annual Review of Quality Education Strategic Support Programme
[37] Wheeler, D and Hammer, D. (November 2010) the economics of population policy for carbon emissions reduction in developing countries. Working Paper 229, Centre for Global Development, Washington D.C.
[38] Hughes, Kerr-Wilson, Mussa and Johnson (2008). ‘Protection of Basic Services: Social Inclusion and Gender Equality.’ Social Development Direct. September 2008.
[39] Jennings, Mary, Mekonnen, Elizabeth and Gudissa, Demissie (2011) ‘Social Assessment for the Education Sector Ethiopia’. 2011
[40] Brocklesby, Hobley and Scott-Villiers (2010). “Raising Voice – Securing a Livelihood: The Role of Diverse Voices in Developing Secure Livelihoods in Pastoralist Areas in Ethiopia.” IDS Working Paper 340. March 2010.
[6] Discussions with Head of Korahey Zonal Administration, March 2013
[7] Additional data points include the following: in Botswana during the 1980s and 1990s non-wage expenditure averaged 15% of total recurrent expenditure in the education sector; and in Malawi in the 1990s it averaged 12%. In Uganda, following significant reforms the share increased from about 7% in the early 1990s to about 27% in the latter part of the decade. Samar al Samarri, Financing Primary Education for All: Public Expenditure and Educational Outcomes in Africa, August 2003, Institute of Development Studies.
[8] Returns to Investment in Education – a Further Update, George Psacharopoulos and Harry Patrinos, World Bank Policy Research Working Paper 2881, 2002. More recently Colclough, Kingdon and Patrinos in The Patterns of Returns to Education (Recoup Policy Brief #4, April 2009) have suggested that the distribution of returns to education may have shifted away from primary education in some developing countries in favour of higher levels of education. However returns to primary education in the Sub-saharan African countries cited by the article are: 12% in South Africa, 11.6% in Kenya, 10.2% in Tanzania and 8.9% in Ghana which appear consistent with an assumed 10% rate of return in Ethiopia.
[9] The 2009 PISA report also analyses the power of a range of factors to explain variations in student and school performance and finds that a school systems overall performance can explain as much as 58% in the variation in performance across participating countries. Volume 4 (page 54).
[10] This reflects the fact that some students will be in their last year as GEQIP begins and hence only benefit for one year; some will be in their penultimate year and benefit for 2 years; and some will be in their first year and benefit for up to 12 years. Assuming that the text books, teacher training and other school improvements undertaken under GEQIP 2 last for 10 years then summing the years benefit enjoyed by students during that period (ie 12+11+ … +3) and dividing by the total of 120 results in 63% which is rounded down to 60%.
[11] Data from January 2013 record of donor spend for 2012.
[12] Thomas Dohrman and Lenny Mendonca, Boosting Government Productivity, McKinsey Quarterly 2004, Issue 4
[13] Baird, Allen et al, Public Service Output, Input and Productivity: Education. National Office of Statistics, November 2010.
[14] World Bank (Islambad) Public Expenditure Review 2010
[15] Nunnenkap et al, US-based International NGOs involved in International Development Cooperation: Survival of the Fittest?
[16] Fiedler J, Day L, A cost analysis of family planning in Bangladesh, International Journal of Health Planning Management, 1997, 1997 Oct-Dec;12(4):251-77
[41] Guoxing Yu (2008) research evidence of school effectiveness in sub-Saharan Africa Sub-Saharan African Countries Sub-Saharan African Countries. Edqual Workng Paper No.7. University of Bristol, UK
[42] DFID How to Note (January 2013) Assessing the Strength of the Evidence
[43] ICAI (2012) DFID’s Education Programmes in Three East African Countries.
[44] Federal Democratic Republic of Ethiopia (September 2012) Education Statistics Abstract 2011 – 2012. Ministry of Education, Addis Ababa
[45] World Bank Aide Memoire. ETHIOPIA General Education Quality Improvement Program Mid-Term Review Mission Addis Ababa, May 2 -26, 2011
[46] Hanushek, E. (2003) The failure of input based schooling policies. The Economic Journal, 113 (February)
[47] USAID (October 30, 2010) Report of the Early Grade Reading Assessment. Prepared by RTI International
[48] Nannyonjo, (2007).Education Inputs in Uganda An Analysis of Factors Influencing Learning Achievement in Grade Six : World Bank, Africa Region Human Development Dept., Washington, D.C.
[17] The National Learning Assessment is a sample based assessment that has been conducted every three years in grades 4 and 8 since 2000. In 2010 it was conducted in grades 10 and 12 for the first time. It includes measures of learning in key subjects and identifies their determinants. Despite some technical weaknesses it is the best measure that we have of learning achievement over time. Some of the reports can be found at http://www.nae.gov.et/Public/MiscellaneousDownloads.aspx
[49] Glewwe, Hanushek, Humpage and Ravina (October 2011) School resources and educational outcomes in developing countries: A review of the literature from 1990 – 2010. National Bureau of Economic Research, Cambridge MA
[50] Report of the General Education Access, Equity and Quality: Research into Practice conference held in Addis Ababa, Ethiopia form 2 – 4 April, 2012.
[51] Mourshed, M., Chijioke, C., and Barber, M, (2010) How the world’s most improved school systems keep getting better, McKinsey&Company
[52] National Examinations Agency (January 2012) Ethiopian fourth and eighth national learning assessments of students in grades 4 and 8. Addis Ababa, Ethiopia
[53] Lewin, K. and Stuart, J. (March 2003) Researching teacher education: new perspectives on practice, performance and policy.MUSTER Synthesis Report, University of Sussex
[54] Akyeampong et al (July 2011) Teacher preparation and continuing professional development in Africa. Univeristy of Sussex
[55] Glewwe, Hanushek, Humpage and Ravina (October 2011) School resources and educational outcomes in developing countries: A review of the literature from 1990 – 2010. National Bureau of Economic Research, Cambridge MA
[56] Das et al (2011) School inputs, household substitution and test scores. World Bank Policy Research Working Paper 5629
[57] Pfaffe, J.(June 2013) Comprehensive Evaluation of GEQIP: Final Exit Survey Report. Hifab/Ministry of Education
[58] Mourshed et al ibid
[59] Barrera, F., Fasih, T., & Patrinos, H. with Santibáñez, L. 2009. Decentralized Decision-Making in Schools. The theory and evidence on School-based management. Washington DC: The World Bank. http://siteresources.worldbank.org/EDUCATION/Resources/278200-1099079877269/547664-1099079934475/547667-1145313948551/Decentralized_decision_making_schools.pdf
[60] Arcia, G., Patrinos, H., Porta, E., & Macdonald, K. 2011. School Autonomy and Accountability in Context: Application of Benchmarking Indicators in Selected European Countries. Regulatory Institutional Framework, Benchmarking Education Systems for Results, Human Development Network. The World Bank, Washington DC. http://siteresources.worldbank.org/EDUCATION/Resources/278200-1290520949227/School_Autonomy_Accountability_Framework.pdf
[61] IOB Impact Evaluation (April 2008) Primary Education in Uganda. Report no. 311
[62] Glewwe, Hanushek, Humpage and Ravina (October 2011) ibid
[63] Condie, R. et al (2007) The impact of ICT in schools – a landscape review. University of Strathclyde for BECTA, Coventry, UK
[64] Ministry of Education. General Education Access, Equity and Quality: Research into Practice. Report of a conference held in Addis Ababa from 2 – 4 April, 2012. DFID/British Council
[65] World Bank (2009) Decentralised decision making in schools. The theory and evidence on school-based management. Washington DC and Bruns et al. Making Schools Work. World Bank 2011

Commercial Case

Direct procurement through a contracted supplier

A. Clearly state the procurement/commercial requirements for intervention / DFID will exercise direct procurement of a management agency to manage QESSP 2 resources (£10 million) mobilising and managing capacity building and technical assistance and administering DFID’s and other donors’ contribution to a pooled fund.
B. How do we expect the market place will respond to this opportunity? / The management of QESSP 2 will require a provider with a presence in Ethiopia to administer local workshops and other events and access to an international network of education expertise. This mix of capacities is quite difficult to find. The British Council has been providing similar services under QESSP 1 and is well placed to compete. We anticipate that other UK based providers, such as Cambridge Education Consultants and CfBT may also consider bidding if they are able to open an office in Addis. Potential providers have been consulted and there is capacity to respond. / The procurement of a management agent has been included on DFID Ethiopia’s procurement pipeline.
C. How does the intervention design use competition to drive commercial advantage for DFID? / Once the business case is approved procurement process through the OJEU procedure will be triggered. It is anticipated that competitive bidding through OJEU will attract wider participation including from potentially new partnerships or sub-contracting arrangement between Ethiopian and foreign organisations. The selection of service providers will primarily be on the basis of ability to deliver a specified set of services to an adequate standard at a reduced budget. However, selection will not be on the basis of cost alone; additional considerations such as quality, relevant expertise, and proposed approaches to delivering the required products will also be considered, in order to ensure that optimal value for money is obtained. / The use of Ethiopian based organisations will be explored during the procurement process by encouraging possible partnerships between organisations in Ethiopia and elsewhere. Potential benefits of using Ethiopian based organisations include: greater knowledge of the programme and the environment in which it is implemented; strengthening of local capacity; and reduced costs. We will encourage applications that include both a mixture of Ethiopian and international experience. / The contract will be agreed for a period of 4 years with the necessary safeguards to ensure that cost increases over the period are subject to agreed limits. VFM reviews of supplier’s performance by DFID Ethiopia will be completed annually using criteria that will be elaborated by DFID in consultation with the service provider. These criteria will be related primarily to the quality and timeliness of the reports submitted by the service provider. Where VFM is not being achieved, there will be scope for early termination of a contract. / The decision to adopt direct procurement for this service, rather than to include them in the Trust Fund arrangements, was influenced by the perceived benefits to the Ministry of Education of having greater control over the selection and supervision of the service provider in these areas. The management agent will require strong networks of education professionals and significant experience of working with government to manage large meetings and workshops in the Ethiopian context. Ultimately, DFID anticipates that QESSP 2 will attract other Development Partners and results in greater coordination of capacity building inputs to the education sector. However, funding contributions from other donors will be transferred directly to the management agent rather than to DFID. Through the education Technical Working Group (TWG) this arrangement has been agreed with other donors.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The direct procurement comprises the provision of services required to mobilise high quality professional services managing events, and provide capacity building support as requested by the government. Therefore, professional fees will form the main cost; other costs will be incurred, such as the costs of hiring meeting premises, transportation to and from the regions plus accommodation and living expenses. Fee rates for the management agent, and the mechanism for review during the 4 years of the programme, will be agreed during contract negotiation. / The main cost drivers will relate to the number of visits, content and location of the work as well as the breadth and depth of analytic work that is carried out. Given the high current rate of price inflation in Ethiopia, the unit cost rates associated with these contracts will be kept under regular review; if needed, work plans will be amended to match the proposed activities and intended deliverables with the available budgets and contracts will be amended to reflect the changes. / Additional value to the programme will be ensured through the use of accredited contractors/bidders with sufficient capacity to perform the tasks required to a high standard. Terms of Reference will be used to define the framework (including key performance indicators such as performance in meeting the milestones detailed in agreed work plans, timeliness in reporting, ability to form professional and delivery-focussed links with a range of stakeholders in difficult operating environments, and budget control) within which contractors will be expected to work. These will provide the benchmark against which satisfactory performance is measured, and payment will be made upon their fulfilment. Regular work plans will detail the expected levels of input required to deliver agreed results.
E. How will the contract be structured and how will contract and supplier performance be managed through the life of the intervention? / Contracts will be awarded for 4 years with quarterly management meetings (more frequent meeting at start up and when necessary)and annual performance reviews carried out by DFID Ethiopia. If performance is assessed as unsatisfactory, as measured against indicators detailed in the respective contracts (including VFM indicators), then break clauses will be executed. Payments will be linked to results and will be made subject to the required level of performance being achieved. As part of contract negotiation, service level agreement and key performance indicators will be agreed with the service provider. The service provider will be expected to be aware of its roles and responsibilities, including the targets and baselines that form the performance based contract. During this post tender negotiation, it will be important for all parties to establish a shared understanding of the expectations from the contract. / Payments will be made by DFID Ethiopia on the basis of satisfactory service delivery measured against agreed quality standards and delivery times detailed in the work plans. Poor performance will result in reduced payments to the contractors. There will be no additional payments for when performance exceeds expectations. These payments will be authorised by the budget holder, using Aries to initiate payment following acceptance of the deliverables. / Variations to contracts will be managed directly with the contractor concerned and with notification to PrG of any potential changes to be made.

Delivery through a third party entity (multilateral organisation; civil society organisation or support to government)

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The bulk of the GEQIP2 funding will be channelled through a Trust Fund. The major part of the spending is Government executed, using Government procurement, treasury and accounting procedures with the World Bank having a strong fiduciary oversight role including issuing objections or no objections at different stages of government procurements. The proposed funding through a World Bank administered Trust Fund enables DFID to invest in a process as a partner without needing to take a lead role in its development and operational management thus reducing resource requirements and adding value. Also, the adoption of multi-donor Trust Funds facilitates the achievement of increased harmonisation amongst the participating DPs, though acknowledging that several DPs have opted for direct funding through traditional project-based interventions. / The World Bank is the preferred choice as the fund administrator. It has been assessed by DFID as an organisation that delivers value for money.[18] It has a successful track record in administering the Trust Fund used in GEQIP 1. It has a strong cadre of technical expertise required to undertake the enhanced supervision that the DPs require; this pool of expertise is available largely in-country and is able to respond promptly to particular needs and problems and informed by a detailed knowledge of the local operating environment. The ability to avoid set up cost help ensure that funds are maximised in the areas for which they are intended. / The Bank also has in place a set of procedures for sanctioning corrupt and fraudulent practices in connection with Bank-funded Bank-executed projects. It takes the issue of fraud and corruption very seriously and its anticorruption policies are of great relevance for procurement. The Bank requires from both the borrower and from the bidders “the highest standard of ethics” during the procurement and execution of contracts. The Guidelines determine ‘ethics’ as referring to ‘corrupt and fraudulent practices’. If mis-procurement based on fraudulent or corrupt practices is detected, the Bank will act not just within the funding agreement to cancel the portion of the loan related to the contract, but can also declare a firm ineligible under its debarment procedures. To enable the Bank to act against private companies, the Guidelines require a provision to be included in the contract giving the Bank full access to the contractor’s accounts and records related to the performance of the contract. The Guidelines define what is meant by fraud and corruption (in section 1.16 of the Procurement Guidelines and section 1.23 of the Consultant Guidelines). These definitions go well beyond the definitions used by other development banks and so evidence the commitment that the Bank has to reducing corruption. / The programme contains specific interventions to strengthen procurement practice, especially at the woreda level. The World Bank, with its in-country procurement expertise, will oversee and support this capacity building in Government. It will also draw on the results of the Country Procurement Assessment Report (CPAR). The key functions of the CPAR are to assess the efficiency, transparency and integrity of a country’s entire procurement system and to promote dialogue with governments on how to strengthen their public procurement systems. The CPAR thus provides a key input to the CAS for the Bank to support public procurement reform as part of an agreed implementation strategy. At a practical level, the main purpose of the CPAR is to establish the need for and guide the development of an action plan to improve a country’s system for procuring goods, works, and consulting services.[19] In addition one of the four cornerstones of WB procurement policies is the development of domestic industries. DFID Ethiopia will work with the WB to ensure opportunities for the local market are available through local and international competitive bidding. / While some other multilateral agencies enjoy some of these advantages the World Bank’s track record in Ethiopia and cost effectiveness as a Trust Fund administrator weigh in the latter’s favour. / The procurement mechanisms to be adopted will be dependent on the nature and size of individual contracts for the supply of goods and services. The procedures to be followed will be in line with Government’s own procurement rules but with additional safeguards administered by the WB in line with its published guidelines and standard operating procedures. E.g. design materials, bidding documents, the bidding process, and contracts may all be Government products but will also be subject to World Bank review and no objection in light of Bank minimum requirements. The WB country office procurement team will oversee the procurement processes to ensure their propriety and appropriateness. The WBs role in GoE's procurement includes the use of WB procedures for its ICB (International Competitive Bidding). It will use its own procedures for National Competitive Bidding which are overseen and supported by the WB. / Although there are many positive features of channelling DFID’s investment through these Trust Funds, this mechanism does present some possible risks. These risks might include: the risk of paying too much for goods and services which are over specified or above comparable market rates, or too little for goods and services which are not fit for purpose; the risk of not getting the services or goods required; and/or the risk of delays arising from completing aspects of the procurement process to a high enough standard to obtain a ‘no objection’ from the Bank’s technical and procurement experts.[20] The semi-annual review process will provide a regular opportunity for these and any other risks to be monitored and for immediate remedial action to be taken, if required. All key decisions and key documents will be stored in Quest so that reliable audit trails are available for the funding processes that are followed. The Ministry of Education as coordinator of GEQIP has developed a good working relationship with the World Bank team and that there will be an on-going dialogue to discuss progress.
B. What assurance has been obtained on capability and capacity to deliver? / With the understanding that major Procurement activities will be carried out by Ministry of Education (MoE); Public Procurement and Property Disposal Services of the MoFED (on behalf of the MoE); Some Regional Education Bureaus (REBs) that have strong procurement capacity, the Bank’s CO procurement unit has conducted procurement capacity assessment on more than 18 Agencies (including: Tigray REB, Mekele University; Abiadi CTE; Amhara REB; Bahir Dar University; Gonder CTE; Afar REB; Samara University; Harari REB; Dire Dawa City Administration. Education Bureau; Haromaya University; Dire Dawa University; Harar CTE; Hawassa University; SNNPR REB; MoE and PPPDS). / The assessment exercise used the Procurement Risk Assessment and Management System (P-RAMS) framework which was developed to align with the Bank’s risk based approach. The ultimate objective of the assessment is to identify procurement risks during project preparation and implementation stages and monitor them throughout the project cycle. The above mentioned GEQIP 2 implementing agencies (IAs) have been assessed for their procurement capacity and the result is that their procurement capacity is generally low. The major areas of weakness across all the IAs are: (i) weakness in their systems and practices of accountability for both quality and timelines of procurement and contract management decisions; (ii) scarcity of ICB procurement skilled staffs associated with high staff turnover; (iii) less experience in the preparation and usage of procurement Planning and implementation monitoring; (iv) less experience in processing and managing ICB contracts procurement and contracts management and administration; (v) except that of the MoE, all other IAs have less experience on Donor financed ICB contracts procurement in general and Bank financed contracts in particular. (v) Less efficient resolution of procurement complaints and procurement oversight systems and practices. / An assessment of the capacity of the Implementing Agencies to implement procurement actions for the project has been carried out by Tesfaye Ayele , a World Bank Procurement Specialist (assisted by different procurement consultants), during December 2012 and the first week of January 2013. The assessment reviewed the organizational structure for implementing the project procurement and the accountability systems including the interaction between the different IAs and the project’s staffs responsible for procurement and the experience of the IAs’ relevant central units for contract administration and finance. The Bank’s P-RAMS 11 risk factors were used for the assessment. In addition, the information in the report of domestic printers’ capacity assessment by Bank retained textbook specialist in 2011 was used as input to this report. / Risks identified: / Most of the issues/ risks concerning the procurement component for implementation of the project have been identified and include: / A major project procurement implementation issue remains to be coordination and supervision of all the decentralized implementation agencies. The MOE has some working experience with IDA financed projects, but and its procurement capacity has been built. However, though the ministry has a department for procurement, in the absence of consultants, the procurement capacity of the MoE is not adequate to handle GEQIP procurement. Similarly, regions and most participating institutions have little familiarity with Bank procurement procedures and have weak procurement capacity; / Outsourcing the procurement responsibility to another public department (PPPDS) may risk timely and quality procurement processing of the project. The PPPDS is only two to three years since its establishment and has not experienced any donor financed ICB contracts procurement and management. The Entity has limited experience and has no skilled staff in consultancy services selection. It has no technical expertise in specialized educational materials and supplies procurement (textbooks and reading materials, science lab equipment, educational IS procurement etc.). The entity is basically established for public assets disposal services and to carry out procurement of common user items and framework contracts for federal procuring entities. This will pose capacity risks with the outsourcing of GEQIP 2 to PPPDS; / Accountability for both quality and timelines of procurement and contract management decisions will be risk for the project procurement implementation; / Processing and managing ICB contracts procurement and contracts management and administration by PPPDS and REBs will be a risk to the project implementation ; / Procurement planning preparation and monitoring is another risk. / Procurement complaints handling and procurement oversight is another risk identified as a concern. / The decentralized implementation with many (more than 60) implementing entities and the weak capacity environment makes the oversight and supervision challenging. / Proposed risk management measures: / The main Project Implementing entity, the MoE, will have a competent project implementation team that can provide a regular oversight and support to all other IAs. This team has to comprise at least two procurement and contract management specialists who can provide the required technical assistance in this regards; / As procurement and contracts management capacity is still very weak, the project has to recruit procurement and contract management consultants to work on the project with the procurement department of the ministry and the Procurement Coordination Unit (PCU); / The GEQIP Programme Implementation Manual (PIM) needs to be revised to incorporate and define the accountability and business standards of each involving unit or individuals with the provision of regular evaluation of the performance of the system. The Procurement Section of the PIM will also include, in addition to the procurement procedures, the SBDs to be used for each procurement method, as well as model contracts for textbooks and goods procurement; / It is suggested that similar contracts would be combined and better packaged or bundled for ICB and sliced in order to attract both international bidders and national bidders. These ICB contracts to be packaged to few number of bigger contracts will be handled at the central level together with major consultancy services selection; / All the procurement staffs of the MoE will take procurement training provided by Ethiopian Management Institute (EMI) and Procurement clinics on procurement planning and monitoring will be provided to the IA’s staffs during project launching; / The Bank task team together with the project team for supervision and monitoring of the project implementation at decentralized levels will conduct regular implementation support and oversight to the project and an annual Independent Procurement Review (IPR) audit shall be conducted by independent firms. The findings of the IPR will be disseminated to all implementing agencies as a process of capacity building; / Procurement complaints against packages subject to prior review will be handled using the Bank’s established procedures. Complaints against packages below the prior review threshold will be handled by the Government but the Bank has been designated to oversee proper resolution of such complaints; / With regards to the IS/ICT procurement, it is recommended that the MoE has to have a clear strategy, feasibility study and identification of the requirements for this activity. We suggest a consultant should be on board, as a matter of urgency, to prepare a brief feasibility study together with implementation strategy from which the detail requirements can be drawn. / The MoE in collaboration with the task team has to start to work on readiness for procurement implementation including: discussing and finalizing the Procurement Plan (PP) (during appraisal) drafting of ToRs, preparation of specifications and schedule of requirements so that procurement may advance. The World Bank task team to hire a consultant (immediately) who can support the Borrower in drafting the ToRs for the consultancy services; Draft specifications, schedule of requirements and Bidding Documents for already identified assignments and Goods/textbook contracts / In general, despite the capacity issues and the risks identified, our intention to use GoE’s procurement and financial systems to deliver this programme is based on: / The above proposed risk mitigation measures and the fiduciary oversight role of the World Bank, / The fact that undertaking the bulk of procurement through GoE systems will incur lower transaction and overhead costs. It is also buildings capacity and strengthening GoE systems in the process / Reassurance gained from the 2010 Country Procurement Assessment Review (CPAR)[66] and the 2010 Public Expenditure and Financial Accountability Review (PEFA) that concluded that overall the public financial management systems and processes were functioning well by international standards. Several weaknesses were identified, but the conclusion was that these areas are being addressed adequately by the Government’s Expenditure Management and Control Programme. / DFID’s 2012 assessment of fiduciary risk[67] is ‘moderate’ which remains unchanged from the previous assessment in 2007. Overall, this rating reflects the view that Ethiopia has a sound Public Financial Management and Accounting system, except for weaknesses in the areas of accountability, transparency and procurement. Despite these weaknesses, the 2012 assessment concluded that “we believe that there is a reasonable confidence that DFID’s money would be used by the Government of Ethiopia for the intended programmes and projects”. DFID Ethiopia’s draft Annual Statement of Progress (April 2013) assessed the overall fiduciary risk to be stable (not improving and not worsening). / This decision is consistent with DFID’s aid effectiveness commitments to use country procurement systems whenever possible.
C. Is there an opportunity to negotiate on anticipated costs? / Government implementing entities will be able to negotiate costs without compromising quality. The available evidence from phase I suggest that competition has generally reduced costs and increased quality. The role of the World Bank has been important in providing technical support and due diligence for large international procurement packages. Value for money in government procurement will be tracked by undertaking periodic unit price comparisons for major items such as text books through annual reviews and with the assistance of World Bank procurement staff. / GEQIP 2 includes significant procurement of goods and services. Through competitive bulk purchase of essential inputs such as printing or reprinting of teaching and learning materials, procurement through GEQIP seeks to drive down unit costs to the lowest possible value without compromising quality. The World Bank’s and GoE’s (with procurement proclamation aligned with the UNCITRAL model) procedures in place to ensure that competitive tendering takes place to ensure cost are competitive.
[18] ‘Multilateral Aid Review - Ensuring maximum value for money for UK aid through multilateral organisations’, DFID, March 2011
[19] Where countries do not have sound systems the ability of those responsible for expenditure is strengthened by instruction in Bank-funded procurement rules and procedures but this will also depend on their familiarity with sound procurement practices. If these are not in place then the Bank may resort to the use of project implementation units (PIUs) to implement projects using resources from outside the government (often from the private sector) rather than relying on government officers.
[20] A review of bottlenecks in the procurement of energy-related contracts in Vietnam at the Bank found that 70% of delays occurred at the design stage of projects and in the bidding and preparation of bid evaluation reports by borrowers. No objections by the Bank accounted for only about 5% of the overall time taken.
[66] World Bank (November 2010) Ethiopia country Procurement Assessment Report. World Bank, Addis Ababa, Ethiopia
[67] DFID Ethiopia (2012): Fiduciary Risk Assessment

Financial Case

A. Who are the recipients of all proposed payments? / Out of the requested £130 million, £120 million will go to the Government of Ethiopia in support of GEQIP 2 through a World Bank Multi Donor Trust Fund (MDTF) and 2% of this will be paid to the bank for administering the trust fund. £10 million (for QESSP 2) will go to a management agent to be identified in a competitive process. It is anticipated that up to 10% of QESSP 2 resources will be a management fee.
B. What are the costs to be incurred directly by DFID? / The World Bank will claim up to 2% of our contribution for managing our finances through a multi donor trust fund (equivalent to £2.4 million over four years). This is for the Bank’s fiduciary oversight role (oversight of the government’s financial management and procurement in GEQIP 2) and for the enhanced project supervision and implementation support missions including hiring experts consultants to help monitor programme implementation as part of the six monthly enhanced supervision missions. As discussed in the commercial case the World Bank is judged to be best placed to continue to provide this service as they have effectively delivered during phase 1. Channelling GEQIP funds though the World Bank MDTF is generally judged as one way of managing DFID Ethiopia portfolio risk as the Bank’s safeguards relevant to this programme will be fully applicable. / Management agent for QESSP 2 will be directly contracted by DFID. Below is indicative allocation by Component. / Table 9: Direct cost by DFID / 2013/14 2014/15 2015/16 2016/17 / Research and evidence building £400,000 £550,000 £625,000 £625,000 / Capacity building and technical assistance £1,500,000 £1,700,000 £1,800,000 £1,800,000 / Management fee £190,000 £250,000 £280,000 £280,000 / Total £2,090,000 £2,500,000 £2,705,000 £2,705,000 / The estimated costs are based on DFID’s past experience of delivering the Quality Education Strategic Support Programme (QESSP) plus anticipated cost of research and evidence building including support to GEQIP’s impact evaluation and a 10% management fee. The management fee is for the services of the management agency that will mobilise capacity building and technical assistance and administer the education pooled fund. / DFID’s Education Adviser and the Deputy Programme Manager with support from other contract management and procurement colleagues will be responsible for ensuring delivery of results and monitoring of the management agent in coordination with the Ministry of Education and the Education Technical Working Group.
C. What are the costs to be incurred by third party organisations? / Table 10: estimated cost of GEQIP 2 and potential funding sources / Project Components Project cost, in million US dollars DFID Contribution in million Us dollars) % share / 1. Curriculum, textbooks and assessments 115 41.2 36% / 2. Teacher development program 70 25 36% / 3. School improvement program and school grants 255 86 34% / 4. Management and administration program 20 7.2 36% / 5. Use of ICT for improving quality of education 35 12.5 36% / 6. Program coordination and monitoring and evaluation 20 7.2 36% / Total Base Costs 500 / Physical contingencies 20 0 / Price contingencies 15 0 / Total Project Costs / Interest During Implementation / Front-End Fees 550 / Total Financing Required 550 179,220,000 33% / *includes DFID’s contribution of £120 million = $179,220,000 At exchange rate £1 = $1.4953 / Contributors Amount ( in USD) in millions % / World Bank (IDA) 80,000,000 14.5 / Finland 25,290,000 4.5 / DFID 179,220,000 33 / GPE 100,000,000 18 / Italy 25,290,000 4.5 / USAID 20,000,000 3.5 / Government 120,200,000 22 / Total 550,000,000 100
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / Together with the World Bank which takes overall responsibility for monitoring of financial arrangements, DFID monitor this through the quarterly Interim Financial Reports, MoE progress reports, the semi-annual programme implementation support missions, audit reports and by undertaking periodic field missions to implementing entities as part of its engagement with all levels of the education system. This mechanism has worked well during phase one and has enabled the World Bank, DFID and other donors to monitor financial performance of the project including the cash at hand and spending status of institutions to inform disbursement decisions. / GEQIP 2 is a financial aid with DFID funds flowing to the Government of Ethiopia through the MDTF arrangement. The UK’s Partnership Principles and the World Bank’s safeguards will be fully applicable to this programme. However, none of QESSP 2 resources and activities delivered by the contracted management agent or directly by DFID constitutes a financial aid. However, in case of breach of partnership principles/s we would review implications for QESSP and take appropriate action. / GEQIP follows existing government systems and mandates for general edu­cation at different levels and, to the extent possible, follows Government planning, bud­geting and implementation structures and systems, financial management, financial regulation procedures and procurement procedures. This means that Government will be responsible for managing the flow of funds to meet the costs associated with each output. The necessary funds will be deposited in designated bank accounts by the Trust Fund administrator based on agreed forecasts of cash requirements. Disbursement to the pooled fund will be based on reported spending in quarterly Interim Financial Reports (IFRs) that are received from all implementing entities and collated by MoFED. / GEQIP’s federal level implementing entities (MoE and Universities) and the Regional Bureaus of Finance and Economic Development (BoFED) will receive GEQIP funds direct from the Ministry of Finance and Economic Development (MoFED). Woreda Offices for Finance and Economic Development (WoFEDs), Regional Education Bureaus (REB) and Colleges of Teacher Education (CTEs) will receive GEQIP resources from their regional BoFEDs. WoFEDs in turn will be responsible for channeling GEQIP resources (mainly school grants) to schools. / MOFED has responsibility for coordinating GEQIP’s finances and for the consolidation of work plans, budgets, and reports of BOFEDs, ZOFEDs and WOFEDs with its own. REBs have responsibility for overseeing all other regional and sub-regional program implementation, including the consolidation of its work plans, budgets and reports from zonal and woreda offices and reviewing those from CTEs. Each region receives an annual grant to imple­ment the agreed regional GEQIP work plan according to a formula on cost estimates from federal and regional plans, and subject to variation based on regional priorities in line with federal standards and guidelines set by MOE. / Figure 4: GEQIP funds flow arrangement / IDA / DPs participating in MDTF / IDA-administered MDTF / Pooled / Designated Account at MOFED (Foreign Currency) / Government’s Regular Birr Account at MOFED which includes Federal Government’s contribution / BOFEDs / WOFEDs / MOE / Universities / REBs / CTEs / Schools / Global Partnership for Education / (IDA-administered) / Including Regions’ contribution
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / The requested £130 million to GEQIP 2 and QESSP 2 will be funded from programme resources and the £65 million expected to be spent in the first two financial years has been budgeted for in DFID Ethiopia’s operational plan. Approval has been obtained from DFID’s Finance and Corporate Performance Division that it is possible to include the £65m expected to be spent beyond the current Spending Review period (£32.5m in 2015/16 and the same in 2016/17) and that HM Treasury approval is not required for this.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / Table 11: spend forecast / Component 1:DFID’s Contribution to GEQIP 2 Multi-Donors Trust Fund / Funding Type: 108-Non budget support financial / Benefiting Country: Ethiopia / Input Sector Input Sector Code Percentage Allocation / Improve the curriculum and number of textbooks available Primary Education (MDG Education) 11220 22% / To undertake teacher training Teacher Training, Education (MDG Education) 11130 18% / To provide grants to schools to implement improvement plans Primary Education (MDG Education) 11220 46% / To improve the capacity and management of educational leaders Education Policy and Administrative Management 11110 3.5% / To develop the information and communication system to improve the quality of teaching and learning Secondary Education (MDG Education) 11320 7% / programme coordination, monitoring and evaluation Education Policy and Administrative Management 11110 3.5% / Component 2: QESSP (Quality Education Strategic Support Program) / Funding Type: 108-Non budget support financial / Benefiting Country: Ethiopia / Input Sector Input Sector Code Percentage Allocation / Research and evidence building Education Policy and Administrative Management 11110 22% / Capacity building and technical assistance Education Policy and Administrative Management 11110 68% / Management Agent fee Education Policy and Administrative Management 11110 10% / For GEQIP with the agreement of DFID Finance Operations Team, the Secretary of State approval will be sought for a single annual payment to the MDTF of £30 million in September each year except the first disbursement which is expected to be made in February 2014. A single disbursement in September is preferred to predictably provide the resources required at the beginning of the academic year and to synchronise our funding with Ethiopia’s July – June financial year. For QESSP funds will be paid to a selected Management Agent and the payment schedule will be defined based on achievement of milestones and any advance payment will be negotiated during the contracting process.
G. What is the assessment of financial risk and fraud? / Government systems / DFID’s 2012 assessment of fiduciary risk is ‘moderate’ which remains unchanged from the previous assessment in 2007. Overall, this rating reflects the view that Ethiopia has a sound Public Financial Management and Accounting system, except for weaknesses in the areas of accountability, transparency and procurement. Despite these weaknesses, the 2012 assessment concluded that “we believe that there is a reasonable confidence that DFID’s money would be used by the Government of Ethiopia for the intended programmes and projects”. DFID Ethiopia’s draft Annual Statement of Progress (April 2013) assessed the overall fiduciary risk to be stable (not improving and not worsening). / Some weaknesses do remain; most notably in the areas of audit (internal and external), the partial coverage of the IBEX system to provide computerised expenditure control and accounting, and the weak financial management capacity especially in the woredas. These weaknesses have been recognised and PBS 3 contains a local financial management component comprising: strengthening woreda-level financial management performance sub-component, support for IBEX roll-out, regional public expenditure and financial management support systems sub-component, support for external audit, and support for the Federal Parliament, Regional and Woreda Councils in their oversight roles and to strengthen the accountability framework. / The prevalence of corruption in Ethiopia, when measured against international benchmarks, is about average in Africa. The World Bank’s African Development Indicators (2011) suggests that Ethiopia is at the 44th percentile in Africa for ‘control of corruption’. Transparency International’s (TI) Corruption Perception Index for 2010 places Ethiopia 20th in the Africa rankings (close to Tanzania and Uganda) and 116th in the World rankings. / However, this ranking has been improving over the last three years. Furthermore, on this positive front, TI’s Global Corruption Barometer highlights that, in comparison to other countries in the region, Ethiopian citizens have a relatively favourable impression of their government’s anti-corruption credentials – and a concomitant high level of trust in government commitment to fight corruption. Also, according to a study that mapped corruption in eight sectors of the country (Joint Governance and Monitoring Programme, 2010), corruption in the delivery of basic services such as primary health, basic education, rural water supply and justice is lower than in similar low income countries, and mainly takes the form of petty corruption. Compared to most other countries in the region, the government stands out for its active commitment to the fight against corruption; not only in terms of having the necessary institutions are in place to accomplish its objectives, but also actual enforcement action. / The programme funds are being administered through two mechanisms: trust fund with the involvement of the World Bank and one Management/Fund Management service provider. / GEQIP2 / Given that GEQIP 2 is a continuation of phase one with similar financial and implementation arrangements, the World Bank’s core systems against the four Due Diligence pillars (governance, ability to delivery, financial stability and downstream partners) are judged to remain suited to administer the MDTF. However, in line with DFID’s recent guidance a due diligence assessment that focuses on locally specific factors will be conducted. / The FM arrangements for GEQIP 2 are anchored in the country’s regular PFM system. Regular government rules and procedures will apply for the program; and the regular government Chart of Accounts and accounting system will be used. This is particularly relevant given that there are a large number of implementing institutions and given that the program would operate throughout the country in all Regions and Woredas. / A recent diagnosis of corruption in key sectors in Ethiopia[68] concludes that perceived corruption risks in Ethiopia’s health and education sectors are lower than those typically encountered in many developing countries as well as in other sectors within the Ethiopian public administration. A range of accountability systems are in place in the sectors, which are particularly strong on the supply side (e.g. internal audit systems and vertical accountability to the various levels of the administration). / The GEQIP FM arrangements are already outlined in a FM Manual, which has been developed for GEQIP 1 and formed part of the Project Implementation Manual (PIM). Since the GEQIP FM arrangements utilize the Government’s regular Public Financial Management (PFM) system, the FM Manual outlines how the government’s PFM system would operate with respect to the GEQIP, and also documents program-specific FM aspects (such as formats of the financial reports, Terms of Reference for the audit, etc.). The manual will cover all program funds i.e., those financed by the Government and DPs. Specifically these FM arrangements will apply to the entire project – covering all project costs (including those financed by Government – federal and regional – and all partners financing GEQIP). The FM design for the project thus follows an approach of harmonization among all DPs around country PFM systems. The FM Manual will be updated to include the new chart of accounts (reflecting the new components introduced in this project), description of the new role of Channel One Projects Coordination Unit (COPCU), duties and responsibilities of accountants at all levels. / Economic pressures on the DPs, especially the bilateral agencies, may reduce their ability to deliver on their funding commitments. In the past, when DPs’ funds have been delayed, Government has stepped in to fill the funding gap on a temporary basis. Again, performance will be kept under close review as part of the compliance with the predictability principle / QESSP 2 / The financial risk of working through a service provider will be addressed through the rigorous selection and contracting process as well as the stringent accounting and audit requirements of DFID issued contracts.
H. How will expenditure be monitored, reported and accounted for? / Accounting / For GEQIP, Government’s accounting policies and procedures will be used for accounting for the project. The Ethiopian Government follows a double entry bookkeeping system and modified cash basis of accounting. This is documented in the government’s accounting manual. This has been implemented at the federal level and in all regions but not in all Woredas. / Accounting centres for program funds would include: (i) MOE; (ii) MOFED; (iii) Universities; (iv) BOFEDs; (v) REBs; (vi) CTEs; and (vii) WOFEDs. All these institutions would maintain accounting books and records, and prepare financial reports in line with the government’s accounting system. / The computerized Integrated Budget and Expenditure (IBEX) accounting system are now operational at the federal level and in all regions. All regions are currently using this system to capture their transactions for GEQIP 1. It has been noted that due to electric failures, breakdown of computers and lack of training, most woredas are not using the system to capture the transactions for the project hence most use manual accounting system. The government is now trying to pilot and roll out the new IFMIS which will enable regions and woredas to capture transactions of projects with more detail than the IBEX system. The current status of the pilot program and the government schedule for rolling out the system will be discussed with MoFED during the appraisal mission. / IFMIS reports will include information such as trial balance; expenditures by line items (based on the GoE’s functional classification system), with a break-down by economic classification for each line item; details of cash and bank balances, and break-down of receivables and payables. / MoFED is responsible for preparing the IFR drawing on information collected from the various agencies on receipts, expenditures and balances. The MoE provides information to MoFED on budgets for the quarter (drawing information from the annual work plan and budget). Subsequently, MoFED will submit consolidated quarterly Interim (unaudited) Financial Reports (IFRs) to Development Partners within 75 days of the end of each fiscal quarter. The IFRs include introductory narrative report of the overall financial performance of the project, comparisons with budgets, financial information for the quarter, and cumulatively for the year and the project. The IFRs also include: (i) sources and uses of funds; (ii) break-down of project expenditures by sub-components, aggregated to components; and (iii) forecast for the next 2 quarters. / Internal Controls / Internal control comprises the whole system of control, financial or otherwise, established by management in order to (i) carry out the project activities in an orderly and efficient manner; (ii) ensure adherence to policies and procedures; (iii) ensure maintenance of complete and accurate accounting records; and (iv) safeguard the assets of the project. Regular government systems and procedures would be followed, including those relating to authorization, recording and custody controls. The FM manual also outlines the necessary internal control procedures for the project. / As in GEQIP 1 it is intended that internal audit will be carried out by the internal audit departments of the respective entities (MOE, Universities, REBs, and CTEs). In addition, MOFED, BOFEDs and WOFEDs have internal audit departments that are expected to perform internal audit, including an assessment of whether the budget utilization is in line with the intended purposes. Furthermore there are inspection department at the MOFED and BOFEDs with a role of ensuring quality of internal audits at the Ministries at Federal level and Sector bureaus at region level, following up on the audit recommendations noted by audit reports, providing training and improving manuals, etc. As noted earlier, the PFM analytic work notes that internal audit is weak, and there is need for significant improvements. This is being addressed through the Expenditure Management and Control sub-program EMCP of the government’s civil service reform program (CSRP) nevertheless the weaknesses noted in internal audit necessitate increased focus on external systems audit in GEQIP 2. / External auditing / The external audit is carried out by the Office of Federal Auditor General (OFAG). Annual audited financial statements and audit report (including Management Letter) of the project are submitted to partners within 6 months of the end of the fiscal year. The annual financial statements are prepared in accordance with the International Financing Reporting Standards (IFRSs) and include the sources and uses of funds on the project (containing the same information as the similar statement in the IFRs), with supporting schedules and other information. The formats of the annual financial statements are included in the Financial Management Manual. The draft annual financial statements are prepared within 3 months of the end of fiscal year and provided to the auditors to enable them to carry out and complete their audit on time. So far three GEQIP 1 external audit reports have been received and they are all unqualified. / A requirement to audit up to 10% of schools annually was agreed during the original appraisal of GEQIP. The audit report is shared with all development partners. The arrangements for the school grant audit are being reviewed as part of GEQIP 2 design and it is likely that the sample size will be reduced to 5% (1500 schools) this is judged to be enough a sample size. / Assets purchased / Assets purchased under this programme cannot be attributed to DFID, nor can DFID track or monitor them given that this is a joint programme and our funds will be pooled with other DPs and GoE. Therefore, the assets will be owned, monitored and controlled by the various GoE implementing entities involved in this programme. QESSP 2 assets purchased by the management agent will be tracked and monitored.
I. Are there any accounting considerations arising from the project? / There are no accounting considerations arising from the project.
[68] World Bank (November 2010) Ethiopia country Procurement Assessment Report. World Bank, Addis Ababa, Ethiopia World Bank (2012) Diagnosing Corruption in Ethiopia: Perceptions, Realities and the Way Forward for Key Sectors

Management Case

A. What are the Management Arrangements for implementing the intervention? / GEQIP 2 and QESSP 2 will be funded and managed through the following arrangements ensuring GoE’s ownership, donor harmonisation and overall programme coordination and sector coherence. / A1. GEQIP 2 (see A2. For QESSP) / Joint funding / GEQIP 2 will operate in a pooled fund arrangement with funds channeled through a World Bank administered Multi-Donor Trust Fund (MDTF). The pooled fund will ensure the application of World Bank safeguards, donor and government coordination, promoting mechanisms of mutual accountability, and government’s ownership of the develop­ment processes. The support is aligned with the priorities identified in ESDP IV (2010/11 – 2014/15). As in phase I GEQIP 2 will follow existing government systems and mandates for general edu­cation at different levels and, to the extent possible, follows Government planning, bud­geting and implementation structures and systems, financial management, financial regulation procedures and procurement procedures. / Channeling funds through the MDTF and having the World Bank in financial and procurement oversight role is judged to provide better fiduciary reassurance and lower transaction costs than the DFID office handling this itself. The use of an MDTF will also help to promote aid effectiveness in the education sector by increasing the harmonisation of donors with respect to their implementation support. When developing the MDTF Agreement, DFID will be clear that it will be fully involved in the technical oversight of the project. Other donors may wish to consider an addendum to the Grant Agreement to this effect. / Division of roles / GEQIP is implemented at three levels of GoE – federal, regional and woreda levels – corresponding to the roles and responsibilities for the management and financing of general education. Management of GEQIP is fully integrated into GoE’s structures as figure 5 below shows. Detailed description of roles and responsibilities can be seen from the World Bank Project Appraisal document. / At the federal level - in addition to overall coordination of GEQIP, the MoE is responsible for certain assigned activities including some procurement packages and programme components that target the Ministry as a beneficiary. The Public Procurement and Property Disposal Services (PPPDS) of the Ministry of Finance and Economic Devel­opment (MOFED) will handle some large procurement outsourced to it by the MoE. Universities at the federal level are responsive for some aspects of the Teacher Development component. / Pooled funding partners do not have a direct role in managing the project. However, they are in principle invited to observe meetings of the Federal GEQIP Co-ordination Committee. They are also involved in reviewing and approving the annual plans, including the resource allocation, and monitoring the progress of the project through review of the Interim Financial Reports (IFRs), the semi-annual project reports and Joint Implementation Support Missions. A MoU governs how the partners co-ordinate themselves in order to engage with GoE with the lowest possible transaction costs. / The Education Technical Working Group (TWG), a sub group of the Development Assistance Group (DAG), is the overall structure for harmonising and aligning donor relations with the GoE in the sector. The TWG has a co-coordinating role with respect to the extent to which GEQIP complements other bilateral and multilateral projects in the sector. / The Federal GEQIP Coordination Committee includes representatives of all MoE Directorates responsible for GEQIP Component and Subcomponent Coordination, REBs, MoFED and civil society. It is intended to: (i) provide overall strategic guidance for the GEQIP implementation; (ii) oversee the equitable distribution of the budget to regions, institutions and components; (iii) ensure that agreed performance targets and timelines for activities under the different components are met; and (iv) ensure effective programme implementation and proactively address critical issues that could hinder implementation. However, in practice oversight of the project is the responsibility of the EMIS, Planning and Resource Mobilisation Directorate. Ultimate responsibility for GEQIP implementation rests with the Minister of Education and he reports to Parliament. / At the regional levels - Regional Education Bureaus (REBs) are responsible for the implementation of activities based on their GEQIP plans that are consistent on the one hand, with national standards and on the other, with regional priorities. They are responsible for overseeing the plans of the Colleges of Teacher Education (CTE), including ensuring that numbers of primary teachers trained is in line with regional requirements. They also oversee the implementation of the school improvement programme in the woredas, and are responsible for decentralized textbook development and distribution. Each region will receive a grant according to a defined formula to implement the agreed regional GEQIP plan. Colleges of Teacher Education (CTEs) at the regional level are responsible for teacher development activities in close coordination with the MoE and REBs, respectively. / At the Woreda levels- Woredas receive no additional financing from the project, but funding for schools and ABE centers is channeled through them. They have oversight of the schools grant programme, including communicating to the Woreda Office of Finance and Economic Development (WoFED) the lists of schools and their enrolment. They are also responsible for supervision, although absence of transport often hampers them in fulfilling this role. Woredas are accountable to the regional governments for their performance. / Figure 5: GEQIP Implementation Arrangements / Beneficiary Representation in GEQIP Governance. / The main mechanism for civil society involvement in GEQIP 2 is through the school improvement committees which develop plans and monitor how school level funds are spent / These structures will be strengthened as part of GEQIP 2. / The GEQIP Co-ordination Committee chaired by the State Minister for General Education meets quarterly. Regional Education Bureau Heads are invited to these meetings. Civil Society organisations and DPs can be invited to observe this meeting. In addition, the Annual Education Conference includes participants from regional bureaus, universities, teacher training colleges, woredas, parent teacher associations, NGOs, and Associations such as those representing teachers and the private sector. This meeting is chaired by the Minister of Education. / A2. QESSP 2 / QESSP 2 which includes complementary capacity building and technical assistance and pooled fund (will be delivered by a contracted management agent. The management agent will be overseen by DFID in coordination with other contributing donors, and the Ministry of Education’s Planning and Resource Mobilisation Directorate which is also responsible for the overall coordination and implementation of GEQIP 2. This arrangement will ensure coordination and coherence of activities in the two programmes. / The Terms of Reference for the management agency has been agreed with the education TWG but DFID has been delegated to lead on the direct procurement of this service and contract management in coordination with the education TWG that is co-chaired by the Planning and Resource Mobilisation Directorate of the MoE. / Figure 6: QESSP Implementation Arrangements / Coordination ( ) / Reporting ( ) / Other donor’s contribution will be directed to the management agent to all or some aspects of QESSP 2. DFID intends to transfer all QESSP resources to the agent but it may retain some funds internally or negotiate for some of its funds to be accounted for separately from other donor’s contribution. This would allow DFID to respond to sector demands and fund specific activities without having to wait for other donor’s consent. / As per the ToR it is envisaged that the Management Agent would mobilise and manage capacity building and technical assistance to the MoE and administer the education pooled fund. By contract, the agent will report to DFID but it will have joint responsibility to the Ministry of Education and the TWG on all technical matters. We anticipate this will work as follows: / A Technical expert will be embedded in the MoE to work closely with the Planning Department in the review of proposals, identification of suitable experts to carry out assignments, and monitoring and evaluation of the work of consultants. The TA would also provide advice to the Planning Directorate on other issues as requested and to act as a focal person for the Education TWG. / The management agent will need to have access to a network of expertise in the education sector both nationally and internationally who can be mobilised quickly to support requests / The co-chairs of the Education TWG will take the lead on identifying proposals to be taken forward with inputs from education pooled fund donors as necessary / The agent will need to respond quickly and flexibly to requests for support approved by the TWG co-chairs and include a range of options for financing, including direct procurement and indirect procurement through third parties. / A3. DFID Management / Within DFID this programme will be overseen by an Education Adviser supported by a Senior Team Leader, a Deputy Programme Manager and a Programme Officer. The education adviser will continue to be part of the joint governance structures of the GEQIP (illustrated above) and the Education TWG. He/she will be supported where necessary by the Head of DFID Ethiopia. The Education Adviser will call on other Advisers from the team as required e.g. for issues relating to public financial management, impacting on women and girls, results monitoring etc. / Financial reports, compliance and administrative functions will be managed by the DFID programme officer in DFID Ethiopia’s Human Development Team. / State Minister / Minister / (MOE) / GEQIP Coordination, EMIS / (Planning and Resource Mobilisation Directorate) / REGIONAL PLANNING DEPT (REB) / MOFED / BOFEDs / Universities / GEQIP / Coordination / Committee / Schools / CTEs / WoFEDs / Education Technical Working Group / Donors’ contribution to the education pooled fund / DFID / QESSP 2 Management Agent: / - Capacity building and technical assistance / - Administering the education pooled fund / Planning and Resource Mobilisation Directorate
B. What are the risks and how these will be managed? / Overall project risks were rated as high at GEQIP 1 appraisal, mainly because of the complexity of the programme and generally weak capacity of multiple implementing partners. However given the experience from phase 1 overall risk is judged to have reduced to medium for phase 2. The procurement and fiduciary risks are in line with the World Bank’s categorisation. / Table 12: Risk Matrix / Risk Mitigation Probability Impact / Implementation/operational risks / 1. Reduction in projected growth of public education budget due to macroeconomic instability, and/or slowing down of economic growth Monitor closely GoE efforts to stabilise macro-economy. / DFID is scaling up its dialogue on and support for wealth creation and economic reform. Medium High / 2. Weak monitoring reporting and implementation capacity, especially at lower levels of government. Monitoring and reporting mechanisms have been integrated into existing GoE systems as much as possible. Capacity of relevant GoE staff and consultants to carry out M&E and implementation is being strengthened through training and mentoring. Medium Medium / 3. Textbooks delayed Most text books procurement commissioned in phase 1 will be finalized by the beginning of phase 2. GEQIP 1 has tried to build MoE’s capacity through hiring a consultant to assist in procuring textbooks in a timely fashion using World Bank procurement procedures and guidelines. Medium High / 4. School grants may not have the expected effects on the quality of schooling Per pupil school grant amount has been revised upwards to 30 birr for primary and 45 birr for secondary. A Rapid Assessment conducted in 2009 indicated that grants were generally being received by schools and plans were in place. A larger school grant evaluation conducted in 2011/12 confirmed that 98% of schools have received the grants and 95% of the funds are used to implement school improvement plan priorities. Medium High / 5. Weak procurement capacity at all levels of GoE and limited understanding of World Bank procurement procedures slows down implementation progress. Weak MoE procurement capacity will be mitigated through technical assistance, and procurement planning. Medium High / 6. Low levels of community participation/social accountability in education. The School Improvement component of GEQIP will continue to strengthen and engage Parent and Teacher Association (PTAs) as school and community level accountability structures. PBS III designed to scale up the Social Accountability and citizen engagement pilot implemented during PBS II. Low Medium / Political risks / 7. GoE does not to allocate sufficient funds to non-salary, quality related recurrent expenditure in regions Despite increasing GoE resources, decentralized quality expenditure is likely to remain constrained over the coming two years. We will continue to monitor through the review process. Medium Medium / 8. Use of GEQIP funds for political purposes e.g. promotion for party members, use of schools for political rallies To mitigate against the risk of political distortion GEQIP has a number of checks and balances. Allocation to implementing entities will be on the basis of a transparent planning process including a costed work plan. There are clear guidelines for use of funds at the different levels, for example, school grants will go to all schools per every pupil and to fund school improvement priorities identified by schools and their parent teacher associations. As in phase 1, guidelines governing the use and accounting of funds at the school level will be followed. Monitoring arrangements include arrangements for semi-annual enhanced joint supervision missions, tracking allocation and use of programme funds through the quarterly interim financial reports, annual audit reports and independent evaluation of the programme. These should reduce but not eliminate this risk UK will continue ongoing constructive and high level dialogue. Low Medium / 9. Extent to which results are being achieved may be over-stated by GoE in its drive to show progress GEQIP includes an element of capacity building to strengthen the GoE’s regular education management information system. Evaluations and joint reviews will be able to triangulate results Low Medium / 10. Development partners, including those funding through the MDTF, fail to align and harmonise in supporting GEQIP resulting in disrupted funding flows and changes in the rules of the game Strong coordination of Development Partners through GoE co-chairmanship of the education TWG, coupled with a MoU for GEQIP partners which sets out the rules of the game. Low Medium / 11. Partnership Principles significantly breached requiring change of approach to delivering aid. Close monitoring, high level dialogue and, where appropriate and useful, programming linked to Partnership Principles where we have the greatest concerns Medium Medium / 12. Reputational risk to DFID arising from allegations that national programmes being used to support resettlement policies/practices by the GoE which are not in line with international good practice. High-Level Dialogue with GoE to press for implementation of resettlement according to international good practice / Implementation of Grievance Response Mechanism (through PBS) / Enhanced social assessment, with social safeguards established and monitored / Joint Technical Reviews include specific provision for “beneficiary” feedback including in areas of resettlement, report any concerns and advise on actions required Medium Medium / 13. Reputational and other risks from failing to take account of needs of marginalised and vulnerable Application of World Bank safeguard specifically completing an enhanced social assessment (in line with World Bank’s OP 4.10) identifies strategies for mitigating risk and adverse impacts for maringalised / Component specific strategies and outputs adapted to the needs of vulnerable and marginalised groups particularly pastoralist communities and special needs children. Low Medium / Fiduciary risks / 14. Weaknesses in the country’s PFM system notably capacity gaps at the local levels undermine implementation and reporting Efforts under way to strengthen sector and national PFM. UK will continue ongoing constructive and high level dialogue. / Action plans to address GEQIP-specific and broader FM weaknesses in sector institutions have been agreed. Timeliness of IFRs continues to be a problem and reported spending is low, especially in universities Medium High. / 15. Evidence of significant instances of corruption found Annual procurement audits, plus annual financial audit will provide disincentive to corrupt behavior and early identification of corrupt activities. The World Bank conducted a corruption diagnostic in the sector early in 2009 which assessed risks as low Low Medium / Climate and Environment risk / 16. Electronic waste The environmental screening that was carried out by the World Bank as part of GEQIP Phase 1 rated the project as low risk with respect to impact on the environment and there is no reason to expect any major changes to this assessment in Phase 2. GEQIP Phase 2 does not include any major construction and the only major new component is the provision of ICT infrastructure and effort will be made to use appropriate technology reducing electronic waste. Low Low
C. What conditions apply (for financial aid only)? / Ahead of disbursements, DFID will assess commitment to the UK’s four partnership principles (necessary for the continuation of financial aid). The four partnership principles are (as set out in HMG’s Conditionality Policy and Guidance and to be agreed in our bilateral MoU between HMG and GoE on this programme): / Commitment to poverty reduction and the millennium development goals / respecting human rights and other international obligations and / improving public financial management, promoting good governance and transparency and fighting corruption; and / strengthening domestic accountability / Every year taking a balanced view across all four Partnership Principles, we will assess whether the Government remains committed to the underlying principles of our engagement. The outcome of the review will be approved by the Secretary of State and GoE’s continued commitment to the Partnership Principles will be necessary for DFID’s disbursement to the World Bank administered multi donor trust fund (MDTF). In case of breach of partnership principles DFID may delay, reduce or suspend its funding commitment. / At programme level, through the MDTF administrative agreement the World Bank are fully responsible for fiduciary oversight of the project and to closely monitor GoE’s compliance with agreed implementation and financial management arrangements. All arrangements are jointly developed and agreed between GoE and DFID through the project design and appraisal process and will be published as part of our Business Case and the Bank’s Project Appraisal Document (PAD). / Disbursement from the MDTF to GoE’s designated account is based on satisfactory assessment of compliance and progress by the World Bank and DFID through review of quarterly Interim Financial Reports (IFRs), semi-annual enhanced supervision missions and annual audits. Non-compliance will be dealt with in accordance with the Bank’s financing (covering IDA credits) and grant (covering MDTF) agreement with the Government of Ethiopia. / DFID’s Business case and bilateral MoU with the GoE, the Bank’s PAD, financing and grant agreement with GoE, and the aid memoires of the enhanced supervision missions will all be published.
D. How will progress and results be monitored, measured and evaluated? / Monitoring strategy / The results framework has been improved from GEQIP 1 building on a strengthened theory of change. In particular the outcome is now described as “improved learning conditions and institutional capacity” a more explicit measure than “education quality” as defined in the previous phase. In GEQIP Phase 1, proxy indicators of school level outcomes were included in the results logframe. These were: a) pupil to textbook ratio and b) percentage of teachers with appropriate qualifications. The use of these indicators at outcome level was heavily criticised by ICAI in its East Africa report43. In Phase 2, therefore, DFID has brokered agreement with government and its partners to focus on indicators that reflect more closely the changes that as currently understood are needed at school level to improve learning outcomes and which also reflect the outputs described in the previous section. These indicators are as follows: / Textbook utilisation (recognising that it is not textbook availability that matters but how books are used) / Degree to which teachers employ student centred approaches (in order to measure the impact of training and policy on teacher behaviour) / % of PTA involved in the management of school grants (as a measure of capacity building at school level) / % of pilot secondary schools using ICT to promote learning / The baseline for the results framework will be populated through a combination of data from the Education Management Information System (EMIS), the results of the National Learning Assessment, data from the Comprehensive Evaluation, and information from the 2013 GEQIP Phase 1 Annual Report. Each of these is discussed in more detail below. / At impact level: Completion rate as a proxy indicator will be tracked annually through the government’s regular monitoring system (EMIS). The sample based National Learning Assessment (NLA) that was first conducted in 2000 and repeated in 2003, 2007 and 2011 will be used to track learning achievement. The NLA tests children in grades 4 and 8 in core subjects. The NLA has also been extended to grades 10 and 12, so baseline data are now available to track progress at this level too. Support is being provided through GEQIP to maximise the comparability of results over time. / At outcome level: EMIS data is not currently generating data on the outcomes that have been proposed for GEQIP 2. The results framework will therefore draw on the results from three additional planned monitoring and evaluation studies to track changes in these outcomes over the period of implementation (baselines are available for the first three from the school grants evaluation conducted in 2011 and the comprehensive evaluation exit survey). / School grants study (bi-annual) / Two school grant evaluations were carried out in 2009 and 2011 during GEQIP 1. These were important in establishing that grants were reaching schools and that a system was in place for planning, utilising and reporting on these grants. However the evaluation did not shed much light on the extent to which grants are impacting on quality improvement. There will be two further evaluations in phase 2 (in 2014 and in 2016). These evaluations will seek to not only provide information on how schools use the grants, but also the extent to which the grants are contributing to quality improvement. The focus may therefore include attention to a broader range of outputs, including textbook utilisation and teachers’ use of student centered methods. / As explained in the strategic case, school grants are meant to finance improvement plans developed around the four domains of Ethiopia’s School Improvement Programme (teaching and learning, community participation, school environment and leadership and management). Previous evaluations have established the reach (to 98% of the schools) and use of grants (95% for SIP priorities). School are free to use grants to fund a range of teaching and learning inputs including buying reference materials and conducting school based CPD for teachers. The scope of the previous evaluations was limited in that they did not assess the impact of school grants on teaching and learning outcomes at school level which for example can include better utilisation of textbooks and application of student centred methods. The planned bi-annual school grant evaluations are meant to address this limitation and attempt to generate evidence in addition to what the independent evaluation will do. / Teacher Development programme / An evaluation of the impact of TDP was planned in the first phase of GEQIP, but it was agreed at the Mid Term Review of Phase 1 that it was too early to assess the impact of the programme on teaching and learning since pre-service courses have a duration of three years. The evaluation was therefore moved to the first year of Phase 2 in order to better test the effects of the programme and to maximise the impact of any recommendations for adjustments. The evaluation will focus on the extent to which pre-service and in-service training has changed teacher classroom behaviour in line with the government’s policy of increasing the use of student centered teaching methods. This is a programme evaluation so will focus on lessons learned, and should also generate data on teachers’ classroom behaviour. / ICT / The use of ICT to improve learning will be piloted in the first two years of GEQIP. The evaluation will test the value added that ICT can have with respect to improvement in learning conditions and the learning experience, for students in the pilot secondary schools. / These three additional monitoring and evaluation studies are already budgeted within the main GEQIP programme and will be procured and managed by the Ministry of Education with technical input from DFID and development partners. / At output level: The annual MoE GEQIP progress report and the Education Management Information System (EMIS) abstract provide data to monitor millstones. In addition, the MoE produces six monthly GEQIP progress reports based on information received from all implementing entities. These reports are the basis for monitoring of progress on key outputs and are aligned with the quarterly financial reports in order to get a picture of both activities and financing. In Phase 1, there were problems with the accuracy and timeliness of the data in the semi-annual report. Development Partners are working closely with the Ministry to ensure that sufficient capacity and systems are in place to collect relevant data and present it in advance of the joint review missions. / The six monthly GEQIP reports (due in March and September each year) are discussed in the GEQIP review missions to which all key stakeholders (The World Bank, DPs, MoE, MoFED and all other federal, regional and local implementing entities) are invited. These missions focus on reviewing the implementation progress of the programme. In consultation with partners, the World Bank may also commission independent consultants to undertake critical reviews of progress and to give recommendations for consideration at the joint review missions. DFID plans to use QESSP resources to strengthen this aspect of programme monitoring. If necessary, additional resources to provide an independent perspective on the outcomes and outputs of GEQIP at school level will be provided through QESSP. / As is indicated in the strategic case, the MoE has been working hard to improve the timeliness and availability of EMIS data. Data quality is considered adequate for reporting purposes by most partners and for the purposes of this case can be rated as medium. The education sector data quality system assessment carried out under PBS2 recognised a number of key strengths but also recommended some areas for further improvement. Through the Managing For Results component of the new phase of PBS, DFID is continuing to invest in EMIS strengthening particularly at the sub-national level. A follow-up data quality assessment across the sector is planned during 2013. GEQIP also includes a sub-component under the management and administration component aimed at strengthening the existing EMIS capacity to collect, analyse and report data accurately and in a timely manner. / DFID is committed to support the tracking of data disaggregated by gender. In addition, we will seek to use QESSP 2 to strengthen the monitoring of the sector and provide more information on the progress of children by sex, socio-economic group, ethnicity, and disability. / DFID will also ensure a rigorous approach to its own Annual Review process through internal and external peer review. These reviews will include a focus on value for money and the effectiveness of government procurement systems in delivering key outputs of the programme. / Evaluation strategy / Purpose / DFID Ethiopia’s Evaluation Strategy identifies 5 key criteria[21] for identifying programmes as candidates for evaluation. GEQIP is accorded priority for evaluation given the overall volume of investment and the variable evidence strength around the theory of change. We are working with partners and MoE to establish an overarching evaluation framework for GEQIP 2. This will focus on addressing key gaps in the overall evidence base to further enhance our understanding of school effectiveness in Ethiopia and to feed into the design of future education quality reforms. The purpose of the evaluation will be to link indicators of school effectiveness (the outputs) with measures of learning (the impact) in order to understand whether GEQIP outputs are impacting on learning for all students. / A comprehensive evaluation of GEQIP 1 was completed earlier this year drawing principally from an analysis of student and teacher perceptions of changes in education quality indicators at school level. Delays in procurement meant that the baseline assessment was not completed until the 2nd year of the programme so measureable changes at output level were difficult to detect. The major limitation in the design of this evaluation was that it was not able to link indicators of school effectiveness with measures of learning and unable to demonstrate which mix of inputs has the greatest impact on learning outcomes. / Evaluation questions / The evaluation design of GEQIP 2 should consider the feasibility of addressing this limitation and the gap in evidence. An evaluability study will be conducted at the initial stage of the evaluation design to better define the scope of evaluation and develop specific evaluation questions based on the gap in evidence and the assertions of the theory of change. At this stage the main set of questions that the evaluation is expected to answer include: / What is the impact of GEQIP on learning outcomes? / To what extent have the outputs of GEQIP contributed to more effective schools? / Did the outputs in combination result in improved learning for all pupils? / Where possible, which output and combination of outputs has the greatest impact on improving learning outcomes? / What were the processes that led to improvement in learning outcomes? / To what extent has QESSP created an enabling environment for improved monitoring, evaluation and evidence generation in the sector? / What is the intended and unintended impact of GEQIP particularly on marginalized and vulnerable groups? / Did the programme achieve overall value for money and how does this differ between components of the programme? / Methodology and timeframe / The overall methodology for the evaluation will draw heavily from a synthesis of existing and planned sources (there is unlikely to be political appetite for an additional measure of learning outcomes). Given the national coverage of the project the scope for any experimental design is limited although it may be possible for the evaluation to look at regional or school level data for some factors to draw comparisons between any potential differences in delivery and use of key GEQIP outputs. The service provider is expected to propose a detailed methodology that will meet the purpose of the evaluation and answer the evaluation questions. / The overall timeframe for the evaluation will need to be agreed taking into account the reasonable period it takes to capture change and conduct a meaningful analysis and also the existing NLA testing cycle (currently scheduled for 2015 and 2019 in grades 4 and 8). It will therefore extend to the end of the programme and potentially beyond in order to maximize impact measurement. Given this at least one comprehensive interim evaluation report is likely, probably linked to the NLA to be conducted in 2015. / Management of evaluation / Whether the proposed evaluation should be commissioned by the Ministry of Education and funded through the multi-donor GEQIP resources or separately funded through DFID’s QESSP 2 is currently under discussion. DFID proposes to use the QESSP component to support independent evaluation of GEQIP in addition to any specific M&E activities to be undertaken through the main programme. In either case the terms of reference for this work will be agreed in consultation with all GEQIP stakeholders including technical input from DFID evaluation colleagues. Suitable evaluators will be identified through a competitive process. As part of the governance of the evaluation a reference group will be established including representatives from outside DFID Ethiopia to quality assure the design and outputs of the evaluation. / The use of the QESSP instrument provides the opportunity to use DFID procurement systems to contract the evaluation including the possibility of selection of providers from the Global Evaluation Framework Agreement. We will consult with partners to ensure the most appropriate approach to contracting to ensure a competitive process with a high calibre of applications. We anticipate that the total cost of the evaluation will likely be between £1.5 million and £2 million. This figure is only indicative and will be reconsidered in consultation with GEQIP donors and the Ministry of Education once the precise scope of the evaluation is defined. / As part of the communications sub-component of GEQIP 2 and beyond the project period lessons and findings will be disseminated to local and international audiences. The research and evidence component of QESSP in particular will work to strengthen Ministry of Education’s capacity in this area. / Other sources of data / DFID, through its investment in PBS is also supporting a facility survey to track key measures of service quality. A national survey of primary schools is planned in 2013 and 2015. A full independent evaluation of the entire PBS programme will also contribute to an understanding of how access to and quality of basic services including education has improved over the period 2013-2017 and the extent to which this can be attributed to a range of funding instruments. / DFID is also investing in independent evaluation of its pilot education Results Based Aid programme and this should also yield a range of complementary evidence over the next few years.
Log frame / The log frame (quest ref: 3963181) is linked to the overarching results frame work of the programme which will be refined in an upcoming final donor-government appraisal mission. It will therefore be subject to further revision.
[21] Strategic importance, size, innovation, coherence and risk

REFERENCES