Type of Review: Annual Review

Project Title: Building Empowerment and Accountability in Malawi (BEAM) programme

Date started:	30/12/2010
Date review undertaken:	April 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The Building Empowerment and Accountability in Malawi (BEAM) programme was launched under a Programme Memorandum in December 2010. The expected impact of the programme is more accountable, responsive and inclusive forms of governance in Malawi, and progress on off-track MDGs. The overall approach is to support citizen and community based projects that promote better information, monitoring and influencing of Government policies and programmes (“demand-side”), as well as supporting selected Government or quasi-Government institutions and initiatives to improve service-delivery and increase transparency and accountability (“supply-side”). In addition, BEAM hoped to support work to bridge this somewhat artificial divide between demand and supply and encourage more collaborative forms of engagement between an empowered citizenry and an increasingly accountable state to identify problems in service delivery and governance and implement solutions together, at national and local levels. / BEAM is a portfolio programme and some components were in-design at its approval stage; others were short extensions to existing projects; and other elements were still to be fully defined. The political context over the course of the next 2 years was increasingly restrictive and unpredictable and the expected final components of BEAM were not all fully realised. Instead BEAM was forced to flexibly adapt to changing circumstances while remaining committed to achieving the overall impact of the programme. / For these reasons this Annual Review has the difficult task of reviewing progress and achievements of BEAM components against a LogFrame that did not keep up with changing priorities and the needs of the overall programme, and where targets were not set due to an uncertain context. A new LogFrame is in design and will be completed after this review. The review itself will use a combination of the existing LogFrame and more project-specific monitoring frameworks to assess performance. The review will also cover the first 2 years of the programme as the first 12 months were largely taken up with design work and full implementation was only judged to have started in late 2011 and therefore no Annual review was required. / The BEAM components covered by this Annual Review have all had their own separate reviews undertaken by members of the Governance and Security Team and this AR will be based upon these reviews. The components are: / Component Description Contributing to output Operational dates / Tilitonse Appraisal and design support and financial contributions to a multi-donor Civil Society Governance Fund (Tilitonse) and an independent impact evaluation agent, with the fund due to run from 2012 until 2016. 1,2 and 3 23/02/2011 – 31/03/2015 / Kalondolondo A new 4-year Accountable Grant to a Community-Based Monitoring programme to allow a scale-up of an approach first piloted under the now closed Performance, Evidence and Accountability (PEA) programme. The project was renamed Kalondolondo for this second phase. 1 and 3 01/09/2011 – 30/08/2014 / Story Workshop AG 12 month grant to Story Workshop to provide bridging funding to a valuable CSO partner and allow continuation of the Zimachitika project aimed at empowering civil society to participate in local governance. 1 and 3 10/11/2010 – 31/10/2011 / Malawi Economic Justice Network (MEJN) AG 12 month grant to MEJN to provide bridging funding to a valuable CSO partner and allow implementation of a project to promote budget transparency, budget literacy and monitoring by citizens. 2 01/11/2010 – 31/10/2011 / Transparency International (TI) Journalist Training Short training of journalists on investigative reporting to help raise issues around anti-corruption. 2 / National Integrity System (NIS) assessment project Support to MEJN, African Institute for Corporate Citizenship (AICC) and TI to engage government and others to assess strengths and weaknesses in the national integrity system and develop an anti-corruption movement. 2 10/05/2011 – 01/10/2013 / Good Governance Fund (GGF) The final 12 months of the GGF, comprising 2 contracts with Capital Radio and Zodiak Radio and 2 accountable grants with Malawi Union for the Blind and Centre for Human Rights Education and Assistance (CHREA) 4 18/06/2010 – 31/03/2013 / NDI Civic and Voter Education 12 month support to the National Democratic Institute of International Affairs (NDI) to provide sub-granting and technical support to civil society to undertake civic and voter education for the 2011 local election. The local elections were later cancelled and the programme adapted to focus on local level civic education. A separate grant to a UNDP Elections Trust Fund was also cancelled. 4 18/06/2010 – 17/06/2011 / Anti-Corruption Bureau (ACB) institutional support Bridging support to ACB between January and June 2012 to enable final agreement on a new long-term support to be concluded: a process that was interrupted by death of the President and sacking of the Director of the ACB. 5 01/01/2012 – 31/12/2015 / National Audit Office Technical Support Technical support to the NAO through the provision of a technical advisor on planning and financial management. 5 01/07/2011 – 30/06/2012 / PFM Reform MDTF Contribution to a World Bank-managed Multi-Donor Trust Fund on PFM reform to back the government’s PFM reform plan that began in January 2012 and is scheduled to run until 2016. 5 01/07/2011 – 30/06/2015

What are the expected results?
The expected impact of BEAM is: / More accountable and responsive and inclusive governance in Malawi able to support progress on off-track MDGs / The expected outcome is: / To empower citizens to hold the Malawi state to account and improve the delivery of basic services, / The outputs are: / Civil society enables citizens to hold service providers to account for service delivery performance / Civil society engagement and action to improve government transparency, public accountability and responsiveness / Excluded and Marginalised groups better able to access services and exercise their rights / Electoral processes able to deliver free and credible local elections in 2011 with increased public participation / Key Malawian public oversight bodies and Government-led initiatives step-up actions to promote political and economic accountability and combat corruption / Following this review, changes to the outcome and outputs, and a new logframe and theory of change will be submitted for head of office approval.

What is the context in which UK support is provided?
As noted above, the context for this intervention has radically changed. / Initially the context moved from a situation of stagnant governance, with concerns about a possible future slide. This moved into one where governance declined more sharply and Government actions restricted both the ability of citizens and civil society to exercise rights and freedoms, and the independence of previously respected state and quasi-state Accountability Institutions to operate effectively. This context represented a serious challenge to the ability of the programme to implement the components originally envisaged and to achieve the results at the level it had anticipated. / This context meant that a number of components had to be abandoned (for example support to the cancelled Local Government Elections in 2011); others faced challenges in achieving implementation (e.g the PFM trust Fund); and many had to move slowly and tread carefully due to heightened political sensitivities about donor support to civil society (e.g the Tilitonse civil society fund). Overall this context meant that BEAM underwent major changes to be able to work towards its objectives, but perhaps played an even more vital role at a time of great uncertainty and challenge to fundamental freedoms. / However, the context changed again in April 2012 following the sudden death of the President and the swearing in of his estranged Vice-President Joyce Banda. President Banda moved quickly to dismiss officials who had been implicated in the Government crack-down or on corrupt dealings and to roll-back some of the repressive legislative and political changes that the previous administration had implemented. Increased state tolerance for civil society and more freedom for the media and citizens to speak out rapidly returned. The new context has been relatively stable since April 2012. However, the initial months of the new Presidency saw a number of positions at the top of Accountability Institutions remain unfilled for a number of months. The NAO had no Auditor-General for a large period of time- a requirement for our support to the NAO through the PFM MDTF- and the Anti-Corruption Bureau went 6 months without a Director, again preventing us from agreeing a new programme of support, and still has no deputy-Director. This slowed the implementation of some projects down, allowed others to speed-up and has led to a re-thinking of others. / Now we have a clear understanding of what BEAM can achieve to contribute towards the impact it is hoping for and have begun constructing a clearer Theory of Change and LogFrame (draft attached at annex B) that fit with the new environment and will demonstrate how the adjustments we have made to BEAM mean it is better equipped to achieve results going forward. However, the flexibility that has been so valuable in allowing BEAM to remain relevant will be maintained.

## Section A: Detailed Output Scoring

Output 1: Civil society enables citizens to hold service providers to account for service delivery performance
Output 1 score and performance description: A+. / The output indicators were intended to measure an increased reach of DFID-funded projects on helping communities hold service delivery providers to account for their performance. While some targets are missing; some have changed and the data is incomplete, it is clear from component logframes that Kalondolondo has scaled-up its engagement and reached more people, and that Tilitonse has achieved its goal of being fully operational, provided grants through two rounds of calls and reached a large amount of people through supported service delivery accountability projects- exceeding its own targets for 2013 already. This evidence backs up an estimate that the output performance has exceeded expectations.
Progress against expected results: / The original LogFrame does not provide Milestones for measuring yearly performance of the programme or specific projects within. However, it is possible to report back on the Indicators to show what progress has been achieved and make a judgement on whether this progress is acceptable. In addition, Kalondolondo and Tilitonse component logframes have indicators that are relevant for an assessment of this output and suggest excellent results have been achieved, over and above milestones for 2012/13. / Indicator from BEAM LogFrame Baseline Target/Milestone Achievement / Number of CSOs benefitting from the CSF (Tilitonse) for service delivery accountability projects 0 None 14 projects out of 33 (2012) / Number of districts covered by Community Based Monitoring and Score-card processes between communities and government 8 (2011) 28 districts by 2014 (original pre-agreement target) 14 by end 2012 (achieving final agreed scale-up) / Number of communities doing score-carding recording an improvement in service-delivery performance Not valid 75% of primary schools and health centres and 20% of water points by 2014 Not recorded / Indicators from Kalondolondo LogFrame Target/Milestone Achievement / Number of projects assessed by community members using the community scorecard process 500 (2012) 1335 (2012) / Number of district and national advocacy meetings held 60 (2015) 31 (2012) / Number of national dissemination events conducted 8 (2015) 2 (2012) / Number of local facility interface meetings held between duty bearers and service providers 375 (2012) 1000 (2012) / Number of multimedia IEC programmes 5 (2012) 3 (2012) / Conduct follow-up and institutionalisation events 8 (2012) 5 (2012) / Indicators from Tilitonse LogFrame Target/Milestone Achievement / Number of people consulted on the quality of public services in funded projects 4000 men, 4500 women: 8500 total (2013) 22,515 total (2013) / Number of representations based on monitoring initiatives made to traditional leaders, officials responsible for public service delivery, MPs 155 (2013) 400 (2013) / Number of people informed through funded projects about their rights to public services n/a 41,157 men, 43,356 women: 84,513 total (2013) / The indicator Number of CSOs benefitting from CSF for service delivery accountability projects refers to the number of CSOs supported by Tilitonse that can be said to focus on service delivery accountability. This area of work remained a key area for Tilitonse during design and has been incorporated into its own Theory of Change, logframe and thematic focus since its inception in November 2011. / Tilitonse has since implemented an accelerated grants round and an open call for proposals which in total have provided 33 grants in its first year of operations, involving some 70 organisations. Of these it can be said that 14 are directly focussed on helping communities to hold service providers directly accountable for the services they provide. Services include health, education, HIV/AIDS, Police and those specifically available to marginalised groups including the disabled, girls and people living with HIV and AIDS. In terms of Tilitonse’s achievement of its Terms of Reference to deliver two rounds, including one in its first year, this has been achieved. In terms of the focus area on service delivery accountability, this represents a good achievement of expected proportion of grants. / In terms of Tilitonse’s own milestones and targets related to this indicator in its logframe (see above), the data shows a large over-achievement in all areas related to providing information on rights to services, consulting people on the quality of services and making representations to local leaders. / The indicator Number of districts covered by Community Based Monitoring and Score-card processes between communities and government refers to a wish to increase the coverage of the Kalondolondo programme. Initially this was to be achieved by a scale-up of the Community Based Monitoring project (Kalondolondo) scale-up to cover the entire country. However, it was agreed that a scale-up to this level was not advisable or achievable and was never included in the final agreement with Kalondolondo when they started in September 2011. Kalondolondo instead were asked to extend their reach from 8 to 14 districts (out of 28 districts) and within each district they have extend their scope and range of issues. It was agreed that it was more effective for Kalondolondo to go deeper to reach more people than it was to go broader but shallower, and to this extent the scale-up agreed with Kalondolondo was achieved. In future years it is likely Tilitonse projects will be able to add to any assessment of district coverage from score-card projects they are supporting, although this is not currently an indicator they are using. / The indicators in the DFID-Kalondolondo specific LogFrame reflect this focus on reaching more people rather than reaching all districts at the potential cost of actual reach of people and quality of process. Output 1 of their project LogFrame was “At least 4000 projects assessed by community members using the community scorecard process”. The year one target for this was 500 projects. So at the one year stage they have already achieved 1,335 project assessments. This reach is impressive and actually exceeds project expectations. Their other outputs are all measures of reach and have largely been met or exceeded. / In Tilitonse’s logframe there is also an indicator related to the number of people consulted on public services. The target was 8500 people by end 2013. They have already over-achieved on this target, reaching 22,515 people in total. / The indicator number of communities doing score-carding recording an improvement in service delivery performance, has not been recorded, and could be seen as better suited to measuring outcomes. In fact, a measure of this has been included in the updated Kalondolondo LogFrame at outcome level and will be reported on at this level in future reviews. For this annual review no quantative data is available to assess performance. However, anecdotal data of changes that have occurred following Kalondolondo interventions suggest that there have been outcome level changes from their ability to assist communities to hold service providers to account and demand improvements. In future years it is likely Tilitonse projects will be able to add to any assessment of service improvement, although this is not currently an indicator they are using. / Recommendations: / This output needs to be fully overhauled to better reflect the objectives of the Kalondolondo and Tilitonse programmes. A revised LogFrame will need to devise ways to better capture BEAM’s contribution to service delivery accountability. / Impact Weighting (%):25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y/N

Output 2: Civil society engagement and action to improve government transparency, public accountability and responsiveness
Output 2 score and performance description: A. / An assessment of this output is hard to make on the basis of the indicators below. However, the main achievement of Tilitonse being set-up and providing grants to 33 CSOs through two call procedures has made a difference to DFID’s support of this output. There is also a small but significant focus on budget engagement in some of its project portfolio- notably though support given to MEJN. More appropriate ways to measure DFID’s support in this area will need to be developed in future.
Progress against expected results: / Indicator Baseline Target Achievement / Number of CSOs benefiting from CSF funding to improve governance in Malawi 0 (2011) none 70 / Number of communities providing input to national budgets 300 stakeholders in 10 districts (2010) 1000 stakeholders in 28 districts (2014) 10 districts (2011) / 8 districts (2012) / % of citizens coming together to raise an issue on a regular basis 66.7% (2008) 75% (2014) 67.7% (June 2012) / Indicator 1 Number of CSOs benefiting from CSF funding to improve governance in Malawi is intended to measure the number of more general governance CSO projects that Tilitonse was able to fund in its lifetime. The absence of a target makes it difficult to measure, as does a lack of definition for what a project to improve governance is and isn’t. However, as noted above, Tilitonse achievement of its own ToRs- 2 calls for proposals in its first year funding 33 projects involving 70 CSOs- suggests an achievement of this indicator. / Indicator 2 Number of communities providing input to national budgets refers directly to the MEJN project funded through BEAM and its successor programme funded through Tilitonse’s first call (accelerated grants) and other future Tilitonse grants that support budget engagement. In terms of MEJN’s first project, they reached stakeholders in 10 districts as well as surveying households across the country for a Service Delivery Satisfaction Survey. In their Tilitonse-funded accelerated grant project they opted for a deeper engagement of more people from community level to district level and national level, but in only 8 districts. In addition to these results other Tilitonse grants have been supporting communities to engage in national budgets. For example, the Centre for Social Concern have been analysing the National budget through a child-friendly lens, advocating for more funding to child-centred policies and projects, and Nanzikambe arts have been working with communities in the Chingale area of Zomba to support their advocacy for road upgrading to be included in National and local budgets an plans, and implemented. However, this specific indicator has not been included in their project specific LogFrames so data is not available to directly measure the contribution towards this indicator. / The third indicator is % of citizens coming together to raise an issue on a regular basis. This is an indicator that BEAM can only hope to have a contribution to and the attribution of this contribution would be very hard to measure. It is a measure that would be better suited to higher levels of a logframe at outcome or impact level and is not well suited to measuring this specific output. The data for this is based on Afrobarometer data and was recorded through a 2012 survey following up on the 2008 survey. The increase was 1% from 66.7% to 67.7% towards a target in 2014 of 75%. This is quite a remarkable statistic as it occurred on the back of 2 years of repressive leadership under the late President Mutharika. While BEAM cannot take credit for the fact this figure was not much lower, it does reflect a slightly positive trend in community participation in Malawian governance and collective action. / Also falling under this output, although with no specific monitoring indicator, is the work of MEJN and the African institute for Corporate Citizenship (AICC), in conjunction with Transparency International, to assess the state of the National Integrity System and build a civil society platform for increased engagement on anti-corruption. Their assessment work is on-track and will be released later this year. Through their civil society work they have directly engaged over 500 people through trainings on national integrity and radio show participants, with actual coverage of their media work likely to be much higher. The main indicators for this project are process- the delivery of an assessment and a national integrity platform (that could become a Transparency International Malawi Chapter). They are well on-track to achieve both of these results, which will be taken up by the future Anti-Corruption programme being designed outside of BEAM. / Recommendations: / This output needs to be fully overhauled to better reflect the objectives of the Kalondolondo, Tilitonse and other civil society anti-corruption programmes. A revised LogFrame will need to devise ways to better capture BEAM’s contribution to Government transparency, political accountability and responsiveness. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Excluded and marginalised groups better able to access services and exercise their rights
Output 3 score and performance description: A. / In terms of BEAM indicators this output is difficult to assess, but the progress achieved merits an A score. Tilitonse success in identifying and supporting excluded and marginalised groups through its grant-making has been demonstrated, although more appropriate ways to measure this success will need to be developed in future.
Progress against expected results: / Indicator Baseline Target Achievement / Number of CSOs benefiting from CSF funding to tackle exclusion Malawi 0 none 17 projects out of 33 fudned (2012) / Access to basic services by disabled people none None No data / Number of women in decision-making positions 22% MPs and 1/27 DCs (2010) 22% of MPs and 3/27 DCs (2012) 22% of MPs and 3/27 DCs (2012) / Indicators from Tilitonse LogFrame Target/Milestone Achievement / Number of monitoring initiatives undertaken that address services and policy commitments to excluded groups 14 (2013) 18 (2013) / Number of advocacy initiatives that promote rights and access to services for poor and excluded groups 20 (2013) 17 (2013) / Indicator 1, Number of CSOs benefiting from CSF funding to tackle exclusion Malawi, again intends to measure Tilitonse’s support for excluded groups through its granting. The results show that over 50% of the 33 grantees have a specific focus on excluded and marginalised groups including children, adolescent girls, sex workers, the disabled, children, women and girls living with HIV, women in relation to land issues, youth, and street children. Others also focus specifically on the very poor. This reflects a positive success on Tilitonse’s commitment to supporting those CSOs promoting the rights and access to services for the excluded. / In addition, specific indicators in the Tilitonse component logframe show good results in specific initiatives aimed at benefiting excluded groups. These include focussed advocacy projects on access to services (17 against target of 20) and monitoring of services for excluded groups (18 against target of 14) / Indicator 2 was intended to be a measure of Access to basic services by disabled people as measured by a social exclusion analysis. However, data on this area was not available without undertaking a household survey and so was abandoned as a measure. More project-specific measures of disabled access to services have been developed and will be measured in future years with specific relation to projects in this area. / Indicator 3, Number of women in decision-making positions, is again of a higher order than output measures should be, and very hard to attribute DFID support towards. However, there has been progress in this area with an increase in the number of DCs, reflecting a generally positive trend. DFID is also supporting other projects outside of BEAM that intend to have a positive impact on the number of women contesting for elected positions in the 2014 local, national and presidential elections. / Recommendations: / This output needs to be fully overhauled to better reflect the objectives of the Kalondolondo and Tilitonse programmes. A revised LogFrame will need to devise ways to better capture BEAM’s contribution to inclusion through both standalone programmes, and through mainstreaming into other programmes. / Impact Weighting (%):25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Electoral processes able to deliver free and credible local elections in 2011 with increased public participation
Output 4 score and performance description: B. / While the local elections were cancelled and planned support for a UNDP trust-fund was also cancelled, DFID did support on-going civic education on local governance- through an NDI grant and Good Governance Fund media support. This work was anecdotally successful, but reporting was poor and quantative data absent. The B score for this output is in reference to the two CVE components only.
Progress against expected results: / A “killer assumption” associated with this output was that the elections would not be cancelled. Unfortunately in the declining governance context of Malawi at the time they were again cancelled by the President. They will now be held in 2014 alongside the parliamentary and presidential elections, support for which is covered under a separate programme (ISEP) outside of BEAM. / The first two indicators for this output refer directly to the elections and as such cannot be scored. However, the third indicator refers to the Coverage of civic and voter education. An NDI project to subgrant and support CSOs to undertake CVE for the local elections was already underway when the elections were cancelled. However, BEAM was able to react in a flexible fashion, helping NDI and their grantees to transform projects into civic education on local governance and how to hold local governments to account in the absence of councillors and other elected representatives. In its own terms this component was relatively successful- most of its partners have gone on to scale-up their projects and have gained funding under Tilitonse- although the absence of quantitative reporting against its own targets (which admittedly changed during the project’s lifetime) can only lead to an assessment that the project did not meet expectations. / Reporting from the Good Governance Fund was particularly poor and we are unable to provide much information on results. The management of the Fund was joint DFID-FCO and this arrangement proved to be difficult to operate while still achieving the level of reporting and partner management DFID requires. The Good Governance Fund has now ended. / Recommendations: / This output will be removed from the LogFrame as no further elections support is planned under BEAM. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 5: Key Malawian public oversight bodies and government-led initiatives step-up \actions to promote political and economic accountability and counter-corruption
Output 5 score and performance description: B. / On balance the performance of the components of output 5 was not satisfactory and did not meet expectations. The reason for this was often outside of the control of BEAM or the Institutions supported. Political events have impacted negatively on achievement of results.
Progress against expected results: / The first indicator for this output is intended to measure progress on PEFA scores. Milestones for this are not included but have been set in the World Bank-managed MDTF which DFID is a key supporter and current Co-Chair of. However, these are high-level indicators that are unlikely to show radical short-term change, and will only be measured at 2-yearly intervals. Currently progress is between measurement and change predicted is not likely to show up in these aggregate indicators. Progress in-between PEFA changes were intended to be measured through short-term indicators set in place in the first 6 months of the specific projects designed and implemented under the MDTF financing. The first project under the MDTF is called the Financial Reporting and Oversight Improvement project- FROI- and was designed, validated and began implementation late 2012. A second project is currently under design and scheduled for a 2013 roll-out. FROI is currently designing its own M&E framework and so no specific judgement can be made under this AR on the basis of this. However, we can judge that the roll-out of the MDTF and FROI is very much behind schedule. While much of the reason for the delay was due to events outside of the control of the MDTF and of BEAM, it is possible more could have been done to speed up implementation once the new Government had been installed following the death of the President Mutharika to capitalise on the support given to the reform plan by President Banda. So, while quantative judgement on PEFA scores cannot be made, or on the basis of in-design short-term indicators for FROI, it can be judged from a process point of view that the implementation of the plan with DFID-support is likely to lead to PEFA improvements, but that the speed of these improvements is likely to be behind the schedule originally envisaged. / The second indicator suggests that other measures should be decided on the basis of a forward plan for the support that would be agreed upon as components were agreed. The Programme Memorandum left what the exact support would be open at the time of its approval. Although no specific forward plan has been developed, in addition to the above support for the PFM Reform Plan DFID has supported two other “public oversight bodies” under this output: The National Audit Office (NAO) and the Anti-Corruption Bureau. / For the NAO, the support has been limited to the co-financing through the Norwegian Embassy of two one-year technical assistance contracts aimed at improving the NAO’s own financial management and planning. This support was intended to be complementary to support previously provided to NAO for undertaking local audits, and as a stop-gap before support to the NAO was taken-up by the PFM MDTF. The FROI project mentioned above does in fact include support to the NAO, but as an audit of our previous support to NAO showed financial mismanagement for which we are yet to receive refunds, and there is no Auditor-General in place following the retirement of the old AG, this support has not been implemented and won’t be until these two conditions are met. In terms of the specific support provided under BEAM, the NAO have been very satisfied with the performance of the technical assistants. / For the Anti-Corruption Bureau (ACB), in the period this AR is concerned with, we provided bridging support for the period January to July 2012. This was to fill a gap between the end of one strategic plan (which DFID had supported) and the development and implementation of another (which DFID would be considering support to). However, the period under discussion was one of great political turmoil with the previous President clamping down further on political liberties and corruption indicators suggesting a major increase in corruption and loss of will to tackle it, followed by the President’s death and removal of the Director of the ACB and failure to replace him until November 2012 under the new President. These events, plus a financial crisis, impacted negatively on the performance of this programme. The bridging programme was provided by financial aid direct to the ACB to support its work on prevention; education; national integrity systems; investigation; and prosecution plus supporting services (M&E etc). Of the 33 targets under the 6 pillars that were set for this programme (most of them activity-focussed) only 12 targets were met. The key reason given was the failure of the Government to provide funding for the recurrent aspects of the work and the devaluation of the Kwacha which reduced the value of the support given by donors. / Recommendations: / Anti-Corruption needs to be given separate consideration in the long-term and a separate Business Case developed for a long-term support to tackling corruption in Malawi (as per recommendations in the DFID Malawi Anti-Corruption Plan) / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y/N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / No. / 1.2 Overall Output Score and Description: / The overall output score is A. This reflects a balance between the progress made and results achieved by components working with civil society (notably Tilitonse and Kalondolondo) and the more halting progress made on the components working with state or quasi-state institutions such as the ACB and the local elections, whose operations are more acutely affected by upheaval in the political context. / 1.3 Direct feedback from beneficiaries / Extract from the Kalondolondo Annual Review: / Beneficiaries of this project constitute communities of the 14 districts where service provision assessments are being done. The Kalondolondo project has focused on service delivery in terms of LDF, FISP, COMSIP, HCT and ART. We visited communities in the LDF project areas in Dedza and the COMSIP clubs in Karonga. Selected CSOs who facilitate the service delivery assessments were also visited in Dedza, Mzuzu and Karonga. Generally, the feedback received about the project is that the Kalondolondo project has empowered communities to hold duty bearers to account for their actions in terms of service delivery. In Dedza where the LDF was assessed, communities were happy with Kalondolondo because through the assessments, it was discovered that the houses built under the LDF were substandard and there was some form of corruption in the manner the artisans were identified and how the procurement of materials was done. Communities indicated that if it were not for Kalondolondo, these issues would not have been raised and those responsible would not have been identified and reported on to authorities. As a result of the Kalondolondo assessments, the National Audit Office dispatched auditors to the area to audit the LDF projects and a reported is yet to be issued out. In Karonga where Titemwanenge COMSIP Cluster was visited, it was learnt that before Kalondolondo came, the clubs were not given any opportunity to raise their concerns about the way COMSIP is being managed. However, when the Kalondolondo came with community service delivery assessments, the club members have been able to raise various issues and the interaction between members and those managing COMSIP has improved significantly. In terms of the CSOs participating in the implementation of the Kalondolondo project, the general feedback is that the project should improve on disbursement of funds to ensure that activities are implemented on time. The training on Score cards should focus more on the process rather than the concept. As is currently the case. / Extracts from the Tilitonse Annual Review: / The Tilitonse approach has been well received in principle by a wide range of stakeholders. There was strong communality of views between most members of the Management Board, Secretariat and civil society organisations. Together these indicate a consensus on the strong emerging characteristics of Tilitonse for many stakeholders, forming the basis for a strong Tilitonse “brand”. / Funders, grantees, Management Board members and Secretariat staff indicated strong support for the Theory of Change and Political Economy Analysis approach. Some thought that Tilitonse would have difficulty refocusing after the political changes of 2012, and that donors might not see the need for supporting governance after the accession of the new president. Stakeholders were therefore pleased that donors remained committed to Tilitonse following the change of government. / Tilitonse‟s public announcement of an Open Call was widely commended, as were the subsequent information sessions; these attracted 600 visitors and resulted in submission of over 200 concept notes. The publication of award recipients and amounts was also praised. / Open Call Grantees called Tilitonse “an emerging model grant-maker”; they welcomed the emergence of a positive engagement with players throughout Malawian society, instead of a focus on criticism, which some saw as potentially destabilising for Malawi. The culture and ways of working demonstrated by Secretariat received particular praise. / Grantees commended Tilitonse staff for: / providing a focal person, with knowledge of the field and in-depth understanding of the grantee, / the ease with which they could contact and meet them, / rapid processing of applications, / support with reporting, / Tilitonse’s willingness to learn and adapt procedures to meet need. / There was concern that Tilitonse’s approach needed to be more firmly rooted in Malawian society than in academic or donor discourse. Terms like ToC and PEA do not make it easy for parties unfamiliar with donor and academic jargon, such as many community based organisations (CBOs), to express their voices. / There was concern about the difficulty of fulfilling the requirements of the approach. Some felt that PEA had become a “mantra”, and that Tilitonse needs to focus more on practical content than the formal language of PEA. Both successful and unsuccessful applicants found Tilitonse‟s approach very challenging, but most felt they had gained through the experience, though we had mixed responses to individual, and group feedback sessions. / There were concerns about Tilitonse’s choice of organisations. CSOs were particularly concerned about the (perceived) emphasis on International NGOs (INGOs) in the Accelerated Grant round, as this left less money for local organisations: Tilitonse should fund more organisations, particularly CBOs. Some stakeholders wanted to see more inclusion of non-traditional CSOs, including business groups, trade unions and media, and considered these critical to Tilitonse’s theory of change.
1.4 Summary of overall progress / BEAM has been slow to move to full implementation, affected as it was by the major changes in political context over the past 2 years. Design, OJEU tendering and implementation of the Tilitonse Fund took almost a whole year. Moving from design of the World Bank MDTF to implementation of the first project took over 6 months. However, the time has also been usefully used to: finalise and close components that BEAM took on from other closing programmes and prior commitments- such as the Good Governance Fund, MEJN and StoryWorkshop AGs; to re-brand the Community-Based Monitoring programme as Kalondolondo and allow a smooth scale-up of their approach; and to respond flexibly to events as they arise with rapid support to areas such as CSO security training and research on the motivations of demonstrators during late 2011. / Now, BEAM is consolidating its complex portfolio to concentrate on its three main components: Tilitonse, Kalondolondo and the PFM MDTF. We are re-working the LogFrame to fully integrate the key outputs, outcomes, impact and indicators of the central components- much of which already exist and will begin to gather valuable data on results over the next 12 months. The Theory of Change is being re-visited and placed clearly within the “Accountability and Empowerment” paradigm of DFID policy, which fits well with BEAM’s aim of linking demand and supply-side interventions together to go beyond simplistic approaches that assume information and voice alone can achieve change in governance. We are also beginning to make progress on impact evaluation of the Tilitonse component through the independent impact evaluation agent (IIEA) whose evaluation strategy and approach will help us generate understanding of what works and what doesn’t and why in our civil society projects.
1.5 Key challenges / Key challenges have been: / The political context I: increasing restrictions on freedoms under the previous Government and a failure of political opposition distracted civil society partners from project implementation to oppositional and often anti-Government campaigning. This also attracted Government attention towards donor-support of civil society which while was clearly separated from support to demonstrations was increasingly questioned by Government Ministers and the President. The expulsion of the British High Commissioner and cancellation of budget support worsened relations further. The cancellation of local elections prevented any progress on a major component of the BEAM programme. / The political context II: following the death of the president and the formation of a new Government much “fell between the cracks”. The removal of most top Government officials delayed implementation of “supply-side” interventions and court cases from those dismissed and political actions from Parliament continue to frustrate progress in some areas (such as the NAO). / The economic context: all partners who receive funding in kwacha have reported a major challenge of devaluation and inability to implement programmes as previously planned. The ACB is a case in point. In general a worsening economic situation has posed challenges for engagement of local communities and morale of partner staff alike. / The size and complexity of the BEAM portfolio: while the team was able to keep on-top of the different components there was a risk of coherence being lost. The need to finish and close pre-existing components while design and implementing new ones has proved to be a major challenge, and has impacted upon our ability to tell a clear story around results. However we are now able to consolidate the key components and gain a greater clarity around BEAM’s objectives, theory of change and results framework. / The challenges of working with and through others: with Tilitonse being a multi-donor fund (Norway, DFID and Ireland) and the PFM MDTF being a similar pooled-fund managed by a multilateral partner (World Bank) there are a number of key donor relationships that need to be kept on-top of and risk overtaking relationships with Governments, implementing partners and beneficiaries. Multiple interests and administration can also slow down implementation- for example, the EU-DFID plan to allow the EU to delegate funding through DFID that was stopped by bureaucracy.
1.6 Annual Outcome Assessment / Outcome: To empower citizens to hold the Malawi state to account and improve delivery of basic services / Indicator Baseline Target Achievement / % of citizens contacting representatives 22.8% (2008) 30% (2012) 14.2% (2012) / Freedom House Civil Liberties score 4 (2009) 3 (2014) 4 (2012) / Satisfaction with service delivery/government performance 55.9% (2008 women) / 64.4% (2008 men) 60% (2014 women) / and 70% (2014 men) 68.1% approve of President performance (2012 non-disaggregated) / Using the current set of indicators in the logframe outcome gives a very mixed picture that says more about the context when they were set and the context of the most recent scores than perhaps it does about the success or otherwise of BEAM in achieving positive outcomes. / The % of citizens contacting representatives (from Afrobarometer) has drastically reduced, reflective of increasing disillusionment with Parliament and MPs. Legitimacy of their elected representatives a number of years after the elections is traditionally at a low-ebb. This is further compounded by the poor performance of Parliament and political opposition in preventing economic crisis and political repression, plus the degree of floor-crossing that took place in early 2012 following the death of the President. Furthermore, the ability of BEAM to influence the MP-Citizen relationship is limited by a focus on other duty bearers and officials who have a higher relevance in people’s day-to-day lives, such as District Health officers and School Teachers. / The Freedom House Civil Liberties score is an annual assessment by “independent experts” and moves between a range of 1 (positive) and 10 (negative). The lack of movement is reflective of a subjective assessment that has remained constant despite major political repression and recent returns. However, a move to 3 would represent a positive trajectory for Malawi. . / The service delivery satisfaction assessment is actually harder to score from Afrobarometer sources than it might appear. The best current question is approval of President. As last survey was taken in the months following the new President’s succession after the death of Mutharika, she could have been expected to have a “honeymoon” period. / For these reasons we will be reviewing the outcome statement and indicators and making a submission to the Head of Office on changes.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Along with the changing political context and changing project portfolio there have understandably been many changes to the projects overall forecast. As we move to consolidate around the three major interventions we will be focussing on their performance in this area. With Tilitonse, we have had some considerable difficulty helping them develop realistic forecasts of expenditure. This is improving as they begin to feel more comfortable with their grant-making procedures and we hope will be improved this year. / Nonetheless we have included the following challenges, recommendations and actions taken so far, to improve Tilitonse’s entire ‘Resource Management’ processes (which includes financial forecasting). These will need to be monitored over the course of the next year and followed up during the next Annual Review exercise; / The Tilitonse budget, which is the largest budget in BEAM, is managed through several contracts. At the onset, the individual contracts set out the strategic priorities and provisional commitments, based on the information that was available during the contracting phase. We have experienced challenges in subsequent phases of the project (Inception and implementation), in relation to the systematic incorporation of changes to, and management of, the funds evolving strategic priorities and related commitments i.e. actions taken to address the loss of the EU as a donor to the fund; addressing the on-going issues in relation to the capacity development component of the fund etc. / We have since set up a Tilitonse Donor group to work on a portion of the issues detailed above. / Further to this the Terms of Reference for the Tilitonse Board and its committees, have been revised by a consultant, to refine the institutional arrangements for the identification of gaps in resource allocation and management, based on a systematically management of Tilitonse’s strategic priorities / We have identified that there is need to further define the DFID role as Lead Donor, as this has presented challenges in terms of responsibility and accountability for the oversight and scrutiny of Tilitonse’s resource management. While DFID has been and still is responsible for providing the led in the contracts management for the fund. On the other hand our donor counterparts to the fund, were also been required by the Tilitonse Memorandum of Understanding, to actively engaged in the various forums where scrutiny of the fund’s planning and performance takes place. However, practice has demonstrated that there is an assumption, that scrutiny is the sole responsibility of DFID. Firstly, this has meant that scrutiny of the wider resource management (budgeting, forecasting, resourcing decisions etc) has not received adequate attention from all the donors to the fund. Secondly, since DFID is the donor ‘most concerned’ with monthly forecasting accuracy, this has meant that the challenges in institutional arrangements for scrutiny, have made it difficult for DFID to influence the fund, and fellow donor partners, on the strict requirement for forecasting accuracy. / We need to put more effort into influencing the Tilitonse board, to ensure that the primary responsibility for resource management is that of the Donor Group Committee, and not just DFID’s responsibility. / DFID needs to utilise the Donor Group Committee to influence fellow donors and the Tilitonse Board, on the high prioritisation of forecasting in the resource management cycle of the fund. / The recommendations provided in this section will be shared with the Tilitonse board and its respective committees. The DFID Tilitonse Programme Management team will prepare an action plan to monitor and act on the recommendations presented above, as well as report on progress during the next annual review. / The World Bank PFM Trust Fund has been slow to start-up and consequently has not been good at providing accurate forecasts of expenditure. This led to one 6-monthly payment being missed entirely and moved to the very end of their programme lifetime. However, with the projects beginning implementation we are getting clearer reporting from the Bank and better estimates of when our funding has been used and when new disbursements will be requested. / Kalondolondo are on track and provide good assurance of forecast and expenditure. / 2.2 Key cost drivers / As the programme was based on a Programme Memorandum not a Business Case, specific cost drivers were not identified and therefore cannot be assessed. / 2.3 Is the project on-track against original timescale: / Tilitonse and Kalondolondo are largely on-track. The PFM Trust Fund is 6 months behind and will likely require an extension.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No explicit Theory of Change was included in the BEAM programme documents. However, work is in-progress to better define the approach and bring it in line with the “meta” theory of change for Empowerment and Accountability paradigm developed by DFID policy division and reflective of the BEAM approach. Although still weak, the evidence base for this theory of change is growing and will be fed by evaluation of the work of Tilitonse and other similar programmes in DFID’s Global portfolio. / 3.2 Where an evaluation is planned what progress has been made? / Impact evaluation of the Tilitonse fund has been contracted on an on-going basis, independent of the Fund’s secretariat. An evaluation strategy has been developed and questions agreed, with a mix of experimental and quasi-experimental approaches to be used, largely to undertake a theory-based evaluation of the Tilitonse theory of change. The potential for undertaking some randomised control trials of typical Tilitonse projects that embody the Tilitonse theory of change is being explored.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / As described above, the main risks for BEAM have been raised and lowered over the past 2 years. / The central risk of Human Rights and Governance Situation deteriorates, restricting space for civil society engagement on governance issues was the heightened during 2011/12 when vocal civil society activists were attacked and threatened. This did lead to a reduction in space for overtly political work, but local level civil society actions that took a more collaborative approach were able to continue relatively unaffected. Meanwhile we were able to provide funding to some of the main national NGOs. We also provided security training and assisted on the political side with a degree of cover for their work. Since mid-2012 the situation has changed and there is a greater degree of freedom for civil society action. The risks have changed. / Co-option of civil society by Government reduces independent and critical voices has become a higher risk, especially in the run-up to the 2014 elections. A general politicisation of civil society voices is a risk and Tilitonse and Kalondolondo are having to be extra careful about their partnerships and the potential for DFID-funded projects to be sued for political purposes / Weal capacity of civil society remains a risk. This was especially evidence in the poor quality of many of the Tilitonse open call proposals. However, capacity building of grantees and those refused alike has been taking place in a tailored fashion. The Tilitonse Annual review recommended further consideration of the approach and greater focus on building capacity, which the board is considering. / The risk of Changes in Tilitonse Board membership leads to failure to maintain consistent understanding of Tilitonse’s goals is at a greater level at the current time. By the end of July all donor representatives who were involved in the design and roll-out of Tilitonse will have been replaced. However, the clarity of the Theory of Change of Tilitonse is a good tool for keeping a focus on its original goals. / Finally, the risks associated with a failure to implement the priority PFM reforms, especially in an election year remain. The political engagement and multi-donor processes help manage this risk and the Government knows the stakes are high for resisting the reform process. However, there is a risk that Government leadership of the process may weaken in the last months of this Government.
Risk of funds not being used as intended / Fiduciary and corruption risks in BEAM component programmes overall are medium. / The Tilitonse management agent has been contracted through OJEU and is held to rigorous standards. The downstream partners are all subject to due diligence assessments and capacity building on financial systems where necessary. / Kalondolondo is a long-term partner. However, due diligence assessments of all their own downstream partners will be undertaken in the 2013/14 financial year to provide added assurance. / The World Bank PFM Trust Fund is a low risk, with World Bank rules being used for procurement and oversight being provided by World Bank staff. / Other components rank as low risks, managed actively through financial aid or accountable grant agreements that will all expire during the next 12 months. / 4.4 Climate and Environment Risk / There has been no change to the Climate and Environment risks. However, as detailed in the programme memorandum, support to organisations working to promote climate smart policies has been pursued through Tilitonse. At least one organisation, Centre for Environmental Policy Advocacy (CEPA) is engaged on influencing environmental policy at the national level. Other opportunities to maximise positive impacts of BEAM will be considered.

5. Value for Money
5.1 Performance on VfM measures / Value for Money measures were not included in the programme memorandum for BEAM, however the following retrospective assessment has been included based on the DFID VFM Principles. / BEAM uses a combination of financial instruments, agreed with both private and public sector partners. These include several contracts, MoU’s, Accountable Grant’s, and a World bank Trust Fund (WBTF). As a result, various strategies have been utilised to address the the 3Es. The largest agreements are the Tilitonse Fund contracts (£8 million), followed by the WB Trust Fund (£7.5 million). Nonetheless, and irrespective of funding agreement size, we have conducted in-depth scrutiny of partner budgets, and have drawn on the various lessons learned. Most notably our approach draws on the SofS’s ‘Statement of Priorities and Expectations for Suppliers’, close working and technical advice from Procurement Group, as well as the Programme Management Cadre lessons learnt from working with the Private sector. / Economy / We will use the largest agreement for the fund to demonstrate economy. The Tilitonse fund managers HTSPE, were recruited through an OJEU process. To ensure economy in the planning and delivery, they are required to justify their budget amendments to both the DFID programme management team, as well as the fund’s management board. Their monthly payments for services delivered are paid in arrears, and payment is conditional on the satisfaction of dual scrutiny of the monthly technical and financial reports. The report are assessed against the contract budget and work plans. / As lead donor we have maintained the emphasis on value for money through the different management and governance structures of the fund. To establish additional recommendations for institutionalising economy in the delivery of the fund, the initial Annual Review of the programme focused on assessing the extent to which the fund’s set up is ‘fit for purpose’, as opposed to measuring progress on the delivery of results. This approach to the AR has assisted us in identifying, and building multi-donor consensus for the institutionalisation of additional operational and strategic measures, to ensure that the fund uses quality inputs which are procured at the right price. / Efficiency / We commenced the process of negotiating key performance indicators (KPI) on for our Tilitonse Fund contracts, to assist in the measurement of efficiency, however this work has been slow to progress due to the pace of setting up the fund within a volatile context. The fund has now managed to establish trends data, which we are monitoring very closely. We also facilitated the building of consensus, amongst the managing and governing stakeholders, more specifically through the annual review process (a process that we led). The outcome of the AR will contribute significantly towards the firming up of the KPI’s. This work will enable a more tangible assessment of efficiency in the next AR. / The exchange rate in Malawi has been in constant flux over the past two years, as such we have had to maintain very close attention to the changes in prices, resulting from inflationary adjustments. This has also meant that we have had to consistently renegotiate budget amendments with our partners to ensure that exchange rate gains or losses are being managed well, and that in the event that exchange rate fluctuation has resulted in gains, it should not be directed towards inappropriate quantities and quality of inputs. This process has been undertaken with all our partners. We have also conducted a spot check of Kalondolondo during the period under review, and the results demonstrated that as a partner managing several downstream partners they are exercising several commendable due diligence measures. Nonetheless, we are planning to conduct a due diligence exercise in the financial year 2013/14, using DFID guidance, to ensure as many safe guards are in place to fully support the increase in the projects depth of coverage. / Effectiveness / As discussed in the above section covering results, it is too early to tell the ‘degree to which’ the combination of interventions, within this programme, are achieving the desired outcome on poverty reduction. However, we have been working with the Results team and the centrally based Evidence Adviser on Empowerment and Accountability, to continuously refine our aggregate and sub-component ‘Theories of Change’, and log-frames, together with our key stakeholders. As such we will be in a better position to comprehensively measure effectiveness in our next AR. / Cost-effectiveness / As the Lead Donor responsible for managing the 2 contracts for the Tilitonse Fund, we plan submitting a proposal to the Head of Office and influencing the fund’s Donor Group, to commission a cost-effectiveness analysis before the mid-term review of the fund. So that the findings of the analysis can be presented as evidence to inform our decision on the extension/exit strategy for the fund. / The preliminary findings from the ICAI Citizen’s Participation review (conducted in May 2013), suggested the need for further investigations into efficacy of the ‘simply’ (Kalondolondo) and ‘complicated’ (Tilitonse) intervention models for Empowerment and Accountability (E&A). We will use these findings, as a basis to make a submission to the Head of Office, to undertake a comparative cost-effectiveness analysis of the two E&A intervention models. If approved we would endeavour to conduct it as a joint exercise, with the partners for both interventions. / Although, a cost-effectiveness analysis of the entire BEAM programme may not be possible, and the proposed analysis of the two interventions above may not be generalizable to the entire programme. Nonetheless, it has the potential to enable us to analysis the cost-effectiveness of the demand side interventions in the programme. The additional advantage of the conduct of such an analysis is that it can contribute towards improved commercial management of our demand side partners. / 5.2 Commercial Improvement and Value for Money / Competition was used to procure a management agent and independent impact evaluation agent for Tilitonse. The marketplace responded positively to the opportunity. By increasing the standard value of the financial criteria from 20/100 to 25/100 points we underlined our desire to see good value for money. Contract management has been used as a tool to maintain downward pressure on costs. However, adjustments have had to be made to contracts to allow more staff to be recruited for the managing agent to help assure the value of results. / 5.3 Role of project partners / The VfM emphasis has been built into the Terms of Reference’s for the contracted Tilitonse partners, as such are required to include their approach and achievements in their Annual Reports, which are then challenged by the Management Board. The KPI’s mentioned under the efficiency paragraph will also include critical VfM indicators. / Kalondolondo through their consortium, lead by Plan Malawi, is required to report on Value for Money in all their reporting, however there is remove for improvement. In the event that the Cost-Effectiveness analysis is approved, we will use its findings to augment the project unit’s capacity to deliver VfM. / In line with the ‘DFID’s strategy for World Bank trust funds’, we will work with our World Bank colleagues to prepare for the Investment Committee of the DFID’s Trust Fund portfolio, scheduled in September 2013. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Budget support to Malawi was suspended in 2011 due to concerns about human rights and macroeconomic management. However, support through financial aid to the Anti-Corruption Bureau was continued to avoid adverse impact on the fight against corruption. Government was engaged on these issues throughout the period under consideration, including the new Government of Joyce Banda.

7. Conclusions and actions
BEAM is a complex portfolio programme that has had to manage a diverse range of components coming on stream and finishing at different times, all during a period of great political instability where much of its work was directly impacted by the political context. Its ability to monitor and evaluate results during the initial period has been a challenge and comprehensive judgements have been difficult to make. / However, despite these challenges it is clear that BEAM has been able to deliver a series of results central to its first full year of implementation. The Tilitonse Fund has been set up and is now operating at full capacity, having provided grants to 33 local organisations. Kalondolondo has successfully scaled-up its operations, extended its reach and continues to win plaudits for its success in uncovering corruption and helping local communities engage duty bearers and unblock bottle necks in service delivery. The World Bank PFM Trust Fund has been able to support the Government’s own PFM reform Plan, focussing on priority areas of donors and government which will help increase financial transparency. Other components of support have had mixed results, often buffeted by the political winds, but over the next 12 months a consolidated BEAM programme will concentrate on delivery of results, capitalising on an improved political context. / Key areas for action, outside of those described in the specific component annual reviews, are: / Development and detailing of the BEAM overall Theory of Change, placing it inside the DFID approach to Empowerment and Accountability (by end June 2013) / Re-drafting of the LogFrame to better capture the results areas featuring in key components and enable improved monitoring of results over the next year, especially around service delivery accountability, political governance and inclusion. (by end June 2013) / Careful crafting of new indicators to enable improved measurement of results in all component areas. (by end June 2013) / Doing more to bring BEAM partners together to share experiences, approaches and examples of “best practice” (such as around score-carding), as well as to encourage synergies (such as between budget monitoring work and the PFM reform programme) (on-going) / Finalisation of current work on anti-corruption and development of a new Business case to house DFID Malawi’s work on Anti-Corruption and Integrity (by end 2013) / Improvement of financial forecasting in all key component areas (on-going) / Bringing sector advisers together under an Accountability Committee in DFID to share work on accountability issues, including sector work done by BEAM partners and sector programmes (from July 2013)

8. Review Process
The review process included individual annual reviews for most components of BEAM, undertaken by members of the Governance and Security Team (Quest # 4026790). In addition, an independent Annual Review was contracted to Coffey for a first year review of the Tilitonse civil society fund, focussing largely on the implementation structures and processes, and the governance structure of Tilitonse to help ensure it is “fit for purpose” to begin meeting its milestones over the next year of full operation. / Data sources include (and can be found at above Quest number): / Kalondolondo annual review / Anti-Corruption Bureau annual review / National democratic Institute project completion review / Story workshop and MEJN AGs / Tilitonse independent annual review / Tilitonse draft annual report / Tilitonse logframe with data on achievements / Tilitonse table of narrative and some number data against outputs / MEJN NIS programme data / Good Governance Fund annual review / All members of the Governance Security Team were involved in this process. Alex Stevens, Governance Team leader, put together this Annual review with reference to this ground work, with assistance from Thoko Chisala, the BEAM lead programme manager.