## MESRP PCR
PROJECT NAME | Malawi Education Sector Reform Programme
IMPACT | Impact Indicator 1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14 | Assumptions
Achievement of MDGs 2 and 3 - universal primary education, and gender parity in primary and secondary schools. | Net and Gross Enrolment Ratios (NER and GER) in primary education (DFID Standard Indicator, MDG 2, Indicator 6 and WB core indicator) Number of children supported by DFID in primary school p.a. (boys, girls and total) (DRF indicator) | Planned | NER 83% GER 115% DFID B: 49,225 G: 49,665 T: 98,890 | NER 83% GER 114% DFID B: 120,000 G: 125,000 T: 245,000 | NER 84% GER 112% DFID B: 135,000 G: 135,000 T: 270,000 | NER 85% GER 110% DFID B: 200,000 G: 200,000 T: 400,000 | NER 100% GER 110% No DFID contribution | Political commitment to education remains. No major drought, flood, earthquake or other natural disaster. Macro-economic stability and economic growth are maintained. Political stability in the country with progressive democratic system maintained. Partnership principles between DFID and GoM are not broken. No major corruption scandals in GoM.
|  | Achieved |  | NER 110% , GER 126%, DFID: B: 123,425, G: 125,474, T: 248,899 | NER 112% , GER 127%, DFID: B 138,510, G 139,246, T: 277,756 | NER 86%, GER 133%, DFID B: 241,758, G: 242,098 T: 483,856 | Figures not yet available
|  | Data source | NERs from annual Welfare Monitoring Survey in 2009 and from EMIS (Education Statistical Bulletin) from 2010 onwards, NERs 2012/13 ESPR 2013. Quest number: 3463158
| Impact Indicator 2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Ratio of girls to boys in primary / secondary education (DFID Standard Indicator, & MDG 3, indicator 9.) (WB has Gender Parity Index (GPI) as a core indicator) | Planned | Prim 100% Secondary 81% | Prim 100% Secondary 81% | Prim 100% Secondary 82% | Prim 100% Secondary 82% | Prim 100% Secondary 82%
|  | Achieved |  | Primary 100% Secondary 83% | Primary 100% Secondary 82% | Primary 100% Secondary 85% | No DFID contribution
|  | Data source: | EMIS (Education Statistical Bulletin) 2010, 2011, 2012, 2013
OUTCOME | Outcome Indicator 1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14 | Assumptions
The Government of Malawi and Development Partners effectively and efficicently implement the ESIP | % of GoM discretionary recurrent budget allocated to education | Planned | 15.8% | 20% | 20% | 20% | 20% | GoM remains committed to meeting spending targets in educaiton. GoM and DPs re-enforce mutual accountability and strong partnership. MoF and MoEST communicate effectively with shared objectives. GoM continues to improve on its overall Public Financail Management. No major corruption scandals in education. DP funding remains additional to domestic resource commitments.
|  | Achieved |  | 18.7% | 20.4% | 20.9% | No DFID Contribution
|  | Data source | World Bank Public Expenditure Review 2013, Figure 5.1
| Outcome Indicator 2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| % of the education budget devoted to primary education | Planned | 44% | 50% | 55% | 60% | 60%
|  | Achieved |  | 56% | 60% | 55% | No DFID Contribution
|  | Data source | Country Status Report (CSR); Annual Budget, Budget Out-turns, MDPC and MoF statistics for CABS
| Outcome Indicator 3 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| % of funding to the recurrent education budget released by MoF to MoEST within year | Planned | 74% | 80% | 85% | 90% | 90%
|  | Achieved |  | 80% |  | 90.5% | No DFID Contribution
|  | Data source | Country Status Report (CSR); Annual Budget, Budget Out-turns, MDPC and MoF statistics for CABS
| Outcome Indicator 4 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Pupil Teacher Ratio (PTR) in primary school | Planned | PTR 81:1 | PTR 76:1 | PTR 71:1 | PTR 66:1 | PTR 66:1
|  | Achieved |  | PTR 76:1 | PTR 74:1 | PTR 69:1 | No DFID Contribution
|  | Data source | EMIS (Education Statistical Bulletin)
| Outcome Indicator 5 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Student Teacher Ratio (STR) in secondary school | Planned | STR 27:1 | STR 28:1 | STR 29:1 | STR 30:1 | STR 30:1
|  | Achieved |  | STR 23:1, SQTR 52:1 | STR 22:1, SQTR 46:1 | STR 22:1, SQTR 46 :1 | No DFID Contribution
|  | Data source | EMIS (Education Statistical Bulletin)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| £50m |  | £565m | £152m | £767m | 6.5% (derived from ESIP & FTI appraisal)
INPUTS (HR) | DFID (FTEs)
2 FTEs per year (2 Education Advisers on programme costs at 0.8 + programme management staff at 0.4).
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14 | Assumption
Expanded and more equitable access to each level of education (NESP statement, p. 1) | Number of primary school classrooms constructed or rehabilitated per year (10% attributed to DFID) (DFID Standard Indicators) and unit costs of classrooms | Planned | 284 | 500+ | 500+ | 500+ | 500+ | EIMU functions at satisfactory standard when fully integrated into MoEST. National progress on gender equality, including in rural areas. Age of marriage, sexual onset and first pregnancy in girls continues to rise. Economic and social incentives for girls to enter secondary school remains.
|  | Achieved |  | 382 | 274 (EIMU) £18,520, 110 (LDF) £10,900 | 288 (EIMU) £18,520), 1220 (LDF) £10,900, 48 UNICEF £22,350 | No DFID Contribution
|  | Data source | EMIS, Department of Planning and EIMU data
| Output Indicator 1.2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Survival rate to Grade 5 (MGD 2 Indicator 7) | Planned | M 55% / F 53% | M 55 / F 54 | M 56 / F 56 | M 56 / F 56 | M 56 / F 56
|  | Achieved |  | M 60%, F 57% | M 58% & F 59% | No data | No DFID Contribution
|  | Data source | CABS review (EMIS data considered unreliable in 2009-2011), 2012 figures from EMIS
| Output Indicator 1.3 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Transition rate from primary to secondary and number of children supported by DFID in lower secondary p.a. (DRF indicator) | Planned | M 35 / F 38 | M 35 / F 38 DFID B: 4570, G 3991, T 8561 | M 34 / F 37 DFID B: 4937, G: 4433, T: 9370 | M 33 / F 36 DFID B:5565, G: 5,500, T: 12,000 | M 33/ F 36 DFID G: 4,281 (KGIS only)
|  | Achieved |  | M30 / F 30 DFID: achieved | M 30 / F30 DFID: achieved | M 32, F 34 DFID: B 7,518 G: 6,826 T: 14,344 (excl. KGIS) | No DFID Contribution
|  | Data source | EMIS. Quest number: 3463158
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
35% | Difference in numbers of boys and girls in Grade 8 | Planned | 18366 | 18000 | 17000 | 16000 | 16000
|  | Achieved |  | 11908 | 14349 | 18504 | No DFID Contribution
|  | Data source | EMIS
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
See purpose
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14 | ASSUMPTIONS
Improved quality and relevance of education with effective learning (NESP statement p. 1) | Number of primary school teachers trained per year (through IPTE in TTs) (DFID standard indicator) | Planned | 3800 (2008) (7.5% = 285 DFID) | 4500 (9.9% DFID) | 4800 (9.9DFID) | 4800 (10% DFID) |  | Teachers' terms and conditionsimprove to maintain motivation. Teachers trained to serve in rural areas actually do so. Teachers trained /hired in numbers which reduce PTR National focus on literacy and numeracy intensified with strong political commitment. Social and economic incentives for primary school completion intensify. Reforms to reduce repetition are implemented as planned.
|  | Achieved |  | 3456 | 4782 | 4360 IPTE plus 3567 Open Distance Learners | No DFID Contribution
|  | Data source | Education Sector Performance Report (ESPR) 2012/13, p.60.
| Output Indicator 2.2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Primary school completion rate and number of children completing primary education supported by DFID p.a. (DRF Indicator) | Planned | M 55%, F 45% (from EMIS 2008 / census data) | M 56%, F 47% | M 57%, F 49% DFID B: 5638, G: 5812, T: 11450 | M 58%, F 51% DFID B: 9000, G: 9000, T: 18000 | M 58%, F 51% DFID B: 9000, G: 9000, T: 18000
|  | Achieved |  | M 56%, F 47% (EMIS) DFID B: 5810, G: 5215, T: 11065 | M 55%, F 47% DFID B: 6542, G:5646, T: 12188 | DFID: B 11,631 G: 9,979, T: 21,610 | No DFID Contribution
|  | Data source | CSR, EMIS, Quest no: 3463158
| Output Indicator 2.3 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| % pass rate in Primary School Leaving Certificate (PSLCE) | Planned | 69% | 70% | 70% | 70% | 70%
|  | Achieved |  | 69% | 69% | 69% | No DFID Contribution
|  | Data source | EMIS (Education Statistical Bulletin) and MANEB reports
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
35% | % pass in Malawi [Secondary] School Exam (MSCE) | Planned | 38% | 39% | 39% | 40% | 40%
|  | Achieved |  | 53% | 55% | 52% | No DFID Contribution
|  | Data source | EMIS (Education Statistical Bulletin)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (£) | DFID (FTEs) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
See purpose
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14 | ASSUMPTIONS
Improved governance and management of the system with more efficient service delivery (NESP Statement, p.1) | Repetition and drop out rates in primary schools (mean) | Planned | R: 18% DO: 12% | R: 16%, DO 12% | R: 14%, DO 11% | R: 12%, DO 10% | R: 12%, DO:10% | Attraction and retention of high performing staff within MoEST. Strengthening of performance culture within MoEST. Political commitment to improve efficiency and reduce unit costs at secondary level. Annual budget passed by parliament on time.
|  | Achieved |  | R: 17.7%, DO 10.3% | R: 18.8%, DO 10.7% | Repetition Girls: 24.1%, boys 25%, Drop out Girls: 12.3%, Boys: 8.6% | GER: 135% NER: 103%; B: 115,424; G: 115,526
|  | Data source | EMIS (Education Statistical Bulletin), 2012/13 data from ESPR report (JSR) 2013 p.45/46
| Output Indicator 3.2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Unit costs in MK by level of education and/ or % GDP | Planned | MWK 3,000 Primary (8.3%), MWK 30,000 Secondary (83%) | MWK 3,500 Primary(10%), MWK 30,000 Secondary (83%) | MWK 4,000 Primary, MWK 25,000 Secondary | MWK 4,400 Primary, MWK 20,000 Secondary, | MWK 6,500 Primary, MWK 26,000 Secondary
|  | Achieved |  | P: MWK 4494, S: MWK 20972 | P: MWK 6244, S: MWK 28,206 | P: MMK 9186 , S: 39,160 | No DFID contirbution
|  | Data source | EMIS 2010, 2011, 2012, 2013
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
30% | Timing of approval of the annual work programme, education sector budget and procurement plan | Planned | 2009-09-01 | 2010-09-01 | 2011-09-01 | 2012-09-01 | 2013-09-01
|  | Achieved |  | Achieved | Achieved | Achieved | No DFID contirbution
Data source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
See purpose
INPUTS (HR) | DFID (FTEs)
Note: there is a timelag of one year in reviewing the results. (ie. 2013 milestones measure 2012 performance)

## For MESRP II
Flag/Annex B
PROJECT NAME | Malawi Education Sector Reform Programme II
IMPACT | Impact Indicator 1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
Achievement of MDGs 2 and 3 - universal primary education, and gender parity in primary and secondary schools. | Net and Gross Enrolment Ratios (NER and GER) in primary education and number of children supported by DFID in primary school p.a. (boys, girls and total) (DRF indicator) | Planned | NER 83% GER 115% DFID B: 49225, G: 49665, T: 98890 | NER 83% GER 114% DFID B: 123425 , G: 125474, T: 248899 | NER 84% GER 112% DFID B: 135845, G: 140058, T: 275903 | NER 85% GER 110% DFID B: 216827, G: 223016, T: 439843 | NER 100% GER 110% DFID B: 203926, G: 227099, T: 431025
|  | Achieved |  | NER 109% , GER 126%, DFID: Achieved | NER 110% , GER 125%, DFID: B 138510, G 139246 | NER 112%, GER 127%, DFID data not yet available
|  | Data source | NERs from annaul Welfare Monitoring Survey in 2009 and from EMIS (Education Statistical Bulletin) from 2010 onwards
| Impact Indicator 2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| % of girls to boys in primary (DFID Standard Indicator, & MDG 3. WB core indicator) | Planned | Prim 50.1% | Prim 50% | Prim 50% | Prim 50% | Prim 50% | Assumptions
|  | Achieved |  | P 50.1% | P 50.1% | P 50.1% |  | Political commitment to education remains. No major drought, flood, earthquake or other natural disaster. Malawi's economy stabilises as recovery measures take hold. Political stability in the country with democratic and peacful elections in 2014. Partnership principles between DFID and GoM are not broken. GoM remians committed to meeting spending targets on education. Unit costs for education delivery do not continue to rise GoM and DPs re-enforce mutual accountability and strong partnership. MoF and MoEST communicate effectively and with shared objectives. GoM continues to improve on its overall Public Financial Management. No major corruption scandals in education. DP funding remains additional to domestic resources. Harmonised SBS leads to expanded service delivery. MoEST has capacity to absorb funds & deliver ESIP II speaks to MDGs 2 and 3
|  | Data source: | EMIS (Education Statistical Bulletin) from GER
OUTCOME | Outcome Indicator 1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
The Government of Malawi and Development Partners effectively and efficiently implement the ESIP II | % of GoM discretionary recurrent budget allocated to education | Planned | 19% | 20% | 20% | 20% | 20%
|  | Achieved |  | 21% | 20% | 21.6%
|  | Data source | Country Status Report (CSR); Annual Budget, Budget Out-turns, MDPC and MoF statistics for CABS, Malawi GPE Report
| Outcome Indicator 2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| % of the education budget devoted to primary education | Planned | 44% | 50% | 55% | 60% | 60%
|  | Achieved |  | 56% | 60% | 60%
|  | Data source | Country Status Report (CSR); Annual Budget, Budget Out-turns, MDPC and MoF statistics for CABS
| Outcome Indicator 3 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| % of funding to the recurrent education budget released by MoF to MoEST within year | Planned | 74% | 80% | 85% | 90% | 90%
|  | Achieved |  | 80%
|  | Data source | Country Status Report (CSR); Annual Budget, Budget Out-turns, MDPC and MoF statistics for CABS
| Outcome Indicator 4 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Pupil Teacher Ratio (PTR) in primary school | Planned | PTR 81:1 | PTR 76:1 | PTR 71:1 | PTR 66:1 | PTR 72:1
|  | Achieved |  | PTR 80:1 | PTR 76:1 | PTR 74:1
|  | Data source | EMIS (Education Statistical Bulletin)
| Outcome Indicator 5 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Student Teadher Ratio (STR) in secondary school | Planned | STR 27:1 | STR 28:1 | STR 29:1 | STR 30:1 | STR 32:1
|  | Achieved |  |  | STR 23:1, SQTR 52:1 | STR 22:1, SQTR 46:1
|  | Data source | EMIS (Education Statistical Bulletin)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| £61.25m |  | £726m | £152m | £878m | 8%
INPUTS (HR) | DFID (FTEs)
1 FTE per year (1 Education Adviser) + programme management staff at 0.8 total and Governance Adviser (PFM) at 30%
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14 | Assumption
Expanded and more equitable access to each level of education (NESP statement, p. 1) | Number of primary school classrooms constructed or rehabilitated per year (DFID Standard Indicators) | Planned | 284 | 500+ | 500+ | 500+ | 1000+ | Classrooms can be constructed a the required rate and at the required standard either centrally through EIMU or through Local Development Fund. National progress on gender equality, including in rural areas. Age of marriage, sexual onset and first pregnancy in girls continues to rise. Economic and social incentives for girls to enter secondary school remains.
|  | Achieved |  | 382 | 274 (EIMU), 110 (LDF) | 288 (EIMU), 1220 (LDF)
|  | Data source | EMIS, Department of Planning and EIMU data
| Output Indicator 1.2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Survival rate to Grade 5 (MGD 2 Indicator 7) | Planned | M 62.7% / F 65.2% | M 55 / F 53 | M 55 / F 54 | M 56 / F 56 | M 60 / F 62
|  | Achieved |  | M 55%, F 53% | M 60%& F 57% | M 58%, 59%
|  | Data source | CABS review (EMIS data considered unreliable in 2009-2011), 2012 figures from EMIS
| Output Indicator 1.3 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Transition rate from primary to secondary and number of children supported by DFID in lower secondary p.a. (DRF indicator) | Planned | M 35 / F 38 | M 35 / F 38 DFID B: 4570, G 3991, T 8561 | M 34 / F 37 DFID B: 4937, G: 4433, T: 9370 | M 33 / F 36 DFID B:5565, G: 13031, T: 18596 | M 70/ F 60 DFID B: 5094, G: 8693, T: 13787
|  | Achieved |  | M35 / F 38 DFID: achieved | M 33 / F32 DFID: achieved | M 69.4, F 54.2
|  | Data source | EMIS
IMPACT WEIGHTING (%) | Output Indicator 1.4 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
35% | Difference in numbers of boys and girls in Grade 8 | Planned | 18366 | 18000 | 17000 | 16000 | 16000
|  | Achieved |  | 11908 | 14349 | 17304
|  | Data source | EMIS
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
See purpose
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14 | ASSUMPTIONS
Improved quality and relevance of education with effective learning (NESP statement p. 1) | Number of primary school teachers trained and hired per year through IPTE (conventional TT) | Planned | 4000 (7.5% DFID) | 4500 (9.9% DFID) | 4800 (9.9DFID) | 4800 (10% DFID) | 4800 (10% DFID) | Teachers' terms and conditions keep pace with current economic conditions to maintain standard of living and motivation. Teachers trained to serve in rural areas actually do so. Teachers trained /hired in numbers which reduce PTR National focus on literacy and numeracy instensified with strong political commitment. Social and economic incentives for primary school completion intensify. Reforms to reduce repetition are implemented as planned. Improved quality of education improves learning outcomes
|  | Achieved |  | 3456 | 4782 | 4360 IPTE plus 3567 Open Distance Learners
|  | Data source | EMIS and DTED data, SWG reports
| Output Indicator 2.2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Primary school completion rate and number of children completing primary education supported by DFID p.a. (DRF Indicator) | Planned | M 55%, F 45% (from EMIS 2008/census data) DFID B: 2318, G: 2097, T: 4415 | M 56%, F 47% | M 57%, F 49% DFID B: 5638, G: 5812, T: 11450 | M 58%, F 51% DFID B: 8998, G: 9255, T: 18253 | M 58%, F 51% DFID B: 8463, G: 9425, T: 17888
|  | Achieved |  | M 56%, F 47% (EMIS) DFID B: 5810, G: 5215, T: 11065 | M 55%, F 47% DFID B: 6542, G:5646, T: 12188 | Data incomplete
|  | Data source | CSR, EMIS
| Output Indicator 2.3 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| % pass rate in Primary School Leaving Certificate (PSLCE) | Planned | 69% | 70% | 70% | 70% | 70%
|  | Achieved |  | 69% | 69% | Data incomplete
|  | Data source | EMIS (Education Statistical Bulletin)
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
35% | % pass in Malawi [Secondary] School Exam (MSCE) | Planned | 38% | 39% | 39% | 40% | 40%
|  | Achieved |  | 53% | 55% | Data incomplete
|  | Data source | EMIS (Education Statistical Bulletin)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (£) | DFID (FTEs) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
See purpose
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14 | ASSUMPTIONS
Improved governance and management of the system with more efficient service delivery (NESP Statement, p.1) | Repetition and drop out rates in primary schools (mean) | Planned | R: 18% DO: 12% | R: 16%, DO 12% | R: 14%, DO 11% | R: 12%, DO 10% | R: 15%, DO:10% | Attraction and retention of high performing staff within MoEST. Strengthening of performance culture within MoEST. Political commitment to improve efficiency and reduce unit costs at secondary level. Annual budget passed on time. PFM improves system effectiveness / efficiency. Training is well targeted and staff have the opportunity to use new skills. Studies reveal new info & DPs, MoEST willing to act on this. Greater understanding of the sector will lead to improved programming and better results. DPs have tools to respond to findings and MoEST responsive
|  | Achieved |  | R: 17.7%, DO 10.3% | R: 18.8%, DO 10.7% | R: 17.5%, DO (not avail)
|  | Data source | EMIS (Education Statistical Bulletin)
| Output Indicator 3.2 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Unit costs in MK by level of education and/ or % GDP | Planned | MK 3k Primary (8.3%), MK 30k Secondary (83%), MK 780k Tertiary (2147%) | MK 3.5k Primary(10%), MK 30k Secondary (83%), MK 700k Tertiary (1900%) | MK 4k Primary (11%), MK 25k Secondary (68%), MK 600k Tertiary (1600%) | MK 4.4k Primary (12%), MK 20k Secondary (55%), MK 400k Tertiary (1100%) | MK 6.5k Primary, MK 26k Secondary, MK 700k Tertiary
|  | Achieved |  | Figures not avail | P: 11%, S: 68%, T: 1739% | P: MK 6244, S: 28,206, T: Not avail
|  | Data source | CSR, EMIS and GoM budget targets
| Output Indicator 3.3 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
| Timing of approval of the annual work programme, education sector budget and procurement plan | Planned | 2009-09-01 | 2010-09-01 | 2011-09-01 | 2012-09-01 | 2013-09-01
|  | Achieved |  | Achieved | Achieved | Achieved
Data source
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline 2009/10 | Milestone 2010/11 | Milestone 2011/12 | Milestone 2012/13 | Target 2013/14
30% | Greater DP and GoM harmonisation on priority areas through targeted policy dialogue informed by studies on sector performance | Planned | Education FRA | n/a | FRA update | PETS, PEA, FRA completed | New DFID BC in line with DPs/GoM priorities
|  | Achieved | FRA completed |  | Update completed
|  | Data source | DFID budget analysis, SWAp and DP monitoring reports
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
See purpose
INPUTS (HR) | DFID (FTEs)
Note: there is a timelag of one year in reviewing the results. (ie. 2013 milestones measure 2012 performance)