Type of Review: Annual Review

Project Title: AAWAZ STRENGTHENING VOICE AND ACCOUNTABILITY IN PAKISTAN PROGRAMME, Pakistan

Date started:	May 2012	Date review undertaken: 10 March 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / The Business Case or earlier project documentation. / The Logframe / The detailed guidance (How to Note)- Reviewing and Scoring Projects / The most recent annual review (where appropriate) and other related monitoring reports / Key data from ARIES, including the risk rating / The separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Acronyms List
AAC	AAWAZ Advisory Council
ADC	AAWAZ Dehi Committee
ADG	AAWAZ District Group
ADR	Alternative Dispute Resolution
ANP	Awami National Party
ASC	AAWAZ Steering Committee
ATT	AAWAZ Taraqiati Tanzeem
BF	Beneficiary Feedback
BISP	Benazir Income Support Programme
CNIC	Computerised National Identity Cards
DAI	Development Alternatives Inc.
DFID-P	Department for International Development - Pakistan
ECP	Election Commission of Pakistan
EU	European Union
FMIS	Financial Management Information System
GBV	Gender Based Violence
GG	Governance Group
GoP	Government of Pakistan
HMC	Health Management Committee
HQ	Headquarters
ID	Identification Document
IP	Implementing Partner
JI	Jamat e Islami
KP	Khyber Pakhtunkhwa
LG	Local Government
LHW	Lady Health Worker
M&E	Monitoring & Evaluation
MDGs	Millennium Development Goals
MO	Management Organisation
MQM	Mutahida Qoumi Movement
PARR	Policy, Analysis, Research and Results
PEA	Political Economy Analysis
PMLN	Pakistan Muslim League
PMLQ	Pakistan Muslim League
PRM	Programme Review Meeting
PPP	Pakistan People's Party
PSP	Peace-building Support Programme
PTC	Parent Teacher Committee
PTI	Pakistan Tehreek e Insaf
RF	Response Fund
SAP-PK	South Asia Partnership – Pakistan
SDPI	Sustainable Development Policy Institute
SMC	School Management Committee
SNG	Sub National Governance
SPO	Strengthening Participatory Organisation
STAEP	Support to Transparent & Accountable Electoral Processes
TNA	Training Need Analysis
ToRs	Terms of References
UC	Union Council
UK	United Kingdome
USAID	United States Agency for International Development
V&A	Voice & Accountability
VAW	Violence Against Women

Introduction and Context
What support is the UK providing?
Up to £34.3 million programme resources and technical assistance over 5 years (May 2012 to May 2017)

What are the expected results?
During the Inception Period the Business Case Results were refined in the logframe as follows: / Outcome: / Democratic processes in Pakistan are more open, inclusive and accountable to citizens. / This will be achieved by working with experienced locally based organisations, to strengthen opportunities for ordinary citizens to engage in governance and hence increase their influence in policy and legislative dialogues. We will bring these organisations together around agreed programmes of work in 45[1] districts prone to local level disputes and disagreements. These districts will form about 75% of the total districts in Punjab and Khyber Pakhtunkhwa, and 30% of districts in Pakistan. The programme will also work at national level to strengthen the legislative and policy environments for women’s equality. Outputs will in approximately 7000 villages and urban communities in the 45 districts between 2013 and 2017: / increase the safe participation of the excluded (women, ethnic and religious minorities, disabled) in politics and in local, provincial and federal governance structures, enabling them to play more robust roles in decision-making;[2] / enhance tolerance of diversity and strengthen the capacity of communities to resolve disputes and differences peacefully without resort to violence; / enable community members to work constructively together in inclusive ways to demand improved service delivery and to address other local problems; / support a locally based facility[3] to develop a robust evidence base to stimulate debate and dialogue, build popular demand for reforms and changes in elite attitudes and behaviours, and maximise results across DFID programmes.
[1] This is a critical geographical mass to achieve change. Areas to be chosen by AAWAZ team in consultation with virtual ‘synergies’ team led by the Sub National Governance team in DFID Pakistan.
[2] DFID's new strategic vision for women and girls states that 'Increasing the power of girls and women includes enabling their active participation in political processes, and this will continue to be an important area of our work.”
[3] the Policy, Analysis, Research and Results (PARR) facility

What is the context in which UK support is provided?
Over time, the Pakistani State has been unable to allocate sufficient resources to meet the development and security needs of the majority of its citizens especially women, young people, low status castes and religious and ethnic marginalised groups. As a result, over 50% of the population remains poor, under-educated, vulnerable to co-option by radical extremist groups and marginalised from the workings of the state. Gender inequality[4] and violence against women is endemic, and Pakistan has some of the worst social indicators in South Asia[5]. In addition to this, the population is set to increase by nearly half again over the next twenty years, leading to a massive youth bulge in search of jobs and even more rapid urbanisation. / UK support is required to assist Pakistan in becoming a stable, inclusive and tolerant democracy. The situation is urgent: the Millennium Development Goals (MDGs) are unlikely to be achieved if governance and society do not become more open and tolerant. In order to make progress, the social exclusion of the majority of the population from politics and governance must be addressed. Robust representation of the voices of women and other excluded groups in decision-making processes at all levels is required to strengthen opportunities for Pakistan’s resources to be distributed more fairly and equitably and for all its citizens to benefit.
[4] Pakistan is 3rd worst country in the world on Gender Gap Index (2010) by World Economic Forum. Also in UNDP’s Human Development Report (2010) , Pakistan is ranked 134 out of 135 countries on the Gender Gap Index (GDI).
[5] For example, approximately 50% of children are out of school, 60% of women are illiterate and infant mortality is 71 per thousand live births.

Section A: Detailed Output Scoring
This annual review covers the period May 2012 to end-February 2013, during the inception period of Aawaz. The inception deliverables were detailed in the Management ToRs, and included delivery of the inception period set-up activities and the piloting of output level activities in seven districts to test implementation approaches and systems. It was envisaged that the pilots would begin after nine months but DAI offered to initiate them after five, which DFID was happy to approve given the potential for improved lesson learning.
In August, targets were agreed for the pilot activities in the work-plans of implementing partners, but were not at that point aggregated by Output. This information is now available as part of the 3rd Quarterly Progress Report. Both the MO and DFID need to ensure that all relevant information is available at the time of the Annual Review in future.
Inception set-up activities for the MO are not included as an output in the logframe, so instead are detailed in a special section below.

Inception phase
During the inception phase, the Management Organisation (MO) agreed to the following activities as set out in the Terms of Reference:
MO Deliverables	Achievement
Establishment of an office in Islamabad and recruitment of qualified staff;	Office established. The MO has adequate staff in the Islamabad Office. However, the experts seconded from the Implementing Partners have a weak link with the field activities. MO Capacity in M&E needs to be strengthened if it is going to deliver its due role in this area. Work is in progress against this recommendation
Development of an Aawaz Implementation Strategy for delivery of all outputs and achievement of results, including identification of different technical approaches and methodologies, management of stake-holders and establishment of partnerships, and management of political and fiduciary risks; processes for periodic quality review, monitoring and financial accountability (including quality assurance), evaluation and impact assessment, management information and audit systems and reporting;	Implementation Strategy has been developed, with requisite sections. Parts on fiduciary and political risks and audit systems should provide information down to Implementing Partner level. The Due Diligence Report should cover the financial management and audit gaps in the Implementation Strategy. On implementation structures, the Tehsil level Aawaz structures were not envisaged during Inception but will be developed as part of Implementation. The Role of the Aawaz Advisory Committee has not yet been fully utilised - their individual expertise should be brought into future programme design. The Policy advocacy/influencing concept is developed in the Implementation Strategy but practice has been weak and needs to be strengthened through the PARR.
All activities must be clearly linked to progress towards milestones and achievement of outputs in the M&E Framework and the logframe;	Activities need to be more clearly defined and linked to progress towards milestones and achievements in both the M&E framework and the logframe (see Annex 1). Reporting was not by output for the initial two quarters but this has now been rectified, and responsibility for overall monitoring is being established. The 3rd quarterly report tracked progress against outputs for the 4 objective areas and provided clear figures against targets. Narrative stories and case studies are now being collected regularly and options for their analysis are being explored.
Drafting of a costed work-plan for the implementation phase, disaggregated by quarters;	This has been done. Some events budgeted at only PKR500 are local meetings, usually held in people’s houses, with drinks and biscuits. It is important not to distort the voluntarism of community members by providing incentives
Drafting of a detailed budget for full implementation period, disaggregated by quarters; including breakdown of inputs, fees, expenses and linked to outputs in the logical framework;	Costed work-plans for first five quarters have been developed. Indicative costs have been outlined for each year of implementation, as agreed by DAI and DFID. A detailed activity level costed work plan will be provided on annual basis in future
Development of the detailed systems and operating procedures necessary for the manage-ment of the programme and disbursement of funds;	Operating procedures are defined in the implementation and partnership strategy. A Financial and accounting manual has also been developed. All implementing partners are using FMIS systems and conduct monthly budget variance analysis. The implementing partners are subject audit by the MO and also conduct third party external audits. The internal audit function was weaker in two of the implementing partners. This is being addressed. The MO is in the process of strengthening this. Procurement arrangements for the programme (using a third party) have been inefficient. DAI could have managed the procurement contract.
Finalisation of contractual arrangements with all consortia partners	Contracts signed with Aurat Foundation, SPO, SAP-PK, SUNGI – Consortium A and SDPI – Consortium B.
Training for all partner organisations in financial systems and reporting, and in monitoring and technical reporting;	The MO has trained the implementing partners in financial management and reporting. The monitoring function is weak and was divided between the MO and SDPI. This is being readjusted (see above).
Finalisation of imple-mentation responsibilities, deliverables and annual workplans with all partner organisations;	Implementation responsibilities are covered in the Output Manual; detailed activity level work plans with all partner organisations have been prepared for first 5 quarters of the implementation phase, as agreed between DFID and DAI. Detailed work-plans for subsequent years will be submitted annually and will incorporate lessons learnt during previous years.
Finalisation of baselines and milestones in the logical framework;	The logical framework was updated with baselines and milestones starting in 2013/4. Specific targets were established to test implementation and assess progress of inception activities as stated in the management terms of reference.
Development of a detailed Monitoring & Evaluation Framework based on the logical framework indicators and milestones. All indicators must be SMART;	The M&E framework is developed but needs more clarity in terms of defining targets and beneficiaries, (i.e. women and ‘excluded’ groups) for better targeting, tracking, evaluation and impact analysis. See also comments on LFA. In addition, clearer M&E functions must be defined for effective analysis, substantive learning, incorporating of learning into the programme and feedback of beneficiaries. A gender strategy is needed to ensure all activities are gender sensitive (i.e. girls/women, minority women, disabled women/girls); and the M&E framework must track changes in social norms and behaviour that underpin gender discrimination. There is a leap from advocacy to changes in practices and policy that needs to be addressed. Consideration should be given to using tools and approaches that establish clear narratives to present meaningful information and data, and to link the results recorded at output level with the outcome indicators. These links will enable the presentation of clear evidence and attribution of changes at outcome level to Aawaz activities. Activities could benefit from focusing on individuals and then moving to collectives and groups to ensure more meaningful and effective change. This should not detract from achieving milestones. / More emphasis is needed on how to interact with and leverage similar initiatives, especially with government. / The overall narrative is inconsistent; a closer look needs to be taken at all documents to ensure a common approach, clarity of concepts and a programme that is set up to be effectively evaluated.
Development of a partner-ship strategy, highlighting linkages and mechanisms for promoting Aawaz and ensuring maximum synergies across all areas and levels of Aawaz activities, highlighting the work of key state and non-state organisations and donor programmes;	Partnership strategy developed, with potential partnerships identified. The ‘how to’ part is weaker, also clarity on DFID’s role in how these synergies will be facilitated, especially within DFID-funded projects. Possible areas of DFID ‘added value’ should be identified where they exist. / DFID and the MO should develop mechanisms to synergise and share lessons effectively between DFID programmes and those of others, (e.g. Citizens’ Voices and Gender Equity Programme, both USAID, Citizens First programme, Oxfam-Novib, Netherlands.)
Establishment of the PARR, ensuring linkages to relevant institutions nationally, regionally and internationally, and to relevant programmes;	PARR established. Baseline, Risk matrix and Political Economy Analysis were completed. Linkages to other institutions and programmes not yet finalised – see output 4 for more detail.
Finalisation of structures and criteria for use of the PARR Response Fund (RF) and identification of processes for assessment, approval and oversight of funding proposals;	PARR Response Fund established. Eight research grants were awarded and draft reports produced of varying quality. The function of the RF should be clarified to move beyond research and include tools and influencing initiatives that could be used across the programme to achieve the objectives in all output areas – see output 4 for more detail

Progress against these deliverables is outlined in more detail in the inception report. Additionally, the Project Steering Committee and Advisory Committees were set up, the former meeting monthly. The project was launched in inception meetings in Islamabad, Punjab and KP.
In addition to the above, pilot activities began in seven districts in September 2012, with Consortium A partners setting up Aawaz structures and initiating activities at district, union council and village level in Punjab and KP. These pilots were designed to test Aawaz systems and implementation approaches. There were no logframe milestones for the pilot activities (the first Output milestones are for 2013/14). Therefore, for the Annual Review, approved activity targets by Output were used instead. The targets reflect both set-up activities as well as the early stages of progress towards outputs. 2013/14 Output milestones have been included against each Output for reference.

Targets for the formation of the cross output groups that will form the backbone of implementation were met across the seven districts:
- 7 Aawaz Districts Groups (ADG) formed (48% female members)
- 70 Aawaz TaraqiatiTanzeem (ATT, Union Council) formed (47% female members)
- 700 Aawaz Dehi Committees (ADC, village level) formed (4000+ members)

Output 1: Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab
Output 1 score and performance description[6]: / Indicator 1.1: Cumulative number of formal engagements on gender issues between Aawaz forums and political representatives at local, provincial and federal levels / 2012/13 Activity Target (first stage activities bringing together local women and political figures in assemblies and rallies, local, district, provincial and national ): 55 / Progress to date: 64 Target exceeded / For comparison, 2013/4 Milestone for 45 districts: Local 12, Provincial 8, National 4. / Progress to date for 7 districts: Local 16, Provincial 3, National 4 / Indicator 1.2: Cumulative % men/ women reporting reduced tolerance of violence against women in programme districts over the previous year / 2012/13 Activity Target (first stage meetings, and discussions bringing together women and men to identify key issues around VaW and women’s political participation) 840 / Progress to date: 857 Target exceeded / For comparison, 2013/4 Milestone for 45 districts: 10% / Progress to date for 7 districts: Perception survey not yet conducted. / Indicator 1.3: % increase in access of women to public spaces (HMC/ SMC/Aawaz Forums) In programme districts. (This indicator and indicator 1.1 need to capture quality – the indicator is not very informative otherwise) / 2012/13 Activity Target (first stage activities bringing together women in public spaces at village, UC and district levels and campaigns to strengthen political participation) 334 events, 42 radio campaigns / Progress to date: 339 events, 36 radio campaigns Events: target exceeded; Campaigns: target almost met / For comparison, 2013/4 Milestone for 45 districts: 20% / Progress to date for 7 districts: 15% / Indicator 1.4 a) % increase in decision making positions held by women within political parties[7] / 1.4b) Percentage of women in legislative bodies at local, provincial and national levels.[8] [9] [10] / 2012/13 Activity targets: No direct activity targets for this indicator as national and local elections were in process. / For comparison, 2013/4 Milestone for 45 districts: Political Parties 35, National 23%, KP 20%, Punjab 28%, Local xx / Progress to date: To be determined after the election. See above for activity level targets
Progress against expected results[11]: / Activity targets were largely met and it is clear that many women have been involved in Aawaz initiatives at all levels. / OUTPUT SCORE: A. There is substantial progress against activity targets for the Inception Phase. There are narrative examples of attitudes beginning to change around both VAW and political participation although this is early days. Monitoring to date shows that some of the Output targets are not stretching enough and will require revisiting to ensure that clear progress is reflected in 2013/14. / Observations of the annual review team: / In Punjab, the Review team met two Aawaz Districts Groups (ADG), two Aawaz Taraqiati Tanzeem (ATT), one women’s resource group and one Aawaz Dehi Committee (ADC). In KP, the team met two Aawaz district groups, one Aawaz Taraqiati Tanzeem, one Aawaz village group, one women’s resource group and beneficiaries and the Aawaz field team from District Charsadda. / The review team heard from participants that there had been a lot of activity in a short space of time. They met with women who belonged to various Aawaz groups, with around 50% participation in all but one district group, which had only 30% female membership. The challenge of women’s participation in any group should not be underestimated and this alone is one form of women engaging in democratic processes. Particularly at the village level but also at UC level, most women had not engaged in any form of group before and in many cases had had to involve their families in order to overcome barriers to participation. Engaging in these groups was beginning to provide a platform for women to voice their concerns, to learn about women’s rights and entitlements and to develop confidence. It also offers the opportunity for men to listen to women’s concerns, often for the first time. / While segregated groups for men and women were also created in Sargodha, gender sensitisation trainings also facilitated mixed groups. There was more resistance to organising groups and mixed gender gatherings in KP. Aawaz field teams in Mardan and Charsadda dealt with this by forming separate groups for men and women at all levels (double the number of committees). In one instance in Mardan, villagers refused to continue work with Aawaz where Aawaz field teams had taken pictures of activities. However, with perseverance, the field teams seemed to be successful in mobilising women and including them in groups, although still facing challenges at the village level. / Women members of the ADG were found to be particularly vocal in KP, which was unexpected given the conservative environment. In addition, one KP ADG member brought along a Christian woman to attend the meeting. One Christian woman was part of the ADG in Sargodha, but no other minority women were encountered in any of the other district or village visits. / Aawaz has provided information about CNIC cards, which enable holders to obtain health care, schooling and voter cards. In the village group, only 3 out of 15 women had held these cards, but as a result of joining Aawaz, 11 women had applied for CNICs. At UC level, one woman reported that she and her 50 year old mother had applied. Due to the imminent general election and the quantity of spoiled votes in previous elections, ‘mock’ voting has been practiced in some districts in order to prepare women for voting for the first time. However, this raises attribution issues, with SUNGI, SPO and Aurat Foundation also doing similar work under STAEP in Abbottabad. In UC Katwal women claimed that they would base their votes on their investigation of which political representative would ensure that they had gas. However, it seemed that some village members were not completely knowledgeable about Aawaz and the specific activities/objectives it sought to carry out and achieve. / Women in KP were particularly vocal, and said they were now able to demand their rights, i.e., to an education, even from family members. Another woman stated she was able to get her brother to stop beating her by informing him of her rights. / An achievement under Aawaz was that men and women sat together for the first time during an Aawaz festival in UC Baigharam KP for the first time. Others claimed to use the Aawaz platform to speak out against violence against women. This is an area where narrative reporting could provide examples of men and women working to reduce VAW to help track results[12]. / This output focuses on women being better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab. With the present lack of local government structures in Punjab and KP (in the latter, systems just being revived after recently adopting a local governance ordinance), there exist few opportunities for women to engage in formal politics. Many of the active female members of the ADGs were members of the local government in the past and had received trainings under various programmes. / Recommendations: / Ensure women’s political participation at all levels: Should the local government structures resume, the relevance of Aawaz Committees needs to be closely analysed for opportunities for women’s participation, and the programme adjusted accordingly (e.g. women’s leadership training, support to women councillors, public speaking, understanding of local government processes etc.). / Develop clarity on concepts of women’s safety, especially with regards to GBV and VAW: The second aspect of the output focuses on women’s safety. This is being translated by the implementing partners in different ways, from dissemination of information about the Sexual Harassment law to bride swapping to domestic violence etc. The remit and expected changes in this area should be clarified with partners, including specific measures to reduce violence against girls in specific areas. A consistent approach to monitoring is required. / Define and include excluded groups at all levels: At present excluded groups are not formally included in this output, but as they are also members of the Aawaz committees, they should be added to this output activities and in the logframe. More concerted efforts must be made to include minority women in activities (see suggestions on the compilation of evidence and use of narrative reporting). Clear measurement of the scales on which inclusion is being achieved is needed. / Develop mitigation measures for risks women may incur because of their involvement with Aawaz and include in risk register with associated monitoring. There were some reports of blocking and retaliation to the programme and women’s participation. As women increasingly gain their voice, this may become greater, both within the Aawaz committees and with external actors. Membership of Aawaz Committees could expose women to risk of harassment, therefore a clear risk management strategy should be developed to provide guidelines to individuals, committee, and implementation partner organisations to prevent this and prepare committees in the event of an untoward incident. / Systematically engage with religious leaders and government officials for greater impact: One group reported the efforts made to deliberately bring on board religious leaders, government officials and community elders to break down any misconceptions, this needs to be more systematic across the groups. / Manage expectations, especially of women and girls: There is a fine balance to be struck between moving at the wider community’s (and men and boys’) pace and managing expectations of women who have had access to information and a platform to voice their concerns for the first time. Partner organisation staff and committees need to be sensitised to this fact and share experiences in an honest way (including failures). IMPLEMENTATION / Develop a comprehensive gender strategy for the Aawaz programme: A comprehensive gender strategy, beyond Output 1, should ensure that all outputs are gender sensitive and reported on accurately and consistently in monitoring and across all output and outcome areas. / Move beyond social mobilization, to substantive trainings geared towards action: there is a need for more substantive and action oriented trainings for women, providing them with the tools and skills needed to engage with relevant government departments (e.g., engaging meaningfully with/within PTCs) / Streamline activities and strategies, to ensure clarity of contribution vs. attribution: Whilst CNIC and voter registration for women may feed into this output, it could mirror activity that partner organizations are carrying out in the same districts (i.e. STAEP), which makes measurement of the outputs and attribution of impact challenging. This should be clarified in activities and reporting. Joint reviews across DFID governance and elections-related programmes will assist in identifying the added value of each and any duplication of effort. The emphasis should be placed on (managed) synergy and/or on reinforcement of messages delivery through different approaches. / Clarify scope of activities at the federal/provincial level. This output refers to influence at the federal or provincial level, however, it is not clear how Aawaz is operating at these levels at present. This needs to be defined, or removed from the output. / Impact Weighting (%): 25% / Revised since last Annual Review? This is the first annual review / Risk: Medium / Revised since last Annual Review? Y/N / This is the first annual review
[6] All output progress is taken from Annex 1, Progress against the Logframe.
[7] The total number of known female party officeholders in the following 7 parties: ANP, JI, MQM, PMLN, PMLQ, PPP, PTI
[8] http://www.ipu.org/wmn-e/classif.htm (Retrieved on Feb 1, 2013)
[9] http://www.pakp.gov.pk/index.php/members/stats/en/19 (Retrieved on Feb 1, 2013)
[10] http://www.pap.gov.pk/index.php/members/stats/en/19
[11] All progress reported is from the Monitoring report dated March 20.
[12] This could be part of perceptions surveys carried out at intervals to assess changes, e.g. to assess reduction in tolerance of VaW. Software based monitoring and analysis tools could help systematise the collation, presentation and sharing of the progress made.

Output 2: Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa and Punjab
Note there is need to make links across outputs – e.g. number of peacefully resolved disputes that address VaW, discrimination against women, and discrimination against excluded groups (see comments on LFAs). / Output 2 score and performance description: / Indicator 2.1: Cumulative no of community level disputes identified, pre-empted and peacefully resolved by the communities themselves or through government notified ADR mechanisms. / 2012/13 Activity Target (first stage activities bringing together men and women at different levels to identify key issues and activities; training sessions with a focus on youth to encourage non-violence) 791meetings, 94 training sessions / Progress: 755 meetings, 98 training sessions. Meetings: Target not met; Training sessions, Target exceeded / For comparison, 2013/4 Milestone for 45 districts: Identified10,000, Pre-empted 7,000, Resolved 7,000 / Progress to date: Identified 0, Pre-empted 0, Resolved 6 / Indicator 2.2: Cumulative no of excluded group households participating in Aawaz Forums and local level peace building initiatives. / 2012/13 Activity Target (first stage activities bringing together men and women to participate in peace building events at village and district levels): 98 / Progress to date: 81 Target not met / For comparison, 2013/4 Milestone for 45 districts: 1000 (50/50)[13] / Progress to date: District level: 56, UC Level:32, Village Level: 206 / Indicator 2.3: % of people in programme districts who consider Aawaz community cohesion mechanisms to be credible and effective / 2012/13 Activity Target: (first stage activities publicising Aawaz and explaining concepts of non-violence) 17,700 newsletters and collection of material; 14 orientation sessions with local correspondents / Progress to date: 26,235 newsletters and collection of material; 13 orientation sessions. Newsletters – target exceeded; Orientation – target almost met / For comparison, 2013/4 Milestone for 45 districts: 1% / Progress to date: Perception survey yet to be conducted
Progress against expected results: / There have been significant levels of activity in this Output and 50% of targets have been met or exceeded. There is, however, a lack of conceptual clarity across three key underlying factors: i) dispute resolution versus dispute mediation and the roles and understanding of Aawaz partners; ii) whether or not to work with traditional dispute resolution mechanisms (such as jirgas or panchayats); iii) classification of ‘excluded groups’ under this output and how will their participation be measured. / OUTPUT SCORE: B. Activity level targets for September 2012 to end February 2013 were partly met. The targets reflect both essential set-up activities as well as the early stages of progress towards outputs. Successful examples of dispute mediation include issues such as a Peace committee successfully challenging bad police behaviour, resolution of property disputes and tent burning, and police and local communities working together to reduce crime. However the lack of conceptual clarity (noted above) could impede progress towards achievement of the Output. Clearer definitions are needed of what is expected, and expectations in relation to participation of excluded groups must be outlined. Some of the Output targets may not be stretching enough and will require re-working. / Observations of the review team: / The escalation of disputes is common and the need to nip these in the bud and to change people’s mind-sets towards respect and understanding of others was noted across the districts visited. / The output has already seen some successes with disputes concerning marriage, water and property being dealt with by Aawaz committees. There appears to be space for pre-emptive, low level dispute mediation, with the Panchayat and Jirga systems dealing with more serious situations and the musalihat anjumans (alternative local government dispute resolution mechanisms presently non-functioning). Should the latter be reinstated, there were different opinions as to how Aawaz should engage. Along with other formal structures, this could be an opportunity for Aawaz forums to refer cases beyond their remit, or to build the capacity of the musalihat anjumans, as these did not always function effectively. However, the work may overlap, with Aawaz forums potentially undermining the musalihat anjumans. Panchayat and Jirgas have limited or no women’s representation, thus a clear modus operandi will be required. Partners had different views on this question. / Recommendations: / Engage and work with traditional and government structures: There was strong resistance to working with existing traditional structures for some implementing partners at HQ level. At local level there appears to be a more practical approach, recognising the need to bring all structures on board with Aawaz to avoid possible backlash and undermining. Involvement of religious leaders was sporadic across the committees visited. The approach needs to be systematic across the programme, and include more clarity within the consortium (i.e. dealing with panchayats/jirgas) and common strategies and interventions to achieve outputs. Engaging positive religious leaders in Aman committees may strengthen Aawaz’s message. / Increase trainings on dispute mediation, especially at the village level: There was a question over whether the committees had the skills to deal with religious disputes and disputes between classes. The latter was partly dealt with by the village forum using the UC or district level to assist with disputes beyond their scope. This needs more specific training in future. / Manage expectations of beneficiaries: Some disputes can only be dealt with through formal systems. As will be dealt with in output 3, this may not always result in change and developing strategies to deal with this and managing community expectations will be necessary. / Create effective monitoring mechanisms for impact analysis: The sustainable nature of dispute resolution may become an issue as time goes on – especially in domestic or neighbourhood issues. Honest monitoring of this will be important for the Aawaz committees to have a lasting impact and to learn from their experiences and to develop strategies to deal with disputes. / Engage women to be included/ accepted in traditional dispute mediation structures: Contrary to traditional Jirga and Panchayat structures, Aawaz Aman committees also include women. However, it was noted in KP that there is potential for women (especially elder women) to be gradually included in wider decision making/dispute mediation structures. This should be encouraged as a specific activity under this output. / Emphasise dispute mediation/facilitation rather than resolution: To highlight support to government structures it may be useful to reinforce dispute ‘resolution’ as a courts matter, and dispute ‘mediation’ as an Aawaz activity. / Map conflicts in target districts: Conflict mapping of the target districts will help respond to the local needs/tensions in a coherent and informed manner. / Impact Weighting (%): 25% / Revised since last Annual Review? This is the first annual review / Risk: High / Revised since last Annual Review? Y/N / This is the first annual review

Output 3: Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa and Punjab
Output 3 score and performance description: / Indicator 3.1: Number and types of issues raised by the local communities through Aawaz Forums with increased participation of women, girls and other excluded groups / 2012/13 Activity Target (first stage activities bringing together men and women at different levels to form groups, identify key issues and activities): / 812 meetings / Progress to date: 614 meetings Target not met (See below comment on security situation) / For comparison, 2013/4 Milestone for 45 districts: 2,000 / Progress to date for 7 districts: Education:4; Health: 5; Political Participation:4; Access and control over resources:5; Gender: 5; Poor law and order situation: 3 / Indicator 3.2: Number and types of service delivery outlets improved in the areas of health, education and other priority areas benefiting women, girls and other excluded groups / 2012/13 Activity Target (first stage activities to train citizens in skills needed to address poor local authority performance): 158 training and orientation events / Progress to date: 138 Target not met (See below comment on security situation). Few issues were expected to be resolved at this early stage; there are, however, documented cases of early successes in resolving service delivery problems (See below) / For comparison, 2013/4 Milestone for 45 districts: Education/ Health issues addressed 900, Other issues addressed 450 / Progress to date: Education/ Health issues addressed 3, Other issues addressed 4 / Indicator 3.3: Percentage of women and excluded households satisfied with the quality of services has improved as a result of Aawaz accountability initiatives / 2012/13 Activity Target: Target not set as too soon in programme cycle / For comparison, 2013/4 Milestone for 45 districts: 5% / Progress to date: perception survey yet to be conducted
Progress against expected results: / Activities under this Output are already starting to contribute to positive results (see below). However, four out of seven pilot districts were in KP, and difficult security circumstances in these districts particularly affected achievement of quantitative activity targets under this Output. The months of November, December and January saw escalated sectarian violence (Muharram days included), bomb blasts, sporadic firing and target killing in D.I. Khan, Mardan and Charsadda. This led to extended winter vacations in schools and education departments, which affected Output 3 work. / OUTPUT SCORE: A Activity level targets for September 2012 to end February 2013 were not all met, mainly due to the security situation. The targets reflect essential set-up activities and training, as well as the early stages of progress towards outputs. However, where activities were possible, there are already a number of successful examples of district authorities responding to citizens’ raising of local problems: / Teacher’s absenteeism addressed (Shabi Kheil) / BISP and Watan cards obtained for poor people (UC MC-1) / Literacy centres opened (UC Tarnab; Hisara Yasin Zal) / Landlord blocking of road overturned (Basti Bhatian) / Water filtration plant repaired (D I Khan UC 1) / Health officials informed the public about availability of health services (Charsadda) / Observations of the review team: / Improving services, particularly in education and health is a priority of the Aawaz committees. Successes have been achieved in improving female enrolment in schools by the employment of a female teacher at a co-ed school and by organising transport for girls to a girls’ school in a neighbouring village. The registration of women (and men) for CNIC cards under output 1 has the additional benefit of enabling holders to access health and education services. In one UC, 15 women had been helped to successfully apply for social welfare. / There were reports of problems that were beyond the scope of the village or UC committees being raised through the Aawaz district forum where there is greater gravitas. This clearly links with supply side funding that DFID is providing through the government of Punjab and KP, although there wasn’t a full understanding by partner organisations of what these programmes are or where they were active. Through MO and Steering Committee, briefings should be arranged for DFID supply side programmes to provide district wide information wherever possible. This needs involvement of other DFID programme staff and should be implemented at partner level and between MOs of the various programmes. / Given the richness of examples emerging to date, strong and comprehensive monitoring and reporting will be needed in order to capture narrative as well as data, and to contribute to the Theory of Change. / Recommendations: / Synergise with other relevant programmes: Mapping of DFID (and other relevant donor programmes) in Aawaz programme areas would enhance the potential multiplier effect of the programme and inform Aawaz forums as to what opportunities are available in their area. Some efforts have been made to do this by the DFID Aawaz team, but it requires broader buy-in / Work with government structures (PTCs, LHW groups): There was some evidence of Aawaz fora linking with school management committees and health committees, but this should be formalised so that structures are strengthened and not undermined by Aawaz. Co-ordination with other DFID programmes is essential / Prioritise demands systematically through community scorecards: Some Aawaz committees had already listed demands and presented them to local government. Demands were not prioritised and were unlikely all to be met. Community scorecards would help make prioritisation more systematic and score all issues so that Aawaz fora can monitor progress. This would have the added advantage of keeping motivation high as each issue is addressed, rather than the potential failure of a long wish-list. If score cards are used then systems must capture on-going changes and be consistent with the indicators and milestones set in the LFA. / Communities could be encouraged to take action to resolve their own problems rather than expecting local authorities to respond to all requests. / Mitigate risks to women involved in the programme: In two different communities there were reports of harassment of women who had spoken out publically against the poor delivery of services in their area. This is a serious concern, which needs to be carefully managed and risks carefully assessed. The use of anonymous texts to public websites or more anonymous media coverage could be considered in order to avoid this. There is a possible link to the Chief Minister’s initiative under SNG in Punjab / Engage female teachers and LHWs at all levels for stronger linkages: Whilst we met lady health workers and teachers in UC level Aawaz committees, it could be beneficial to invite them to be members of all UC Aawaz committees so that maximum linkage can be made through members demands, and also though committees assisting with problems raised by LHW and teachers. / Focus on substantive, action oriented trainings, moving beyond mobilisation: Linking to output 1, Aawaz must move beyond awareness raising and social mobilization and provide training for women who are being socially mobilised. For example, more women must be trained to liaise and interact with relevant education and health offices for action. Rigour in M&E will help partners identify ways to amass evidence needed to support arguments for change. This is a clear SDPI/PARR area in which to work with partners. / Ensure that i) monitoring captures and aggregates examples of positive outcomes ii) that successes are tracked to follow-up on sustainability and iii) findings are shared across the partners. / Impact Weighting (%): 25% / Revised since last Annual Review? This is the first annual review / Risk: Medium / Revised since last Annual Review? Y/N / This is the first annual review
[13] (No less than 50% participation of women and excluded groups

Output 4: Improved evidence generated, synthesised and communicated/ championed to political leaders/ elites in Khyber Pakhtunkhwa and Punjab
Output 4 score and performance description: / Indicator 4.1: Cumulative no of evidence-based policy studies (e.g. on inclusive governance, peace-building and accountability) shared with politicians and decision makers / 2012/13 Activity Target (first stage activities to develop baseline studies and PEA from which to produce baseline indicators for logframe and for policy studies) 3 (not finalised) / Progress to date: 3 Target partially met / 2013/4 Milestone: 2 / For comparison, 2013/4 Milestone for 45 districts: 3 underway / Indicator 4.2: No of policy changes/reviews advocated for with provincial and decision makers, national legislators and politicians. / 2012/13 Activity Target: (first stage activities to develop Response Fund studies and Analysis of M&E data) 1 / Progress to date: 1 (RF) underway but policy briefs not finalised; M&E analysis not addressed yet Target partially met / For comparison, 2013/4 Milestone for 45 districts: KP 2, Punjab 2, National 2 / Progress to date: KP 0, Punjab 0, National 4 (underway but not completed) / Indicator 4.3: Number of organizations capacitated and commissioned in carrying out research and advocacy initiatives to inform Aawaz and other programmes on selected themes / 2012/13 Activity Target: (first stage activities to commission RF studies and train organisations) 8 organisations / Progress to date: 8 studies produced of variable quality; 0 organisations trained Target partially met / For comparison, 2013/4 Milestone for 45 districts: Commissioned 16, Trained Organizations 4 / Progress to date: Commissioned 8, Trained Organizations 0
Progress against expected results: / Numerical targets have been broadly met in terms of drafts produced (e.g. political economy analysis, baseline, stakeholder analysis, risk analysis) but finalised versions not yet produced after feedback. The quality of the documents is variable and links to the rest of the programme are unclear. / The PARR Response Fund commissioned 8 studies, which have been conducted and peer reviewed. Final revisions are still on-going and quality is variable. Study areas and successful proposals were agreed by the Steering Committee. Future use of the RF needs to relate more closely to implementation and to achieving the programme objectives – see Aawaz vision and plans. / OUTPUT SCORE: C The review team had some concerns about this output, particularly around the clarity of the vision, M&E roles, and the quality and timeliness of outputs. The team recommends a review of the PARR to determine functions and added value and to help ensure PARR’s potential to maximise results for Aawaz. / Observations of the review team: / There are almost too many long documents to deal with under PARR, and the links between them and implementation are not always clear – e.g. Baseline Policy Briefs, the PEA and the Response Fund studies. Processes in some cases have been rushed – e.g. the M&E guidance, the Response Fund, the Baseline exercise – and quality has suffered (RF studies). Final versions of studies are still awaited. / The advocacy/influencing part of the programme, including the PARR response fund, was unclear. There was confusion over whether the research products should be academic or provide useful information for Aawaz/other partners/influencing. Strategies for dissemination, communication and influencing were not clear – nor the mechanism for operating at Provincial level. Output indicator 4.3 states that organisations conducting research would benefit from capacity building, but grantees reported that it had been a simple contractual arrangement. / The PARR function is clear in the programme design but so far there is a confused conceptualisation of roles during implementation. A review of structures set up to date is needed and implementing partner representatives should work with the PARR to help to define needs for research and support towards achieving the communications and influence objectives of Aawaz at output and outcome levels. So far, there is limited evidence of PARR analysis adding value to Cons A activities. / The PARR review should also define PARR contributions to M&E, as currently there appears to be an overlap with the function of the MO in terms of verifying that activities have taken place and commenting on the quality. It was expected that the PARR would identify relevant grassroots issues to take forward issues to influence policy change. For example, the review team heard how a Christian boy was provided a place in a technical training college They were not clear how this issue could have been further developed and discussed with all technical training colleges so that it doesn’t remain an isolated incident. / The Response Fund was rushed, and should have focused on clearer themes, with objectives showing how the response fund studies would feed into Aawaz activities. The studies would have been more useful if they had focused on the pilot districts so that they could have directly linked to and benefited Aawaz thinking. RF themes were decided by the Programme Steering Committees, but it may also have been useful to have asked Programme Review Committees (field teams) for views. This could also support achievement of a stronger cross-partner team approach. Timeliness was poor. / Recommendations: / Ensure that all PARR analysis/outputs have demonstrated links to Aawaz implementation and/or overall objectives and are of good quality. This will help to i) build the partnership between different Aawaz organisations, ii) ensure the relevance and usefulness of materials; iii) add an extra peer review dimension to improve quality, and iv) strengthen the potential for sustainable reform. / Clarify monitoring and evaluation roles in terms of substantive learning and added value: The PARR has the potential to yield essential evidence-based results for advocacy and influencing, and for planning within Aawaz. The M&E functions of PARR should thus be clarified in relation to the DAI function. The Review Team recommends that DAI monitor partner activities in accordance with partner workplans, and that the PARR review partner reports and select common issues for further analysis and possibly research. This can be backed up by field visits as necessary. The PARR should focus on more substantive and strategic learning to add value to exisiting knowledge and create useful links with other DFID V & A/research funds, i.e., Ilm Ideas and other programmes. / Improve M&E framework: The M&E system needs to be improved so that reporting against outputs is clear. The issue of an Aawaz website needs to be clarified and the MO tasked with developing and maintaining it. Suggestions on how this can be achieved are made throughout this AR. / Clarify advocacy/influencing function: Provincial level advocacy/influencing is unclear – the Consortium A partners who have a presence and relationship at this level might be best placed to take this forward, in co-ordination with the PARR. This should also be coordinated with any national level advocacy/ influencing being carried out by the PARR or commissioned under the Response Fund. Whilst there is a plethora of programme documents, there appears to be a lack of a clear advocacy/influencing/communications strategy for Aawaz as a whole or the PARR in particular. This should include recent evidence on social communications which notes that messages within already accepted programmes are more effective than one off campaigns (see 3.1 below). This is critical if Aawaz is to achieve genuine reforms and changes for its stakeholders. / Clarify function and purpose of the Response Fund: The Response Fund needs to be clarified in terms of the purpose of outputs and in line with a clear advocacy/influencing/communications strategy (along with monitoring of the resulting change). The fund should be used to commission high quality research products to build the evidence base, and to take forward initiatives to maximise results or leverage changes (e.g. engaging lawyers to take forward the technical college issue highlighted above). In addition, PARR staff should work closely with Consortium A partners and response fund recipients to ensure a clear focus and to help develop methodologies to strengthen research. Some grantees noted that they would prefer more of a partnership approach in working with SDPI on research products. / Clarify roles of and relationship between the two Consortia particularly in relation to M&E activities and analysis, and use of evidence: the links of the two Consortia and their effect on the beneficiaries require further definition. In particular, ways in which research results are shared with beneficiaries and their reactions taken on board are not evident. / Impact Weighting (%): 25% meetings. / Revised since last Annual Review? This is the first annual review / Risk: Medium / Revised since last Annual Review? Y/N / This is the first annual review

## Section B: Results and Value for Money.
1. Progress and results

1.1 Has the logframe been updated since last review? / Yes, it was updated after the Baseline studies. Further recommendations for improvement are outlined in the logical framework set out in Annex 4. Other suggested changes are highlighted in the beneficiary feedback (see 1.3 below). / Monitoring reports should be organised by output so that progress towards the agreed results can be tracked. (Already implemented) / 1.2 Overall Output Score and Description: B / Aawaz has been scored against its inception deliverables and activity targets for 2012/13. The activity targets cover progress over 5 months in 7 districts. The review highlighted areas of success and areas for improvement. The performance against 2013/14 output milestones and achievements has been included for comparison. The next annual review will be clearly scored against the 2013/4 milestones, which are based on implementation in up to 45 districts. / Progress to date indicates that Aawaz implementing partners are very capable and well positioned to effect an ambitious scale-up to 45 districts over the next 15 months. This scale-up is essential to creating a critical mass of calls for reform which will support the achievement of Aawaz objectives. / 1.3 Direct feedback from beneficiaries / On top of the Annual Review Team meeting with beneficiaries of the project, there was a comprehensive beneficiary feedback study in January. The report indicates that it was too early to gauge full feedback, since implementation had begun only 4 months earlier. However, the study highlighted the need to revisit/ refine the logframe better to capture changes in women’s attitudes; dispute resolution/ mediation by men vs. women; and the number of issues identified and addressed. The report notes that there could be handholding by Consortium A staff – beneficiary dependency – although this is difficult to judge after 4 months. Membership of the groups needs to be more selective. Roles and links between the two consortia are unclear – especially with regard to how the research links back to the beneficiaries. The BF recommended the ARM to meet with the poorest of the groups, as their voices were not heard during the BF study, but this was not possible due to time constraints and logistics. / Other recommendations included sensitisation for men in groups to reduce patronising behaviour with female counterparts, and training for group members to engage effectively with politicians. Linking with other organisations /projects working for voter registration/CNICs was stressed. Committee structures should be stream-lined as too many committees may distract from focus. Guidelines should be developed across partners to agree on attribution issues and to train Aawaz communities to differentiate between work done under Aawaz and past work by Aawaz partners/others. Knowledge of women’s legal rights and laws should be contextualised and women need to be comfortable with knowledge of their legal rights and getting help without fear of backlash. Links between research reports and audiences need to be clarified. Messages should reach grassroots communities. / The BF exercise will be repeated, and planned perception surveys will help to triangulate information. In addition the team met around 80 project beneficiaries and the feedback has been incorporated into the main body of the AR.
1.4 Summary of overall progress / Aawaz has started strongly and has achieved a lot in a short time. The fact that positive changes for communities are already being to be demonstrated is very encouraging. The innovative model programming (combination of Cons A & B) has the potential to be adaptive/flexible, lead to real time learning and leverage critical changes for the poor. Partners are committed, knowledgeable and hard-working. / The programme has provided a boost to human rights organisations at a time of despondency with increasing extremism, corruption and political wrangling. It has created an opportunity for partners to work together in one platform, and has also strengthened some institutions by expanding their reach from District level down to union and village level – leading to greater opportunities for people to engage in democratic processes and providing partners with grassroots experience and reach. / There is evidence of learning from inception phase: eg there has been a streamlining of the number of sub-committees whilst at the same time, the Tehsil level has been created. There has also been agreement to establish a ‘district opening meeting’ to clarify the project and the various partners. / There are already some reported results e.g., improved school enrolment by girls and boys, improved irrigation water access, resolution of property, land and domestic disputes and the registering for CNIC and voter cards. It will be important to monitor the progress of these activities, to determine the lasting nature of successes, report any backlash, manage expectations and include spoilers and blockers in the programme. Reporting, learning and sharing difficulties are important aspects of the programme which could be enhanced by exchange visits between Aawaz forums. / Working with local voluntary groups with a good and trusted reputation assisted women being able to take part.
1.5 Key challenges / The absence of local government in Punjab and in KP is an unknown factor at present and consortium partners need to strategise and follow closely developments in this area for opportunities and synergies. / Due to this absence, decision-making takes place at the provincial level. It is therefore important for Aawaz to develop stronger and more formal communication and coordination mechanisms at provincial levels. (Focus currently on district, union and village groups, but links to provincial decision making bodies are weaker) / Most of the Aawaz fora being set up are new, especially at UC and village levels. This leads to questions of sustainability and an exit strategy for these informal structures. This is a mismatch between DAI/DFID discouragements of setting up new structures with the partner activities. Ensuring that these structures work closely with formal structures (local government, school management committees, health committees) as well as existing traditional structures is important to ensure the results of the project are achieved and sustained. There is already evidence that those not involved in the project can work against it - e.g. a mosque refusing to advertise an Aawaz event, members of conservative Islamist groups issuing direct threats to women, as well as constructive engagement by some Aawaz committees to engage with potential blockers and spoilers. / The legislative and social norms around women and excluded groups are clearly a challenge for meaningful participation. Excluded groups were less represented in Aawaz committees – it is important that partners are utilising the same definition and challenging committees to review their composition in light of this (2 UCs didn’t recognise that there were any excluded groups in their UC). Opening meetings with readings from all religious groups represented (not just readings from the Q’ran) was welcomed in one district. / There was an initial lack of coordination with government at Provincial level in Punjab, although this has begun to be rectified in the last six months. The MO will have a role in taking this coordination forward after the elections. Closer coordination with the government should produce a greater multiplier effect. The KP government Planning and Development Department intends to bring all donors/projects onto a single platform, to facilitate mapping, information sharing, and coordination whilst reducing the risk of duplication. / It was noted that scaling up the project will require increased implementation capacity for consortium A partners. This will also require articulation and understanding of the programme concept at all levels. Learning from each partner’s areas of strengths and arranging exchange visits for the Aawaz committees will help strengthen capacity. / Given that the Consortium A partners have been working on similar issues previously, there may be difficulties in attributing results to Aawaz. / Managing expectations at all levels is crucial for the programme to maintain momentum over five years, including the sustainability of dispute resolution and the question of whether public and media pressure is enough to bring about change in services despite corruption and limited accountability. / There was a request for the Aawaz committee members to have ID cards in order to give members more standing and to reduce misunderstandings and encourage women to join. Other DFID programmes have requested this too but it cannot be allowed. / Performance of the procurement agent has been weak. The Management Organisation and consortium partners report that no guidelines were received at the start of the process from agent; requested specifications were not followed; costs appear not to have been kept down; deadlines were not met; and a number of the goods received have been faulty. This happened despite regular communication including daily meetings. Procurement processes will require close monitoring and robust follow-up during implementation phase. / Forecasting was initially weak mainly because consortium partners lacked experience on projections. Costs were overestimated; Communication between finance, monitoring and evaluation, and implementation teams was weak during initial inception phase but improved over the last quarter of the period. Realistic forecasting from MO and partners will be critical for the implementation phase. / While the security situation is fragile throughout Pakistan, it is of particular concern in KP. In the recent past, militancy and extremism have resulted in a shrinking space for development initiatives and have hampered implementation efforts. Some Aawaz members reported difficulty in carrying out activities, especially with regard to women’s and service delivery activities, in both Mardan and in Charsadda. Expansion of Aawaz in other districts must include careful assessment of local security situations to assess risks related to implemention. In addition, harsh weather conditions and mountainous terrain of the KP have impacted organization of village level activities.
1.6 Annual Outcome Assessment / The outcome of the project is: Democratic processes in Pakistan are more open, inclusive and accountable to citizens. / After only 9 months of inception and 5 months of pilot implementation it is too soon to comment on achievement towards this outcome. Successes to date have been encouraging: Outputs 1 and 3 are clearly on track, and Output 2 is already demonstrating added-value that will be further strengthened when conceptual clarity is achieved. With further investments in planning, management and oversight, a more focused Output 4 is judged likely to be able to fulfil its critical role in maximising Aawaz results to achieve lasting changes

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes. Despite a slow start the programme was able to meet a revised projection of £3.2m while delivering value for money. The original forecast of £4.7m was reduced following in depth due diligence of consortium partner budgets by the Management Organisation. / 2.2 Key cost drivers: The main cost driver of the programme is salaries. The Management Organisation has developed salary rate cards for consortium partners to ensure fees are set at the right level. Competition between DFID and other donor Management Organisations is a real risk and can affect staff retention. Consideration should be given to reviewing salary rates across DFID Management Organisations to ensure they are standardised. (NB. this is happening in Governance Group. Fee rates for AAWAZ were shared with two newer GG projects: SNG and PSP. GG Project Managers are taking forward). / 2.3 Is the project on-track against original timescale: Yes. Inception completed on time. Pilots in 7 districts delivered earlier than planned during inception phase.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There are two pieces of evidence which are highlighted below, which are relevant for the recommendations of this annual review. / Aawaz should consider social communications as part of its advocacy strategy, either creating something new, or linking up with existing popular soap operas or radio shows to present messages regarding attitudes towards women and excluded groups, and in terms of political participation, violence and resolving disputes. The Girl Hub has documented evidence that social communications (or social marketing) can be more effective at changing behaviour than one-off campaigns. There is need to recognise that the Aawaz vision is about achieving changes in the lives and roles of women and other marginalised groups which require policy changes through advocacy and influencing, but as significantly assisting groups acquire the tools, confidence and status they need. / Review of this evidence reveals the following lessons about what makes social communications more or less effective in delivering behavior change goals: / Mass media has delivered changes in knowledge, attitudes and behaviour, from ‘The Archers’ to Brazilian telenovelas. / Drama is an effective way to engage large audiences and address relevant issues (Aawaz partners are already implementing drama/theatre activities). / Behavioural interventions are most effective when they are relevant and entertaining, when they provide models of desired behaviors, and when they are linked to social and cultural narratives. / Modeling through mass entertainment is not sufficient. Effective strategies need to factor in the opportunities and obstacles found in communities. / Both media and interpersonal intervention activities should be linked to existing resources in the community and, where possible, provide increased access to preventive services, supplies, and other support. / Duration of listening is associated with more positive outcomes than the other measures. There may be a stronger correlation between exposure to these programs and behaviour change. / Using mass media alone can stimulate conversations among listeners, which create opportunities for social learning as people, individually and collectively, consider new patterns of thought and behaviour. / Social conversations about educational content create learning environments in which people evaluate ideas, consider options and identify steps to initiate social change. Listening together is important. / Strategies for dealing with resistance to change need to be built in, e.g. engaging religious leaders, or men and boys. / This evidence points towards building a long-running and sustainable campaign which can sustain different story strands over a long period of time, address various themes relevant to the desired behaviour change, and spark conversations within communities. / David Booth (ODI) has been researching whether we are ‘overstating the claims on social accountability’. Evidence emerging from his work on Governance and Transparency Fund projects would support the argument that targeted social accountability initiatives can work. However, current research also suggests that these social accountability successes do not develop in a vacuum, but tend to be linked with shifts in incentives from the supply side. In other words, progressive change seems to happen as a combination of both top-down and bottom-up pressures. This links up with recommendations to link demand side focus explicitly with DFID (and other) supply side activities. / 3.2 Where an evaluation is planned what progress has been made? / An independent and comprehensive programme evaluation is part of both the business case and the implementation work plan. A baseline has been produced in the inception phase. Regular M&E framework, beneficiary feedback loops, quarterly rapid and annual full-scale surveys are in place to follow up on the baseline. A Mid-term evaluation is programmed between second and third annual reviews.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Except Output 4, the output risk ratings are not defined in the LFA. The AR mission has attempted to define the risk ratings on the basis of assumptions provided each output in the LFA against. The risk ratings are as follows: / Output Risk Rating / Output 1 Medium / Output 2 High / Output 3 Medium / Output 4 Medium / 4.2 Assessment of the risk level / The overall assessment of the risk level is a medium. The breakdown output wise is given below: / Output 1: The security situation close to and during elections will be a large predictor of female participation in the elections. Increased incidents of terrorism in Karachi, Quetta and KPK are indications of violence during elections. However, the decision by ECP to declare void election results in areas where female voter turnout is less than 10 per cent is a positive move that could prevent systematic exclusion of women from elections. After the general elections 2013, the revival of the LG system will also play a significant role on participation of women in politics. Local level politics served as a training ground for female politicians from non-traditional political backgrounds, many of whom then became social activists and community leaders in the post local government period (2007). Leading political parties (PPP, PML-N) have supported legislation on women harassment and taken measures to increase female participation in civil services (women development package of GoP). On this basis the risk level associated with Output 1 is medium. / Output 2: The revival of the LG system particularly its ADR mechanisms (Musalihaat Anjuman) will have implications for Aawaz Committees. In the event of the revival of LG Act 1979 (likely) the relevance of Aawaz Committees will remain but that will not be the case if LG Act 2001 is used (unlikely). Multiple structures at the same administrative levels may create friction and reduce efficacy of Aawaz Committees. Influence of conservative islamist groups in Southern Punjab and KPK will also impact the remit of Aawaz Committees on sectarian issues. Addressing this requires intensive training of Committee members and sensitization of the wider community. Also Committees face risks of political takeover: as there is no policy barring membership of individuals with strong political affiliations, committees could become politicised and reduce wider confidence in their objectives/motives. Based on these observations the risk rating for Output 2 is high. / Output 3: The future of the local government is also relevant to this output, the level of accountability and response to public concerns is correlated with public representation at the local level. Continued success of the Aawaz committees will depend on its composition at the district level (that help bridge the link with concerned departments) and performance of the concerned departments on commitments made to the communities. This is a cyclical risk where performance delivery is contingent upon committee composition and linkages and vice versa. Guidelines, ToR and criteria for committee composition are given in the Output Manual and these are being revisited in the light of lessons learnt during inception phase. Risk level linked to output 3 is medium. / Output 4: The topics selected for research and policy advocacy will be contingent upon the political environment and government policy – especially on issues of accountability and peace building. While these issues are high on the agenda of the political parties going to elections, the real determinant of receptivity would be the core agenda of the next governments. Also the output will not meet its objective if the information is only created and disseminated at federal and provincial capital levels; information transmission lines need to be developed to local levels with the intent to both receive and inform. The risk level associated with output 4 is medium.
Risk of funds not being used as intended / DAI operates its core corporate functions such as finance, project management, and internal audit operate from its Islamabad office and is subject to extra scrutiny from the London office. DAI has designed and implemented financial protocols (process and procedures), and also shared the financial manual with the implementing partners. It has oriented the finance department staff across the consortia on DAI financial policies and DFID reporting mechanism/systems. This involved trainings and focused workshops on budgeting and financial management. DAI has also conducted due diligence of its implementing partners in accordance with DFID rules, but the report did not highlight the criteria DAI used for Due Diligence. / On the institutional structure side both DAI and its implementing partners have finance sections, procurement sections, and external audit arrangements. One partner did not have an internal audit arrangement, but this has been rectified. The management boards of all the implementing partners conduct financial oversight through the Finance and Audit Committees. DAI and its partners are using FMIS and carrying budget variance analysis on a monthly basis, which allows strong financial monitoring and management. Procurement using an external agent appears to have been problematic. At the local partner level, capacity in budgeting, financial management and procurement needs to be further developed. / A robust process for checking payments is in place i.e. 40-60% sampling of receipts. Payments are disallowed if sufficient justification is not provided or due process not followed. No evidence of misappropriation during inception but some mistakes were spotted and rectified. External audits are planned for consortium partners and Management Organisations. / Intense negotiations between DFID and DAI around vfm have driven continued improvements over the inception period. Sub-contracting elements have been renegotiated and savings of £1.5m identified. DAI’s robust due diligence process, oversight and management of the downstream supply base provides additional assurance that DFID funds are being spent for their intended purpose and allows DFID access to all parts of the supply chain. Effective coordination with implementing partners has realised significant economy of scale and enabled DAI to vire back office costs to front end strategic delivery. / The overall risk of funds not being used as intended is medium. / 4.4 Climate and Environment Risk / Due to the nature of this programme, the climate and environment risk is low.

5. Value for Money
5.1 Performance on VfM measures / Economy / Economy is primarily considered in terms of inputs, their quality and procurement. / The selection of Development Alternatives Inc. (DAI), was done by competitive tender following EU procurement directives. / DFID’s transaction costs are lowered by using some of the existing structures, networks, contacts and “on-the-ground knowledge” of the implementing partners. The data gathered from the Aawaz programme has the potential to offer synergies to other DFID programmes by identifying gaps between demand and supply and allowing further interventions to be targeted. This will be of most use to the current Health and Education programmes, but also the potential for any future programmes with a focus on wealth creation and skills development. / DAI conducted due diligence of the Implementing Partner’s programmes according to their criteria (Attachment A). As a result of this process, the submitted budget for the inception phase was reduced by 28%[14]. The Review Team asked if the savings had been made through a reduction in the “Programme” component, as in the final revised budget the programme component is at 38% overall, while fees are at 47%. In response, revision of the Programme budget after due diligence did not impact on programme activities. Costs were reduced after addressing issues like double counting, but of the total Fee component, 75% is for strategic inputs (ie. delivering activities), 15 % is for operational and 10% is for administrative inputs. Taking this into account, programme costs are 70% overall of total project value. / The substantial savings generated during inception meant that DFID and DAI were able to increase target communities from 5000 to about 7000, consistent with the project design and maximising opportunities to increase pressure on the duty bearers to bring about reform. Given the complexity of delivering change and reform for Pakistan’s most marginalised citizens, this scale-up represents an additional boost to support progress towards Aawaz objectives. A full analysis of implementation will be carried out at the beginning of 2014 and will further inform decisions around scale-up. / An issue that was brought up amongst all the implementing partners, as well as DAI was the significant delays in procurement through a procurement agent. While these issues were eventually resolved for the Inception Phase, the delays meant that implementing partners had to find other funds and/or that activities were delayed. Some equipment delivered did not meet specifications due to a lack of guidance as to what information the procurement agent required. The requirement to use a procurement agent for all items has also presented a dilemma in that some items could be procured on the local market at a reduced cost. The review team recommends that DFID-P assess the scope for procurements below a certain percentage of the project value to not be directed through procurement agent. / While setup costs will be lowered through partnerships with local organisations, and VFM strengthened, it is also true that some of the structures of Aawaz have been in place, albeit under a different name, and funded by other donors. It could be argued that DFID funding may have been provided from some other source. However, the Review Team’s observations acknowledge that the comprehensive support from village to district level, and the platform the programme provides, is/was unlikely to be provided through some other means. / Efficiency / Efficiency is considered in terms of how the outputs are realised. / As noted, the programme has achieved a lot in a short space of time. Most of the inception targets have been met and at a reduced cost (£3,350,121) instead of originally anticipated cost of £4,662,970), a saving of almost 28%. / The Review Team recognises that Implementing Partners and their local partners require the flexibility to respond to the particular needs of the area in which they operate. This was evidenced by the differing nature of activities that were being undertaken, eg. raising awareness of the Sexual Harassment Law in one place, and looking at Home Worker issues in another. However, this could also reflect the particular expertise of the Implementing Partner. As the programme moves into implementation phase the review team recommends that there is a coherent plan of what activities will take place and ensure that all outputs are targeted – the costed activities produced by the MO provides a framework to allow for this. / In organisational terms the Aawaz structure can seem complicated, though this has been streamlined with the removal of sub-groups at the village level. There appears to be 4 different sets of Monitoring and Evaluation, which could potentially lead to duplication of effort and may not be necessary (see output 4 for further details and recommendations). This should be reviewed in the light of observations in this AR. and greater clarity and more appropriate structures developed, even if this requires changes in partner and responsibilities. / A constant theme when discussing the Aawaz committee structure with particular reference to their “dispute resolution” function is that of their relationship with pre-existing traditional systems i.e. the Panchayat and Jirga systems. The presence of parallel systems runs the risk of creating conflict and it is unclear whether these systems are in effect “competing” with each other, though there was evidence that the two systems dealt with different issues. A consistent and positive approach between and within organisations is needed (see Output 2 under Section A). / During the Review Team’s meetings with the MO and SDPI (the research partner), there was some discussion about the divergence between the baseline areas and the pilot areas. It would have been more efficient to link the two as this would have provided data on the impact of Aawaz and points of reference as the programme progresses, though this is unlikely to have an impact on the overall effectiveness of the programme. A wider observation from the Review Team noted that there was some confusion as to the purpose of Response Fund and PARR facility – (see output 4 for further details and recommendations). / Effectiveness / ‘Effectiveness’ is considered in terms of how well the programme is geared towards achieving its outcomes and wider benefits. / The Review Team acknowledges the Aawaz programme has provided a platform for previous ad hoc and sporadic community mobilisation efforts and has a reach that extends to the grassroots level. The structure has bought together civil society and provides a potential direction to further facilitate community empowerment. While the committee members were appreciative of the benefits of Aawaz, this represents an element of “self-selection” which means that members are more receptive of the ideas and principles that Aawaz advocates and therefore more satisfied with them. It will be necessary to gauge the response of the wider community to assess whether the benefits of Aawaz stretch beyond the committee rooms. Continued use of Beneficiary Feedback at agreed intervals and at different locations will help monitor the participation and inclusion objectives of Aawaz. / Members have highlighted the types of training that they have undertaken, though it would be more helpful to understand how training is targeted according to need, rather than generic training provided to people who would not be expected to use it e.g. training for the budget cycle. A sample of trainees should be monitored after a few months to assess continued effectiveness. A training need analysis (TNA) was carried out for implementing partners’ staff and field workers but there should also be a targeted approach for the communities on training. / The participation of women is encouraging, as well as that of minorities (the team observed a District Committee chaired by a transvestite as well as attendance of Hindus and Christians). There is also a marked effort to increase female registration for CNICs, which is essential in civic and electoral participation. All this provides an opportunity for the programme to achieve its aims once in full implementation. / However, for this opportunity to be realised, a number of issues need to be resolved. Firstly and most importantly, democratic empowerment can only be effective with economic empowerment. The Aawaz programme will provide a rich source of data that will allow for the better targeting of service provision allowing for significant multiplier effects. The communities themselves have repeatedly expressed a desire for greater skills and technical training. This is an opportunity for government and donors to target their efforts. DFID should use this opportunity to exploit potential synergies with health and education programmes, as well as any future wealth creation/skills development programme. / In terms of the Aawaz programme, the PARR facility, which has not yet delivered its full potential, should be geared towards analysing data and making it useful for policy purposes. This would also help to strengthen the link between the two Aawaz consortia. The PARR facility should also look at answering the question of attribution – if some activities were being undertaken previously under another name, then to what extent can the gains of the programme be reliably attributed to Aawaz? / While Aawaz has the potential to increase community empowerment and engagement, this needs to be matched with greater responsiveness on the part of government. Where this responsiveness has occurred already, it has been due to the make-up of Aawaz committees, some of whose members are from professional bodies or teaching and health councils. These links have been leveraged to obtain changes in service delivery for the good of the community, e.g. a female teacher being posted to a co-ed girls' school to increase girls’ attendance. The Review Team recognises that diversity of professions will vary across communities, and not all will be able to utilise such advantages. It is thus necessary to link the demand-side of Aawaz with the supply-side i.e. citizen empowerment with improved governance, accountability with local government service delivery. The SNG programme may help to achieve this along with mapping DFID programmes in Aawaz areas. / Another aim of Aawaz is to strengthen the capacity of implementing and local partners – this has not yet taken place under output 4, where there is an indicator for measuring this. However it is not clear whether we are measuring this more broadly. / The effectiveness of Aawaz will also rest on appropriate management of risks. This rests mainly on the interaction with local government structures. As highlighted in the Risks section, the form of local government – if reconstituted – will impact on how Aawaz committees operate. It would be beneficial for a contingency plan to be devised that takes into account these eventualities. / 5.2 Commercial Improvement and Value for Money / DAI have in place a ‘due diligence’ approach to analyse costings (attachment A) –which has reduced input costs without compromising on programme activities as explained to review team. / The inception phase has been delivered at reduced cost (32%) and thus the Team has confidence that the MO will maintain value for money in terms of input costs. / 5.3 Role of project partners / There is a strong relationship between the Management Organisation and Consortium Partners on Programme and Financial Management. There has been a focus on increasing the management skills of consortium partners. Training has been undertaken e.g. on forecasting and a lesson-learning workshop is planned on M&E/Programme Management/Human Resource Management. There should be a strong focus on capacity building, given the extent of the scale up and the need for partners to strengthen their systems to manage this. / 5.4 Does the project still represent Value for Money : Y/N Yes / As the Value for Money assessment is in the context of the programme’s inception phase, the analysis rests on how well the programme is placed to achieve as it moves towards implementation. / The programme has achieved a lot in a short space of time, notably in getting partners to work together, forming the institutional structures through which the programme will operate, and securing involvement with communities. The Review Team notes the potential of the programme to deliver as more activities come on stream. The MO is well positioned to contain and monitor costs, and clear results should be forthcoming in the next year with a focus on how the beneficiaries at the grassroots level are benefitting from DFID funds. Better organisation of the partners and their activities also needs to be demonstrated. However, at this stage, after reviewing the inception phase, it was observed that programme is heading in the right direction and representing a good value for money. / As the programme is implemented a number of issues need to be resolved and progress against these need to be considered at the next AR stage to determine whether Aawaz is performing as intended, some of which have been outlined in previous sections: / Greater coherence amongst the activities and across the partners / Clear linkages of activities with each of the outputs as well as the costs / Better data collection/documentation to indicate progress and achievements / Greater co-ordination amongst other DFID-P programmes to generate multiplier effects / 5.5 If not, what action will you take? / N/A
[14] Submitted budget of £4,662,970, reduced to £3,350,121 after DAI’s due diligence procedure.

6. Conditionality
6.1 Update on specific conditions / This project does not constitute financial aid; therefore DFID’s conditionality policy does not apply.

## 7. Conclusions and actions
Recommendations have been covered for all outputs above and are summarised and prioritised below.

Recommendation	Action/ timing
Social inclusion/ exclusion/ gender
Develop a comprehensive gender strategy, which separates out women and other excluded groups by strengthening the narrative, as well as recording figures and comparative information;	All outputs. Review Implementation strategy for gender, definitions of excluded groups. August 2013
Ensure women’s political participation is clearly defined at all levels and that beneficiaries’ expectations are managed, especially those of women and girls;	Output 1 linking to 2, 3, and 4. November 2013
Define and disaggregate excluded groups including women and variation across regions/geographical areas and at all levels in the programme and clear measurement of the scales on which inclusion is being achieved;	All annual Review
Synergies
Link with other projects/organizations working for voter registration/CNICs; (already underway)	Output 1. On-going.
Map conflicts in target districts;	Output 2. On-going
Increase coherence across the partners and activities	All outputs. On-going
Develop a formal platform for prevention of duplication, building of synergies and strengthening of VFM among DFID programmes by building in coordination as a deliverable for all	All relevant DFID P programmes (and those of others.)
DFID to examine consistency of fees and expenses across Management organisations to improve staff retention;	Actioned by DFID Aawaz team – awaiting responses from other teams
Ensure that voice and accountability (demand) projects are linked with and/or complementary to service delivery projects supported by DFID	All relevant DFID P programmes (and those of others.)
With the MO, coordinate closely with provincial governments to explore windows of opportunities for collaboration with government and increase multiplier effects	On-going
Programme implementation, capacity building etc
The relevance of Aawaz Committees should be analysed in the context of emerging local government structures (eg. in relation to opportunities for women’s participation) and the programme adjusted accordingly (e.g. women’s leadership training, support to women councillors, public speaking, support to LG processes);	All outputs. Timing linked to progress with Constitutional Amendment 18, Local ordinances. On-going
Sensitisation for men in groups to ensure understanding of correct behaviour towards female counterparts;	All Outputs. LFA indicators and perception surveys etc. LFA Review July 2013 and on-going
Provide training so that group members can engage effectively with politicians;	Output 1. End October 2013
Develop a shared understanding among partners as to the definition of dispute mediation, Aawaz roles in mitigation, and how to monitor;	Output 2. On-going.
Engage and work systematically with traditional and government structures/ officials where possible and appropriate, including involvement of women in traditional dispute mediation structures;	Output 2. On-going
Work with government structures (PTCs, LHW groups) and engage female teachers and LHWs at all levels for stronger linkages;	Output 3. On-going
Prioritise demands systematically through community scorecards and/or other methods;	Output 3, with links to 1 and 2. On-going
Encourage communities to take action to resolve their own problems rather than expecting local administrations to respond to all requests;	Output 3, with links to 1 and 2. On-going
Clarify the function of the RF to move beyond research and include tools and influencing processes that could be used across programme in all output areas;	Output 4. In process
Clarify and strengthen advocacy/influencing functions;	Output 4 and MO
Manage expectations, especially of women and girls: Partner organisation staff and committees need to be sensitised to this fact and share experiences in an honest way (including failures)	All outputs. On-going
Discuss and agree procurement and benefits of local vs management organizations;	MO and DFID. Started.
Move beyond social mobilization, to substantive trainings geared towards action and results; this could include focusing initially on individuals, then moving to collectives and groups to ensure more meaningful and effective changes;	All outputs. On-going
Ensure that training is targeted according to need, rather than generic training provided. Training should cover technical subjects where required, not just financial compliance. A sample of trainees should be monitored after a few months to assess continued effectiveness;	MO
Increase and focus trainings on dispute mediation, especially at the village level;	Output 2. On-going
Strengthen focus on capacity building for all partners where needed, and use evidence and experience of capacity building from other programmes if relevant;	All outputs. On-going
Monitoring & Evaluation
Develop clarity with partners on concepts of women’s safety, especially with regards to GBV and VAW, and the remit and expected changes in this area, including specific measures to reduce violence against girls;	Output 1. Develop indicators and baselines on VAW perceptions. LFA Review July 2013
Define tolerance and what “improved” means in the targets and milestones;	LFA Review July 2013
Revise the LFA to clarify links between outputs and outcomes, with a brief narrative to define targets and beneficiaries; ensure that activities are clearly linked to progress towards milestones and achievements in both the M&E framework and the logframe;	LFA Review July 2013
Establish tools to support the development of a clear narrative to present qualitative information and data, and to link output level results with outcome indicators and the ToC.	Review of analytical tools and software: MO, July 2013
Address attribution in the M&E framework: clarify causal links and key assumptions and streamline activities and strategies to ensure clarity of contribution vs. attribution;	LFA Review July 2013
Strengthen MO Capacity in M&E to strengthen its role in monitoring and reporting, and define clear responsibilities with time frames for the submission of progress reports, and effective mechanisms for impact analysis (already underway);	Structure and operations of PARR, Consortium A partners and MO M and E functions redesigned.
Clarify roles of and relationship between the two Consortia, particularly in relation to M&E, and collection, analysis and use of evidence;	As above
Identify evaluation questions for impact: eg. How much money is spent on demand/voice and is it being spent effectively? What should advocacy/ influencing cost? Can services be strengthened at the same rate as demands for services are created?[15] How do/should citizens communicate with service providers;	MO and DFID. Before next Annual Review
Develop guidelines across Consortium A, to agree on how attribution challenges can be addressed and train Aawaz members and communities to differentiate;	All outputs. On-going
Add Output 5 – see under Management Organisation.	LFA Review July 2013
Management Organisation
Design an additional OUTPUT area (5) in LFA to track and assess performance of Management Organisation;	LFA Review July 2013
Strengthen links of partner experts seconded to MO with field activities and work on synergies with DFID and other partners;	TBD
Ensure implementation strategy on fiduciary and political risks and audit systems provides information down to implementing partner level;	TBD
Carry out a substantial review of Output 4, possibly with additional expertise, to clarify all the functions, systems, personnel, roles and responsibilities, and ensure quality, added value timeliness of outputs and added-value to Aawaz;	Performance Management Plan, by June - September 2013
Build role of the AAC in future programme design in areas such as advocacy / influencing policy and practice;	TBD
Develop mitigation measures for risks women may incur because of their involvement with Aawaz and include in risk register with associated monitoring in quarterly reporting;	TBD
Clarify scope of activities at the federal/provincial level through discussions in PMR meetings;	TBD
Synergise with other relevant programmes especially supply-side programmes being implemented by DFID;	TBD
Introduce one external audit for whole programme in place of separate audits for MO and partners;	TBD
Share field visit reports with DFID and DFID to participate in monitoring visits on ad hoc basis;	TBD
[15] – The Parliamentary International Development Committee made the point that Pakistan would be able to meet the needs of its citizens if revenue sources were properly tapped. Aawaz and similar local level programmes are key to meeting citizens’ demands and needs, as well as donor efforts to support services GoP should and could supply.

8. Review Process
The review took place between March 11 to 22, 2013. The team comprised: / Colleen Wainwright (lead): Senior Social Development Advisor, DFID Ethiopia / Jawairia Jilani: Independent Consultant / Shumaila Rifaqat: Governance Advisor, DFID Pakistan / Will Guest: Deputy Head of Governance Group, DFID Pakistan / Ilyas Malek: Economist, DFID Pakistan / Moeen Akhter: Deputy Programme Manager, DFID Pakistan / Meetings were held with the MO, the five implementing partners, 3 members of the Advisory Committee, two Senators, 3 team leaders of other projects funded by DFID (SNG, PSP, TEP), two recipients of the Research Response Fund, field visits to 5 districts, with meetings with union, district and village level Aawaz committees.

Annex 1: Aawaz PROGRAMME PROGRESS AGAINST LOGFRAME INDICATORS

OUTCOME	Outcome Indicator 1		Baseline / 2008-12	Milestone 2013/14		Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
Democratic processes in Pakistan are more open, inclusive and accountable to citizens.	a). Cumulative no of new and revised laws positively affecting the status of women enacted (between 2012 and 2017) / b). Number of new bills introduced (tabled) by women legislators	Planned / New and revised laws / National / KP / Punjab / New bills / National / KP / Punjab	Existing / 6[16] / 2[17] / 4[18] / 11[19] / - / -	7 / 3 / 5 / 14 / 3 / 3		8 / 4 / 6 / 16 / 5 / 5	9 / 5 / 7 / 18 / 7 / 7	10 / 6 / 8 / 20 / 9 / 9
		Achieved
			Source
			Legislative Watch Report. / Reports of Women Caucuses
	Outcome Indicator 2		Baseline / 2012		Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	O2. % of excluded groups reporting improved tolerance in over the last 12 months in society [KP/Punjab][20]	Planned	0%		5%	10%	15%	20%
		Achieved	To be conducted
			Source
			Monitoring Reports of Consortium-A partners based on periodic Focused Group Discussions with local communities conducted by M&E Sections / Periodic perception surveys to be conducted by PARR.
	Outcome Indicator 3		Baseline / 2012		Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	O3. Cumulative % increase in access by women / other excluded groups to public services in project districts[21]	Planned	69.4%		75%	78%	80%	82%
		Achieved	To be conducted
			Source
			Periodic perception survey commissioned by PARR
	Outcome Indicator 4		Baseline / 2012	Milestone 2013/14		Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	% increase in level of media reporting on gender equality, tolerance and inclusion in political processes.[22]	Planned / Electronic (Time) / Print (Coverage) / Social (Pax)	5% / 2% / 3,000	6% / 3% / 10,000		7% / 4% / 15,000	8% / 5% / 35,000	10% / 6% / 65,000
		Achieved
[16] Source: http://www.na.gov.pk/en/acts-tenure.php (includes only laws passed in parliament since 2008)
[17] http://www.pakp.gov.pk/index.php/acts/bytenure/en/19 (Retrieved on March 5, 2013)
[18] http://www.punjablaws.gov.pk/index3.html (Retrieved on March 5, 2013) and http://www.af.org.pk/activity-detail.php?nid=21 (Retrieved on March , 2013). Does not include formation of women’s universities
[19] These are numbers for 2002-2007
[20] Percentage of women and minority men reporting
[21] Calculated as the percentage of women and minority men who claimed access to some government health AND education service in the last 12 months
[22] Source: A study conducted by Alternative Media and Research Islamabad

OUTPUT 1	Output Indicator 1.1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab	Cumulative number of formal engagements (as defined in output manual) on gender issues between Aawaz forums and political representatives at local, provincial and federal levels	Planned / Local / Provincial / National	0 / 0 / 0	12 / 8 / 4	24 / 16 / 8	36 / 24 / 12	48 / 32 / 16
		Achieved / Local / Provincial / National	During pilots / 16 / 3 / 4
		Source
		Reports of implementing partners Independent surveys commissioned by partners/PARR/MO
	Output Indicator 1.2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	Cumulative % men/ women reporting reduced tolerance of violence against women in programme districts over the previous year[23]	Planned	8.27%	10%	12%	15%	20%
		Achieved	To be conducted
		Source
		Independent annual perception survey commissioned by PARR
	Output Indicator 1.3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	% increase in access of women to public spaces (HMC/ SMC/Aawaz Forums) In programme districts.	Planned	15%	20%	25%	35%	40%
		Achieved	During Pilots / 15%
		Source
		Independent annual perception survey commissioned by PARR
IMPACT WEIGHTING (%)	Output Indicator 1.4		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
30%	a) % increase in decision making positions held by women within political parties[24] / b) Percentage of women in legislative bodies at local, provincial and national levels.[25] [26] [27]	Planned / Political Parties / Legislative Bodies / National / KP / Punjab / Local	28 / 21.07% / 17.89% / 25.89% / xx[28]	35 / 23% / 20% 28% / Xx	40 / 23% / 20% / 28% / xx	45 / 25% / 22% / 30% / xx	50 / 25%[29] / 22% / 30% / xx
		Achieved / Political Parties / Legislative Bodies / National / KP / Punjab		Election Year / (To be conducted)
		Source
		Independent annual perception survey commissioned by MO
[23] Calculated by adding the percentages of men and women reporting VAW incidents in the past 12 months. An increase would probably represent an increase in reporting of VAW
[24] The total number of known female party officeholders in the following 7 parties: ANP, JI, MQM, PMLN, PMLQ, PPP, PTI
[25] http://www.ipu.org/wmn-e/classif.htm (Retrieved on Feb 1, 2013)
[26] http://www.pakp.gov.pk/index.php/members/stats/en/19 (Retrieved on Feb 1, 2013)
[27] http://www.pap.gov.pk/index.php/members/stats/en/19
[28] There are currently no elected local governments in place
[29] We should not expect these numbers to go up every year. Elections are not held every year. The increase in year three is based on an expectation that LG elections will be held.

OUTPUT 2	Output Indicator 2.1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa and Punjab	Cumulative no of community level disputes identified, pre-empted and peacefully resolved by the communities themselves or through government notified ADR mechanisms.	Planned / Identified / Pre-empted / Resolved	0 / 0 / 0	10,000 / 7,000 / 7,000	31,000 / 21,000 / 21,000	47,000 / 42,000 / 35,000	54,000 / 63,000 / 40,000
		Achieved / Identified / Pre-empted / Resolved	During Pilots / -- / -- / 6
		Source
		Data tracking system of Implementing Partners / Implementing Partners’ report / Periodic evaluations by PARR
	Output Indicator 2.2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	Cumulative no of excluded group households participating in Aawaz Forums and local level peace building initiatives.	Planned	a) 0	1000 / (50/50)[30]	5000 (50/50)	20,000 (50/50)	80,000 (50/50)
		Achieved	During Pilots / District level: 56 / UC Level:32 / Village Level:206
		Source
		Data Tracking System / Monitoring data, reports of implementing partners analysed by PARR / Annual surveys organised by Aawaz
IMPACT WEIGHTING (%)	Output Indicator 2.3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	% of people in programme districts who consider Aawaz community cohesion mechanisms to be credible and effective	Planned	0%	1%	3%	6%	12%
20%		Achieved	To be conducted
		Source
		Perception surveys Reports of implementing partners analysed by PARR
[30] (No less than 50% participation of women and excluded groups

OUTPUT 3	Output Indicator 3.1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa and Punjab	Number and types of issues raised by the local communities through Aawaz Forums with increased participation of women, girls and other excluded groups	Planned / Issue Raised / Public participation	0 / 0	2,000 / 50,000	4,000 / 90,000	6,000 / 105,000	8,000 / 140,000
		Achieved / Issue Raised / Public participation	Education:4 / Health: 5 / Political Participation:4 / Access and control over resources:5 / Gender: 5 / Poor law and order situation: 3
		Source
		Press releases / Event reports and photographs / Monitoring Reports / Periodic evaluations by PARR
	Output Indicator 3.2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	Number and types of service delivery outlets improved in the areas of health, education and other priority areas benefiting women, girls and other excluded groups	Planned / Education/ Health issues addressed / Other issues addressed	0 / 0	900 / 450	1,800 / 900	2,700 / 1350	3,600 / 1,800
		Achieved / Education/ Health issues addressed / Other issues addressed	During Pilots / Education:3 / Health: / Others:4
		Source
		Press releases / Data Tracking System / Monitoring Reports / Periodic evaluations by PARR
IMPACT WEIGHTING (%)	Output Indicator 3.3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
30%	Percentage of women and excluded households satisfied with the quality of services has improved in result of Aawaz accountability initiatives	Planned	0%	5%	10%	15%	20%
		Achieved	To be conducted
		Source
		Citizen Score Cards / Perception surveys

OUTPUT 4	Output Indicator 4.1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
Improved evidence generated, synthesised and communicated/ championed to political leadership in Khyber Pakhtunkhwa and Punjab	Cumulative no of evidence-based policy studies (e.g., on inclusive governance, peace-building and accountability) shared with politicians and decision makers	Planned	0	2	8	14	25
		Achieved	During Pilots / 3 (including Response Fund)
		Source
		PARR Reports
	Output Indicator 4.2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	No of policy changes/reviews advocated for with provincial and decision makers, national legislators and politicians.	Planned / Approved by: / KP / Punjab / National	0 / 0 / 0	2 / 2 / 2	4 / 4 / 4	6 / 6 / 6	8 / 8 / 8
		Achieved / Approved by: / KP / Punjab / National	During Pilots / -- / -- / 4
		Source
		PARR Reports. / Reports from DFID’s other initiatives
IMPACT WEIGHTING (%)	Output Indicator 4.3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	Number of organizations capacitated and commissioned in carrying out research and advocacy initiatives to inform Aawaz and other programmes on selected themes	Planned / Commissioned / Trained Organizations	8 / 0	16 / 4	24 / 8	32 / 12	36 / 16
		Achieved / Commissioned / Trained Organizations	During Pilots / 8 / --
20%		Source
		Annual content analysis of media commissioned by PARR

Annex 2: Corporate Governance and Political Economy Assessment of Aawaz
Annual Review March 2013

I	Institutional Capacity and Corporate Governance – MO, Consortia A, Consortia B
Development Alternatives Inc. is a well-established company registered in UK and owned by its employees. It has robust internal control systems that are mirrored in Islamabad. Some core functions eg. finance, project management and internal audit, operate from the Islamabad office and are also subject to scrutiny from the London office. DAI has designed and implemented the financial protocols (process and procedures), and also shared the financial manual with the IPs.

DAI has oriented the finance staff across the consortia on DAI financial policies and DFID reporting mechanism/systems. This involved trainings and focused workshops on budgeting and financial management. DAI has also conducted a due diligence of IPs in accordance with DFID rules and DAI’s own criteria. This will help in strengthening core governance capacities of the implementing partners (IP), as noted in the implementation strategy for Aawaz. However, DAI should perform a more active role in monitoring project operations at district and UC levels. Currently this role is split between DAI and SDPI: as a result, operations oversight is weak (this should be performed by the MO) and field activities can lack focus and direction.

On IP corporate governance, SPO is registered as Not for Profit Company under Section 42 of Companies Ordinance 1984; whereas SDPI, Aurat Foundation, and SAP-PK are registered under Societies Act 1860. The organisational structures are similar; each IP organisation is governed by a General Body and Board of Directors/Governors, and organisational management is represented by a CEO or General Manager. Core internal control functions - finance, procurement and internal audit - mostly exist in the partner organisations, but the absence of this latter function in some partners is a fiduciary risk and a limitation on the oversight role of the Board of Directors/Governors. For external audit, the IPs have commissioned Chartered Accounting firms. All IPs are using FMIS for financial management and reporting, but none have automated procurement systems. This is not a fiduciary concern at this stage, but in the event of a scale up or changes in procurement arrangements, automated procurement systems at the IP level would support service delivery and performance of Aawaz.

The physical presence of IPs is limited to District Offices level: actual implementation is delivered with the support of their local partners (LP) in Union Councils. SPO operates from a regional office in Multan, which could be the reason for a relatively weak Aawaz District Group (ADG) in Muzzafargarh. ADGs were particularly vibrant in districts where the IPs had physical presence and full time staff. The capacity of the LPs varies: those closer to urban centres have better capacity compared to non-urban LPs (eg. Dhamrian). The LPs need capacity building support from the IPs in budgeting, financial management, advocacy and risk assessment – this will be instrumental in their effectiveness if the same model is used in the scale up phase. Also, IPs should provide LPs with training, formal instruments and communication material focusing on Aawaz focus areas. This will streamline their work and also facilitate greater legitimacy from involved communities as well as opposing groups.
II	Overall Political Economy Observations/Risks
Direct Challenge to existing traditional power structures
Aawaz is primarily aimed at giving local communities a voice to enable accountability in service delivery, community level dispute resolution, and protect the rights of excluded groups. This is a direct challenge to traditional power structures of ‘Panchayat and Jirga’ as well as the public administration systems. Changing mind-sets has to be an inclusive process: while exclusionary policies (Panchayat, Jirga) may achieve small successes in the short run, they could create friction as the Aawaz Committees gain momentum. SAP-PAK is the only IP that is working with these structures for sustained change: others take the approach of parallel structures which could be exclusionary and could create conflict between the two structures.

Risk of Political Takeover of the Aawaz Committees
Membership from diverse sectors - government, legal sector, academia, media, etc. - adds to vibrancy and dynamism of Aawaz Committees. However, given the outreach of the Committees, they could attract individuals with strong political affiliations (in case of Aurat Foundation). While the programme also benefits from involvement of political workers in terms of community support, it also creates the risk of political takeover of Aawaz Committees especially around the election period. A clear membership and engagement policy should be adopted by the IPs to avoid politicization of Aawaz Committees.

Revival of the Local Government (LG) Systems
The likely revival of the LG after elections has implications for Aawaz. Alternate Dispute Resolution mechanisms (Musalihaat Anjuman, MA) were established down to UC level under the LG Act 2001, and had the same function as Aawaz Committees - arbitration, mediation and reconciliation of disputes relating to violence and abuse. The LG Act 1979 did not include MAs. New LG Acts are more likely to be based on LG 1979, which creates more space for formal Aawaz structures but there should be detailed analysis of LG Acts to inform project strategy and planning.

Risk Exposure of Aawaz Committee members and Expectation Management
Female members of the Aawaz Committees (village, and UC level) are exposed to possible risks of violence and harassment due to increased engagement in Aawaz issues. A clear risk assessment of female participation should be carried out by DAI and IPs and an action plan developed to protect women from untoward incidents.

Risk Register
The Risk Register is maintained by DAI with input from IPs in Programme Review Meetings. The risk roster does not cover the risks listed above nor does it include possible negative perceptions concerning NGOs among communities at local level. Risk mitigation measures recommend greater policy engagement which is not yet reflected in planned activities (e.g. using SDPI and Response Fund). Neither is there a defined mechanism for channelling information from the field to policy forums (with the exception of Aurat Foundation, which is more personality based than structural). This also explains ignorance of the field staff concerning the risk register. It is recommended that the risk register is shared with the field staff as a significant proportion of risks are related to field operations and should receive their direct input.

Annex 3: Programme Management - Aawaz Programme Annual Review 2013

Findings
- Strong relationship between Management Organisation and Consortium Partners on Programme and Financial Management due to robust management with regular interaction including monthly meetings.
- Capacity building – clear focus on strengthening management skills of partners. Training undertaken e.g. on forecasting. Lesson-learning workshop planned on M&E/Programme Management/Human Resource Management. Capacity of consortium partners is mixed.
- Financial Management – in-depth due diligence of partner budgets - £0.7m reduction in costs.
- Robust process for checking payments. 40-60% sampling of receipts. Payments disallowed if sufficient justification is not provided or due process not followed. No evidence of misappropriation during inception but some mistakes made.
- Costs standardised across partners and rate cards for salaries agreed.
- Audit – Separate external audits planned for consortium partners and Management Organisations.
- Forecasting – Forecasting initially weak. Consortium partners lacked experience on projections. Costs were overestimated and communications between finance, monitoring and evaluation, and implementation teams were weak. Improvements were made over the last quarter of the inception period.
- Procurement – Performance of procurement agent has been weak. The MO and consortium partners report that no guidelines were received at the start of the process, requested specifications were not followed, costs were not kept down, deadlines not met and a number of goods received were faulty. This is despite regular communication including daily meetings.
- Monitoring and Evaluation/Verification – Quarterly visits/field visits undertaken to pilot districts – reporting not shared with DFID.

Recommendations
- Maintain a strong focus on capacity building of partners – the lack of a strong management set up amongst some partners will become more apparent as the programme scales up. Capacity building under earlier programmes has worked.
- Consider streamlining the payments process: it can take 10 days to process an advance and 30 days advance when working in multiple districts may not be practical. Perhaps move to 60-90 day advances and try to reduce paper work.
- There should be one external audit for the whole programme rather than two separate audits of the Management Organisation and consortium partners.
- Consider costs and benefits of using procurement agents vs. using management organisations with track records on procurement and delivering value for money.
- Reporting from field visits should be shared with DFID. DFID should ensure participation in monitoring visits on an ad hoc basis.
- DFID Pakistan should look at costs across Management Organisations and ensure charging for fees and expenses are consistent. This will help to reduce competition and ensure staff retention.
Annex 4: Suggested Logical Framework Revisions

PROJECT NAME	Aawaz LOGICAL FRAMEWORK
IMPACT	Impact Indicator 1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
Stable, inclusive and tolerant democracy in Pakistan.	G1 Pakistanis who feel quite safe or very safe over the course of a year.	Planned	38%	38%	40%	44%	50%
		Achieved
			Source
			Gallup & Gilani : Annual polling on Crimes, Violence, Terrorism and Social Evils National Survey
	Impact Indicator 2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	G2. World Bank “Worldwide Governance Indicators” : Voice and Accountability Score	Planned	-1.01	-0.95	-0.82	-0.75	-0.7
		Achieved
			Source
			World Bank Governance indicators
	Impact Indicator 3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	G3. International Gender Gap rank	Planned	134/135	133/135	132/135	130/135	128/135
		Achieved
			Source
			World Economic Forum – Annual Gender Gap Reports

OUTCOME	Outcome Indicator 1			Baseline / 2008-12	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17	Assumptions
Democratic processes in Pakistan are more open, inclusive and accountable to citizens.	a). Cumulative no of new and revised laws positively affecting the status of women enacted (between 2012 and 2017) / b). Number of new bills introduced (tabled) by women legislators	Planned / New and revised laws / National / KP / Punjab / New bills / National / KP / Punjab		Existing / 6[31] / 2[32] / 4[33] / 11[34] / - / -	7 / 3 / 1 / 14 / 3 / 3	8 / 4 / 2 / 16 / 5 / 5	9 / 5 / 3 / 18 / 7 / 7	10 / 6 / 4 / 20 / 9 / 9	Those in power will act in response to the louder more strategic voices that this programme aims for, and tackle violence and exclusion. Pakistan does not revert to highly unstable democracy or to autocratic rule. Other donors continue to support efforts to establish and consolidate a stable, inclusive democracy in Pakistan. No major environmental/natural disasters. / Parliamentarian activities in support of women and other excluded groups are not disrupted by elections in 2012/2013 Macro-economic stability
		Achieved
				Source
				Assessment by PARR using DFID methodology. Average score, covering extent to which (a) six key laws* have been enacted/ revised; (b) level of public awareness of the laws; (c) level of implementation of laws; (d) resulting changes in behaviour or perception of public (1= completed/high; 2 = In process/medium; 3 = Not yet addressed/low). * Example of Key laws on : (i) Sexual harassment in the workplace; (ii) Domestic violence; (iii) Acid burning; (iv) ‘Anti Women Practices’; (v) Unequal rights in marriage, property and inheritance; (vi) non compoundabilty of “Honour killings”. / Legislative Watch Report. / Reports of Women Caucuses
	Outcome Indicator 2			Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	O2. % of excluded groups reporting improved tolerance in over the last 12 months in society [KP/Punjab][35]	Planned		0%	5%	10%	15%	20%
		Achieved
				Source
				Monitoring Reports of Consortium-A partners based on periodic Focused Group Discussions with local communities conducted by M&E Sections / Periodic perception surveys to be conducted by PARR.
	Outcome Indicator 3			Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	O3. Cumulative % increase in access by women / other excluded groups to public services in project districts[36]	Planned		69.4%	75%	78%	80%	82%
		Achieved
				Source
				Periodic perception survey commissioned by PARR
	Outcome Indicator 4			Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	% increase in level of media reporting on gender equality, tolerance and inclusion in political processes.[37]	Planned / Electronic (Time) / Print (Coverage) / Social (Pax)		5% / 2% / 3,000	6% / 3% / 10,000	7% / 4% / 15,000	8% / 5% / 35,000	10% / 6% / 65,000
		Achieved

INPUTS (£)	DFID (£)		Govt (£)		Other (£)	Total (£)		DFID SHARE (%)
		£34.05m	0		0	£34.05m		100 %
INPUTS (HR)	DFID (FTEs)
[31] Source: http://www.na.gov.pk/en/acts-tenure.php (includes only laws passed in parliament since 2008)
[32] http://www.pakp.gov.pk/index.php/acts/bytenure/en/19 (Retrieved on March 5, 2013)
[33] http://www.punjablaws.gov.pk/index3.html (Retrieved on March 5, 2013) and http://www.af.org.pk/activity-detail.php?nid=21 (Retrieved on March, 2013). Does not include formation of women’s universities
[34] These are numbers for 2002-2007
[35] Percentage of women and minority men reporting
[36] Calculated as the percentage of women and minority men who claimed access to some government health AND education service in the last 12 months
[37] Source: A study conducted by Alternative Media and Research Islamabad

OUTPUT 1	Output Indicator 1.1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17	Assumption
Women better able to participate safely in politics and in public spaces at federal, provincial and local levels in Khyber Pakhtunkhwa and Punjab	Cumulative number of formal engagements (as defined in output manual) on gender issues between Aawaz forums and political representatives at local, provincial and federal levels	Planned / Local / Provincial / National	0 / 0 / 0	12 / 8 / 4	24 / 16 / 8	36 / 24 / 12	48 / 32 / 16	Those in power will respond effectively to increased levels of demand from women for access to services, and strengthened equality under the law Parliamentarians and justice system actors are open to pressure to enact and enforce legislative reforms. Conservative groups accept or are unable to stop greater women’s participation in politics and public spaces Women do not suffer increased violence as a result of enhanced political engagement
		Achieved
		Source
		Reports of implementing partners Independent surveys commissioned by partners/PARR/MO
	Output Indicator 1.2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	Cumulative % men/ women reporting reduced tolerance of violence against women in programme districts over the previous year[38]	Planned	8.27%	10%	12%	15%	20%
		Achieved
		Source
		Independent annual perception survey commissioned by PARR
	Output Indicator 1.3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	% increase in access of women to public spaces (HMC/ SMC/Aawaz Forums) In programme districts.	Planned	0%	2%	4%	7%	10%
		Achieved
		Source
		Independent annual perception survey commissioned by PARR
IMPACT WEIGHTING (%)	Output Indicator 1.4		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
30%	a) % increase in decision making positions held by women within political parties[39] / b) Percentage of women in legislative bodies at local, provincial and national levels.[40] [41] [42]	Planned / Political Parties / Legislative Bodies / National / KP / Punjab / Local	28 / 21.07% / 17.89% / 25.89% / xx[43]	35 / 23% / 20% 28% / xx	40 / 23% / 20% / 28% / xx	45 / 25% / 22% / 30% / xx	50 / 25%[44] / 22% / 30% / xx
		Achieved
		Source						RISK RATING
		Independent annual perception survey commissioned by MO
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
		£13.05m	0	0	£13.05m		100 %
INPUTS (HR)	DFID (FTEs)
[38] Calculated by adding the percentages of men and women reporting VAW incidents in the past 12 months. An increase would probably represent an increase in reporting of VAW
[39] The total number of known female party officeholders in the following 7 parties: ANP, JI, MQM, PMLN, PMLQ, PPP, PTI
[40] http://www.ipu.org/wmn-e/classif.htm (Retrieved on Feb 1, 2013)
[41] http://www.pakp.gov.pk/index.php/members/stats/en/19 (Retrieved on Feb 1, 2013)
[42] http://www.pap.gov.pk/index.php/members/stats/en/19
[43] There are currently no elected local governments in place
[44] We should not expect these numbers to go up every year. Elections are not held every year. The increase in year three is based on an expectation that LG elections will be held.

OUTPUT 2	Output Indicator 2.1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17	Assumptions
Citizens and communities better able to resolve disputes peacefully, and work together for common solutions in Khyber Pakhtunkhwa and Punjab	Cumulative no of community level disputes identified, pre-empted and peacefully resolved by the communities themselves or through government notified ADR mechanisms.	Planned / Identified / Pre-empted / Resolved	0 / 0 / 0	10,000 / 7,000 / 7,000	31,000 / 21,000 / 21,000	47,000 / 42,000 / 35,000	54,000 / 63,000 / 40,000	Those in power will act in response to the louder more strategic voices that this programme aims for; to respond effectively to increased levels of demand from excluded groups, including young people, for services. Improved resolution of local disputes leads to greater community cohesion and strengthens voice of excluded groups in local and district politics. Conservative groups accept or are unable to stop greater participation by excluded groups and young people in politics and public spaces. Local organisations with access to excluded communities can be identified and contracted.
		Achieved
		Source
		Data tracking system of Implementing Partners / Implementing Partners’ report / Periodic evaluations by PARR
	Output Indicator 2.2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	Cumulative no of excluded group households participating in Aawaz Forums and local level peace building initiatives.	Planned	a) 0	1000 / (50/50)[45]	5000 (50/50)	20,000 (50/50)	80,000 (50/50)
		Achieved
		Source
		Data Tracking System / Monitoring data, reports of implementing partners analysed by PARR / Annual surveys organised by Aawaz
IMPACT WEIGHTING (%)	Output Indicator 2.3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	% of people in programme districts who consider Aawaz community cohesion mechanisms to be credible and effective	Planned	0%	1%	3%	6%	12%
20%		Achieved
		Source						RISK RATING
		Perception surveys Reports of implementing partners analysed by PARR
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
		£12.15m	0	0	£12.15m		100 %
INPUTS (HR)	DFID (FTEs)
[45] (No less than 50% participation of women and excluded groups

OUTPUT 3	Output Indicator 3.1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17	Assumptions
Women and other excluded groups better able to demand improved delivery of services in Khyber Pakhtunkhwa and Punjab	Number and types of issues raised by the local communities through Aawaz Forums with increased participation of women, girls and other excluded groups	Planned / Issue Raised / Public participation	0 / 0	2,000 / 50,000	4,000 / 90,000	6,000 / 105,000	8,000 / 140,000	Those in power will respond to increased demands for services from excluded groups, including young people. Local groups are prepared to work together towards shared priorities Improved resolution of local disputes leads to greater community cohesion and strengthens voice of excluded groups to demand improved service delivery at local and district levels.
		Achieved
		Source
		Press releases / Event reports and photographs / Monitoring Reports / Periodic evaluations by PARR
	Output Indicator 3.2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	Number and types of service delivery outlets improved in the areas of health, education and other priority areas benefiting women, girls and other excluded groups	Planned / Education/ Health issues addressed / Other issues addressed	0 / 0	900 / 450	1,800 / 900	2,700 / 1350	3,600 / 1,800
		Achieved
		Source
		Press releases / Data Tracking System / Monitoring Reports / Periodic evaluations by PARR
IMPACT WEIGHTING (%)	Output Indicator 3.3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
30%	Percentage of women and excluded households satisfied with the quality of services has improved in result of Aawaz accountability initiatives	Planned	0%	5%	10%	15%	20%
		Achieved
		Source						RISK RATING
		Citizen Score Cards / Perception surveys
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
		£4.05m	0	0	£4.05m		100 %
INPUTS (HR)	DFID (FTEs)

OUTPUT 4	Output Indicator 4.1		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17	Assumptions
Improved evidence generated, synthesised and communicated/ championed to political leadership in Khyber Pakhtunkhwa and Punjab	Cumulative no of evidence-based policy studies (e.g., on inclusive governance, peace-building and accountability) shared with politicians and decision makers	Planned	0	2	8	14	25	Pakistani politicians and bureaucrats will respond positively to better informed and more strategic citizen demands and ensure more effective policy implementation Media campaigns and public events are effective in changing public (citizens') attitudes and lead to increased tolerance Pakistani politicians and bureaucrats are able to respond citizen demands for greater tolerance
		Achieved
		Source
		PARR Reports
	Output Indicator 4.2		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	No of policy changes/reviews advocated for with provincial and decision makers, national legislators and politicians.	Planned / Approved by: / KP / Punjab / National	0 / 0 / 0	2 / 2 / 2	4 / 4 / 4	6 / 6 / 6	8 / 8 / 8
		Achieved
		Source
		PARR Reports. Reports from DFID’s other initiatives
IMPACT WEIGHTING (%)	Output Indicator 4.3		Baseline / 2012	Milestone 2013/14	Milestone 2014/15	Milestone 2015/16	Milestone 2016/17
	Number of organizations capacitated and commissioned in carrying out research and advocacy initiatives to inform Aawaz and other programmes on selected themes	Planned / Commissioned / Trained Organizations	8 / 0	16 / 4	24 / 8	32 / 12	36 / 16
		Achieved
20%		Source						RISK RATING
		Annual content analysis of media commissioned by PARR						Medium
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	(up to 30% for Response Fund)	£4.8m	0	0	£4.8m		100 %
INPUTS (HR)	DFID (FTEs)