## Consolidated Logframe
PROJECT NAME | Integrated Emergency Response Programme for Yemen (IERP) 2012-2013
IMPACT | Impact Indicator 1 |  | Baseline 2010 | Milestone 1 | Milestone 2 | Target 2013
Contribute to improved lives of vulnerable and conflict-affected people | The mortality levels, resilience and recovery of those in acute humanitarian crisis remains stable | Planned |  |  |  | <1 /10,000 /day
|  | Achieved |  |  |  | No information
Source
Target: Yemen Consolidated Appeals Process 2013
| Impact Indicator 2 |  | Baseline 2010 | Milestone 1 | Milestone 2 | Target 2013
OUTCOME | Outcome Indicator 1 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
Vulnerable groups in six targeted governorates are assisted to recover from the shocks of conflict and the socio-economic crisis through an integrated package of interventions | Number of vulnerable people residing in the six selected governates assisted to recover from the shocks of conflict and the socio-economic crisis through an integrated package of time critical and early recovery initiatives, supporting durable solutions | Planned | 0 |  |  | Total Beneficiaries: 308,201 | Security situation remains stable in targeted locations with no significant outbreak of fighting. No extreme weather patterns such as drought. All levels of government (local authority and executive units) & local authorities and partners remain supportive and collaborative to IERP interventions Ongoing political crisis in Yemen does not escalate to point of deterring NGO operation; No massive influx of IDPs as a result of the national crisis or escalation of the Sa’ada crisis; Inter-tribal tensions do not escalate in the intervention areas either as a result of inequalities in humanitarian assistance or for any other reason; Humanitarian access improves especially to Houthi controlled areas;
|  | Achieved |  |  |  | Total Beneficiaries: 349,643
Source
Target: IERP III Final report; Final external evaluation findings
| Outcome Indicator 2 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
| Percentage of targeted sample beneficiaries reporting timely and quality delivery of services | Planned |  |  |  | At least 75% of targeted sample
|  | Achieved |  |  |  | 81%
Source
Target: IERP III Final report; Final external evaluation findings
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1: HEALTH (Lead: ADRA) | Output Indicator 1.1 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
Essential health services which meet the needs of the target populations are delivered | Number of beneficiaries that receive primary and maternal health care, including the treatment of chronic and conflict-related cases, vaccination and medical referrals | Planned | 0 |  |  | 43300 | Ministry of Health supports interventions, provides necessary staff and coordinates effectively Availability of necessary supplies Communities are receptive to health education messages
|  | Achieved |  |  |  | 79589
Source
IERP III Consortium Partner & PMU monitoring reports ADRA ( 1.1a+1.1b+1.1c)
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target (date)
| Number of households that receive essential household items | Planned | 0 |  |  | 210000
Achieved
Source
ICRC annual report
| Output Indicator 1.2 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
| Number of health facilities provided with medical equipment, medical supplies, consumables, medications, and/or staff capacity building | Planned | 0 |  |  | 33
|  | Achieved |  |  |  | 15
Source
IERP III Consortium Partner & PMU monitoring reports ADRA (1.2A= 8) +IRY (1.2A =5) + SCY (1.2A=20)
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
20% | Number of beneficiaries that receive health education messages, including patients treated by supported medical centres, families and community members | Planned | 0 |  |  | 7250
|  | Achieved |  |  |  | 9154
|  | Source |  |  |  |  | RISK RATING
|  | IERP III Consortium Partner & PMU monitoring reports ADRA (1.3A= 7250) |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2: NUTRITION (Lead: SCY) | Output Indicator 2.1 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
Vulnerable communities receive both preventive and curative nutrition services | Number of beneficiaries receiving nutrition education | Planned | 0 |  |  | 27750 | In-kind support from WFP and UNICEF are provided in sufficient quantities and in a timely manner (Plumpy-Nut, RUSF) Ministry of Health supports interventions, provides necessary staff and coordinates effectively Malnutrition rates remain at current levels (ie no major shocks raise these levels) Communities are receptive to nutrition education messages and breastfeeding promotion
|  | Achieved |  |  |  | 59453
Source
IERP III Consortium Partner & PMU monitoring reports IRY (2.1B=1500)+SCY(2.1B=26,250)
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
15% | Number of beneficiaries admitted to Moderate and Severe Acute Malnutrition (MAM and SAM) services by type (< 5s and adults) | Planned | 0 |  |  | 3000
|  | Achieved |  |  |  | 6119
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | IERP III Consortium Partner & PMU monitoring reports SCY (2.2 =3000) |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3: WASH (Lead: Oxfam) | Output Indicator 3.1 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
Vulnerable families are supported with water, sanitation and hygiene inputs | Number of water facilities rehabilitated/provided | Planned | 0 |  |  | 32 | Local community cooperation with IERP CPs to implement activities Women show interest to practice better hygiene; In selected project areas water sources available through out the year and with non-saline water; Security allows access to project area; No further population displacement happens during the project period
|  | Achieved |  |  |  | 35
Source
IERP III Consortium Partner & PMU monitoring reports CARE (3 tankers +8wells+1network system+1ground water tank + 12 schools receiving plastic water tanks)+ OXFAM( 5Wells +2 water systems) CARE (3.1 a+ 3.1b =18800) + OXFAM (3.1A=15550)
| Output Indicator 3.2 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
| Number of households provided with training on safe hygiene practices | Planned | 0 |  |  | 6800
|  | Achieved |  |  |  | 7468
Source
IERP III Consortium Partner & PMU monitoring reports CARE (3.2B=2500)+OXFAM (3.2B+3.2C=4300)
| Output Indicator 3.3 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
| Number of households reached with hygiene materials | Planned | 0 |  |  | 4000
|  | Achieved |  |  |  | 4200
Source
IERP III Consortium Partner & PMU monitoring reports OXFAM = 1500 + CARE = 2500
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
15% | Number of students reached with hygiene materials | Planned | 0 |  |  | 11973
|  | Achieved |  |  |  | 11973
|  | Source |  |  |  |  | RISK RATING
|  | IERP III Consortium Partner & PMU monitoring reports CARE = 11,973 |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4: PROTECTION (Lead: CIY) | Output Indicator 4.1 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
Protection services provided to vulnerable conflict-affected people | Number of women that receive protection services including legal advice or other counselling services | Planned | 0 |  |  | 3997 | Local partner remains supportive and collaborative Target groups willing and able to access protection services Community leaders and government authorities receptive to advocacy messages and training
|  | Achieved |  |  |  | 9976
Source
IERP III Consortium Partner & PMU monitoring reports CARE (4.1A+4.1B+4.1C=3997)
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
10% | Number of community leaders and government aides that receive advocacy messages about the protection needs of women and girls | Planned | 0 |  |  | 475
|  | Achieved |  |  |  | 2425
|  | Source |  |  |  |  | RISK RATING
|  | IERP III Consortium Partner & PMU monitoring reports CARE (4.2A+4.2B=475) |  |  |  |  | Medium
INPUTS (£) |  |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5: EDUCATION (lead: SCY) | Output Indicator 5.1 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
School age children receive formal and informal education services | Number of teachers, school managers and school councils trained on planning, active learning and education in emergencies (including MRE) | Planned | 0 |  |  | 60600 | Principals and school managers cooperate and coordinate fully with consortium partners Ministry of Education supports IERP interventions and provides staff for trainings and capacity building Ongoing conflict does not lead to occupation of schools by armed groups or to bombing campaigns that further affect school construction
|  | Achieved |  |  |  | 69817
Source
IERP III Consortium Partner & PMU monitoring reports SCY (5.1A=600, 5.1C=60,000)
IMPACT WEIGHTING (%) | Output Indicator 5.2 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
15% | Number of schools/learning spaces improved through minor physical rehabilitation | Planned | 0 |  |  | 30
|  | Achieved |  |  |  | 31
|  | Source |  |  |  |  | RISK RATING
|  | IERP III Consortium Partner & PMU monitoring reports SCY (5.2A =30) |  |  |  |  | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  |  | - |  |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 6: EARLY RECOVERY / LIVELIHOODS (lead: Oxfam) | Output Indicator 6.1 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
Vulnerable people in target areas are provided with livelihoods support | Number of people that participate in vocational or business management training | Planned | 0 |  |  | 3700 | Communities accept and adopt the alternative livelihood option(s); beneficiaires are able to market their product or skills; IERP CPs able to access beneficiaries; Tension and tribal confilect do not adversely affect project implementation; Women in rural villages willing & able to attend vocational skills training
|  | Achieved |  |  |  | 3991
Source
IERP III Consortium Partner & PMU monitoring reports ADRA (6.1A=200)+IRY (6.1A=1160)+OXFAM ( 6.1B= 2340)
| Output Indicator 6.2 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
| Number of households that receive financial or non-financial productive inputs to develop an income generating activity | Planned | 0 |  |  | 3650
|  | Achieved |  |  |  | 3913
Source
IERP III Consortium Partner & PMU monitoring reports ADRA( 6.2B=150)+IRY (6.2B=1160)+OXFAM (6.2A=2340)
IMPACT WEIGHTING (%) | Output Indicator 6.3 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
15% | Number of community members actively engaged in supporting livelihood activities | Planned | 0 |  |  | 165
|  | Achieved |  |  |  | 174
Source
IERP III Consortium Partner & PMU monitoring reports OXFAM (6.3A=165)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  |  | - |  |  | 100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 7: Integration | Output Indicator 7.1 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013 | Assumptions
Increased synergies for a cohesive program approach within the consortium activities | Number of functional coordination mechanism | Planned | 0 |  | 2 | 2 | Procedures/ systems will not conflict with organisational policies and practicesof each CP Emergency situation in country requires international response
|  | Achieved |  |  |  | 2
Source
IERP III Consortium Partner & PMU monitoring reports
| Output Indicator 7.2 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
| Standard Operating procedures developed and used for the project | Planned | 0 | 1 | 2 | 2
|  | Achieved |  |  |  | 2
Source
IERP III Consortium Partner & PMU monitoring reports
IMPACT WEIGHTING (%) | Output Indicator 7.3 |  | Baseline 2012 | Milestone 1 | Milestone 2 | Target 2013
10% | Long term strategy for consortium project developed | Planned | 0 | Initiate the process for development of long tem strategy | 1 | 1
|  | Achieved |  |  |  | 0
|  | Source |  |  |  |  | RISK RATING
|  | IERP III Consortium Partner & PMU monitoring reports |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
Note on G9: Output 1 Health: 106,600 Output 2 Nutrition: 39,000 Output 3 WASH: 71,764 Output 4 Protection: 4,472 Outout 5 Education: 60,600 Output 6 Early Recovery: 25,765
Note on G10: Output 1 Health: 113,793 Output 2 Nutrition: 59,453 Output 3 WASH: 67,567 Output 4 Protection: 12,439 Outout 5 Education: 68,748 Output 6 Early Recovery: 27,643
Note on G24: 35,667 male and 43,922 female
Note on G53: Of which Female children <5: 2,794, Male children <5: 2,310, Pregnant and lactating women: 1,015

## PCR
Integrated Emergency Response Programme for Yemen (IERP) 2012-2013
Results Chain |  |  | Indicators | Planned | Achieved |  | Score |  | Risk
|  |  |  | 2014 |  |  | 2014 |  | 2014
IMPACT | Contribute to improved lives of vulnerable and conflict-affected people |  | The mortality levels, resilience and recovery of those in acute humanitarian crisis remains stable | <1 /10,000 /day | No information
OUTCOME | Vulnerable groups in six targeted governorates are assisted to recover from the shocks of conflict and the socio-economic crisis through an integrated package of interventions |  | Number of vulnerable people residing in the six selected governates assisted to recover from the shocks of conflict and the socio-economic crisis through an integrated package of time critical and early recovery initiatives, supporting durable solutions | Total Beneficiaries: 308,201 | Total Beneficiaries: 349,643 |  | A | 100%
|  |  | Percentage of targeted sample beneficiaries reporting timely and quality delivery of services | At least 75% of targeted sample | 81%
OUTPUTS | Essential health services which meet the needs of the target populations are delivered | 20% | Number of beneficiaries that receive primary and maternal health care, including the treatment of chronic and conflict-related cases, vaccination and medical referrals | 43300 | 79589 | 183.8% | A | 100% | Medium
|  |  | Number of health facilities provided with medical equipment, medical supplies, consumables, medications, and/or staff capacity building | 33 | 15 | 45.45%
|  |  | Number of beneficiaries that receive health education messages, including patients treated by supported medical centres, families and community members | 7250 | 9154 | 126.3%
| Vulnerable communities receive both preventive and curative nutrition services | 15% | Number of beneficiaries receiving nutrition education | 27750 | 59453 | 214.2% | A++ | 150% | Medium
|  |  | Number of beneficiaries admitted to Moderate and Severe Acute Malnutrition (MAM and SAM) services by type (< 5s and adults) | 3000 | 6119 | 204%
|  |  | 0 | 0 | 0 | #DIV/0!
|  |  | 0 | 0 | 0 | #DIV/0!
| Vulnerable families are supported with water, sanitation and hygiene inputs | 15% | Number of water facilities rehabilitated/provided | 32 | 35 | 109.4% | A | 100% | Medium
|  |  | Number of households provided with training on safe hygiene practices | 6800 | 7468 | 109.8%
|  |  | Number of households reached with hygiene materials | 4000 | 4200 | 105%
|  |  | Number of students reached with hygiene materials | 11973 | 11973 | 100%
| Protection services provided to vulnerable conflict-affected people | 10% | Number of women that receive protection services including legal advice or other counselling services | 3997 | 9976 | 249.6% | A++ | 150% | Medium
|  |  | Number of community leaders and government aides that receive advocacy messages about the protection needs of women and girls | 475 | 2425 | 510.5%
|  |  | 0 | 0 | 0 | #DIV/0!
|  |  | 0 | 0 | 0 | #DIV/0!
| School age children receive formal and informal education services | 15% | Number of teachers, school managers and school councils trained on planning, active learning and education in emergencies (including MRE) | 60600 | 69817 | 115.2% | A | 100% | Medium
|  |  | Number of schools/learning spaces improved through minor physical rehabilitation | 30 | 31 | 103.3%
|  |  | 0 | 0 | 0 | #DIV/0!
|  |  | 0 | 0 | 0 | #DIV/0!
| Vulnerable people in target areas are provided with livelihoods support | 15% | Number of people that participate in vocational or business management training | 3700 | 3991 | 107.9% | A | 100% | Medium
|  |  | Number of households that receive financial or non-financial productive inputs to develop an income generating activity | 3650 | 3913 | 107.2%
|  |  | Number of community members actively engaged in supporting livelihood activities | 165 | 174 | 105.5%
| Increased synergies for a cohesive program approach within the consortium activities | 10% | Number of functional coordination mechanism | 2 | 2 | 100% | A | 150% | Low
|  |  | Standard Operating procedures developed and used for the project | 2 | 2 | 100%
|  |  | Long term strategy for consortium project developed | 1 | 0 | 0%
OVERALL OUTPUT SCORE |  | 100% |  |  |  |  | A+ | 117.5%
| Value | Threshold
A++ | 150% | 137.5% | Outputs substantially exceeded expectation
A+ | 125% | 112.5% | Outputs moderately exceeded expectation
A | 100% | 87.5% | Outputs met expectation
B | 75% | 62.5% | Outputs moderately did not meet expectations
C | 50% |  | Outputs substantially did not meet expectations
n/a | 0%
Risk
Low | 1
Medium | 2
High | 3