Annual Review - Summary Sheet

Title: Financial Sector Deepening Zambia (FSDZ)
Programme Value: £15.0m		Review Date: November 2016
Programme Code: 203000	Start Date: May 2013	End Date: May 2018

Summary of Programme Performance
Year	28/02/2014	28/11/2014	27/11/2015	30/11/2016
Programme Score	B	A	A	A
Risk Rating	Medium	Low	Medium	Minor

Summary of progress

The Financial Sector Deepening Zambia (FSDZ) programme has been operating for three years, and 31 March 2016 marked the end of the programme delivery by DAI and the start of FSDZ as a local company limited by guarantee. FSDZ has continued to deliver strong results over this difficult period of transition as its systems and processes bed down, and its understanding of the market dynamics and financial inclusion environment in Zambia deepens. The transition also meant the recruitment of a new CEO, new Programme Investment Committee and Board of Directors; as well as agreeing new systems and processes, including taking on an independent fiduciary service provider. Co-funding from Sweden also came on stream during this period.

Besides these organisational changes, FSDZ continues to make a real difference to the lives of poor men and women. The Savings Group component was rolled out with three partners in different locations, which is giving poor people in rural areas the opportunity to collectively save and borrow individually for the first time, while also building assets to increase resilience to shocks and opening opportunities for income earning activities. In addition, more than 72,000 women have received financial education.

Policy makers and financial service providers (FSPs) have used the FinScope survey to enhance their understanding of the financial inclusion landscape in Zambia. In addition, the first cohort of the diploma course in SME Banking, offered together with the Zambia Institute of Banking and Financial Services (ZIBFS), graduated. Insurance companies are working on insurance products that are affordable for poor people, including weather index insurance for farmers. Overall, this means real people and businesses are accessing quality financial services that will make sustainable improvements to their livelihoods, and strong foundations are being laid for the expansion of inclusive financial services in Zambia.

Lessons learnt since last review

- Allowing adequate time for the effects of a market systems approach to take effect is necessary, which can clearly be seen in the J-curve growth of the Savings Groups[1].
  [1] J-curve growth refers to the slow initial establishment of Savings Groups in the early stages of the programme, with a more rapid increase in numbers later on due to for example the demonstration effect of existing groups.
- When transitioning from a supplier contract to a special purpose vehicle, DFID needs to ensure strong oversight of the transition process.
- Reaching women with financial services and education is still a challenge that requires continued effort, monitoring and innovation.

Summary of recommendations for the next year

Recommendations are listed throughout this review, but can be grouped in the following areas:

Logframe indicators
1. FSDZ and DFID should consider raising the 2018 targets for 1.1 and 1.2, pending the impact of the proposed wording changes which better capture quality.
2. A new indicator for output 6.2 should be agreed now that the SPV has been established, potentially focusing on external fundraising.
3. Add an indicator to capture quality of financial services and reach at Outcome level.

Research / Monitoring
It would be helpful to better understand the impact of the beneficiaries under output 3 and 2:
  1. What types of SMEs are benefiting (e.g. location, size, sector)?
  2. What is the experience of farmers enrolled in the weather insurance index?
1. FSDZ could do more to understand the impact of the SME diploma training.
2. Ensure that reporting on indicator 4.1 captures evidence that the Financial Service Providers (FSPs) are growing in their capacity to reach poor women, men and microenterprises.
3. Use a bigger sample to measure whether all Savings Group (SG) members are below $2.50 per day, and report on the percentage of PPI level 1.
4. Provide some form of continued monitoring (beyond the grant end) to ensure new SGs are well-supported by the Private Service Providers (PSP).
5. Undertake research on linkages to financial sector for SG members.
6. The Monitoring Impact Survey (MIS) of the different SGs is a very valuable source of information. It is recommended to:
  1. Add an indicator relating to quality or impact of the SGs rather than just the numbers reached.
  2. Pay particular attention in the CARE MIS to discern impacts of SGs in areas with Social Cash Transfer (SCT) beneficiaries.

Gender
1. FSDZ should consider how to reach women with financial education beyond the Savings Groups.
2. There seems to be no specific attention to women in microinsurance product development or consumer education, although microinsurance does get sold through women’s market groups. FSDZ and IAZ should ensure this is aligned to mitigate risks of selling products to potentially vulnerable or non-financially literate consumers.
3. Sweden’s support to FSDZ specifically focuses on women financial inclusion, which will likely offer valuable lessons across FSDZ’s work which the team should ensure are widely shared, including with DFID.
4. There might also be a need to revisit the ambitious targets that were set on reaching women.

Management
1. FSDZ should ensure continued close collaboration with Private Enterprise Programme Zambia (PEPZ) in joint initiatives such as the LiveLabs.
2. Continued emphasis on phasing out of FSDZ (financial) support on Insurance Week and the Technical Advisory Group (TAG).
3. Ensure the Regulatory Assessment Toolkit is utilised in time for the next Annual Review to formally measure progress on improving the capacity of policy makers.
4. FSDZ to update its finance and procurement and operations policies, as recommended by the 2016 due diligence assessment, to be approved at the next Board meeting in March 2017

Value for Money
1. Closely monitor admin costs and overall financial forecasts – ensure these are on track by March 2017.
2. The move to the Special Purpose Vehicle (SPV) structure means additional discussions are recommended on setting appropriate VfM indicators, including but not limited to agreeing a second Efficiency indicator and setting benchmarks for the Economy indicators based on international practice.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3549927.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4380062.xlsx

Outline of the programme
FSDZ is a five year programme to support inclusive financial sector development in Zambia. The programme targets increased access to a wide range of financial services from savings, through to loans, payment services, insurance and pensions for poor households, smallholder farmers and micro, small and medium-sized enterprises (MSMEs).

The programme takes a ‘making markets work for the poor’ approach and tackles a broad array of sector constraints at the policy level, through to direct interventions with financial service providers (FSPs). This includes commercial banks, microfinance institutions (MFIs) and community based finance initiatives. The programme initially was managed by a supplier, DAI, and following a 4 month inception phase, the 5 year programme commenced implementation in September 2013. In accordance with a clause in the contract, DFID took the decision to end the contract with DAI at the 3 year point and set up a special purpose vehicle to deliver the programme from 1 April 2016. This approach gives FSDZ more independence as a stand-alone Zambian organisation and allows FSDZ to diversify its funding sources away from dependence on UKaid. This change in delivery mechanism has not altered the goals of the organisation or the DFID Logframe targets.

The impact of the programme is to make sustainable improvements in the livelihoods of poor people by supporting 138,750 people with increased incomes or a reduction in vulnerability.

The outcome of the programme is a financial sector capable of delivering a wide range of financial services to more people and businesses in Zambia. It will provide:

- 300,000 additional people with access to finance (of which 65% will be women)
- 50,000 smallholder farmers with access to agricultural finance (of which 50% will be women)
- 12,000 additional SMEs with finance from banks and MFIs.

At impact and outcome level these figures are directly attributable to DFID funding.

FSDZ has focused on developing several thematic areas: Rural and Household Finance (RHF) including Insurance; SME Finance; Digital Financial Services (DFS); Policy and Financial Capabilities (PFC); and Information. Each of these thematic areas does not directly map onto a Logframe output or outcome. Rather, they interact with one another and each contributes towards various elements of the 5 programmatic Logframe outputs and the outcome targets. This is reflective of the market systems approach that underlies FSDZ’s design, and seeks to achieve an outcome that is greater than the sum of its parts. So although FSDZ reporting is disaggregated to show the contribution of each thematic area to each output and outcome, we would expect over time to see acceleration in progress towards the ultimate impact as systemic change takes place. Further information can be found at: www.fsdzambia.org

Context
Zambia has experienced significant growth in the last decade but with little change in poverty especially in rural areas. Poverty levels now stand at around 54.4% nationally and 76.6% in rural areas and have been relatively static for a number of years (LCMS 2015). Economic growth is narrowly focused around the mining, services and construction sectors, while most Zambians rely on subsistence agriculture for a living.

Evidence points to the development of the financial sector as an important driver of the rural economy and a critical means for poor people, small businesses and smallholder farmers to smooth income, manage risks and invest in productive capacity. Financial exclusion in Zambia remains high. It has reduced from 62% in 2009 to 40% in 2015, but this masks significant variations. Nationally, 62% of adults still have no access to formal financial services, and in rural areas 50% of adults have no access to any financial service, whether formal or informal. Exclusion is worse for women than men, and for farmers, fishermen, traders and casual labourers than formal wage earners.

The Government of Zambia has shown commitment to expanding financial inclusion and has implemented a Financial Sector Development Plan II (2010 to 2015), coordinated by the Bank of Zambia – though this ended on 30 June 2015. The Government has now established a Financial Inclusion Unit in the Ministry of Finance to lead the development of a National Financial Inclusion Strategy, although progress on this has been slow in 2016 despite assistance from the World Bank’s Financial Inclusion Support Framework. The 2015 FinScope showed good progress on financial inclusion, although there is still a long way to go on formal services when Zambia is compared to its peers. Although some issues have been identified at the policy level, many of the constraints to financial sector development arise from significant market failure and the focus and strategies of individual banks and other non-bank financial institutions (NBFIs). Most do not provide accessible financial services to the rural population in any significant way. Thus without catalytic interventions, many Zambians will continue to be financially excluded.

The output scores are set against the 31 March 2016 data, but the review also incorporates additional information collected since that point where relevant and informative.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
Progress against the March 2016 Outcome milestones is shown below.

Indicator(s)	Target for March 2016	Results achieved	Progress against milestone
Outcome indicator 1 Number of poor people and microenterprises accessing a new financial service	180,000 / (117,000 women)	219,557 / (99,554 women)	122% / (85%, but 45% of increased reach)
Outcome indicator 2 Number of smallholder farmers accessing a new financial service	15,000 / (7,500 women)	30,083 / (7,472 women)	201% / (100%, but 25% of increased reach)
Outcome indicator 3 Number of SMEs accessing a new financial service	4,000	10,006	250%

FSDZ has clearly exceeded all three of the outcome targets, although the disaggregated target on outcome 1 for women was not met. 45% of beneficiaries under Outcome 1, mainly from Savings Groups, life insurance provision and new money transfer clients, are women – which is largely the same as last year at 44% and short of the target of 65%. The additional Savings Groups that were created since March 2015 have raised this ratio somewhat as most of those are women-dominated – and the September 2016 report shows 50% of beneficiaries reached are women. However, FSDZ should ensure that women are also reached in the other areas of their work. Its new Women and Financial Inclusion programme, funded by Sweden, is an exciting development in this regard. FSDZ should redouble its efforts to reach more women, by revisiting its Gender Strategy and ensure lessons and innovations from the Swedish component are shared widely across FSDZ’s work. A discussion should also take place on the level of female reach that was set at the start of the programme, and a possible revision of those ambitious targets based on experience on the ground so far and the Swedish component findings.

The majority of results for outcome 2 are farmers accessing Weather Index Insurance. Outcome 3 results were achieved through support to SME financial service providers such as Investrust Bank and other banks and MFIs.

Given this track record we expect FSDZ to achieve the outcomes envisaged by the end of the programme in 2018. In fact, FSDZ is currently projecting to reach 333,000 poor people (outcome 1) by March 2017, a full year ahead of the 2018 final target of 300,000. As noted above, during 2017 DFID will explore extended funding for FSDZ and if this is forthcoming will agree a new set of targets for FSDZ from 2018-2021. An additional indicator to measure the quality of the financial services being accessed would also be required at that stage.

It is also worth noting that 31 March 2016 was the first year that FSDZ was able to collate data to measure progress against the overall impact target. This has been exceeded by 46% – 63,166 poor people (against a target of 43,250) have experienced an expansion in income opportunities or a reduction in vulnerability thanks to FSDZ. Of these, 51,676 were women, which exceeds the target of 28,113 by 84%.

Overall output score and description
The overall output score is Outputs met expectation (A). Detailed output scoring follows in section C. It should also be noted that the first five outcomes, for which FSDZ is directly responsible, performed above expectation at A++ or A+ level, whereas the final one – on the transition from a DAI contract to independent company – received a B.

Key lessons
FSDZ continues to take a holistic, thorough, market systems approach[2] that will ensure systemic and sustainable change. Allowing adequate time for the effects of a market systems approach to take effect is necessary, which can clearly be seen in the J-curve growth of the Savings Groups.
[2] Market systems approaches, or Making Markets Work for the Poor (M4P), reduce poverty by enhancing the ways that poor people interact with markets. For more information, see the Donor Committee on Enterprise Development (DCED): http://www.enterprise-development.org/implementing-psd/market-systems/

When transitioning from a supplier contract to a special purpose vehicle, DFID needs to ensure strong oversight of the transition process. In the case of FSDZ, the DFID Senior Responsible Owner (SRO) established a Transition Committee (comprising DFID, DAI London and the FSDZ Technical Director) which met weekly and was chaired by DFID. This committee was crucial to ensuring timely and effective transition to a Special Purpose Vehicle.

Agreements made between DFID and suppliers should be formally written into contract amendments in order to avoid lengthy disputes.

DFID’s milestone payment approach does not always create the right incentives for suppliers nor give DFID sufficient control – it is hard to agree on appropriately specific and meaningful milestones in advance.

Key actions
DFID Zambia met with FSDZ during the year to discuss the future of DFID funding. Currently DFID funding ends on 31 March 2018, which is two years after the new special purpose vehicle has been set up. It was agreed that this is a short timeframe for FSDZ to secure full funding from other sources to continue beyond 31 March 2018. It was therefore agreed that during 2017 DFID Zambia will seek ministerial approval for 3 years of additional funding. This will be structured in such a way as to incentivise FSDZ to raise funding from other sources – e.g. DFID will cover an element of core costs and will offer additional programme funding as long as it is matched from other sources, up to a certain level. That is – for every £1 that FSDZ raises from another source, DFID will match it with £1. This is to ensure a smooth and sustainable exit from DFID Zambia funding in 2021.

Besides follow up on the recommendations, there are 3 key actions DFID and FSDZ will need to undertake in the coming year:
Monitor administration spend under the new governance structure – encourage FSDZ to keep levels of admin spend below the agreed 17.5% in the concept note as we move beyond the transition period.
- Increase and monitor efforts to reach women, particularly outside of Savings Groups;
- Bed down governance processes (especially operation of the Programme Investment Committee).

Has the logframe been updated since the last review?
Following last year’s Annual Review, in consultation and agreement with DFID, FSDZ revised the wording of 7 logframe indicators to better capture both the quality, and the qualitative aspects of FSDZ’s work. The changes are summarised below. Output indicator 3.2 will be measured using an 8-scale assessment tool (more information in section C under Output 3).

Previous output indicator wording	Revised wording
Output Indicator 2.2: % change in capacity of policy making bodies to formulate and implement effective financial sector policies and regulation	Improved capacity of policymakers to formulate and implement effective financial sector policies and regulations
Output indicator 3.1: number of Financial Service Providers (FSPs) benefitting from new or improved support service	Number of new or improved support service offerings to stakeholders
Output indicator 3.2: Number of categories of financial infrastructure recording improved service delivery to FSPs	Number of financial infrastructure functions recording progress during the year
Output indicator 4.1: Number of FSPs with increased capacity to reach poor women and men with financial services	Number of FSPs with increased capacity to reach poor women and men, and microenterprises with financial services
Output indicator 5.1: Number of FSPs with increased capacity to reach MSMEs with financial services	Number of FSPs with increased capacity to reach SMEs with financial services

It was also agreed to reduce the output level targets for indicator 4.2 “Number of sustainable community based financial institutions providing financial services to poor women and men” for March 2017 from 6,000 to 5,000 groups, and for March 2018 from 7,500 to 5,500 groups. FSDZ is confident that this will not have an impact on achieving the outcome level indicators – which as seen above, are already exceeding their targets.

## C: DETAILED OUTPUT SCORING

Output Title	More and better industry data and public information on the financial sector is available and used by stakeholders
Output number per LF		1	Output Score	A++
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		Y (from Low)	Impact weighting % revised since last AR?	N

Indicator(s)	Results target for March 2016	Results achieved	Related comments
Output indicator 1.1 Number of financial sector stakeholders using new and industry data and public information products	14	28	200%
Output indicator 1.2 Number of target beneficiaries receiving financial education	90,000 / (45,000 women)	113,727 / (72,630 women)	126% / (161%)

Key Points
FSDZ is doing excellent work to build the evidence and statistical base in Zambia on financial inclusion.

Output indicator 1.1 was exceeded by 100%, recording 28 stakeholders using new data and information from FSDZ. The critical message videos for Savings Groups reached 12 partners, while 7 organisations were provided with the FinScope database – including the Bank of Zambia, the African Development Bank, the World Bank, and Standard Bank. 9 SME partners used FSDZ’s Relationship Banking papers.

FinScope is an impressive survey (especially so since it is representative to the district level). DFID met with several FSDZ partners during the Annual Review period, including the Bank of Zambia, who highlighted their appreciation of the information included in FinScope. FSDZ has done an excellent job at publicising the dataset through events and through distributing more than 1000 copies of the report. The topic specific papers are excellent way to break down the data into more focused detail.

Another major achievement over this period was FSDZ’s geospatial mapping exercise. Whereas the FinScope study provides valuable insights with regard to financial sector usage, information was still missing on proximity of access. The geospatial mapping took this additional step and mapped 28,061 service access points, including 15,371 financial service access points, 7,336 educational service access points, 1,462 health service access points and 3,892 agricultural service access points. Data was collected between September and December 2015, verified with key stakeholders in February 2016 and analysed in March. The public launch took place in May 2016.

Output indicator 1.2 was exceeded by 26% and the gender target by 61%. This was primarily delivered through Savings Groups; education to farmers receiving life insurance; and large scale campaigns through Insurance Week and Financial Literacy week. The majority of the women being reached with increased financial education is through the Savings Groups –which comes to an end before the 2018 programme completion. Although it is excellent to see such a significant proportion of women, it would be helpful for FSDZ to consider how to better reach significant numbers of women through the other channels such as the Insurance and Financial Literacy weeks.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
Both 1.1 and 1.2 are relatively crude quantitative indicators that do not capture quality (e.g. of the information provided/used, or the education received), while the overall output is “more and better data”. FSDZ, in discussion with DFID, should consider revising these indicators in a way that can capture quality.	FSDZ has proposed ways to measure more qualitatively the ‘better’ data component of this indicator. FSDZ will measure for indicator 1.1: / A qualitative assessment of the relevance, robustness, and technical content of the new data products; / A qualitative description of how new data products are being used by stakeholders to fill information gaps to address market failures and take advantage of opportunities; / Qualitative feedback from stakeholders regarding new data products and how they assist them to understand markets and end clients better, to set/improve rules, create new partnerships/deals, increase capacity, change practices, form new relationships, enter new markets, or develop new services for better financial inclusion facilitation and deepening. / And for indicator 1.2: / Qualitative feedback on how poor women and men understand financial services offered. / A qualitative assessment of the relevance, satisfaction, and content of financial education to inform financial decisions of poor women and men; / Qualitative feedback on poor women and men’s ability to make appropriate choices regarding financial services on offer.
FSDZ could consider documenting a few case studies on women’s financial education to complement the quantitative numbers reported	FSDZ documented several case studies during the year on women’s financial management as a result of financial education received by participating in Savings Groups. FSDZ will also carry out a more detailed investigation into the role of financial education and capabilities among female Savings Group members during the coming year.

In addition, in response to last year’s recommendations FSDZ proposed changing the wording of the two indicators to better capture the quality aspects as follows:
- Indicator 1.1: Number of stakeholders recording relevance of technical content of new industry data and public information products to inform decisions.
- Indicator 1.2: Number of target beneficiaries receiving financial education to understand financial services and make better financial management choices.
DFID agrees with the proposed changes and suggested ways to qualitatively measure these as outlined in the table above. These will be measured for the next annual review. Particular attention will need to be paid to ensure that there is verifiable evidence that the 113,000 beneficiaries reached have also all made better financial management choices.

Recommendations
1. FSDZ and DFID should consider raising the 2018 targets for 1.1 and 1.2, pending the impact of the proposed wording changes to better capture quality.
2. FSDZ should consider how to reach women with financial education beyond the savings groups.

Output Title	Improved policy and regulatory environment for the delivery of financial services
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y (from Medium)	Impact weighting % revised since last AR?	N

Indicator(s)	Results target for March 2015	Results achieved	Related comments
Output indicator 2.1 Number of organisations demonstrating improved effectiveness in advocating for financial sector reform	3	4	133%
Output indicator 2.2 Improved capacity of policy makers to formulate and implement effective financial sector policies and regulations.	5%	Not formally measured	The Regulatory Assessment Toolkit was not deployed to measure progress. However, partner feedback from Pensions and Insurance Authority (PIA), Bank of Zambia (BoZ) and Patent and Companies Registration Agency (PACRA) is positive.

Key Points
On indicator 2.1, FSDZ is providing support to the Insurers’ Association of Zambia (IAZ) for the development of their Strategic Plan 2015-2019, and for Consumer Education (for example to expand the annual Insurance Week, which is now co-funded by its members). FSDZ also fulfils the secretariat role at the microinsurance Technical Advisory Group (TAG), which was highly appreciated by IAZ who commented on FSDZ’s pivotal role in the development of this market in Zambia. However, it is important for FSDZ to think about sustainability of this work: the Insurance Week is in its 4th year and although it is co-funded by the insurance companies, there should be a clear plan to move this to complete self-funding (similar to the TAG, where a plan has now been drawn up and accepted by its members to move the Secretariat to IAZ). The other two organisations supported under this output are the Bankers Association of Zambia and the Digital Financial Services (DFS) Working Group – which was established by FSDZ during the review period. There is evidence of the improved effectiveness of these organisations in terms of advocacy[3].
[3] FSDZ collected qualitative feedback through interviews with members of the TAG including the Chair and the IAZ Executive Director, which are available on the FSDZ podcast.

This is the first year a target has been set for output 2.2, which aims to measure the impact of FSDZ’s policy influencing work with partners. By March 2016, FSDZ developed a ‘Policy and Regulatory Assessment Toolkit” to measure partner’s capacity to formulate, implement and improve policy and regulatory development. The first partner to apply the toolkit was the Pensions and Insurance Authority (PIA). A baseline was constructed, however it was then decided to postpone measuring of PIA’s capacity changes until Quarter 4 of 2016/2017 as the current level of FSDZ contributions was deemed not sufficient to justify the costly detailed evaluation. This is somewhat disappointing, as it would have been valuable to be able to measure more quantitatively FSDZ’s many anecdotal examples of policy impact. Over the next year, the Tool will be applied to PIA, the Bank of Zambia and the Patent and Companies Registration Agency (PACRA).

This would also further support the positive feedback from partners interviewed during the review period. For example, PACRA commented they were very pleased with FSDZ support on the public communications on their new Collateral Registry. PACRA was fully involved in the process of choosing a consultant, and is also receiving technical advice from FSDZ where necessary. In the next Review, we look forward to having an assessment of the impact of this positive working relationship in terms of PACRA’s improved capacity with the Policy and Regulatory Assessment Toolkit.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
The technical team should give careful consideration as to how “a percentage change in capacity of policy making bodies” will be accurately measured in March 2016 and whether this is a meaningful indicator. The Logframe targets for March 2016, 2017 and 2018 are 5%, 15% and 25% respectively - what do these mean? Will only one policy making body be tracked over time, or several?	The Toolkit has been developed over this period, but not yet fully applied beyond establishing a baseline for PIA. Each policy body (BoZ, PIA, PACRA) will be assessed separately, with focused recommendations for further improvements. An international expert will be contracted to complete these Assessments in time for the next annual review.
FSDZ should ensure it engages closely with the World Bank FISF team to ensure coordination and complementary efforts at supporting policy and regulatory improvement.	Regular meetings with the WB FISF teams were held during the reporting period. FSDZ also works closely with the WBG (IFC) on developing infrastructure (e.g. collateral registry) which has policy and regulatory aspects.

Recommendations
1. Continued emphasis on phasing out of FSDZ (financial) support on Insurance Week and the TAG.
2. Ensure the Regulatory Assessment Toolkit is utilised in time for the next Annual Review to formally measure progress on improving the capacity of policy makers.
3. There seems to be no specific attention to women in microinsurance product development or consumer education, although microinsurance does get sold through women’s market groups. FSDZ and IAZ should ensure this is aligned to mitigate risks of selling products to potentially vulnerable or non-financially literate consumers.

Output Title	Adequate infrastructure and support services in place to support financial sector development
Output number per LF		3	Output Score	A+
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		Y (from Low)	Impact weighting % revised since last AR?	N

Indicator(s)	Results target for March 2016	Results achieved	Related comments
Output indicator 3.1 Number of new or improved support service offerings to stakeholders	6	10	167%
Output indicator 3.2 Number of financial infrastructure functions recording progress during the year	3	3	100%

Key Points
An important component of a market systems approach to financial sector development is ensuring sufficient market infrastructure and support services are in place (the meso level – for example a credit reference bureau or collateral registry), to facilitate effective functioning of the market at the micro level. This is almost a ‘behind the scenes’ component, but a critical one nonetheless.

The wording for indicator 3.1 was changed so it could demonstrate innovation and quality of services rather than just counting the number of Financial Service Providers (FSPs). Like last year, the target was exceeded with FSDZ facilitating improved support services to ten stakeholders against a target of six. This cumulative number includes support from Catholic Relief Services to the Catholic Diocese of Ndola (CDN) to run their Savings Groups; support from MicroSave to help transform MFinance into a deposit taking institution; SME relationship banking training via the Zambia Institute of Banking and Financial Services (ZIBFS) to various banks; continued support from the Technical Advisory Group (TAG) to insurers such as African Life and Professional Insurance.

Also indicator 3.2 changed from last year to better capture progress in the area of financial infrastructure development. FSDZ developed a ‘Financial Infrastructure Status Assessment matrix’ to benchmark progress along 8 levels as described in the table below.

Level 0	Nothing in place
Level 1	Stakeholders in broad agreement on need and functionality of the infrastructure
Level 2	Operational plan developed
Level 3	Enabling regulations / legislation in place
Level 4	Funding secured and contract awarded for development of the infrastructure
Level 5	Infrastructure in place and fully operational
Level 6	Infrastructure in use by < 10% of relevant FSPs
Level 7	Infrastructure in use by < 50% of relevant FSPs
Level 8	Infrastructure in use by > 50% of relevant FSPs

In each infrastructure area FSDZ will measure progress annually. Where last year only the ZIBFS recorded progress, this year also the Credit Reference Bureau (Level 1) and Collateral Registry (Level 3) can be reported on. In addition, ZIBFS also continued to improve (Level 2). The relatively low levels reached on these infrastructure scores also demonstrates continued need for FSDZ involvement in these areas. The table below will allow for tracking improvements over the coming years.

Infrastructure	Achievement Level 2016
Zambia Institute of Banking and Financial Services	Level 2
Credit Reference Bureau	Level 1
Collateral Registry	Level 3

FSDZ’s efforts have focused on supporting the ZIBFS to upgrade its training capacity for SME finance. The goal of this intervention is to build a pool of bankers with specific skills to manage SMEs. At the time of meeting with the ZIBFS, two courses had been delivered. The relationship between ZIBFS and FSDZ did not appear to have always been smooth, and continued communication from both sides on expectations of anticipated work and outputs is key. Feedback from several of the banks who had sent personnel on these courses was positive (AB Bank, Cavmont) – although it was also mentioned the course is a big time commitment and more senior staff might not be able to combine it with the heavy demands they face in their job. A very good example is that the Zambian Chief Operating Officer of AB Bank is a graduate of the course, who commented that succession planning and handover to local staff were two positive results from working with FSDZ.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
Consideration should be given to whether “categories” of financial infrastructure is a valuable indicator for this output, and whether a more suitable indicator can be used in its place.	Done – new wording has been agreed.

Recommendations
1. FSDZ could do more to understand the impact of the SME diploma training – for example through interviews with bank managers, participants or considering evidence from participating banks’ SME portfolios. This would also help in promoting the course in future.

Output Title	Increased capacity of financial service providers to deliver products that are accessible, affordable and appropriate to poor people
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y (from Medium)	Impact weighting % revised since last AR?	Y (from 35%)

Indicator(s)	Results target for March 2016	Results achieved	Related comments
Output indicator 4.1 Number of financial service providers with increased capacity to reach poor women, men and microenterprises with financial services	8	13	163%
Output indicator 4.2 Number of sustainable community based financial institutions providing financial services to poor men and women	4,500	2,810	62%

Key Points
The target for indicator 4.1 has been substantially exceeded, with FSDZ counting 13 Financial Service Providers (FSPs) as having increased capacity to reach poor men and women against a target of 8. This includes competitive grant recipients of the Microinsurance Accelerator Facility (such as Professional Life); various insurance stakeholders that have received technical assistance such as health insurance training (Barclays Life, African Life, Holland Life); support to Zoona to increase access to money transfers and technical assistance to MFinance from MicroSave. It should be noted that this is continued support to these FSPs as they were reached by FSDZ during the last reporting period as well.

It would be helpful to understand better the evidence that FSPs are growing in their capacity to reach poor women, men and microenterprises – in addition to the increased number of beneficiaries they are reaching within these groups.

On indicator 4.2, progress continues to be slower than expected. By end-March FSDZ had facilitated the creation of 2,810 Savings Groups (Catholic Diocese of Ndola (CDN): 1,659 - CARE: 502 - PLAN: 634 - FSDZ groups: 15) against the target of 4,500. There are several factors behind continued (but accelerating) progress on this indicator:
- FSDZ continued to note that the scope and capacity of local Savings Groups (SGs) in Zambia is far lower than had been expected. This has meant that Q1 for all partners is spent as a ‘start up’ quarter to prepare the communities they will operate in, rather than immediately starting Savings Groups. On the other hand, acceleration in subsequent quarters is faster than expected, reinforcing the point made in the last ARs that progress is not linear but has a “J-curve” growth, also building on the demonstration effect in communities.
- PLAN also noted that uptake is much lower in the rainy season as people are busy with planting and tending their fields, and that the election period undermined some of their work through handouts.
- CARE started later than expected due to unforeseen circumstances with a delivery partner, which meant they implemented the groups themselves.
- Field data verification reduced some of the numbers as the partners starting using SAVIX MIS as their management information system. This was the result of corrections in terms of overlap and double-counting, but this has improved the quality of reporting. PLAN is now also using the SAVIX, and during the review visit the team saw a demonstration of this rich, online dataset.

Although progress is slower than expected in the logframe in terms of number of groups, FSDZ and partner projections show they are now much more in the ‘acceleration’ part of the J-curve and are therefore confident the end-of-programme targets on access will be reached.

Several other issues came up when the review team visited the implementing partners:
- Some members join 2 groups as they feel they cannot save enough in just one. It is unclear whether this is a widespread practice, but FSDZ should ensure no double-counting of these SG members occurs. It also raises a question on linkages to the more formal financial sector for more experienced Savings Group (SG) members who may need access to additional financial services. . There might be linkages to explore with mobile financial services providers such as Zoona. FSDZ is undertaking research on linkages with FSD Uganda and will be piloting new digital financial services to savings groups under the new Sida funding.
- The J-curve growth also means many new groups will be set up towards the last quarters of support from FSDZ and its partners, and will move directly to the Private Service Provider (PSP) model. Although there are several safeguards within this model (i.e. the PSP have been trained and get continued support from a master trainer and their PSP network; and quality is important for their reputation and future business development), FSDZ and partners should provide continued monitoring to ensure these groups are well-supported by the PSPs.
- Linkages to other programmes: CARE operates in areas where Social Cash Transfers (SCTs) are distributed as well. In these areas it could help SCT recipients have a safe place to save and manage money. CARE noted the the SGs seem to also help prevent people from falling back on SCTs. It would be interesting for the Monitoring Impact Survey (MIS) of the CARE Savings Groups to consider the interaction between SG and SCT beneficiaries. CARE also wondered if more could be done to link SG members to skills training and potentially large scale economic empowerment programmes for women and youth.

All partners mentioned that FSDZ’s results team is responsible for measuring impact of the SGs. One Monitoring Impact Survey (MIS)was done with Catholic Diocese of Ndola (CDN) beneficiaries in 2015. This was a quantitative survey of 150 beneficiaries in 5 districts in the Copperbelt, and in-depth interviews with 10. This showed that 60% use savings to improve or start a business and 33% to pay school fees. The Social Fund (a small fund that each member contributes some kwacha to at each meeting) was used to pay for emergency medical expenses or funerals. These findings point to a reduction in vulnerability and an increase in income-generating opportunities for SG members.

FSDZ does not measure reductions in poverty amongst beneficiaries (for example there are no baseline measurements of new SG members), but uses the Progress out of Poverty Index (PPI) to measure poverty levels of SG members. FSDZ used a PPI approach on the sample of 150 to calculate that all respondents were from a household with an income of less than USD2.50 per day. FSDZ then assumed that all members of CDN, CARE, Plan and FSDZ Groups have similar socio-economic status. The review team noted it would like to see more evidence from a bigger sample outside of CDN-beneficiaries, to come to this conclusion. It would also be interesting to know how many beneficiaries are at PPI level 1. FSDZ is planning another MIS with beneficiaries from the other partners as well, which should provide more of this evidence. In addition, it was noted that by only doing a MIS , there is no real-time monitoring and no opportunity for possible adjustments. The SAVIX MIS could provide more opportunities for this.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
FSDZ should explore options to scale up Savings Groups interventions that are excelling at both quantity and quality in terms of Savings Groups (e.g. consider increasing support to the partners/projects that are doing well), or agree with DFID to scale down the ambitions of this target in line with on the ground experience.	FSDZ decided to stick to original distribution of resources to the three implementing partners. The difference in reach was due to unexpected later starts, and being in different sections of the J-curve. All partners are expected to meet agreed targets by the end of their grant agreements.
Consideration should be given to scaling up the more cost effective Savings Groups channels, as well as to understanding why there is such large variation in delivery costs across partners (see VFM section).	Grant agreements for CDN, PLAN and CARE end in FY2016. Cost-Per-Member (CPMs) were projected for each of the grantees at end-of-intervention and will be evaluated then. Projected CPMs will most likely differ from end-of-grant CPMs, and FSDZ will make recommendations on the different implementation models (direct vs indirect, with or without a TA component).

Recommendations
1. Ensure that reporting on indicator 4.1 captures evidence that the Financial Service Providers (FSPs) are growing in their capacity to reach poor women, men and microenterprises.
2. Use a bigger sample to measure whether Savings Group members are below $2.50 per day, and report on the percentage of PPI level 1.
3. Provide some form of continued monitoring (beyond the grant end) to ensure new Savings Groups are well-supported by the Private Service Providers (PSPs).
4. Undertake further research on linkages to the formal financial sector for SG members.
5. The MIS of the different SGs is a very valuable source of information. It is recommended to:
  1. Add an indicator relating to quality or impact of the SGs rather than just the numbers reached.
  2. Pay particular attention in the CARE MIS to discern impacts of SGs in areas with SCT beneficiaries.

Output Title	Increased capacity of financial service providers to deliver products that are accessible, affordable and appropriate to MSMEs and smallholder farmers
Output number per LF		5	Output Score	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		Y (from Low)	Impact weighting % revised since last AR?	Y (from 25%)

Indicator(s)	Results target for March 2016	Results achieved	Related comments
Output indicator 5.1 Number of financial service providers with increased capacity to reach SMEs with financial services	6	13	217%
Output indicator 5.2 Number of financial service providers with increased capacity to reach smallholder farmers with financial services	4	4	100%

Key Points
Output indicator 5.1 was substantially exceeded, as FSDZ has supported a range of financial service providers to improve their ability to serve SMEs, including MFinance, Focus Finance, MicroFinance Zambia, Investrust Bank, AB Bank and Cavmont. The objective is to build capacity within these institutions to increase their SME Finance operations and to better serve the SME segment. One example on how to do this is through the SME training course for bank staff – which is described under Output 2. Capacity of these FSPs is not measured as such, but the fact that additional SMEs are reached is an indicator of improved capacity throughout the sector. It would be interesting to understand whether this trend is driven by a small number of FSPs or by all those supported.

It should be noted that the current macroeconomic situation has made commercial finance to the private sector in Zambia very expensive (and hard to come by given high government borrowing, and very limited liquidity in the market), and it was noted by several of the banks interviewed that this is posing a constraint on their ability to increase the SME portfolio. One bank mentioned its interest in working with both FSDZ and Private Enterprise Programme (PEP) Zambia on the SME LiveLabs, but noted a need for continued alignment of the 2 programmes.

For output 5.2, Over the reporting year, three additional aggregators were supported to partner with insurance companies to offer weather index insurance to smallholder farmers. Feedback from one of the insurance companies was that this was a new market for them, and they had suffered losses in these initial years (likely also due to El Niño’s impact on agricultural production) but they were continuing their efforts. The review team did not manage to speak to one of the aggregators or the beneficiary farmers, and we would encourage FSDZ to understand the experience of the farmers as the ultimate beneficiaries of these interventions.

As noted in the last Review, FSDZ has consistently struggled to recruit an appropriately skilled senior expert to lead its agricultural finance and small holder farmer work, which has reduced its ability to deliver in this area. In May 2016, FSDZ recruited a new full-time Project Manager who has already worked with an expert consultant to develop a new Rural and Agricultural Finance project that has been presented to the Investment Committee. This is now undergoing some refinement but FSDZ is confident it will make significant progress over the coming year.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation last AR	Progress so far
Given the slow progress on smallholder farmers, FSDZ should perhaps step back and identify clearly what the need is, what other players are already doing, what role FSDZ can best play and how. Having a strong lead expert on this area would help make a difference and perhaps new ideas can be proposed on how to attract the right talent.	FSDZ recruited a full-time Project Manager in May 2016 who has already helped develop a new Rural and Agricultural Finance project.
Consider increasing the impact weighting from 25% to 30% as these two outputs (5.1 and 5.2) contribute directly to two outcomes (SMEs and smallholder farmers). The impact weighting of output 4 could be reduced from 35% to 30% as it only contributes directly to one outcome (poor men and women).	The output weighting has been revised following a recommendation in the last review, from 25% to 30% as this output contributes directly to two outcomes (SMEs and smallholder farmers). The impact weighting of output 4 has been reduced from 35% to 30% as it only contributes directly to one outcome (poor men and women).

Recommendations
1. It would be helpful to better understand the impact on beneficiaries of services delivered under both these outputs:
  1. What types of SMEs are benefiting (e.g. location, size, sector)?
  2. What is the experience of farmers enrolled in the weather insurance index?
2. FSDZ should ensure continued close collaboration with PEPZ in joint initiatives such as the LiveLabs.

Output Title	Establishment and operation of Access to finance Zambia
Output number per LF		6	Output Score	B
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y (was High)	Impact weighting % revised since last AR?	N

Indicator(s)	Results target for March 2016	Results achieved	Related comments
Output indicator 6.1 Strategic plan and business plan completed	Annual workplans and budget submitted, approved and implemented and programme managed effectively and efficiently by the supplier.	Workplans and budgets submitted, and broadly accurate financial forecasts provided. Quarterly reports submitted on time.	Score in the Contract Performance Review by DFID decreased between May and November 2015. Several milestones were delivered late.
Output indicator 6.2 Special purpose vehicle established and operational	SPV established	The SPV was established and operational by 1 April, although several activities such as IT transition were delayed.	FSDZ staff worked hard to get everything in place by 1 April. DAI opened a contract dispute with DFID which delayed several activities.

Key Points
Under indicator 6.1, reporting by the FSDZ team has been excellent – high quality quarterly and annual reports have been delivered on time (within a month of the quarter end). Monthly financial forecasts have generally been accurate up to 31 March, although following the transition to a new entity on 1 April financial forecasting has faced some challenges.

In March, a 3-year Strategy and Budget were submitted and approved by the new Board of Directors – and an Annual Workplan was developed for the 2016-2017 period including an annual budget. The implementation of the budget has since then run into some problems with overspend on operational costs. It was difficult for the new FSDZ management to make an accurate assessment of running costs as this was done centrally during the DAI-contract. This also meant there was no local system in place to precisely report on funding items. Moreover, the transition period meant additional management costs were incurred, and the lack of any systemic automation or computer systems management added significant additional costs.

Prior to the transition, in November 2015 DAI scored lower in DFID’s Contract Performance Review than in the review 6 months earlier. This reduction was driven by particularly bad scores on regularity of communication with DFID and delivery of agreed action points.

On output indicator 6.2, significant amount of effort was required to ensure that the transition happened on 1 April 2016. DFID constituted a transition committee in September 2015, comprising DFID (chair), DAI London and the FSDZ Technical Director, which met weekly to agree actions and monitor progress towards the transition. Progress on the action points was mixed. There was considerable uncertainty for local staff as the process for contract termination/renewal or novation was not handled in a timely manner nor well communicated, and several critical components such as transition of IT software and hardware were delayed well beyond 1 April.

As described in earlier sections, DAI ceased delivering the FSDZ programme from 1 April 2016.

Summary of responses to issues raised in previous annual reviews

Recommendation last AR	Progress so far
The transition committee must continue to ensure timely progress on all aspects of the transition, with DAI applying sufficient resource to this process and maintaining effective delivery of programme outputs and results.	Progress was mixed – numerous delays occurred during the transition process, but ultimately the new FSDZ was able to start operating on 1 April.

Recommendations
1. Closely monitor admin costs and overall financial forecasts – ensure these are on track by March 2017.
2. A new indicator for output 6.2 should be agreed now that the SPV has been established, potentially focusing on external fundraising.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Note that with the ending of the service provider contract and move to SPV, the cost structure has now changed. The overview below is based on the financial year ending 31 March 2016 and the VfM Monitoring System used under the DAI-contract.

Key cost drivers and performance
The majority of FSDZ support is capacity building and technical assistance, with a major cost driver being staff salaries (permanent staff and consultants) and associated costs. The Economy measures were chosen to reflect these key costs and how FSDZ aims to keep them under control. In the original contract, the milestones versus total programme spend ratio was agreed at 41%, where at the end of March 2016 this stood at 38% (i.e. slightly lower milestone payments to DAI). This ratio should not be compared to a admin vs total cost ratio, as the milestones included technical payments and DAI’s profit margin or mark up besides pure admin costs. Under the new governance structure, an additional economy indicator on the admin versus total, including targets, should be added.

Economy
Indicator 1: Ratio of national to international STTA consultants
This indicator compares trends of the use of Zambian and international expertise, with the aim of having a cost effective and appropriate mix of international and national staff while not compromising on quality. The table below shows a clear move towards a more balanced mix, which is welcomed for the longer-term M4P knowledge in Zambia. These ratios should be benchmarked ahead of the next Review.

Consultants	March 2015	March 2016
National STTA	5	10
International STTA	20	12
Ratio	1/5	1/1.2

Indicator 2: Cost savings (£)
FSDZ annually report on costs savings through 2 main channels: use of its guesthouse for external consultants and use of the FSDZ office for (smaller) conferences or workshops. FSDZ saved £17,100 by using its guesthouse rather than hotels, and £1,365 from using the FSDZ training centre. These are both lower savings than over 2015, when the guesthouse was used more frequently and saved FSDZ nearly £50k in accommodation expenses. The quality of the guesthouse deteriorated with frequent lack of water or power – and a new guesthouse needs to be sought. FSDZ should ensure that the savings calculated in this indicator take account of the guesthouse costs, and a target should be set for next year.

Efficiency
Indicator 1: Average cost per beneficiary (ACPB)
This indicator mainly looks at Savings Group (SG) beneficiaries. As all costs of the intervention are included, the costs are higher in the early stages of the intervention but reducing over time. The average cost across the region (Tanzania, Uganda, Kenya) is £14, and the forecasted ACPB for the different SG providers was expected to be between £7 and £16. As the table shows, Catholic Diocese of Ndola (CDN) and PLAN are already performing below their respective expected ACPBs with CARE making good progress towards it target.

	CDN	CARE	PLAN
Expected Cost per Beneficiary at end of grant	£12	£7	£16

Cost as at March 2015	£221,042	£69,671	£138,726
Number of beneficiaries reached as at March 2015	15,930	2,410	0
Cost per beneficiary	£13.88	£28.91	N/A

Cost as at March 2016	£319,381	£96,249	£176,053
Number of beneficiaries reached as at March 2016	40,075	10,057	12,148
Cost per beneficiary	£7.97	£9.57	£14.49

Indicator 2: Partner leverage ratio
This ratio reflects the partner contribution as a percentage of the FSDZ financial commitment. FSDZ negotiates strongly when providing financial support, whether it is grants to NGOs for savings groups, or co-financing with MFIs or commercial banks for capacity building. For private sector partners, the target is to achieve a ratio of no more than 50% contribution by FSDZ. Four of the 16 agreements show this ratio, which is a reduction from 5 out of 9 in the last AR. It is recommended FSDZ continues to strive for 50% or more partner contributions.

Indicator 3: Percentage partnerships resulting in sustainable practice change
This indicator aims to measure change in systems and processes practices that result from being in partnership with FSDZ, for example improved procurement processes, or better financial planning. This is a qualitative measure, and more thought could be put into how to report on this – for example through the use of case studies – and the use of it as an indicator in the VfM matrix. For example, at the end of this reporting period, the Catholic Diocese of Ndola (CDN) has shown very good results and improved capacity – which FSDZ attributes to better resource planning, close cooperation with Catholic Relief Services and therefore better implementation on the ground.

Indicator 4: Crowding in ratio
This indicator attempts to capture FSDZ’s success in achieving market system change, but has not been reported on for this year.

Effectiveness
Indicator 1: Number of actual people utilizing financial services vs planned
This is a cumulative count of beneficiaries reached against planned outreach under outcomes 1, 2 and 3 (poor people, microenterprises and smallholder farmers accessing a new financial service). As the earlier sections showed, FSDZ is reaching good numbers and performing well above its targets.
Indicators Outcome	Milestone March 2016	Progress
Outcome Indicator 1: poor people/micro-enterprises access a new financial service	180,000	219,557(122%)
Outcome Indicator 2: smallholder farmers access a new financial service	15,000	30,083 (201%)

Indicator 2: To be determined
Up until last year, a second effectiveness indicator measured the number of beneficiaries per £1 spend but it was recommended to be dropped as it was not easy to interpret. DFID and FSDZ are in discussions on an alternative VFM measure, for example on measuring the economic returns on specific projects.

Equity
Indicator 1: Percentage of beneficiaries that is female
As the Outcome indicator section showed, reaching women with financial services remains a challenge. Although the Savings Groups reached very good numbers of women (90%), this is not the case in other interventions which means that the overall reach is 45% compared to a 65% target. Similarly under the Insurance and Rent To Own interventions, women were 25% of those reached.
In March 2015 FSDZ updated its Gender Inclusion Strategy, which identified several interventions where gender mainstreaming would increase women’s’ participation. As noted earlier in this review, DFID and FSDZ should continue to aim to reach more women and monitor this.

Indicator 2: Percentage of beneficiaries below $2.5/day as measured by PPI
This indicator uses the Progress out of Poverty Index (PPI) which uses 10 simple questions about a household’s characteristics and asset ownership to compute the likelihood that the household is living below the poverty line. The first PPI results were collected during the reporting period and give an indication that all FSDZ beneficiaries are below $2.5/day. However, a large sample size covering different geographical areas would give a better picture, and consideration should be given to reporting on a lower $/day ratio as well.

VfM performance compared to the original VfM proposition in the business case
The Business Case for FSDZ highlighted a range of difficulties associated with assessing the cost benefit ratio for this type of project. In particular, the nature of the intervention means that neither the resources required for individual interventions, nor their intended outcomes are known ex-ante. This places additional emphasis on the need for strong monitoring of value for money during project implementation. Given this, the business case recommended the measurement of three types of indicators:
The ratio of programme management to total costs (<20%);
- Estimated economic returns on specific project activities (>15%), and;
- The cost of financial inclusion for each additional person (<£24).
Over the programme’s implementation, the VfM matrix was developed which aims to cover several of these proposed indicators alongside others. The move to the SPV structure means additional discussions are recommended on setting the appropriate indicators – including on how to include the more qualitative Efficiency output 3; plans for calculating Efficiency indicator 4; ideas on how to gain additional insight on Private Sector partners; adding an economy measure on the programme vs. management ratio; and a second efficiency indicator.

Assessment of whether the programme continues to represent value for money
Our assessment is that the programme does continue to represent value for money. The programme is scoring an A against its outputs and is on track to meet outcome and impact indicators. In addition, the Theory of Change as set out in the business case and the associated economic appraisal still hold. Lastly, performance against VfM indicators is largely on track, although specific attention should be given to reaching women and monitoring the level of admin costs. The move to the SPV requires discussions on several indicators to ensure continued VfM going forward.

Quality of financial management
This is a milestone contract with a service provider. Since the last AR, the quality of financial forecasting has been good, and since inception, the programme has remained within the approved budget. No additional audit was done after August 2015 as this was not a contractual requirement for DAI.

Date of last narrative financial report	30 March 2016
Date of last audited annual statement	24 August 2015 (covers the 25 month period to 31 March 2015)

E: RISK

Overall risk rating: Minor

Overview of programme risk
The overall assessment of programme risk is minor. The SRO and the FSDZ technical team review the risk matrix for the programme each quarter. This focuses on what are considered the top 5 risks at a given point in time, and tracks their status and trend.

The top five risks currently include:
1. Transition and operating risks: The first few months of the special purpose vehicle causes disruption to programme delivery and outputs. The new FSDZ structure (under new management and with a new Board) takes time to settle down, and incurs additional transition related costs.
2. Misuse of funds (fraud and corruption): Risk of funds not being used as intended (a proportion of the programme funds will be subcontracted and granted to other organisations).
3. Policy environment and partner support: Deterioration in the Zambian policy/regulatory environment (e.g. reserve requirements further crowd out SME lending; no follow up to FSDP II). Key policy partners such as Bank of Zambia, Ministry of Finance, or the Pensions and Insurance Authority cease to be supportive of financial inclusion.
4. Macroeconomy: Significant deterioration in the global environment or the Zambian macroeconomy (e.g. a combination of low copper prices, fiscal deficits, weak kwacha raise interest rates and crowd out SME and other lending). Low GBP exchange rate impacts on programme purchasing power as well as international staff and contractor remuneration.
5. Financial sustainability – Given that DFID funding is expected to move to an incentive-based, matched fund model, there is a risk that sufficient additional funding is not forthcoming

Most macroeconomic indicators have stabilised or improved in recent months, though risks remain for private sector lending and access to finance. While the move to an SPV has now been made, a prolonged and costly transition period could still negatively affect FSDZ's programme delivery and continued oversight is needed to ensure the programme stays on track. On a positive note, the interest rate caps on lending have been removed and the government is developing a National Financial Inclusion Strategy, led by the Ministry of Finance, so there have been some encouraging signals in the policy environment. On balance, this programme remains minor risk, down from the last quarter.

Likelihood and impact of risks:

		Impact
		Insignificant	Minor	Moderate	Major	Severe
Likelihood	Almost Certain
	Likely
	Possible		4.Macroeconomy: significant deterioration in the global or Zambian economy	5. Financial sustainability: new funding sources are not sufficient
	Unlikely		1.Transition and operating risks	2.Misuse of funds (fraud and corruption / 3. Policy environment and partner support
	Rare

While some of the risks in the table above could have moderate impacts, given the stage of the programme (it is approaching its final year) and the performance (on track to exceed outcome targets), it is judged to be minor risk overall. This is also in line with most of the output risk assessments.

Outstanding actions from risk assessment
DFID’s Internal Audit Department (IAD) visited Zambia in late September 2015 and conducted a review of the FSDZ programme. Several recommendations were made following that review, summarised with responses below.

SPV transition, governance and risk. IAD recommended that: DFIDZ sets a clear risk appetite around the structures and delivery mechanisms for the programme and the transition to an SPV; the office initiates early engagement with London departments to support decision making and, DFIDZ ensures that there is clarity over the level of control DFID wants in the final arrangements.
DFIDZ has been managing this process very closely since September when it established a Transition Committee, chaired by the SRO, that meets weekly and ensures progress is on track. The SRO has sought and received the necessary approval from London departments, and has set out clear governance, risk and control structures that will be embedded in the new entity.

Supply chain oversight. The FSDZ supply chain should be fully mapped to identify all downstream partners and identify any fraud and delivery risks associated with this. DFIDZ should ensure that all relevant partners are managing due diligence down the chain effectively.
DFID has worked with FSDZ to further map the supply chain to identify all downstream partners and identify any fraud and delivery risks and clarify FSDZ’s responsibility for this oversight.

Financial spot checks. IAD suggests that additional financial spot checks are undertaken and that a detailed financial breakdown of spend allocated to Savings Group work is requested. This will provide additional assurance that spend is fully in line with the expectations of the programme team.
DFID will take a proportionate approach to managing the risks identified including undertaking ad hoc spot checks and securing a breakdown of Savings Groups spend by March 2016. A spotcheck was done in January 2016, with another one planned for January 2017.

In addition, as part of moving to the SPV a Due Diligence was carried out in February. One of the main recommendations was: Given that FSDZ was incorporated only one month ago, the key policies, although in draft form, are currently untested under the CLG structure and so DFID will need to monitor FSDZ closely in the first few months to ensure satisfactory governance arrangements and controls are implemented effectively to safeguard DFID funds.

The following recommendation was made: DFIDZ should ensure that all key policies and procedures (including funds; human resources; operations; finance and procurement) are all formally approved by the board and effectively implemented by the next Board meeting (June 2016). DFID will check on the assessment of the governance and control pillar following the June board meeting.

These policies and procedures have now been approved by the Board, with the exception of the finance and procurement and operations policies. These are scheduled to be presented at the next Board meeting in March 2017.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme is broadly delivering as planned against the envisaged timeframe and is expected to achieve or exceed the end-of programme targets. Outputs in certain areas are taking longer than expected to achieve, but given the market systems development approach employed by FSDZ this is manageable with a high degree of confidence that these outputs will be delivered by project end. The DAI contract has ended, and the new delivery vehicle – a local company limited by guarantee – is now in place. All partners visited during the review period were aware of the transition and commended FSDZ for the smooth process which did not affect downstream operations.

Performance of partnership
Until 31 March 2016, DAI was the partner implementing the project through a contract, which included working with other downstream partners, some on a grant basis and some on a contract basis. The supplier score fell by 8% in November 2015 compared to May 2015. This is because although the programme was delivering effectively on most programme areas, there were several instances of significant delays and poor communication. For example, the delivery of an external audit was behind schedule, and the delivery of the SPV analysis was later than expected.

Since the transition to an SPV there have been several changes in the DFID programme management team, but a new SRO and programme officer have now been appointed and are getting to know the FSDZ programme and team. FSDZ has also taken part in the DFID Partner Voice pilot in which our office gathered feedback from the FSDZ team on the working relationship with DFID. Overall, feedback has been largely very positive, commending on flexibility to learn (within budget and logframe), and usefulness for networking.

Asset monitoring and control
FSDZ has maintained a well-documented asset register which is updated regularly with clear description of assets and the date of purchase. A spot check was done in January 2016 and all assets were found in good condition. During the transition from DAI contract to a special purpose vehicle, an updated asset register was compiled and all assets were transferred to FSDZ. A spot check has been scheduled for January 2017.

G: CONDITIONALITY

An assessment of the Partnership Principles is not relevant as this programme does not directly engage with the Government of the Republic of Zambia, nor does it use government systems.

H: MONITORING & EVALUATION

Evidence and evaluation
No external evaluation is currently planned for FSDZ. During the last Annual Review, DFID’s results adviser joined the review team and found that FSDZ has an adaptive and strong theory-based approach to monitoring and evaluation (M&E). The project has placed the theory of change at the heart of its M&E function, and reviews and adapts the theory of change on a regular basis, changing it as new evidence and monitoring data is produced, creating a valuable feedback loop. It has a structured approach with nested theories of change for each thematic area, and links all the way down to the intervention level.

FSDZ conducts regular field visits to all partners to ensure quality. For example, in June 2015 FSDZ’s MRM team joined the CRS/CDN Programme Quality Assessment for Savings Groups. This assessed the capacity and quality of groups, their records, structure and procedures, compliance and capacity of field agents. It found the groups are of high quality and are being successfully implemented.

As noted in section C above, FSDZ is doing excellent work to build the evidence and statistical base in Zambia on financial inclusion. FSDZ has injected pace and depth into the production of statistics and evidence in Zambia on financial inclusion (including FINSCOPE, financial diaries and geo-spatial mapping). FinScope is an impressive survey, especially because it is representative to the district level across Zambia, and the plans to use the data to produce a series of analysis papers (i.e. FinScope FOCUS Series), as well as combining it with qualitative work such asdiaries and focus groups, is extremely welcome.

There is very good networking on M&E across the FSD Africa offices. What is very clear is that FSD offices across Africa (with good support from FSD Africa, a centrally funded regional programme) are sharing evidence and M&E approaches in a very constructive way. This can range from using evidence generated in another office or collaboration on a research topic (e.g. with Uganda on Savings Groups’ linkages to formal financial services) to improve the evidence base and theory of change in Zambia to the discussion of indicators and methodology tools for in country M&E systems. It appears that the M&E system developed in Zambia is being promoted as exemplary across other FSD offices – which should lead to M&E improvements in FSD projects outside Zambia, creating positive spillovers.

Last Annual Review recommended 3 areas for improvement:

Recommendation last AR	Progress so far
1. Strong risk/context/assumption monitoring is missing. FSDZ needs to strengthen formal monitoring of risk (including assumptions/context). The team is very good at monitoring implementation and systemic change but does not seem to have a robust system in place for the monitoring of risk. This should not be a major challenge given the team’s existing knowledge but it needs to be systematised. Improvements were made in the IAD preparation.	The new Board and Investment Committee actively discuss risks at their quarterly meetings. The FSDZ team also collaborated with FSD Africa to learn from them on how to monitor and measure assumptions and risk. During the coming year FSDZ will develop a structured approach to assumption scanning and risk measurement as part of revisiting its Project and Intervention Results Chains.
2. More qualitative tools need to be developed. The logframe has quite a few qualitative statements within it (especially around capacity building and improved effectiveness). It is very important to have strong methodology/tools in place to remove as much of subjectivity as possible. The Regulatory Assessment Toolkit is a good example of this but more qualitative tools could be developed.	In the year under review, 4 qualitative surveys were undertaking by FSDZ which have been drawn upon for this review. In addition, several other qualitative measure studies are planned, for example: financial education impact (Output 2); SMEs and end users, health insurance training with insurers (Output 3); capacity and effectiveness of support to AB bank, Investrust, MFinance (Output 5), and an SMEs use and benefits study (Outcome 3).
3. Logframe could benefit from more disaggregation and information. FSDZ understands the management tool role of a logframe very well. However, in some areas too much has been aggregated and it would be useful to unpack some of the indicators so that the contributions of each thematic area can be clearly seen. In addition, where there are small numbers (i.e. 2-5) it would be good to state the name of the target organisation, as it wouldn’t overburden the logframe to do so. There will be occasions when the organisation is unknown but where it is known a name should be given.	Several changes to the logframe were made to allow for more discussion of impact rather than merely the number of Financial Service Providers (FSPs) reached. FSDZ’s Annual Report mentions by name the FSPs and other partners/stakeholders under each logframe indicator, which have not been repeated for brevity’s sake in this document.

Monitoring progress throughout the review period
The DFID team has attended many external FSDZ events throughout the year, such as the launch of the geospatial mapping; a workshop on the financial diaries; and financial literacy events. All have been very high quality and well attended. The annual review process involved meetings with a wide range of stakeholders including commercial banks, microfinance institutions, a training institution, regulators, SMEs and a field visit to meet mobile money agents. Throughout the review period the SRO has had the opportunity to meet various partners and gain informal feedback on FSDZ’s performance. The Annual Review visits were carried out in August 2016 by DFID Zambia’s Economic Adviser and Social Development Adviser, which included field visits to Zoona (training centre, market agents, and head office) and a Village Savings Group. In the coming year, where possible additional field visits should be arranged to meet beneficiaries and provide additional monitoring opportunities.