Type of Review: Annual Review

Project Title: Programme for Improving Mental Health Care (PRIME) - RPC (2011-17)

Date started:	1st May 2011
Date review undertaken: 3rd September 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context
What support is the UK providing?
The UK is providing £6 million over the period 2011 – 2017 to generate world-class research evidence on the implementation and scaling up of treatment programmes for priority mental disorders in primary and maternal health care contexts in low resource settings.

What are the expected results?
PRIME is based in Ethiopia, India, Nepal, South Africa and Uganda. Comparing experiences across these diverse settings, which include fragile settings, will enable PRIME to generate knowledge with local and international relevance. By the end of the RPC, the following key research questions will have been answered: / a) What are the feasible and acceptable components and packages of care for priority disorders and how can they be integrated into routine primary health care and maternal health care? / b) What is the feasibility, acceptability, costs and impact of various models for delivery of the packages of care in routine primary health care and maternal health care settings? / c) What are the health system requirements for scaling up: human resources; training and supervision needs; infrastructure; drugs; budgets; and the incremental cost of increasing coverage per new patient treated? / d) What are the specific barriers which influence access to services for people living in poverty with mental disorders, particularly women during the perinatal period? / e) What is the impact of scaling up of the integrated mental health care plan on coverage and utilisation of mental health care?

What is the context in which UK support is provided?
The need for mental health services is high. Life time prevalence for mental disorders is between 12.2% - 48.6 % globally and the one year prevalence is between 8.4% - 29.1%. More than 13% of the global burden of disease is due to neuropsychiatric disorders. Almost three quarters of this huge burden lies in low and middle-income countries (LMIC) and this burden is projected to grow dramatically in the next decade, in part due to the demographic and epidemiological transitions in LMIC. Mental disorders are a major contributor to economic hardships and are strongly associated with social and economic disadvantage. / Despite this enormous burden, a multi-country survey supported by the World Health Organization (WHO) showed that almost four out of five people with severe mental disorders in LMIC had received no treatment whatever in the previous year. "Treatment gaps" were especially large for depression and alcohol use disorders. Where treatments are accessed, they are often inappropriate and involve considerable out of pocket payments, leading to catastrophic health expenditure.

## Section A: Detailed Output Scoring
Output 1: Establish and maintain an efficient and well managed RPC which draws on the strengths of each partner to deliver a high quality research programme that achieves the RPC’s goal and purpose.
Output 1 score and performance description: A+ Output moderately exceeded expectation
Progress against expected results: / 1. PRIME is now fully established as a research consortium and is functioning well. The Prime Management Team (PMT) is performing effectively, as are the PRIME Management Group (PMG) and the Consortium Advisory Group (CAG). During this year, Community Advisory Boards (CABs) have been established in all of the countries, with the exception of India, where the process has taken a bit longer but is nearing completion. In South Africa, due to the close linkages with the MoH, the CAG was originally established as part of the structure of the Ministry. The original structure was then disbanded and alternative arrangements are now being put in place. The structured quarterly reporting mechanisms are reported to be working well in all participating countries. / As the research protocols are being implemented in all five countries, to overcome any delays in decision making or collaboration issues, a Core Group has been established to discuss the technical details of research design. This group includes the CEO, the various Research Directors, Principal Investigators and other key partners for a particular research programme. The group meets monthly via tele-conferences and has had face-to-face meetings in Cape Town (May 2011), Goa (November 2011), Kampala (April 2012), London (November 2012) and Addis Ababa (April 2013). / The RPC has experienced difficulties with financial forecasting and ended the year some 25% under budget, even although almost all the Logframe targets were met or even substantially exceeded. This underspend has been largely driven by weakening in LMIC currencies against the pound. This is an area that needs some improvement, particularly over the next two years. / Recommendations: / Strong progress has continued during the second year of the RPC, the first full year of implementation. A strong framework has been established which is working well and the RPC managers are giving priority towards ensuring all the country-based partners are participating effectively. Important work has been done this year to prioritise the key research activities, which will directly lead to the planned outcomes. Experience from the RPC has been effectively shared with WHO and other interested agencies/countries. The key issue is to maintain this progress and help those countries where progress has been slightly slower than expected, so that the key research programmes are completed on time. Financial forecasting needs to be improved and it is important that the RPC does not allow the substantial additional funding from other sources to displace planned DFID-funded expenditure. / Impact Weighting (%): 10% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 2: Develop a coherent body of high quality, peer-reviewed and policy relevant research that makes a significant contribution to understanding the implementation and scaling up of packages of care for mental disorders.
Output 2 score and performance description: A+ Output moderately exceeded expectation / Progress against expected results:
The consortium is making very good progress and is on track to produce high quality research. The RPC has completed the formative research, which included focus groups and semi‐structured interviews with key stakeholders and service users. The research also involved theory of change workshops and the development of a potentially innovative mental health Gap Action Plan (mhGAP) related costing tool. Formative research has been supplemented by analysis of secondary data, through systematic literature reviews, on the effect of psychosocial interventions on social functioning, for people with depression and schizophrenia, in low and middle income countries, along with approaches for evaluating the coverage of mental health programmes. The results of this formative research will be written up and published. / There has been a thorough evaluation of the plans for the implementation phase of PRIME. This included inputs from experts within the PRIME consortium, followed by an external review of Community and Facility protocols by two reviewers (from Harvard University and TPO Uganda). Similarly, the protocols for the cohort and case studies are now under development and the RPC are also planning external review, to ensure high quality. / At this relatively early stage, the RPC has published 11 peer reviewed journal articles, including the PRIME flagship paper published in PLoS Medicine, which outlines the objectives and methods of PRIME. RPC staff and collaborators have presented the RPC’s work at 12 conferences including the Public Health Association of South Africa, the Ugandan Psychiatric Association and a national seminar of the Nepal Mental Health Foundation. This has exceeded the milestones established for year two by a considerable margin. / The RPC has given close attention to gender issues and data collected is disaggregated. Women were first authors on 3 of the published papers and on 6 conference presentations. The RPC hopes to improve on these results and held a writing skills training workshop and a gender mainstreaming workshop at their annual meeting in Ethiopia in April 2013. / A significant output has been the development of PRIME Mental Health Care Plans, developed using the outcomes from the formative research and consultation with district and national level policy makers. Plans are developed for later implementation at three levels of the healthcare system: healthcare organisations, facility level and community level. / Recommendations: / Strong progress during year two and commendable rigour, including external peer review of the plans for the implementation phase. The research programme is ambitious but, based on year two progress, could be achieved. It will be important to continue to prioritise these key activities which will directly lead to the planned outcomes. The RPC is producing important findings already and these should continue to be shared, as appropriate, with WHO. / Impact Weighting (%): 50% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No
Output 3: Effective communication of relevant research findings and their uptake by national and international stakeholders to influence policy and practice in the study countries and other low and middle-income countries.
Output 3 score and performance description: A+ Output moderately exceeded expectation
Progress against expected results: / Research Uptake continues to be a strong component of the PRIME RPC. A number of “introductory” products have been produced which articulate the work and objectives of the RPC. PRIME has produced 11 products, which have been disseminated to various policy makers and 5 of the products were also disseminated to funding agencies. This includes a major policy brief on Poverty and Mental Disorders. This year, 31 separate engagement meetings have been held with selected key policy makers. Linkages have been developed with Grand Challenges Canada, with 3 PRIME partners on their Scientific Review Committee. / Although at a relatively early stage of the RPC, PRIME has already published 11 articles in peer-reviewed journals. A citation analysis in Google Scholar has shown that PRIME outputs have been cited 116 times in academic publications, already well beyond the logframe target. / Engaging with key stakeholders at community levels is proving more difficult, as there are few networks for mental health practitioners and service users and, in many places, mental health services are extremely weak or absent. Needs assessments have been conducted and some countries are planning to establish groups of mental health service users, with psycho-social support and livelihood development activities. / PRIME has been particularly active in generating media interest and coverage. 25 website articles, 21 printed articles, 6 radio shows and 3 television programmes. The focus is often on or around World Mental Health Day, held in October each year. / Recommendations: / The strong early progress from the first year has been continued and consolidated in the second year. The RPC is working hard and has a clear, coherent strategy for carrying forward research uptake activities. In the next year and subsequent years it will be important to gauge the impact that the various products, programmes and meetings are having, particularly to document any changes in policy or legislation that directly result from the RPC’s activities. Liaison with WHO will continue to be important. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 4: Capacity exists in study countries to conduct and effectively disseminate research to improve access to mental health care.
Output 4 score and performance description: A+ Output moderately exceeded expectation
Progress against expected results: / A key component of PRIME is the development, implementation and monitoring of a structured programme to build sustainable capacity for mental health research and evidence-informed policy and planning. The RPC has continued to implement their Capacity Building Strategy and are making good progress. / Formal capacity building training workshops have been organised in Research Uptake and in Qualitative Research Methods (Uganda, after the annual RPC meeting). Research Methods workshops have been conducted for junior researchers involved in the consortium, in various countries. A symposium in New Directions in Public Health Evaluation (at LSHTM) was attended by several PRIME researchers. Three key mid-level researchers are involved in a structured programme of mentoring, with each allocated a senior PRIME researcher to take responsibility for planning and supervising the mentorship programme. Four male and nine female PhD students are now registered as part of the RPC, along with a further 3 Masters students. Of particular note is that two PRIME researchers, have successfully competed for a LSHTM/Wellcome Trust fellowship and a Wellcome Trust PhD fellowship respectively. / Although the registration of Masters students is included in the PRIME Logframe as a target, almost all the funds for these Masters courses are provided from other funding sources, with a total of 36 registering against a target of 25. The RPC has asked that tracking Masters students be dropped from the Logframe from year three and beyond, in order to focus on other aspects of capacity building that are actually funded by the PRIME RPC. / The RPC has been successful in gaining multiplier funding, including capacity building, amounting to £10 million. This includes a Health Systems Grant led by a PRIME member from Kings College London. The programme will be closely aligned with PRIME and will investigate Emerging Mental Health Systems in low and middle income countries. The RPC has also been granted funding from the National Institute for Mental Health, for the development of collaborative hubs in South Asia and Africa. World Vision Australia has also awarded funding for the implementation of the WHO mhGAP training programme in Uganda. / Early indications are that capacity among partners is already increasing, demonstrating a 41% increase in research outputs over year one, well beyond the logframe target of 10%. There is a particular focus on building the capacity of female researchers. / Recommendations: / Good early progress has been further consolidated in the second year. There will be a need to carefully prioritise activities, using the additional external funding to build and not divert from the RPC’s activities. Continued liaison with WHO is important. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.
1. Progress and results
Has the logframe been updated since last review? Yes / In view of the substantial progress during the first two years, the RPC has developed increased targets against a number of key performance indicators. / Overall Output Score and Description: A+ Outputs moderately exceeded expectation / 1.3 Direct feedback from beneficiaries / There have been positive inputs from all the participating countries. Useful work has been taken forward in establishing Community Advisory Boards (CAB’s) in all countries, with India still in process and South Africa changing the institutional arrangement for the CAB, within the MoH structures. The RPC has also begun to engage with people affected by mental illness, along with their families and community leaders/stakeholders. This has been done through the CAB meetings and by participation in formative research (interviews, focus groups and Theory of Change workshops). Work to develop groupings of professionals working on mental health issues will also be important and the development of electronic means of communication with fledgling groups will be useful.
1.4 Summary of overall progress / The PRIME RPC has effectively built upon the strong progress made during the Inception Phase and year two has established strong platforms for success across all major areas of activity. The RPC is well managed and is demonstrating success in involving and even integrating the various countries and lead institutions. The RPC is managing its research portfolio, dissemination and capacity building programmes appropriately and has already made progress beyond the level that might have been expected at this stage. In summary, another strong year, building on the success of the Implementation Phase, fully establishing the research programmes, capacity building and research uptake measures. Impressive progress overall.
1.5 Key challenges / The current economic situation means that RPC partner institutions are struggling to pre-finance activities and this has slowed down disbursement. Despite this, all targets have been met and some substantially exceeded. In India, PRIME has attempted to address this issue by switching the relationship between Sangath and the Public Health Foundation of India. This now means that PHFI (with greater liquidity) has primary responsibility for pre-financing of the RPCs activities. Devaluations of local currencies in several of the countries have led to exchange windfalls for the overall budget, which has exacerbated the issue of under-disbursement. / Mental Health remains much neglected in almost all countries of the world and the RPC is making efforts to change this general trend in the participating countries. Through the formative research, and by compiling the data on the proportion of the global burden of disease contributed from mental health conditions, the RPC is helping WHO and others to increase the profile of mental health and to solicit for additional funding in the future. / Retaining highly qualified and experienced staff is always a challenge and the RPC has had remarkable stability so far, with only two changes of key personnel in the first two years. By building up local capacity, the RPC is helping to enable participating countries to steadily build up their research and mental health services.
1.6 Annual Outcome Assessment A+ Outcome moderately exceeded expectation / The RPC has put into place strong management and supervisory mechanisms, along with clear organisational structures, designed to work effectively with other key players to achieve the planned outcomes. The RPC is working to overcome the problems of significant under-disbursement, establishing careful plans for next year and beyond.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: No / The programme is underspent against financial forecasts. At the end of Year Two, the programme was underspent by 20% against the overall projected budget. / 2.2 Key cost drivers / The development and implementation of high quality research programmes, combined with adequate dissemination and building up of local research capacity, are costly processes. Key cost drivers are direct and indirect staff, travel costs, research consumables and related transport and supervision costs. The RPC is fully aware of the need to work carefully within the planned budget. Costs have been contained and there has been some slippage in disbursement. Most of the participating countries have seen some slippage of exchange rates for the local currency, taken against international hard currencies. As the programme budget is denominated in Pounds sterling, and funds are only transferred into local currencies as the funds are directly required, the overall RPC budget has so far received exchange rate windfalls, increasing the issue of under disbursement. The RPC has prepared specific proposals for increasing research and capacity building activities in the next two years, in order to ensure the budget is on track by the end of the programme. These proposals are currently under review. / 2.3 Is the project on-track against original timescale: Yes / Many Logframe targets have been significantly exceeded.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The RPC has been directly involved in developing new evidence, such as the 2nd Lancet series on Global Mental Health, which involved six major articles, four of which included authors directly involved in the PRIME RPC. The RPC is also working in liaison with the Mental Health Department of the WHO and helped support the development of several major publications, including the WHO Global Mental Health Action Plan (2013-2020). This year, 11 peer-reviewed journal articles were published. / 3.2 Where an evaluation is planned what progress has been made? / Not applicable at this stage

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / Although there has been strong progress, on balance, we judge that the RPC should remain high risk. At the next visit to the programme, DFID staff should consider whether there is a case to reduce the risk level to medium. / The RPC Prime Management Team and the Consortium Advisory Board regularly review the risks. As mental health is still a relatively low priority for many Ministries of Health, despite the considerable contribution to the overall burden of disease, it is difficult to guarantee that staff and financial resources will be forthcoming, when required, to step-up high quality mental health services. The RPC is operating across five countries, Ethiopia, India, Nepal, South Africa and Uganda, which includes fragile settings. / Risks related to the research portfolio are reducing and there is strong evidence of engagement by national and local authorities, but still relatively little funding being made available for mental health services, so sustainability concerns remain in the medium to long-term. Risks related to non-technical issues such as funding and organisational functioning, supervision and management are assessed by the Prime Management Team and the Consortium Advisory Board. The main risks this year have been related to administrative delays, exchange rate devaluations and difficulties with pre-financing RPC activities. / For DFID, the main risk remains that there will be insufficient uptake of the high quality research, as Ministries of Health struggle to provide essential services. Strong engagement with WHO, and with participating governments does mitigate this risk, to some extent, but for now the overall programme remains high risk, high potential impact.
Risk of funds not being used as intended / This is considered to be low risk. The earlier RPC, also managed through the University of Cape Town, had a strong reputation for management and financial oversight. The PRIME Management Board has endorsed a new “Counter Fraud and Anti-Corruption” policy, on the advice of DFID. There have been no difficulties reported with misappropriation of funds. The RPC Prime Management Team is effectively overseeing all aspects of the programme and has performed well during the first two years. / The RPC has established strong functioning mechanisms for management and oversight. These include the Prime Management Team and the Consortium Advisory Board. The Prime Management Group, which includes all participating lead institutions, meets periodically to oversee RPC activities. The Consortium Advisory Group (CAG) and Community Advisory Boards (apart from India and South Africa in process) have also been established to feed-in external points of view. / 4.4 Climate and Environment Risk / Climate and environmental risks continue to be effectively managed by the RPC. All the participating institutions review research activities to reduce the impact on climate and the environment. Where possible, tele-conference and “Skype” meetings take place, in order to minimise the impact of national and international travel. / In time, the provision of more local high quality mental health services will reduce the requirement for patients to travel to regional or national treatment centres, in order to access care. Reduction in treatment times should lead to reduced need for travel by patients and improve patient drop-out rates and overall waste.

5. Value for Money
5.1 Performance on VfM measures / Funding high quality research into neglected non-communicable diseases, such as mental health, provides value for money through: reducing the impact and burden of mental ill health; encouraging governments to provide essential services which are able to intervene early, before a lengthy and potentially costly breakdown or in-patient admission; ensuring that individuals with mental health conditions, and their direct families, are able to function in employment or farming, instead of becoming a burden on local communities or governments. / The macroeconomic impact of mental ill health is very significant, with an estimated 13% of the global burden of disease being due to neuro-psychiatric disorders. Almost three quarters of this huge burden of disease falls on low and middle income countries. Most important of all, it is projected by WHO that this global burden is projected to grow dramatically in the next decade, in part due to demographic and epidemiological transitions. Mental disorders are a major contributor to economic hardships and are also strongly associated with social and economic disadvantage. / 5.2 Commercial Improvement and Value for Money / Through its internal processes, identifying the most promising new research proposals from the participating countries and institutions, the RPC is able to provide a “competitive” environment for innovative new approaches and work to keep costs low to achieve improved value for money. Paradoxically, exchange rate windfalls have contributed towards a significant problem of under-disbursement, but all the major targets have been achieved and several substantially exceeded, offering good value for money. / 5.3 Role of project partners / The RPC is managed by the University of Cape Town, and includes the following key institutions: University of Addis Ababa, Ethiopia; Basic Needs, an NGO; the Centre for Global Mental Health, UK; Healthnet TPO, an NGO in Nepal; Makerere University, Uganda; Sangath, India; University of Kwa Zulu Natal, South Africa; and the Mental Health Department, WHO, Geneva. All the partners are represented in the PRIME Management Group and also have Community Advisory Boards in each of the country research sites, except for India (under development) and South Africa (institutional arrangements recently changed by the MoH). / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? Not applicable

6. Conditionality
Update on specific conditions / Not applicable

7. Conclusions and actions
The performance of the PRIME RPC is exceeding expectations and they have made strong progress in this second year, the first year of implementation, following the inception year. / Progress on research, capacity building and research uptake has been impressive overall but there have been some administrative delays and a substantial underspend. Research is a long-term activity and the RPC is now proposing measures to speed up disbursement by expanding the research programmes and capacity building. Strong partnerships are now in place with the five participating countries and the leading research institutions. Substantial add-on funding has been provided from other funding agencies and it will be important to manage this additional funding in a way that does not slow down the DFID programme and budget. Overall a very strong performance over the first two years of the RPC. / Recommendations: / The RPC needs to maintain progress and help those countries where progress has been slightly slower than expected, so that the key research programmes are completed on time. / Financial forecasting needs to be improved and it is important that the RPC does not allow the substantial additional funding from other sources to displace planned DFID-funded expenditure. / It will be important to continue to prioritise key research activities which lead directly to the planned outcomes. The RPC is producing important findings already and these should continue to be shared, as appropriate, with WHO. / The RPC is working hard and has a clear, coherent strategy for carrying forward research uptake activities. In the next and subsequent years it will be important to gauge the impact that the various products, programmes and meetings are having, particularly to document any changes in policy or legislation that directly result from the RPC’s activities. Liaison with WHO will continue to be important. / There was good early progress with capacity development activities which has been further consolidated in the second year. The RPC must carefully prioritise activities, using the additional external funding to build and not divert from the RPC’s activities. Continued liaison with WHO is important.

8. Review Process
The review was carried out by members of the Human Development Research Team in DFID, with extensive support from Link Advisers in DFID South Africa, India and in DFID HQ. The process involved discussions with the RPC, WHO and other organisations working on mental health issues. DFID staff attended the CAG meeting. / Materials used included reports from a variety of sources including the second PRIME Annual Report; publications from the Mental Health Department of WHO; and the 2nd Lancet Special Series on Mental Health.