Type of Review: Project Completion Review

Project Title: Financial and Legal Sector Technical Assistance Project

Date started: 2004	Date ended: 2013	Date review undertaken: September 2013

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The UK Government provided a total of US$10 Million towards a technical assistance programme providing expert advice to address financial and legal sector weaknesses in Kenya. A joint World Bank-IMF Financial Sector Assessment Program (FSAP) had been concluded in Kenya in late- 2003. It provided a broad overview of potential financial sector vulnerabilities and development needs. In view of the development constraints identified, the government developed a financial sector reform programme to address issues constraining the operation of the sector. The Government of Kenya (GoK) asked the World Bank for a Technical Assistance credit to assist in the implementation of reforms. The UK co-financed the project, as this was a key objective of the DFID Kenya’s Country Assistance Paper (CAP).

What were the expected results?
The main objective of the project was to create a strengthened legal and judicial capacity that would ensure broad access to financial related legal services for business. The project did not have a DFID logframe. Throughout the lifetime of the project, the World Bank’s results framework was used for reporting progress. However, this was aligned to DFID’s Logframe and results chain structure which is not dissimilar to the Bank’s. As such, this Project Closure review (PRC) used the World Bank’s results framework and selected seven components below and corresponding indicators as the evaluation methodology: / 1. Financial institutions and the judiciary targeted by the strategies implement reforms named in the strategies, creating the basis for improving access, enhancing efficiency, and strengthening the soundness of Kenya’s financial system. / 2. Government’s ownership stake in the banking sector reduced, enhancing its soundness. / 3. Effectiveness of financial sector regulators strengthened / 4. Integrated debt management system in place. / 5. Stability and soundness of money transmission systems increased. / 6. Legal and institutional framework strengthened to encourage financial institutions and others to increase lending, especially to small and medium size enterprises. / 7. Commercial justice is more efficient.

What was the context in which UK support was provided?
A new Government had taken office in December 2002. It had prepared an Economic Recovery Strategy for Wealth and Employment Creation (ERSWEC) which aimed to restore the economy to a path of high growth. Within this framework, the government committed to a stable macro-economy, reforming the financial sector, implementing PPP in infrastructure services, and improving the environment for private investment in sectors such as tourism, trade and industry. The Government had agreed a Poverty Reduction and Growth Facility (PRGF)[1], with the International Monetary Fund (IMF), and the first review had been positive on reform processes by contract with the previous period. / State of the financial and legal sectors: A joint Bank-Fund Financial Sector Assessment Program (FSAP) for Kenya, completed in late-2003 provided an overview of financial sector developmental needs, including: / Limited access to financial services by households, notably in rural areas, private enterprises, especially micro, small and medium enterprises (MSMEs). / Lack of competition with weak banks unable to exert competitive pressure on the few strong banks. / High level of Non-performing loans (NPLs). / Structural problems in the non-bank sector including weak supervisory capability of the insurance sector. / Limited coverage of the pension system, inadequate benefits, and high levels of unfunded liabilities. / Limited capacity of the Capital Markets Authority with no operational independence. / The legal framework for property rights, insolvency, and creditor rights was incomplete, requiring legal review aimed at making it relevant. / Legal and judicial sector institutional issues including weak capacity, corruption, and poor enforcement of laws. / Inefficient court system, with operations handled manually. Improving the court system was considered central to the legal and judicial framework. / System for legal education suffered from neglect and had become largely inadequate for the rapidly growing needs of the Kenyan economy. / In view of the above constraints, the WB and Government developed a financial sector reform program to address policy, institutional and legal issues. / At inception, the new Government agreed a reform platform. However, constituting the PIU with expatriates (an internal factor), led to a lack of Government ownership of the project. This caused delays, but was corrected with ministry of finance secondees. / Post election violence and coalition working led to a focus on judicial reforms, and continuity of the reforms agenda on which FLSTAP was based, but slowed up the process of reform, as the new constitutional process took priority
[1] Implementation of Fund policy in four areas: governance, fiscal sustainability, financial sector, and poverty reduction. less successful in responding to the recommendations of the Fund and the Bank to reduce public sector ownership of banks. The government has indicated that the slow progress in this area reflects primarily fears that privatization may adversely affect financial intermediation in rural areas.

## Section A: Detailed Output Scoring
Output 1: Financial and Judicial Sector Strategy Development
Output 1: final score and performance description: A Outputs met expectation / Output indicator Baseline value Target values Actual value achieved at completion Output indicator score / Judicial sector strategic plan (JSP) adopted and being implemented No Background Strategic Plans at Project Inception Judiciary Strategic Plan 2009 - 2013 approved and under implementation JSP 20092013 approved and under / implementation A / Comprehensive Financial Sector Reform and Development (CFSRD) strategies adopted by the Cabinet. Background studies for strategies completed CFSRD approved by Cabinet, adopted for implementation CFSRD) / submitted to MOF / (Oct.2011) has / Been adopted by Ministry of Finance / (MOF) A
Final results: / The Project supported the a financial sector strategy involving broad consultations among stakeholders and studies on the financial sector. The Comprehensive Financial Sector Reform and Development Strategy (CFSRD) has been instrumental in guiding the development of the Medium Term Plan 2013-2017 (MTP2) for the Financial Services Sector. / The Judiciary strategic plan as provided in the Governance, Justice, Law and Order Sector (GJLOS), included the introduction of performance and service standards, a comprehensive training program, and the introduction of a credible system for the selection, appointment, and removal/discipline of judges and other judicial staff, and the strengthening the Judicial Service Commission. The Project supported relevant agencies in developing a framework for monitoring and evaluating progress in financial sector development and judicial and legal reforms. This output met expectation. / Impact Weighting (%): 10% / Revised since last Annual Review? NO / Risk: High / Revised since last Annual Review? NO

Output 2: Restructuring and Privatization of Financial Institutions
Output 2: final score and performance description A Outputs Met expectations / Output indicator Baseline value Target values Actual value achieved at completion Output indicator score / Submission of plans to Parliament of the transaction to dispose of State-influenced shares of National Bank of Kenya (NBK) &Consolidated Bank (CK). No plans in place Plans for the privatization of GoK stakes in NBK and CB approved by Cabinet and submitted to Parliament. Plans for the privatization of GoK stakes in NBK and CB approved by Cabinet and submitted to Parliament. A
Final results: / The banking system had at the time a very high level of non-performing loans concentrated in four commercial banks with state interests. The Project supported the establishment of a specialist Bank Restructuring and Privatization Project (BRPP) within the Ministry of Finance to guide a privatization process (partial and slow but underway). This helped to strengthen competition and improve stability, and is expected to result in downward pressure on the high interest rate margins and increase the incentives to reach underserved markets. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Strengthening Financial Sector Regulators and the Deposit Protection Fund Board
Output 3: final score and performance description: A Outputs Met expectations / Output indicator Baseline value Target values Actual value achieved at completion Output indicator score / CBK’s compliance (compliant or largely complian with Basel core principles (BCP) rises to atleast 18 Principles CBK compliant/largely compliant with 16 BCPs At least 18 18 A / Financial sector regulators adopt risk based supervision Regulators at various stages in implementing RBS CBK, RBA, CMA, IRA and SASRA implementing at different levels of progress. RBA, CMA, IRA, SASRA implementing RBS, A / Proportion of financial institutions in compliance with capital adequacy ratios rises 93% 96% 100% A+ / Autonomy of Financial Sector Regulators: Insurance Regulatory Agency (IRA), Capital Markets Authority (CMA), Retirement Benefits Authority (RBA), Saccos Regulatory Authority and CBK-Bank Supervision Department) established. CMA, RBA partially autonomous; Commissioner of Insurance is a dept. of MoF; DPFB operated CBK though it has separate Board / June 2005. CMA, RBA, IRA, CBK –BSD remain autonomous. SASRA more autonomous. CMA, RBA, IRA, CBK –BSD remain autonomous. SASRA more autonomous. A
Final results: / The Project provided support for the amendment and drafting of financial sector laws and regulations that govern regulators and the DPF, with the objective of strengthening their effectiveness. It also supported capacity building initiatives for these institutions, including training needs assessment, training of staff, resident advisors, and establishment of capacity to regulate and supervise the microfinance and SACCOs sectors under the proposed new legislation. In addition, improvements were made to the Management Information Systems (MIS) of these institutions, including software upgrades and purchase of IT hardware/systems. / Impact Weighting (%): 10% / Revised since last Annual Review? N. / Risk: Medium / Revised since last Annual Review? N

Output 4: Strengthening Debt Management and Debt Markets
Output 4: final score and performance description: A+ outputs moderately exceeded expectations / Output indicator Baseline value Target values Actual value achieved at completion Output indicator score / Non-Performing Loans (NPLs) drop to 8% of Total Loans (net of interest in suspense) by end of project. NPLs drop to 8% 3.62% A++ / Integrated debt management system in place No comprehensive debt management strategy developed Comprehensive debt management strategy developed Comprehensive debt management strategy, annual debt management reports issued. A / Final results: / The updating of Government debt databases was being handled by individual entities in the Ministry of Finance and CBK responsible for parts of debt management and there was no coordination or consolidation of data. The Project provided technical support for setting up a unified and sustainable Debt Management Office, including review of relevant legislation. The Project also supported a number of improvements with a view to enhancing the operation of the primary and secondary debt markets. These yielded more results than anticipated, with the non-performing loans dropping to 3.26%.
Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 5: Modernizing the National Payments System
Output 5: final score and performance description: A+ Outputs moderately exceeded expectations / Output indicator Baseline value Target values Actual value achieved at completion Output Indicator score / % of clearing house transactions processed through RealTime Gross Settlement (RTGS) rises to at least 95% zero At least 95% transactions by RTGS; RTGS backup centre established The net settlement of all transactions in ACH is processed through KEPSS meaning 100 %. . A+
Final results: / The Project provided technical assistance and funding to acquire Script less Securities Settlement System/Central Depository System (CDS) to facilitate the clearance and settlement of funds and securities transfers in line with best international practice. In addition, the project supported the establishment of an appropriate legal and oversight framework, and training for staff of the Department of Payments System in the CBK. The Project funded a study to identify how to improve mechanisms for low value payment transfers. / Impact Weighting (%): 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 6: Improving the Lending Environment
Output 6: final score and performance description: A Outputs moderately exceeded expectations / Output indicator Baseline value Target values Actual value achieved at completion Output indicator score / Private credit registries operational and sharing data. nil 2 private reference bureaus 2 private / Credit Reference / Bureaus (CRBs) operational. .Average Number of credit reports accessed: / 180,000 A
Final results: / FLSTAP funded a consultancy to support CBK Banking Supervision Dept. on the licensing of credit reference bureaus (CRBs), for capacity building of BSD staff, and purchase of ICT office equipment. CRB regulations were drafted with project support. / FLSTAP financed the preparation of a draft policy and consumer protection law 2012, as well as a market survey and proposals for increasing access to lease financing. / Impact Weighting (%): 20% / Revised since last Annual Review? N. / Risk: Medium / Revised since last Annual Review? N

Output 7: Legal and Judicial Reform
Output 7: final score and performance description A+ Outputs moderately exceeded expectations / Output indicator Baseline value Target values Actual value achieved at completion Output indicator score / Laws of Kenya revised and online access provided/enhanced with Judges Help Desk established and operational. Judges Help-Desk. Existing laws outdated and not available online. All Laws of Kenya revised, and available in Hardcopy, CD-ROM, online (in acceptable formats) All laws of Kenya Revised, and available in hardcopy (being cleared in customs expected shortly), CD-Rom, Online (in acceptable formats). Help Desk is established and operational. A / Civil Procedure Rules (CPR) reviewed and published Existing procedures outdated CPR approved CPR 2010 gazetted and in operation A / Time taken to register companies declines by 8days by project end 47 days to register a company 39 days to register a company 31 days to register a company A++ / Automation of recording and transcription services in at least the commercial and civil divisions of the high court completed No automation of court processes and case management Equipment operative but not being used Automation of recording and transcription services in its final days of completion in both divisions A / Number of courses offered at the University of Nairobi (UON) School of Law and the Kenya School of Law (KSL) on commercial and financial law rises 16 courses for 2004/05 academic year. / None for KSL UON – 20 courses / KSL – 10 courses UON – 20 courses / KSL – 10 courses A
Final results: / FLSTAP funds were used to improve the legal case management system; capacity building, and legal reform were supported; legal resources were made publicly accessible; and specialization in commercial and financial law was fostered at university and with the judiciary and Government. A major achievement was reduction of time taken to register companies in Kenya, which substantially exceeded expectation, leading to an enhanced business environment. / Impact Weighting (%):10% / Revised since last Annual Review? N. / Risk: Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.
1. Achievement and Results

Has the log frame been changed since the last review? No / The project did not have a DFID logframe. The World Bank’s results framework was used for reporting. This was aligned to DFID’s Logframe and results chain structure which is not dissimilar to the Bank’s. / 1.2 Final Output score and description: A Outputs Met expectation / Overall, FLSTAP project achieved a majority of output targets and exceeded others. However, most of these outputs were achieved in the last three years of the project, following the mid-term review that led to a restructuring of the project. Key lessons learned from the challenges faced at the early years of the project were incorporated in the implementation process to turn around results. This project ultimately lasted close to a decade: most outputs were delivered long after the original project envisaged.
Direct feedback from beneficiaries / The primary target beneficiaries for this project was the Ministry of Finance, with also: Kenya School of Monetary Studies, Central Bank of Kenya (CBK), Capital Markets Authority, Insurance Regulatory Authority, Retirement Benefits Authority, Deposit Protection Fund Board, MoCD & M/SASRA, Ministry of Lands, Registrar General, Kenya Law Reform Commission, Judiciary, State Law Office, and National Council for Law Rep, / These beneficiaries almost unanimously were pleased with the support given by FLSTAP, which in many cases was instrumental in transforming aspects of the agencies’ work. / FLSTAP supported the establishment of an independent Kenya Deposit Insurance Corporation (KDIC), assisting with the drafting of a new law (Kenya Deposit Insurance Act) and financing workshops to sensitize members of parliament prior to the discussion of the draft law. KDIC expressed satisfaction with the work performed by project-financed consultants, particularly the training offered on bank resolution proceedings. / FLSTAP financed activities of SASRA, including: equipment (hardware and software), institutional strengthening and study tours abroad. Training was important - SASRA is a new regulatory agency established three years ago, without experience in oversight. SASRA may not have had a successful launch and the progress achieved in the past three years without FLSTAP support. This is recognized by the agency. / CBK – National Payment System (NPS). The project financed a missing piece of infrastructure (hardware, communication, and security requirements) in the form of a remote disaster recovery site, providing back up for the operation of the large payment system. / Activities financed under the Project were deemed by CBK to have been of importance to enhance the efficiency and security of electronic payments in Kenya. Efficiency gains and security enhancements were confirmed through interviews of payment system users (NBK). Although most of the implementing agencies rated the project as satisfactory, through a world bank beneficiary survey, most made the following negative remarks: / (a) the procurement process was cumbersome and slow, and it needs to be streamlined; having to deal with two different procedures seemed unnecessary to them, who demanded a unification/harmonization of the process / (b) they identified as one of the problems with channelling funds for equipment to be the absence of a technical specialist within the FLSTAP / (c) the clearance process (no-objection) resulted in excessive delays, and there were problems of miscommunication (by the time WB gave clearance, the request was no longer in valid).
Overall Outcome score and description: / A Outcome met expectation / Outcome indicator Baseline value Target value Actual value achieved Outcome score / At least 15 new or upgraded Commercial/ Financial and related laws and subsidiary legislation developed, approved by Cabinet and published by the State Law Office (Attorney General’s Office) none At least 15 23 A++ / Interest rate spread between Average Deposit Rates and Lending Rates falls below 8% by end of project 8.6% Originally 6%, changed to 8% at restructuring 11.6% B / Percentage of population with access to formal rural financial services increases to at least 40% by end of project. 23.4% 40% 59.8% A+ / Credit extended to the private sector as a percentage of GDP increases to at least 37% by end of project. 25.8% Originally 30%, changed to 37%at restructuring 33.5% B / Percentage of population with access to formal financial services increases to 50% by end of project. 26.4% Originally 20%, changed to 50% at restructuring 66.9% A+ / Number of accounts in the financial sector increases to 15 million accounts by project end. 2.2 million 15 million 17.6million A++ / Most of the project outcome indicators were over-achieved. However, two indicators fell below targets mainly due to external factors. / Impact and Sustainability / The financial and legal/judicial sector reforms supported by FLSTAP have created opportunity for impact and sustainability in these sectors. The project supported the development and amendment of 23 laws and regulations, which are now in operation and are sustainable. Other avenues for impact and sustainability of FLSTAP include: / Building on FLSTAP, the development objective of the WB Infrastructure Finance Public Private Partnerships (IFPPP) is to increase private investment in the Kenya infrastructure market. The first stage is to improve the enabling environment to generate a pipeline of bankable projects. This phase will directly benefit from FLSTAP activities such as a draft PPP pipeline. / The development objective of the Judicial Performance Improvement Programme is to improve the performance of the Judiciary to provide its services in a more effective and accountable manner; build on lessons of the 2008 forensic audit, and the recommendations made in the policy framework to address fiduciary capacity constraints in the Judiciary. These build on the Judiciary’s ICT and case management groundwork financed by the FLSTAP. / Government has made a commitment to sustainability of FLSTAP outputs, and deepening the reform agenda. It has a financial and judicial reform agenda, as articulated in the Draft Medium Term Plan 2013-2017 for the Financial Services Sector. / Further, the World Bank maintains active engagement in the financial and judicial/legal sectors through two newly approved loans: IFPPP project and JPIP; and is undertaking a Capital markets mission in September 2013 with a view to further work in this field.

2. Costs and timescale
Was the project completed within budget / expected costs: Y/N Yes / Even though the project lasted eight years instead of five, the project achieved objectives at a lower cost US$29.1 million, versus an estimated cost of US$30 million at appraisal. / However, Bank administrative costs for project supervision were high, averaging over US$190,000 throughout project implementation, compared to the Africa regional average of US$112,000. While high, these high costs reflect the magnitude of the project, with a total of 20 experts hired in the last 4.5 years. / Key cost drivers / The key cost drivers for this project were: Goods and Equipment, Consultancy Services, Training and Workshops and Operating Costs. / Throughout the life of the project plans for financing the various components were modified. As a result, financing for the different categories also changed (see graph below). More goods and equipment were funded under the project (43%) than initially envisaged and less was financed under the other categories, particularly consultancy services (38%) and training and workshops (12%). / 2.3 Was the project completed within the expected timescale: Y/N No / Owing to the slow start of the project due to initial implementation challenges, the project was extended by 3 years to provide sufficient time to achieve the outcome objectives. This was informed by a February 2010 restructuring, based on results of Feb 2009 Mid Term Review. A two-stage approach was pursued in which the first extension was for one year and six months to September 30th 2011, and a second extension in September 2011, to enable successful implementation. The project completed in March 2013 with final payments between WB/Government being made in June.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / An updated Financial Sector Assessment Program was launched in 2010. As a result, FLSTAP changed, including additional procurement and installation of ICT equipment for several regulatory agencies. The original components however remained the same during the project implementation. / 3.2 Set out what plans are in place for an evaluation. / There are no plans in place for evaluation. However, the World Bank maintains dialogue through two newly approved loans and is considering further capital markets work.

4. Risk
4.1 Risk Rating (overall project risk): Medium / The risks in this project included failure to maintain a stable macroeconomic environment, and others related to lack of Government’s commitment and capacity to define and implement necessary reform policies. Other project related risks included: limited technical and absorptive capacity of the various implementing agencies, and lack of collaboration and coordination among Government agencies / The risk for DFID was the hands off approach at the inception of the project. It is only at the latter stage of the project that DFID got involved in active participation in and sought accountability of the WB project management team. / Did the Risk Rating change over the life of the project? No / The risk rating remained the same throughout the project life. However, better mitigation strategies were enforced following learning from the project. In the end, the risks were overcome, but at a high price of 3 year project extension. / 4.2 Risk funds not used for purposes intended / Initially, there were challenges to put in place an effective financial management system, robust enough to be able to meet high auditing standards. Only in the later phase of the project were unqualified audit statements delivered. / 4.3 Climate and Environment Impact / FLSTAP was a technical assistance programme, and did not have climate and environmental impact measures set at project development stage. Even though direct climate and Environment impact may be considered not applicable for FLSTAP, this report recommends that in future, climate and environmental impact measures be included in such projects due to the heavy investment in ICT.

5. Value for Money
5.1 Performance on VfM measures / The FLSTAP had no VfM metrics or measures set at the project development stage. Overall, the costs were reasonable for the benefits produced by the project. The institutions created and laws supported by the project will live beyond the project and create a lasting impact on the financial and legal sectors in Kenya. The project team faced challenges in value for money. For instance: / Managing and supervising dozens of procurement processes and coordinating with 22 implementing agencies was a constant challenge. Implementing agencies almost unanimously criticized the World Bank for slow turnaround of procurement approvals. / The minimal experience of WB, Government, PIU and Implementing Agencies in the acquisition of complex ICT systems (software and hardware) posed a challenge. It took a long time to develop technical specifications for complex ICT services and equipment. / The lack of harmonization of GoK and WB procurement requirements. In later years with the World Bank Task team Leader in the field improved coordination and timeliness. / The delays in setting up an effective PIU at the inception of the project, and slow procurement processes, caused delays in results. The lesson learnt was that such projects should foster Government ownership by involving a local management team right from the design of the project. / The project flexibility in responding to changing client priorities and conditions ensured effective use of resources. For example, FLSTAP was able to re-align activities to respond to the 2009 Financial sector assessment programme, update recommendations, and support implementation of the new constitution of 2010. / Being a technical assistance project, an economic analysis was not done. As such, the benefits of the project are not quantifiable, but it is considered economic benefits have flowed to users of the financial and legal system. / 5.2 Commercial Improvement and Value for Money / The project’s procurement process, managed by the world Bank, was designed to obtain value for money. Indeed, it was cited as quite onerous by most beneficiary agencies. But having to subject contracts to open bids subject to bank no-objection - in many cases prior to awarding contracts - means transparency. / 5.3 Role of project partners / The project was steered by a Project Implementation Unit (PIU), and implemented by a total of 22 implementing partners. The initial phase of implementation was characterised by weak ownership, weak oversight of the initial PIU, and weak leadership of the reform process. After Government took action to second technical personnel from the CBK to the new PIU, this noticeably improved. / The Implementing Agency got off to a poor start characterized by managerial problems and infighting within the first PIU and a difficult relationship with GOK. However, following this poor beginning the MoF took charge of the PIU, staffing it with adequate managerial, technical, procurement, and financial management skills. / 5.4 Did the project represent Value for Money : Y/N Yes / In the first phase, the project encountered several difficulties including a long delay in setting up the PIU. In the second phase, the Ministry of Finance took over implementation and set up a strengthened PIU which laid the groundwork for improved project performance. In the third phase, from the MTR to project closure, project implementation improved tremendously, through strong and effective project management, both from Government/PIU and enhanced Bank supervision; required by DFID.

6. Conditionality
6.1 Update on specific conditions / NO Conditionality

7. Conclusions
Fostering relationship with Government of Kenya: FLSTAP represents the set of traditional technical assistance programmes that DFID was implementing prior to the Bilateral Aid Review (BAR) and Operational Plan period. The project allowed DFID and World Bank to have a relationship with Kenya’s Ministry of Finance who were the project’s lead implementation agency. This is something that could be credited to the project as it allowed regular access to key contacts (and information) on a wide range of economic and financial sector issues. / Delivering results while building institutions: As an economic governance programme FLSTAP was predominantly focused on building the enabling environment, and the necessary institutions, while at the same time delivering on headline outcome indicators. While these two aspects sometimes tend to pull in the opposite direction: building new institutions ostensibly takes time, and this tends to deliver less on tangible results, institutional building gave the FLSTAP a more sustainable outlook. Most of the institutions created have now taken a life of their own and will live long beyond the project. / Modest programme management: DFID participated in FLSTAP as a silent partner until 2011. This limited our involvement to regular progress reports, without oversight. Even though DFID became more involved in the latter stages of the project in which more results were achieved, it is difficult to fully attribute these achievements to DFID’s active involvement. But the lesson learned with these projects is that continuous oversight and operational engagement is a necessary risk mitigation tool. / Visibility and communications: As a reform programme, FLSTAP needed to front GoK and other delivery agencies as the real owners and winners in programme reforms and results. In Kenya’s context, that is a sine non qua to maintaining political and institutional will to drive difficult reforms. This tended to mean that project financiers and donors would have less visibility, resulting to the strong ownership of the project deliverables. The project achieved a good balance between donor visibility and having frontline agencies be seen as the winners of these reforms for long-term sustainability. But a lesson is that a firmer grasp of benefit flows and benefitting groups should be established at outset.

8. Review Process
This review has been undertaken by John Ndubi, DFID’s Programme officer – accountability, Results and Procurement; and Eunice Ogolo, DFID’s senior Programme officer- wealth creation, who also moderated the scores. Caroline Wangeci moderated and commented on text. / The review was informed by the World Bank’s Implementation Completion and Results Report (ICR), and involved consultations with the author of the Bank’s ICR, DFID advisors, and other project leads. / The report has gone through DFID’s Quality Assurance process.