Annual Review - Summary Sheet

Tanzania Land Tenure Support Programme
Programme Value: £4,740,000		Review Date: 10 October 2015
Programme Code: / 202843	Start Date: 20 October 2014	End Date: 30 June 2017

Summary of Programme Performance
Year	2014/15	2015/16	2016/17
Programme Score	C
Risk Rating	Medium

Summary of progress and lessons learnt since last review

This is the first Annual Review of the Tanzania Land Programme.

At the time of writing this annual review, the programme is still functionally in a pre-implementation phase. The contract for the Technical Assistance (TA) Company has not yet been awarded and none of the technical advisers that will provide support to national staff are in position yet. As a result, the programme logframe that exists continues to be the draft version produced alongside the business case. This version does not include information on milestones, so it has not been possible to assess programme performance against the logframe in this annual review. As the main programme activities have yet to start, there is limited progress to report against overall.

That said, while the contracting of the management company has delayed the programme’s start, since business case approval the programme has made progress in the following areas including:

- The development partners and the Government of Tanzania has put in place a Memorandum of Understanding (MOU) which sets out respective responsibilities in the management of the programme.
- The Ministry of Lands Housing and Human Settlements Development (MLHHSD) has recruited a Programme Coordinator, replacing the previous coordinator who moved to another position in the Ministry.
- The MLHHSD and development partners have developed an Operational Management Manual which governs the administration and operational procedures of the Programme Implementation Unit (PIU).
- The recruitment of local programme staff is underway; a recruitment firm is in the process of interviewing and pre-selecting eligible candidates for the vacant positions.

A priority for the Government of Tanzania and its development partners is to ensure that any remaining challenges that may further delay contracting of the management company programme implementation are resolved thoroughly and efficiently, allowing the programme to commence in earnest as soon as possible. Once technical advisers are in position, it will be important to agree to a workplan alongside a revised logframe as quickly as feasible.

Lessons learnt:
DFID and development partners need to engage more closely in procurement procedures and flag any issues that may pose a threat to programme implementation and advise the MLHHSD. However, it would be challenging to go beyond the offer of development partners to hire a consultant to support the process, without compromising the commitment to rely on government systems.

PIU and development partners should examine closely the future procurement exercises the programme will undertake, and assess if these processes face similar challenges e.g. ambiguity over procurement processes, long waiting times that could cause delays. Based on this analysis, partners should agree on which procurement channels to use.

DFID should share details of this experience internally with those considering procurement alternatives to minimise the chance of further delays.

Summary of recommendations for the next year

At the time of this review, the contract for technical assistance is being concluded and there are no recommendations on specific activities to include at this stage. A priority once technical advisers are in place will be to revisit the logframe to ensure these remains accurate and current. This should include updating expected timelines for deliverables to account for any impact resulting from the delay in starting the programme. The PIU, together with development partners, should also urgently finalise the programme budget and workplan in the first few months. If it does not appear feasible to complete the programme by the scheduled programme end date, DFID should consider extending this.

Context change

There have been no significant changes to the LTSP’s context since the Business Case was approved.

Language in the proposed new constitution—drawn up during Tanzania’s 2014 constitutional review — strengthens provisions for women’s rights to own and use land. However the fate of the constitutional review is very much up in the air and will depend upon action taken by the new government after the forthcoming election. At the time of writing, the context is not expected to change substantially after the forthcoming election.

However, there are several new planned programmes related to land and it will be important for DFID and the PIU to consider how they create synergies.

The DFID-funded Landesa project on Responsible Investment in Land (RIPL) has selected to develop one of its “Playbooks”—How-to Guides—in Tanzania. These will provide guidance to investors, governments and communities on how to support equitable and socially responsible land-related investments. The programme will carry out extensive consultations with each of these groups. As such, there are important areas of complementarity, especially with the LTSP’s plans to establish a multi-stakeholder group, and for this forum to discuss and agree on roles and responsibilities of different actors in the governance of land investments.

DFID is also considering contributing to a DANIDA-led support programme for civil society, which will fund civil society organisations to work on land issues. The DFID-commissioned options paper for the design of this programme considered areas of complementarity with the LTSP programme (ODI 2014). Once up and running, each programme should consider coordinating their activities, both in supporting participation of civil society in the multi-stakeholder forum and in the geographic location of their activities. The delay in the LTSP programme may provide greater scope for the programme to synchronise its activities with the CSO programme once this starts.

USAID is launching a new programme to support registration of rural land in two districts in Tanzania. Once details of this programme become available, the LTSP programme should coordinate activities to ensure alignment between approaches and selection of districts.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4528742.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4945939.xlsx

Outline of the programme

The three-year land tenure support programme will tackle weaknesses in the land administration system that constrain efficient delivery of land services and good governance, targeting processes of how land certificates are issued to rural and urban citizens, and how land is leased to investors. The programme will support the Government of the United Republic of Tanzania (GURT), through the Ministry of Land Housing and Human Settlements Development (MLHHSD), to make information on land records and processes of land allocation publicly available, and clarify and address current constraints to protecting legitimate land claims. Ultimately, these measures are expected to strengthen security of tenure, contributing to growth in agricultural production and more and better-planned investment in urban infrastructure, including housing.

The programme will introduce a multi-stakeholder group (MSG) to strengthen civil society oversight of government services and actions in the land sector, and coordination between government, civil society and private sector actors. DANIDA is facilitating the design of an additional programme to support civil society organisation (CSO) engagement in the MSG.

The programme will also improve the cost-effectiveness of surveying and adjudicating land, and issuing certificates in two target districts, which will create cost savings for future rollout of national implementation of land laws.

The programme’s aims as its impact to increase confidence to invest for all landholders in Tanzania. The main expected outcome is more transparent and accountable land governance, and effective land administration systems in Tanzania. This outcome is expected to lead to more secure tenure and will result from three outputs:

- Output 1: Proven low cost and equitable land tenure regularisation implemented in two districts – benefitting an estimated 300,000-land owners.
- Output 2: Policy and institutional framework strengthened (including the creation of a Multi Stake Holder Group in line with GURT’s international commitments on land governance)
- Output 3: Transparency improved and greater benefits from investment for all land use right holders (including the publication of data relating to existing and future large-scale land transactions).

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

There is no progress to report against any of the outcome indicators after the first year as the programme has not started implementing any of its activities. There is a risk that the outcome of the programme as currently stated will not be met in the remaining two and a half years, and partners should consider extending the programme to account for the delay. As there remain decisions and processes to implement before programme activities can begin, and there is no guarantee that these will be immune from further delay, it is unclear when the programme will be able to start. There is therefore no guarantee that the programme activities outputs and outcomes can be achieved by the current programme end i.e. June 2017.

Although the recruitment of technical assistance has been delayed, the PIU and development partners have made effective use of the time in the inception period by setting up the programme office, procuring necessary assets for the programme start, preparing an operational manual for the programme and making arrangements to recruit local staff.

Summary of the events to date:

Formalising the responsibilities of the MLHHSD, PIU and Development Partners.

In January 2015, the MLHHSD, Ministry of Finance signed a Memorandum of Understanding (MoU) with the three Development Partners which sets out roles and responsibilities of each partner. This confirmed that the Programme Implementation Unit (PIU) under the MLHHSD will implement the programme. A management committee that includes the Programme Coordinator and representatives from each development partner have met weekly during the recent phase to monitor process and agree on tasks. Early outputs agreed through this committee included the Operational Manual that guides the PIU’s management and administration, and the inception workplan.

Selecting the management company to provide technical advisers.

The process for contracting the management company responsible for technical assistance has been severely delayed as a result of irregularities in the procurement process, which lead to a series of appeals from unsuccessful bidders. These have cumulated in delaying the start of the inception period by around ten months (as of October 2015, the programme was delayed by eight months with an expected start date in December 2015).

Initial guidance in the call for proposals from the MLHHSD stated that a quality-cost-based selection method would be used to choose the winning bid, but before the bid deadline, it also issued guidance that a budget ceiling applied. However, it did not apply a budget ceiling in its evaluation process, and the winner it first selected had a budget higher than the indicative ceiling. This decision was subsequently contested in an appeal to the Public Procurement Appeal Authority (PPAA) by an unsuccessful bidder—the only one that had submitted a bid below this budget ceiling. The PPAA found that the process had been improperly run, and ruled that the MLHHSD should rerun the bid evaluation using a fixed budget method, which took account of a budget ceiling. The MLHHSD evaluation committee did so and awarded the contract to the bidder that had contested. This award decision has been contested by unsuccessful bidders who have called for the whole process to be annulled and rerun. At present, it is still unclear if unsuccessful bidders will submit formal appeals, which could further delay the process.

Progress against the inception work plan.

The four areas of work included in the workplan for the inception period included: recruitment of human resources; establishment of a PIU office; capacity building of PIU staff; and coordination of programme activities, which largely involved arranging payments of PIU staff. Of these, most progress has been made in establishing the PIU office and getting underway staff recruitment. Progress has also been made on procuring vehicles for the programme.

The necessary delayed recruitment of most staff has meant it has not been possible to progress with capacity building or coordination of programme activities without technical advisers in place.

Establishing the PIU office

The MLHHSD has rented office premises to house programme staff since May 2015. The Programme Coordinator, Accountant and Team Leader for Land Tenure Regularisation have been seconded from the Ministry since July 2015. Office assets for these staff and furniture for the office have already been procured.

Recruitment
MLHHSD and its development partners agreed to use a recruitment firm to hire the directly-recruited programme staff. These include the following positions:

- Team Leader for Institutional and Policy Development
- Database Manager
- GIS/Surveying specialist
- Social Expert
- Procurement Specialist
- Project Administrator
- Communications Specialist
- Administrative assistant
- Driver.

 This process started in July 2015 and interviews are expected to be finished by early October, with candidates notified in early November. The large number of candidates for the tasks has resulted in a minor falling behind schedule. There is a small risk that the process will fall further behind schedule in the final stages of selection as senior officials from the MLHHSD are meant to interview up to four candidates for each of the nine positions within a two-week period, which may be optimistic given their likely availability. It is recommended that MLHHSD and development partners revisit plans for the final interviewing stage to ensure that the timeframe for completing this is commensurate with availability of senior staff, and any delays in completing this process do not risk delaying the programme start.

Procuring programme vehicles
Programme partners agreed for DFID to procure the four programme vehicles through DFID’s procurement channel with Crown Agents. Following responses to a tender issued by Crown Agents, a cost-effective supplier has been selected and vehicles are expected for delivery in December 2015.

Overall output score and description

The overall output score is C: Outputs substantially did not meet expectations.

The intention during programme design was for the logframe to be completed through discussion with the technical advisers that will support in implementing the programme. In the current version of the logframe five of 12 output indicators have provisional Year 1 milestones but since activities have not commenced, these are inevitably unmet.

Key lessons

The protracted procurement process highlights a possible need for DFID and development partners to engage more closely in procurement procedures and flag any issues that may pose a threat to programme implementation and advise the MLHHSD. However, it would be challenging for development partners to go beyond the offer of development partners to hire a consultant to support the process, without compromising the commitment to rely on government systems.

 A more practical recommendation is that the PIU and development partners should examine closely the future procurement exercises the programme will undertake, and assess if these processes face similar challenges e.g. ambiguity over procurement processes, long waiting times that could cause delays. On the basis of this analysis, partners should agree on what procurement channels to use.

It is recommended that DFID should share details of this experience internally with those considering procurement alternatives to minimise the chance that this situation repeats itself.

Key actions

- Once the TA contract is awarded, the PIU, development partners and the selected management company should develop priorities for the inception period. These should include finalising the programme logframe, workplan and budget.
- A thorough analysis of the pros and cons of different options for programme procurement should be carried out. This should explore the relative efficiency of procuring future goods for the programme through the MLHHSD systems in comparison to alternative channels. On a basis of a sound understanding of realistic timelines for procuring needed goods and services through alterative options, the management committee should decide upon a course of action for procurement.
- Partners should confirm the need for a project extension, and how this will be managed. A course of action should be agreed within the first month of the contract starting.

Has the logframe been updated since the last review?

The logframe has not been updated since approval of the programme business case. Once the MLHHSD contracts the TA, a priority for the programme will be to review and update the logframe outputs, activities and indicators.

C: DETAILED OUTPUT SCORING (1 page per output)

Note: as the logframe has not been finalised it has not been possible to provide scoring in this annual review.

Output Title	Proven low cost and equitable land tenure regularisation implemented in two districts – benefitting an estimated 300,000 land owners.
Output number per LF		1	Output Score	C
Risk:		Medium	Impact weighting (%):	34
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Number of parcels demarcated, adjudicated and registered in ILMIS (or equivalent) in target areas
1.2 % households collecting title
1.3 % of those registered as land owners in target areas that are women, disaggregated by female headed households and co titling with husband
1.4 Average cost (of production) of title
1.5 % demarcation and adjudication complying with programme social safeguards
1.6 % decrease in number of land disputes in villages compared to baseline in target areas

Key Points
N/A
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
N/A

Output Title	Policy and institutional framework strengthened (including the creation of a Multi Stake Holder Group in line with GURT’s international commitments on land governance)
Output number per LF		2	Output Score	C
Risk:		Medium	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Multi-stakeholder group established and operating effectively (i.e. senior representation with constituency fully represented
2.2 Necessary changes in legal, policy and institutional framework to safeguard tenure security, and clarify land allocation/transfer procedures implemented
2.3 Climate change and resilience incorporated into national and local land use planning procedures and policies

Key Points
N/A
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations
N/A

Output Title	Transparency improved and greater benefits from investment for all land use right holders( including the publication of data relating to existing and future large scale land transactions)
Output number per LF		3	Output Score	C
Risk:		Low/Medium/High	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 % of existing and new large-scale land acquisitions with key information available in a public database (information to be defined through MSG)
3.2 Guidelines for roles and responsibilities of investors, government and villages approved by MSG and implemented across government
3.3 [BLANK]

Key Points
N/A
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

As the PIU’s first financial report is not due until after this Annual Review, only those disbursments that DFID Tanzania has made directly are reviewed here. These disbursements are expected to account for the overwhelming majority of disbursements so far, as the the PIU has only reported procured a small number of low value items—mainly office assets.

Item	Cost (£)
Deposit and rent for PIU offices for one year	34,736
First disbursement for the programme	226,672
Contract for hiring local staff through the recruitment firm	28,646
Consultancy for inputs into the drafting of the new constitution	17, 075

In addition, DFID is in the process of procuring programme vehicles. The anticipated cost for this is around £200,000.

VfM performance compared to the original VfM proposition in the business case

The VfM proposition as set out in the business case remains unchanged. It has not been possible to comment on this as up until now the programme has spent a very low portion of its available resources and its activity has been restricted to setting up systems and undertaking limited procurement. The business case identified the main drivers critical to VfM being those associated with programme activities, and did not consider in detail issues arising during this pre-implementation phase.

No payments against milestones have been made yet, but the programme appears to have made choices on procurement and recruitment that are cost efficient and therefore deliver value for money. The PIU has asked DFID to procure vehicles on the programme’s behalf through a tender process run by Crown Agents which has led to the selection of the offer that presents the best value. Although the offices and salary costs of the three MLHHSD staff seconded to the programme have been paid for by the programme during a period of limited activity since July, the PIU and partners have delayed hiring any other staff until the technical advisers are in position, averting further salary costs during pre-implementation. Both processes are currently underway and current expectations are that they will be finalised on time and to cost.

From the PIU’s side, although no financial reports have been issued yet, the only spending reported to date has been on procuring assets necessary for current programme staff. Unnecessary costs incurred by premature spending have thus been avoided.

Assessment of whether the programme continues to represent value for money

As reported above, until now, the programme has spent a very small portion of its available resources and implemented very few activities. The programme context remains the same and therefore the programme is expected to deliver value for money as predicted once it starts, although this will be informed by actual performance. The next annual review will therefore contain more analysis of value for money performance.

The PIU and development partners should examine closely the future procurement the programme will undertake, and assess if these processes face similar challenges to those encountered for contracting technical advisers, e.g. ambiguity over procurement processes and long bureaucratic deliberation that could cause delays. Based on this analysis, partners should agree on which procurement channels to use. In addition, several of the development partners have recently flagged as an issue relevant to value for money the relatively high salary scale for non-technical assistance programme staff. Views among development partners differ on this as the scale originally agreed to by DPs reflected market rates in the private sector seen to be necessary in order to avoid high levels of staff turnover. It is recommended that the development partners periodically assess performance of staff once the programme activities start to assess if performance of key staff in the PIU is in line with expectations for the salary levels.

Quality of financial management

Since the programme has not begun its main activities, there is little financial activity to report against. Financial management of activities so far is sound overall. DFID has procured the majority of goods and services during this pre-implementation phase, including the recruitment firm and project vehicles through Crown Agents. DFID has also made payments for the rent of the PIU offices. The PIU has procured furniture and office assets. The PIU has not yet delivered its financial report for the first quarter so it is not possible to assess the quality of its financial reporting or of its systems for financial management. The PIU’s systems are meant to be set up according to the guidelines of the Government of Tanzania, and it is recommended that the PIU provide guidance to development partners on how these will be adapted for the programme, including information on financial reporting cycles and contents of reports. A priority for when the technical advisers arrive is the preparation of a programme budget that will allow development partners to prepare a disbursement plan for funding the programme.

Date of last narrative financial report	None to date
Date of last audited annual statement	None to date

E: RISK (½ page)

Overall risk rating: Medium
This remains unchanged since the business case.

Overview of programme risk: The risk assessment and mitigation strategy set out in the LTSP business case identifies risks to successful programme implementation, including economic and financial, institutional, environment and climate, social and political and reputational risks. All risks presented in the business case have been reviewed, and both the overall categories and the suggested mitigating actions remain relevant and should be reviewed once the programme starts.

Several identified risks are worth highlighting:

Institutional Risk: Because the programme start has been delayed, there has not been an opportunity to demonstrate effective implementation before Tanzania’s General Election as recommended in the risk assessment. However, the GURT’s political commitment to the programme remains strong and the post-election outcome is not expected to affect programme delivery. If feasible and appropriate, the contract with the management company should be signed before the election to prevent further delays.

The business case also included risks and mitigating actions from a Fiduciary Risk Assessment (FRA) that was carried out during the programme design phase. Most of the recommended mitigating actions made in the FRA were taken up and included when drawing up the Memoranda of Understanding between the development partners and the Government of Tanzania, and confirmed in the programme’s Operational Manual.

Outstanding actions from risk assessment

Apart from risks from the FRA, all risks and recommendations for mitigation made in the business case remain outstanding and will need to be addressed once the programme starts.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is behind its planned timeframe. The reason for this is the delayed contracting of the management company responsible for providing technical advisers. According to the original timeframe, the programme was meant to start in May 2015 after contract award and finalisation of bilateral agreements. If the remaining process of awarding and contracting the winning management company is resolved without further hitches, the earliest date for deployment of technical advisers is early December 2015, seven months behind schedule.

Performance of partnership (s)

The partnership between DFID and the Government of Tanzania is working well. The PIU has been responsible for carrying out all the main tasks in the inception period, including contracting the management company, establishing the project office, procuring assets and producing a set of terms of reference for a consultant to translate the land laws into Kiswahili. DFID has provided support to the MLHHSD as and when requested, including in running the procurement process for vehicles through Crown Agent, and procuring services for hiring non-government staff.

The MLHHSD independently conducted the process of tendering and awarding the Technical Assistance contract, and DFID and other development partners have been supportive of this process, providing advice and support upon request. While closer donor engagement in the procurement process may have resulted in fewer procedural errors and resulting delays, using the Ministry’s tendering system has strengthened the government’s ownership and strengthened trust in the partnership. Looking ahead past the forthcoming election, it will be important for DFID to maintain the strong sense of mutual trust with the MLHHSD through regular meetings and provding assistance upon request.

The partnership with SIDA and DANIDA is also working well, with all partners attending regular meetings to discuss progress. PIU has suggested that two representatives from each development partner attend coordination meetings to ensure institutional memory is not lost when representatives move on, and this view is supported.

As the management company has not yet been contracted, there is nothing to report on the relationship between technical advisers, the MLHHSD and development partners.

Asset monitoring and control

The programme is following instructions in the Operational Manual for monitoring assets. So far the only assets procured have been for office staff already employed on the project. These have been registered and the programme accountant will record future assets in an asset register. An asset verification check will be carried out yearly. As the PIU office is not part of the Ministry, there is a low risk that programme assets get mixed up with those in the ministry.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
As per DFID’s conditionality policy, financial aid is provided to a country government based on a commitment to the ‘partnership principles’ by that country government, namely:
- Reducing poverty and achieving the MDGs;
- Respecting human rights and other international obligations; and
- Strengthening financial management and accountability, which reduces the risk of funds being misused through weak administration.
- A commitment to strengthening domestic accountability

In the context of this programme, these will be applied to the land sector specifically. Particular attention will be given to respect for the legal, economic, social and cultural rights of poor landowners, and women.
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

As the programme has yet to commence, there is no update. The evidence underpinning this intervention as described in the business case has not changed and remains relevant.

Monitoring progress throughout the review period

A Monitoring expert will be recruited through the technical assistance contract. As part of revisiting the logframe, it will be important that (s)he update the monitoring plan and establish appropriate indicators to assess programme performance. This should include both procedural indicators as well as indicators that measure impacts on direct beneficiaries and other stakeholders. To establish appropriate indicators for outputs related to the policy and institutional framework and transparency, the M&E specialist should engage with a broad selection of representatives to ensure indicators are meaningful and appropriate.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / ’As per DFID’s conditionality policy, financial aid is provided to a country government on the basis of a commitment to the ‘partnership principles’ by that country government, namely: / Reducing poverty and achieving the MDGs; / Respecting human rights and other international obligations; and / Strengthening financial management and accountability, which reduces the risk of funds being misused through weak administration. / A commitment to strengthening domestic accountability / In the context of this programme these will be applied to the land sector specifically. Particular attention will be given to respect for the legal, economic, social and cultural rights of poor landowners, and women. / Failure to fulfil any of the commitments referred to above, in respect to activities in the land sector, may lead to DFID’s aid being interrupted, reduced or suspended, delivered in a different way or terminated.’’
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process