## A1 Goal, Purpose, Risk
Annual Review (reviewed August 2010)
ARIES Project Code
ARIES Project Description | Education Sector Support Programme in Nigeria (ESSPIN
A1: Goal, Purpose, Risk
Goal
Goal statement | Nigeria's own resources are efficiently and effectively used to achieve the MDGs for universal education and gender equity
Indicator 1 | G.1 Primary and junior secondary education net enrolment rate %
Milestone for this review (if any) | Milestones were set for 2010
What progress has been made in the period covered by this review? | Progress has not been systematically recorded since 2008. There is no reliable enrolment data for pre-primary, primary and junior secondary schools in Nigeria over time. ESSPIN has been dependent, to date, on household and other survey data to set its baselines. The Nigeria DHS EdData Survey 2010 (using attendance rather than enrolment rates) reports that 61% of children aged 6–11 attend primary school (64% boys and 58% girls). Survey data tends to be lower than administrative enrolment data
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | G.2 Primary and junior secondary education completion rate (%)
Milestone for this review (if any) | 2010 Milestones were set for the six ESSPIN States based on 2006 National Core Welfare Indicators Survey (2006).
What progress has been made in the period covered by this review? | This is a weak basis for assessing completion rates. There has been no tracking of completion rates.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | G.3 Gender parity index in primary and junior secondary education
Milestone for this review (if any) | Milestones were set for the six ESSPIN States in 2010 based on 2006 National Core Welfare Indicators Survey
What progress has been made in the period covered by this review? | No tracking of results has been possible. The publication of annual census data in the six ESSPIN States will make this possible from 2011
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Evidence is restricted. As yet, it is insufficiently collated and reported on for the 1000 schools which ESSPIN is supporting directly. Greater attention to the collection and analysis of sex disaggregated data within ESSPIN is required.
Goal Recommendation 1 | The milestones and the targets for this goal should be revisited and recast based, a) on available data-based evidence and b) on a re-assessment of the likely achievement of the Programme's purpose
Goal Action Point 1 | This work should be part of the proposed revision of the Logframe
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | The planning, financing and delivery of sustainable and replicable basic education services, in terms of access, equity and quality are improved at Federal level and in up to six States
Indicator 1 | P.1 Primary education net enrolment rate of the bottom two consumption quintiles (%)
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Baselines and targets yet to be established
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | P.2 Proportion of Class 4 students in public primary schools who demonstrate ability to read with comprehension (%)
Milestone for this review (if any)
What progress has been made in the period covered by this review? | It is too early to assess progress in the six ESSPIN States. The only targets are for 2014. The basis for these targets is unclear.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | P.3 Percentage of teachers in public primary and junior secondary schools with at least "near sufficient " professional working knowledge
Milestone for this review (if any)
What progress has been made in the period covered by this review? | ESSPIN has established its own baseline data (2010) with targets set for 2014 in the six ESSPIN States
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4 | P.4 State Government education budget utilisation rate (%)
Milestone for this review (if any) | Band baselines for budget utilisation rates were set for 2009, to be reported on in 2011, by State. Jigawa, Kano, Kwara and Lagos 80-100%, Enugu 90-100% and Kano 70- 100%.
What progress has been made in the period covered by this review? | Release of data from State Accountants General awaited. Preliminary evidence shows variation by State and between capital and recurrent expenditure
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Not yet. The risks that underpin Purpose level assumptions remain high, especially given the uncertainties arising from the recent State and Federal elections. ESSPIN has some control and influence in setting new milestones and targets enabling better monitoring at the State level. It can also contribute to stimulating demand for schooling. There is some traction too through collective SLP action to further political engagement and leverage. But the assumptions that underpin replication within and beyond ESSPIN States needs greater analysis and programme elaboration. Progress seems most likely in mid 2011 in Jigawa, Kaduna, Lagos and Kwara
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | The gap between the purpose of the ESSPIN programme and the realisation of significant MDG related gains is large, especially within the timeframe of 2008-2014. The Programme is not well served either by the convoluted Purpose level statement and by the level and the construction of its indicators
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | ESSPIN has been effective in enabling some systemic technical reforms to be introduced and instituted in six Nigerian States under its four Output driven activities. This now provides a launch pad for more sustainable State support for basic education. But this in turn, depends on high level political support being maintained over the next four years (2011-14).
Purpose Recommendation 1 | The purpose level statement requires reworking (with its indicators) as a part of a wider ESSPIN reappraisal process to determine what can realistically be achieved by 2014.
Purpose Action Point 1 | Within three months ESSPIN (with SPARC) should provide an assessment of political buy in to school improvement reforms in new State governments
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 3 | #VALUE!
Purpose Justification | ESSPIN is not well served by its convoluted Purpose level statement. For the first two and a half years of the Programme, ESSPIN has been initiating and demonstrating good practice, in six States; in school level improvement, and in planning, budgeting, organisation and management, at the Output and sub-output levels. It cannot be stated with confidence, in mid 2011, that there is good progress towards project completion as much needs to be done to finish work at the Output and sub-output levels. Its evidence base is uneven and the tracking of results poor. An early re-appraisal exercise is being recommended. In addition, the purpose level targets cannot be achieved without significant political buy-in, for which a well-honed strategy is yet to emerge.
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1 | A much more rigorous risk analysis is required as part of a proposed Programme re-appraisal. There are no risk ratings in the February 2011 Logframe.
Risk Action Point 1 | Recommendation 1 should be addressed in the next three months
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | The present Logframe is weak on a number of counts. It fails to represent a clear theory of change in its goal, purpose and output statements and in its choice of indicators. Secondly, it needs to be reassessed in the light of risk analysis and within the timeframe for the ESSPIN programme. Thirdly, it needs to be re-examined in the light of DFID's new imperatives as reflected in its new Operational Plan.
Logframe Recommendation 1 | The Logframe should be reworked as part of a re-appraisal process in the next three months
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Federal Government governance framework for enabling basic education reform strengthened
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | Needs to be re-assessed as part of Programme re-appraisal
Original or Revised Impact Weight (%) | 15% on Logframe but 20% in ESSPIN ARIES return
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
#VALUE!
DFID Share revised/needs revision? | Yes
If Yes, why was/is this? | Given, a) the relatively low level of performance at the Federal level and, b) the intention to give greater attention to service delivery at the State level, the overall share of Output 1 should be reassessed. | 1
Original or Revised DFID Share | Unclear. If the Logframe figure of £12.6 million is correct. This is approximately 15% of the DFID budget. But other ESSPIN data puts the figure at 6% | 2
3
Indicator 1 (leave blank if standard indicator) | O.1.1 Utilisation rate of UBEC-IF funds for basic education (three year rolling) | 4
Is this a Standard Indicator? |  | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestones were set for 2010 for the six ESSPIN States, and non-ESSPIN States, based on a three year rolling performance with a 2007-2009 baseline. In 2010: 70% for ESSPIN States and 60% for non-ESSPIN States | 0
Progress made in the period covered by this review, including numbers. | ESSPIN draft ARIES report records disbursement rates for 2008-2010 at above 80% for Jigawa, Kaduna, Kwara and Lagos, 42% for Enugu and 0% for Kano. These figures could not be fully verified by the MTR on the ground in the States. No figure is available for non-ESSPIN States against a 2010 milestone of 60%
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | O1.2 The number of Nigerian States which replicate good practices: a) develop MTSS and AESR b) implement policy of direct funding to primary and/or junior schools c) publish school census report by August d) apply revised quality instrument e) follow national SBMC policy, f) implement periodic teacher assessments and g) implement periodic assessments of learning outcomes
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestones were set for 2011 by number of States (including ESSPIN States) against a number of sub-indicators: a) 6 MTSS and AESR b) 0 for direct funding c) 14 for school census d) 6 for quality assurance e) 10 for SBMC f) 6 for teacher assessment and g) 6 for learning outcomes assessment
Progress made in the period covered by this review, including numbers | a) MTSS and AESR is operational in all six ESSPIN States (two cycles) b) ESSPIN has provided school grants through SUBEBs but this has not yet been adopted by any State through the budget c) In the second cycle of school censuses in all six ESSPIN States and assistance is being provided to six other States on data processing and analysis d) Variable progress in instituting systemic quality assurance reforms which require high level State approval e) Good progress on SBMCs in ESSPIN supported schools in ESSPIN States; 85% functional. Working with UBEC to replicate this practice in up to six more States and f) TDNA and MLA surveys have been conducted in all six States
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 4 | 0.25
Impact Weighted Score | 15 | #VALUE!
Justification for the Score | Work at the Federal has changed course during the first three years of ESSPIN. It has moved from a reform agenda - as reflected in the Output statement - to a more pragmatic approach to working with Federal bodies that have the authority and the capacity to advance the replication of ESSPIN good practice beyond ESSPIN States. As a result, both the Output statement and the second indicator don't reflect the current work programme. Relative to levels of investment on Output 1 thus far, the return on investment is relatively limited.
Output 1 Recommendation 1 | The Logframe requires revision, as the indicators are not a clear reflection of Federal level action and the way in which activities for this Output have evolved. This Output also needs to be re-assessed in relation to planned levels of investment into Outputs 2-4 (at State level).
Output 1 Action Point 1 | Action needed as part of Logframe revision
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | State level and local government governance and management of basic education strengthened
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.2
DFID Share revised/needs revision? | Yes
If Yes, why was/is this? | Needs re-appraisal if reforms are to be sustained in ESSPIN States and replicated more widely
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | O.2.2.1 Percentage of annual State budget derived from the MTSS
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone set for 2011: 50% in Enugu, Kaduna and Kano 60% in Lagos, Kwara and Jigawa
Progress made in the period covered by this review, including numbers | ESSPIN reports data for the 2011 budget compared to MTSS as: Enugu 95%; Jigawa 95%; Kaduna 65%; Kano 73% Kwara 82% and Lagos 79%. Caution is needed in accepting these figures at face value given that budgets exceed plans and disbursement is uncertain and erratic. Disbursement and expenditure relative to MTSS would be a better measure of performance
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | O.2.2.2 Percentage of Departments in SMoE and SUBEBs using Departmental Work Plans developed from MTSS and annual budget (%)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Percentage figures by ESSPIN State for 2011 - 65% in all States
Progress made in the period covered by this review, including numbers | ESSPIN records Enugu, Kano and Kwara with 100% in MoE and SUBEBS respectively; Jigawa 60% and 100%, Kaduna 90% and 100% and Lagos 75% and 100%. There is a small amount of sample evidence on the ground that suggests that these figures may exaggerate a little, the actual use of work plans.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | O.2.2.2 Institutional functionality for State Basic Education Bodies of a) policy and planning b) financing c) pre-service teacher education d) teacher management e) quality assurance and f) partnerships with non-State providers
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestones are set for each category for 2012. A ranking A,B, C and D system is used with a descriptor for each sub-indicator
Progress made in the period covered by this review, including numbers | a) Policy and planning capacity and organisation has been strengthened in the six States to produce an MTSS b) Some but limited progress on alignment of plans and budgets; much less on ensuring that releases and expenditure are on plan c) Modest progress in assisting reform in teacher training colleges of two States. Major reform of pre-service education lies beyond the design of ESSPIN d) Two State studies on deployment and management of teachers and work on teacher payrolls e) Gradual progress towards quality assurance reforms with variations in new structures and political support across the six States f) ESSPIN engagement with CSOs in all six states with sample evidence of the willingness of the MOEs and SUBEBS to recognise CSOs as partner agencies
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | O2.3 Number of schools inspected using the reformed quality assurance process
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone set for 2011 for each ESSPIN State. This includes an indicator for primary and junior secondary schools as one group and one for senior secondary schools. The rationale for each milestone target is unclear: Enugu 100 basic and 20 SS; Jigawa 265 and 14; Kaduna 500 and 60; Kano 100 and 20; Kwara 223 and 29; and Lagos 153 and 35
Progress made in the period covered by this review, including numbers | Limited progress: Nothing in Enugu; Jigawa 13 Kwara 12 Kaduna 360 and Lagos 695. This is very early in the roll out of new inspection practice.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 3 | 0.5
Impact Weighted Score | 20 | 0.1
Justification for the Score | There is an uneven performance across this Output. New ways of working have been introduced but their benefits are not yet realised in better schools. The adoption of new ways of working depends on their political acceptance and sustenance.
Output 2 Recommendation 1 | Assess the relative weight of short term technical TA in advancing sustainable reforms relative to a continuous process of political engagement involving SPARC and other SLPs
Output 2 Action Point 1 | This recommendation should be addressed as part of the proposed re-appraisal process.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Capacity of primary and junior secondary schools to provide an improved learning environment developed and sustained
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | Advancing an integrated school improvement approach across States is key to the success of ESSPIN 2011-2014
Original or Revised Impact Weight (%) | 45%
Risk revised/needs revision? | Yes
If Yes, why was/is this? | As with the other Outputs, there is insufficient risk analysis and a clear distinction as to what ESSPIN can do, what the SLPs collectively can do, what DFID can do and what is beyond influence
Original or Revised Risk | High | 1
0.45
DFID Share revised/needs revision? | Yes
If Yes, why was/is this? | Increased share for greater level of service delivery (PSA) in ESSPIN interventions
Original or Revised DFID Share | None provided
Indicator 1 (leave blank if standard indicator) | O.3.1 Percentage of public primary schools with a School Development Plan (SDP)
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestones set for 2012 in the six States: Enugu 10% Jigawa 20% Kaduna 25% Kano 20% Kwara 50% Lagos 35%
Progress made in the period covered by this review, including numbers | No measurement of SDPs in the six States undertaken beyond ESSPIN supported schools. It is estimated that these represent 7.5% of all primary and junior secondary schools in the six States. All of these schools have conducted self evaluations before undertaking SDPs
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | O 3.2 Percentage of public primary and junior secondary schools inspected using the reformed inspection process being graded satisfactory or better
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone set for 2012: Enugu 3% Jigawa 25% Kaduna 5% Kano 10% Kwara 25% and Lagos 25%.
Progress made in the period covered by this review, including numbers | No baseline established and early days in developing the capacity of inspectors
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | O.3.3 Percentage of headteachers in public primary schools with at least "near sufficient professional competence"
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | 2011 Milestones set by State for ESSPIN schools and non ESSPIN schools: Enugu 5% and 1%; Jigawa 30% and 5%; Kaduna 10% and 4%; Kano 15% and 1%: Kwara 30% and 5%; and Lagos 20% and 5%
Progress made in the period covered by this review, including numbers | This milestone is to be assessed in 201 -12. Its baseline (2010) is drawn from an ESSPIN survey. The rationale for the milestones is unclear. "Near sufficient professional competence" is second on a grading scale of four.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | O.3.4 Percentage of public primary and junior secondary schools with water supply and latrines
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone for 2012. This is by ESSPIN State for water supply and separate latrines for girls. A baseline has been set, using 2009/10 Annual School Census data. The 2012 target is set at 5% points higher than the baseline.
Progress made in the period covered by this review, including numbers | Water and toilet blocks has been provided in 273 ESSPIN support schools. 2010/11 Annual School Census data awaited for wider picture in six ESSPIN States.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 3 | 0.5
Impact Weighted Score | 45 | 0.225
Justification for the Score
Output 3 Recommendation 1 | Output needs to be reconceived a) to reflect school improvement as the central driver for change for ESSPIN and b) to develop indicators that are more complete in their assessment of school improvement.
Output 3 Action Point 1 | As part of the re-appraisal process
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Mechanisms for accountability strengthened through increased capacity of communities and civil society to support schools and articulate demand for inclusive, quality basic education services.
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | An insufficiently weighted, critical component of school improvement
Original or Revised Impact Weight (%) | 20%
Risk revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Risk | High | 1
0.2
DFID Share revised/needs revision? | Yes
If Yes, why was/is this? | Requires reassessment in an overall reappraisal of ESSPIN and the use of its funds especially with regard to direct service delivery
Original or Revised DFID Share | None provided
Indicator 1 (leave blank if standard indicator) | O.4.1 Percentage of public primary schools with functioning SBMCs
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestone set for 2012 by State: Enugu 20% Jigawa and Kaduna 40%; Kano 50%; Kwara 70% and Lagos 0% (based on 2010 ESSPIN Community Survey)
Progress made in the period covered by this review, including numbers | SBMCs established in 85% of ESSPIN supported schools. Work with UBEC designed to extend ESSPIN approach to SBMCs to other States. Planned ESSPIN census follow-up survey (2012) should update wider progress
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | O.4.2 Percentage of communities where women and children perceive SBMC decisions to be reflecting their concerns
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Milestones set for 2011 by State. Enugu 0% and the other five States 5%
Progress made in the period covered by this review, including numbers | Reporting depends on CSO reports which is variable across States. Some initial results Jigawa 5% Kaduna 2.5% Kano 1.3% Kwara 2% Lagos 0.3%. Reporting on this indicator is inadequate; there is not even numbers of women and children on SBMCs or serving as officers.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) | O 4.3 Quality and scale of civil society partners basic education advocacy work on behalf of communities
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestones are set in the Logframe, only 2014 targets. But 2012 Community Survey is to be conducted
Progress made in the period covered by this review, including numbers | 36 CSOs working with ESSPIN as contractors on SBMCs. Gradual move towards CSOs working with Social Mobilisation Units. Sample evidence of CSOs being supported on local-level accountability issues but not yet on identifying and progressing advocacy issues at policy level
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator) | O. 4.4. Percentage of parents/guardians of public primary school students who were informed by the school, in the previous three months, of school resources and their use.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | No milestones set, only 2014 targets based on 2010 ESSPIN Community Survey. Community Survey to be conducted in 2012
Progress made in the period covered by this review, including numbers | No numerical data. No reporting mechanisms yet in place. MTR observations and interviews suggest increased interaction but possibly dependent on levels of literacy, influence, status etc.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator) | O.4.5 Percentage of schools where community demand was responded to with the provision of resources
Is this a Standard Indicator? | No
Select standard indicator from drop down list | Milestones set for 2011 by State: Enugu 2% Kano 5% Kaduna 10% and Jigawa, Kwara and Lagos 20% | 0
Milestone for this review (including number, if any) | According to the Logframe handbook, a 10% sample of schools is being monitored intensively by CSOs. Unable to get the analysis of this sample in Kaduna, Jigawa or Kano. MTR evidence suggests that this is definitely happening in more than a few schools but impossible to estimate scale. Results to date: Enugu has not started; Lagos 1.2%; Kwara 5%; Kano 0.4%; Kaduna 8% and Jigawa 10%. 2011 milestones seen as unrealistic. ESSPIN plans to move towards a more comprehensive model of bottom up planning involving school, community and LGEA.
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 | 3 | 0.5
Impact Weighted Score | 20 | 0.1
Justification for the Score | Uneven progress across the sub-outputs. Sound work on establishing SBMCs, on raising awareness of the right to education and involvement in schools, and piloting a demonstration of the importance of water and latrines in a school improvement model. Lack of evidence to show that access and equity issues are being thought through in a fundamental way. Little attention to replication strategies
Output 4 Recommendation 1 | Need for clearly thought-out strategy on access and equity including a reappraisal of the degree to which women and children plus e.g. those from minority ethnic or indigene groups and those who are illiterate are involved fundamentally in the school improvement
Output 4 Action Point 1 | To be assessed as part of re-appraisal
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-06-03
Impact Weighting (must = 100) | 100%
Total Impact Score | 60 | #VALUE!
Output Risk | High | #VALUE!
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review | X
DFID staff review
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant | X
Donor partners
DFID staff | X
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | ESSPIN'S Integrated School Improvement model requires that partnerships be created at all levels in Nigeria's complex education system, as well as with, political agencies, other aid agencies, CSOs, the media and with other SLPs. It has been broadly effective in creating working relationships with officials in State ministries and SUBEBs. Efforts to create State Steering Committees to approve/guide ESSPIN programmes have not been effective although in one or two States broader aid coordination mechanisms have been established (e.g. Kaduna). In two States ESSPIN has offices within the Ministry. Partnership with the Federal Ministry has been much less effective. Building partnerships is now focused on particular institutions that have the authority and the potential to replicate good school improvement practice. Working with CSOs as contractors is largely productive. Considerable trust has been built up at the school, community and LGEA level where ESSPIN has been active through pilot activity. Potential for deepening collaboration with GEP/UNICEF and ensuring clarity of messages on e.g. Planning (MTSS & SDPs) and Budgeting; EMIS and SBMCs
Working with Partners Recommendation 1 | An early re-assessment of the likely political support for ESSPIN assisted activities is required in the next three months
Working with Partners Action Point 1 | This assessment should be a joint SLP process
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | The school improvement model is well-founded in the evaluation and research literature. In dysfunctional systems there may be quick wins through single interventions but Nigeria requires systemic reform and evidence that an integrated approach can bring change in teaching and learning practice and community engagement. In this respect ESSPIN is innovative in Nigeria. It is also innovative in supporting the direct movement of funds to schools.
Best Practice / Innovation Recommendation 1 | Strategies for rolling out and replicating good practice requires urgent attention - technical and political
Best Practice / Innovation Action Point 1 | This issue will be central to the proposed reappraisal process over the next three months
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | The ESSPIN programme is well planned and coordinated at the central level in Abuja. Planning and report mechanisms are well understood across the State teams, the calibre and commitment of which is high. Areas needing attention include the input into planning and management of all consortium partners, relations with DFID and the need for a greater measure of decentralisation to the State teams.
Project Management Recommendation 1 | As part of a re-appraisal process attention should be paid to the size, location and primary responsibilities of the Abuja based team and to newly financial reporting systems able to link expenditure to Output (and sub-output) and by State.
Project Management Action Point 1 | To be assessed within three months
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2 | Need for re-defined working practices and reporting procedures between ESSPIN and DFID in Abuja without delay.
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | The changing aid imperatives of DFID since May 2010 have impacted on ESSPIN in a number of ways. Implicitly the governance reform-led theory of change model is being questioned, especially in relation to the likelihood of substantive gains in access, equity and quality within the timeframe of the programme. ESSPINS's response is deemed inadequate by DFID in relation to its spending patterns (TA v PSA) and its ability to respond to new needs and act flexibly (private schools, girls' education in Northern Nigeria). It is essential that this discordance of view and expectations be resolved to ensure consistency with DFIDs new Operational Plan and the achievements, trust and evidence for change that ESSPIN has brought about.
Key issues, points of information or additional comments that may be useful for this or other project teams. | The success of ESSPIN 2011-2014 will depend heavily on a joined up Programme/SLP/DFID approach to political engagement geared to leveraging political support, and to more and better-used financial resources for basic education.
Other Recommendation 1 | A joint DFID ESSPIN programme re-appraisal within 3 months
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
ESSPIN Logframe February 2011 and Logframe Handbook Feb 2011
ESSPIN Inception Review (2009) and Annual Review (2010)
ESSPIN Quarterly Reviews to March 2011
ESSPIN Results Table March 2011
ESSPIN Output and Strategy Reports prepared for the Mid Term Review.
ESSPIN State Team Outputs and Strategy Reports prepared for the Mid Term Review
State Level MTSS, School Census and Annual Education Sector Performance Reports 2009/10 and 2010/11
Evidence Recommendation 1 | No one document fully captures the headline results and achievements of ESSPIN and there is no tracking data in place to monitor progress towards milestones and targets over time. Despite a volume of reports it is a struggle to get a clear picture of what change is happening and why/not.
Evidence Action Point 1 | Reporting to DFID on a set of high level indicators needs to be introduced without delay
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | At this stage it is impossible to gauge the sustainability of the access, quality and equity benefits that are beginning to be realised (largely at a pilot level). Until there is greater clarity on the costs of replication for an integrated approach to school improvement, a clear and costed replication, roll out and leverage strategy is in place, and an assessment of the political environment 2011-2014 is conducted, judgements on sustainability are premature.
Sustainability Recommendation 1 | Issues of sustainability within ESSPIN States and beyond are strong considerations to be factored into recommended re-appraisal
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | The milestones and the targets for this goal should be revisited and recast based, a) on available data-based evidence and b) on a re-assessment of the likely achievement of the Programme's purpose | ESSPIN DFID and External TA as necessary
R2 | 0
R3 | 0
A1: Purpose
R1 | The purpose level statement requires reworking (with its indicators) as a part of a wider ESSPIN reappraisal process to determine what can realistically be achieved by 2014. | ESSPIN DFID
R2 | 0
R3 | 0
A1: Risk
R1 | A much more rigorous risk analysis is required as part of a proposed Programme re-appraisal. There are no risk ratings in the February 2011 Logframe. | ESSPIN with other SLPS
R2 | 0
R3 | 0
A1: Logframe
R1 | The Logframe should be reworked as part of a re-appraisal process in the next three months | ESSPIN DFID IMEP
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | The Logframe requires revision, as the indicators are not a clear reflection of Federal level action and the way in which activities for this Output have evolved. This Output also needs to be re-assessed in relation to planned levels of investment into Outputs 2-4 (at State level). | ESSPIN DFID and external TA as necessary
R1.2 | 0
R1.3 | 0
R2.1 | Assess the relative weight of short term technical TA in advancing sustainable reforms relative to a continuous process of political engagement involving SPARC and other SLPs | ESSPIN DFID
R2.2 | 0
R2.3 | 0
R3.1 | Output needs to be reconceived a) to reflect school improvement as the central driver for change for ESSPIN and b) to develop indicators that are more complete in their assessment of school improvement. | ESSPIN
R3.2 | 0
R3.3 | 0
R4.1 | Need for clearly thought-out strategy on access and equity including a reappraisal of the degree to which women and children plus e.g. those from minority ethnic or indigene groups and those who are illiterate are involved fundamentally in the school improvement | ESSPIN
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | An early re-assessment of the likely political support for ESSPIN assisted activities is required in the next three months | ESSPIN SPARC Other SLPs
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | Strategies for rolling out and replicating good practice requires urgent attention - technical and political | ESSPIN and SLPs
R2 | 0
R3 | 0
Project Management
R1 | As part of a re-appraisal process attention should be paid to the size, location and primary responsibilities of the Abuja based team and to newly financial reporting systems able to link expenditure to Output (and sub-output) and by State. | ESSPIN and its full Management Consortium and DFID
R2 | Need for re-defined working practices and reporting procedures between ESSPIN and DFID in Abuja without delay. | ESSPIN DFID
R3 | 0
C: Other Comments
R1 | A joint DFID ESSPIN programme re-appraisal within 3 months | ESSPIN DFID
R2 | 0
R3 | 0
C: Evidence
R1 | No one document fully captures the headline results and achievements of ESSPIN and there is no tracking data in place to monitor progress towards milestones and targets over time. Despite a volume of reports it is a struggle to get a clear picture of what change is happening and why/not. | ESSPIN
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | Issues of sustainability within ESSPIN States and beyond are strong considerations to be factored into recommended re-appraisal | ESSPIN DFID
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | The milestones and the targets for this goal should be revisited and recast based, a) on available data-based evidence and b) on a re-assessment of the likely achievement of the Programme's purpose | ESSPIN Management Team with Senior Education Adviser Abuja
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | Within three months ESSPIN (with SPARC) should provide an assessment of political buy in to school improvement reforms in new State governments | ESSPIN Management Team with SPARC
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | Recommendation 1 should be addressed in the next three months | ESSPIN Management Team with SPARC
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | Action needed as part of Logframe revision
AP1.2 | 0
AP1.3 | 0
AP2.1 | This recommendation should be addressed as part of the proposed re-appraisal process.
AP2.2 | 0
AP2.3 | 0
AP3.1 | As part of the re-appraisal process
AP3.2 | 0
AP3.3 | 0
AP4.1 | To be assessed as part of re-appraisal
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | This assessment should be a joint SLP process | ESSPIN Management Team
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | This issue will be central to the proposed reappraisal process over the next three months | ESSPIN Management Team
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | To be assessed within three months | ESSPIN Management Team and DFID Senior Education Adviser
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | Reporting to DFID on a set of high level indicators needs to be introduced without delay | ESSPIN Management Team
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3