Type of Review: Annual Review

Project Title: Enhancing Nigerian Advocacy for a Better Business Environment [ENABLE]

Date started:	1 Oct 2008
Date review undertaken: Aug 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
ENABLE is a 4.5 year, £11m DFID-funded business advocacy programme, which commenced on 1 April 2009 following a six month inception phase and is therefore due to end 31 March 2013.

What are the expected results?
The goal is “Policy and regulatory environment for doing business improved”, measured by four indicators: improvement in Nigeria’s ranking in the World Bank’s Doing Business league table; an improvement in business leaders’ perception of the ease of doing business; number of policy, legal and regulatory changes; and number of people (entrepreneurs and workers) benefiting from policy, legal and regulatory changes. The results of ENABLE’s work will be unlikely to make a discernible difference, at least in the short term, to the first two indicators, but the last two, adopted during the last log frame review, are central to DFID Nigeria’s Growth Programme and it is on these that ENABLE has focused its attention. / ENABLE’s purpose is “to raise the level and quality of private sector advocacy and the effectiveness of public private dialogue in lead states and at the federal government level”. This is measured by the number of additional public private dialogues each year and by business leaders' satisfaction with the level of public private dialogue. / ENABLE asserts that it is unique in that it is the first advocacy support programme to apply the principles of M4P and systems thinking to business environment reform. This requires more intensive effort in supporting a range of stakeholders so that it is not only business membership organisations that are supported but also ministries, departments & agencies, media houses and research institutions.

What is the context in which UK support is provided?
As with many developing countries, the business environment, especially for micro and small businesses makes doing business difficult. Business Membership Organisations (BMOs) that might be expected to advocate change in public policy are generally weak and policy making is, in any event, often opaque. This project aims to assist business associations and the business media access technical assistance to enhance their capacity to advocate effectively for change in public policy and to monitor Government’s progress. Enhancing the capacity of business associations to collaborate with government will lead to improvements in the enabling environment which will, in turn, lead to sustainable economic growth. Strengthening the capacity of the media to undertake effective research on key issues and reporting them in a user-friendly and timely manner will enhance the advocacy capacity of the private sector by providing appropriate information. Supporting research institutions will ensure the provision of relevant information to support private sector policy positions. Government is also encouraged to consult. This process will enable government to engage businesses at all levels in policy development and the implementation of its economic growth agenda.

## Section A: Detailed Output Scoring

Output 1: Business Membership Organizations (BMOs) demonstrate competence to engage in effective advocacy
Output 1 score and performance description: A+
Progress against expected results: Output 1 covers ENABLE’s work to develop the competence of BMOs so that they are able to engage in effective advocacy. We have based our score on review meetings with BMOs and ENABLE’s additional indicators as well as on the three indicators provided in the log frame: / Indicator 1 assesses the improvement in advocacy competence as measured by a diagnostic assessment tool, originally developed by David Irwin and Annabel Jackson, and modified by ENABLE and which is administered by ENABLE staff. ENABLE has set targets for improvement in the index achieved by each BMO, with a target of 5% increase in 2011, 10% increase in 2012 and 20% by the end of the programme. The achievement in 2011 was 3%. The 2012 assessments have not yet been completed, but the average increase of those that have been assessed is 24%. ENABLE asserts that BMOs are raising their competence and this would appear to be reflected in the increasing number of dialogues and to some extent in the number of policy changes. Many of the BMOs interviewed by the review team appear to be performing well. / Indicator 2 measures the number of BMOs achieving a sustained improvement in their advocacy competence score. The target for this is 10 by 2012 and 20 by 2013. ENABLE has achieved 5 in 2012. / Indicator 3 measures the percentage of BMO members reporting satisfaction with the advocacy performance of their BMO. A target has not yet been agreed and no assessment has been undertaken. Satisfaction surveys do not necessarily give an indication of whether competence is improving and are more likely to reflect how well the BMO communicates with its members. Asking public sector target audiences to comment might give a better reflection. Ultimately competence is reflected in the ability of a BMO actually to bring about change, so monitoring issues raised and successes would provide the best indicator though this is monitored at the outcome level and goal level. We recognise however that changing an indicator at this late stage would probably not be helpful. Mentors, if used more regularly with BMOs, could also provide a third party assessment of improvement in competence. / ENABLE monitors three other indicators, not included in the log frame: / The number of BMOs introducing new advocacy practices, which they put at 8. The impression gained from interviews with BMOs is that they are all adopting new practices and endeavouring to become better at existing practices, such as using evidence based policy positions, so this is probably an under-estimate. / Financial resources applied to advocacy in addition to the support provided by ENABLE which is estimated at £637,000. Some of this has been spent from the BMOs’ existing resources, but much has come from seeking additional resources from members and sponsors. / Human resources applied to advocacy which is estimated at 2,100 days. This is also probably an under-estimate: LCCI for example employed an advocacy officer in 2009 with ENABLE’s support for the first six months and she is still there. More time, provided voluntarily, is being devoted by board members of BMOs, so this is largely an increase in effort. / ENABLE works with BMOs covering a wide range of experience and competence. In year four, ENABLE has actively reduced the number of partners to work specifically with those appearing to sustain new working practices. Working with more BMOs could potentially lead to more policy change, but this would require a change in approach, so that the support is less intense. / Recommendations: / Undertake a member satisfaction survey with a small number of BMO partners now and next year; / Make more use of mentoring in supporting BMOs. / Impact Weighting (%): 28 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Media proactively investigates and airs public policy and regulatory issues affecting private sector
Output 2 score and performance description: A++
Progress against expected results: Output 2 measures ENABLE’s work to encourage the media to devote more attention to the importance of the private sector to the economy and in particular to the importance of improving the enabling environment to encourage private sector investment. Compared to other advocacy funds, ENABLE has made considerable efforts in forging relationships with the media and appears to be having some considerable success. It has three indicators: / Indicator 1 measures improvement in a media quality index which covers content & analysis, accessibility and interactivity. The target is for 10% in 2012 and 20% in 2013. ENABLE has achieved 32% in 2012, so has well achieved the target. However, the index is calculated using a score card which is rather subjective (and thus open to bias) and which has questions which may provoke a good discussion with the organisation but which are not necessarily an indicator of quality. / Indicator 2 measures the number of business media products achieving a sustained improvement in their media quality score. A product is essentially a radio programme or a newspaper column or something similar rather than a one off broadcast or article. ENABLE has a target of 10 products for 2012 and 20 for 2013. It has achieved 17 in 2012, though is currently working with only five partners. / Indicator 3 measures audience satisfaction of ENABLE assisted business media projects. This has a target of 50% in 2012 and 60% in 2013. No scoring is yet available. As noted above, satisfaction surveys do not really provide any indication of whether the output is being achieved. It would be better to measure the media’s own satisfaction, perhaps evidenced by time of day for radio broadcasts, length of programme, positioning of articles for newspapers, length of articles etc. and stakeholders’ satisfaction, perhaps demonstrated through ability to attract sponsorship and advertising. The radio stations report that they are achieving and sustaining much higher audience numbers. / ENABLE monitors two other indicators, not included in the log frame: / Financial resources applied to reporting on business environment issues in addition to the support provided by ENABLE which is estimated at £600,000. / Human resources applied to reporting on enabling environment issues, which is estimated at 2,800 days. / This does not necessarily represent additional resources spent by the media organisations, but it does demonstrate a switch of resources to cover business enabling environment issues. The radio stations have been successful at securing significant levels of sponsorship, which will ensure some sustainability. / ENABLE is now measuring audience figures, though prior to 2011, there were no independent figures available so should be able to comment on growth in audiences next year. / Recommendations: / The score card, if it is retained, should be reviewed to provide a more objective assessment of media quality. / ENABLE is, to some extent, monitoring government action arising from media coverage – anecdotal evidence suggests that it is high, albeit for minor issues, though that at least demonstrates that key people in government are listening but it could so more comprehensively, perhaps developing an indicator that measures government action. / The media will always want to pursue their own agenda, but there is a desire to assist BMOs to use the media to assist with specific advocacy campaigns. ENABLE does support individual linkages between BMOs and the media (for example, linking KASTU and Freedom Radio on the issue of the Kano market relocation), but there is a need to go further, supporting BMOs to develop public relations strategies. / Impact Weighting (%): 24 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Ministries, Departments & Agencies (MDAs) demonstrate willingness and capacity to engage with private sector
Output 3 score and performance description: A
Progress against expected results: This output attempts to measure improvements in the engagement of the private sector by the public sector. Whilst in principle this is no different from looking at a BMO, in practice it is very different, since a Ministry is so much larger, and interacts with the private sector in many different ways. So one division, such as the trade division in Federal Ministry of Trade & Investment (FMTI) may make a real effort, but other divisions may not do the same. The large number of Ministries and Agencies that impact on the private sector and the large number of people who work in them make this a particularly challenging output to deliver. Interviews by the review team of MDAs suggest that the public sector is becoming more open and more likely to engage in dialogue. It has three indicators: / Indicator 1 assesses the improvement of supported MDAs as measured by a dialogue capacity index. There is a target of 10% in 2012 and 20% in 2013. Whilst a baseline has been undertaken, there are no repeat diagnostic assessments and so no scores available. / Indicator 2 measures the number of MDAs achieving a sustained improvement in their dialogue capacity score. Targets are relatively modest with 6 for 2012 and 10 for 2013. No scores are available for 2012. / Indicator 3 measures the percentage of BMOs reporting an improvement in the dialogue capacity and openness of Ministries Department & Agencies (MDAs) compared to 12 months earlier. Targets have not been agreed for this indicator, so it is not possible to assess ENABLE’s performance. They report however that 10% of supported BMOs reported positively in 2011 and 31% reported positively in 2012. This indicator is rather subjective. It would be better to look at the record of MDAs in inviting BMOs to consult, comment and engage in dialogue. This is partly picked up at the outcome level, by counting dialogues, though the indicator does not differentiate between those arising from BMO efforts and those arising from MDA initiatives. / ENABLE monitors three other indicators, not included in the log frame: / The number of MDAs introducing new consultation practices, which they put at six. MDAs, at least nominally, have been consulting for years, but the impression gained from the interviews is that many are now more willing genuinely to listen and to take on board suggestions in the expectation that regulations will then be accepted, as evidenced, for example, by the Federal Ministry of Health consultation to revive the stalled process on introducing a food safety legislation. / Financial resources applied to consultation in addition to the support provided by ENABLE which is estimated at £937,000 / Human resources applied to consultation which is estimated at 3,000 days. / This does not represent additional expenditure by the MDAs, but it does demonstrate considerable commitment in that they are becoming more willing to consult – and recognition that effective consultation requires effort. / Recommendations: / For selected MDAs, count the occasions that the private sector is invited to provide comment or feedback on proposals to change public policy and the number of times that the private sector is invited to engage in dialogue. / Impact Weighting (%): 28 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Effective and affordable support services (especially research provision) are available to BMOs and MDAs on a sustainable basis
Output 4 score and performance description: A
Progress against expected results: Output 4 is concerned with encouraging more research to take place, on the basis that better evidence leads to more compelling policy positions, and positioning research institutions to undertake such research for BMOs. It also covers other support services such as media relations and BMO member surveys. It has three indicators: / Indicator 1 measures the number of BMOs and MDAs securing research from ENABLE supported research institutions. The target is a modest 6 by 2012 and 10 by 2013. ENABLE has achieved 10 by 2012 so is well ahead of target. / Indicator 2 assesses the percentage of BMOs who are satisfied with the availability and quality of research. This is another satisfaction survey, which does not really assist in assessing the quality of research, since those doing the assessment do not have a suitable frame of reference. There is no target yet agreed for this indicator. / Indicator 3 measures the number of BMOs and MDAs that obtain support services from ENABLE supported providers. The target is 6 by 2012 and 10 by 2013. ENABLE has achieved 14 so this is ahead of target. ENABLE is keen to develop a ‘market place’ for research in which more BMOs buy research and more research institutes are able to sell them research. Originally, ENABLE heavily subsidised research. They argue that as more BMOs have come to appreciate the value of research and as Research Institutions have become better at delivering affordable and relevant research, it has been able to reduce the subsidy and believes the number of research commissions is growing. They agree, however, that most BMOs are unlikely in the short term to have the resources to buy research unless there is a significant external subsidy. / ENABLE monitors three other indicators, not included in the log frame: / The value of transactions in which BMOs (without ENABLE’s support) buy research which is estimated at £51,000 / Financial resources applied to enabling environment research in addition to the support provided by ENABLE which is estimated at £137,000 / Human resources applied to enabling environment research which is estimated at 1,100 days. / ENABLE has been providing capacity building support to research institutions as well as commissioning research on behalf of BMOs. The underlying objective is to develop a market in which BMOs recognise the need for research and will continue to buy in research after ENABLE support ends. There is a weakness in this approach, however, in that the BMOs are, generally, weak and most, at least in the short term, will be unlikely to have the necessary resources to buy in the research that they need. / We also have a major criticism: we reviewed all of the research reports and, in general, they were poor, inter alia, with research objectives formulated too widely, with small sample populations, with limited use of existing research results, with data not used in drawing conclusions and conclusions which did not follow from the evidence. This is an area that needs to be addressed. If BMOs are unable to assess the quality of research, then perhaps it could be assessed through a peer review system or by asking public sector target audiences whether it makes a persuasive case or by asking an independent evaluator to assess the quality of research, using objective criteria, and to look at the way that research is actually used by BMOs and MDAs. / Recommendations: / We recommend that ENABLE makes an effort to improve the quality of research reports. This could include providing much more feedback on research reports, preparing a briefing note for BMOs highlighting some of the potential problems likely to arise with commissioned research and giving BMOs a tool to assess research prepared for them. This would then help to address problems inherent in using BMO satisfaction of research as an indicator. / Impact Weighting (%): 20 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

## If the project involves more than 4 Outputs please copy the box above and paste below.

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the log frame been updated since last review? N / 1.2 Overall Output Score and Description: A+ / 1.3 Direct feedback from beneficiaries / The review team met with nine BMOs, three research institutes, five Ministries (three Federal and two State) and four media organisations. We also met with other stakeholders. Everyone we met was extremely positive about ENABLE with many saying that it had changed the way that they work. ENABLE was recognised as a facilitator – indeed, the biggest complaint was that it would not provide direct funding – but once organisations understood the way in which support could be provided, most responded positively. Government in particular seemed to welcome the support that ENABLE is able to give the private sector to help them become better advocates. BMOs reported that they had become more competent. Whilst the numbers are still small, several BMOs did report that they have been able to continue with activities originally started with ENABLE support.
1.4 Summary of overall progress / The log frame provides 18 indicators. 2 still do not have targets (or baselines) and 5 do not have 2012 data. ENABLE has achieved or exceeded the 2012 milestone for 7 out of the remaining 11 indicators. It has achieved 2 of the 4 goal level indicators and 1 of the 2 purpose level indicators. / At the purpose level, ENABLE measures the number of dialogues held per annum and business leaders’ satisfaction with the level of public private dialogue. The level of satisfaction at 1.98 is slightly below the 2012 target of 2.1. However, this is another satisfaction rating and does not really reflect whether the level and quality of private sector advocacy and the effectiveness of public private dialogue has been raised. The number of dialogues is a good measure. The target for 2012 is 10 and ENABLE supported organisations have apparently engaged in 39. This is very positive. However, it almost certainly under-estimates the level of activity occurring as a result of ENABLE’s support since they only capture dialogues that are tightly defined, yet there is evidence that there is a lot more activity taking place, with BMOs being invited to participate in more dialogues and to comment on more public policy changes. / At the goal level, indicators cover World Bank Doing Business ranking, business leaders’ perception of difficulty of doing business, number of policy changes and number of people benefiting from policy changes. The targets for the first two have not been achieved, though these are especially high level and the impact of ENABLE’s work is unlikely to be captured in those surveys. The results of the other two indicators are much more positive. The target for policy changes is 4 by 2012 and 8 by 2013. It would appear that 8 policy changes have been achieved already with a further 4 still under discussion and 4 in the pipeline. The target is relatively modest but reflects the desire to change the way that BMOs and others work so is probably not unreasonable. The programme target has already been exceeded so is particularly encouraging. The target for people benefiting is set at 500,000 by 2012 and 1m by 2013. It seems that some 719,000 have benefited to date and there is an expectation that this will rise to 5.2m once agreed policy changes are implemented. Whilst focusing on people benefiting can, to some extent demonstrate value for money, there is a danger that only changes that directly and immediately provide economic benefits are supported, yet other changes could ultimately have a more far-reaching effect. For example, encouraging MDAs to undertake regulatory impact assessments would not have an immediate impact but would ultimately lead to better regulation. / In summary, however, ENABLE has achieved the key targets set out in the log frame.
1.5 Key challenges / There are challenges: / In working simultaneously with four target audiences, the potential synergies are not always exploited as well as they might be though, as ENABLE explains, there was no need for partners across all components to build competence before synergies can be exploited. / In managing an organisation with a matrix management structure in which there are component managers for each of the four components together with state co-ordinators whose roles are not clearly defined / There is a challenge, too, in that some of the log frame indicators do not necessarily demonstrate whether the output is being delivered and the annual review does not take into account impact and outcome level indicators. However, ENABLE has already delivered on one of the two key impact level indicators (policy changes) and is more than on track to meet the second (people and businesses benefiting).
1.6 Annual Outcome Assessment / As noted above, ENABLE has exceeded its programme target (8 by the end of the programme; 4 by 2012) for policy changes and is well ahead of its 2012 target for individual beneficiaries. / Partner Policy change / FMoH Draft food safety policy: amended / FMTI Draft investment & trade policy: amended / EPPAN Cashless Nigeria policy: thresholds and pilot / FEPSAN FGN persuaded to exit fertiliser subsidy, procurement & distribution / FCTA Proposal for transport policy: amended / KASTU Relocation of market: agreed / LCCI Lagos Local Levies Act: enacted & publicised / FRCN Kaduna Abattoir conditions improved / ENABLE, through detailed calculations, demonstrates that it has delivered benefits to more than 719,000 people (of whom 46% are women). More than 500,000 of this are accounted for by the businesses seeing reduced taxation as a result of the local levies legislation in Lagos. Given the population of Lagos and the large number of micro and small businesses, we think this is an under-estimate. The balance is the estimate of micro and small businesses who will benefit from the cashless Nigeria policy which is difficult to estimate since it is only businesses transacting with the banks above a threshold that would have been affected. The way in which the estimate has been derived seems logical. / ENABLE estimates that the changes in the fertiliser policy could make a difference to more than 4.3m farmers, based on figures from the Federal Fertiliser Department. Estimating benefits is also difficult as the effect of ending the subsidy will be that the price of fertiliser ultimately rises, though the expectation in the short term is that more farmers will benefit and, for a period, they will also benefit through the subsidy delivered via vouchers. Ultimately, ending fertiliser subsidy should mean that it becomes more widely available, with significant impact on yields and thus on incomes. This could potentially be an interesting project to evaluate on a longitudinal basis. / It is estimated by Royal Life Savings Society and the Food Vendors’ Association that the food safety policy will impact on 4.5m vendors. On the assumption that food businesses do not already cut corners on food safety and hygiene, the cost implications should be minimal for responsible businesses – and no-one wants to see unsafe food in the market – with benefits for businesses able to demonstrate that they meet the standards, especially important for exporters, as well as health benefits for everyone in Nigeria. / Estimating the financial benefits is challenging. We have reviewed the calculations made by ENABLE, in which they estimate that benefits amount to £12 for every £1 of spend and believe that they are credible. However, it would be sensible to review all these on a regular basis. The cashless Nigeria policy is likely to be rolled out nationally if the pilot in Lagos is successful. If the thresholds utilised in the pilot are used elsewhere, then many more businesses will benefit; on the other hand, it is likely that the threshold will be reduced as appropriate technology is rolled out, so that businesses are increasingly caught by the legislation. However, businesses may then benefit in different ways.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: N / ENABLE is a little underspent and has proposed to DFID a six month no cost extension. This would make sense since DFID is now considering supporting a second phase of the work commenced by ENABLE but would be unable to complete the design and contractual arrangements in time for an April 2013 start but might be able to do so in time for an October 2013 start. A no cost extension would avoid having an interregnum during which time momentum would be lost. / 2.2 Key cost drivers / There are three costs: the cost of providing support on behalf of partners, the cost of staff and the overheads. These will not change. Compared to other funds, ENABLE is well staffed, though it has to contend with a large country and is working in selected states, so the level of staff is probably fair. However, the staff complement could probably manage a bigger ‘fund’ were it thought that there was sufficient demand. / 2.3 Is the project on-track against original timescale: N / The original expectation was for ENABLE to last for 3 years. The first annual review recommended consideration of an extension, reaffirmed in the second review. The programme will now last for a total of 4.5 years in addition to a six month inception period. It is on track against the revised timescale.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The theory of change – that promoting the importance of and supporting public private dialogue and private sector advocacy will lead to changes impacting positively on the enabling environment and subsequently to more private sector investment and thus poverty alleviation – is still valid and ENABLE’s work is beginning to demonstrate this in practice. The key assumption in the log frame – that the public sector will listen and act – is not only proving true (at least where the private sector is able to make a compelling case), but the public sector appears to becoming ever keener to consult and to involve the private sector in dialogue. / The main challenge for ENABLE is posed by the security issues, especially in the north, not only because it makes it harder for ENABLE itself to engage, but also because it makes an enormous difference to the enabling environment and the ease of ‘doing business’. / 3.2 Where an evaluation is planned what progress has been made? / None planned

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / Key risks recognised within the project design and which may influence the impact: / Willingness of the public sector to listen and to act – though the impression at the moment is that the government is keen to improve the investment climate, with ambitious targets to improve Nigeria’s Doing Business and World Economic Forum (WEF) Competitiveness rankings, and a desire to consult with and to involve the private sector. / Political and economic environment – political and economic stability has been maintained, with good economic growth recently. / Vested interests amongst policy makers and regulators – it is difficult to assess the impact of vested interests, but there is no doubt that it is a factor in delaying or preventing policy change that could have a positive impact on the private sector. ENABLE is unable to do anything to change this, but continuing pressure from the World Bank, WEF and others could ultimately lead to change (though the recent resignation of the Minister for Power is not encouraging). / There is an additional, exogenous, risk: / The security position might deteriorate further, making it harder for ENABLE to operate and making it less likely that the private sector will invest, creating jobs and tax revenue, irrespective of changes to the regulatory environment.
Risk of funds not being used as intended / Where ENABLE agrees to support a project, it is ENABLE that enters into relevant contracts and ENABLE that pays the bills. Thus there is no danger of fraud or other problems within partners causing funds not to be used as intended. ENABLE has tight financial control within the organisation. / 4.4 Climate and Environment Risk / The programme does not hold any identified climate or environment risks per se. There is always the possibility that a project by a BMO or MDA might ultimately lead to climate or environment risks but none have been identified. Indeed, given the increased awareness of climate change and environment, it is more likely that BMOs will seek support to change policy for the better.

5. Value for Money
5.1 Performance on VfM measures / The original project memorandum and the inception period redesign had no VfM measures, but ENABLE has worked hard particularly over the last year or so to develop appropriate VfM measures and to measure its performance against those measures. Overall, we believe that ENABLE is making a good effort to assess effectiveness and impact and intends to commission regulatory impact assessments and expects to have much better data on which to base its cost benefit calculations. / At the economy level, ENABLE adheres to DFID practice for procurement. Where possible, it uses Nigerian consultants to keep costs down (and has achieved a rate of 75% use of local consultants) and shares advisers and co-ordinators with other programmes. We recognise that this might reduce costs but wonder whether it may also reduce effectiveness. ENABLE has more staff than all programmes except BUSAC in Ghana, though BUSAC has many more projects all of which are much smaller. It is inappropriate to compare the costs of staff and consultants given the difference in cost of living. It is difficult to compare performance since ENABLE staff undertakes some activities, such as mentoring, that are sub-contracted on other programmes. / ENABLE has been successful in levering additional resources, though this is in line with its approach of facilitation. It has succeeded particularly in assisting the media to identify programme sponsors but has also done well in helping FMTI to find money for the National Competitiveness Council. ENABLE has achieved excellent leverage – averaging 67% across the four components – ensuring that DFID’s spend goes further. If the additional cost is taken into account, the benefit reduces to £7.44 for each £1 of spend, which still represents a good return. / The EFInA evaluation notes the difficulty of isolating a particular category of expense in order to calculate an efficiency indicator since the activities are intended to be mutually reinforcing and, as a result, it considers the totality of impact against the totality of expenditure. ENABLE appears to be in a similar position. ENABLE has supported BMOs to bring about 8 policy changes with a further 8 in the pipeline and at least 39 additional dialogues. These would not have happened or would have taken much longer without ENABLE support. It has also helped to transform the approach taken by five media houses, including assisting in raising sponsorship. This would not have happened without ENABLE’s support. / About 35% of total budget goes into overheads – staff time not associated directly with providing support, office costs etc. ENABLE notes that this is in line with other M4P programmes, but a better bench mark is other advocacy funds, whose admin costs are generally in the range of 28-35%. / ENABLE reports on effectiveness by treating all expenditure as the cost of achieving all the policy changes, irrespective of whether they come from BMOs, or MDAs, or media or, most likely, a combination and by counting the total number of beneficiaries. / Overall, ENABLE has spent some £7.5m and to date has impacted on 719,000 beneficiaries giving a cost per beneficiary of £10.91 (Figures are rounded: the two key ratios use ENABLE’s calculations; we calculate the cost/ beneficiary to be slightly less and the benefit cost ratio to be slightly better. If the additional policy changes that have been agreed are implemented, the number of beneficiaries will rise at least to 5.2m, reducing the cost per beneficiary to £1.44. The average benefit is £129 so, for beneficiaries to date, the benefit equates to £11.97 for every £1 spent by ENABLE. Other funds, on the whole, do not have comprehensive data on numbers of beneficiaries and level of benefit but they have now undertaken, as far as possible, to gather and report those figures.[1] However, a benefit cost ratio of this magnitude demonstrates that ENABLE’s total activities represent good value for money. / VfM comparisons / Benefit Cost Benefit/ cost ratio Adjusted cost Benefit/ cost ratio (adjusted) / Cashless Nigeria £93m £87,000 (total, ex research) 1069 £117,000 795 / FPEAK (Kenya) KES5.84bn KES8m 730 KES16m 365 / MOA (Kenya) KES500m KES1m 500 KES2m 225 / ZACPO (Zanzibar) £8m £50,000 160 £100,000 80 / Sources: BAF, BEST-AC / ENABLE explains that it provides support over a period to change the way that, say a BMO operates rather than funding projects. This makes it difficult to calculate accurately value for money ratios at the project level apart from benefit/beneficiary. We would encourage ENABLE to estimate project equivalent costs which would then allow benchmarking across funds at the project level. An estimate for the one project with detailed data is provided in the table together with comparisons from Kenya and Tanzania. These selected cases suggest that ENABLE is offering good value for money at the project level. / As observed in the business environment reform practice note, “success in a systems framework is measured by how much the elements of systems have improved and how much more capable stakeholders are at sustaining existing change and articulating, demanding, executing or managing further change”. So value for money would be determined by taking a rather longer view and taking into account how much more advocacy work is being undertaken, and how much more success is being achieved, by the BMOs that are supported. So, the real value is yet to be realised on the basis that BMOs will continue to influence public policy successfully and that MDAs will continue to value a private sector input to policy debate. / 5.2 Commercial Improvement and Value for Money / There is always scope to review whether the same outcome could have been achieved in a different way. It is possible, for example, to compare ENABLE’s expenditure with that incurred by other advocacy funds. ENABLE is aiming to take an approach that is wholly consistent with the principles of M4P. Whilst there is no evidence that other funds are compromising those principles, the approach does require an intensive level of support. Given that level of support, it is unlikely that support could be delivered more cheaply, though support could be delivered in a different way (probably with a different level of achievement). If ENABLE delivers its stated aim of ensuring sustainability of advocacy effort by the BMOs that it has supported, then the cost will have been worthwhile. / 5.3 Role of project partners / There are no implementing partners as such, though ENABLE does refer to the organisations that it supports as partners and does encourage them to behave as partners rather than clients. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take?
[1] At the first African advocacy fund managers conference, Dar es Salaam, September 2012

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Our assessment is that ENABLE is fulfilling a valuable role in encouraging and supporting greater levels of public private dialogue and private sector advocacy. It has adopted an approach that is very similar, though not identical, to other advocacy funds in sub-Saharan Africa. BMOs supported by ENABLE are beginning to have some success and the government appears to be engaging with the private sector more than ever before. ENABLE defines success, at least in relation to dialogue, quite tightly and it is likely that there is much more activity than revealed by the figures. / We have some specific recommendations which may serve to improve the programme for its last few months: / Recommendation Priority / VFM Make more use of ex ante estimates (necessary for comprehensive research reports and policy position papers); set out cost benefit analyses in a standard way, make them public and encourage feedback to refine the analysis and justify the conclusion; commission a small number of ex post evaluations to assess impact and vfm. A / Indicators Drop from the log frame indicators that seek to measure satisfaction (though there may be other reasons to continue to assess satisfaction) A / VFM Explore the scope for benchmarking value for money with other advocacy funds B / Output 1 & 2 Support BMOs to develop and implement public relations strategies A / Output 1 Make greater use of mentoring to support BMOs, not just to assess research undertaken on their behalf, but to support the translation of research into policy positions and to speed progress where possible. A / Output 1 Undertake a survey of members of a small number of BMO partners now and annually to assess their perception of the credibility and competence of their BMO C / Output 2 Explore scope to develop indicator which captures government action resulting from media coverage B / Output 2 Encourage the media to be more proactive in seeking issues to air and to talk regularly to BMOs to keep abreast of the issues B / Output 2 Review the media quality score card to provide a more objective assessment B / Output 3 Reach out to Government Agencies as well as Ministries A / Output 3 Count the number of occasions the private sector is invited proactively to comment or feedback on proposals for public policy (rather than waiting until private sector reacts) C / Output 4 Provide more feedback on research reports during drafting and support BMOs to assess quality of research undertaken on their behalf A / Given that momentum is now beginning to build, recognising that changing public policy takes time and that BMOs, in general, need more support to strengthen their engagement in public policy dialogue, we recommend that DFID supports a successor programme. / To allow time to undertake the design and complete the contractual requirements, and given that ENABLE is underspent, we recommend that DFID approves the request for a no cost extension, though we suggest that the targets for policy changes and dialogues are raised.

8. Review Process
The review was undertaken with a field mission by David Irwin and Dahiru Sani between 13 and 22 August. They were accompanied to meetings by Ogechukwu Omeribe and Sila Sahin both from DFID. They were provided with numerous background documents, including previous narrative reviews, progress reports, annual business plan, revised log frame and targets and ENABLE’s recent self-assessment. Between them they met with a large number of partners and stakeholders. They presented to DFID and took on board feedback and questions.