Mid-term Review of the DFID Support to the National Malaria Programme (SuNMaP) Nigeria

Report of the independent consultants:
John James
Bruce Mackay
Ivy Papps

Final Report: 20 September 2011

Contents

# Acknowledgements

The three independent consultants who wrote this report want to thank all those whom we met. All were generous with their time, patience, and insights. The list is long: the review team members who accompanied us on this mission; staff in the federal and state ministries, and in particular those working on malaria control; DFID Nigeria staff, especially Ebere Anyachukwu, David Ukagwu, Edward Idenu and Susan Elden; all those in the SuNMaP Abuja and state offices; SuNMaP partners Malaria Consortium, World Bank, Crown Agents, Clinton Foundation and GRID.

We thank also the patients and staff at the health facilities, the patent medicine vendors, and the community workers that we met during our field trips; here we were able to experience first hand the results of malaria control efforts

Finally, our especial thanks to SuNMaP and DFID for organising an excellent and enjoyable mission.

# Abbreviations and acronyms

ACT	Artemisinin Combination Therapy
AMFm	Affordable Medicines Facility – Malaria
ANC	Antenatal care
BCC	Behaviour change communication
CHAN	Christian Health Association of Nigeria
CSP	Commercial sector partners
DALY	Disability adjusted life years
DFID	Department for International Development
ENR	Enhanced Nigerian response to HIV/AIDS
EPI	Expanded programme of immunisation
ESSPIN	Education Sector Support in Nigeria
EU	European Union
FMoH	Federal ministry of health
FOMWAN	Federation of Muslim Women Associations of Nigeria
GFATM	Global Fund to Fight AIDS, Tuberculosis and Malaria
HERFON	Health Reform Foundation of Nigeria
HMIS	Health management information system
HPI	Health Partners International
IEC	Information, education and communication
IPT	Intermittent preventive treatment
IRS	Indoor residual spraying
ITNs	Insecticide treated nets
LGA	Local government area
LLIN	Long lasting insecticidal net
M4P	Making markets work for the poor
M&E	Monitoring and evaluation
MDG	Millennium Development Goals
MEDA	Mennonite Economic Development Association
MIS	Malaria indicator survey
MoA	Memorandum of agreement
MNCH	Maternal and child health
MTR	Mid-term review
NMCP	National Malaria Control Programme
OPR	Output to purpose review
OVI	Objectively verifiable indicator
PATHS	Partnership for Transforming Health Systems
PATHS2	Partnership for Transforming Health Systems - Phase 2
PIPs	Project Implementing partners
PMG-MAN	Pharmaceutical Manufacturers Group of the Manufacturers Association of Nigeria
PMV	Patent medicine vendor
PRRINN	Partnership for Reviving Routine Immunisation in Northern Nigeria
PSD	Private sector development
PSM	Procurement and supplies management
RBM	Roll Back Malaria
RDT	Rapid diagnostic test
SFH	Society for Family Health
SMoH	State Ministry of Health
SMCP	State Malaria Control Programme
SMO	Social marketing organisation
SP	Sulphadoxine pyrimethamine
SPARC	State partnerships for accountability, responsiveness and capability
SuNMaP	Support to National Malaria Programme
TA	Technical assistance
U5	(child) under-five
UNICEF	United Nations Children’s Fund
USAID	US Agency for International Development
VfM	Value for money
WHO	World Health Organization

# Executive summary and priority recommendations
This is the independent consultants’ report of the mid-term (year 3) review of the UK Department for International Development (DFID) support to the Nigeria national malaria programme (SuNMaP). The in-country review took place 4 – 15 July. Overall, the consultants found that SuNMaP, together with its 11 programme implementing partners (PIPs) were making good progress towards achieving the purpose and outputs of the support.

SuNMaP’s achievements include:
- Establishing a harmonisation mechanism whereby ministry, institutions, organisations, partners and people develop a common approach to strategic areas.
- Capacity building resulting in the development of effective national and state malaria control plans.
- Development of management, planning and malaria case management training modules that have shown impact (and that have been used across the health sector).
- A key role in the coordination of the successful distribution of 60 million free LLIN nationally

Key findings:
Progress in respect of agreed programme outputs and purpose
Overall, SuNMaP has made good progress against the programme outputs; not all milestones for 2011 have been achieved; in the majority of cases, the reasons are due to external circumstances over which SuNMaP has no control.
Logframe
The logframe remains unchanged from May 2010, despite the recommendations from the June 2010 OPR. The changes were recommended due to the “changes in the wider context, overlap of some indicators, and some outputs do not have an appropriate set of indicators”. The review team would endorse the need for these changes in the logframe. The indicators require further revision as they do not reflect properly the purpose or outputs; the purpose is strengthening delivery – i.e., system strengthening – yet the indicators are outcomes. Several indicators are no longer relevant to the SuNMaP programme, and should be removed.
Appropriateness of capacity building, strategic direction and coordination
SuNMaP’s capacity building support has been successful at all levels – from the NMCP, through state ministries, down to primary health care facilities and the community. The mechanisms have included direct technical support, training (training of trainers using modern teaching methods, management, planning and malaria case management module), and mentoring (especially at the state level in the development and monitoring of annual malaria operational plans). These approaches will contribute to the sustainability of malaria control in the longer term.

The strategic direction of the programme is sound, although there is a need to better understand the market for nets

Approach to and management of the commercial sector
This is an area for concern. Following recommendations from previous reviews, SuNMaP did made staff changes but were unable to appoint an appropriately qualified manager to drive this component. These reviews had also urged SuNMaP to gain a deeper understanding of the market for nets; again, no proper formative market research has been carried out. (The review team understand that research to inform and guide the generic marketing programme has subsequently been planned, and will start shortly). SuNMaP has now adopted a strategy based on ‘Making markets work for the poor’ (M4P) but the review team felt that DFID should consider carefully the best way of taking forward the commercial sector component in this programme.
Management arrangements and internal coordination
Apart from the issues over the management of the commercial sector, SuNMaP management and internal coordination is excellent. Their technical expertise and support is both respected and appreciated, and the Abuja office functions well, with well-motivated happy staff. The state offices appear to be operating well, although all report heavy workloads. Although the Abuja office does communicate regularly with the state offices, increasing the frequency of visits to state offices is recommended. Staffing levels could be reviewed –the appointment of additional technical assistance in the Abuja office, and additional operational staff in state offices could be of benefit.
Value for money
SuNMaP takes VfM issues seriously, in that a number of measures are taken to reduce operational costs. Financial information is recorded in such a way that the construction of unit costs of inputs and activities is feasible. DFID’s recent outline of its approach to VfM implies that output indicators should all be factors that are controlled directly by the programme. However as several output indicators require inputs by partners attribution continues to be an issue. In order to fully assess VfM, it will be necessary to have a breakdown of total expenditure for malaria control by all partners, as well as an agreed methodology for calculating DALYs in order to convert to this common metric. DFID should agree with SuNMaP appropriate unit costs to be calculated and monitored over time, and disseminate the information to partners (thereby encouraging better performance). Properly calculated, it should be possible to convert all progress to DALYs

Priority recommendations
Logframe outputs
The changes to the logframe indicators and milestones recommended by the 2010 OPR should be incorporated in a revised logframe
Commercial sector
DFID Health & PSD should agree on the objectives of M4P interventions in the commercial LLIN market, and how they can best be implemented.
Management and coordination -
- The appointment of an additional technical staff member to the SuNMaP Abuja office
- Review SuNMaP state staffing levels: consider need for additional operational staff members
- Introduction of continuous professional development for SuNMaP staff

4. Value for Money
- Identify and monitor key unit costs to provide management information
- Improve performance through dissemination of unit costs to partners
- DFID should commission research to estimate DALYs averted for IPT (first assessing whether PSI DALY methodology is suitable for VfM analysis)
- SuNMaP should report progress against purpose in DALYs averted
- Obtain overall expenditure on malaria control in order to determine attribution and overall cost effectiveness of DFID support
5.	Extent of project engagement in new DFID states
- DFID should consider whether SuNMaP should engage in the four states at all if the programme is not extended to 2015
- SuNMaP’s role should be integrated with the PATHS 2 and PRRIN-MNCH programmes (recognising considerable overlap between current roles and strengths)
- DFID should consider whether extending to DFID-supported states represents the best value for money

# Background
## Malaria in Nigeria
The human cost of malaria in Nigeria is extremely high. With a population estimated to be around 160 million:
- Nigeria accounts for over a quarter of all cases of malaria in Africa
- Over 300,000 Nigerians – the majority under five years – die of malaria every year
- Malaria accounts for 30% of childhood deaths
- Malaria accounts for 60% of outpatient visits, and 30% of hospital admissions

In economic terms, it is estimated that malaria accounts for over US$ one billion in lost productivity and the costs of treating infections
## Partnerships against malaria in Nigeria
The NMCP of the Federal and State Ministries of Health is actively leading the fight against malaria and working towards its elimination and eradication, a malaria free Nigeria. It works closely with partners such as Roll Back Malaria (RBM), the Global Fund To Fight AIDS, Tuberculosis and Malaria (GFATM), the President’s Initiative against Malaria, World Bank, DFID and a number of for profit and not for profit organisations.

At a global level DFID provides support for Roll Back Malaria, the World Bank and the GFATM. In Nigeria in recognition of the magnitude of the malaria problem and to help Africa and Nigeria achieve the Millennium Development Goals, DFID is a contributor to the NMCP through SuNMaP.
## The SuNMaP programme 2008 - 2013
The £50 million, five-year programme, supports the NMCP through six outputs: capacity development; harmonisation; prevention; treatment; demand creation; and operational research. SuNMaP works at the federal level, and in six states (Anambra, Kano, Katsina, Lagos, Ogun and Niger), potentially providing coverage of around one third of the country’s population. SuNMaP’s support includes long- and short-term technical assistance, operational and financial support for scale-up of key interventions, malaria commodities, and support to the commercial sector. DFID intends to expand the programme to involve four additional DFID-supported states late 2011.
## The mid-term review process
The mid-term review was conducted in-country 4 – 15 July, 2011. The review team comprised John James, Bruce Mackay and Ivy Papps, independent consultants, DFID Nigeria staff, and representatives from the Federal Ministry of Health (NMCP) and State Ministries of health. The independent consultants wrote this report.

The review team were tasked with reviewing progress made so far and to make recommendations to enhance programme effectiveness (full terms of reference, annex 1). The review was requested to focus on the following:
- Progress of SuNMaP in respect of agreed programme outputs and purpose
- Appropriateness of SuNMaP’s monitoring and evaluation (M&E) framework and logframe
- Appropriateness of SuNMaP approach, strategic direction and risk mitigation strategies
- Review progress with SuNMaP’s work in the commercial sector
- Review effectiveness of coordination between SuNMaP, DFID and other development partners
- Review effectiveness of management arrangements and internal coordination
- Review economic, financial and budget processes, and in particular, value for money
- To review extent of project engagement in new DFID-supported states

The review comprised:
- Desk review of relevant documents (prior to the in-country visit): annex 4
- Meetings with the SuNMaP team and partners, FMoH, NMCP, DFID, representatives from development partners – WB, USAID, and key stakeholders: annex 3
- Field visits to 5 (of the six) SuNMaP-supported states accompanied by SuNMaP, NMCP and DFID representatives : annexes 2,3
  - SuNMaP state offices
  - SMoH, SMCP, stakeholders, and partners
  - Public and private health facilities (meet staff and patients)
  - Commercial sector providers
- Data analysis for value for money
- Presentation of draft findings of the review to DFID and SuNMaP at the end of the mission.

# Findings on progress against the logframe and workplan

Praise for SuNMaP
“Everyone we spoke to praised SuNMaP” Extract from MTR review team presentation to DFID
“They are really making a difference” SMoH Kano
“We appreciate the way SuNMaP works with us as partners. They don't just tell us what to do” SMoH Niger
“They give us the support we really need” NMCP
“The technical advice is top grade. They don't bulldoze us, they always seek our consent and plan with us” Director of Disease Control, Lagos SMOH
“SuNMaP support in harmonising the partners and leveraging resources really helps the state's quarterly review of the operational plan” WHO Zonal Malaria Programme Officer, Lagos

This section presents and considers the logframe indicators and 2011 milestones for the programme. Progress against the milestones is presented in tabular form. Specific comments and recommendations are made within each table (italicised), and in the text that follows.

We note that SuNMaP has not addressed the logframe changes recommended by the 2010 OPR.
## Purpose: strengthening delivery
Table 1: Purpose: To strengthen delivery of Nigeria’s national malaria control effort
No.	Indicator and Milestone	Progress
1	National indicator - Percentage of all children under 5 who slept under a ITN the night before the interview / Baseline 2007: 4% (MICS) / Milestone 2012: 80%	Milestone might be achieved / Malaria indicator survey, MIS, 2010: 30%. Significant progress has been made over the past year; together with the continued distribution of 60 million nets, the 2012 milestone might be achieved
2	National indicator - Proportion of all women with birth in last 2 years who received at least two doses of IPT / Baseline 2007: 3% (MICS) / Milestone 2012: 25%	Milestone might be achieved / MIS 2010: 13.2%. Progress is being made, and plans are in place. Hence the milestone might be achieved by 2012
3	National indicator - Proportion of children age under 5 with a fever episode in last two weeks who received treatment with ACT / Baseline 2007: 2% (MICS) / Milestone 2012: 30%	Milestone might be achieved / MIS 2010: 5.9% If ACTs availability is increased, this milestone might be achieved / NMCP strategy required RDT diagnosis prior to ACT treatment; may need to change the wording
4	State level indicator - Percentage of all children under 5 in supported states that slept under a ITN the night before the interview / Baseline 2007: 3% (MICS) / Milestone 2011: 60%	No comprehensive data: awaiting secondary, disaggregated data from 2010 MIS / SuNMaP surveys: / Kano 2009: 43.8% / Anambra 2009: 42.0% / Niger 2010: 31.1% / Ogun 2010: 15.4%
5	State level indicator - Proportion of all women with birth in last 2 years in supported states who received at least two doses of IPT / Baseline 2007: 2% (MICS) / Milestone 2011: 25%	Programme states data will only be available when secondary (disaggregated) analysis of 2010 MIS is released: / Data from programme sentinel sites / 2009 2010 / Kano: 26.7% 25.3% / Anambra : 22.4% 42.9%
6	State level indicator - Proportion of children age under 5 with a fever episode in last two weeks in supported states who received treatment with ACT / Baseline 2007: 3% (MICS) / Milestone 2011: 30%	Data for SuNMaP states will only be available when secondary (disaggregated) analysis of 2010 MIS is released. Data from programme sentinel sites (not representative for the state) / 2009 2010 / Kano: 0.7% 0% / Anambra: 4.5% 21.1% / NMCP strategy required RDT diagnosis prior to ACT treatment; may need to change the wording

Comments
The purpose-to-goal logic is valid. All interventions have proven effectiveness against malaria morbidity and mortality. The largest contribution towards the goal is expected from the use of LLINs which can be expected to reduce malaria specific mortality by 55% among children using LLINs and possibly higher where community coverage is exceeding 70-80% (mass effect). Based on verbal autopsy studies, the proportion of malaria specific mortality in children under 5 in Nigeria is expected to be 25-30%. From the recent 2010 MIS the prevalence of Malaria in under 5s is 51.5% (RDT) / 42% (Microscopy). Effective reduction in malaria mortality will, therefore significantly contribute to the overall mortality reduction (including indirect effects).

The outputs, which include mass distribution campaigns for LLINs, LLINs and IPT for pregnant women, BCC, and treatment of malaria with ACT are the key evidence-based interventions to address malaria control.

Purpose-level recommendations
- DFID should recognise the likelihood that providing every household with 2 LLINs will require significant funding from donor partners
- SuNMaP should undertake research to determine the reasons why not all children under-5 are not sleeping under LLINs, even though the household possess a LLIN

## Output 1: Capacity strengthening
Table 2. Output 1: National, State and LGA capacity for policy development, planning and coordination are improved
No.	Indicator and Milestone	Progress
1	NMCP annual operational planning process in place / Milestone 2011: / Process to review NMCP AOP in place and showing up to 60% implementation	2011 milestone not fully achieved (30% implementation), but 2011 AOP implementation shows significant improvements (due to more realistic target-setting)
2	SMCP annual operational planning process in place in all supported states / Milestone 2011: Process to review SMCP AOPs in place and showing up to 60% implementation	2011 milestones not fully achieved for 2010 AOP (implementation around 30% in three states). However, 2011 AOP implementation in states shows significant improvement as targets are more realistic. The planning process has proved fruitful
3	NMCP coordination mechanism in place / Milestone 2011: / NMCP branches heads, partners forum and sub-committee meetings taking place regularly	Milestone achieved. / The various coordination platforms have been functional and meeting regularly with varying degrees of performance. Sub committees are functioning well. However the partners’ forum is in need of improvement. A review of the PPP, coordination and coordination framework is being planned.
4	SMCP coordination mechanism in place / Milestone 2011: Partners forum for malaria control coordination meetings taking place regularly in all supported states	Milestone partially achieved / National coordination framework adapted in all programme states, and TWG sub-committees constituted. Kano, Lagos and Anambra have a functioning partners forum; the remaining 3 states have established the for a this year

SuNMaP has made considerable progress in supporting the planning processes at both federal and state level, although the “60% implementation of AOP” target has not been fully achieved. This reflects over-ambitious target-setting in both federal and state AOPs for 2010. This has provided important lesson-learning; the 2011 AOPs were prepared following detailed review of the achievements of the 2010 AOP implementation. The resulting 2011 AOPs have set more realistic targets; subsequent analysis (quarterly) shows significantly higher levels of achievement for 2011. At this stage, state ministries remain dependent on SuNMaP’s technical support for planning and managing malaria control activities. It will be important that over the next two years SuNMaP gradually withdraw this support to ensure the state ministries are able to plan and manage independently by the end of the programme.

The coordination processes are in place in all six programme states (although at an early stage of development in Katsina, Niger and Ogun).

The SuNMaP-supported NMCP management and planning training modules have contributed directly to the state AOP development process (and have contributed to planning processes across the sector in programme states).

SuNMaP continues to provide valued capacity building support to NMCP.

Recommendations for Output 1
SuNMaP should develop an explicit capacity building exit strategy to ensure state ministries can demonstrate their ability to plan and manage independently by the end of the programme

## Output 2: Harmonisation
Table 3. Output 2: All agencies’ support for the malaria sub-sector at federal, state and LGA levels are effectively harmonised
No.	Indicator and Milestone	Progress
1	Cumulative number of strategic areas for which harmonized methodologies and tools are developed and used by partners / Milestone 2011: / 4 strategic areas	Milestone achieved: / NMCP coordination framework endorsed / LLIN universal coverage distribution campaigns / ASCM national strategic framework / Malaria control capacity building programme
2	Mechanism in place for public-private partnership coordination / Milestone 2011: / Forum for interaction between NMCP, RBM partners & private sector partners meetings taking place regularly	Milestone achieved / Significant increase in interactions with private sector partners

SuNMaP’s achievements have been considerable:

At the national level:
- NMCP coordination framework: framework revised, endorsed by partners and implementation supported
- LLIN universal coverage distribution campaigns: resource mapping, national plan, implementation guidelines and tools, training materials, management structure
- ACSM: national strategic framework, joint partners implementation plan, state-level tool kit developed
- Malaria control capacity-building: 13 programme management and service delivery training modules developed, and endorsed by partners. The training modules, developed with NMCP are proving effective – the planned roll-out of training is ongoing – with evidence that they are improving both planning and case management of malaria. The training modules are being used by other partners, including the World Bank.
- National malaria operational research agenda setting: programme technical and financial support to a NMCP- led process for setting priorities and mapping resources (May 2010).
- SuNMaP is also in the process of coordinating a harmonised approach to:
  Development of a procurement and supply chain framework
RDT roll-out plan: support RBM partners, document lessons learned
At the state level
Malaria control AOPs capture partners’ and stakeholders' contribution to MC (including harmonised roll-out of MC training)
The past year has seen greater interaction with the commercial sector, with regular SuNMaP-led meetings held between NMCP, RBM partners and private sector partners. These include M4P market analysis training and feedback. Several other interactions with private sector partners have taken place in which SuNMaP contributed but did not lead (e.g. AMFm, GF corporate businesses engagement meetings). A ToR has been agreed with NMCP to review the PPP which will commence shortly. The outcome of this consultancy will contribute to revising the current coordination framework. However, the team learned that SFH, a commercial sector actor, has not fully engaged in the harmonisation process; NMCP is not aware of all their plans and activities

Recommendation for Output 2:

DFID should press donors supporting SFH to ensure that NMCP and SMCPs are fully aware of SFH's plans and activities

## Output 3: Prevention
Table 4. Output 3: Population coverage of effective measures for the prevention of malaria is increased
No.	Indicator and Milestone	Progress
1	Proportion of households in supported states with at least one ITN / Milestone end 2011: 70%	Achieved. / % of households with at least one ITN / Nigeria MIS 2010 : 41.5% (2008 - 8%) / Kano 2009: 69.3% (2008 - 7.2%) / Anambra 2009: 64.3% (2008 - 12.7%) / Niger 2010: 51.4% (2008 - 5.2%) / Ogun 2010: 52.4% (2008- 5.1%) / SuNMaP has coordinated the LLIN mass distribution from the start, and now has a similar role in routine LLIN distribution through ANC and EPI
2	Proportion of nets received from the distribution campaign still in possession of the household 4-6 months after distribution / Milestone 2011: 90%	More than achieved / % campaign nets present in household at 4-7 months after distribution: / Kano 92%; / Anambra 98%; / Ogun 94%; / Niger 99%.
3	Cumulative number of SP doses distributed in supported states in public facilities. / Milestone: 10.2 million	Not achieved. / 1.4m doses have been distributed, a further 2.6m have been procured. / SP procured and delivered at State level - all planned to be distributed by end 2011: / Anambra: 925,000 / Kano: 1,085,000 / Katsina: 205,000 / Lagos: 1,830,280 / Niger: 350,000 / Ogun: 770,000 / Total 6.09m / SP delivered to facilities at the time of the review, delivery process commenced cot 2010 after sign off of MoA: / Anambra: 250,000 / Kano: 600,000 / Katsina: 109,960 / Lagos: 408,445 / Niger: 179,680 / Ogun: 183,760 / Others: not yet / Total 1.73m
4	Cumulative number of LLINs sold by supported commercial sector partners on the retail market / Milestone end 2011: 5 million	No longer an appropriate indicator / This is because DFID limited the intervention to 15 months from July 2009 to end-Sept 2010, during which three companies sold 613,000 LLINs through retail channels. SuNMaP provided £1.3m to the companies, most of it as direct price subsidy of 300Naira for each LLIN sold. SuNMaP also spent £470K on additional support. Before the intervention the companies were selling bundled rather than long-lasting nets, so there is no baseline, and thus is no way of judging whether sales after Sept 2010 were higher or lower than they would have been without the DFID support over the preceding 15 months. / SuNMaP has now adopted the approach known as ‘Making markets work for the poor’ (M4P).
5	Proportion of sampled outlets selling nets that have at least one LLIN brand on sale / Milestone 2011: 80%	Achieved. Retail survey 2009: 79% / The survey covered three areas: Anambra, Kano and Ogun/Lagos and three locations in each (central, peripheral, remote). Over 10,000 outlets were screen with 344 found selling any nets, of which the great majority stocked an LLIN. Given the unstable market following free distribution, this indicator is not a very meaningful one, and will be replaced when the new M4P approach is finalised. .

The main LLIN element of this output has been achieved because of the free distribution of 60m nets. SuNMaP played a key role in coordinating this nationally, and it’s planning and guidelines made every state campaign remarkably efficient. It has also made the follow-up very effective in the states where it works. (SuNMaP provided direct implementation/support role in Anambra and Kano. In Ogun and Niger, SuNMaP provided support through the NMCP's State Support Teams which SuNMaP trained, plus some limited support at State level). Much of this contribution is reflected more in Outputs 1 and 2 than in this one.

SuNMaP organised follow-up surveys about 6 months after the free distribution, the results of which are shown above under Indicator 2. Respondents said that the missing nets had been passed on to relatives (2.6%). There were some free LLINs for sale in local shops but these seem to have mostly come from the supply chain, not from ordinary people.

Work on increasing coverage by distributing LLINs and SP at routine ANC and EPI sessions systems has started and will make a significant contribution to maintaining the coverage achieved by the free nets. SP consumption data from facilities is not available yet, but SuNMaP is providing TA support to SMOH to improve the quality assurance of the data. The Milestone figure for SP in Indicator 3 above represents a cumulative total for 3 years, however there was no SP distribution supported by SuNMaP in 2009. These figures therefore reflect 2010 only and the distribution commenced in selected facilities in the states and later half of the year. The plan this year is to continue with the distribution based on consumption and expand to more health facilities.

For the commercial LLIN sector, SuNMaP planned to spend £1.6m to increase competition through supporting new brands and Nigerian businesses in the LLIN market. By the end of the 15 months SuNMaP had spent £1.3m on the support scheme, i.e. £300,000 less than budgeted. This was made up of:
- £100,000 as grants to distribution
- £150,000 as grants to promotion (the companies matched this with £60,000 of their own expenditure)
- £760,000 as grants for direct price support, being 300N for each of the 613,000 LLINs sold by the three companies through retail shops during these 15 months.
- £ 280,000 as grant for seed stock

At the end of the scheme, one company, Teta, had not sold enough nets to pay back their advances from the direct price subsidy. In fact, Teta owed SuNMaP £200,000. They have paid back £40,000 of this in cash and the rest with 36,000 LLINs which will be distributed as part of the programme support to routine distribution in programme states. The programme thus recovered all funds owed by Teta.

In addition to its expenditure with the three companies, SuNMaP has spent £470,000 on support to this component. This is made up of:
- £ 220,000 on long-term and short term technical support;
- £150,000 on management and financial oversight and fees;
- £100,000 for commissioning of reviews and market analysis.

DFID has now recommended that SuNMaP adopt M4P. Consultants visited in April-May 2011, and SuNMaP produced a new strategy in June 2011. Three staff and the DFID health adviser are now attending M4P training in the UK. In the meantime, SuNMaP had developed a £1m generic marketing campaign aimed at encouraging purchase of LLINs. The campaign is designed to boost retail sales and may do so.

Recommendations on Output 3.
- DFID should clarify why SuNMaP has not done formative research and hired staff with appropriate commercial expertise.
- DFID Health & PSD should agree on the objectives of M4P interventions in the commercial LLIN market, and how they can best be implemented.

## Output 4. Treatment
Table 5. Output 4: Access of the population to effective treatment for malaria improved
No.	Indicator and Milestone	Progress
1	Proportion of health facilities in supported states with adequate logistics compliance for ACTs / Milestone 2011: / TBD	No progress because health facility staff in programme states have not received the Global Fund Procurement and Supply management training. However, DFID has agreed that SuNMaP programme funds will now support health facility training 2011-2012 / It follows that a proportion of health facilities should have logistics compliance for ACTs by the programme end
2	Proportion of U5 malaria cases that were reviewed in sampled health facilities in supported states and were treated with ACTs / Milestone 2011: / TBD	No data available from the health facility assessment survey to date. / Limited availability of ACTs will further compromise effective facility treatment of malaria
3	Cumulative number of commercial sector ACTs sold by supported commercial sector partners / Milestone 2011: / 4,500,000	No data available / Achieving this milestone will be dependent on the availability of AMFm ACTs into the commercial sector (they are not available in programme states at present.)

Based on the above indicators, there is no means for assessing progress (and milestones are yet to be established for two indicators). The GF-managed procurement and supply management training has not been extended to the programme states. However, DFID has agreed for SuNMaP funds to support this training for programme states health facility staff 2011-12, so progress by the programme end should be demonstrated (no milestones have been determined at this stage).

There is no data on the proportion of children treated with ACTs. The results of the household survey are awaited, so it is not possible to establish a baseline (or, indeed, a measure of progress). Interpretation will be further compounded as the current shortage of ACTs may be limiting appropriate treatment (the review team visited facilities that had stock-out of ACTs).

The review team were impressed by the knowledge of primary health care staff who had received the malaria case management training. However, the training had been classroom-based (with pre- and immediate post-training assessments), and SuNMaP
has not incorporated follow-up evaluation of the training in the programme. This should take the form of ongoing on-the-job assessments, training and supervision SuNMaP envisage that this will be provided through the planned integrated supportive supervision, ISS, programme. However, ISS is aimed at supporting all elements of health care delivery, and (in the opinion of the independent consultants) it is unlikely that there will be adequate resources to cover the syllabus areas adequately. The consultants recommend that SuNMaP incorporate ongoing malaria training into their current programme.

Recommendations for output 4
- The indicators for output 4 should be revised
  - SuNMaP should incorporate ongoing evaluation of the NMCP service delivery training modules (post training, OJT, mystery patients)

## Output 5. Awareness
Table 6. Output 5: Community awareness and demand for effective malaria treatment and prevention are improved
No.	Indicator and Milestone	Progress
1	Proportion of nets received from the distribution campaigns and retained by the household that were used by any household member the night before the survey / Milestone 2011: 70%	Partially achieved / Surveys 4-6 months after distribution show use of any LLIN among households that had retained any of the campaign nets: / Kano: 68% / Anambra: 56% / Niger : 87% / Ogun : 63%
2	Proportion of women in child bearing age in supported states who know the preventive benefits of LLIN / Milestone 2011: 70%	Not achieved - indeed, it is going in the wrong direction. / February 2010:58% / October 2010: 56% / February 2011: 51% / SuNMaP only just received the results of the Feb 2011 survey, which it is now analysing.
3	Proportion of women in child bearing age in supported states who know the preventive benefits of IPT / Milestone 2011: 40%	Achieved. / February 2010:39.6% / October 2010: 37.9% / February 2011: 48.5% / For this indicator SuNMaP referred the MTR team to output 2 (SuNMaP leading development of joint partners comprehensive ACSM strategic framework and implementation plan).
4	Proportion of care givers in supported states who recognize need for treatment of malaria within 24 hours / Milestone 2011: 90%	Largely achieved, but baseline not far off target.. / February 2010:87% / October 2010: no data / February 2011: 85%

Most indicators are positive, and SuNMaP argued that this output should be scored '1', but while awareness may be high, this does not necessarily translate into 'demand', which is what the output specifies. It is also not yet clear whether people who are aware of preventive benefits of LLINs and who can afford nets will buy them when their free ones become ineffective. This will be a crucial test of demand for prevention.

The focus of the free distribution campaigns was on getting the nets out, and it is not surprising that use has lagged a bit. This problem is acknowledged in SuNMaP’s Demand Creation Strategy, that ‘the low utilization of LLIN is associated with myriad of behavioural and social change issues including inadequate knowledge, negative perception and beliefs, and limited economic capacity at household level.’ The 6-month follow-up surveys and rapid assessment of reasons for non-use led to SuNMaP doing radio & face-to-face social mobilisation, all of which was good work using Omnibus survey data. The national and state Advocacy, Communications and Social Mobilisation (ACSM) plans are sound but maybe a bit too ambitious – there is always the risk that TA to BCC tends to ‘take over’, when the objective is a realistic level of capacity maintained after the end of the project.

Indicator 2 appears to be going in the wrong direction. This may simply be due to margins of error (e.g. 58% could have been 55%, 51% could have been 54%, so no change). Or it may be due to the question itself not being understood as intended. (It would be useful if the actual Nigerbus question were included in the reporting of indicators). We question why it is restricted women of child-bearing age - it may be that their mothers or mothers-in-law, being older and remembering their own use of untreated nets, have a negative influence on this opinion.

The main driver of Indicator 3 will be getting pregnant women to come to ANC (not all SuNMaP SMCPs know what % do so); getting supplies of SP into ANC clinics; and getting ANC workers to persuade women it is important. Also see the comments above for the possible negative (or maybe positive) influence of mothers and mothers-in-law. Monthly dip-stick interviews with 100 women leaving ANC clinics might cast light on why some women do not take up SP.

Indicator 4 covers ‘awareness’, which is certainly important, but an indicator showing 'demand' would be better, i.e. what % of care-givers act on their knowledge or want to act but cannot for some reason. There are several steps people must take from knowing that something is important to actually doing something about it. Without research on which consumers do and which ones do not act quickly, and why, the ACSM efforts could be wasted. SuNMaP needs to help the NMCP and SMCPs face two issues - that these care-givers may act quickly but end up getting fake ACTs; or they may act quickly and go to an untrained (or trained but still poor quality) for-profit provider. It would better for each SMCP to know what % of under-5s with malaria are 'likely to be seen within 24 hours by a skilled provider with appropriate ACTs in stock', as this would combine care-givers health-seeking behaviour, provider training and follow-up, and the availability of ACTs.

Recommendations for Output 5
- SuNMaP should help NMCP and SMCPs to do and use the research needed to achieve behaviour change; and get SFH more fully on board in this effort.
- SuNMaP should report 'demand' separately from 'awareness', and focus its efforts on demand
- SuNMaP should advise NMCP & SMCPs of the risk that care-givers may go to poor quality providers or buy fake ACTs

## Output 6. Operational research
Table 7. Output 6: Operational research into key areas of prevention and treatment provides the evidence base for more effective strategies
No.	Indicator and Milestone	Progress
1	Cumulative number of OR studies completed and disseminated / 2011 Milestone: 6 / .	One OR study has been completed / Two studies are in the pipeline / Three studies have been defined
2	% of OR studies that have confirmed current malaria strategies and practices or contributed to changes in malaria strategies or practices / 2011 Milestone: 20%	Workshop on completed study resulted in advice to SMCPs. / Therefore, 100% of completed studies have contributed to change

As noted in the 2010 Annual Review, SuNMaP has approached this task with a cooperative methodology. This approach is intended to both develop a sense of ownership in the research and to build a sustainable capacity for future research to support policy development. The studies are not only important in themselves as producing knowledge but also as a process by which NMCP is introduced to the process of commissioning, managing and using evidence in policy development. Similarly, researchers have been introduced to the issues of undertaking OR to support policy development.

This approach has required a long period of engagement with NMCP, the Nigerian research community and other stakeholders in order to commission the studies and to develop an environment in which they can be used.

Activities noted in the 2010 Annual Review included:
- A priority-setting exercise, involving all stakeholders, in which questions were identified that might be suitable for OR;
- Refinement of questions to eliminate overlap and duplication;
- Stakeholder ranking of refined questions according to a pre-agreed scoring scheme;
- Commissioning of studies with the highest priority.

Other work has included a review of current and recent research in Nigeria of relevance for malaria control. There are plans to use the information gained from this review to develop a virtual resource centre.

This process is necessarily slower than could have been achieved by a less inclusive approach. SuNMaP appear to have underestimated the time required to require buy-in in this way and there was a significant underspend in Year 3 (approximately £130,000 or 48% of the amount budgeted) as a result in delays in commissioning and managing the research.

There is evidence that NMCP is now taking evidence more seriously in the development of policy in that they have begun to request technical information from SuNMaP.

In addition, OR3 has now been completed and was the subject of a workshop with key stakeholders and led by NMCP. The outcome of the workshop was a one-page document providing advice to SMCPs on factors to take into account when considering the integration of other items into LLIN distribution. This is a significant achievement in that NMCP has taken note of technical knowledge based on research within Nigeria and confirms the value of the SuNMaP approach. Now that the mechanism is established, studies could be expected to proceed more speedily.

Future work will focus on developing a sustainable mechanism by which the technical results generated by researchers can be interpreted for policy makers.

The SuNMaP team responsible for the OR studies are also responsible for Monitoring and Evaluation, M&E. While this link has been useful in establishing the importance of OR, in that it has been possible to use the M&E platform to drive forward the work on Operational Research, the team is currently overstretched and requires strengthening to consolidate the gains already made and to support further developments. The team is well-led by SuNMaP’s Technical Director who is well-respected by stakeholders and has established good relationships with NMCP. It is important that he should have sufficient time to continue this work without being diverted by routine tasks. Therefore, we recommend that SuNMaP should appoint an additional TA to support the team.

Recommendation for output 6
SuNMaP should appoint additional TA to the SuNMaP team to support operational research

# SuNMaP’s M&E framework and logframe
The Logframe was revised in May 2010, but not revised again after the 2010 OPR, despite that review concluding that 'some more changes to the indicators are required'. The 2010 OPR recommended changes 'because of a mix of: (i) changes in the wider context; (ii) there is overlap of some indicators; iii) some outputs do not have an appropriate set of indicators; and (iv) thinking on what is, and is not, useful to measure has changed'. The 2011 MTR team agree, and in addition to the comments above on each output, has 3 new recommendations.

First, the indicators should reflect the purpose or output itself. The purpose is 'strengthening delivery', i.e. the system, but the indicators are all outcomes, such as improvements in women’s and children’s health. These indicators reflect much wider impacts than SuNMaP, and so they are not very useful for reviewers such as the MTR team, or for the project managers. The new M4P approach should mean that market-related issues such as increasing competition or wider distribution, which are more useful indicators of what SuNMaP is trying to achieve than simply the number of nets sold, feature in the logframe.

Secondly, indicators which reflect activities, such as number of SP doses distributed, the numbers of PMVs trained should show coverage as well. Coverage was a recurring question we had for the SuNMaP team and for the NMCP and SMCPs.

Thirdly, the capacity-building indicators record that a process such as planning is in place, not how well it is working. It is always difficult to measure capacity-building, but DFID's ENR project is doing very similar work on state responses to HIV/AIDS, and has much more useful indicators, based on a self-assessment by the State AIDS Control Agencies as to how well they think they are doing on five or six key functions. The results are moderated and verified by the project managers, and the exercise of reflecting and analysing its own performance is itself evidence of a stronger organisation. Other DFID state-level programmes such as SPARC and ESSPINN can also provide lessons. Indeed, it would be useful for DFID to have some standard indicators for this activity, which is common to so many of its programmes in Nigeria.

Recommendations
  - The indicators should reflect the purpose or output itself. For example, the purpose is 'strengthening delivery', i.e. the system, but the indicators are all outcomes, such as women and children benefiting.
  - DFID and SuNMaP should address the logframe changes recommended by the2010 OPR and this MTR.
  - All indicators should show coverage (for example % of target group reached), rather than just numbers.
  - SuNMaP’s main presentation to the next OPR should go through the logframe, indicator by indicator, and include assumptions.
## Assumptions
The Purpose-to-Goal assumptions in the logframe remain valid. They are:
- Commitment to Nigeria’s PRSP (Vision 20 2020) continues beyond the planning stage into effective implementation
- Sustained Commitment by NMCP to achieving targets in National Malaria Strategic Plan (2009 – 2013)
- ACTs and LLINs remain effective
- No large scale other disease epidemics

Output 1-to-Purpose assumptions 1 and 2 are questionable, given what we learned from meetings with PATHS 2. Assumption 3 is still valid, thanks in no small part to the efforts of SuNMaP itself.
- FGN continues to implement health system reforms and increases health spending
- Accountability mechanisms between National, State, LGA and community levels are strengthened
- Government and Partners are committed to NMCP Coordination Framework

Output 2-to-Purpose assumptions are still valid.
- FGN, State and donor agencies are willing and able to combine resources in support of NMSP
- NMCP provides leadership and stewardship to RBM Partnership

Output 3-to-Purpose assumptions are still valid, though No 4 is now out-of-date given the massive distribution of free LLINs.
- Sufficient LLIN for campaigns are available from other sources outside the project
- There is minimal leakage of free LLINs from donor programmes into the commercial market
- ANC attendance in supported states remains at weighted averaged NDHS 2008 rate of 62%
- There is no major competing price-support programme that undercuts commercial efforts

Output 4-to-Purpose assumptions are still valid, but there have been so many delays in getting AMFM ACTs into Nigeria that they are not very useful for the project.
- Sufficient and consistent resources are provided from global sources for commercial sector ACTs distribution
- There is high acceptance of ACT amongst health workers in their treatment practices

Output 5-to-Purpose assumption has proven to be sound, not least thanks to SuNMaP’s own efforts
RBM partners harmonize malaria control communication messages

Output 6-to-Purpose assumption has not yet been tested.
Results of OR are accepted at policy development level
## Risks
We would add one new risk to the 15 in the project memorandum, namely that ‘Widespread availability of counterfeit, cheap ACTs undermine consumer confidence in the effectiveness of ACTs’. This is a slightly different (and more specific) issue than Risk No 2 in the table below, as SWuNMaP and others are training PMVs and we did find one PMV selling fake ACTs (and state ministries agreed that this was common practice).

Several of the risks to the LLIN market remain valid. Many consumers still buy untreated nets (No 3), which are much cheaper (and often come in more consumer-friendly sizes and shapes) than LLINs. Better research into consumer habits and preferences (and paying more attention to existing research) would help to minimise this risk. No 6 is less likely and No 9 has been superseded for now by free distribution, but it remains a possibility that in the future demand for ‘replacements’ as free LLINs get worn out could exceed supply.

Table 8
Risks	Probability	Impact
1. Competition from cheap monotherapies cannot be minimised	High	Low
2. Drug quality is not adequately assured	High	Medium
3. LLINs cannot be marketed in the face of competition from untreated nets and ITNs	Low	Medium
4. Import duties are not adjusted to allow cheap imports	Low	Low
5. Malaria parasites develop resistance to SP	Medium	Low
6. Other household members use the ITNs rather than target groups	Low	Medium
7. ACTs cannot be delivered in Nigeria at an affordable cost	Medium	High
8. Oil prices stabilise or fall	Medium	Medium
9. ITN demand cannot be met	Low	High
10. Women do not continue to attend ANC	Low	Medium
11. NEEDS is not effective at reducing poverty in Nigeria	Low	Medium
12. Prevention strategies do not continue to be effective	Medium	Low
13. FGN does not deliver health sector reform	Medium	Medium
14. Strengthened RBM secretariat weakens ownership by states	Low	High
15. Geographical coverage of project inputs is not sufficient to deliver national impact	Medium	High
16. Widespread availability of counterfeit, cheap ACTs undermine consumer confidence in the effectiveness of ACTs’	Low	Low

## SuNMaP’s approach, strategic direction and risk mitigation
SuNMaP is operating in a challenging environment. The health system is weak, characterised by under-funding, poor governance, limited human resources, weak and under-utilised service delivery, and lack of commodities. There is widespread use of the largely unregulated private sector.

SuNMaP’s approach throughout the programme has been to provide support to NMCP and SMCPs based on ownership and harmonisation. Their capacity building strategy[1] (June 2011) provides a succinct summary of their approach:
[1] Support to National Malaria Programme: Updated strategy for building capacity for malaria control. June 2011. SuNMaP Abuja, 2011
- participatory appraisals and assessments
- building of individual and team capabilities using multiple approaches
- Strengthening of line systems
- Institutional strengthening of state and national programme units
- Incorporation of elements to promote sustainability and expansion of capacity building beyond programme efforts

The review team found universal support and praise for SuNMaP’s capacity building efforts. Furthermore, the review team found instances where the processes adopted in developing AOPs for malaria had been used for state health planning across the sector. The SuNMaP management/ planning and service delivery training modules for malaria were singled out for praise (and also impressed the review team). It is clear that national and state capacity for malaria control has been strengthened; sustainability after the programme ends will be dependent on greater financial commitment from government.

On a technical level, SuNMaP is working to its strengths in that Malaria Consortium, the SuNMaP lead partner, has recognised expertise in malaria control in the public sector in resource-poor settings. SuNMaP has less experience in working in the commercial and private for profit health sector.

As described earlier, this approach has led to a number of notable achievements:
- Federal and State malaria control AOPs developed with all stakeholders, ensuring federal and state ownership; recent indications suggest that implementation will be improved significantly in 2011
- Harmonised approach (Ministry, donors and partners, stakeholders – including the private sector) to key strategic areas in malaria (e.g. LLINs)

# SuNMaP’s work with the commercial LLIN sector
This section addresses the three topics specified in the TORs - a review of SuNMaP’s progress, of its plans, and of its approach to the commercial LLIN sector. It also addresses DFID’s management of this component of the project.
## Progress to June 2011 against the logframe
This is reported under paragraph 4.1.3 .above.

Comment
The logframe covers only the LLINs sold by three companies which supported by SuNMaP during the 15 months of that support. In the next 9 months the three CSPs reported sales of 100,000 LLINs through the retail channel, compared to 225,000 in the same 9 months of subsidy. (See Table 5 in Annex 5.) Sales in this latter period may well been lower had there not been the preceding support, in which case SuNMaP could be credited with a proportion of these post-support sales. SuNMaP did not present any estimate of what proportion of the additional 125,000 might be due to the preceding support, and the MTR team agrees that attributing all, some or none to SuNMaP would be difficult and hence unreliable. (Before-and-after comparisons are not possible because before the SuNMaP support the three companies were marketing bundled nets, not LLINs).

It is widely acknowledged that whatever you do to influence markets, it should be long-term and consistent. At the time DFID’s decision in 2009 to limit the intervention to 15 months made sense, because SuNMaP was reluctant to renege on the contracts it had signed with the LLIN companies. With the benefit of hindsight this meant the 2009-2010 intervention was ‘neither fish nor fowl’ - direct subsidies to the companies were probably too big and too direct (a point also raised in Annex 5 below), while 15 months was too short for an intervention such as this.
## Progress against other objectives
In an email on July 14th 2011 the programme director restated the objectives of this component of the SuNMaP programme, ‘to increase the choice, quality, reach and affordability of LLINs in Nigeria’.

It was not possible for the MTR to reach a conclusion on whether the project has achieved these four objectives. Neither the June 2011 Strategy Paper for the LLINs commercial sector, nor the ‘Final justification memorandum on closure with CSPs’ (undated) addresses these four issues as objectives.

The former does mention affordability (‘Average consumer price of N800 may still be a barrier to purchase amongst the poor’) and reach (‘Sales and outlet penetration beyond urban centres into rural areas requires additional support’). The Nigerbus survey to which SuNMaP subscribes does suggest that price is a barrier, and not just for poor people, as 75% of respondents say they would find a price of even N500 too high. On reach, the survey data on which outlets sell LLINs does not show that distribution requires additional support – such an assessment needs evidence that people who want to buy an LLIN and can afford to do so cannot find them in the market, i.e. that supply is failing to meet demand. We heard anecdotal evidence that this was the case, and SFH told us that, as so often with conventional social marketing, support to distribution would be a priority if they had the funds to do it.

During our discussions SuNMaP pointed to greater choice in the LLIN market, as indicated by an increase in the number of LLIN brands; and to new products such as insecticide-treated curtains. No data or analysis of this was covered in any of the reports provided or in the meetings, so it was difficult for the MTR to judge the significance of this. LLINs are in effect a new product, and we would expect them to follow the normal trajectory of such markets, with new entrants and new product development as players seek to establish themselves in the market, and to distinguish their brand from their competitors. It will be difficult to analyse changes in such factors until the market settles down after the massive injection of free nets.
## SuNMaP’s plans for the commercial LLIN sector
### Generic Marketing Campaign (GMC)
The Nov 2010 Strategy says that SuNMaP will support generic marketing ‘to encourage net use culture’. The Year 4 Plan is more specific and says the aim is to ‘increase consumer understanding and demand for LLINs’, and that ‘it will be closely monitored using pre, during and post researches’. The budget is about £1m.

The brief for advertising agencies to bid for this campaign is quite good, and includes data from the Nigerbus survey. The advertising agency (Insight) told us that the objectives of the campaign, which is due to start in August, are to ‘increase awareness of LLIN from 16% to 21%; increase the purchase level of LLIN from 16% to 18% pan Nigeria; and increase usage of the LLIN in all households’. The target audience is lower middle class parents and their children, with a strongly emotional appeal that ‘parents who value their children make sure they sleep under a net’.

Comment
Research
The generic marketing campaign is well-intentioned and looks to be well-executed by the advertising agency. But to be effective, marketing requires in-depth information about people who have recently bought the product; about those who had thought of buying but did not (to understand the barriers to purchase); and about those who say they are likely to buy in the future.

The 2010 OPR made the same recommendation as the 2009 review, and urged SuNMaP to ‘develop a deeper understanding of the market for nets…of capacity to pay, and of the supply chain’. Before embarking on the generic marketing campaign SuNMaP should have commissioned formative research into the potential consumers they say they are seeking to influence - people who have received a free LLIN which is now needing replacement, or who got some free nets but want additional nets for their children and are willing to pay for them.

Generic marketing and branded promotion
We agree with the suggestion of the M4P consultants that any generic marketing ‘should be part of a longer-term programme of continuous marketing effort’. 6 months is almost certainly too short (and £600K probably too little) for this sort of campaign. We also agree with the M4P consultants that the owners of the LLIN brands (whose business stands to benefit) should be the ‘drivers’ of any such generic marketing, the effectiveness (and VfM) of which will be diminished if it is not matched by branded promotion. SuNMaP has not got commitment from the LLIN companies that they will do this, nor did we hear it from the companies in our discussions with them.

Measuring impact
The specification for monitoring the impact of the generic marketing campaign is poorly done, and the timescales for the baseline survey are unrealistic. If SuNMaP proceeds with the campaign as planned, they will not be able to say with any confidence what impact the campaign has had.
### Making markets work for the poor (M4P)
In 2010 SuNMaP and DFID agreed on the need for a new strategy to achieve the project’s objectives for the commercial LLIN sector. M4P was selected as the best approach. A team of consultants worked with the project in April-May 2011. The latest June 2011 commercial sector strategy reflects the M4P approach. It does not include any objectives or outcomes as such, but sets out 5 ‘strategic interventions’
- Consumers understand the value of LLIN
- Stronger and wider distribution network reaching the urban and rural market
- Establishment of local manufacturing facility
- Development and promotion of variable sizes, packaging and features of LLIN meeting the local demand
- Favourable market environment for commercial market

Comment
After reading this strategy document, DFID’s Private Sector Advisor suggested during the MTR that ‘the first priority is for DFID to decide what it wants the market to look like by the end of the programme’, and to make sure that DFID and SuNMaP have the same goal. We agree that it is not yet clear what SuNMaP’s objectives are for the commercial LLIN sector. We suggest that after their M4P training, DFID Health and PSD and SuNMaP should address this question; and consider the pros and cons of not intervening at all, as well as M4P interventions.

If DFID decides to support M4P interventions, we suggest there be a separate logframe for this component. This would have a number of benefits. It would enable SuNMaP to articulate the theory of change behind its approach, and hence demonstrate the evidence on which the theory of change is based; it would record explicitly as outputs the objectives (choice, reach etc) which have been implicit in the current logframe; it would identify indicators by which these objectives could be monitored (and thus enable future reviews to assess progress); and it would make explicit the assumptions about how other donors and the government might fund both free and subsidised LLINs, and thus influence the commercial market.

M4P is a hands-off approach, which will require a very different strategy to that which SuNMaP has pursued so far. The MTR team shares the concern of DFID’s PSD advisor that SUNMAP may not be suited to the role of ‘market facilitator’ which the M4P approach is likely to require.
### SuNMaP’s approach to the commercial LLIN sector
At the inception review in 2009 SuNMaP agreed that the then commercial manager was not the right person to manage the planned £2m budget and contracts with three LLIN companies. He left shortly before the 2010 OPR, which recommended that the SuNMaP bring in someone with appropriate commercial experience and expertise. A new manager with a sales management background was subsequently appointed, but at this MTR SuNMaP’s senior management team told us they had concluded that ‘this is not the right background for this post’. They explained that SuNMaP had recently engaged a high level independent marketing consultant (a Professor from Lagos Business School) ‘to serve as part-time overall technical lead of the initiative.’ (Unfortunately this information came too late for the MTR team to meet or speak on the phone with this consultant). SuNMaP has brought in international consultants to advise on the new M4P strategy, and is sending staff for training in M4P.

Comment
The SuNMaP management team, guided by the core partners group, has done a good job of almost all aspects this programme. This is largely due to SuNMaP hiring the right staff for the job, and then managing those staff in an effective way. The exception to this is the commercial LLIN component, for which SuNMaP has not hired a heavy-weight commercial marketing director. SuNMaP explained to the MTR team the difficulties they had faced in recruiting someone, but we were not persuaded by their explanation for the failure to follow up this key recommendation of both previous reviews.

## DFID’s management of the commercial sector component.

DFID’s health and PSD teams could have collaborated more closely over SuNMaP’s commercial sector work. Essentially, any such intervention is more about markets and business than about health, so we suggest it makes more sense for PSD to take the lead on this component.
# Management and coordination
## Effectiveness and coordination between SuNMaP and others

There is good coordination between SuNMaP and the other DFID programmes (PATHS 2, PRRINN- MCH and others). SuNMaP attends the DFID monthly meetings, and hold regular meetings with PATHS 2 and PRRINN- MCH staff both in Abuja and in DFID-supported states (especially now that the programme will expand into four of these states). As described earlier, SuNMaP coordinates closely with other development partners, both at federal and state level.

Whilst there has been coordination with the commercial sector, it was apparent that the social marketing organisation SFH was not sharing its plans and progress with SuNMaP and other partners.

Recommendation:
DFID should press donors supporting SFH to ensure that NMCP and SMCPs are fully aware of SFH's plans and activities

## Effectiveness of management arrangements and internal coordination
“The right people doing the right things”
### SuNMaP Abuja office:
The Abuja office appeared to function well: staff interacted well, morale appeared high, and information was readily available. The review team observed the excellent relationship that existed between SuNMaP and colleagues from NMCP. The core group of the three SuNMaP partners works well. Although Abuja office staff were in regular contact with SuNMaP state office staff, there was general agreement that visits to state offices could be made more frequently. SuNMaP technical staff do quality assure short-term technical assistance reports, but it appeared that there was no overall analysis of the TA, or whether the QA was acted upon. It was apparent that the technical staff were under pressure; the review team recommended the appointment of an additional technical staff member (to focus on operational research and M and E) would be of benefit
### SuNMaP state offices
The state offices have an onerous role. They are responsible for close working with state ministries, the public and private sectors, partners and the public themselves. They are responsible for ensuring national malaria policies and strategies are incorporated into state plans and implemented. The review team were impressed by the calibre and commitment of the managerial and technical staff they met; they gained the impression that some of the technical staff felt stretched – primarily because they had to assume operational roles as well.

Relationships between SuNMaP and the state authorities appeared strong; ministries valued the support SuNMaP had provided for malaria control – the management/ planning training was singled out as of especial benefit. Relationships were more difficult in Katsina state, where the permanent secretary was critical of SuNMaP “technical support not always there when needed”, and who did not appear to understand SuNMaP’s role outside providing financial support for malaria control “the state has no money for this”. The Katsina SuNMaP were working hard to improve relationships, and reported that progress had been made in the past 6 months (coinciding with the appointment of a technical adviser).

Continuous professional development, CPD
Support and training for staff is provided by senior staff on an ad-hoc basis; all staff undergo annual appraisals. However, there is no formal process of CPD. This issue was raised by staff in two SuNMaP state offices; staff would welcome the opportunity for professional development.

Recommendations:
- The appointment of an additional technical staff member to the SuNMaP Abuja office
- Review SuNMaP state staffing levels: consider need for additional operational staff members
- Introduction of continuous professional development for SuNMaP staff
# Value for Money
## Value for Money: what it is and how it can be used
DFID[2] has defined Value for Money (VfM) as “maximising the impact of each pound spent to improve poor people’s lives”. Figure 1 demonstrates this process in terms of the project log frame.
[2] DFID (2011)

Figure 1: Programme Process
While the overall VfM refers to cost-effectiveness (the relationship between inputs and goal), we can identify some intermediate steps that are of interest. These intermediate steps are commonly known as:
- Economy: minimising the cost of inputs or activities;
- Efficiency: maximising the output obtained from inputs/activities;
- Effectiveness: maximising the effect of outputs on the purpose.

Analysis of each of these intermediate steps can provide useful management information to monitor and improve programme performance.

An important issue to be resolved in the analysis of VfM of development programmes is that of point of view to be used. Are we concerned only with the VfM to be obtained from DFID expenditures? Or do we want to include expenditures by other partners? Given that the goal of development programmes is to support the people of the recipient country, there is a strong argument for including at least the resources contributed by the Nigerian people. In addition, it would be helpful to be able to assess the overall VfM of the efforts of all partners. Indeed, one of the objectives of DFID’s VfM approach is “to improve the VfM of all aid”.
## Calculating VfM components in SuNMaP
### Availability of costs and forecasts
SuNMaP has developed a management information system that records expenditure by outputs, activities and key inputs, and expenditure against outputs is routinely reported. The MTR Team tested the ability of this system to provide information on unit costs by requesting the unit costs of a sample of items and the results of this exercise are reported below.
### Availability of information to understand the effectiveness of outputs to deliver results
For Outputs 3, 4 and 5, this information is available for many – though not all - of the indicators. This information is based on international research on the efficacy of various malaria control instruments and the MTR Team were told that this information was used to ensure that the relationship between output, purpose and goal indicators was consistent. However, these relationships are not routinely used to interpret data on output, purpose and goal indicators. Data on the indicators are gathered through a variety of survey instruments and it is planned that “(A)ll output data will be captured in an overall SUNMAP data base or information system so that any information of output performance can be made available to implementation managers at any time.”[3]
[3] SuNMaP, Updated Strategy on Providing Evidence for Malaria Control, June 2011.

For Outputs 1, 2 and 6, a clear technical link between the output and purpose/goal indicators does not exist. The rationale for these outputs is the sustainability of gains made by SuNMaP after the end of the project. From this point of view, purpose and goal indicators over the life of the project will not give a good indication of the value of these outputs. One would need to examine them five years, say, after the DFID Programme has ended. However, with over £10 million (20% of the total budget) budgeted for these outputs, it would be helpful to have a clearer view of how exactly they might be expected to contribute to the purpose and goal in the medium and long term.
### Assessing the economy, efficiency and effectiveness of SuNMaP
Economy
The unit cost of various categories of TA was fixed in the original contract and there is, therefore, no scope for analysis of these costs in a MTR.

Office rents are “negotiated and paid in advance in order to mitigate against inflationary costs and other potential rent increases” together with “(C)ost sharing arrangements in various offices with NMCP and other stakeholders”.[4] SuNMaP is able to justify the amount of space used by each office.[5]
[4] SuNMaP, Value for Money Self-Assessment Report”, July 2011.
[5] Baker Tilley External Audit, March 2010.

For procurement undertaken by the SuNMaP offices, there are clear procedures defined according to the type and value. These procedures include templates for aspects of the procurement such as Terms of Reference (for short-term TA - STTA) and a useful costing template for the delivery of a training event. The actual expenditure on such events is captured by the programme’s information system in such a way that it is possible to extract the unit costs of a variety of activities.

Tables 1, 2 and 3 in Annex 5 give examples of unit costs calculated from the information system. These costs include only expenditure by SuNMaP. They do not include, for example, the costs to the Nigerian economy of the participants of training courses or the distribution costs borne by the state or LGAs. Some key points emerge from the analysis of unit costs.

1. There is considerable variation across states in the case of training courses with Ogun being the most expensive and Kano being the least.
2. Costs of routine distribution of LLINs are least expensive; campaign distribution costs more; and the distribution encouraged by a subsidy to the commercial sector was the most expensive. Again, there is considerable variation across states.
3. The cost of developing training materials averages about £10 per participant and seems quite reasonable for materials that are widely agreed to be of high quality.
4. There appears to be little price benefit gained from buying large quantities of items such as LLINs or SP doses.

Efficiency
Although the May 2010 version of the log frame details the total budget against the six outputs, the programme does not report annually or cumulatively against this framework but the programme’s financial system is able to allocate 80% of total expenditure to a specific output. It is, therefore, not possible at this stage to estimate with confidence the overall efficiency of each output although, as we saw above, it is possible to calculate the unit costs of activities contributing to the achievement of some parts of the output. However, we have a considerable issue of attribution since SuNMaP was not the only partner undertaking activities resulting in these outputs. Even if we could attribute DFID’s impact with confidence, the output indicators in the log frame are not very helpful for VfM estimates. We might be able to estimate how much DFID has spent to achieve an additional ten (say) percentage points of LLIN coverage but this figure in itself will not tell us very much. It is much better to (a) review the costs of distributing LLINs by a variety of methods and (b) examine the impact of each method on total coverage. As we have seen, (a) is quite straightforward so long as the programme has a suitable financial system. On the other hand, (b) requires knowledge about the impact on household behaviour in Nigeria of different methods of distribution and could be the subject of future Operational Research.

Effectiveness
In terms of VfM, changes in the purpose indicators could be used to estimate the number of DALYs (Disability Adjusted Life Years) generated by SuNMaP, thus providing a consistent metric for cost-effectiveness estimates.

PSI[6] estimates that 520 DALYs will be averted[7] for every 470 children aged under 5 sleeping under a LLIN. Therefore, for a change in the indicator “Percentage of all children Under 5 in supported states that slept under an ITN the night before the interview”, we can estimate that a total 776,173 DALYs have been averted in four states by this means. If similar results were to be achieved for the other two indicators in all six supported states, the total number of DALYs averted could be considerable. However, a number of other partners have been involved in the achievement of these results and we do not at present have the information necessary to estimate the individual contribution of SuNMaP.
[6] http://www.psi.org/resources/publications?pub_type=All&field_target_audience_value_many_to_one=All&health_area=All&country=All&field_year_value=&keywords=DALY&language=English
[7] Assuming that a LLIN lasts for 5 years

Without being able to attribute results to the programme and in the absence of information on the other two indicators, we cannot provide any estimate of the cost per DALY averted at this stage in the programme.

Externalities
There is evidence of externalities (that is, effects on individuals/ organisations other than the principal target) being generated by the programme. All of the externalities identified are positive.

## VfM Conclusions and detailed recommendations
### Conclusions
SuNMaP is a well-managed programme in which VfM issues are taken seriously in that a number of measures are taken to reduce operational costs. In addition, financial information is recorded in such a way that the construction of unit costs of inputs and activities is feasible. However, although individual programme managers review their own unit costs, there does not appear to be the routine generation and analysis of unit costs.

DFID’s recent outline of its approach to VfM implies that output indicators should all be factors that are controlled directly by the programme. However, the achievement of a number of the output indicators in the revised log frame require inputs by partners so that attribution continues to be an issue.

Cost-effectiveness could in principle be estimated for SuNMaP by converting all progress on purpose to the common metric of a DALY. In practice, we cannot provide such estimates at this stage for three reasons:
1. We do not have the total expenditure by all partners needed to estimate the cost-effectiveness of all activities or attribute a portion to the DFID funding.
2. We do not have current estimates of two of the indicators.
3. PSI has not developed an estimate of DALYs averted in the case of IPT.

None of this should be seen as a criticism of SuNMaP. The programme has responded actively to DFID’s reporting requirements. However, going forward there are a number of actions that could be taken to facilitate VfM analysis.
### Detailed recommendations
Monitor unit costs
SuNMaP should use their excellent information system to calculate unit costs and monitor them to ensure that there are no unexplained differences. There is little point in monitoring unit costs simply for report. SuNMaP and DFID should consider which unit costs would provide useful management information.

Disseminate information about unit costs to partners
A major reason for monitoring unit costs is to disseminate them to partners. This dissemination can help partners with their own budgeting. By encouraging transparency, all partners, including SuNMaP, may be able to improve their performance.

Review PSI methodology for DALYs in Nigeria
In the example set out in this report, we have used PSI estimates for the DALYs averted as a result of LLIN use by the under fives. DFID should review this methodology to assess whether it is suitable for their VfM analysis on this and other health projects and, if so, commission research to estimate the DALYs averted for the purpose indicator relating to IPT.

Estimate DALYs
When such estimates are available, SuNMaP should report progress against Purpose in DALYs averted as well as by the change in each indicator.

Get information on partners’ expenditure
It is important that there is information about the total expenditures on malaria control. While we recognise that this is no easy matter, neither attribution of the results to DFID funding nor estimation of overall cost effectiveness can be undertaken without it.

Recommendations
- Identify and monitor key unit costs to provide management information
- Improve performance through dissemination of unit costs to partners
- DFID should commission research to estimate DALYs averted for IPT (first assessing whether PSI DALY methodology is suitable for VfM analysis)
- SuNMaP should report progress against purpose in DALYs averted
- Obtain overall expenditure on malaria control in order to determine attribution and overall cost effectiveness of DFID support

# Engagement in new states
DFID has made the decision to extend the programme to four new states over the next few months. PATHS 2 are working in three of the states; PRRINN-MNCH is active in the fourth. The rationale for extending into these states is that SuNMaP should be able to link its malaria control programme activities into mechanisms that will have been established by the ongoing DFID programmes. The review team understand that extension of the SuNMaP programme to 2015 is under consideration. The review team considered the extent of project engagement by considering five questions:

- How much longer should SuNMaP continue to provide support to the present six states if the programme was extended to 2015?
- What is the added value of moving into PATHS 2/ PRRINN states?
- Would moving into GFATM or WB resourced states be a better option?
- Consider moving into poorly performing states?
- How much impact would the new programme have if the DFID SuNMaP programme ends 15-18 months after its commencement?

The team consider that SuNMaP should continue to support the six states up to 2015 (if the programme is to be extended), with a focus on technical support only (thereby reducing overall costs). This should lead to greater sustainability after the programme end.

The review team could see the advantages of moving into PATHS 2/ PRRINN states, in that there were opportunities for cost savings (shared office space, logistics etc), and that good relationships with SMOHs will have been established, thereby reducing the programme set-up times. Against this, the review team considered that there would be considerable overlap of SuNMaP’s strengths (planning, coordination, harmonisation, technical support and training) with those of PATHS 2 and PRRINN-MNCH. Furthermore, PATHS 2 has a focus on reproductive health (which includes antenatal care), and PRRINN a focus on child health. Malaria control is a key element of both areas. It is clear that SuNMaP’s inputs would strengthen both elements; furthermore, SuNMaP support to the states in developing malaria control plans would be of considerable benefit (although there may be some overlap with PATHS 2 system strengthening. Again, it could be argued that the NMCP/SuNMaP training modules could be delivered through the current DFID programmes. If DFID pursue this option, SuNMaP support should be limited, and integrated with the activities of the current DFID programmes.

The review team considered two alternatives: moving into WB or GFATM-supported states, or working in poorly-performing states. If moving into WB/GFATM supported states, SuNMaP support would benefit from the availability of malaria commodities, thereby allowing a focus on technical support – malaria control planning, coordination of activities and training. Moving into poorly performing states would prove challenging, and set-up times would be lengthy. This would prove a costly venture.

Finally, the team concluded that working in four states for no more that 15-18 months would be unlikely to show impact. SuNMaP’s experience has shown that set-up times can take up to 12 months, and improvement (e.g., in developing malaria control AOPs) will not be apparent for at least two years. Hence the review team’s recommendation that this option should be considered only if the programme is to be extended to 2015

Recommendations:
- DFID should consider whether SuNMaP should engage in the four states at all if the programme is not extended to 2015
- SuNMaP’s role should be integrated with the PATHS 2 and PRRIN-MNCH programmes (recognising considerable overlap between current roles and strengths)
- DFID should consider whether extending to DFID-supported stated represents the best value for money

# Annex 1: Terms of Reference
MID TERM REVIEW OF DFID SUPPORT TO NATIONAL MALARIA PROGRAMME (SuNMaP) - 4TH – 15TH JULY 2011
Objective
The objective of this Mid Term Review (MTR) is to provide a clear assessment of the performance and progress with the implementation of the SuNMaP programme. To analyse and assess reasons that explain current indicators of progress and good practice; as well as review performance against progress with recommendations made during the 2010 programme Annual Review. Based on above analysis and assessment of performance and progress, propose recommendations for future effectiveness and impact.
Recipient
The recipients of the work are the Federal Government of Nigeria; State Governments in Kano, Katsina, Niger, Anambra, Ogun, Lagos; DFID Nigeria; and other Development Partners.
Scope of Work
The Review Team will focus its attention on issues of relevance, efficiency, effectiveness, impact and sustainability progress made so far by SuNMaP and make recommendations to enhance programme continued effectiveness in performance and impact. The MTR will take particular account of whether SuNMaP is providing value for money (VfM) and is driven by the achievement of key targets and results in access, equality and quality. The review will seek to address in particular the following:
1. Quantitative and qualitative progress of SuNMaP in respect of agreed programme outputs and purpose.  This will include a full assessment against the revised SuNMaP log-frame milestones and targets as well as progress against the work-plan and the likelihood of the project purpose being achieved.
2. The appropriateness of SuNMaP’s monitoring and evaluation framework and logframe, including whether any assumptions or risks have changed.
3. The appropriateness of SuNMaP’s approach, strategic direction, and risk mitigation strategies, including any strategies relating to the post political elections period.
4. Review progress with SuNMaP’s work with the commercial sector, including its revised strategic approach and the management of its commercial sector programme.
5. Review effectiveness of coordination between SuNMaP, other DFID health programmes, and other development partners working at the Federal level and in supported States.
6. Review effectiveness of management arrangements and internal coordination within the programme.
7. Review economic, financial and budget processes; in particular, specific Value for Money (VfM) recommendations and issues as suggested below:
1. Break down input and out put costs to show how money is being spent,
2. Develop benchmarks and compare costs of different inputs and outputs, (for, both service provider costs and commodities),
3. Identify efficiency savings by service providers,
4. What are the trends in efficiency over time?
5. Examine the efficacy of different outputs in contributing to project purpose and goals,
6. Is there evidence of spin off?  Broader benefits? Possible longer-term impacts?
7. In scoping positive and negative project scenarios, assess how they affect the risk of achieving good VfM for the project?
8. Specify any considered contractual changes needed and set out specific recommendations on improving VfM.
To review extent of project engagement in new States, (Yobe, Jigawa, Kaduna and Enugu) where PATHS 2 and PRRINN-MNCH operate; as well as extent of integration with these programmes for malaria control and other health systems interventions in Nigeria
 Method
1. The Mid Term Review team will be made up of three independent consultants, a representative from other development partners, a representative from the Federal Ministry of Health (NMCP), and/or State Ministries of Health and DFID staff.
2. Review of relevant documentation and programme log frame (see list below for background reading requirements).to be made available to Consultants by SuNMaP, at least a week before commencement of MTR exercise.
3. Briefing of Review team by DFID Health Adviser and by SuNMaP senior management team; on the first day of commencement of review exercise.
4. Visits to existing SuNMaP States (Kano, Katsina, Anambra, Niger, Ogun, Lagos), and new scale up States (Yobe, Zamfara, Kaduna and Enugu); as well as work within Abuja
5. Interviews and meetings with SuNMaP staff and key stakeholders, such as Government Health officials, NMCP Director General and Senior Management team, other DFID programmes (particularly PATHS 2, PRRINN-MNCH and HERFON), other development partners, the commercial sector, and civil society organisations.
6. Presentation of draft findings of review to SuNMaP, Government, other partners and DFID as stated in review time lines for debrief.
 Reporting and Outputs
The MTR team leader will be required to produce the following reports:
a.     SuNMaP Mid Term Review Report
b. Completed DFID Review (excel) form. Deliverable	Timing
Initial presentation and debrief of key findings and recommendations of the mid term review to Government, other partners, SuNMaP and DFID staff	Friday 15th July, 2011
Draft SuNMaP MTR Report and completed review excel template form submitted to DFID	Friday 22nd July 2011
Final agreed mid term review report submitted to DFID	Friday 29th July 2011

Timing
 The mid term review will take place in country from Monday, 4th July to Friday, 15th July 2011; and produce finalized review reports not later than Wednesday, 29th July 2011.
 It is currently estimated that this consultancy will require a total of 21 days for the first two independent consultants; and about 14 - 16 days for the third consultant. The tasks, their duration and timing are:
- 3 days prior to commencement of the assignment for reading, examination and analysis of key review documentation; and 2 days for third consultant.
- 12 full working days in Nigeria for the main review mission (excl. Sunday); possibly 10 days for third consultant.
- 6 days after completion of the mission to complete draft deliverables and follow up editing (2 days where necessary for third consultant).
DFID Co-ordination
The overall coordinator for this review is Ebere Anyachukwu, Health Adviser, who will be supported by David Ukagwu, Programme Officer - DFID Nigeria
SUNMAP Mid Term Review Team Members
1. One International Consultant and Team Leader: The team leader will have competencies in public health with specific expertise in malaria control. S/he should have relevant experience working in Nigeria, and will have overall responsibility for delivery of the outputs of this review.
2. A second international consultant who will have competencies in private sector development and/or market development. S/he should have relevant experience working in Nigeria or Africa, and will have responsibility for reviewing SuNMaP’s revised work plan with the commercial sector as well as any other tasks allocated by the team leader.
3. A third consultant who will have competencies in health economics and cost effectiveness/ value for money assessments of development interventions.. S/he will join some parts of the review (not full time) and will have responsibility for the value for money assessment aspects of the review.
4. One or two representatives of NMCP and the Federal or State Ministries of Health – TBC
5. One or two representatives of other development partners such as the World Bank, World Health Organization and/or USAID -TBC
6. Ebere Anyachukwu, DFID Health Adviser
7. Gill Rogers ,DFID Private Sector Development Adviser (p/t) - TBC
8. Susan Elden, DFID Kano Health Adviser (p/t)
9. Jane Miller, DFID Human Development team leader (p/t)
10. Mick McGill, DFID Programme Manager (p/t)
11. David Ukagwu, DFID Programme Officer
  Logistics and Planning for the mid term review will be provided by SuNMaP and supported by David Ukagwu, Programme Officer, Human Development, DFID Nigeria.
Background
The £50m DFID Support to National Malaria Programme (SuNMaP) was started in April 2008. Its purpose is to strengthen delivery of Nigeria’s Roll Back Malaria Control Programme. It is scheduled to run for five years and is currently operating in six States – Lagos, Kano, Niger, Katsina, Ogun, and Anambra.
The programme approach includes: building capacity at Federal, State and local levels to develop and implement plans for effective malaria control; supporting FMOH to harmonize efforts of donors and funding agencies around national plans, policy and priorities; and direct support to the delivery of effective malaria prevention and treatment through the public and private sectors. This approach will require engagement with Government partners at all levels, as well as extensive work with the commercial sector.
The purpose of the programme is “To strengthen delivery of Nigeria’s National Malaria Control Effort”. It has the following six outputs:
1. National, State, and LGA capacity for policy development, planning and coordination are improved
2. All agencies’ support for the malaria sub-sector at federal, state and local levels are effectively harmonized
3. Population coverage of effective measures for the prevention of malaria is increased
4. Access of the population to effective treatment for malaria is improved
5. Community awareness and demand for effective malaria treatment and prevention are improved
6. Operational research into key areas of prevention and treatment provides the evidence base for more effective strategies
18.     Nigeria has started an unprecedented effort, backed by DFID, USAID, the World Bank, The Global Fund, UNITAID/UNICEF and other partners, to distribute 2 insecticide treated bednets to each Nigerian household (totaling 63 million bednets) by 2010. SuNMaP is providing technical and coordination support; and has contributed an initial 2 million nets to this effort. As at April 2010, 19 million LLINs had been distributed in 11 Nigerian States.
With the scale up of DFID’s Operational Plan, there are plans to extend the spread and activities of SuNMaP to integrate more into other Health systems strengthening activities and Maternal and New Born Child (MNCH) health care interventions in other DFID States. SuNMaP would therefore need to work out harmonious integration with other DFID programmes (e.g. PATHS 2 and PRRINN-MNCH) in such States as Yobe, Jigawa, Kaduna and Enugu; to achieve the required programme scale up.
Required background reading
- SUNMAP Quarterly reports and Year 2 report.
- SUNMAP Updated Strategic approach papers for each output and cross-cutting themes
- SUNMAP Programme Memorandum
- SUNMAP Programme logframe in revised DFID format
- SUNMAP self assessment against logframe using DFID annual review excel format
- Post inception phase review report of SUNMAP Commercial sector support interventions
- SUNMAP 2009 inception review report & 2010 Annual Review Report
- SUNMAP Monitoring and Evaluation framework’ including baseline and progress report
- Results of post bednet campaign surveys
- SUNMAP workplans for 10/11 and 11/12
- National/State Malaria Control Programme Strategic Plan and operational plans
- Year 2009 Audited Report  & Records/Analysis of SuNMaP’s Procurement so far (for third Consultant looking at VfM)

# Annex 2: People met

Place	Person Met	Job Title
NMCP in Abuja	Dr. David Durojaiye	Head of Prog. Management Unit
	Mrs. Felicia Ewoigboikhan	Head of ACSM Unit
	Mrs. Amajoh Chioma	Head of IVM Unit
	Mrs. G. Chukwuma	Head of PSM Unit
SunMaP Abuja	Maxwell Kolawole	Programme director
	Steve Cooper	Deputy programme director
	Ebenezer Sheshi Baba	Programme technical director
	John Dada	Communications specialist
	Adejoke Aaregbesola	Finance manager
	Nnana Ikwuo	Deputy finance manager
	Marian Ekhator	Office manager
	Dr Phillip Bassey	Senior health systems expert
	Emmanuel Adegbe	Senior M and E officer
	Essien Esseinawan	Programme assistant
	Evelyn Patrick	Senior clinical expert
Federal MoH Abuja	Dr Babajide Coker	National coordinator, DPH
	Dr Tim Obot	NMCP
PATHS2, Abuja	Kaw Lages
World Bank, Abuja	Dr Oluwnole Odutolu
	Marian Olaide Jagun
CCM GFATM, Abuja	Ope Abegunde	Programme manager
DFID Abuja	Sarah White	Human development team leader
	Ebere Anyachukwu	Health adviser
	Susan Elden	Health adviser, Northern Nigeria
	Christopher Hindley	Deputy head, DFID Northern Nigeria
	Oiza Nicholson	Deputy programme manager, Governance and Development team
	Mick McGill	DFID programme manager
	Tony Gardener	DFID commercial adviser
	Esther Furman	DFID results adviser
Clinton Foundation, AMFm	Joshua Chu
Abuja (other)	Dr. Baley Kassau	USAID
	Ernest Nwokolo -	Malaria manager, SFH
	Sunil Mehra	Executive director (UK)
	James Tibenderana	Africa technical director
	Dr Sylvia Meek	Technical director (UK)
Lagos at the SMOH	Dr Olugbile	Permanent Secretary
	Dr Taiwo	Director Disease Control
	Dr Bakare	Lagos State Malaria Control Programme Manage
	Dr Layeni-Adeyemi	Chairperson Lagos Advocacy Communication and Social Mobilisation Commitee
Lagos (SuNMaP Partners)	Dr Tolu Arowolo	WHO Zonal Malaria Programme Officer South West
	Dr Tosin Kuti/ Dr Audu Ansalem	FHI Malaria Focal Person,
	Dr Yinka Goodman	SFH Regional Coordinator
Lagos (other)	Laja Odunuga	SuNMaP Technical Malaria Manager (Lagos State
	Abidemi Okechukwu	SuNMaP Senior Technical Malaria Officer (Lagos State)
	Bimbola Olutola	SuNMaP Operations Officer (Lagos State)
	Gabriel Akuegbo	SuNMaP Commercial Sector Manager
	Oghenovo Ugbebor	SuNMaP Commercial Sector Analyst
	Monday Egume	Director, GRID
	Sarah Agah	Insight Advertising
Anambra	Prof Amobi Linus Ilika	Hon Commissioner
	Lady (Mrs) Evelyn Magulike	Permanent Secretary
	Mrs J. Okedo	Director, Nursing Services
	Dr Obi Ezeaku	Rep Director, PHC (but Programme Manager, HIV/AIDS
	Anthony Ogoegbunam	Special Assistant to Hon Commissioner
	4 others from the SMoH	Reps from PRS, Medical & Pharmaceutical Depts
	Dr (Mrs) Rose Onyibe	State Rep
	Gbofyen Diden	State Consultant
	Dr (Mrs) Justina Ifeorah	Zonal Manager, SE
	Dr Romanus Nriagu	State Chairman/Programme Manager
	Dr Denis Aribodor	State Secretary/Head of Dept
	Dr Douglas Nkemdilim	State Chairman/CMO
	Names to be sent bcob Monday 11th July	Included Deputy President General, Secretary, PRO, Health Committee Chair & Women Leader)
	Dr Joe A. Oranuba	Head/Project Manager
	Mrs Edith A. Ike	Logistics Officer
	Mrs Virginia N. Onwuvunka	Training Officer
	Chibuzo Oguoma	Technical Malaria Manager
	Isaac Adiele	Operations Officer
SuNMaP, Kano State	Dr Gaji Alkali	Technical manager
	Olatunde Oladimeji	Operations officer
	Okoh Abu Michael	Accounts officer
	Tarauni	LGA
	Hasiya Rbaiu	In charge
	Talatu Baia Bichi	In charge
	Abdullahi Manya	Health educator
	Maryam Musa	HOD
	Zulaitu Mahd	Maternal and child health coordinator
	Abdullahi Sa’idu	Local immunisation officer
Staff and patients at Saye PHC, Lamba PHC, Kano State,	Sani Madaki	Zonal director
	Halilu Samail Beli	Zonal Administrative secretart
	Farouk Bashir Yakasai	Zonal head of Nursing
	Dahiru Abdu	Zonal chief community health officer
	Dr Donaefus Nwikedi	Chief medical officer
	Musa Aliyu Bichi	Pharmacist
Bichi Hospital, Kano State	Sani Madaki	Zonal director
	Halilu Samail Beli	Zonal Administrative secretart
	Farouk Bashir Yakasai	Zonal head of Nursing
	Dahiru Abdu	Zonal chief community health officer
	Dr Donaefus Nwikedi	Chief medical officer
	Musa Aliyu Bichi	Pharmacist
	Amal Jaarat Shelley	Society for Family Health
SMoH, Kano	Dr Alhaji Gambo	Permanent secretary
	Dr Isah Baca	SMoH planners
	Dr Al-Mukata Ademu
	Gati Sule
	Alhaj Kademi	State malaria programme manager
SMCP master trainers, Kano	Pharm Salisu Hashim	Pharmacist
	Bilkisu Umar Bayero	Nurse tutor, Kano school of nursing
	Al-Muktar Adamu	Sir Sunusi General hospital
	Muna Adamu	Nurse/midwife
SMOH, Kano	Pharm Ghali Sule
ASCM representatives	Hadiza Habib	DD Ministry of information
	Rabi Bature	Reporter, Trump publishers
	Yusuf Yau	ARTV
	Sanusi Uba	Coord Mosquito Centre
	Fatima Aliyu	IHVN Kano
	Abdullaziz Bagara	Community consultant
	Sani Ahmed Rufai	SMoH
	Ahiru Mohd	Principal nursing officer
SuNMaP office Minna, Niger state	Kolo Yakubu	SunMaP senior technical malaria officer
	Momoh Abdulmalik	SuNMaP Niger administration/ accounts officer
Niger SMoH	Dr Usman Mohammed	Director Public Health
	Rakiya Datti	Deputy Director, Public Health/Environment
	Dr. Ibrahim Idris	Deputy Director, Public Health/Disease Control and State
	Mercy Dawab	State Malaria Control Program Coordinator
	Bilkisu Ibrahim	Deputy State Malaria Control Program Coordinator
	Dr. Olukosi	Medical Director, Standard hospital, Minna, Niger State
	Tajudeen Badmus	Life Care Patent Medicine Vendor
	Blessing Stephen	Association for Reproductive and Family Health
	Umar Sanda	HERFON, Niger
	Amina Abdulkadir	FOMWAN, Niger
	Rev. Sani Barde	CHAN, Niger
Katsina state SuNMaP Katsina state office	Mumammed Basheer Yahya	Senior technical malaria officer
	Fatima Garba	Administrative officer
Katsina SMoH	Dr Mohammed Qabasiyu	Permanent Secretary
	Dr Idriss Halliru	Director of public health
	Junaidu Murnai	IVM officer
	Yusufu Danjuma	RBM manager
	Parm Adamu Barchi	Director of pharmacy
KSPHCDA	Dr A T Hamzah	Director
	Dr Muawiya Ahmed	Chairman
	Dr Usman Matazzu	PPRINN state team manager

# Annex 3: Itinerary

Third SuNMaP Annual / Mid term Review Visit Schedule (4th - 15th July 2011)

Date	Loc	Time	Schedule	Venue	Participants from SuNMaP and stakeholders	Participants from review team	Output
Monday, 4th July	ABUJA	9:00am	Objectives of the annual review	SuNMaP Abuja Office	Represenatives of Programme Core Partners( Malaria Consortium, Health Partners International & GRID Consulting ) Dr Kolawole Maxwell - SuNMaP Programme Director Steve Cooper - SuNMaP Deputy Programme Director Dr. E S. Baba - SuNMaP Programme Technical Director Gabriel Akuegbo - SuNMaP Commercial Sector Manager Mr. John Dada - SuNMaP Programme Communication Specialist Essien Essienawan - SuNMaP Programme Assistant	All	All
		11:00am	Overview of SuNMaP * Approaches and Progress to date – logframe achievements and beyond * Overview of key plans for year 4 of implementation * Key risks and challenges * VFM	SuNMaP Abuja Office
		2:00pm	NMCP (National Malaria Control Programme) Meeting * National Coordinator (NC) Courtesy Meeting * NC and Unit Heads	NMCP Office	Dr. Babajide Coker - NMCP National Coordinator Dr. David Durojaiye - Head of Prog. Management Unit Mrs. Felicia Ewoigboikhan - Head of ACSM Unit Dr. Ntadom - Head of Case Management Unit Dr. Bala Audu - Head of M&E unit Mrs. Amajoh Chioma - Head of IVM Unit Mrs. G. Chukwuma - Head of PSM Unit	All	All
		4.00pm	Team Meeting *Agreeing field visits tasks / itinerary and breaking into teams	SuNMaP Abuja Office	Review Team	All
Tuesday, 5th July		9:00am	Team Meeting	SuNMaP Abuja Office	Review Team	All
		10.00am	Meeting with Federal Ministry of Health (FMOH)	Director Public Health Office, FMOH	Dr. Kabir Director of Public Health, FMOH	All	All
		11.00am	Meeting with NMCP SST (LLIN State Support Team)	NMCP Office	LLIN campaigns Mrs. Amajoh Chioma - Head of IVM Unit SST Coordinators - Dorothy Onyango Technical Advisor - Dr. Akinpelumi Demand Creation Advisor - JKT Logistics Advisor - Emma Ogwuche NMCP Team Leaders ( Emma Obi, Akilah)	All	3
		12.00pm	Detailed meetings with heads of Units in NMCP		Dr. David Durojaiye - Head of Prog. Management Unit Mrs. Felicia Ewoigboikhan - Head of ACSM Unit Dr. Ntadom - Head of Case Management Unit Dr. Bala Audu - Head of M&E unit Mrs. Amajoh Chioma - Head of IVM Unit Mrs. G. Chukwuma - Head of PSM Unit	All	All
		4.00pm	Meeting with former NMCP – Long Term TA (LTTA) on Coordination	NMCP Office	Dr. Tunde Ipaye	All	2
		6.25pm	Travel to Kano			Team B
STATE VISITS - Team B (Kano, Katsina, Jigawa & Niger)
Wednesday, 5th July	KANO	11.00am	PHC	Community	PHC Staff: Saye PHC, Lamba PHC Bichi LGA, (2) Kauyen Alu peri-urban or Unguwa Uku, urban PHC in Tarauni LGA (3)Dalal peri-urban PHC or Yadakunya rural PHC in Ungogo LGA	Team B	All
		12.00pm	Community	Community	PMVs and CCGs joint meetings within facility settings	Team B	1, 2, 3, 4, 5
		2.00pm	Hospital	Facility	Hospital staff : Gen Hosp Bichi, semi-urban secondary facility	Team B	3
		3:00pm	Meeting with Kano State Malaria Control Programme (SMCP)	SMCP Office	Alhaji Baffah Kademi - State Malaria Programme Manager	Team B	All
		4:00pm	Updates of Year 3 ProgrammeImplementation	SuNMaP office	Gaji Alkali - SuNMaP Technical Malaria Manager Dr Osita Oknokwo SuNMaP State Technical Malaria Officer Tunde Oladimeji - SuNMaP Operations Officer	Team B	All

Thursday, 7th July	KATSINA	7.00am	Travel to Katsina			Team B
		11.30 am	Meeting with SuNMaP Katsina team	SuNMaP Katsina Office	Gaji Alkali - SuNMaP Technical Malaria Manager Basheer Yahya - SuNMaP Senior Technical Malaria Officer	Team B	All
		12.30 pm	Meeting with Director Public Health/ State Malaria Control Programme (SMCP) team	SMOH	Dr. Idris Haliru - Director of Public Health, SMOH Mr. Danjuma - State Malaria Programme Officer	Team B	All
		2.00 pm	Meeting with the Permanent Secretary (PS) SMOH	SMOH	Dr. Kabasiyu - PS, SMOH	Team B	All
		3.00 pm	Meeting with State Primary Health Care Agency (SPHCDA)	SPHCDA	- Executive Secretary, SPHCDA	Team B	All
		4.00pm	Joint Partners Meeting * Programme for Reviving Routine Immunisation in Northen Nigeria - Maternal, Neonatal and Child Health (PRRINN - MNCH) * Girls Education Programme (GEP) * Save the Children UK (SCU)	SuNMaP Office	- State Manager PRRINN - MNCH Malam Yahaya Maiyama - GEP Karina Lopez - SCU	Team B	All
		5.00 pm	Return to Kano			Team B
Friday, 8th July	KANO	9.00am	Joint Partners Meeting	SuNMaP Kano Office SMoH	STL PATHS2- Dr Abubakar Izge SFH Representative Bilkisu Abubakar IHVN Malaria Coordinator- Fatima Aliyu	Team B
		10.30 am -12.30	Meeting with State Ministry of Health (SMOH) Commissioners and Directors		- Honourable Commissioner for Health Alhaji Tajuddeen Gambo - Permanent Secretary Dr Dayyabu Muhammad - Director Primary Health Care Alhaji Tijjani Nasidi - Director Pharmaceutical Services Dr Shehu Abdullahi -Asst Director Alhaji Tijjani Umar Director- Nursing Services, MOH Kano Alhaji Bappah Mahmood Kademi-State Malaria Programme Manager	Team B
		12.30 am - 2.00 pm	Joint meeting with SuNMaP Programme Implementing Partners (PIPs)	SuNMaP Kano Office SMoH	FOMWAN Reps-Zainab Suraj HERFON Reps- Amina Yahyadeen	Team B
		3.00pm - 4.00pm	Meet with Technical Working Group Operational Planning	SuNMaP Kano Office SMoH	Operational Planning Team	Team B
		4.00-5.00pm	Meeting with Kano CB/training team		Selected Team Master Trainers	Team B
Saturday, 9th July		8.30am	Return to Abuja			Team B

Monday, 11th July		7:00am	Review team Departs Abuja for Minna
	NIGER	10:00am	Meeting with SuNMaP Niger team	SuNMaP Niger Office	Kolo Yakubu- SuNMaP Senior Technical Malaria Officer	Team B	All
		11:00am	Meeting with top official of Niger State Ministry of Health	Commissioner's Office, New secretariat Complex , Minna.	- Hon. Commissoner of Health and Hospital services Dr Ibrahim B. Chindo - Permanent Secretary MoH Dr Mohamed. B Usman - Director Public Health MoH Mrs Mercy Dawaba - State Roll Back Malaria Coordinator	Team B	All
		12:00pm	Meeting with Roll Back Malaria unit, SMOH	Room 27, Old Secretariat Complex, Minna.	Mrs Mercy Dawaba - State Roll Back Malaria Coordinator Hajia Bilkisu Ibrahim - Deputy Roll Back Malaria Coordinator Daniel Iliya - Roll Back Malaria Unit Staff Amina Zimro - Roll Back Malaria Unit staff	Team B	All
		2.00pm	Joint Partners Meeting *Association for Reproductive and Family Health (ARFH) *World Health Organization (WHO)	SuNMaP Niger Office	Blessing Stephen- ARFH State Programme Officer Dr Lynda Ozor- WHO Zonal Malaria Programme Officer	Team B	All
		2.30pm	Field Visit -Gwari Road Clinic (ANC/Routine systems)	SuNMaP Niger Office/SMCP	Interract with ANC clinic staff on SuNMaP routine system support	Team B
		3.00pm	Joint Meeting with SuNMaP Programme Implementing Partners * CHAN * FOMWAN * HERFON	SuNMaP Niger Office	Rev Yusuf Barde -CHAN Amina Abdulkadir- FOMWAN Umar Sanda- HERFON	Team B	5
		4.00pm	Debriefing Meeting	SuNMaP Niger Office	Kolo Yakubu- SuNMaP Senior Technical Malaria Officer	Team B	All
		5:00pm	Review Team departs Niger for Abuja
STATE VISITS - Team A (Ogun, Lagos, Anambra & Enugu)
Wednesday, 6th July	LAGOS	8.00am	Travel to Lagos			Team A
		10.00am	Meeting with SuNMaP Lagos team	SuNMaP Office Lagos	Laja Odunuga - SuNMaP Technical Malaria Manager Abidemi Okechukwu - SuNMaP Senior Technical Malaria Officer Bimbola Olutola - SuNMaP Operations Officer	Team A	All
		10.45am	Meeting with SuNMaP Commercial Sector Staff	SuNMaP Office Lagos	Gabriel Akuegbo - SuNMaP Commercial Sector Manager Oghenovo Ugbebor - SuNMaP Commercial Sector Analyst Monday Egume - Director, GRID	Team A	3 & 4
		11.30am	Meeting with Commercial Sector Partners	SuNMaP Office Lagos	Gabriel Akuegbo - SuNMaP Commercial Sector Manager Oghenovo Ugbebor - SuNMaP Commercial Sector Analyst Monday Egume - Director, GRID Mr. Martines Awofisayo - Harvestfield Mr. Ogunleye - Teta	Team A	3
		1.30pm	Meeting with SMOH Commissioner and Directors	Lagos State Ministry of Health	Dr Olugbile- Permanent Secretary Dr Taiwo - Director Disease Control Dr Bakare - Lagos State Malaria Control Programme Manager Dr Layeni-Adeyemi - Chairperson Lagos Advocacy Communication and Social Mobilisation Commitee	Team A	All
		3.00pm	Meeting with Insight (Provider of Generic Marketing)	SuNMaP Office Lagos	Gabriel Akuegbo - SuNMaP Commercial Sector Manager Oghenovo Ugbebor - SuNMaP Commercial Sector Analyst Monday Egume - Director, GRID Sarah Agah - Insight Dawodu - Insight	Team A	All
		4.00pm	Joint meeting with partners * World Health Organisation (WHO) * Family Health International (FHI) * Society for Family Health (SFH)	SuNMaP Office Lagos	Dr Tolu Arowolo - WHO Zonal Malaria Programme Officer South West Dr Tosin Kuti/ Dr Audu Ansalem - FHI Malaria Focal Person, Dr Yinka Goodman - SFH Regional Coordinator	Team A	All

Thursday, 7th July	ANAMBRA	8.00am	Travel to Enugu( flight) > drive to Awka			Team A
		10.00 am	Meeting with SuNMaP Anambra Team	SuNMaP Office Anambra	Chibuzo Oguoma - SuNMaP Technical Malaria Manager Issac Adiele - SuNMaP Operations Officer	Team A	All
		11.00 am	Meeting with State Malaria Control Programme Unit	SMCP Office	Dr. Joe Oranuba - State Malaria Project Manager Mrs Edith Ike - Logistics Officer	Team A	All
		12.00 am	Meeting with Commissioner and Directors	SMOH	Prof. Ilika - Commissioner for Health Lady (Mrs) Evelyn Magulike - Permanent Secretary Dr CJ Okoye - Director Primary Health Care & Disease Control	Team A	All
		2.00 pm	Meeting with SuNMaP Programme Implementing Partners * HERFON * CHAN	SuNMaP Office Anambra	Dr Romanus Nriagu, Dr. Aribodor Dennis - HERFON Dr Douglas Nkemdilim - CHAN	Team A	3 & 5
		3.00 pm	Joint meeting with Partners * GHAIN/FHI (GF8 PR), * WHO * UNICEF	SuNMaP Office Anambra	Dr (Mrs) Justina Ifeora - GHAIN / FHI Dr (Mrs) Rose Onyibe - WHO Gbofeyin Diden - UNICEF	Team A	All

Friday, 8h July	ANAMBRA	8.00am	Travel to an LGA	Visit Oyi LGA communities: Nteje, Nkwele Ezunaku	Chibuzo Oguoma - SuNMaP Technical Malaria Manager Issac Adiele - SuNMaP Operations Officer	Team A
		10.00 am - 3.00 pm	Meetings with SHC & PHC staff and PMVs	Select persons from 8 LGAs and host in Awka	Chibuzo Oguoma - SuNMaP Technical Malaria Manager Issac Adiele - SuNMaP Operations Officer	Team A	1

Saturday, 9th July		8:50am	Travel to Abuja			Team A

Both Teams Back to Abuja
		8:00am	Travel to Abuja (From Ogun, via Lagos airport)
Tuesday, 12th July	ABUJA
		12.00pm	Meeting with Crown Agents	Crown Agents Office	Sandra Odogwu- Senior Procurement Manager Jiru Bako -
		2.00pm	Meeting on AmFM	SuNMaP Office Abuja	Joshua Chu - Clinton Foundation James Timbederana - MC Director of Case Management Dr Kolawole Maxwell - SuNMaP Programme Director Steve Cooper - SuNMaP Deputy Programme Director Dr. E S. Baba - SuNMaP Programme Technical Director		4
		3.00pm	Further discussions with SuNMaP / NMCP	SuNMaP Office Abuja	As required
Wednesday, 13th July		9.00am	Review SuNMaP’s Programme management *Organisation/Administrative and Finance discussion	SuNMaP Office Abuja	Sunil Mehra - MC Executive Director Bryan Haddon - HPI Chair Ike Osakwe - GRID Managing Director Kolawole Maxwell - SuNMaP Programme Director Steve Cooper - SuNMaP Deputy Programme Director		All
		12.00pm	Joint meeting with partners * USAID / MAPS * World Bank (WB) * WHO * UNICEF * Global Fund Principal recipients (NMCP, Society for Family Health (SFH), Yakubu Gowon Centre (YGC))	SuNMaP Office Abuja	John Quinley / Dr. Baley Kassau - USAID Wole Adeusi / Uwem Inyang - MAPS Dr. Wole Odutolu / Mariam Jagun- WB Dr Lynda / Dr Cephas - WHO Dr. Gemade - UNICEF Mrs. Ope Abegunde - GF Manager NMCP Ernest Nwokolo - SFH - YGC		2
		2.00pm	Meeting with SuNMaP’s Programme management *Commercial Sector	SuNMaP Office Abuja	Sunil Mehra - MC Executive Director Ike Osakwe - GRID Managing Director Kolawole Maxwell - SuNMaP Programme Director Steve Cooper - SuNMaP Deputy Programme Director Monday Egume - Director, GRID Gabriel Akuegbo - SuNMaP Commercial Sector Manager M4P Consultants		All
		3.30pm	Meeting with SuNMaP Programme Implementing Partners	SuNMaP Office Abuja	Dr. Soyinka / Dr Ben Ayene - HERFON Edward Egede - CHAN Medipharm Mairo Mandara - FOMWAN Patrick Kwakfut - CHAN Funke Fagbemi - CCPN		All
Thursday, 14th July		9.00am	Review Team report writing	SuNMaP Office Abuja
		2.00pm	Debrief with SuNMaP team	SuNMaP Office Abuja	SuNMaP technical Staff in Abuja & Representatives from the States
Friday, 15th July		11.00am	Debrief with DFID and Stakeholders	DFID Office Abuja	DFID, SuNMaP technical Staff in Abuja & Representatives from the States, Stakeholders
		1.00pm	Report writing

			Team A Bruce Mackay Ebere Anyachukwu Ebenezer Baba Edward Idenu Tim Obot		Team B John James Ivy Paylps Susan Eldon Sarah White Oiza Nicholson Steve Cooper

# Annex 4: Reference documents

SunMaP documents:
- Programme strategy for improving access to malaria diagnosis and treatment SuNMaP June 2011
- Updated strategy for building capacity for malaria control SuNMaP June 2011
- Updated strategy for promoting harmonisation and coordination in malaria control; SuNMaP June 2011
- SuNMaP quarterly reports 2010 and 2011
- SuNMaP year three plan and budget (2010)
- Programme relevant data by states June 2011
- Interim commercial sector strategy
- Updated commercial sector strategy
- NMCP/SuNMaP capacity building training materials (14 modules). NMCP, 2010
- How to train Management and planning
- Case management of malaria (hospitals, and PHC level)
- Programme state malaria control plans 2010 and 2011
- Self Assessment Value for Money Report for DFID Mid Term Review
- Support to National Malaria Programme: Updated Strategy for Providing Evidence for Malaria Control;
- Availability and cost of mosquito nets, ITN and LLIN in the commercial market in Nigeria Report on the first assessment
- Survey reports of the programme including retail outlet

Nigeria LQAS survey 2010: preliminary report: NMCP and World Bank. PHSS, 2010
DALY Brief :DALY Calculation for Malaria PPT (ACT) & Rapid Diagnostic Kit (RDK)

DALY Brief: DALY Calculation for Long Lasting Insecticide Nets (LLIN)

Support to National Malaria ProgrammeMAKING MARKETS WORK FOR LLINs IN NIGERIA: Market Analysis: Harald Bekkers, Md. Rubaiyath Sarwar, Fazle Razik, Edward Offor

PROGRESS & IMPACT SERIES Number 3. September 2010 Saving Lives with Malaria Control: Counting Down to the Millennium Development Goals

Federal Republic of Nigeria, 2006 Population and Housing Census POPULATION DISTRIBUTION BY AGE & SEX (STATE & LOCAL GOVERNMENT AREA)

DFID’s Approach to Value for Money (VfM)

Operational Plan 2011-2015
DFID NIGERIA

Malaria Indicator Survey 2010 Preliminary Report

National Population Commission Federal Republic of Nigeria
# Annex 5: Value for Money
Value for Money: what it is and how it can be used
DFID[8] has defined Value for Money (VfM) as “maximising the impact of each pound spent to improve poor people’s lives”. At its most strategic level, Value for Money analysis is concerned with assessing the value of the impact of a programme with the cost of the inputs required to deliver that impact. The greater the ratio of impact to cost, the better VfM the programme represents. So, for example, if the goal of the programme is to reduce infant mortality, the lower the cost of each life saved the better the VfM of the programme.
[8] DFID (2011)

For a Mid-Term Review, it is also useful to consider the intermediate processes required to transform inputs into final impact. Figure xxx.1 demonstrates this process in terms of the project log frame.

Figure1: Programme Process
While the overall VfM refers to cost-effectiveness (the relationship between inputs and goal), we can identify some intermediate steps that are of interest. These intermediate steps are commonly known as:
- Economy: minimising the cost of inputs or activities;
- Efficiency: maximising the output obtained from inputs/activities;
- Effectiveness: maximising the effect of outputs on the purpose.

Analysis of each of these intermediate steps can provide useful management information to monitor and improve programme performance.

Economy can be assessed by calculating the unit costs of inputs (drugs, nets) or activities (training courses). By tracking unit costs of activities over time, the extent to which experience can result in economy gains can be assessed. Comparison of unit costs in different places within the programme (across states, for example) the performance of local teams can be judged or special factors affecting the costs of delivery can be identified. Comparing unit costs on an international level can be a useful benchmarking exercise. Finally, sharing information on unit costs with other stakeholders can both help in developing budgets and contribute to a shared awareness of the cost environment resulting in a better use of resources by all stakeholders.

Efficiency can be assessed by calculating the unit cost of achieving the output as measured by the indicator.

The major difficulty encountered in the assessment of efficiency is in the question of attribution. For example, one of the Output 5 Indicators for SuNMaP is “Proportion of women in child bearing age in supported states who know the preventive benefits of LLIN”. However, SuNMaP was not the only partner in the supported states involved in communicating the benefits of LLINs (long-lasting insecticidal nets) and it seems unlikely that all of the increased awareness could be attributed to SuNMaP. If we are interested in the efficiency of the DFID expenditure, we need to find some way of estimating the relative importance of that expenditure compared with that of other partners. One way of attributing the proportion for which DFID was responsible would be to assume that this effect was relative to the proportion of total expenditure on communications. Of course, some partners’ expenditure may be used more efficiently than others but the proportion of expenditure would give us a place to start.

Effectiveness measures face many of the same difficulties of attribution as do measures of efficiency. However, for many health programmes the relationship between programme outputs and the purpose is based on technical relationships that are widely reported in the literature[9].
[9] See, for example, WHO-CHOICE, http://www.who.int/choice/en/ and Eisele et al (2010).

Cost-effectiveness measures rely on the ability to attribute changes in the goal indicators. However, as with the relationship between output and purpose indicators, there is often a technical relationship between changes in purpose and goal indicators. Therefore, in principle, progress against the purpose indicators can provide information about the likelihood of achieving the goal by continuing programme activities.

An important issue to be resolved in the analysis of VfM of development programmes is that of point of view to be used. Are we concerned only with the VfM to be obtained from DFID expenditures? Or do we want to include expenditures by other partners? Given that the goal of development programmes is to support the people of the recipient country, there is a strong argument for including at least the resources contributed by the Nigerian people. In addition, it would be helpful to be able to assess the overall VfM of the efforts of all partners. Indeed, one of the objectives of DFID’s VfM approach is “to improve the VfM of all aid”.

Calculating VfM components in SuNMaP

Availability of costs and forecasts
SuNMaP has developed a management information system that records expenditure by outputs, activities and key inputs, and expenditure against outputs is routinely reported. At the strategic level, the SuNMaP Workplans and Budgets are produced annually and these plans always review the actual against planned expenditures of the previous year, although it is not clear what purpose these reviews serve. The workplan budgets are constructed on the basis of detailed budgets of activities planned at national and state level. Unit costs are not routinely extracted to provide management information for the Senior Management Team, although individual Programme Managers calculate specific unit costs for their own budgetary and monitoring purposes. The MTR Team tested the ability of this system to provide information on unit costs by requesting the unit costs of a sample of items and the results of this exercise are reported below.

Availability of information to understand the effectiveness of outputs to deliver results
For Outputs 3, 4 and 5, this information is available for many – though not all - of the indicators. This information is based on international research on the efficacy of various malaria control instruments and the MTR Team were told that this information was used to ensure that the relationship between output, purpose and goal indicators was consistent. However, these relationships are not routinely used to interpret data on output, purpose and goal indicators. Data on the indicators are gathered through a variety of survey instruments and it is planned that “(A)ll output data will be captured in an overall SUNMAP data base or information system so that any information of output performance can be made available to implementation managers at any time.”[10]
[10] SuNMaP, Updated Strategy on Providing Evidence for Malaria Control, June 2011.

For Outputs 1, 2 and 6, a clear technical link between the output and purpose/goal indicators does not exist. The rationale for these outputs is the sustainability of gains made by SuNMaP after the end of the project. From this point of view, purpose and goal indicators over the life of the project will not give a good indication of the value of these outputs. One would need to examine them five years, say, after the DFID Programme has ended. However, with over £10 million (20% of the total budget) budgeted for these outputs, it would be helpful to have a clearer view of how exactly they might be expected to contribute to the purpose and goal in the medium and long term.

Assessing the economy, efficiency and effectiveness of SuNMaP

Economy
The unit cost of various categories of TA was fixed in the original contract and there is, therefore, no scope for analysis of these costs in a MTR.

Office rents are “negotiated and paid in advance in order to mitigate against inflationary costs and other potential rent increases” together with “(C)ost sharing arrangements in various offices with NMCP and other stakeholders”.[11] SuNMaP is able to justify the amount of space used by each office.[12]
[11] SuNMaP, Value for Money Self-Assessment Report”, July 2011.
[12] Baker Tilley External Audit, March 2010.

For procurement undertaken by the SuNMaP offices, there are clear procedures defined according to the type and value. These procedures include templates for aspects of the procurement such as Terms of Reference (for short-term TA - STTA) and a useful costing template for the delivery of a training event. The actual expenditure on such events is captured by the programme’s information system in such a way that it is possible to extract the unit costs of a variety of activities. Tables 1, 2 and 3 give examples of unit costs calculated from the information system.

Table 1 provides information on the unit costs of delivering training courses in the six supported states.
Table 1: Unit Costs of Capacity Building Roll-out in Six States, 2010-11
		Costs per participant per day, £
Type of Training	Category of Health Worker	Anambra	Kano	Katsina	Lagos	Niger	Ogun
Training of Trainers - Service Delivery	Trainer	£ 75.38	£ 74.49	£ 58.91	£ 89.10	£121.72	£ 123.58
Cascade Training - Service Delivery	PHC	£ 25.84	£ 24.95	£ 28.15	£ 37.48	£ 28.54	£ 40.45
Cascade Training - Service Delivery	SHC/THC	£ 25.84	£ 24.95	£ 28.15	£ 37.48	£ 28.54	£ 40.45
Cascade Training - Service Delivery	PMV	£ 25.84	£ 24.95	£ 28.15	£ 37.48	£ 28.54	£ 40.45
Cascade Training - Service Delivery	CCG	£ 25.84	£ 24.95	£ 28.15	£ 37.48	£ 28.54	£ 40.45

It is worth noting the following points about the information in Table 1.

1. The costs only include expenditure by SuNMaP. They do not include the costs to the Nigerian economy of the participants. For example, a PMV undergoing training is not working in his shop but the costs shown in Table 1 do not show his loss of sales or the cost of hiring a replacement.
2. There is considerable variation across states with the training of trainers in Ogun being 65% more expensive than that in Kano, while cascade training is 62% more expensive.
3. As one might expect, training of trainers is more expensive than the cascade training but the relative cost varies across states. In most states, training a trainer cost about three times the cost of cascading the training but in Niger it is over four times more expensive while in Lagos it is only just over twice as expensive.

The reasons for these patterns are not clear. A high cost of training in Lagos might be expected but it is not obvious why Ogun and Niger should be so expensive for the training of trainers.

Table 2 shows the cost to DFID of distributing nets by a variety of methods. All of the unit costs shown exclude the costs of the nets themselves and, in some cases, the cost of getting the net to final user. In the case of the campaign distributions, DFID provided the finance to buy the nets but this was outside the SuNMaP envelope. For the routine distribution[13], SuNMaP also procured the nets and the unit costs of this procurement are shown in Table 3 below. For the commercial sector distribution, the nets were paid for by the Nigerian consumer. Table 2 shows considerably higher distribution costs[14] for the commercial sector and, if the only purpose of the work with the commercial sector were to distribute LLINs over the period of the subsidy, it would clearly provide poor value for money as compared with the other methods of distribution. We consider the alternative reasons for the commercial sector activity under Efficiency.
[13] Routine distribution of LLINs was accompanied by the routine distribution of SPs at negligible additional cost. Over a million doses of SPs were3 delivered alongside the LLINs shown in Table 2.
[14] The unit costs for the Commercial Sector were based on sales assumptions and costs provided by SuNMap. In particular, we believe that the assumption that all sales made during the period of the subsidy can be attributed to SuNMaP is unwarranted. If a more realistic attribution were taken the unit cost of distribution would be even higher.

Table 2: Unit costs of LLIN distribution by type of distribution
Type of Distribution	Number of LLINs	Total Cost, £	Unit cost, £
Campaign
Anambra	590,641	£ 290,907.00	£ 0.49
Kano	1,115,377	£ 403,638.00	£ 0.36
Routine
Anambra	175,700	£ 9,124.99	£ 0.05
Kano	124,450	£ 28,956.26	£ 0.23
Katsina	79,736	£ 1,906.59	£ 0.02
Lagos	160,857	£ 34,621.26	£ 0.22
Niger	69,400	£ 20,316.64	£ 0.29
Ogun	116,935	£ 16,944.25	£ 0.14

Commercial	612,769	£ 1,300,000.00	£ 2.12
TOTALS	3,045,865	£ 2,106,415

As with the capacity building roll-out costs, there is some variability in unit costs, particularly for the routine distribution. It is clear that distribution costs will vary according to factors such as the size of the state and the costs of warehousing. However, it is not obvious why Anambra and Katsina should have unit costs of distribution that are so much lower than those of other states. Anambra also had the lowest costs for the capacity building roll-out so it might be worth exploring the reasons for these differences.

Table 3 shows the unit costs of producing the tools for the capacity development analysed in Table 1.

Table 3: Unit costs of capacity building tools
Type	Title	Budget Yr 3	Total Cost Yr 3
		GBP	GBP
Trainer Module	Case Management PHC	£ 14,803	£ 10,780
Trainer Module	Case Management Hospitals	£ 14,803	£ 11,682
Trainer Module	Malaria Diagnosis	£ 14,803	£ 12,400
Trainer Module	Malaria Prevention in Pregnancy	£ 14,803	£ 13,334
Trainer Module	Case Management CCG	£ 14,803	£ 10,090
Trainer Module	Case Management PMV	£ 14,803	£ 12,030
	Total cost		£ 70,315

Given that over 7,000 people have been trained by SuNMaP, a cost of material development of about £10 per person seems quite reasonable. Moreover, these tools have been widely appreciated by partners and we were told of cases where partners have used them for the capacity building funded by themselves. Finally, the fact that the actual cost of developing each module was lower than the budget is a testament to SuNMaP’s careful use of resources.

The contract includes a sum of approximately £10 million for procurement of items by a Procurement Agent. Some of these items – such as cars and office equipment - are to assist the operation of the national and state offices but the majority of the procurement expenditure (almost 95% of the £9.3 million spent up to the end of Year 3) has been for items distributed by SuNMaP – LLINs and SPs. Table 4 show unit costs by date of payment for the three items (LLINs, SP doses and vehicles) for which it was practicable to calculate them.

Table 4: Unit costs of items procured by Crown Agents
Date	Item	Number	Total Cost, £	Unit cost, £
31-Mar-09	LLINs	500,000	£1,833,343.38	£ 3.67
31-Mar-10	LLINs	1,000,000	£3,298,816.12	£ 3.30
24-Feb-11	LLINs	700,000	£2,325,485.61	£ 3.32
30-Mar-11	LLINs	300,000	£ 870,397.07	£ 2.90
TOTALS		2,500,000	£8,328,042.18	£ 3.33
27-Mar-09	SP Doses	850,000	£ 91,064.36	£ 0.11
24-Mar-10	SP Doses	2,000,000	£ 210,937.97	£ 0.11
08-Mar-11	SP Doses	2,310,000	£ 195,581.71	£ 0.08
TOTALS		5,160,000	£ 497,584.04	£ 0.10
03-Sep-08	Prado vehicles	4	£ 101,494.00	£25,373.50
30-Apr-10	Prado vehicles	2	£ 68,603.37	£34,301.69
TOTALS		6	£ 170,097.37	£28,349.56

For LLINs and SP doses, unit costs are remarkably stable until March 2011 when a marked fall is observed, particularly in the case of the SP doses where there is a fall of almost 30%. Surprisingly, there appears to be no marked gain from purchasing in larger quantities.

Efficiency
Although the May 2010 version of the log frame details the total budget against the six outputs, the programme does not report annually or cumulatively against this framework but the programme’s financial system is able to allocate 80% of total expenditure to a specific output. Table 5 shows the expenditure by output to the end of Year 3.

Table 5: Total expenditure by output, April 2008 – March 2011

	Output 1	Output 2	Output 3	Output 4	Output 5	Output 6	Unallocated	Total

Total Expenditure	£2,646,635	£206,218	£ 4,472,679	£ 862,784	£3,551,743	£655,382	£3,169,971	£15,565,411
%	17%	1%	29%	6%	23%	4%	20%	100%

The 20% of expenditure that remains unallocated is for operational costs and consists mainly of the running costs of the Abuja and state SuNMaP offices and 67% of the LTTA. It is reasonable to believe that the outputs could not have been achieved without this unallocated expenditure so it would be helpful for DFID and SuNMaP to discuss how this expenditure might be allocated. It would not, therefore, be possible at this stage to estimate with confidence the overall efficiency of each output although, as we saw above, it is possible to calculate the unit costs of activities contributing to the achievement of some parts of the output. However, we have a considerable issue of attribution since SuNMaP was not the only partner undertaking activities resulting in these outputs. Even if we could attribute DFID’s impact with confidence, the output indicators in the log frame are not very helpful for VfM estimates. We might be able to estimate how much DFID has spent to achieve an additional ten (say) percentage points of LLIN coverage but this figure in itself will not tell us very much. It is much better to (a) review the costs of distributing LLINs by a variety of methods and (b) examine the impact of each method on total coverage. As we have seen, (a) is quite straightforward so long as the programme has a suitable financial system. On the other hand, (b) requires knowledge about the impact on household behaviour in Nigeria of different methods of distribution and could be the subject of future Operational Research.

The commercial sector has been the subject of considerable debate in earlier reviews as well as in this one. As we saw earlier, the costs of distributing LLINs by the intervention in the commercial sector have been much higher than those incurred by the programme in the distribution by other means. However, SuNMaP argues that net distribution was not the sole purpose of the intervention. Additional reasons were to:
- develop the CSPs so that there was commercial availability of LLINs when the free nets were due for replacement; and
- encourage competition in the market.

Commercial availability of LLINs
Table 5 shows the retail sales of LLINs by the CSPs before, during and after the price support by SuNMaP.

Table 5: Retail sales of LLINs by CSPs, October 2007 – June 2011

			Subsidy
Commercial Sector Partners	Oct 07-	Jul 08-	Jul-Sep	Oct-Dec	Jan-Mar	Apr-Jun	Jul-Sep	Oct-Dec	Apr-Jun
	Jun-08	Jun-09	2009	2009	2010	2010	2010	2010	2011
Harvestfield	0	0	47,615	15,461	17,843	6,577	22,763	16,581	964
Rosies Textile	0	0	178,972	41,779	43,832	62,630	131,523	20,516	33,041
Teta Pharmaceuticals	0	0	0	2,698	25,900	9,472	5,704	1,362	7,128

TOTAL	0	0	226,587	59,938	87,575	78,679	159,990	38,459	41,133

Table 5 is encouraging in terms of commercial availability. It shows no retail sales before SuNMaP support, a large increase during the period of price support and continuing sales at about half the amount as during support. Moreover, the commercial sector indicator of the availability of nets[15] (proportion of shops selling any nets that have at least one LLIN brand on sale) was almost achieved by April
[15] 80% by end of 2011
2010[16].
[16] Retail Outlet Survey, 2010

However, some caution is needed in this interpretation.

1. Table 5 is based on reports of retail sales by the three CSPs. It is not certain that there were no retail sales of LLINs before July 2009. Unfortunately, we do not have a baseline Retail Outlet Survey that would allow us to estimate the extent of retail sales. On the other hand, the Retail Outlet Survey of 2010 identified sales of a brand that was not supported by SuNMaP and this brand was found in more outlets than were two out of the three supported brands. From this evidence, we cannot say that there were no retail sales before SuNMaP support.
2. The relatively buoyant sales of the CSPs after the price support ended raises a question about the need for the substantial expenditure on the subsidy. Marketing support and seed stock financing may have been sufficient.
3. This point is reinforced by the information that two manufacturing establishments for LLINs are currently under construction and will soon be in operation in spite of the cessation of the subsidy.
4. The fact that the milestone for November 2011 was effectively achieved sixteen months earlier may be interpreted either as a stupendous success for the commercial sector strategy or as an indicator that the sector did not need quite so much help to get its product into retail outlets. Given that there appear to be no serious barriers to the development of a commercial market in LLINs, it seems that the latter interpretation is more likely.

Encourage competition
By working with only three CSPs, SuNMaP risked encouraging an oligopoly in the Nigerian LLIN market. Fortunately, as shown by the Retail Outlets Survey, there was at least one other brand in the market in April 2010, although this diversity appears to be in spite of rather than because of SuNMaP.

The overall conclusion must be that the evidence does not clearly support the efficiency of the commercial sector approach. In particular, one has to question the need for the subsidy even in the context of the free net distribution. If intervention in the market (by marketing support and seed stock funding, for example) were required, the programme could have continued more efficiently more by delaying implementation and gathering more appropriate baseline market information to guide the intervention.

Effectiveness
In terms of VfM, changes in the purpose indicators could be used to estimate the number of DALYs (Disability Adjusted Life Years) generated by SuNMaP, thus providing a consistent metric for cost-effectiveness estimates.

PSI[17] estimates that 520 DALYs will be averted[18] for every 470 children aged under 5 sleeping under a LLIN and that 68 DALYs will be averted for every 1,000 doses of ACT prescribed presumptively for children under 5 with fever[19]. They do not provide estimates for IPT[20]. The SuNMaP self-assessment only provides estimates for a change in the indicator “Percentage of all children Under 5 in supported states that slept under an ITN the night before the interview” and Table 6 shows the implications for DALYs averted for these changes.
[17] http://www.psi.org/resources/publications?pub_type=All&field_target_audience_value_many_to_one=All&health_area=All&country=All&field_year_value=&keywords=DALY&language=English
[18] Assuming that a LLIN lasts for 5 years
[19] The estimates for LLINs are for Kenya. A full analysis would require the use of parameters specific to Nigeria.
[20] Hutton et al provide estimates of DALYs averted by the use of IPT for Tanzania (118.9 per 1,000 doses of IPT) and Mozambique (47.6 per 1,00 doses of IPT). The PSI methodology takes a somewhat wider definition of a DALY by including disability as well as death in the estimates.

Table 6: Estimated DALYs averted by LLIN provision and promotion in four supported states
State	Indicator	Change in indicator, 2009-2010 (Percentage points)	Total number of children U5, (2006 census)	Number of children U5 benefiting	DALY averted per child	Total DALYs averted

Kano	Percentage of all children Under 5 in supported states that slept under a ITN the night before the interview	18.6	1,818,598	338,259	1.106383	374,244
Anambra	Percentage of all children Under 5 in supported states that slept under a ITN the night before the interview	13.4	473248	63,415	1.106383	70,162
Niger	Percentage of all children Under 5 in supported states that slept under a ITN the night before the interview	31.3	786,009	246,021	1.106383	272,193
Ogun	Percentage of all children Under 5 in supported states that slept under a ITN the night before the interview	10.2	527,897	53,845	1.106383	59,574
	Total DALYs averted					776,173

If similar results were to be achieved for the other two indicators in all six supported states, the total number of DALYs averted could be considerable. However, a number of other partners have been involved in the achievement of these results and we do not at present have the information necessary to estimate the individual contribution of SuNMaP.

Without being able to attribute results to the programme and in the absence of information on the other two indicators, we cannot provide any estimate of the cost per DALY averted at this stage in the programme.

Externalities
There is evidence of externalities (that is, effects on individuals/ organisations other than the principal target) being generated by the programme. All of the externalities identified are positive. The main examples are:
- use of the capacity building tools by other partners;
- application of capacity building tools to other areas of health systems management by state health departments;
- reported increased attendance at public ANC as a result of the provision of SPs;
- development of a tool (Netcalc) to estimate the required number of LLINs under a variety of scenarios that has been made available to other countries.

The average cost of developing the capacity building modules so far is £11,719. This cost could be used as an estimate of the savings achieved as a result of the use of these tools by other partners or in other areas of the health system. If we had information on the extent of this use, we could obtain an indication of the value of the externalities as a result of this wider use.[21] To estimate the value of this externality, we would require consistent information on the extent to which these modules are used outside of SuNMaP activities. This usage is not monitored.
[21] Such an estimate would only provide an indication of the value of the externality because it does not tell us what would be the value of the impact of this additional use. It could be greater – or, indeed, less – than the devleopment cost.

The value of a woman attending ANC would require further research as would the obtaining of robust information on the increased attendance arising out of SuNMaP’s activities.

Impact on VfM of differing scenarios
We see no reason why economy should change for inputs or activities. SuNMaP has good procedures and the management team are diligent about using them. The costing and procurement templates provide transparency and consistency an costing.

For efficiency and effectiveness, we have insufficient information to build alternative scenarios and to analyse their impact.

Issues in VfM in SuNMaP
Attribution
The major issue is that of attribution of the output and purpose indicators. The task of attribution is particularly difficult in the case of SuNMaP because much of the activity under Outputs 1 and 2 is related to working closely with NMCP, SMCPs and other donors in order to make the total expenditure more effective. However, even ignoring this issue, we do not have information on the expenditure by other partners[22] that would be necessary to start the process of apportioning responsibility for results.
[22] Although we do know that DFID funded two million LLINs for campaign distribution at a cost of £6,600,000 outside the SuNMaP envelope.

An alternative approach to attribution would be to model the counterfactual; that it, to predict what would have been the outputs/outcomes if SuNMaP’s expenditures had not been made. Such an approach could be attractive in the context of some health sector projects where the technical relationships are well-researched, where, for example, there is a clear relationship between the number of under-fives sleeping under and ITN and the number of DALYs averted. However, where programme activities are also focused on changing behaviour – encouraging families to us the free nets – the technical relationship between programme activities and outputs/outcomes are less clear-cut and the development of the counter-factual is considerably more difficult. This is not to say that it would not be worthwhile to do so but such research is far beyond the capacity of a mid-term review.
Uncertainty about effect size
All of the output and purpose indicators available for use in VfM analysis are obtained by survey data. All of the data on indicators given as examples in this report use the point estimates as provided in the SuNMaP self-assessment. However, reporting of such measures on a regular basis should report a range within which the VfM indicator might be expected to fall.

Lack of suitable baselines
Most of the important indicators have suitable baselines which allow for estimates of the change over the period of the programme. Unfortunately, the area in which VfM might be most contentious – commercial sector development – does not appear to have rigorous baselines to allow for the analysis of progress.

Value for WHOSE money?
Because of a lack of information about the financial contribution of other partners, all of the cost estimates presented in this report are based on DFID programme costs. However, financial contributions from the Nigerian public sector (national, state and local), the Nigerian private sector (retail buyers of nets, PMVs taking time off work to be trained) and other donors have been essential in delivering many of these activities. It may be argued that the analysis should include all expenditure and this approach would, at least, have the virtue that it would not be necessary to attribute the results. On the other hand, one might argue that focusing on programme costs is the correct approach because we need to consider the VfM for the UK tax payer. DFID have identified the former inclusive approach as the one to follow but this analysis requires very much more information than we currently have for SuNMaP. However, even if we focused only on programme expenditures, we would still need information on other expenditures in order to address issues of attribution.

Conclusions and Recommendations
Conclusions
SuNMaP is a well-managed programme in which VfM issues are taken seriously in that a number of measures are taken to reduce operational costs. In addition, financial information is recorded in such a way that the construction of unit costs of inputs and activities is feasible. However, although individual programme managers review their own unit costs, there does not appear to be the routine generation and analysis of unit costs.

DFID’s recent outline of its approach to VfM implies that output indicators should all be factors that are controlled directly by the programme. However, the achievement of a number of the output indicators in the revised log frame require inputs by partners so that attribution continues to be an issue.

Cost-effectiveness could in principle be estimated for SuNMaP by converting all achievements to the common metric of a DALY. In practice, we cannot provide such estimates at this stage for three reasons:
1. We do not have the total expenditure by all partners that would allow us to estimate either the cost-effectiveness of all activities or attribute a portion of the results to the DFID funding.
2. We do not have current estimates of two of the indicators.
3. PSI has not developed an estimate of DALYs averted in the case of IPT.

None of this should be seen as a criticism of SuNMaP. The programme has responded actively to DFID’s reporting requirements. However, going forward there are a number of actions that could be taken to facilitate VfM analysis.

Recommendations
Monitor unit costs
SuNMaP should use their excellent information system to calculate unit costs and monitor them on a regular basis to ensure that deviations from a “normal” level are explained. For some items, it may be appropriate to compare these costs with international experience or with other programmes in Nigeria. In addition to the examples in this report, SuNMaP could consider monitoring the unit costs of:
- developing a state operational plan;
- distribution of SPs;
- operational research study.
There is little point in monitoring unit costs simply for report. SuNMaP and DFID should consider which unit costs would provide useful management information.

Disseminate information about unit costs to partners
A major reason for monitoring unit costs is to disseminate them to partners. This dissemination can fulfil two purposes.
1. Partners can have a benchmark for their own budgetary exercises. Such benchmarking can be helpful for SMCPs in their annual planning. I can also be helpful to donors – particularly when a SMCP has requested them to undertake capacity building using SuNMaP tools.
2. Partners could be encouraged to share their own costings, thus helping SuNMaP to assess its own performance.

Review PSI methodology for DALYs in Nigeria
In the example set out in this report, we have used PSI estimates for the DALYs averted as a result of LLIN use by the under fives. DFID should work with SuNMaP review this methodology to assess whether it is suitable for their VfM analysis on this and other health projects. If it is, further research would be required to estimate the DALYs averted for the purpose indicator relating to IPT.

Estimate DALYs
DFID should ensure that, when such estimates are available, SuNMaP should report progress against Purpose in DALYs averted as well as by the change in each indicator. This reporting should make clear the range within which these estimates are expected to lie.

Get information on partners’ expenditure
It is important that there is information about the total expenditures on malaria control. While we recognise that this is no easy matter, neither attribution of the results to DFID funding nor estimation of overall cost effectiveness can be undertaken without it.

Disclaimer

The DFID Human Development Resource Centre (HDRC) provides technical assistance and information to the British Government’s Department for International Development (DFID) and its partners in support of pro-poor programmes in education and health including nutrition and AIDS. The HDRC services are provided by three organisations: HLSP, Cambridge Education (both part of Mott MacDonald Group) and the Institute of Development Studies.

This document is issued for the party which commissioned it and for specific purposes connected with the captioned project only. It should not be relied upon by any other party or used for any other purpose.
We accept no responsibility for the consequences of this document being relied upon by any other party, or being used for any other purpose, or containing any error or omission which is due to an error or omission in data supplied to us by other parties.